## Nesma____PR_to_PO_Status_Repor_
Project No | Project Name | Pr Num | Description | PR Status | PR Closed | PR Submission Date | Pending With | Pending Since | PR Approved Date | PR Return Date | PR Reject Date | PR Note | PR Value | Po Num | Revision Num | PO Type | Vendor Name | Currency Code | PO Value | PO Status | PO submittal date | SCM approval date | PO Approved Date | Saving Amount | PR to PO in days | Agent | PR approval to SCM approval | PR approval to PO approval
105-1 | Streetlight Makkah, Phase 2 | 41 | Streetlight Makkah, Phase 2-MCB | REJECTED | No | 2021-08-11 | Chughtai, Sameer | 2021-09-16 | 2021-09-16 | 2021-09-13 | 2021-09-20 | The lowest price is 7.3 SAR, please modify price in PR | 328500 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44455 | -44455
105-1 | Streetlight Makkah, Phase 2 | 71 | Streetlight Makkah, Phase 2-LED-Makkah | APPROVED | No | 2021-08-31 | Abas, Mohammed Fekry | 2021-09-01 | 2021-09-01 |  |  |  | 18566519.04 | 3794 | 0 | STANDARD | SCHREDER GULF LIGHTTING LLC. | USD | 18566519.04 | APPROVED |  |  | 2021-09-21 | 0 | 20 | Babic, Marian | -44440 | 20
105-1 | Streetlight Makkah, Phase 2 | 92 | Streetlight Makkah, Phase 2-installation | APPROVED | No | 2021-09-14 | Abas, Mohammed Fekry | 2021-09-14 | 2021-09-15 |  |  |  | 3581430 | 3801 | 0 | STANDARD | MAHAR ALFANN FOR CONTRACTING | SAR | 3581430 | APPROVED |  |  | 2021-10-07 | 0 | 22 | Babic, Marian | -44454 | 22
105-1 | Streetlight Makkah, Phase 2 | 114 | Streetlight Makkah, Phase 2-MCB Makkah | APPROVED | No | 2021-10-04 | Abas, Mohammed Fekry | 2021-10-05 | 2021-10-05 |  |  |  | 375000 | 3820 | 0 | STANDARD | Saudi Panels and Breakers Manufacturing Co. | SAR | 365000 | APPROVED |  |  | 2021-10-18 | 10000 | 13 | Babic, Marian | -44474 | 13
105-1 | Streetlight Makkah, Phase 2 | 187 | Streetlight Makkah, Phase 2-Schreder | APPROVED | No | 2021-11-11 | Abas, Mohammed Fekry | 2021-11-16 | 2021-11-17 |  |  |  | 9968201.01 | 3794 | 1 | STANDARD | SCHREDER GULF LIGHTTING LLC. | USD | 9968201.01 | APPROVED |  |  | 2021-12-27 | 0 | 40 | Babic, Marian | -44517 | 40
105-1 | Streetlight Makkah, Phase 2 | 561 | Streetlight Makkah, Phase 2-survey | RETURNED | No | 2022-03-14 | Babic, Marian | 2022-06-01 | 2022-03-16 | 2022-06-01 |  | No feedback | 13800 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44636 | -44636
105-1 | Streetlight Makkah, Phase 2 | 591 | Streetlight Makkah, Phase 2-installation | APPROVED | No | 2022-04-06 | Abas, Mohammed Fekry | 2022-04-12 | 2022-04-13 |  |  |  | 310000 | 3801 | 1 | STANDARD | MAHAR ALFANN FOR CONTRACTING | SAR | 310000 | APPROVED |  |  | 2022-04-26 | 0 | 13 | Babic, Marian | -44664 | 13
105-2 | Streetlights Jeddah, Phase 4 | 69 | Streetlights Jeddah, Phase 4-LED | APPROVED | No | 2021-08-30 | Abas, Mohammed Fekry | 2021-08-31 | 2021-08-31 |  |  |  | 26477281.4 | 3785 | 0 | STANDARD | SCHREDER GULF LIGHTTING LLC. | USD | 26477281.4 | APPROVED |  |  | 2021-09-14 | 0 | 14 | Babic, Marian | -44439 | 14
105-2 | Streetlights Jeddah, Phase 4 | 69 | Streetlights Jeddah, Phase 4-LED | APPROVED | No | 2021-08-30 | Abas, Mohammed Fekry | 2021-08-31 | 2021-08-31 |  |  |  | 26477281.4 | 3785 | 1 | STANDARD | SCHREDER GULF LIGHTTING LLC. | USD | 26477281.4 | REJECTED |  |  |  | 0 |  | Babic, Marian | -44439 | -44439
105-2 | Streetlights Jeddah, Phase 4 | 93 | Streetlights Jeddah, Phase 4-Survey and installation | APPROVED | No | 2021-09-14 | Abas, Mohammed Fekry | 2021-09-14 | 2021-09-15 |  |  |  | 2480000 | 3802 | 0 | STANDARD | EXPERIENCE&EXCELLENCE FOR CONTRACTING | SAR | 2480000 | APPROVED |  |  | 2021-10-07 | 0 | 22 | Babic, Marian | -44454 | 22
105-2 | Streetlights Jeddah, Phase 4 | 93 | Streetlights Jeddah, Phase 4-Survey and installation | APPROVED | No | 2021-09-14 | Abas, Mohammed Fekry | 2021-09-14 | 2021-09-15 |  |  |  | 2480000 | 3802 | 1 | STANDARD | EXPERIENCE&EXCELLENCE FOR CONTRACTING | SAR | 1060200 | APPROVED |  |  | 2022-03-09 | 1419800 | 175 | Babic, Marian | -44454 | 175
105-2 | Streetlights Jeddah, Phase 4 | 93 | Streetlights Jeddah, Phase 4-Survey and installation | APPROVED | No | 2021-09-14 | Abas, Mohammed Fekry | 2021-09-14 | 2021-09-15 |  |  |  | 183000 | 3825 | 0 | STANDARD | EXPERIENCE&EXCELLENCE FOR CONTRACTING | SAR | 150000 | APPROVED |  |  | 2022-03-31 | 33000 | 197 | Babic, Marian | -44454 | 197
105-2 | Streetlights Jeddah, Phase 4 | 101 | Streetlights Jeddah, Phase 4-Materials | APPROVED | No | 2021-09-16 | Abas, Mohammed Fekry | 2021-09-22 | 2021-09-26 |  |  |  | 53000 | 3807 | 0 | STANDARD | Br.Salem IbrahimSalem Saeed Trading Est | SAR | 53000 | APPROVED |  |  | 2021-10-05 | 0 | 9 | Alamri, Nedhal | -44465 | 9
105-2 | Streetlights Jeddah, Phase 4 | 101 | Streetlights Jeddah, Phase 4-Materials | APPROVED | No | 2021-09-16 | Abas, Mohammed Fekry | 2021-09-22 | 2021-09-26 |  |  |  | 30000 | 3808 | 0 | STANDARD | Khubara Al-Emaar Trading Est. | SAR | 30000 | APPROVED |  |  | 2021-10-07 | 0 | 11 | Alamri, Nedhal | -44465 | 11
105-2 | Streetlights Jeddah, Phase 4 | 150 | Streetlights Jeddah, Phase 4-subcontractor | APPROVED | No | 2021-10-17 | Abas, Mohammed Fekry | 2021-10-18 | 2021-10-18 |  |  |  | 2294000 | 3839 | 0 | STANDARD | MAHAR ALFANN FOR CONTRACTING | SAR | 2294000 | APPROVED |  |  | 2021-11-01 | 0 | 14 | Babic, Marian | -44487 | 14
105-2 | Streetlights Jeddah, Phase 4 | 150 | Streetlights Jeddah, Phase 4-subcontractor | APPROVED | No | 2021-10-17 | Abas, Mohammed Fekry | 2021-10-18 | 2021-10-18 |  |  |  | 2294000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44487 | -44487
105-2 | Streetlights Jeddah, Phase 4 | 175 | Streetlights Jeddah, Phase 4-MCB | APPROVED | No | 2021-10-31 | Abas, Mohammed Fekry | 2021-11-01 | 2021-11-01 |  |  |  | 568000 | 3853 | 0 | STANDARD | AL-MARSHAD GROUP CO.FOR TRADING | SAR | 568000 | APPROVED |  |  | 2021-11-07 | 0 | 6 | Babic, Marian | -44501 | 6
105-2 | Streetlights Jeddah, Phase 4 | 189 | Streetlights Jeddah, Phase 4-schreder LED | APPROVED | No | 2021-11-15 | Abas, Mohammed Fekry | 2021-11-16 | 2021-11-17 |  |  |  | 3774959.8 | 3785 | 1 | STANDARD | SCHREDER GULF LIGHTTING LLC. | USD | 3774959.8 | REJECTED |  |  |  | 0 |  | Babic, Marian | -44517 | -44517
105-2 | Streetlights Jeddah, Phase 4 | 189 | Streetlights Jeddah, Phase 4-schreder LED | APPROVED | No | 2021-11-15 | Abas, Mohammed Fekry | 2021-11-16 | 2021-11-17 |  |  |  | 3774959.8 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44517 | -44517
105-2 | Streetlights Jeddah, Phase 4 | 313 | Streetlights Jeddah, Phase 4-Arm for 6M | INCOMPLETE | No |  | BABEKAR, MOHAMMED HUSSAIN | 2021-12-13 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-2 | Streetlights Jeddah, Phase 4 | 314 | Streetlights Jeddah, Phase 4-Arm for 6M pole | RETURNED | No | 2021-12-13 | Babic, Marian | 2021-12-20 | 2021-12-14 | 2021-12-20 |  | As discussed | 24900 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44544 | -44544
105-2 | Streetlights Jeddah, Phase 4 | 317 | Streetlights Jeddah, Phase 4-Materials | INCOMPLETE | No |  | Althubaiti, Ahmed | 2021-12-14 |  |  |  | As discussed | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-2 | Streetlights Jeddah, Phase 4 | 339 | Streetlights Jeddah, Phase 4-Arms- Bahra | REJECTED | No | 2021-12-21 | Alameer, Waleed | 2021-12-22 | 2021-12-22 |  | 2021-12-22 |  | 383195.5 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -44552 | -44552
105-2 | Streetlights Jeddah, Phase 4 | 340 | Streetlights Jeddah, Phase 4-Arms revised-Bahra | APPROVED | No | 2021-12-21 | Abas, Mohammed Fekry | 2021-12-27 | 2021-12-27 |  |  |  | 403945.5 | 3806 | 1 | STANDARD | Bahra for Manufacturing of Electrical Devices | SAR | 403945.5 | APPROVED |  |  | 2021-12-30 | 0 | 3 | Babic, Marian | -44557 | 3
105-2 | Streetlights Jeddah, Phase 4 | 340 | Streetlights Jeddah, Phase 4-Arms revised-Bahra | APPROVED | No | 2021-12-21 | Abas, Mohammed Fekry | 2021-12-27 | 2021-12-27 |  |  |  | 403945.5 | 3806 | 2 | STANDARD | Bahra for Manufacturing of Electrical Devices | SAR | 307509.3 | APPROVED |  |  | 2022-02-21 | 96436.2 | 56 | Babic, Marian | -44557 | 56
105-2 | Streetlights Jeddah, Phase 4 | 371 | Streetlights Jeddah, Phase 4-Final Revision of Arms PO# 3806-ES191-1 | RETURNED | No | 2022-01-10 | Babic, Marian | 2024-03-26 | 2022-01-16 | 2024-03-26 |  | PO for this subject already issued, this PR is a balance which is not needed | 100800 | 3806 | 2 | STANDARD | Bahra for Manufacturing of Electrical Devices | SAR | 100800 | APPROVED |  |  | 2022-02-21 | 0 |  | Babic, Marian | -44577 | 36
105-2 | Streetlights Jeddah, Phase 4 | 371 | Streetlights Jeddah, Phase 4-Final Revision of Arms PO# 3806-ES191-1 | RETURNED | No | 2022-01-10 | Babic, Marian | 2024-03-26 | 2022-01-16 | 2024-03-26 |  | PO for this subject already issued, this PR is a balance which is not needed | 100800 | 3806 | 3 | STANDARD | Bahra for Manufacturing of Electrical Devices | SAR | 97944 | APPROVED |  |  | 2022-09-12 | 2856 |  | Babic, Marian | -44577 | 239
105-2 | Streetlights Jeddah, Phase 4 | 371 | Streetlights Jeddah, Phase 4-Final Revision of Arms PO# 3806-ES191-1 | RETURNED | No | 2022-01-10 | Babic, Marian | 2024-03-26 | 2022-01-16 | 2024-03-26 |  | PO for this subject already issued, this PR is a balance which is not needed | 293649.3 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44577 | -44577
105-2 | Streetlights Jeddah, Phase 4 | 535 | Streetlights Jeddah, Phase 4-installation | APPROVED | No | 2022-03-08 | Abas, Mohammed Fekry | 2022-03-14 | 2022-03-14 |  |  |  | 806000 | 3839 | 1 | STANDARD | MAHAR ALFANN FOR CONTRACTING | SAR | 806000 | APPROVED |  |  | 2022-03-27 | 0 | 13 | Babic, Marian | -44634 | 13
105-2 | Streetlights Jeddah, Phase 4 | 560 | Streetlights Jeddah, Phase 4-Survey | APPROVED | No | 2022-03-14 | Abas, Mohammed Fekry | 2022-03-15 | 2022-03-16 |  |  |  | 19800 | 3825 | 0 | STANDARD | EXPERIENCE&EXCELLENCE FOR CONTRACTING | SAR | 19800 | APPROVED |  |  | 2022-03-31 | 0 | 15 | Babic, Marian | -44636 | 15
105-2 | Streetlights Jeddah, Phase 4 | 573 | Streetlights Jeddah, Phase 4-ammendment (Schreder) | APPROVED | No | 2022-03-21 | Abas, Mohammed Fekry | 2022-03-22 | 2022-03-23 |  |  |  | 3798861.5 | 3785 | 1 | STANDARD | SCHREDER GULF LIGHTTING LLC. | USD | 3798861.46 | REJECTED |  |  |  | 0.04 |  | Babic, Marian | -44643 | -44643
105-2 | Streetlights Jeddah, Phase 4 | 573 | Streetlights Jeddah, Phase 4-ammendment (Schreder) | APPROVED | No | 2022-03-21 | Abas, Mohammed Fekry | 2022-03-22 | 2022-03-23 |  |  |  | 3798861.5 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44643 | -44643
105-2 | Streetlights Jeddah, Phase 4 | 766 | Streetlights Jeddah, Phase 4-Final Amendment of arms PO#3806 | RETURNED | No | 2022-08-22 | Babic, Marian | 2024-04-15 | 2022-09-01 | 2024-04-15 |  | not required | 123670 | 3806 | 3 | STANDARD | Bahra for Manufacturing of Electrical Devices | SAR | 8881 | APPROVED |  |  | 2022-09-12 | 114789 |  | Babic, Marian | -44805 | 11
105-2 | Streetlights Jeddah, Phase 4 | 766 | Streetlights Jeddah, Phase 4-Final Amendment of arms PO#3806 | RETURNED | No | 2022-08-22 | Babic, Marian | 2024-04-15 | 2022-09-01 | 2024-04-15 |  | not required | 290664.3 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44805 | -44805
105-3 | Flyadeal A320 NEO Launching | 32 |  | APPROVED | No | 2021-08-08 | Abas, Mohammed Fekry | 2021-08-08 | 2021-08-08 |  |  |  | 198200 | 3758 | 0 | STANDARD | Smart link Est | SAR | 198200 | APPROVED |  |  | 2021-08-09 | 0 | 1 | Abuhammad, Samir | -44416 | 1
105-3 | Flyadeal A320 NEO Launching | 506 | Flyadeal A320 NEO Launching-Payment against Realfiction Content Development | APPROVED | No | 2022-02-24 | Abas, Mohammed Fekry | 2022-02-24 | 2022-02-27 |  |  |  | 5154.89 | 4043 | 0 | STANDARD | Gluk Media | EUR | 5148.25 | APPROVED |  |  | 2022-03-23 | 6.64 | 24 | Babic, Marian | -44619 | 24
105-4 | Iman General Hospital in Riyad | 72 | Iman General Hospital in Riyad-CEWE Elite meters and accesories | APPROVED | No | 2021-09-01 | Abas, Mohammed Fekry | 2021-09-01 | 2021-09-02 |  |  |  | 20531 | 3786 | 0 | STANDARD | Washa Al Wisam Factory Company | SAR | 20531 | APPROVED |  |  | 2021-09-16 | 0 | 14 | Abuhammad, Samir | -44441 | 14
105-4 | Iman General Hospital in Riyad | 82 | Iman General Hospital in Riyad-Quotation for Installation of Energy Meter | REJECTED | No | 2021-09-07 | Chughtai, Sameer | 2021-09-07 | 2021-09-07 |  | 2021-09-07 |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -44446 | -44446
105-4 | Iman General Hospital in Riyad | 83 | Iman General Hospital in Riyad-Quotation for Installation of Energy Meter | APPROVED | No | 2021-09-08 | Abas, Mohammed Fekry | 2021-09-09 | 2021-09-09 |  |  |  | 49715 | 3793 | 0 | STANDARD | Smart Controls Systems Contracting Est. | SAR | 49715 | APPROVED |  |  | 2021-10-07 | 0 | 28 | Babic, Marian | -44448 | 28
105-4 | Iman General Hospital in Riyad | 353 | Iman General Hospital in Riyad-LG PACKAGE INVERTER 25/20 ton | APPROVED | No | 2021-12-28 | Abas, Mohammed Fekry | 2022-01-02 | 2022-01-03 |  |  |  | 289952 | 3939 | 0 | STANDARD | AL HASSAN GHAZI IBRAHIM SHAKER COMPANY | SAR | 289952 | APPROVED |  |  | 2022-01-20 | 0 | 17 | Babic, Marian | -44564 | 17
105-4 | Iman General Hospital in Riyad | 354 | Iman General Hospital in Riyad-supply and install LED lights in IGH | APPROVED | No | 2021-12-28 | Abas, Mohammed Fekry | 2022-01-02 | 2022-01-03 |  |  |  | 843333.03 | 3944 | 0 | STANDARD | Index Lights | SAR | 837067.47 | APPROVED |  |  | 2022-01-26 | 6265.56 | 23 | Babic, Marian | -44564 | 23
105-4 | Iman General Hospital in Riyad | 355 | Iman General Hospital in Riyad-Chiiler replacement IGH | APPROVED | No | 2021-12-28 | Abas, Mohammed Fekry | 2022-01-02 | 2022-01-03 |  |  |  | 958000 | 3937 | 0 | STANDARD | DAIKIN AIR CONDITIONING SAUDI ARABIA | SAR | 958000 | APPROVED |  |  | 2022-02-01 | 0 | 29 | Abuhammad, Samir | -44564 | 29
105-4 | Iman General Hospital in Riyad | 358 | Iman General Hospital in Riyad-Carrier Scope in IGH | APPROVED | No | 2021-12-30 | Abas, Mohammed Fekry | 2022-01-02 | 2022-01-03 |  |  |  | 1080975 | 3945 | 0 | STANDARD | ARABIAN AIR CONDITIONING COMPANY LTD | SAR | 1080975 | APPROVED |  |  | 2022-01-26 | 0 | 23 | Babic, Marian | -44564 | 23
105-4 | Iman General Hospital in Riyad | 359 | Iman General Hospital in Riyad-S.E.S.S | APPROVED | No | 2021-12-30 | Abas, Mohammed Fekry | 2022-01-02 | 2022-01-03 |  |  |  | 1250000 | 3970 | 0 | STANDARD | Specialized Establishment for System Supplies | SAR | 1250000 | APPROVED |  |  | 2022-02-17 | 0 | 45 | Babic, Marian | -44564 | 45
105-4 | Iman General Hospital in Riyad | 369 | Iman General Hospital in Riyad-Lighting control Supply and installation IGH | APPROVED | No | 2022-01-09 | Abas, Mohammed Fekry | 2022-01-10 | 2022-01-13 |  |  |  | 237639 | 3946 | 0 | STANDARD | Index Lights | SAR | 232732 | APPROVED |  |  | 2022-01-26 | 4907 | 13 | Babic, Marian | -44574 | 13
105-4 | Iman General Hospital in Riyad | 379 | Iman General Hospital in Riyad-PACU Units installation at IGH | APPROVED | No | 2022-01-16 | Abas, Mohammed Fekry | 2022-01-19 | 2022-01-20 |  |  |  | 152000 | 3958 | 0 | STANDARD | EXPERIENCE&EXCELLENCE FOR CONTRACTING | SAR | 152000 | APPROVED |  |  | 2022-02-01 | 0 | 12 | Babic, Marian | -44581 | 12
105-4 | Iman General Hospital in Riyad | 432 | Iman General Hospital in Riyad-AC split units IGH | APPROVED | No | 2022-01-26 | Abas, Mohammed Fekry | 2022-01-30 | 2022-01-30 |  |  |  | 95400 | 3985 | 0 | STANDARD | ARABIAN AIR CONDITIONING COMPANY LTD | SAR | 95400 | APPROVED |  |  | 2022-02-28 | 0 | 29 | Abuhammad, Samir | -44591 | 29
105-4 | Iman General Hospital in Riyad | 454 | Iman General Hospital in Riyad-outdoor lights for IGH ( color 4000K) | APPROVED | No | 2022-02-01 | Abas, Mohammed Fekry | 2022-02-06 | 2022-02-07 |  |  |  | 54255.66 | 3998 | 0 | STANDARD | Index Lights | SAR | 53808.66 | APPROVED |  |  | 2022-03-31 | 447 | 52 | Abuhammad, Samir | -44599 | 52
105-4 | Iman General Hospital in Riyad | 455 | Iman General Hospital in Riyad-AC split installation | APPROVED | No | 2022-02-01 | Abas, Mohammed Fekry | 2022-02-10 | 2022-02-13 |  |  |  | 31500 | 4014 | 0 | STANDARD | EXPERIENCE&EXCELLENCE FOR CONTRACTING | SAR | 31500 | APPROVED |  |  | 2022-03-08 | 0 | 23 | Abuhammad, Samir | -44605 | 23
105-4 | Iman General Hospital in Riyad | 642 | Iman General Hospital in Riyad-Gateway for LG package | APPROVED | No | 2022-05-19 | Abas, Mohammed Fekry | 2022-05-24 | 2022-05-24 |  |  |  | 8300 | 4118 | 0 | STANDARD | AL HASSAN GHAZI IBRAHIM SHAKER COMPANY | SAR | 8300 | APPROVED |  |  | 2022-06-20 | 0 | 27 | Abuhammad, Samir | -44705 | 27
105-4 | Iman General Hospital in Riyad | 1531 | Iman General Hospital in Riyad-IGH - Chiller PM | APPROVED | No | 2023-09-28 | Abas, Mohammed Fekry | 2023-09-28 | 2023-09-29 |  |  |  | 15000 | 4641 | 0 | STANDARD | DAIKIN AIR CONDITIONING SAUDI ARABIA | SAR | 15000 | APPROVED |  |  | 2023-10-26 | 0 | 27 | Abuhammad, Samir | -45198 | 27
105-4 | Iman General Hospital in Riyad | 2881 | Iman General Hospital in Riyad-Streetlights | REJECTED | No | 2024-03-27 | Issa, Amr Ali | 2024-03-31 | 2024-03-27 |  | 2024-03-31 |  | 15208.65 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45378 | -45378
105-4 | Iman General Hospital in Riyad | 2955 | Iman General Hospital in Riyad-Streetlights | APPROVED | No | 2024-03-31 | Abas, Mohammed Fekry | 2024-04-07 | 2024-04-07 |  |  |  | 15208.65 | 5434 | 0 | STANDARD | SAUDI LIGHTING CO LTD | SAR | 15208.52 | APPROVED |  |  | 2024-05-14 | 0.13 | 37 | Abuhammad, Samir | -45389 | 37
105-4 | Iman General Hospital in Riyad | 3288 | Iman General Hospital in Riyad-IGH - Chiller Test | APPROVED | No | 2024-05-05 | Abas, Mohammed Fekry | 2024-05-09 | 2024-05-12 |  |  |  | 14400 | 5533 | 0 | STANDARD | DAIKIN AIR CONDITIONING SAUDI ARABIA | SAR | 14400 | APPROVED |  |  | 2024-06-03 | 0 | 22 | Abuhammad, Samir | -45424 | 22
105-4 | Iman General Hospital in Riyad | 4474 | Iman General Hospital in Riyad-IGH - AHU Actuator | APPROVED | No | 2024-09-18 | Abas, Mohammed Fekry | 2024-09-24 | 2024-09-24 |  |  |  | 12500 | 6227 | 0 | STANDARD | ARABIAN AIR CONDITIONING COMPANY LTD | SAR | 12500 | APPROVED |  |  | 2024-09-29 | 0 | 5 | Abuhammad, Samir | -45559 | 5
105-4 | Iman General Hospital in Riyad | 6187 | Iman General Hospital in Riyad-IGH - PR for Renewal O&M Contract related to Daikin PO 4641 | APPROVED | No | 2025-03-16 | Abas, Mohammed Fekry | 2025-03-18 | 2025-03-20 |  |  |  | 15000 | 4641 | 1 | STANDARD | DAIKIN AIR CONDITIONING SAUDI ARABIA | SAR | 15000 | APPROVED |  |  | 2025-04-14 | 0 | 25 | Abuhammad, Samir | -45736 | 25
105-4 | Iman General Hospital in Riyad | 6675 | Iman General Hospital in Riyad-IGH - PR for Chiller | APPROVED | No | 2025-05-20 | Abas, Mohammed Fekry | 2025-05-21 | 2025-05-21 |  |  | 4.1 - O&M - NTT-Projects Services-Services (Non-Classified) - Q4 PPM (4th Visit) | 8866.25 | 7350 | 0 | STANDARD | DAIKIN AIR CONDITIONING SAUDI ARABIA | SAR | 8866.25 | APPROVED |  |  | 2025-06-22 | 0 | 32 | Abuhammad, Samir | -45798 | 32
105-5 | Fixed network rollout | 125 | Fixed network rollout-Corrugated flexible Hose 32mm | APPROVED | No | 2021-10-10 | Abas, Mohammed Fekry | 2021-10-12 | 2021-10-12 |  |  |  | 21158.4 | 3707 | 0 | STANDARD | Tassne Alladaen Company | SAR | 21158.4 | APPROVED |  |  | 2021-10-16 | 0 | 4 | Abuhammad, Samir | -44481 | 4
105-5 | Fixed network rollout | 127 | Fixed network rollout-Passive Electronic Marker, OM-05 NO.52085012 | APPROVED | No | 2021-10-11 | Abas, Mohammed Fekry | 2021-10-12 | 2021-10-12 |  |  |  | 101430 | 3671 | 0 | STANDARD | Bright Wire Company | SAR | 101430 | APPROVED |  |  | 2021-10-17 | 0 | 5 | Abuhammad, Samir | -44481 | 5
105-5 | Fixed network rollout | 128 | Fixed network rollout-Supply of Spacers | APPROVED | No | 2021-10-11 | Abas, Mohammed Fekry | 2021-10-12 | 2021-10-12 |  |  |  | 390792.6 | 3673 | 0 | STANDARD | Tassne Alladaen Company | SAR | 390792.6 | APPROVED |  |  | 2021-10-17 | 0 | 5 | Abuhammad, Samir | -44481 | 5
105-5 | Fixed network rollout | 130 | Fixed network rollout-FO Closure | APPROVED | No | 2021-10-11 | Abas, Mohammed Fekry | 2021-10-12 | 2021-10-12 |  |  |  | 6150.4 | 3773 | 2 | STANDARD | Optotec International SA | USD | 6150.4 | APPROVED |  |  | 2021-10-16 | 0 | 4 | Abuhammad, Samir | -44481 | 4
105-5 | Fixed network rollout | 130 | Fixed network rollout-FO Closure | APPROVED | No | 2021-10-11 | Abas, Mohammed Fekry | 2021-10-12 | 2021-10-12 |  |  |  | 23904 | 3711 | 0 | STANDARD | Optotec International SA | USD | 23904 | APPROVED |  |  | 2021-10-16 | 0 | 4 | Abuhammad, Samir | -44481 | 4
105-5 | Fixed network rollout | 131 | Fixed network rollout-Ducts & accessories | APPROVED | No | 2021-10-11 | Abas, Mohammed Fekry | 2021-10-12 | 2021-10-12 |  |  |  | 6790592 | 3681 | 2 | STANDARD | Al Wasail Industrial Company | SAR | 205448 | APPROVED |  |  | 2022-02-21 | 6585144 | 132 | Abuhammad, Samir | -44481 | 132
105-5 | Fixed network rollout | 131 | Fixed network rollout-Ducts & accessories | APPROVED | No | 2021-10-11 | Abas, Mohammed Fekry | 2021-10-12 | 2021-10-12 |  |  |  | 6978161.4 | 3681 | 0 | STANDARD | Al Wasail Industrial Company | SAR | 6978161.4 | APPROVED |  |  | 2021-10-17 | 0 | 5 | Abuhammad, Samir | -44481 | 5
105-5 | Fixed network rollout | 132 | Fixed network rollout-Supply of Manholes | APPROVED | No | 2021-10-11 | Abas, Mohammed Fekry | 2021-10-14 | 2021-10-14 |  | 2021-10-12 |  | 2027800 | 3672 | 0 | STANDARD | ABER AL RIYADH FOR CONTRACTING EST | SAR | 2027800 | APPROVED |  |  | 2021-10-18 | 0 | 4 | Abuhammad, Samir | -44483 | 4
105-5 | Fixed network rollout | 137 | Fixed network rollout-dsfd | APPROVED | No | 2021-10-12 | Abas, Mohammed Fekry | 2021-10-14 | 2021-10-14 |  |  |  | 41040 | 3769 | 2 | STANDARD | MIDDLE EAST FIBER CABLE MANUFACTURING CO. | SAR | 41040 | APPROVED |  |  | 2021-10-18 | 0 | 4 | Abuhammad, Samir | -44483 | 4
105-5 | Fixed network rollout | 137 | Fixed network rollout-dsfd | APPROVED | No | 2021-10-12 | Abas, Mohammed Fekry | 2021-10-14 | 2021-10-14 |  |  |  | 6862616.2 | 3739 | 0 | STANDARD | MIDDLE EAST FIBER CABLE MANUFACTURING CO. | SAR | 6862616.2 | APPROVED |  |  | 2021-10-19 | 0 | 5 | Abuhammad, Samir | -44483 | 5
105-5 | Fixed network rollout | 139 | Fixed network rollout-ISP installation | APPROVED | No | 2021-10-13 | Abas, Mohammed Fekry | 2021-10-14 | 2021-10-14 |  |  |  | 1500150 | 3649 | 0 | STANDARD | QUALITY NETWORKS ICT EST. | SAR | 1500150 | APPROVED |  |  | 2021-10-18 | 0 | 4 | Abuhammad, Samir | -44483 | 4
105-5 | Fixed network rollout | 139 | Fixed network rollout-ISP installation | APPROVED | No | 2021-10-13 | Abas, Mohammed Fekry | 2021-10-14 | 2021-10-14 |  |  |  | 1500150 | 3649 | 1 | STANDARD | QUALITY NETWORKS ICT EST. | SAR | 738378.1 | APPROVED |  |  | 2023-05-10 | 761771.9 | 573 | Abuhammad, Samir | -44483 | 573
105-5 | Fixed network rollout | 140 | Fixed network rollout-duct sealing | APPROVED | No | 2021-10-13 | Basyouni, Sara | 2021-10-17 | 2021-10-17 |  |  |  | 48336 | 3784 | 2 | STANDARD | Restart Limited Company | SAR | 48336 | APPROVED |  |  | 2021-10-18 | 0 | 1 | Abuhammad, Samir | -44486 | 1
105-5 | Fixed network rollout | 144 | Fixed network rollout-consulting | APPROVED | No | 2021-10-14 | Abas, Mohammed Fekry | 2021-10-18 | 2021-10-18 |  |  |  | 11909170 | 3656 | 0 | STANDARD | NORCONSULT TELEMATICS | SAR | 11909170 | APPROVED |  |  | 2021-10-18 | 0 | 0 | Abuhammad, Samir | -44487 | 0
105-5 | Fixed network rollout | 145 | Fixed network rollout-ISP | APPROVED | No | 2021-10-14 | Abas, Mohammed Fekry | 2021-10-18 | 2021-10-18 |  |  |  | 3975008 | 3651 | 0 | STANDARD | Gulf Power International LTD | SAR | 3975008 | APPROVED |  |  | 2021-10-21 | 0 | 3 | Abuhammad, Samir | -44487 | 3
105-5 | Fixed network rollout | 148 | Fixed network rollout-Fencing the outside store for Neom | REJECTED | No | 2021-10-17 | Ashkan, Ashwag | 2021-10-18 | 2021-10-17 |  | 2021-10-18 |  | 85000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -44486 | -44486
105-5 | Fixed network rollout | 157 | Fixed network rollout-Civil Work | APPROVED | No | 2021-10-19 | Abas, Mohammed Fekry | 2021-10-25 | 2021-10-25 |  | 2021-10-22 |  | 1214333 | 3641 | 0 | STANDARD | Multi Technology Company | SAR | 1214333 | APPROVED |  |  | 2021-10-31 | 0 | 6 | Abuhammad, Samir | -44494 | 6
105-5 | Fixed network rollout | 168 | Fixed network rollout-ISP material | APPROVED | No | 2021-10-25 | Abas, Mohammed Fekry | 2021-10-26 | 2021-10-26 |  |  |  | 77533850.7 | 3563 | 0 | STANDARD | Bayt Al Egada for Trading and Technology | SAR | 77533850.7 | APPROVED |  |  | 2021-11-04 | 0 | 9 | Abuhammad, Samir | -44495 | 9
105-5 | Fixed network rollout | 172 | Fixed network rollout-Fencing the outside store for Neom - PO# 3772-ES141-0 | APPROVED | No | 2021-10-27 | Abas, Mohammed Fekry | 2021-10-31 | 2021-10-31 |  |  |  | 85000 | 3772 | 2 | STANDARD | Binaa AlMurooj General Contracting Est | SAR | 85000 | APPROVED |  |  | 2021-11-02 | 0 | 2 | Abuhammad, Samir | -44500 | 2
105-5 | Fixed network rollout | 179 | Fixed network rollout-ISP | APPROVED | No | 2021-10-31 | Abas, Mohammed Fekry | 2021-11-01 | 2021-11-01 |  |  |  | 18995161.3 | 3563 | 0 | STANDARD | Bayt Al Egada for Trading and Technology | SAR | 18995161.3 | APPROVED |  |  | 2021-11-04 | 0 | 3 | Abuhammad, Samir | -44501 | 3
105-5 | Fixed network rollout | 194 | Fixed network rollout-ISP civil work | APPROVED | No | 2021-11-17 | Abas, Mohammed Fekry | 2021-11-25 | 2021-11-28 |  | 2021-11-21 |  | 167422 | 3641 | 1 | STANDARD | Multi Technology Company | SAR | 167422 | APPROVED |  |  | 2021-11-30 | 0 | 2 | Abuhammad, Samir | -44528 | 2
105-5 | Fixed network rollout | 236 | Fixed network rollout-Duct&accessories | APPROVED | No | 2021-11-21 | Abas, Mohammed Fekry | 2021-11-21 | 2021-11-21 |  |  |  | 8260000 | 3865 | 1 | STANDARD | Tahwelya Converting Industries Company | SAR | 7266000 | APPROVED |  |  | 2022-05-17 | 994000 | 177 | Abuhammad, Samir | -44521 | 177
105-5 | Fixed network rollout | 236 | Fixed network rollout-Duct&accessories | APPROVED | No | 2021-11-21 | Abas, Mohammed Fekry | 2021-11-21 | 2021-11-21 |  |  |  | 8288662.6 | 3865 | 0 | STANDARD | Tahwelya Converting Industries Company | SAR | 8288662.6 | APPROVED |  |  | 2021-11-23 | 0 | 2 | Abuhammad, Samir | -44521 | 2
105-5 | Fixed network rollout | 241 | Fixed network rollout-civil work | APPROVED | No | 2021-11-21 | Abas, Mohammed Fekry | 2021-11-28 | 2021-11-28 |  |  |  | 883225.8 | 3641 | 2 | STANDARD | Multi Technology Company | SAR | 883225.8 | APPROVED |  |  | 2021-12-06 | 0 | 8 | Abuhammad, Samir | -44528 | 8
105-5 | Fixed network rollout | 241 | Fixed network rollout-civil work | APPROVED | No | 2021-11-21 | Abas, Mohammed Fekry | 2021-11-28 | 2021-11-28 |  |  |  | 883225.8 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44528 | -44528
105-5 | Fixed network rollout | 368 | Fixed network rollout-Additiona Material EMS PR# 12 - NEOM Fixed Network | REJECTED | No | 2022-01-06 | AHMED, AQUEEL | 2022-02-06 | 2022-01-09 |  | 2022-01-12 |  | 147846.75 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -44570 | -44570
105-5 | Fixed network rollout | 481 | Fixed network rollout-Spacer for BB & Culvert | APPROVED | No | 2022-02-13 | Abas, Mohammed Fekry | 2022-02-15 | 2022-02-15 |  |  |  | 151952.79 | 4017 | 0 | STANDARD | Elfit Arabia Factory Company | SAR | 151951.2 | APPROVED |  |  | 2022-02-28 | 1.59 | 13 | Abuhammad, Samir | -44607 | 13
105-5 | Fixed network rollout | 482 | Fixed network rollout-EMS | APPROVED | No | 2022-02-14 | Abas, Mohammed Fekry | 2022-02-15 | 2022-02-15 |  |  |  | 39375 | 3671 | 1 | STANDARD | Bright Wire Company | SAR | 39375 | APPROVED |  |  | 2022-02-28 | 0 | 13 | Abuhammad, Samir | -44607 | 13
105-5 | Fixed network rollout | 482 | Fixed network rollout-EMS | APPROVED | No | 2022-02-14 | Abas, Mohammed Fekry | 2022-02-15 | 2022-02-15 |  |  |  | 203650 | 4015 | 0 | STANDARD | Al Mona Plastic Products Factory LTD.Co | SAR | 190525 | APPROVED |  |  | 2022-02-28 | 13125 | 13 | Abuhammad, Samir | -44607 | 13
105-5 | Fixed network rollout | 511 | Fixed network rollout-Duct | APPROVED | No | 2022-02-28 | Abas, Mohammed Fekry | 2022-03-01 | 2022-03-01 |  |  |  | 2501250 | 4037 | 0 | STANDARD | Tahwelya Converting Industries Company | SAR | 2501250 | APPROVED |  |  | 2022-03-17 | 0 | 16 | Abuhammad, Samir | -44621 | 16
105-5 | Fixed network rollout | 588 | Fixed network rollout-Spacer | APPROVED | No | 2022-04-03 | Abas, Mohammed Fekry | 2022-04-04 | 2022-04-05 |  |  |  | 74250 | 4077 | 0 | STANDARD | Elfit Arabia Factory Company | SAR | 74250 | APPROVED |  |  | 2022-04-10 | 0 | 5 | Abuhammad, Samir | -44656 | 5
105-5 | Fixed network rollout | 604 | Fixed network rollout-CCS | RETURNED | No | 2022-04-20 | Babic, Marian | 2025-11-12 | 2022-04-20 | 2025-11-12 |  | not required | 16199631.9 | [5 empty] | 0 |  |  |  |  | 0 |  | BABEKAR, MOHAMMED HUSSAIN | -44671 | -44671
105-5 | Fixed network rollout | 604 | Fixed network rollout-CCS | RETURNED | No | 2022-04-20 | Babic, Marian | 2025-11-12 | 2022-04-20 | 2025-11-12 |  | not required | 22751098.6 | [5 empty] | 0 |  |  |  |  | 0 |  | BABEKAR, MOHAMMED HUSSAIN | -44671 | -44671
105-5 | Fixed network rollout | 632 | Fixed network rollout-Intermediate spacer | APPROVED | No | 2022-05-10 | Abas, Mohammed Fekry | 2022-05-11 | 2022-05-11 |  |  |  | 16500 | 4017 | 1 | STANDARD | Elfit Arabia Factory Company | SAR | 16500 | APPROVED |  |  | 2022-05-17 | 0 | 6 | Abuhammad, Samir | -44692 | 6
105-5 | Fixed network rollout | 632 | Fixed network rollout-Intermediate spacer | APPROVED | No | 2022-05-10 | Abas, Mohammed Fekry | 2022-05-11 | 2022-05-11 |  |  |  | 16500 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44692 | -44692
105-5 | Fixed network rollout | 643 | Fixed network rollout-PR Tehweliya 71km | REJECTED | No | 2022-05-19 | Alameer, Waleed | 2022-05-22 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-5 | Fixed network rollout | 652 | Fixed network rollout-Detasad | APPROVED | No | 2022-05-26 | Abas, Mohammed Fekry | 2022-05-29 | 2022-05-30 |  |  |  | 7500000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44711 | -44711
105-5 | Fixed network rollout | 653 | Fixed network rollout-Hayat Alqassim S.O | RETURNED | No | 2022-05-26 | Abuhammad, Samir | 2024-05-01 | 2022-05-30 | 2024-05-01 |  | PM has to issue the SO | 23796298.84 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44711 | -44711
105-5 | Fixed network rollout | 653 | Fixed network rollout-Hayat Alqassim S.O | RETURNED | No | 2022-05-26 | Abuhammad, Samir | 2024-05-01 | 2022-05-30 | 2024-05-01 |  | PM has to issue the SO | 35415532.56 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44711 | -44711
105-5 | Fixed network rollout | 654 | Fixed network rollout-S.O for ALCO | APPROVED | No | 2022-05-26 | Abas, Mohammed Fekry | 2022-05-29 | 2022-05-30 |  |  |  | 3000000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44711 | -44711
105-5 | Fixed network rollout | 663 | Fixed network rollout-MHs | APPROVED | No | 2022-05-31 | Abas, Mohammed Fekry | 2022-06-01 | 2022-06-01 |  |  |  | 1058400 | 3672 | 1 | STANDARD | ABER AL RIYADH FOR CONTRACTING EST | SAR | 1058400 | APPROVED |  |  | 2022-06-15 | 0 | 14 | Abuhammad, Samir | -44713 | 14
105-5 | Fixed network rollout | 664 | Fixed network rollout-MHs | APPROVED | No | 2022-05-31 | Abas, Mohammed Fekry | 2022-06-01 | 2022-06-01 |  |  |  | 1774500 | 4132 | 0 | STANDARD | ABER AL RIYADH FOR CONTRACTING EST | SAR | 1729000 | APPROVED |  |  | 2022-06-22 | 45500 | 21 | Abuhammad, Samir | -44713 | 21
105-5 | Fixed network rollout | 681 | Fixed network rollout-Submarine Cable | APPROVED | No | 2022-06-06 | Abas, Mohammed Fekry | 2022-06-14 | 2022-06-15 |  |  |  | 1509000 | 4145 | 0 | STANDARD | Prysmian Cables Spain S.A. | EUR | 1496400 | APPROVED |  |  | 2022-06-26 | 12600 | 11 | Abuhammad, Samir | -44727 | 11
105-5 | Fixed network rollout | 683 | Fixed network rollout-HDD materials | APPROVED | No | 2022-06-07 | Abas, Mohammed Fekry | 2022-06-21 | 2022-06-22 | 2022-06-13 |  | Due to change the price as per PM request. | 119100 | 4148 | 0 | STANDARD | Al Mona Plastic Products Factory LTD.Co | SAR | 115100 | APPROVED |  |  | 2022-06-29 | 4000 | 7 | Abuhammad, Samir | -44734 | 7
105-5 | Fixed network rollout | 694 | Fixed network rollout-Altahweleya amendment to P.O 3865 | RETURNED | No | 2022-06-15 | Abuhammad, Samir | 2022-06-21 | 2022-06-21 | 2022-06-21 |  | Due to change the UOM item No.4 from Roll to mtr ,so we need to creat a new PR with Correct UOM | 1029500 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44733 | -44733
105-5 | Fixed network rollout | 695 | Fixed network rollout-Norconsult amendment | APPROVED | No | 2022-06-16 | Abas, Mohammed Fekry | 2022-06-20 | 2022-06-21 |  |  |  | 2090830 | 3656 | 1 | STANDARD | NORCONSULT TELEMATICS | SAR | 2043701.91 | APPROVED |  |  | 2023-06-11 | 47128.09 | 355 | Abuhammad, Samir | -44733 | 355
105-5 | Fixed network rollout | 698 | Fixed network rollout-PR for Additiona Civil and E&M Works for CSS Sites (As per attached SRF) | APPROVED | No | 2022-06-20 | Abas, Mohammed Fekry | 2022-06-23 | 2022-06-26 |  |  |  | 497475 | 3641 | 3 | STANDARD | Multi Technology Company | SAR | 307110 | APPROVED |  |  | 2022-09-12 | 190365 | 78 | Abuhammad, Samir | -44738 | 78
105-5 | Fixed network rollout | 703 | Fixed network rollout-ISP Material | INCOMPLETE | No |  | BABEKAR, MOHAMMED HUSSAIN | 2022-06-22 |  |  |  |  | 24376 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-5 | Fixed network rollout | 704 | Fixed network rollout-ISP | INCOMPLETE | No |  | BABEKAR, MOHAMMED HUSSAIN | 2022-06-22 |  |  |  |  | 24376 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-5 | Fixed network rollout | 705 | Fixed network rollout-Al-tahweleya Amendment P.O 3865 | APPROVED | No | 2022-06-22 | Abas, Mohammed Fekry | 2022-06-26 | 2022-06-26 |  |  |  | 1029500 | 3865 | 2 | STANDARD | Tahwelya Converting Industries Company | SAR | 1029500 | APPROVED |  |  | 2022-08-08 | 0 | 43 | Abuhammad, Samir | -44738 | 43
105-5 | Fixed network rollout | 715 | Fixed network rollout-ISP Work | INCOMPLETE | No |  | BABEKAR, MOHAMMED HUSSAIN | 2022-06-29 |  |  |  |  | 24376 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-5 | Fixed network rollout | 725 | Fixed network rollout-ISP Work | INCOMPLETE | No |  | Baskaran, Biju | 2022-07-04 |  |  |  |  | 24376 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-5 | Fixed network rollout | 726 | Fixed network rollout-ISP Work | INCOMPLETE | No |  | Baskaran, Biju | 2022-07-04 |  |  |  |  | 24376 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-5 | Fixed network rollout | 728 | Fixed network rollout-Purchase Request for ISP Works | RETURNED | No | 2022-07-07 | Abuhammad, Samir | 2022-10-02 | 2022-07-07 | 2022-10-02 |  | Due to change UOM | 31103.3 | 4191 | 0 | STANDARD | Electrolink Co Ltd | SAR | 31103.3 | APPROVED |  |  | 2022-08-23 | 0 |  | Abuhammad, Samir | -44749 | 47
105-5 | Fixed network rollout | 728 | Fixed network rollout-Purchase Request for ISP Works | RETURNED | No | 2022-07-07 | Abuhammad, Samir | 2022-10-02 | 2022-07-07 | 2022-10-02 |  | Due to change UOM | 6727.3 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44749 | -44749
105-5 | Fixed network rollout | 736 | Fixed network rollout-PR for Civil Work for 2 CCS Sites | INCOMPLETE | No |  | Baskaran, Biju | 2022-07-26 |  |  |  | Due to change UOM | 519450 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-5 | Fixed network rollout | 737 | Fixed network rollout-PR request for 48F ODF ( 200 Qty.) for RAN Sites for NFL project | INCOMPLETE | No |  | Baskaran, Biju | 2022-07-26 |  |  |  | Due to change UOM | 107373.75 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-5 | Fixed network rollout | 738 | Fixed network rollout-Purchase Request for 2 CCS Sites | APPROVED | No | 2022-07-28 | Babic, Marian | 2022-07-31 | 2022-08-02 |  |  |  | 519450 | 4196 | 0 | STANDARD | Multi Technology Company | SAR | 274533.6 | APPROVED |  |  | 2022-10-25 | 244916.4 | 84 | Abuhammad, Samir | -44775 | 84
105-5 | Fixed network rollout | 739 | Fixed network rollout-Purchase Request for 48F ODF | REJECTED | No | 2022-07-28 | BABEKAR, MOHAMMED HUSSAIN | 2022-07-28 |  |  | 2022-07-28 | please attached the support documents . | 107373.75 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-5 | Fixed network rollout | 740 | Fixed network rollout-Purchase Request for 48F ODF | APPROVED | No | 2022-07-28 | Abas, Mohammed Fekry | 2022-08-02 | 2022-08-02 |  |  |  | 107373.75 | 4189 | 0 | STANDARD | Optotec International SA | USD | 107373.75 | APPROVED |  |  | 2022-09-12 | 0 | 41 | Abuhammad, Samir | -44775 | 41
105-5 | Fixed network rollout | 750 | Fixed network rollout-additional materials needed for route C & RAN | REJECTED | No | 2022-07-31 | Alameer, Waleed | 2022-08-02 | 2022-07-31 |  | 2022-08-07 |  | 109850.4 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -44773 | -44773
105-5 | Fixed network rollout | 754 | Fixed network rollout-Purchase Request for Sindal ISP CSS Sites | APPROVED | No | 2022-08-03 | Abas, Mohammed Fekry | 2022-08-11 | 2022-08-14 |  |  |  | 1840441.01 | 4188 | 0 | STANDARD | REDINGTON SAUDI ARABIA DISTRIBUTION CO. | SAR | 1840441.01 | APPROVED |  |  | 2022-09-06 | 0 | 23 | Abuhammad, Samir | -44787 | 23
105-5 | Fixed network rollout | 757 | Fixed network rollout-2Africa HDD | APPROVED | No | 2022-08-07 | Abas, Mohammed Fekry | 2022-08-11 | 2022-08-14 |  |  |  | 7889800 | 4192 | 0 | STANDARD | Power Sub Link SA | EUR | 7889799.45 | APPROVED |  |  | 2022-09-15 | 0.55 | 32 | Abuhammad, Samir | -44787 | 32
105-5 | Fixed network rollout | 758 | Fixed network rollout-PR Request for End Caps & Closure | APPROVED | No | 2022-08-09 | Abas, Mohammed Fekry | 2022-08-14 | 2022-08-18 |  |  |  | 40000 | 4195 | 0 | STANDARD | Al Mona Plastic Products Factory LTD.Co | SAR | 40000 | APPROVED |  |  | 2022-08-31 | 0 | 13 | Abuhammad, Samir | -44791 | 13
105-5 | Fixed network rollout | 758 | Fixed network rollout-PR Request for End Caps & Closure | APPROVED | No | 2022-08-09 | Abas, Mohammed Fekry | 2022-08-14 | 2022-08-18 |  |  |  | 109560 | 4213 | 0 | STANDARD | Optotec International SA | USD | 109560 | APPROVED |  |  | 2022-09-06 | 0 | 19 | Abuhammad, Samir | -44791 | 19
105-5 | Fixed network rollout | 778 | Fixed network rollout-services of supply and re-filling Fuel at CSS sites location of NEOM | APPROVED | No | 2022-08-30 | Abas, Mohammed Fekry | 2022-09-05 | 2022-09-07 |  |  |  | 100000 | 4223 | 0 | STANDARD | Othman Hammoud Al-Zaydi Est | SAR | 100000 | APPROVED |  |  | 2022-09-15 | 0 | 8 | Abuhammad, Samir | -44811 | 8
105-5 | Fixed network rollout | 785 | Fixed network rollout-PR for ISP Materials- CCTV system for Sindhala CSS & 7 x CSS container sites as per attached SRF | REJECTED | No | 2022-09-04 | Malek, Warren | 2022-09-05 | 2022-09-05 |  | 2022-09-05 |  | 267866.56 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -44809 | -44809
105-5 | Fixed network rollout | 849 | Fixed network rollout-PR for CCTV Cameras for 7 CSS sites and Sindhala CSS | REJECTED | No | 2022-09-25 | BABEKAR, MOHAMMED HUSSAIN | 2022-09-25 |  |  | 2022-09-26 |  | 16427.34 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-5 | Fixed network rollout | 850 | Fixed network rollout-PR for Cameras Storage (NVR) for 7 CSS sites and Sindhala CSS | RETURNED | No | 2022-09-21 | Abuhammad, Samir | 2023-02-09 | 2022-10-10 | 2023-02-09 | 2022-10-02 | Dut to change the UOM as per project request | 167814.79 | 4262 | 0 | STANDARD | Gulf Application Co | SAR | 167768 | APPROVED |  |  | 2022-11-17 | 46.79 |  | Abuhammad, Samir | -44844 | 38
105-5 | Fixed network rollout | 850 | Fixed network rollout-PR for Cameras Storage (NVR) for 7 CSS sites and Sindhala CSS | RETURNED | No | 2022-09-21 | Abuhammad, Samir | 2023-02-09 | 2022-10-10 | 2023-02-09 | 2022-10-02 | Dut to change the UOM as per project request | 1215 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44844 | -44844
105-5 | Fixed network rollout | 853 | Fixed network rollout-PR for CCTV Cameras for 7 CSS sites and Sindhala CSS | APPROVED | No | 2022-09-28 | Abas, Mohammed Fekry | 2022-10-06 | 2022-10-09 |  |  |  | 85763.46 | 4256 | 0 | STANDARD | Advance International Company | SAR | 85763.46 | APPROVED |  |  | 2022-11-01 | 0 | 23 | Abuhammad, Samir | -44843 | 23
105-5 | Fixed network rollout | 855 | Fixed network rollout-PR- Request End Cap 110 m- | APPROVED | No | 2022-09-29 | Abas, Mohammed Fekry | 2022-10-06 | 2022-10-09 |  |  |  | 5062.5 | 4015 | 1 | STANDARD | Al Mona Plastic Products Factory LTD.Co | SAR | 5062.5 | APPROVED |  |  | 2022-10-25 | 0 | 16 | Abuhammad, Samir | -44843 | 16
105-5 | Fixed network rollout | 870 | Fixed network rollout-PR -Cable tray Materials -ISP works | APPROVED | No | 2022-10-10 | Abas, Mohammed Fekry | 2022-10-14 | 2022-10-16 |  |  |  | 6727.3 | 4191 | 5 | STANDARD | Electrolink Co Ltd | SAR | 6727.3 | APPROVED |  |  | 2022-10-19 | 0 | 3 | Abuhammad, Samir | -44850 | 3
105-5 | Fixed network rollout | 950 | Fixed network rollout-PR for Services of Router Upgrade | APPROVED | No | 2022-12-11 | Abas, Mohammed Fekry | 2022-12-18 | 2022-12-18 |  |  |  | 22400 | 4299 | 0 | STANDARD | Bayt Al Egada for Trading and Technology | SAR | 22400 | APPROVED |  |  | 2022-12-27 | 0 | 9 | Abuhammad, Samir | -44913 | 9
105-5 | Fixed network rollout | 959 | Fixed network rollout-PR- for New block wall with plaster | APPROVED | No | 2022-12-29 | Abas, Mohammed Fekry | 2023-01-02 | 2023-01-02 |  |  |  | 62500 | 4196 | 1 | STANDARD | Multi Technology Company | SAR | 62500 | APPROVED |  |  | 2023-01-23 | 0 | 21 | Abuhammad, Samir | -44928 | 21
105-5 | Fixed network rollout | 960 | Fixed network rollout-PR for HDD marine OSP Part | REJECTED | No | 2023-01-01 | Alameer, Waleed | 2023-01-01 | 2023-01-01 |  | 2023-01-01 |  | 269154.8 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -44927 | -44927
105-5 | Fixed network rollout | 975 | Fixed network rollout-PR For HDD Marine Scope OSP Part | RETURNED | No | 2023-01-02 | Abuhammad, Samir | 2023-08-24 | 2023-01-09 | 2023-08-24 |  | Due to change the requirment. | 10509 | 4017 | 2 | STANDARD | Elfit Arabia Factory Company | SAR | 10509 | APPROVED |  |  | 2023-02-26 | 0 |  | Abuhammad, Samir | -44935 | 48
105-5 | Fixed network rollout | 975 | Fixed network rollout-PR For HDD Marine Scope OSP Part | RETURNED | No | 2023-01-02 | Abuhammad, Samir | 2023-08-24 | 2023-01-09 | 2023-08-24 |  | Due to change the requirment. | 173714 | 4037 | 1 | STANDARD | Tahwelya Converting Industries Company | SAR | 173714 | APPROVED |  |  | 2023-03-12 | 0 |  | Abuhammad, Samir | -44935 | 62
105-5 | Fixed network rollout | 975 | Fixed network rollout-PR For HDD Marine Scope OSP Part | RETURNED | No | 2023-01-02 | Abuhammad, Samir | 2023-08-24 | 2023-01-09 | 2023-08-24 |  | Due to change the requirment. | 2949.4 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44935 | -44935
105-5 | Fixed network rollout | 979 | Fixed network rollout-PR For HDD Marine BMH | APPROVED | No | 2023-01-02 | Abas, Mohammed Fekry | 2023-01-05 | 2023-01-09 |  |  |  | 24500 | 4132 | 1 | STANDARD | ABER AL RIYADH FOR CONTRACTING EST | SAR | 24500 | APPROVED |  |  | 2023-02-26 | 0 | 48 | Abuhammad, Samir | -44935 | 48
105-5 | Fixed network rollout | 985 | Fixed network rollout-PR- Route "C" cable blowing subsea cable | REJECTED | No | 2023-01-04 | BABEKAR, MOHAMMED HUSSAIN | 2023-01-04 |  |  | 2023-01-04 |  | 300000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-5 | Fixed network rollout | 986 | Fixed network rollout-PR- Route "C" Cable Blowing Subsea Cable & Normal Cable | REJECTED | No | 2023-01-04 | Baskaran, Biju | 2023-01-10 |  |  |  |  | 510000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-5 | Fixed network rollout | 993 | Fixed network rollout-PR for Submarine Joint Closure | APPROVED | No | 2023-01-08 | Abas, Mohammed Fekry | 2023-01-11 | 2023-01-15 |  |  |  | 45000 | 4342 | 0 | STANDARD | Prysmian Cables Spain S.A. | EUR | 44600 | APPROVED |  |  | 2023-02-19 | 400 | 35 | Abuhammad, Samir | -44941 | 35
105-5 | Fixed network rollout | 995 | Fixed network rollout-PR- Route "C" Cable Blowing Subsea Cable & Normal Cable -Resubmit | APPROVED | No | 2023-01-10 | Abas, Mohammed Fekry | 2023-01-19 | 2023-01-22 |  |  |  | 150000 | 4326 | 0 | STANDARD | Arabian Lions For Contracting Co | SAR | 150000 | APPROVED |  |  | 2023-04-13 | 0 | 81 | Abuhammad, Samir | -44948 | 81
105-5 | Fixed network rollout | 1054 | Fixed network rollout-PR for Cameras Storage (NVR) change in the UOM for Twisted-Pair Cable | APPROVED | No | 2023-02-09 | Abas, Mohammed Fekry | 2023-02-12 | 2023-02-13 |  |  |  | 1215 | 4262 | 2 | STANDARD | Gulf Application Co | SAR | 1215 | APPROVED |  |  | 2023-03-12 | 0 | 27 | Abuhammad, Samir | -44970 | 27
105-5 | Fixed network rollout | 1061 | Fixed network rollout-PR- Route "C" Cable Blowing Normal Cable -Resubmit | APPROVED | No | 2023-02-12 | Abas, Mohammed Fekry | 2023-02-14 | 2023-02-16 |  |  |  | 210000 | 4348 | 0 | STANDARD | Samah Al Badaa Establishment for General Constructions | SAR | 210000 | APPROVED |  |  | 2023-04-06 | 0 | 49 | Abuhammad, Samir | -44973 | 49
105-5 | Fixed network rollout | 1072 | Fixed network rollout-PR-Material Requirement for New Scope Route J2 | RETURNED | No | 2023-02-14 | Abuhammad, Samir | 2023-08-24 | 2023-02-21 | 2023-08-24 |  | due to change the requirment. | 8067.8 | 4364 | 0 | STANDARD | Bright Wire Company | SAR | 8067.8 | APPROVED |  |  | 2023-03-29 | 0 |  | Abuhammad, Samir | -44978 | 36
105-5 | Fixed network rollout | 1072 | Fixed network rollout-PR-Material Requirement for New Scope Route J2 | RETURNED | No | 2023-02-14 | Abuhammad, Samir | 2023-08-24 | 2023-02-21 | 2023-08-24 |  | due to change the requirment. | 963000 | 4366 | 0 | STANDARD | Tahwelya Converting Industries Company | SAR | 963000 | APPROVED |  |  | 2023-04-06 | 0 |  | Abuhammad, Samir | -44978 | 44
105-5 | Fixed network rollout | 1072 | Fixed network rollout-PR-Material Requirement for New Scope Route J2 | RETURNED | No | 2023-02-14 | Abuhammad, Samir | 2023-08-24 | 2023-02-21 | 2023-08-24 |  | due to change the requirment. | 42000 | 4398 | 0 | STANDARD | Al Mona Plastic Products Factory LTD.Co | SAR | 39750 | APPROVED |  |  | 2023-04-02 | 2250 |  | Abuhammad, Samir | -44978 | 40
105-5 | Fixed network rollout | 1072 | Fixed network rollout-PR-Material Requirement for New Scope Route J2 | RETURNED | No | 2023-02-14 | Abuhammad, Samir | 2023-08-24 | 2023-02-21 | 2023-08-24 |  | due to change the requirment. | 16000 | 4399 | 0 | STANDARD | Optimum Network Services | SAR | 16000 | APPROVED |  |  | 2023-04-09 | 0 |  | Abuhammad, Samir | -44978 | 47
105-5 | Fixed network rollout | 1072 | Fixed network rollout-PR-Material Requirement for New Scope Route J2 | RETURNED | No | 2023-02-14 | Abuhammad, Samir | 2023-08-24 | 2023-02-21 | 2023-08-24 |  | due to change the requirment. | 3600 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44978 | -44978
105-5 | Fixed network rollout | 1105 | Fixed network rollout-PR-Route C - for Cable Tag,Orange flexible pipe and OTDR test for fiber works | APPROVED | No | 2023-03-07 | Abas, Mohammed Fekry | 2023-03-13 | 2023-03-13 |  |  |  | 30000 | 4326 | 1 | STANDARD | Arabian Lions For Contracting Co | SAR | 30000 | APPROVED |  |  | 2023-06-11 | 0 | 90 | Abuhammad, Samir | -44998 | 90
105-5 | Fixed network rollout | 1125 | Fixed network rollout-PR-Material Requirement for New Scope Route C | APPROVED | No | 2023-03-12 | Abas, Mohammed Fekry | 2023-03-13 | 2023-03-13 |  |  |  | 6750 | 4398 | 0 | STANDARD | Al Mona Plastic Products Factory LTD.Co | SAR | 6750 | APPROVED |  |  | 2023-04-02 | 0 | 20 | Abuhammad, Samir | -44998 | 20
105-5 | Fixed network rollout | 1125 | Fixed network rollout-PR-Material Requirement for New Scope Route C | APPROVED | No | 2023-03-12 | Abas, Mohammed Fekry | 2023-03-13 | 2023-03-13 |  |  |  | 40000 | 4399 | 0 | STANDARD | Optimum Network Services | SAR | 40000 | APPROVED |  |  | 2023-04-09 | 0 | 27 | Abuhammad, Samir | -44998 | 27
105-5 | Fixed network rollout | 1125 | Fixed network rollout-PR-Material Requirement for New Scope Route C | APPROVED | No | 2023-03-12 | Abas, Mohammed Fekry | 2023-03-13 | 2023-03-13 |  |  |  | 9000 | 4488 | 0 | STANDARD | Tahwelya Converting Industries Company | SAR | 9000 | APPROVED |  |  | 2023-06-05 | 0 | 84 | Abuhammad, Samir | -44998 | 84
105-5 | Fixed network rollout | 1255 | Fixed network rollout-PR- For ISP Installation Work-PO#8196 | APPROVED | No | 2023-05-11 | Abas, Mohammed Fekry | 2023-05-11 | 2023-05-14 |  |  |  | 300000 | 4456 | 0 | STANDARD | Omed Information Technology for Communicatioms | SAR | 300000 | APPROVED |  |  | 2023-05-29 | 0 | 15 | Abuhammad, Samir | -45060 | 15
105-5 | Fixed network rollout | 1291 | Fixed network rollout-PR for Beach Manholes | REJECTED | No | 2023-05-28 | Mraish, Fahed Mhd Yaser | 2023-05-31 | 2023-05-30 | 2023-05-30 | 2023-05-31 | For PR modification. | 121840 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45076 | -45076
105-5 | Fixed network rollout | 1298 | Fixed network rollout-PR for Beach Manholes | RETURNED | No | 2023-05-31 | Abuhammad, Samir | 2023-06-14 | 2023-06-14 | 2023-06-14 |  | No need as we modifiythe Qty from the prevuse CO. | 49000 | 4132 | 4 | STANDARD | ABER AL RIYADH FOR CONTRACTING EST | SAR | 24500 | APPROVED |  |  | 2024-01-25 | 24500 |  | Abuhammad, Samir | -45091 | 225
105-5 | Fixed network rollout | 1298 | Fixed network rollout-PR for Beach Manholes | RETURNED | No | 2023-05-31 | Abuhammad, Samir | 2023-06-14 | 2023-06-14 | 2023-06-14 |  | No need as we modifiythe Qty from the prevuse CO. | 85280 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45091 | -45091
105-5 | Fixed network rollout | 1654 | Fixed network rollout-Fixed network rollout-PR for HAYAT To Issue Service Order under Balnket PO-3668 | APPROVED | No | 2023-11-02 | Abas, Mohammed Fekry | 2023-11-13 | 2023-11-14 |  |  |  | 999339.23 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45244 | -45244
105-5 | Fixed network rollout | 1655 | Fixed network rollout-Fixed network rollout-PR For CCS to Issue Service Order under Blanket PO-3667 | APPROVED | No | 2023-11-02 | Abas, Mohammed Fekry | 2023-11-13 | 2023-11-14 |  |  |  | 789710.54 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45244 | -45244
105-5 | Fixed network rollout | 1880 | Fixed network rollout-PR for Circle Cluster CSS Civil & Electro Mechanical works | APPROVED | No | 2023-12-03 | Abas, Mohammed Fekry | 2023-12-06 | 2023-12-07 |  |  |  | 599357 | 4829 | 0 | STANDARD | Eastern Power Contracting Est. | SAR | 440390 | APPROVED |  |  | 2024-01-01 | 158967 | 25 | Abuhammad, Samir | -45267 | 25
105-5 | Fixed network rollout | 2027 | Fixed network rollout-PR for SC CSS ISP equipment migration to telco Park -For Services | APPROVED | No | 2023-12-24 | Abas, Mohammed Fekry | 2023-12-25 | 2023-12-26 |  |  |  | 999000 | 4929 | 0 | STANDARD | High Point Technology Co, | SAR | 408000 | APPROVED |  |  | 2024-01-07 | 591000 | 12 | Abuhammad, Samir | -45286 | 12
105-5 | Fixed network rollout | 2039 | Fixed network rollout-PR- Service item for SC CSS migration to Telco Park | APPROVED | No | 2023-12-26 | Abas, Mohammed Fekry | 2023-12-28 | 2023-12-28 |  |  |  | 1210530.71 | 4938 | 0 | STANDARD | Bayt Al Egada for Trading and Technology | SAR | 1210527 | APPROVED |  |  | 2024-08-23 | 3.71 | 239 | Abuhammad, Samir | -45288 | 239
105-5 | Fixed network rollout | 2569 | Fixed network rollout-PR for Southern cluster international subsea OSP | APPROVED | No | 2024-02-15 | Abas, Mohammed Fekry | 2024-04-03 | 2024-04-04 |  |  |  | 1184800 | 5346 | 0 | STANDARD | Al Mona Plastic Products Factory LTD.Co | SAR | 1184800 | APPROVED |  |  | 2024-04-28 | 0 | 24 | Abuhammad, Samir | -45386 | 24
105-5 | Fixed network rollout | 2569 | Fixed network rollout-PR for Southern cluster international subsea OSP | APPROVED | No | 2024-02-15 | Abas, Mohammed Fekry | 2024-04-03 | 2024-04-04 |  |  |  | 397300 | 5479 | 1 | STANDARD | Tahwelya Converting Industries Company | SAR | 275500 | APPROVED |  |  | 2025-02-10 | 121800 | 312 | Abuhammad, Samir | -45386 | 312
105-5 | Fixed network rollout | 2569 | Fixed network rollout-PR for Southern cluster international subsea OSP | APPROVED | No | 2024-02-15 | Abas, Mohammed Fekry | 2024-04-03 | 2024-04-04 |  |  |  | 1184800 | 5479 | 0 | STANDARD | Tahwelya Converting Industries Company | SAR | 1184800 | APPROVED |  |  | 2024-05-11 | 0 | 37 | Abuhammad, Samir | -45386 | 37
105-5 | Fixed network rollout | 2829 | Fixed network rollout-PR in system for Front haul services scope- Subsea International cable southern cluster NEOM | REJECTED | No | 2024-03-14 | Mraish, Fahed Mhd Yaser | 2024-03-14 |  |  | 2024-03-31 | Please check the exact amount for the last quote | 5487329 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-5 | Fixed network rollout | 2959 | Fixed network rollout-PR-For OSP NEOM Bay Airpoirt Connetivity | REJECTED | No | 2024-04-01 | Mraish, Fahed Mhd Yaser | 2025-05-07 |  |  | 2025-05-07 | 1.1-OSP Work- Subcontracting-NTT-Projects Services-Equipment installation | 465271.58 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-5 | Fixed network rollout | 2971 | Fixed network rollout-PR For system for Front haul services scope- Subsea International cable southern cluster NEOM | APPROVED | No | 2024-04-01 | Abas, Mohammed Fekry | 2024-04-04 | 2024-04-04 |  |  |  | 4633905.5 | 5345 | 0 | STANDARD | Pearl Arab International Contracting Company | SAR | 4633905.5 | APPROVED |  |  | 2024-05-05 | 0 | 31 | Abuhammad, Samir | -45386 | 31
105-5 | Fixed network rollout | 2981 | Fixed network rollout-PR for Dismantling & Transportation to NEOM Community | APPROVED | No | 2024-04-03 | Abas, Mohammed Fekry | 2024-04-10 | 2024-04-15 |  |  |  | 175000 | 5412 | 0 | STANDARD | High Point Technology Co, | SAR | 175000 | APPROVED |  |  | 2024-05-20 | 0 | 35 | Abuhammad, Samir | -45397 | 35
105-5 | Fixed network rollout | 2998 | Fixed network rollout-PR for supply of below materials for NEOM | APPROVED | No | 2024-04-04 | Abas, Mohammed Fekry | 2024-04-24 | 2024-04-24 |  |  |  | 348000 | 4132 | 7 | STANDARD | ABER AL RIYADH FOR CONTRACTING EST | SAR | 348000 | APPROVED |  |  | 2024-06-05 | 0 | 42 | Abuhammad, Samir | -45406 | 42
105-5 | Fixed network rollout | 2999 | Fixed network rollout-PR For Civil and Fiber work CC2 Connectivity - Route-A | APPROVED | No | 2024-04-04 | Abas, Mohammed Fekry | 2024-05-09 | 2024-05-12 |  |  |  | 54447.2 | 5668 | 0 | STANDARD | Samah Al Badaa Establishment for General Constructions | SAR | 54406 | APPROVED |  |  | 2024-07-07 | 41.2 | 56 | Abuhammad, Samir | -45424 | 56
105-5 | Fixed network rollout | 3117 | Fixed network rollout-PR for OSP Fibers Break on Route-8 (C) Rectification work | APPROVED | No | 2024-04-24 | Abas, Mohammed Fekry | 2024-04-29 | 2024-04-30 |  |  |  | 586520 | 5502 | 0 | STANDARD | Samah Al Badaa Establishment for General Constructions | SAR | 586520 | APPROVED |  |  | 2024-05-26 | 0 | 26 | Abuhammad, Samir | -45412 | 26
105-5 | Fixed network rollout | 3480 | Fixed network rollout-PR For Route-8 Rectification Work | APPROVED | No | 2024-05-23 | Abas, Mohammed Fekry | 2024-06-03 | 2024-06-03 |  |  |  | 349940 | 5686 | 0 | STANDARD | Samah Al Badaa Establishment for General Constructions | SAR | 349940 | APPROVED |  |  | 2024-10-29 | 0 | 148 | Abuhammad, Samir | -45446 | 148
105-5 | Fixed network rollout | 3480 | Fixed network rollout-PR For Route-8 Rectification Work | APPROVED | No | 2024-05-23 | Abas, Mohammed Fekry | 2024-06-03 | 2024-06-03 |  |  |  | 349940 | 5686 | 1 | STANDARD | Samah Al Badaa Establishment for General Constructions | SAR | 323622 | APPROVED |  |  | 2024-12-29 | 26318 | 209 | Abuhammad, Samir | -45446 | 209
105-5 | Fixed network rollout | 3990 | Fixed network rollout-PR for Generator Services ( Replacement of 12V bat, change filer , change engine oil etc ) at NC1 CSS –NEOM | RETURNED | No | 2024-07-22 | Abuhammad, Samir | 2024-08-15 | 2024-07-29 | 2024-08-15 |  | As per PM request, cash @site. | 8285 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45502 | -45502
105-5 | Fixed network rollout | 4064 | Fixed network rollout-PR for supply of a MDB enclosure main breaker 400 Amp | RETURNED | No | 2024-07-31 | Abuhammad, Samir | 2024-08-15 | 2024-08-01 | 2024-08-15 |  | As per PM request, cash @site. | 6800 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45505 | -45505
105-5 | Fixed network rollout | 4106 | Fixed network rollout-PR For Rectification work of Damaged Ducts & Cable | APPROVED | No | 2024-08-06 | Abas, Mohammed Fekry | 2024-08-07 | 2024-08-07 |  |  |  | 1081510 | 5969 | 0 | STANDARD | Nets international Limited | SAR | 704520 | APPROVED |  |  | 2024-08-22 | 376990 | 15 | Abuhammad, Samir | -45511 | 15
105-5 | Fixed network rollout | 4106 | Fixed network rollout-PR For Rectification work of Damaged Ducts & Cable | APPROVED | No | 2024-08-06 | Abas, Mohammed Fekry | 2024-08-07 | 2024-08-07 |  |  |  | 1081510 | 5969 | 1 | STANDARD | Nets international Limited | SAR | 637955.2 | APPROVED |  |  | 2024-12-12 | 443554.8 | 127 | Abuhammad, Samir | -45511 | 127
105-5 | Fixed network rollout | 4195 | Fixed network rollout-PR for Installation of ISP equipment's at NC1 TEB01 | APPROVED | No | 2024-08-19 | Abas, Mohammed Fekry | 2024-08-25 | 2024-08-25 |  |  |  | 215000 | 6098 | 0 | STANDARD | High Point Technology Co, | SAR | 215000 | APPROVED |  |  | 2024-09-02 | 0 | 8 | Abuhammad, Samir | -45529 | 8
105-5 | Fixed network rollout | 4331 | Fixed network rollout-PR for patch cords and CAT6 UTP cables required for SC CSS migration to Telco Park Project | APPROVED | No | 2024-09-01 | Abas, Mohammed Fekry | 2024-09-09 | 2024-09-09 |  |  |  | 42055 | 6167 | 0 | STANDARD | Integrated Network Solutions Trading Est. | SAR | 36050 | APPROVED |  |  | 2024-10-07 | 6005 | 28 | Abuhammad, Samir | -45544 | 28
105-5 | Fixed network rollout | 4459 | Fixed network rollout-PR for fiber connectivity from Telco Park MMR 1 & 2 to CLS-Using budget Line-1.1 (OSP Subcontracting) | APPROVED | No | 2024-09-15 | Abas, Mohammed Fekry | 2024-10-07 | 2024-10-07 |  |  |  | 19254.34 | 6193 | 0 | STANDARD | Nets international Limited | SAR | 19254.34 | APPROVED |  |  | 2024-10-13 | 0 | 6 | Abuhammad, Samir | -45572 | 6
105-5 | Fixed network rollout | 4459 | Fixed network rollout-PR for fiber connectivity from Telco Park MMR 1 & 2 to CLS-Using budget Line-1.1 (OSP Subcontracting) | APPROVED | No | 2024-09-15 | Abas, Mohammed Fekry | 2024-10-07 | 2024-10-07 |  |  |  | 19254.34 | 6193 | 1 | STANDARD | Nets international Limited | SAR | 16679.41 | APPROVED |  |  | 2025-01-01 | 2574.93 | 86 | Abuhammad, Samir | -45572 | 86
105-5 | Fixed network rollout | 4522 | Fixed network rollout-PR For Comatec -Manual PO#8199-0 | APPROVED | No | 2024-09-29 | Abas, Mohammed Fekry | 2024-10-03 | 2024-10-04 |  |  |  | 3144765.8 | 6309 | 0 | STANDARD | Comatec Saudi Arabia Co. LTD | SAR | 3144765.8 | APPROVED |  |  | 2024-10-08 | 0 | 4 | Abuhammad, Samir | -45569 | 4
105-5 | Fixed network rollout | 5307 | Fixed network rollout-PR For Rectification of damaged civil & Fiber cable on route J2-(Budget-1.1) | APPROVED | No | 2024-12-31 | Abas, Mohammed Fekry | 2025-01-02 | 2025-01-02 |  |  |  | 130092 | 6731 | 0 | STANDARD | Nets international Limited | SAR | 130092 | APPROVED |  |  | 2025-01-15 | 0 | 13 | Abuhammad, Samir | -45659 | 13
105-5 | Fixed network rollout | 5416 | Fixed network rollout-PR For Duct Request(Tahwelya) for Qty Difference(PO#5479) | APPROVED | No | 2025-01-14 | Abas, Mohammed Fekry | 2025-01-18 | 2025-01-19 |  |  |  | 22500 | 5479 | 1 | STANDARD | Tahwelya Converting Industries Company | SAR | 22500 | APPROVED |  |  | 2025-02-10 | 0 | 22 | Abuhammad, Samir | -45676 | 22
105-5 | Fixed network rollout | 5425 | Fixed network rollout-PR for Rectification scope on Route-J2 (5) | RETURNED | No | 2025-01-14 | Abuhammad, Samir | 2025-01-19 | 2025-01-19 | 2025-01-19 |  | As the request saml value less 1000 SAR, for 6 items with 5 different supplier" cash site" | 952.6 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45676 | -45676
105-5 | Fixed network rollout | 5779 | Fixed network rollout-PR for Fiber connectivity - Sindhala UAH to COW site-Budget Item#1.1 | APPROVED | No | 2025-02-04 | Abas, Mohammed Fekry | 2025-02-05 | 2025-02-05 |  |  |  | 99820 | 6875 | 0 | STANDARD | Samah Al Badaa Establishment for General Constructions | SAR | 99820 | APPROVED |  |  | 2025-02-17 | 0 | 12 | Abuhammad, Samir | -45693 | 12
105-5 | Fixed network rollout | 5817 | Fixed network rollout-Equipment and tools for Nesma fiber team-Brightwires | APPROVED | No | 2025-02-09 | Abas, Mohammed Fekry | 2025-02-17 | 2025-02-18 |  |  |  | 178580 | 6937 | 0 | STANDARD | Bright Wire Company | SAR | 178580 | APPROVED |  |  | 2025-03-11 | 0 | 21 | Abuhammad, Samir | -45706 | 21
105-5 | Fixed network rollout | 5818 | Fixed network rollout-Equipment and tools for Nesma fiber team-Integrated Networks | APPROVED | No | 2025-02-09 | Abas, Mohammed Fekry | 2025-02-17 | 2025-02-18 |  |  |  | 9460 | 6935 | 0 | STANDARD | Integrated Network Solutions Trading Est. | SAR | 8374 | APPROVED |  |  | 2025-03-18 | 1086 | 28 | Abuhammad, Samir | -45706 | 28
105-5 | Fixed network rollout | 6056 | Fixed network rollout-PR for fiber cable connectivity from Telco Park –MMR# 1 & MMR# 2 to HSDC | APPROVED | No | 2025-02-26 | Abas, Mohammed Fekry | 2025-02-27 | 2025-02-27 |  |  | Fiber Connectivity Scope-Buget Task#1.1 | 52201.34 | 6979 | 0 | STANDARD | Samah Al Badaa Establishment for General Constructions | SAR | 52201.34 | APPROVED |  |  | 2025-03-09 | 0 | 10 | Abuhammad, Samir | -45715 | 10
105-5 | Fixed network rollout | 6671 | Fixed network rollout-PR For TCIL To Issue Service Order Under Blanket PO-4372 | APPROVED | No | 2025-05-20 | Abas, Mohammed Fekry | 2025-05-26 | 2025-05-26 |  |  | PR for TCIL Under Blanket PO #4372 ,Budget Task(#1.1-OSP Work- Subcontracting) | 1186270.78 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45803 | -45803
105-5 | Fixed network rollout | 6672 | Fixed network rollout-PR For Mawarid To Issue Service Order Under Blanket PO-4527 | APPROVED | No | 2025-05-20 | Abas, Mohammed Fekry | 2025-05-26 | 2025-05-26 |  |  | PR For Mawarid under Blanket PO#4527 ,(Budget Task# 1.1 -OSP Work Subcontracting) | 223326.4 | 4527 | 0 | BLANKET | Mawarid Electronics Limited Co. (MEL) | SAR | 0 | APPROVED |  |  | 2023-07-18 | 223326.4 | -678 | Abuhammad, Samir | -45803 | -678
105-5 | Fixed network rollout | 8299 | PR For Hayat To Issue Service Order Under Blanket PO-3668 | APPROVED | No | 2025-11-20 | Abas, Mohammed Fekry | 2025-11-25 | 2025-11-29 |  |  | Hayat Service Order-OSP Work (Budget Task#1.1) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45990 | -45990
105-6 | SANG Hospitals-Jeddah Neuro | 149 | SANG Hospitals-Jeddah Neuro-SANG Hospitals-Jeddah Neuro PO#S48E00196 | APPROVED | No | 2021-10-17 | Abas, Mohammed Fekry | 2021-10-18 | 2021-10-18 |  |  |  | 945778.46 | 3851 | 0 | STANDARD | MULTINET COMMUNICATION FZE | SAR | 933645 | APPROVED |  |  | 2021-11-16 | 12133.46 | 29 | Abuhammad, Samir | -44487 | 29
105-6 | SANG Hospitals-Jeddah Neuro | 149 | SANG Hospitals-Jeddah Neuro-SANG Hospitals-Jeddah Neuro PO#S48E00196 | APPROVED | No | 2021-10-17 | Abas, Mohammed Fekry | 2021-10-18 | 2021-10-18 |  |  |  | 55760 | 4097 | 0 | STANDARD | Axis Networks Est | SAR | 55760 | APPROVED |  |  | 2022-05-17 | 0 | 211 | Abuhammad, Samir | -44487 | 211
105-6 | SANG Hospitals-Jeddah Neuro | 366 | SANG Hospitals-Jeddah Neuro-Jeddah data center services | APPROVED | No | 2022-01-05 | Abas, Mohammed Fekry | 2022-01-05 | 2022-01-09 |  |  |  | 23475.7 | 3938 | 0 | STANDARD | Starlink Computer and Networks Company | SAR | 23475.7 | APPROVED |  |  | 2022-01-12 | 0 | 3 | Babic, Marian | -44570 | 3
105-6 | SANG Hospitals-Jeddah Neuro | 389 | SANG Hospitals-Jeddah Neuro- Air freight of materials | APPROVED | No | 2022-01-19 | Abas, Mohammed Fekry | 2022-01-27 | 2022-01-30 |  | 2022-01-25 |  | 15000 | 3989 | 0 | STANDARD | MULTINET COMMUNICATION FZE | SAR | 15000 | APPROVED |  |  | 2022-02-28 | 0 | 29 | Abuhammad, Samir | -44591 | 29
105-6 | SANG Hospitals-Jeddah Neuro | 718 | SANG Hospitals-Jeddah Neuro-SANG Hospitals-Jeddah Neuro-data center - services | RETURNED | No | 2022-07-03 | Abuhammad, Samir | 2024-03-25 | 2022-07-04 | 2024-03-25 |  | Duplicate. | 21300 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44746 | -44746
105-7 | MoH-PMAH | 170 | MoH-PMAH-Installation of power meters for Prince Muhammad Bin Abdulaziz Hospital | APPROVED | No | 2021-10-26 | Abas, Mohammed Fekry | 2021-10-31 | 2021-10-31 |  |  |  | 27000 | 3864 | 0 | STANDARD | Energy Tracks For Contracting | SAR | 27000 | APPROVED |  |  | 2021-11-28 | 0 | 28 | Abuhammad, Samir | -44500 | 28
105-7 | MoH-PMAH | 190 | MoH-PMAH-Design for Energy Recovery in PMAH Hospital - Riyadh | APPROVED | No | 2021-11-16 | Abas, Mohammed Fekry | 2021-11-22 | 2021-11-23 |  |  |  | 30000 | 3884 | 0 | STANDARD | Abdulaziz Mohammad Al Suhaimi For Engineering Consultants Office | SAR | 30000 | APPROVED |  |  | 2021-12-09 | 0 | 16 | Abuhammad, Samir | -44523 | 16
105-7 | MoH-PMAH | 621 | MoH-PMAH-Siemens scope in PMAH | APPROVED | No | 2022-04-26 | Abas, Mohammed Fekry | 2022-04-27 | 2022-04-28 |  |  |  | 1561468 | 4116 | 0 | STANDARD | SIEMENS LIMITED | SAR | 1561468 | APPROVED |  |  | 2022-06-15 | 0 | 48 | Abuhammad, Samir | -44679 | 48
105-7 | MoH-PMAH | 622 | MoH-PMAH-PV- AUS | APPROVED | No | 2022-04-26 | Abas, Mohammed Fekry | 2022-04-27 | 2022-04-28 |  |  |  | 3676200 | 4104 | 0 | STANDARD | Advanced United Systems Ltd. | SAR | 3676200 | APPROVED |  |  | 2022-05-30 | 0 | 32 | Abuhammad, Samir | -44679 | 32
105-7 | MoH-PMAH | 627 | MoH-PMAH-lighting scope in PMAH | APPROVED | No | 2022-04-28 | Abas, Mohammed Fekry | 2022-04-28 | 2022-05-05 |  |  |  | 1050888.9 | 4102 | 0 | STANDARD | Index Lights | SAR | 1050888.9 | APPROVED |  |  | 2022-05-26 | 0 | 21 | Abuhammad, Samir | -44686 | 21
105-7 | MoH-PMAH | 657 | MoH-PMAH-INTEMPUS CSV-LED | APPROVED | No | 2022-05-29 | Abas, Mohammed Fekry | 2022-05-30 | 2022-05-30 |  |  |  | 172627 | 4124 | 0 | STANDARD | Rwazen international company | SAR | 172627 | APPROVED |  |  | 2022-06-30 | 0 | 31 | Abuhammad, Samir | -44711 | 31
105-7 | MoH-PMAH | 665 | MoH-PMAH-Samrt Control Scope in IGH | APPROVED | No | 2022-06-01 | Abas, Mohammed Fekry | 2022-06-07 | 2022-06-12 |  |  |  | 593817 | 4141 | 0 | STANDARD | Smart Controls Systems Contracting Est. | SAR | 593817 | APPROVED |  |  | 2022-08-02 | 0 | 51 | Abuhammad, Samir | -44724 | 51
105-7 | MoH-PMAH | 711 | MoH-PMAH-AC split unit EER abive 13 | APPROVED | No | 2022-06-26 | Abas, Mohammed Fekry | 2022-06-28 | 2022-06-30 |  |  |  | 51200 | 4161 | 0 | STANDARD | DAIKIN AIR CONDITIONING SAUDI ARABIA | SAR | 51200 | APPROVED |  |  | 2022-09-25 | 0 | 87 | Abuhammad, Samir | -44742 | 87
105-7 | MoH-PMAH | 751 | MoH-PMAH-supply of lighting control sensors for Parking in PMAH | APPROVED | No | 2022-07-31 | Abas, Mohammed Fekry | 2022-08-03 | 2022-08-07 |  |  |  | 16920 | 4202 | 0 | STANDARD | Said For Electrical Materials | SAR | 16920 | APPROVED |  |  | 2022-09-06 | 0 | 30 | Abuhammad, Samir | -44780 | 30
105-7 | MoH-PMAH | 790 | MoH-PMAH-Variation order for PO: 4102 ( replacing the 10.5 w with 13 W) | APPROVED | No | 2022-09-05 | Abas, Mohammed Fekry | 2022-09-12 | 2022-09-15 |  |  |  | 23028.6 | 4102 | 1 | STANDARD | Index Lights | SAR | 23028.6 | APPROVED |  |  | 2022-10-18 | 0 | 33 | Abuhammad, Samir | -44819 | 33
105-7 | MoH-PMAH | 793 | MoH-PMAH-Emergency batteries | APPROVED | No | 2022-09-27 | Abas, Mohammed Fekry | 2022-10-02 | 2022-10-03 |  |  |  | 271000 | 4261 | 0 | STANDARD | Lighting Experts and design trading company | SAR | 180000 | APPROVED |  |  | 2022-11-06 | 91000 | 34 | Abuhammad, Samir | -44837 | 34
105-7 | MoH-PMAH | 884 | MoH-PMAH-Variation order for PO 4116 | APPROVED | No | 2022-10-24 | Abas, Mohammed Fekry | 2022-10-31 | 2022-11-01 |  |  |  | 60040 | 4116 | 1 | STANDARD | SIEMENS LIMITED | SAR | 60040 | APPROVED |  |  | 2022-11-30 | 0 | 29 | Abuhammad, Samir | -44866 | 29
105-7 | MoH-PMAH | 891 | MoH-PMAH-Parking lighting control installation | APPROVED | No | 2022-10-26 | Abas, Mohammed Fekry | 2022-10-31 | 2022-11-01 |  |  |  | 100800 | 4265 | 0 | STANDARD | Omed Information Technology for Communicatioms | SAR | 39168 | APPROVED |  |  | 2022-12-08 | 61632 | 37 | Abuhammad, Samir | -44866 | 37
105-7 | MoH-PMAH | 947 | MoH-PMAH-Change order ( PO 4104) | APPROVED | No | 2022-12-08 | Abas, Mohammed Fekry | 2022-12-11 | 2022-12-12 |  |  |  | 115500 | 4104 | 1 | STANDARD | Advanced United Systems Ltd. | SAR | 115500 | APPROVED |  |  | 2023-01-18 | 0 | 37 | Abuhammad, Samir | -44907 | 37
105-7 | MoH-PMAH | 949 | MoH-PMAH-16 split units ( inverter Type) installation in place of 16 AC windows | APPROVED | No | 2022-12-08 | Abas, Mohammed Fekry | 2022-12-11 | 2022-12-12 |  |  |  | 32000 | 4292 | 0 | STANDARD | Omed Information Technology for Communicatioms | SAR | 32000 | APPROVED |  |  | 2022-12-19 | 0 | 7 | Abuhammad, Samir | -44907 | 7
105-7 | MoH-PMAH | 1342 | MoH-PMAH-PV- maintenance contract for 3 years | APPROVED | No | 2023-07-06 | Abas, Mohammed Fekry | 2023-07-26 | 2023-07-27 |  |  |  | 600000 | 4562 | 0 | STANDARD | Advanced United Systems Ltd. | SAR | 600000 | APPROVED |  |  | 2023-09-13 | 0 | 48 | Abuhammad, Samir | -45134 | 48
105-7 | MoH-PMAH | 1431 | MoH-PMAH-PMAH// Siemens Scope of O&M | APPROVED | No | 2023-08-22 | Abas, Mohammed Fekry | 2023-08-24 | 2023-08-24 |  |  |  | 267163 | 4605 | 0 | STANDARD | SIEMENS LIMITED | SAR | 267163 | APPROVED |  |  | 2023-10-04 | 0 | 41 | Abuhammad, Samir | -45162 | 41
105-7 | MoH-PMAH | 1440 | MoH-PMAH-PMAH// Battrey & 2% Stock | APPROVED | No | 2023-08-28 | Abas, Mohammed Fekry | 2023-09-03 | 2023-09-05 |  |  |  | 64796.7 | 4102 | 2 | STANDARD | Index Lights | SAR | 64796.7 | APPROVED |  |  | 2023-09-17 | 0 | 12 | Abuhammad, Samir | -45174 | 12
105-7 | MoH-PMAH | 2808 | MoH-PMAH-Pathway Stairs for PV Installation | APPROVED | No | 2024-03-10 | Abas, Mohammed Fekry | 2024-03-10 | 2024-03-10 |  |  |  | 12078 | 5277 | 0 | STANDARD | Ibrahim Bin Naser Moh. Al-saif Decoretion Est. | SAR | 12078 | APPROVED |  |  | 2024-04-15 | 0 | 36 | Abuhammad, Samir | -45361 | 36
105-7 | MoH-PMAH | 4122 | MoH-PMAH-PMAH - Emergency Battery PR - Budget Line #5 (This PR is created again as per Procurement Request) | APPROVED | No | 2024-08-08 | Abas, Mohammed Fekry | 2024-08-12 | 2024-08-13 |  |  |  | 43500 | 5947 | 0 | STANDARD | Lighting Experts and design trading company | SAR | 36000 | APPROVED |  |  | 2024-08-22 | 7500 | 9 | Abuhammad, Samir | -45517 | 9
105-7 | MoH-PMAH | 4282 | MoH-PMAH-PMAH - Lighting Stock PR - Budget Line #1.1 | APPROVED | No | 2024-08-27 | Abas, Mohammed Fekry | 2024-09-01 | 2024-09-02 |  |  |  | 10500 | 6136 | 0 | STANDARD | Optical Circuit Trading Co | SAR | 10500 | APPROVED |  |  | 2024-09-11 | 0 | 9 | Abuhammad, Samir | -45537 | 9
105-7 | MoH-PMAH | 5760 | MoH-PMAH-PMAH - Emergency Battery PR (O&M) | APPROVED | No | 2025-02-03 | Abas, Mohammed Fekry | 2025-02-06 | 2025-02-09 |  |  |  | 36000 | 6881 | 0 | STANDARD | Lighting Experts and design trading company | SAR | 36000 | APPROVED |  |  | 2025-02-12 | 0 | 3 | Abuhammad, Samir | -45697 | 3
105-9 | 8387-King Salman Park Project | 195 | 8387-King Salman Park Project-Design & Engineering | APPROVED | No | 2021-11-18 | Abas, Mohammed Fekry | 2021-11-18 | 2021-11-21 |  |  |  | 200000 | 3867 | 0 | STANDARD | Fahd Alireza Engineering Consultants | SAR | 200000 | APPROVED |  |  | 2021-11-29 | 0 | 8 | Babic, Marian | -44521 | 8
105-9 | 8387-King Salman Park Project | 251 | 8387-King Salman Park Project-Panels- SCADA/SAS | APPROVED | No | 2021-11-22 | Abas, Mohammed Fekry | 2021-11-22 | 2021-11-24 |  |  |  | 1710236 | 3879 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 1710236 | APPROVED |  |  | 2021-12-01 | 0 | 7 | Babic, Marian | -44524 | 7
105-9 | 8387-King Salman Park Project | 255 | 8387-King Salman Park Project-8387-Communication | APPROVED | No | 2021-11-22 | Abas, Mohammed Fekry | 2021-11-22 | 2021-11-24 |  |  |  | 1570725 | 3874 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 1570725 | APPROVED |  |  | 2021-12-01 | 0 | 7 | Babic, Marian | -44524 | 7
105-9 | 8387-King Salman Park Project | 258 | 8387-King Salman Park Project-8387, Panels-Control | APPROVED | No | 2021-11-22 | Abas, Mohammed Fekry | 2021-11-22 | 2021-11-24 |  |  |  | 280121 | 3879 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 280121 | APPROVED |  |  | 2021-12-01 | 0 | 7 | Babic, Marian | -44524 | 7
105-9 | 8387-King Salman Park Project | 261 | 8387-King Salman Park Project-8387-Panels-Protection | APPROVED | No | 2021-11-22 | Abas, Mohammed Fekry | 2021-11-22 | 2021-11-24 |  |  |  | 2275675 | 3879 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 2275675 | APPROVED |  |  | 2021-12-01 | 0 | 7 | Babic, Marian | -44524 | 7
105-9 | 8387-King Salman Park Project | 277 | 8387-King Salman Park Project-8387-Geo technical Investigation | APPROVED | No | 2021-11-23 | Abas, Mohammed Fekry | 2021-11-24 | 2021-11-28 |  |  |  | 25000 | 3916 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 15730 | APPROVED |  |  | 2021-12-22 | 9270 | 24 | Babic, Marian | -44528 | 24
105-9 | 8387-King Salman Park Project | 291 | 8387-King Salman Park Project-Capacitor bank 13.8kV, 7 MVAR | APPROVED | No | 2021-12-01 | Abas, Mohammed Fekry | 2021-12-05 | 2021-12-06 |  |  |  | 750000 | 3971 | 0 | STANDARD | EATON (COOPER POWER SYSTEMS) | USD | 736218.75 | APPROVED |  |  | 2022-03-09 | 13781.25 | 93 | Babic, Marian | -44536 | 93
105-9 | 8387-King Salman Park Project | 393 | 8387-King Salman Park Project-8387- 67MVA Power Transformer | APPROVED | No | 2022-01-19 | Abas, Mohammed Fekry | 2022-01-20 | 2022-01-20 |  |  |  | 8716087.5 | 4249 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 8716087.5 | APPROVED |  |  | 2022-10-20 | 0 | 273 | Babic, Marian | -44581 | 273
105-9 | 8387-King Salman Park Project | 396 | 8387-King Salman Park Project-8387- Porta cabins for site office | APPROVED | No | 2022-01-19 | Abas, Mohammed Fekry | 2022-01-23 | 2022-01-23 |  |  |  | 345150 | 3978 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 340000 | APPROVED |  |  | 2022-03-17 | 5150 | 53 | AlQuraish, Sajjad Hazem | -44584 | 53
105-9 | 8387-King Salman Park Project | 396 | 8387-King Salman Park Project-8387- Porta cabins for site office | APPROVED | No | 2022-01-19 | Abas, Mohammed Fekry | 2022-01-23 | 2022-01-23 |  |  |  | 345150 | 3978 | 2 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 340000 | APPROVED |  |  | 2023-01-10 | 5150 | 352 | Babic, Marian | -44584 | 352
105-9 | 8387-King Salman Park Project | 397 | 8387-King Salman Park Project-8387- 132kV GIS Service & CIF | APPROVED | No | 2022-01-19 | Abas, Mohammed Fekry | 2022-01-30 | 2022-01-31 |  |  | kindly Wait for the other PR that including test pushing as per Safdar comment, as Both PR will be issued in one PO. | 974737.5 | 4030 | 0 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 974749.68 | APPROVED |  |  | 2022-03-09 | -12.18 | 37 | Babic, Marian | -44592 | 37
105-9 | 8387-King Salman Park Project | 398 | 8387-King Salman Park Project-8387- 67MVA Power transformer Service & CIF | APPROVED | No | 2022-01-19 | Abas, Mohammed Fekry | 2022-01-20 | 2022-01-20 |  |  |  | 691162.5 | 4249 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 691162.5 | APPROVED |  |  | 2022-10-20 | 0 | 273 | Babic, Marian | -44581 | 273
105-9 | 8387-King Salman Park Project | 416 | 8387-King Salman Park Project-8387 - 13.8kV NGR | APPROVED | No | 2022-01-24 | Abas, Mohammed Fekry | 2022-01-25 | 2022-01-26 |  |  |  | 75000 | 4018 | 0 | STANDARD | National Switchgears | USD | 63562.2 | APPROVED |  |  | 2022-03-17 | 11437.8 | 50 | AlQuraish, Sajjad Hazem | -44587 | 50
105-9 | 8387-King Salman Park Project | 420 | 8387-King Salman Park Project-8387- 132kV Surge arresters | APPROVED | No | 2022-01-24 | Abas, Mohammed Fekry | 2022-01-25 | 2022-01-26 |  |  |  | 51000 | 4000 | 0 | STANDARD | 2100698 Siemens Energy Global GmbH & Co. KG | EUR | 50991.52 | APPROVED |  |  | 2022-03-08 | 8.48 | 41 | AlQuraish, Sajjad Hazem | -44587 | 41
105-9 | 8387-King Salman Park Project | 428 | 8387-King Salman Park Project-8387- 13.8kV MV Switchgear panels | APPROVED | No | 2022-01-24 | Abas, Mohammed Fekry | 2022-01-25 | 2022-01-26 |  |  |  | 5750000 | 3960 | 0 | STANDARD | ALFANAR CO | SAR | 5700000 | APPROVED |  |  | 2022-02-06 | 50000 | 11 | Babic, Marian | -44587 | 11
105-9 | 8387-King Salman Park Project | 445 | 8387-King Salman Park Project-8387- 13.8kV RMU | APPROVED | No | 2022-01-31 | Abas, Mohammed Fekry | 2022-02-02 | 2022-02-02 |  |  |  | 150000 | 3982 | 0 | STANDARD | ALFANAR CO | SAR | 58000 | APPROVED |  |  | 2022-09-05 | 92000 | 215 | Babic, Marian | -44594 | 215
105-9 | 8387-King Salman Park Project | 477 | 8387-King Salman Park Project-8387- Battery & Battery Charger | APPROVED | No | 2022-02-13 | Abas, Mohammed Fekry | 2022-02-13 | 2022-02-13 |  |  |  | 478250 | 4128 | 0 | STANDARD | Alassas Specialized Company Ltd | SAR | 459600 | APPROVED |  |  | 2022-06-22 | 18650 | 129 | Babic, Marian | -44605 | 129
105-9 | 8387-King Salman Park Project | 494 | 8387-King Salman Park Project-8387- Civil & Structural Works | APPROVED | No | 2022-02-20 | Abas, Mohammed Fekry | 2022-02-27 | 2022-02-27 |  |  |  | 7414270 | 4173 | 0 | STANDARD | Inshat Al Awtan General Contracting Co | SAR | 6400000 | APPROVED |  |  | 2022-08-08 | 1014270 | 162 | Babic, Marian | -44619 | 162
105-9 | 8387-King Salman Park Project | 494 | 8387-King Salman Park Project-8387- Civil & Structural Works | APPROVED | No | 2022-02-20 | Abas, Mohammed Fekry | 2022-02-27 | 2022-02-27 |  |  |  | 7414270 | 4173 | 1 | STANDARD | Inshat Al Awtan General Contracting Co | SAR | 640000 | APPROVED |  |  | 2024-03-13 | 6774270 | 745 | Babic, Marian | -44619 | 745
105-9 | 8387-King Salman Park Project | 496 | 8387-King Salman Park Project-8387- SIS (Solid Insulated system) | APPROVED | No | 2022-02-22 | Abas, Mohammed Fekry | 2022-02-27 | 2022-02-27 |  |  |  | 1935759.38 | 4158 | 0 | STANDARD | RITZ INSTRUMENT TRANSFORMERS GMBH | EUR | 1800706.4 | APPROVED |  |  | 2022-08-08 | 135052.98 | 162 | Babic, Marian | -44619 | 162
105-9 | 8387-King Salman Park Project | 498 | 8387-King Salman Park Project-8387- 132kV GIS and Extension GIS for 8164 & 8219 | APPROVED | No | 2022-02-22 | Abas, Mohammed Fekry | 2022-02-27 | 2022-02-27 |  |  |  | 11817712.5 | 4030 | 0 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 11817712.5 | APPROVED |  |  | 2022-03-09 | 0 | 10 | Babic, Marian | -44619 | 10
105-9 | 8387-King Salman Park Project | 500 | 8387-King Salman Park Project-8387-Site Mobilization and fencing activities. | APPROVED | No | 2022-02-23 | Abas, Mohammed Fekry | 2022-02-27 | 2022-02-27 |  |  |  | 265000 | 4035 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 159664.5 | APPROVED |  |  | 2022-03-31 | 105335.5 | 32 | AlQuraish, Sajjad Hazem | -44619 | 32
105-9 | 8387-King Salman Park Project | 512 | 8387-King Salman Park Project-8387- Overhead electrical single girder crane complete with accessories | APPROVED | No | 2022-02-28 | Abas, Mohammed Fekry | 2022-03-07 | 2022-03-08 |  |  |  | 160000 | 4168 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 130350 | APPROVED |  |  | 2022-08-04 | 29650 | 149 | Babic, Marian | -44628 | 149
105-9 | 8387-King Salman Park Project | 531 | 8387-King Salman Park Project-8387-Outdoor AMI CT for Auxiliary Transformer details | APPROVED | No | 2022-03-07 | Abas, Mohammed Fekry | 2022-03-07 | 2022-03-08 |  |  |  | 100000 | 4218 | 0 | STANDARD | ELEQ B.V. | EUR | 85768.08 | APPROVED |  |  | 2022-09-11 | 14231.92 | 187 | Babic, Marian | -44628 | 187
105-9 | 8387-King Salman Park Project | 633 | 8387-King Salman Park Project-Auxiliary Transformer for 8387 | APPROVED | No | 2022-05-11 | Abas, Mohammed Fekry | 2022-05-15 | 2022-05-22 |  |  |  | 100000 | 4175 | 0 | STANDARD | ALFANAR CO | SAR | 100000 | APPROVED |  |  | 2022-09-12 | 0 | 113 | Babic, Marian | -44703 | 113
105-9 | 8387-King Salman Park Project | 638 | 8387-King Salman Park Project-Service vehicle for Company(SEC) Project Staff | RETURNED | No | 2022-05-12 | Babic, Marian | 2024-04-15 | 2022-05-16 | 2024-04-15 |  | this was not purchased through PO | 165000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44697 | -44697
105-9 | 8387-King Salman Park Project | 644 | 8387-King Salman Park Project-ACDB,DCBD & sub panles | APPROVED | No | 2022-05-22 | Abas, Mohammed Fekry | 2022-05-23 | 2022-05-23 |  |  |  | 600000 | 4182 | 0 | STANDARD | ALFANAR CO | SAR | 600000 | APPROVED |  |  | 2022-08-21 | 0 | 90 | Babic, Marian | -44704 | 90
105-9 | 8387-King Salman Park Project | 676 | 8387-King Salman Park Project-Window/split/Freestanding AC's for Site for 8387 & 8388 S/S | APPROVED | No | 2022-06-04 | Abas, Mohammed Fekry | 2022-07-21 | 2022-07-24 |  |  |  | 48400 | 4193 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 29881.94 | APPROVED |  |  | 2022-08-29 | 18518.06 | 36 | Babic, Marian | -44766 | 36
105-9 | 8387-King Salman Park Project | 771 | 8387-King Salman Park Project-150sqmm, Soft annealed copper conductor ,Round Non compacted | APPROVED | No | 2022-08-25 | Abas, Mohammed Fekry | 2022-08-30 | 2022-08-30 |  |  |  | 188726.38 | 4205 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 183726.37 | APPROVED |  |  | 2022-09-06 | 5000.01 | 7 | Babic, Marian | -44803 | 7
105-9 | 8387-King Salman Park Project | 791 | 8387-King Salman Park Project-Diesel generator with fuel tank and transportation charges | APPROVED | No | 2022-09-05 | Abas, Mohammed Fekry | 2022-09-05 | 2022-09-06 |  |  |  | 59000 | 4264 | 0 | STANDARD | SUDHIR EQUIPMENT RENTAL COMPANY | SAR | 59000 | APPROVED |  |  | 2022-11-09 | 0 | 64 | Babic, Marian | -44810 | 64
105-9 | 8387-King Salman Park Project | 795 | 8387-King Salman Park Project-Surge arrester TPI PR for 8387 SS | APPROVED | No | 2022-09-07 | Abas, Mohammed Fekry | 2022-09-11 | 2022-09-11 |  |  |  | 1250 | 4224 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 2250 | APPROVED |  |  | 2022-09-13 | -1000 | 2 | Babic, Marian | -44815 | 2
105-9 | 8387-King Salman Park Project | 799 | 8387-King Salman Park Project-132kV GIS TPI PR for 8387 SS | APPROVED | No | 2022-09-07 | Abas, Mohammed Fekry | 2022-09-11 | 2022-09-11 |  |  |  | 3800 | 4225 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 3675 | APPROVED |  |  | 2022-09-19 | 125 | 8 | Babic, Marian | -44815 | 8
105-9 | 8387-King Salman Park Project | 803 | 8387-King Salman Park Project-NGR TPI PR for 8387 SS | APPROVED | No | 2022-09-07 | Abas, Mohammed Fekry | 2022-09-11 | 2022-09-11 |  |  |  | 750 | 4226 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 731.25 | APPROVED |  |  | 2022-09-15 | 18.75 | 4 | Babic, Marian | -44815 | 4
105-9 | 8387-King Salman Park Project | 823 | 8387-King Salman Park Project-Security Systems-8387 SS | APPROVED | No | 2022-09-13 | Abas, Mohammed Fekry | 2022-09-13 | 2022-09-18 |  |  |  | 650000 | 4300 | 0 | STANDARD | Equipment & Technical Services Co.(ETECHS) | SAR | 500000 | APPROVED |  |  | 2023-01-26 | 150000 | 130 | Babic, Marian | -44822 | 130
105-9 | 8387-King Salman Park Project | 827 | 8387-King Salman Park Project-Deisel Supply for 8387 SS | APPROVED | No | 2022-09-13 | Abas, Mohammed Fekry | 2022-09-13 | 2022-09-14 |  |  |  | 21603.56 | 4232 | 0 | STANDARD | Othman Hammoud Al-Zaydi Est | SAR | 21603 | APPROVED |  |  | 2022-09-20 | 0.56 | 6 | Abuhammad, Samir | -44818 | 6
105-9 | 8387-King Salman Park Project | 832 | 8387-King Salman Park Project-HVAC system -8387 SS | APPROVED | No | 2022-09-14 | Abas, Mohammed Fekry | 2022-09-18 | 2022-09-25 |  |  |  | 1500000 | 4239 | 0 | STANDARD | Ramz Alataa Company for Trading | SAR | 1500000 | APPROVED |  |  | 2022-10-04 | 0 | 9 | Babic, Marian | -44829 | 9
105-9 | 8387-King Salman Park Project | 844 | 8387-King Salman Park Project-Addtional cost 132kV GIS as per change order-4 | APPROVED | No | 2022-09-17 | Abas, Mohammed Fekry | 2022-09-18 | 2022-09-20 |  |  |  | 375000 | 4030 | 1 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 375000 | APPROVED |  |  | 2022-10-04 | 0 | 14 | Babic, Marian | -44824 | 14
105-9 | 8387-King Salman Park Project | 862 | 8387-King Salman Park Project-Additional cost for Power transformers | APPROVED | No | 2022-10-05 | Abas, Mohammed Fekry | 2022-10-10 | 2022-10-10 |  |  |  | 1945110.04 | 4249 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 1945110 | APPROVED |  |  | 2022-10-20 | 0.04 | 10 | Babic, Marian | -44844 | 10
105-9 | 8387-King Salman Park Project | 866 | 8387-King Salman Park Project-Y/G Cables | RETURNED | No | 2022-10-06 | Babic, Marian | 2023-01-26 | 2022-10-10 | 2023-01-26 |  | Please revise the unit price to be 74.90 SAR (length 305m) | 142903.19 | 4209 | 0 | STANDARD | ALFANAR CO | SAR | 67610 | APPROVED |  |  | 2022-10-17 | 75293.19 |  | Babic, Marian | -44844 | 7
105-9 | 8387-King Salman Park Project | 866 | 8387-King Salman Park Project-Y/G Cables | RETURNED | No | 2022-10-06 | Babic, Marian | 2023-01-26 | 2022-10-10 | 2023-01-26 |  | Please revise the unit price to be 74.90 SAR (length 305m) | 112721.5 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44844 | -44844
105-9 | 8387-King Salman Park Project | 886 | 8387-King Salman Park Project-Earthing materials for 8387 SS | APPROVED | No | 2022-10-25 | Abas, Mohammed Fekry | 2022-10-31 | 2022-11-01 |  |  |  | 52932 | 4267 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 52932 | APPROVED |  |  | 2022-11-15 | 0 | 14 | Babic, Marian | -44866 | 14
105-9 | 8387-King Salman Park Project | 887 | 8387-King Salman Park Project- Earthing materials-part-2, Exothermic weld powder | APPROVED | No | 2022-10-27 | Abas, Mohammed Fekry | 2022-10-31 | 2022-11-01 |  |  |  | 30131 | 4267 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 30131 | APPROVED |  |  | 2022-11-15 | 0 | 14 | Babic, Marian | -44866 | 14
105-9 | 8387-King Salman Park Project | 888 | 8387-King Salman Park Project-Earthing Materilas part-3 | APPROVED | No | 2022-10-25 | Abas, Mohammed Fekry | 2022-10-31 | 2022-11-01 |  |  |  | 32575.5 | 4267 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 32575.5 | APPROVED |  |  | 2022-11-15 | 0 | 14 | Babic, Marian | -44866 | 14
105-9 | 8387-King Salman Park Project | 913 | 8387-King Salman Park Project-TPI for Power Transformer in 8387 SS | APPROVED | No | 2022-11-16 | Abas, Mohammed Fekry | 2022-11-17 | 2022-11-17 |  |  |  | 14300 | 4280 | 0 | STANDARD | VELOSI SAUDI ARABIA CO LTD | SAR | 14300 | APPROVED |  |  | 2022-11-28 | 0 | 11 | Babic, Marian | -44882 | 11
105-9 | 8387-King Salman Park Project | 937 | 8387-King Salman Park Project-DC-DC converter TPI | APPROVED | No | 2022-12-06 | Abas, Mohammed Fekry | 2022-12-12 | 2022-12-12 |  |  |  | 9150 | 4293 | 0 | STANDARD | SGS GULF LIMITED | USD | 4500 | APPROVED |  |  | 2022-12-19 | 4650 | 7 | Babic, Marian | -44907 | 7
105-9 | 8387-King Salman Park Project | 1015 | 8387-King Salman Park Project-Cable Y/G 1x240mm2- 8387 SS | APPROVED | No | 2023-01-24 | Abas, Mohammed Fekry | 2023-01-24 | 2023-01-25 |  |  |  | 15548.5 | 4209 | 1 | STANDARD | ALFANAR CO | SAR | 15475.75 | APPROVED |  |  | 2023-02-06 | 72.75 | 12 | Babic, Marian | -44951 | 12
105-9 | 8387-King Salman Park Project | 1027 | 8387-King Salman Park Project-Cable Y/G 1x240mm2- 8387 SS(2) | APPROVED | No | 2023-01-30 | Abas, Mohammed Fekry | 2023-02-02 | 2023-02-02 |  |  |  | 22844.5 | 4209 | 1 | STANDARD | ALFANAR CO | SAR | 22844.5 | APPROVED |  |  | 2023-02-06 | 0 | 4 | Babic, Marian | -44959 | 4
105-9 | 8387-King Salman Park Project | 1073 | 8387-King Salman Park Project-OH Crane TPI- 8387 SS | APPROVED | No | 2023-02-14 | Abas, Mohammed Fekry | 2023-02-15 | 2023-02-16 |  |  |  | 800 | 4352 | 0 | STANDARD | SGS INSPECTION SERVICES SA. LTD | SAR | 800 | APPROVED |  |  | 2023-02-26 | 0 | 10 | Babic, Marian | -44973 | 10
105-9 | 8387-King Salman Park Project | 1075 | 8387-King Salman Park Project-TPI for Bare copper conductor- 8387 SS | APPROVED | No | 2023-02-16 | Abas, Mohammed Fekry | 2023-02-19 | 2023-02-20 |  |  |  | 467 | 4357 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 466.67 | APPROVED |  |  | 2023-03-05 | 0.33 | 13 | Babic, Marian | -44977 | 13
105-9 | 8387-King Salman Park Project | 1118 | 8387-King Salman Park Project-Protection and Control System TPI 8387 | APPROVED | No | 2023-03-09 | Abas, Mohammed Fekry | 2023-03-13 | 2023-03-13 |  |  |  | 7000 | 4382 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 7000 | APPROVED |  |  | 2023-03-21 | 0 | 8 | Babic, Marian | -44998 | 8
105-9 | 8387-King Salman Park Project | 1145 | 8387-King Salman Park Project-Power Transformer's Offloading -8387 SS | APPROVED | No | 2023-03-22 | Abas, Mohammed Fekry | 2023-03-27 | 2023-03-28 |  |  |  | 50000 | 4434 | 0 | STANDARD | MOHAMMED HAMAD AL-AHMADE FOR TRADING AND CONSTRACTION | SAR | 30000 | APPROVED |  |  | 2023-05-03 | 20000 | 36 | Abuhammad, Samir | -45013 | 36
105-9 | 8387-King Salman Park Project | 1147 | 8387-King Salman Park Project-OH Crane TPI-8387 SS | APPROVED | No | 2023-03-27 | Abas, Mohammed Fekry | 2023-03-28 | 2023-03-30 |  |  |  | 1600 | 4352 | 1 | STANDARD | SGS INSPECTION SERVICES SA. LTD | SAR | 800 | APPROVED |  |  | 2023-04-06 | 800 | 7 | Babic, Marian | -45015 | 7
105-9 | 8387-King Salman Park Project | 1201 | 8387-King Salman Park Project-TELECOMMUNICATION EQUIPMENT (MPLS,DVM,MDF,DDF) and LAN TPI | APPROVED | No | 2023-04-18 | Abas, Mohammed Fekry | 2023-04-22 | 2023-04-30 |  |  |  | 1400 | 4440 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 4200 | APPROVED |  |  | 2023-05-21 | -2800 | 21 | Eranhikkal, Mr. Riyaz Mohammed | -45046 | 21
105-9 | 8387-King Salman Park Project | 1213 | 8387-King Salman Park Project-SAS TPI- 8387 SS | APPROVED | No | 2023-04-20 | Abas, Mohammed Fekry | 2023-04-22 | 2023-04-30 |  |  |  | 9375 | 4450 | 0 | STANDARD | Bureau Veritas Branch Saudi Arabia | SAR | 9375 | APPROVED |  |  | 2023-05-21 | 0 | 21 | Babic, Marian | -45046 | 21
105-9 | 8387-King Salman Park Project | 1220 | 8387-King Salman Park Project-(25M)LIGHTNING MAST (LCLM)with accessories-8387 SS | APPROVED | No | 2023-05-01 | Abas, Mohammed Fekry | 2023-05-03 | 2023-05-08 |  |  |  | 58320 | 4484 | 0 | STANDARD | Hesham El-Sewedy Trading Co. LTD. | SAR | 58320 | APPROVED |  |  | 2023-07-19 | 0 | 72 | Babic, Marian | -45054 | 72
105-9 | 8387-King Salman Park Project | 1250 | 8387-King Salman Park Project-Services-Installation and configuration-8387 SS | APPROVED | No | 2023-05-11 | Abas, Mohammed Fekry | 2023-05-15 | 2023-05-15 |  |  |  | 1343800 | 5213 | 0 | STANDARD | Hussain Ali Hussain Contracting Company | SAR | 1343800 | APPROVED |  |  | 2024-03-18 | 0 | 308 | Babic, Marian | -45061 | 308
105-9 | 8387-King Salman Park Project | 1283 | 8387-King Salman Park Project-Power Transformer Oil filteration- 8387 SS | APPROVED | No | 2023-05-25 | Abas, Mohammed Fekry | 2023-05-28 | 2023-05-28 |  |  |  | 100000 | 4550 | 0 | STANDARD | Al-Handasah Al-Namuudhajyyah Contracting Company | SAR | 57000 | APPROVED |  |  | 2023-07-27 | 43000 | 60 | Babic, Marian | -45074 | 60
105-9 | 8387-King Salman Park Project | 1296 | 8387-King Salman Park Project-TPI MV switchgear 8387 & 8388 SS | RETURNED | No | 2023-05-30 | Babic, Marian | 2023-07-25 | 2023-06-04 | 2023-07-25 |  | This PR was removed from PO 4297 as it was from the wrong project. | 1500 | 4297 | 1 | STANDARD | INTERTEK SAUDI ARABIA LTD | SAR | 1500 | APPROVED |  |  | 2023-06-07 | 0 |  | Babic, Marian | -45081 | 3
105-9 | 8387-King Salman Park Project | 1296 | 8387-King Salman Park Project-TPI MV switchgear 8387 & 8388 SS | RETURNED | No | 2023-05-30 | Babic, Marian | 2023-07-25 | 2023-06-04 | 2023-07-25 |  | This PR was removed from PO 4297 as it was from the wrong project. | 1500 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45081 | -45081
105-9 | 8387-King Salman Park Project | 1377 | 8387-King Salman Park Project-TPI (AC-DC Panels # SS 8387, 8388 & 8390) under 8387 Budget | APPROVED | No | 2023-07-31 | Abas, Mohammed Fekry | 2023-08-01 | 2023-08-01 |  |  |  | 5400 | 4558 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | SAR | 5400 | APPROVED |  |  | 2023-08-06 | 0 | 5 | Babic, Marian | -45139 | 5
105-9 | 8387-King Salman Park Project | 1410 | 8387-King Salman Park Project-TPI (FAT) 132 KV GIS Adaptor for 8219 & 8164 SS (Remote Ends of 8387) | APPROVED | No | 2023-08-14 | Abas, Mohammed Fekry | 2023-08-20 | 2023-08-20 |  |  |  | 13200 | 4582 | 0 | STANDARD | Bureau Veritas Branch Saudi Arabia | SAR | 13200 | APPROVED |  |  | 2023-08-28 | 0 | 8 | Babic, Marian | -45158 | 8
105-9 | 8387-King Salman Park Project | 1417 | 8387-King Salman Park Project-wire | REJECTED | No | 2023-08-16 | Almehmadi, Fahed | 2023-08-16 |  |  | 2023-08-16 |  | 12846600 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-9 | 8387-King Salman Park Project | 1418 | 8387-King Salman Park Project-THHN Wires (Lighting Cables) SS # 8387 | APPROVED | No | 2023-08-17 | Abas, Mohammed Fekry | 2023-08-20 | 2023-08-20 |  |  |  | 21000 | 4583 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 20930 | APPROVED |  |  | 2023-08-30 | 70 | 10 | Babic, Marian | -45158 | 10
105-9 | 8387-King Salman Park Project | 1418 | 8387-King Salman Park Project-THHN Wires (Lighting Cables) SS # 8387 | APPROVED | No | 2023-08-17 | Abas, Mohammed Fekry | 2023-08-20 | 2023-08-20 |  |  |  | 21000 | 4825 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 21000 | APPROVED |  |  | 2023-12-31 | 0 | 133 | Babic, Marian | -45158 | 133
105-9 | 8387-King Salman Park Project | 1422 | 8387-King Salman Park Project-Lighting Fixtures (indoor - outdoor) - Nardeen for SS # 8387 | REJECTED | No | 2023-08-21 | Almehmadi, Fahed | 2023-08-21 |  |  | 2023-08-21 |  | 39491.6 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-9 | 8387-King Salman Park Project | 1423 | 8387-King Salman Park Project-Lighting Fixtures (indoor - outdoor) - Nardeen for SS # 8387 | APPROVED | No | 2023-08-21 | Abas, Mohammed Fekry | 2023-08-24 | 2023-08-24 |  |  |  | 39491.6 | 4697 | 0 | STANDARD | Nardeen Lighting Company Ltd. | SAR | 39491.6 | APPROVED |  |  | 2023-11-07 | 0 | 75 | Babic, Marian | -45162 | 75
105-9 | 8387-King Salman Park Project | 1425 | 8387-King Salman Park Project-Lighting Fixtures (indoor - outdoor) - Nardeen for SS # 8387 | APPROVED | No | 2023-08-22 | Abas, Mohammed Fekry | 2023-08-24 | 2023-08-24 |  |  |  | 20871 | 4697 | 0 | STANDARD | Nardeen Lighting Company Ltd. | SAR | 20871 | APPROVED |  |  | 2023-11-07 | 0 | 75 | Babic, Marian | -45162 | 75
105-9 | 8387-King Salman Park Project | 1426 | 8387-King Salman Park Project-TPI for SIS System FAT (SS 8387) SGS | APPROVED | No | 2023-08-22 | Abas, Mohammed Fekry | 2023-08-24 | 2023-08-24 |  |  |  | 6375 | 4599 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | SAR | 6225 | APPROVED |  |  | 2023-09-12 | 150 | 19 | Babic, Marian | -45162 | 19
105-9 | 8387-King Salman Park Project | 1588 | 8387-King Salman Park Project-TPI Inspection for DDC Panels for SS 8387 | APPROVED | No | 2023-10-12 | Abas, Mohammed Fekry | 2023-10-17 | 2023-10-17 |  |  |  | 2000 | 4669 | 0 | STANDARD | Atlas Support and Services | SAR | 2000 | APPROVED |  |  | 2023-10-29 | 0 | 12 | Babic, Marian | -45216 | 12
105-9 | 8387-King Salman Park Project | 1605 | 8387-King Salman Park Project-TPI for SIS System FAT (SS 8387) (Lot-2) | RETURNED | No | 2023-10-17 | Babic, Marian | 2023-11-01 | 2023-10-23 | 2023-11-01 |  | Please referer to the blank agreement signed with Intertek | 6225 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45222 | -45222
105-9 | 8387-King Salman Park Project | 1617 | 8387-King Salman Park Project-Third Party FAT (Control & Protection) SS 8387 (all 4 SS balance panels) | RETURNED | No | 2023-10-21 | Babic, Marian | 2024-03-26 | 2023-10-23 | 2024-03-26 |  | old PR, not required | 5800 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45222 | -45222
105-9 | 8387-King Salman Park Project | 1684 | 8387-King Salman Park Project-Lighting Pole | APPROVED | No | 2023-11-12 | Abas, Mohammed Fekry | 2023-11-14 | 2023-11-15 |  |  |  | 12080 | 4804 | 0 | STANDARD | Hesham El-Sewedy Trading Co. LTD. | SAR | 12080 | APPROVED |  |  | 2023-12-14 | 0 | 29 | Babic, Marian | -45245 | 29
105-9 | 8387-King Salman Park Project | 1685 | 8387-King Salman Park Project-RGS Conduits and Accessories (Lighting works) 8387 | RETURNED | No | 2023-11-12 | Babic, Marian | 2024-03-26 | 2023-11-14 | 2024-03-26 |  | PO for this subject already issued, this PR is a balance which is not needed | 53958 | 4790 | 0 | STANDARD | ELECTRIC HOUSE EST. | SAR | 20076.6 | APPROVED |  |  | 2023-12-10 | 33881.4 |  | Babic, Marian | -45244 | 26
105-9 | 8387-King Salman Park Project | 1685 | 8387-King Salman Park Project-RGS Conduits and Accessories (Lighting works) 8387 | RETURNED | No | 2023-11-12 | Babic, Marian | 2024-03-26 | 2023-11-14 | 2024-03-26 |  | PO for this subject already issued, this PR is a balance which is not needed | 810.88 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45244 | -45244
105-9 | 8387-King Salman Park Project | 1786 | 8387-King Salman Park Project-POWER RECEPTACLE FOR 8387 (Budget Item # 1.21) | APPROVED | No | 2023-11-19 | Abas, Mohammed Fekry | 2023-11-22 | 2023-11-22 |  |  |  | 78410 | 4875 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 60265 | APPROVED |  |  | 2023-12-31 | 18145 | 39 | Babic, Marian | -45252 | 39
105-9 | 8387-King Salman Park Project | 1822 | 8387-King Salman Park Project-Service of C1/C2 holder for 8387 remote end - 8164 & 8219 ( budget line item 1.36) | APPROVED | No | 2023-11-27 | Abas, Mohammed Fekry | 2023-11-30 | 2023-11-30 |  |  |  | 136000 | 4830 | 0 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 134200 | APPROVED |  |  | 2024-01-01 | 1800 | 32 | Babic, Marian | -45260 | 32
105-9 | 8387-King Salman Park Project | 1888 | 8387-King Salman Park Project-TPI SIS (SS 8387) / Additional 2 days to cover Lot-2 FAT / Budget Line item 1.29 | APPROVED | No | 2023-12-04 | Abas, Mohammed Fekry | 2023-12-06 | 2023-12-07 |  |  |  | 6225 | 4599 | 1 | STANDARD | INTERTEK SAUDI ARABIA LTD | SAR | 6225 | APPROVED |  |  | 2023-12-21 | 0 | 14 | Babic, Marian | -45267 | 14
105-9 | 8387-King Salman Park Project | 1913 | 8387-King Salman Park Project-TPI 132 KV GIS Adaptor for 8219 & 8164 SS (8387) / Additional 2 days to cover Weekends / Budget Line item 1.29 | APPROVED | No | 2023-12-06 | Abas, Mohammed Fekry | 2023-12-07 | 2023-12-10 |  |  |  | 3300 | 4582 | 1 | STANDARD | Bureau Veritas Branch Saudi Arabia | SAR | 3300 | APPROVED |  |  | 2023-12-21 | 0 | 11 | Babic, Marian | -45270 | 11
105-9 | 8387-King Salman Park Project | 2555 | 8387-King Salman Park Project-Supply of diesel supply for King Salman PArk Projects | APPROVED | No | 2024-02-13 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-18 |  |  |  | 77180.56 | 4232 | 1 | STANDARD | Othman Hammoud Al-Zaydi Est | SAR | 77180.56 | APPROVED |  |  | 2024-03-13 | 0 | 24 | Babic, Marian | -45340 | 24
105-9 | 8387-King Salman Park Project | 2608 | 8387-King Salman Park Project-ACSR Connectors ( Budget Line Item 1.26) | APPROVED | No | 2024-02-19 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 4752.3 | 5152 | 0 | STANDARD | Arruti Subestaciones , S.A.U | EUR | 4748.54 | APPROVED |  |  | 2024-03-11 | 3.76 | 14 | Babic, Marian | -45348 | 14
105-9 | 8387-King Salman Park Project | 2631 | 8387-King Salman Park Project- Fire Stop material ( Budget Line Item 1.19) | APPROVED | No | 2024-02-20 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 91980 | 5169 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 81960 | APPROVED |  |  | 2024-03-14 | 10020 | 17 | Babic, Marian | -45348 | 17
105-9 | 8387-King Salman Park Project | 2634 | 8387-King Salman Park Project-PDS System for SS 8387 | APPROVED | No | 2024-02-20 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 160000 | 5162 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 155500 | APPROVED |  |  | 2024-03-18 | 4500 | 21 | Babic, Marian | -45348 | 21
105-9 | 8387-King Salman Park Project | 2638 | 8387-King Salman Park Project-Installation of Capacitor Banks on Civil Foundation (Budget Line item 1.19) | APPROVED | No | 2024-02-21 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 30000 | 5167 | 0 | STANDARD | YASIR M ALI AL-ZAHRANI EST. | SAR | 30000 | APPROVED |  |  | 2024-03-12 | 0 | 15 | Babic, Marian | -45348 | 15
105-9 | 8387-King Salman Park Project | 2664 | 8387-King Salman Park Project-Lighitng Installation works for S/S 8387 (Budget Line item # 1.34) | APPROVED | No | 2024-02-25 | Abas, Mohammed Fekry | 2024-02-27 | 2024-02-28 |  |  |  | 200000 | 5213 | 0 | STANDARD | Hussain Ali Hussain Contracting Company | SAR | 200000 | APPROVED |  |  | 2024-03-18 | 0 | 19 | Babic, Marian | -45350 | 19
105-9 | 8387-King Salman Park Project | 2672 | 8387-King Salman Park Project-Testing & Commissioning Services for SS 8387 (Budget Line item # 1.36) | APPROVED | No | 2024-02-25 | Abas, Mohammed Fekry | 2024-02-27 | 2024-02-28 |  |  |  | 2527322 | 5205 | 0 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 2082032 | APPROVED |  |  | 2024-05-19 | 445290 | 81 | Babic, Marian | -45350 | 81
105-9 | 8387-King Salman Park Project | 2688 | 8387-King Salman Park Project-Rental Manpower for S/S # 8387 (Budget Line item 1.50) | APPROVED | No | 2024-02-26 | Abas, Mohammed Fekry | 2024-02-29 | 2024-03-03 |  |  |  | 320580 | 5146 | 0 | STANDARD | Jasem M.AlJasem Contracting Est. | SAR | 319696 | APPROVED |  |  | 2024-05-05 | 884 | 63 | Babic, Marian | -45354 | 63
105-9 | 8387-King Salman Park Project | 2697 | 8387-King Salman Park Project-Third party Testing for Precast Boundary Wall (Budget Item # 1.29) | APPROVED | No | 2024-02-26 | Abas, Mohammed Fekry | 2024-02-29 | 2024-03-03 |  |  |  | 30000 | 5249 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 30000 | APPROVED |  |  | 2024-03-26 | 0 | 23 | Babic, Marian | -45354 | 23
105-9 | 8387-King Salman Park Project | 2724 | 8387-King Salman Park Project-Cable Ladders / Trays for SS 8387 (Budget Line Item 1.22) | APPROVED | No | 2024-02-28 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 11918.4 | 5188 | 1 | STANDARD | AL-AMAL ELECTRICAL SWITCHBOARDS | SAR | 11918.4 | APPROVED |  |  | 2024-05-13 | 0 | 67 | Babic, Marian | -45358 | 67
105-9 | 8387-King Salman Park Project | 2724 | 8387-King Salman Park Project-Cable Ladders / Trays for SS 8387 (Budget Line Item 1.22) | APPROVED | No | 2024-02-28 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 307781.11 | 5188 | 0 | STANDARD | AL-AMAL ELECTRICAL SWITCHBOARDS | SAR | 311448.31 | APPROVED |  |  | 2024-03-18 | -3667.2 | 11 | Babic, Marian | -45358 | 11
105-9 | 8387-King Salman Park Project | 2731 | 8387-King Salman Park Project-Building Precast SS # 8387 (Budget Line item 1.19. This PR is to convert the Manual PO # 8080 to Oracle PO as per CEO office instruction | APPROVED | No | 2024-03-03 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 1413950 | 5179 | 0 | STANDARD | EASTERN READYMIX CONCRETE COMPANY | SAR | 1413950 | APPROVED |  |  | 2024-03-18 | 0 | 11 | Babic, Marian | -45358 | 11
105-9 | 8387-King Salman Park Project | 2733 | 8387-King Salman Park Project-Boundary Wall Precast for SS # 8387 (Budget Line item 1.19) | APPROVED | No | 2024-03-03 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 454169.35 | 5223 | 0 | STANDARD | Prainsa Saudi for precast Concrete | SAR | 454169.35 | APPROVED |  |  | 2024-04-03 | 0 | 27 | Babic, Marian | -45358 | 27
105-9 | 8387-King Salman Park Project | 2742 | 8387-King Salman Park Project-Outdoor steel structure for SIS system SS 8387 (Budget Line item 1.38) PO # 8560 coversion from manual | INCOMPLETE | No |  | Almehmadi, Fahed | 2024-03-03 |  |  |  |  | 86710 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-9 | 8387-King Salman Park Project | 2748 | 8387-King Salman Park Project-Outdoor Steel Structure for SIS & Capacitor Cable Support | APPROVED | No | 2024-03-04 | Abas, Mohammed Fekry | 2024-03-07 | 2024-03-07 |  |  |  | 86710 | 5181 | 0 | STANDARD | Energy Field Trading Est | SAR | 86710 | APPROVED |  |  | 2024-03-14 | 0 | 7 | Babic, Marian | -45358 | 7
105-9 | 8387-King Salman Park Project | 2788 | 8387-King Salman Park Project-Installation Services for SS # 8387 (Budget Line item 1.34) | APPROVED | No | 2024-03-05 | Abas, Mohammed Fekry | 2024-03-11 | 2024-03-11 |  |  |  | 219047 | 5213 | 0 | STANDARD | Hussain Ali Hussain Contracting Company | SAR | 219047 | APPROVED |  |  | 2024-03-18 | 0 | 7 | Babic, Marian | -45362 | 7
105-9 | 8387-King Salman Park Project | 2819 | 8387-King Salman Park Project-Civil Construction Works (for Manual PO# 8217 JABCO) Budget Line Item 1.19) | APPROVED | No | 2024-03-13 | Abas, Mohammed Fekry | 2024-03-17 | 2024-03-19 |  |  |  | 7850000 | 5276 | 0 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 7850000 | APPROVED |  |  | 2024-03-28 | 0 | 9 | Babic, Marian | -45370 | 9
105-9 | 8387-King Salman Park Project | 2944 | 8387-King Salman Park Project-Lighting Accessories (Budget Line Item 1.21) | APPROVED | No | 2024-03-28 | Abas, Mohammed Fekry | 2024-04-04 | 2024-04-04 |  |  |  | 23003.2 | 5440 | 0 | STANDARD | Current Makers For Contracting EST | SAR | 21600 | APPROVED |  |  | 2024-05-08 | 1403.2 | 34 | Babic, Marian | -45386 | 34
105-9 | 8387-King Salman Park Project | 2986 | 8387-King Salman Park Project-Fire Fighitng Scope @ 8387 (from Budget Line item 1.18) Manual PO # 8121 conversion | APPROVED | No | 2024-04-03 | Abas, Mohammed Fekry | 2024-04-04 | 2024-04-04 |  |  |  | 1500000 | 5397 | 0 | STANDARD | Equipment & Technical Services Co.(ETECHS) | SAR | 1500000 | APPROVED |  |  | 2024-04-18 | 0 | 14 | Babic, Marian | -45386 | 14
105-9 | 8387-King Salman Park Project | 3084 | 8387-King Salman Park Project-MV Termination Kits @ 8387 (for conversion of Manual PO# 8530) to oracle PO. Budget Line item # 1.20 (termination power Cables) | APPROVED | No | 2024-04-21 | Abas, Mohammed Fekry | 2024-04-22 | 2024-04-23 |  |  |  | 47557 | 5444 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 44703.58 | APPROVED |  |  | 2024-05-12 | 2853.42 | 19 | Babic, Marian | -45405 | 19
105-9 | 8387-King Salman Park Project | 3109 | 8387-King Salman Park Project-SAS Furnitures @ 8387 (under Budget Line # 1.6) for conversion of Manual PO # 8251 | APPROVED | No | 2024-04-23 | Abas, Mohammed Fekry | 2024-04-28 | 2024-04-29 |  |  |  | 55000 | 5480 | 0 | STANDARD | ALFANAR CO | SAR | 55000 | APPROVED |  |  | 2024-05-08 | 0 | 9 | Babic, Marian | -45411 | 9
105-9 | 8387-King Salman Park Project | 3113 | 8387-King Salman Park Project-Cyber Security SS 8387 (Manual PO # 8168) Budget Line # 1.8 | APPROVED | No | 2024-04-23 | Abas, Mohammed Fekry | 2024-04-28 | 2024-04-29 |  |  |  | 1500000 | 5487 | 0 | STANDARD | ALFANAR CO | SAR | 1500000 | APPROVED |  |  | 2024-05-16 | 0 | 17 | Kumar, Mr. Ranjan | -45411 | 17
105-9 | 8387-King Salman Park Project | 3119 | 8387-King Salman Park Project-150mm2, Bare Copper conductor 8387 (Budget Line # 1.23: Grounding) | APPROVED | No | 2024-04-24 | Abas, Mohammed Fekry | 2024-04-28 | 2024-04-29 |  |  |  | 55000 | 5495 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 51821.1 | APPROVED |  |  | 2024-05-21 | 3178.9 | 22 | Babic, Marian | -45411 | 22
105-9 | 8387-King Salman Park Project | 3227 | 8387-King Salman Park Project-lighting accessories (budget line item 1.21) | APPROVED | No | 2024-04-30 | Abas, Mohammed Fekry | 2024-05-01 | 2024-05-01 |  |  |  | 1680 | 5440 | 0 | STANDARD | Current Makers For Contracting EST | SAR | 1680 | APPROVED |  |  | 2024-05-08 | 0 | 7 | Babic, Marian | -45413 | 7
105-9 | 8387-King Salman Park Project | 3295 | 8387-King Salman Park Project-Repair of dilo (Budget Line Item 1.19) | APPROVED | No | 2024-05-05 | Abas, Mohammed Fekry | 2024-05-06 | 2024-05-07 |  |  |  | 16000 | 5519 | 0 | STANDARD | GULF EXPERTS COMPANY LIMITED | SAR | 15986 | APPROVED |  |  | 2024-05-21 | 14 | 14 | Babic, Marian | -45419 | 14
105-9 | 8387-King Salman Park Project | 3352 | 8387-King Salman Park Project-Control & power cable (budget line item 1.15) | REJECTED | No | 2024-05-08 | Issa, Amr Ali | 2024-05-22 | 2024-05-08 |  | 2024-05-22 |  | 128336.8 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45420 | -45420
105-9 | 8387-King Salman Park Project | 3515 | 8387-King Salman Park Project-Remote End Civil Works + Additional works in KSP (by JABCO) | APPROVED | No | 2024-05-28 | Abas, Mohammed Fekry | 2024-06-02 | 2024-06-02 |  |  |  | 136000 | 5276 | 1 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 87000 | APPROVED |  |  | 2024-10-01 | 49000 | 121 | Babic, Marian | -45445 | 121
105-9 | 8387-King Salman Park Project | 3584 | 8387-King Salman Park Project-Adding Air-Freight Charges for HV Connectors in (Arruti) PO # 5152 | APPROVED | No | 2024-06-04 | Abas, Mohammed Fekry | 2024-06-04 | 2024-06-04 |  |  |  | 2520 | 5152 | 1 | STANDARD | Arruti Subestaciones , S.A.U | EUR | 2460 | APPROVED |  |  | 2024-06-26 | 60 | 22 | Babic, Marian | -45447 | 22
105-9 | 8387-King Salman Park Project | 3765 | 8387-King Salman Park Project-Final Inspection & Certification of Capacitor Bank Installation (optional Price in PO # 5167) | APPROVED | No | 2024-07-04 | Abas, Mohammed Fekry | 2024-07-06 | 2024-07-07 |  |  |  | 14500 | 5167 | 1 | STANDARD | YASIR M ALI AL-ZAHRANI EST. | SAR | 14500 | APPROVED |  |  | 2024-07-11 | 0 | 4 | Babic, Marian | -45480 | 4
105-9 | 8387-King Salman Park Project | 4062 | 8387-King Salman Park Project-Generator for the Supply of Electricity for Site Construction activities | RETURNED | No | 2024-07-31 | Babic, Marian | 2025-05-29 | 2024-08-05 | 2025-05-29 |  | not used | 50000 | 5946 | 0 | STANDARD | SUDHIR EQUIPMENT RENTAL COMPANY | SAR | 37600 | APPROVED |  |  | 2024-08-28 | 12400 |  | Babic, Marian | -45509 | 23
105-9 | 8387-King Salman Park Project | 4062 | 8387-King Salman Park Project-Generator for the Supply of Electricity for Site Construction activities | RETURNED | No | 2024-07-31 | Babic, Marian | 2025-05-29 | 2024-08-05 | 2025-05-29 |  | not used | 50000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45509 | -45509
105-9 | 8387-King Salman Park Project | 4603 | 8387-King Salman Park Project-AMI T&C S/S 8387 budget line (1.36) | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-10 | 2024-10-12 |  |  |  | 60000 | 6339 | 0 | STANDARD | SYSTEM HOUSE FACTORY FOR ELECTRIC PANELS (SEP) | SAR | 53750 | APPROVED |  |  | 2024-10-30 | 6250 | 18 | Babic, Marian | -45577 | 18
105-9 | 8387-King Salman Park Project | 4625 | 8387-King Salman Park Project-Generator for the Supply of Electricity for Site Construction activities (amendment in PO 5946) Budget Line 1.19 | RETURNED | No | 2024-10-08 | Babic, Marian | 2025-05-29 | 2024-10-16 | 2025-05-29 |  | not used | 24000 | 5946 | 1 | STANDARD | SUDHIR EQUIPMENT RENTAL COMPANY | SAR | 19560 | APPROVED |  |  | 2024-10-30 | 4440 |  | Babic, Marian | -45581 | 14
105-9 | 8387-King Salman Park Project | 4625 | 8387-King Salman Park Project-Generator for the Supply of Electricity for Site Construction activities (amendment in PO 5946) Budget Line 1.19 | RETURNED | No | 2024-10-08 | Babic, Marian | 2025-05-29 | 2024-10-16 | 2025-05-29 |  | not used | 24000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45581 | -45581
105-9 | 8387-King Salman Park Project | 4802 | 8387-King Salman Park Project- Testing & start Up of PACU (350 KVA rental generator) | RETURNED | No | 2024-10-28 | Babic, Marian | 2024-11-28 | 2024-11-03 | 2024-11-28 |  | not required | 9500 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45599 | -45599
105-9 | 8387-King Salman Park Project | 4953 | 8387-King Salman Park Project-Rental C1-C2 Holder (for Amendment of PO# 4830, Rev-01) | APPROVED | No | 2024-11-14 | Abas, Mohammed Fekry | 2024-11-20 | 2024-11-21 |  |  |  | 79200 | 4830 | 1 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 79200 | APPROVED |  |  | 2024-12-15 | 0 | 24 | Babic, Marian | -45617 | 24
105-9 | 8387-King Salman Park Project | 5037 | 8387-King Salman Park Project-Diesel Supply for SS 8387 (Conversion of Manual PO # 8790 to Oracle) | APPROVED | No | 2024-11-24 | Shoujra, Ishfaq Yousef | 2024-11-27 | 2024-11-27 |  |  |  | 89999.52 | 6560 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 89999.52 | APPROVED |  |  | 2024-12-04 | 0 | 7 | Babic, Marian | -45623 | 7
105-9 | 8387-King Salman Park Project | 5037 | 8387-King Salman Park Project-Diesel Supply for SS 8387 (Conversion of Manual PO # 8790 to Oracle) | APPROVED | No | 2024-11-24 | Shoujra, Ishfaq Yousef | 2024-11-27 | 2024-11-27 |  |  |  | 89999.52 | 6560 | 1 | STANDARD | Talaea Alahlam Trading Company | SAR | 89999.52 | REQUIRES REAPPROVAL |  |  |  | 0 | 431 | Babic, Marian | -45623 | -45623
105-9 | 8387-King Salman Park Project | 5054 | 8387-King Salman Park Project-test | INCOMPLETE | No |  | Jaber, Mohammed Ali | 2024-11-26 |  |  |  |  | 2000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-9 | 8387-King Salman Park Project | 5068 | 8387-King Salman Park Project-Fiber Optic Cable works 8387 (Converting Manual PO # 8534 to Oracle) Budget line # 1.20 (Fiber) | APPROVED | No | 2024-11-27 | Abas, Mohammed Fekry | 2024-12-02 | 2024-12-02 |  |  |  | 174000 | 6577 | 0 | STANDARD | SMART TECH | SAR | 174000 | APPROVED |  |  | 2024-12-05 | 0 | 3 | Babic, Marian | -45628 | 3
105-9 | 8387-King Salman Park Project | 5108 | 8387-King Salman Park Project-Rental C1-C2 Holder (for conversion of manually issued Rev-01 PO# 4830 to Oracle PO) under Budget line # 1.36 | APPROVED | No | 2024-12-01 | Abas, Mohammed Fekry | 2024-12-02 | 2024-12-02 |  |  |  | 189200 | 4830 | 1 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 189200 | APPROVED |  |  | 2024-12-15 | 0 | 13 | Babic, Marian | -45628 | 13
105-9 | 8387-King Salman Park Project | 5164 | 8387-King Salman Park Project-Control Cabels [Conversion of Manual PO # 8152 (Rev-0) to Oracle PO] Budget Line # 1.24 Control | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-08 | 2024-12-09 |  |  |  | 339982.55 | 6609 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 339982.55 | APPROVED |  |  | 2024-12-23 | 0 | 14 | Babic, Marian | -45635 | 14
105-9 | 8387-King Salman Park Project | 5166 | 8387-King Salman Park Project-Conversion of Manual PO # 8152 (Rev-0) to Oracle PO_ Budget Line # 1.26 (LV Power Cable) | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-10 |  |  |  | 452227.87 | 6609 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 452227.87 | APPROVED |  |  | 2024-12-23 | 0 | 13 | Babic, Marian | -45636 | 13
105-9 | 8387-King Salman Park Project | 5167 | 8387-King Salman Park Project-Conversion of Manual PO # 8152 (Rev-1) to Oracle PO_ Budget Line # 1.24 Control Cables | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-10 |  |  |  | 112181 | 6609 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 112181 | APPROVED |  |  | 2024-12-23 | 0 | 13 | Babic, Marian | -45636 | 13
105-9 | 8387-King Salman Park Project | 5168 | 8387-King Salman Park Project-Conversion of Manual PO # 8152 (Rev-1) to Oracle PO_ Budget Line # 1.26 LV Power Cables | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-10 |  |  |  | 16053 | 6609 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 16053 | APPROVED |  |  | 2024-12-23 | 0 | 13 | Babic, Marian | -45636 | 13
105-9 | 8387-King Salman Park Project | 5184 | 8387-King Salman Park Project-Conversion of Manual PO # 8152 (Rev-0) to Oracle PO_ Budget Line # 1.25 MV Cable | APPROVED | No | 2024-12-08 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-10 |  |  |  | 204991.4 | 6609 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 204991.4 | APPROVED |  |  | 2024-12-23 | 0 | 13 | Babic, Marian | -45636 | 13
105-9 | 8387-King Salman Park Project | 5212 | 8387-King Salman Park Project-Pre-Energization Oil Sampling Tests (Power + Station Service Transformers) | APPROVED | No | 2024-12-10 | Abas, Mohammed Fekry | 2024-12-18 | 2024-12-18 |  |  |  | 35585 | 6648 | 0 | STANDARD | Gulf Laboratory Technical Services (S) | SAR | 35585 | APPROVED |  |  | 2024-12-24 | 0 | 6 | Babic, Marian | -45644 | 6
105-9 | 8387-King Salman Park Project | 5225 | 8387-King Salman Park Project-Re-issuing Oralce PO # 5946 (due to wrong distribution of Months/Mobilization) 350&250 kVA generators | APPROVED | No | 2024-12-14 | Abas, Mohammed Fekry | 2024-12-17 | 2024-12-17 |  |  |  | 41600 | 5946 | 2 | STANDARD | SUDHIR EQUIPMENT RENTAL COMPANY | SAR | 41600 | APPROVED |  |  | 2024-12-26 | 0 | 9 | Babic, Marian | -45643 | 9
105-9 | 8387-King Salman Park Project | 5226 | 8387-King Salman Park Project-Re-issuing Oracle PO # 5946 (due to wrong distribution of Months/Mobilization) 350 kVA generators | APPROVED | No | 2024-12-14 | Abas, Mohammed Fekry | 2024-12-18 | 2024-12-18 |  |  |  | 28600 | 5946 | 2 | STANDARD | SUDHIR EQUIPMENT RENTAL COMPANY | SAR | 28600 | APPROVED |  |  | 2024-12-26 | 0 | 8 | Babic, Marian | -45644 | 8
105-9 | 8387-King Salman Park Project | 5335 | 8387-King Salman Park Project-Conversion of Manual PO # 8589 to Oracle PO (budget line item # 1.26) | APPROVED | No | 2025-01-02 | Abas, Mohammed Fekry | 2025-01-07 | 2025-01-07 |  |  |  | 6675 | 6747 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 6675 | APPROVED |  |  | 2025-01-16 | 0 | 9 | Babic, Marian | -45664 | 9
105-9 | 8387-King Salman Park Project | 5698 | 8387-King Salman Park Project-Additional THHN Wires (SESCO) Conversion of Manual PO #8803 to Oracle | APPROVED | No | 2025-01-28 | Abas, Mohammed Fekry | 2025-02-04 | 2025-02-05 |  |  |  | 39600 | 6869 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 39600 | APPROVED |  |  | 2025-02-12 | 0 | 7 | Babic, Marian | -45693 | 7
105-9 | 8387-King Salman Park Project | 5703 | 8387-King Salman Park Project-Steel Name Plates for Site equipments (task # 1.21) | APPROVED | No | 2025-01-28 | Abas, Mohammed Fekry | 2025-02-04 | 2025-02-05 |  |  |  | 19970 | 6921 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 19083 | APPROVED |  |  | 2025-02-25 | 887 | 20 | Babic, Marian | -45693 | 20
105-9 | 8387-King Salman Park Project | 6348 | 8387-King Salman Park Project-Rental C1-C2 Holder (for Amendment of PO# 4830, Rev-03) | APPROVED | No | 2025-04-16 | Abas, Mohammed Fekry | 2025-04-22 | 2025-04-22 |  |  | Rental C1-C2 Holder (for Amendment of PO# 4830, Rev-03) | 132000 | 4830 | 2 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 132000 | APPROVED |  |  | 2025-04-28 | 0 | 6 | Babic, Marian | -45769 | 6
105-10 | 8388-King Salman Park Project | 196 | 8388-King Salman Park Project-Engineering & Design | APPROVED | No | 2021-11-18 | Abas, Mohammed Fekry | 2021-11-18 | 2021-11-21 |  |  |  | 200000 | 3871 | 0 | STANDARD | Fahd Alireza Engineering Consultants | SAR | 200000 | APPROVED |  |  | 2021-11-29 | 0 | 8 | Babic, Marian | -44521 | 8
105-10 | 8388-King Salman Park Project | 252 | 8388-King Salman Park Project-8388-Panles-SCADA/SAS | APPROVED | No | 2021-11-22 | Abas, Mohammed Fekry | 2021-11-22 | 2021-11-24 |  |  |  | 1146623 | 3880 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 1146623 | APPROVED |  |  | 2021-12-01 | 0 | 7 | Babic, Marian | -44524 | 7
105-10 | 8388-King Salman Park Project | 256 | 8388-King Salman Park Project-8388-Communication panel | APPROVED | No | 2021-11-22 | Abas, Mohammed Fekry | 2021-11-22 | 2021-11-24 |  |  |  | 1771220 | 3875 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 1771220 | APPROVED |  |  | 2021-12-01 | 0 | 7 | Babic, Marian | -44524 | 7
105-10 | 8388-King Salman Park Project | 259 | 8388-King Salman Park Project-8388-Panles-Control | APPROVED | No | 2021-11-22 | Abas, Mohammed Fekry | 2021-11-22 | 2021-11-24 |  |  |  | 280121 | 3880 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 280121 | APPROVED |  |  | 2021-12-01 | 0 | 7 | Babic, Marian | -44524 | 7
105-10 | 8388-King Salman Park Project | 262 | 8388-King Salman Park Project-8388-Panels-Protection | APPROVED | No | 2021-11-22 | Abas, Mohammed Fekry | 2021-11-22 | 2021-11-24 |  |  |  | 2070507 | 3880 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 2070507 | APPROVED |  |  | 2021-12-01 | 0 | 7 | Babic, Marian | -44524 | 7
105-10 | 8388-King Salman Park Project | 278 | 8388-King Salman Park Project-8388-Geo Technical Investigation | APPROVED | No | 2021-11-23 | Abas, Mohammed Fekry | 2021-11-24 | 2021-11-28 |  |  |  | 25000 | 3917 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 15730 | APPROVED |  |  | 2021-12-22 | 9270 | 24 | Babic, Marian | -44528 | 24
105-10 | 8388-King Salman Park Project | 292 | 8388-King Salman Park Project-Capacitor bank 13.8kV, 7 MVAR | APPROVED | No | 2021-12-01 | Abas, Mohammed Fekry | 2021-12-05 | 2021-12-06 |  |  |  | 750000 | 3972 | 0 | STANDARD | EATON (COOPER POWER SYSTEMS) | USD | 736218.75 | APPROVED |  |  | 2022-03-09 | 13781.25 | 93 | Babic, Marian | -44536 | 93
105-10 | 8388-King Salman Park Project | 394 | 8388-King Salman Park Project-8388- 132kV GIS | APPROVED | No | 2022-01-19 | Abas, Mohammed Fekry | 2022-01-20 | 2022-01-20 |  |  |  | 6593250 | 3965 | 0 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 6593250 | APPROVED |  |  | 2022-02-10 | 0 | 21 | Babic, Marian | -44581 | 21
105-10 | 8388-King Salman Park Project | 395 | 8388-King Salman Park Project-8388- 67MVA Power Transformer | APPROVED | No | 2022-01-19 | Abas, Mohammed Fekry | 2022-01-20 | 2022-01-20 |  |  |  | 8716087.5 | 4250 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 8716087.5 | APPROVED |  |  | 2022-10-20 | 0 | 273 | Babic, Marian | -44581 | 273
105-10 | 8388-King Salman Park Project | 399 | 8388-King Salman Park Project-8388- 132kV GIS Service & CIF | APPROVED | No | 2022-01-19 | Abas, Mohammed Fekry | 2022-01-20 | 2022-01-20 |  |  |  | 598500 | 3965 | 0 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 605981.25 | APPROVED |  |  | 2022-02-10 | -7481.25 | 21 | Babic, Marian | -44581 | 21
105-10 | 8388-King Salman Park Project | 400 | 8388-King Salman Park Project-8388- 67MVA Power Transformer Service & CIF | APPROVED | No | 2022-01-19 | Abas, Mohammed Fekry | 2022-01-20 | 2022-01-20 |  |  |  | 691162.5 | 4250 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 691162.5 | APPROVED |  |  | 2022-10-20 | 0 | 273 | Babic, Marian | -44581 | 273
105-10 | 8388-King Salman Park Project | 417 | 8388-King Salman Park Project-8388- 13.8kV NGR | APPROVED | No | 2022-01-24 | Abas, Mohammed Fekry | 2022-01-25 | 2022-01-26 |  |  |  | 75000 | 4019 | 0 | STANDARD | National Switchgears | USD | 63562.2 | APPROVED |  |  | 2022-03-17 | 11437.8 | 50 | AlQuraish, Sajjad Hazem | -44587 | 50
105-10 | 8388-King Salman Park Project | 421 | 8388-King Salman Park Project-8388- 132kV Surge arresters | APPROVED | No | 2022-01-24 | Abas, Mohammed Fekry | 2022-01-25 | 2022-01-26 |  |  |  | 51000 | 4001 | 0 | STANDARD | 2100698 Siemens Energy Global GmbH & Co. KG | EUR | 50991.52 | APPROVED |  |  | 2022-03-08 | 8.48 | 41 | AlQuraish, Sajjad Hazem | -44587 | 41
105-10 | 8388-King Salman Park Project | 457 | 8388-King Salman Park Project-8388- Security Cabin ( Delivery & Installation) | APPROVED | No | 2022-02-01 | Abas, Mohammed Fekry | 2022-02-03 | 2022-02-07 |  |  |  | 9000 | 4007 | 0 | STANDARD | Allied General Contracting Est. | SAR | 5850 | APPROVED |  |  | 2022-03-03 | 3150 | 24 | AlQuraish, Sajjad Hazem | -44599 | 24
105-10 | 8388-King Salman Park Project | 457 | 8388-King Salman Park Project-8388- Security Cabin ( Delivery & Installation) | APPROVED | No | 2022-02-01 | Abas, Mohammed Fekry | 2022-02-03 | 2022-02-07 |  |  |  | 9000 | 4080 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 7200 | APPROVED |  |  | 2022-04-14 | 1800 | 66 | Babic, Marian | -44599 | 66
105-10 | 8388-King Salman Park Project | 458 | 8388-King Salman Park Project-8388- Porta cabin for Site Office (Delivery & Installation) | APPROVED | No | 2022-02-01 | Abas, Mohammed Fekry | 2022-02-03 | 2022-02-07 |  |  |  | 50000 | 4007 | 0 | STANDARD | Allied General Contracting Est. | SAR | 41850 | APPROVED |  |  | 2022-03-03 | 8150 | 24 | AlQuraish, Sajjad Hazem | -44599 | 24
105-10 | 8388-King Salman Park Project | 458 | 8388-King Salman Park Project-8388- Porta cabin for Site Office (Delivery & Installation) | APPROVED | No | 2022-02-01 | Abas, Mohammed Fekry | 2022-02-03 | 2022-02-07 |  |  |  | 50000 | 4080 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 44000 | APPROVED |  |  | 2022-04-14 | 6000 | 66 | Babic, Marian | -44599 | 66
105-10 | 8388-King Salman Park Project | 478 | 8388-King Salman Park Project-8388-Battery and Battery charger | APPROVED | No | 2022-02-13 | Abas, Mohammed Fekry | 2022-02-13 | 2022-02-13 |  |  |  | 478250 | 4129 | 0 | STANDARD | Alassas Specialized Company Ltd | SAR | 459600 | APPROVED |  |  | 2022-06-22 | 18650 | 129 | Babic, Marian | -44605 | 129
105-10 | 8388-King Salman Park Project | 483 | 8388-King Salman Park Project-13.8kV MV Switchgear Panels | APPROVED | No | 2022-02-14 | Abas, Mohammed Fekry | 2022-02-16 | 2022-02-16 |  |  |  | 5750000 | 4012 | 0 | STANDARD | ALFANAR CO | SAR | 5750000 | APPROVED |  |  | 2022-03-20 | 0 | 32 | Babic, Marian | -44608 | 32
105-10 | 8388-King Salman Park Project | 484 | 8388-King Salman Park Project-13.8kV RMU,400A | APPROVED | No | 2022-02-14 | Abas, Mohammed Fekry | 2022-02-16 | 2022-02-16 |  |  |  | 150000 | 4011 | 0 | STANDARD | ALFANAR CO | SAR | 58000 | APPROVED |  |  | 2022-09-05 | 92000 | 201 | Babic, Marian | -44608 | 201
105-10 | 8388-King Salman Park Project | 486 | 8388-King Salman Park Project-8388- SIS (Solid Insulated System) | APPROVED | No | 2022-02-14 | Abas, Mohammed Fekry | 2022-02-16 | 2022-02-16 |  |  |  | 1935759.38 | 4156 | 0 | STANDARD | RITZ INSTRUMENT TRANSFORMERS GMBH | EUR | 2025794.7 | APPROVED |  |  | 2022-08-04 | -90035.32 | 169 | Babic, Marian | -44608 | 169
105-10 | 8388-King Salman Park Project | 513 | 8388-King Salman Park Project-8388- Overhead electrical single girder crane complete with accessories | APPROVED | No | 2022-02-28 | Abas, Mohammed Fekry | 2022-03-07 | 2022-03-08 |  |  |  | 160000 | 4169 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 129650 | APPROVED |  |  | 2022-08-10 | 30350 | 155 | Babic, Marian | -44628 | 155
105-10 | 8388-King Salman Park Project | 532 | 8388-King Salman Park Project-8388-Outdoor AMI CT for Auxiliary Transformer details | APPROVED | No | 2022-03-07 | Abas, Mohammed Fekry | 2022-03-07 | 2022-03-08 |  |  |  | 100000 | 4219 | 0 | STANDARD | ELEQ B.V. | EUR | 82368 | APPROVED |  |  | 2022-09-11 | 17632 | 187 | Babic, Marian | -44628 | 187
105-10 | 8388-King Salman Park Project | 541 | 8388-King Salman Park Project-Sign Board with Digital boards for 8388 & 8387 SS. | APPROVED | No | 2022-03-08 | Abas, Mohammed Fekry | 2022-03-14 | 2022-03-15 |  |  |  | 48000 | 4006 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 43600 | APPROVED |  |  | 2022-03-17 | 4400 | 2 | AlQuraish, Sajjad Hazem | -44635 | 2
105-10 | 8388-King Salman Park Project | 542 | 8388-King Salman Park Project-Security cabin delivery and installation for 8387 SS | APPROVED | No | 2022-03-08 | Abas, Mohammed Fekry | 2022-03-14 | 2022-03-15 |  |  |  | 9000 | 4040 | 0 | STANDARD | Allied General Contracting Est. | SAR | 5850 | APPROVED |  |  | 2022-03-17 | 3150 | 2 | AlQuraish, Sajjad Hazem | -44635 | 2
105-10 | 8388-King Salman Park Project | 542 | 8388-King Salman Park Project-Security cabin delivery and installation for 8387 SS | APPROVED | No | 2022-03-08 | Abas, Mohammed Fekry | 2022-03-14 | 2022-03-15 |  |  |  | 9000 | 4079 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 7200 | APPROVED |  |  | 2022-04-14 | 1800 | 30 | Babic, Marian | -44635 | 30
105-10 | 8388-King Salman Park Project | 568 | 8388-King Salman Park Project-8388- Civil & Structural works | APPROVED | No | 2022-03-20 | Abas, Mohammed Fekry | 2022-03-21 | 2022-03-21 |  |  |  | 7414270 | 4142 | 0 | STANDARD | Branch of Ahmed Abdel Khaleq Abdel Hamud and his Partner al Shibl Contracting Company | SAR | 7100000 | APPROVED |  |  | 2022-09-12 | 314270 | 175 | Babic, Marian | -44641 | 175
105-10 | 8388-King Salman Park Project | 626 | 8388-King Salman Park Project-Site Mobilization-8388 | APPROVED | No | 2022-04-27 | Abas, Mohammed Fekry | 2022-05-09 | 2022-05-11 |  |  |  | 243000 | 4112 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 230275 | APPROVED |  |  | 2022-05-30 | 12725 | 19 | Babic, Marian | -44692 | 19
105-10 | 8388-King Salman Park Project | 634 | 8388-King Salman Park Project-Auxiliary Reansformers for 8388 | APPROVED | No | 2022-05-11 | Abas, Mohammed Fekry | 2022-05-15 | 2022-05-22 |  |  |  | 100000 | 4176 | 0 | STANDARD | ALFANAR CO | SAR | 100000 | APPROVED |  |  | 2022-09-12 | 0 | 113 | Babic, Marian | -44703 | 113
105-10 | 8388-King Salman Park Project | 645 | 8388-King Salman Park Project-ACDB, DCDB & Sub panels | APPROVED | No | 2022-05-22 | Abas, Mohammed Fekry | 2022-05-23 | 2022-05-23 |  |  |  | 600000 | 4183 | 0 | STANDARD | ALFANAR CO | SAR | 600000 | APPROVED |  |  | 2022-08-18 | 0 | 87 | Babic, Marian | -44704 | 87
105-10 | 8388-King Salman Park Project | 772 | 8388-King Salman Park Project-150sqmm, Soft annaled copper conductor round compacted | APPROVED | No | 2022-08-25 | Abas, Mohammed Fekry | 2022-08-30 | 2022-08-30 |  |  |  | 188726.38 | 4206 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 183726.37 | APPROVED |  |  | 2022-09-06 | 5000.01 | 7 | Babic, Marian | -44803 | 7
105-10 | 8388-King Salman Park Project | 796 | 8388-King Salman Park Project-Surge arrester TPI PR for 8388 SS | APPROVED | No | 2022-09-07 | Abas, Mohammed Fekry | 2022-09-11 | 2022-09-11 |  |  |  | 1250 | 4224 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 2250 | APPROVED |  |  | 2022-09-13 | -1000 | 2 | Babic, Marian | -44815 | 2
105-10 | 8388-King Salman Park Project | 800 | 8388-King Salman Park Project-132kV GIS TPI PR for 8388 SS | APPROVED | No | 2022-09-07 | Abas, Mohammed Fekry | 2022-09-11 | 2022-09-11 |  |  |  | 3800 | 4225 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 3675 | APPROVED |  |  | 2022-09-19 | 125 | 8 | Babic, Marian | -44815 | 8
105-10 | 8388-King Salman Park Project | 804 | 8388-King Salman Park Project-NGR TPI PR for 8388 SS | APPROVED | No | 2022-09-07 | Abas, Mohammed Fekry | 2022-09-11 | 2022-09-11 |  |  |  | 750 | 4226 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 731.25 | APPROVED |  |  | 2022-09-15 | 18.75 | 4 | Babic, Marian | -44815 | 4
105-10 | 8388-King Salman Park Project | 824 | 8388-King Salman Park Project-Security Systems-8388 SS | APPROVED | No | 2022-09-13 | Abas, Mohammed Fekry | 2022-09-13 | 2022-09-18 |  |  |  | 550000 | 4301 | 0 | STANDARD | Equipment & Technical Services Co.(ETECHS) | SAR | 500000 | APPROVED |  |  | 2023-01-26 | 50000 | 130 | Babic, Marian | -44822 | 130
105-10 | 8388-King Salman Park Project | 828 | 8388-King Salman Park Project-Deisel supply for 8388 SS | APPROVED | No | 2022-09-13 | Abas, Mohammed Fekry | 2022-09-13 | 2022-09-14 |  |  |  | 12875 | 4232 | 0 | STANDARD | Othman Hammoud Al-Zaydi Est | SAR | 12875 | APPROVED |  |  | 2022-09-20 | 0 | 6 | Abuhammad, Samir | -44818 | 6
105-10 | 8388-King Salman Park Project | 833 | 8388-King Salman Park Project-HVAC System 8388 SS | APPROVED | No | 2022-09-14 | Abas, Mohammed Fekry | 2022-09-18 | 2022-09-25 |  |  |  | 1500000 | 4241 | 0 | STANDARD | Magna Contracting Co | SAR | 1500000 | APPROVED |  |  | 2022-10-05 | 0 | 10 | Babic, Marian | -44829 | 10
105-10 | 8388-King Salman Park Project | 845 | 8388-King Salman Park Project-Addtional cost 132kV GIS as per change order-4 | APPROVED | No | 2022-09-17 | Abas, Mohammed Fekry | 2022-09-18 | 2022-09-20 |  |  |  | 375000 | 3965 | 1 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 375000 | APPROVED |  |  | 2022-10-04 | 0 | 14 | Babic, Marian | -44824 | 14
105-10 | 8388-King Salman Park Project | 863 | 8388-King Salman Park Project-Addtiona cost for Power Transformers | APPROVED | No | 2022-10-05 | Abas, Mohammed Fekry | 2022-10-10 | 2022-10-10 |  |  |  | 1945110.04 | 4250 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 1945110 | APPROVED |  |  | 2022-10-20 | 0.04 | 10 | Babic, Marian | -44844 | 10
105-10 | 8388-King Salman Park Project | 867 | 8388-King Salman Park Project-Y/G cables | RETURNED | No | 2022-10-06 | Babic, Marian | 2023-01-25 | 2022-10-10 | 2023-01-25 |  | Please modify the price to be 74.90 SAR, length 305m | 142903.19 | 4210 | 0 | STANDARD | ALFANAR CO | SAR | 67610 | APPROVED |  |  | 2022-10-17 | 75293.19 |  | Babic, Marian | -44844 | 7
105-10 | 8388-King Salman Park Project | 867 | 8388-King Salman Park Project-Y/G cables | RETURNED | No | 2022-10-06 | Babic, Marian | 2023-01-25 | 2022-10-10 | 2023-01-25 |  | Please modify the price to be 74.90 SAR, length 305m | 112721.5 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44844 | -44844
105-10 | 8388-King Salman Park Project | 893 | 8388-King Salman Park Project-Earthing Materials-8388 SS | APPROVED | No | 2022-10-26 | Abas, Mohammed Fekry | 2022-10-31 | 2022-11-01 |  |  |  | 111648.5 | 4274 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 111648.5 | APPROVED |  |  | 2022-12-01 | 0 | 30 | Babic, Marian | -44866 | 30
105-10 | 8388-King Salman Park Project | 906 | 8388-King Salman Park Project-DSM- 8388 SS | APPROVED | No | 2022-11-10 | Abas, Mohammed Fekry | 2022-11-13 | 2022-11-16 |  |  |  | 300000 | 4284 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 265000 | APPROVED |  |  | 2022-12-01 | 35000 | 15 | Babic, Marian | -44881 | 15
105-10 | 8388-King Salman Park Project | 914 | 8388-King Salman Park Project-TPI for Power Transformer in 8388 SS | APPROVED | No | 2022-11-16 | Abas, Mohammed Fekry | 2022-11-17 | 2022-11-17 |  |  |  | 14300 | 4281 | 0 | STANDARD | VELOSI SAUDI ARABIA CO LTD | SAR | 14300 | APPROVED |  |  | 2022-11-28 | 0 | 11 | Babic, Marian | -44882 | 11
105-10 | 8388-King Salman Park Project | 938 | 8388-King Salman Park Project-DC-DC converter 8388 SS | APPROVED | No | 2022-12-06 | Almehmadi, Fahed | 2022-12-12 | 2022-12-13 |  |  |  | 9150 | 4296 | 0 | STANDARD | SGS GULF LIMITED | USD | 4500 | APPROVED |  |  | 2022-12-18 | 4650 | 5 | Babic, Marian | -44908 | 5
105-10 | 8388-King Salman Park Project | 942 | 8388-King Salman Park Project-MV SWGR TPI 8388 | APPROVED | No | 2022-12-06 | Almehmadi, Fahed | 2022-12-12 | 2022-12-13 |  |  |  | 4800 | 4297 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | SAR | 4500 | APPROVED |  |  | 2022-12-18 | 300 | 5 | Babic, Marian | -44908 | 5
105-10 | 8388-King Salman Park Project | 1006 | 8388-King Salman Park Project-Y?G cables TPI | APPROVED | No | 2023-01-19 | Abas, Mohammed Fekry | 2023-01-22 | 2023-01-24 |  |  |  | 2300 | 4328 | 0 | STANDARD | VELOSI SAUDI ARABIA CO LTD | SAR | 1975 | APPROVED |  |  | 2023-02-02 | 325 | 9 | Babic, Marian | -44950 | 9
105-10 | 8388-King Salman Park Project | 1016 | 8388-King Salman Park Project-Cable Y/G 1x240mm2- 8388 SS | APPROVED | No | 2023-01-24 | Abas, Mohammed Fekry | 2023-01-24 | 2023-01-25 |  |  |  | 15548.5 | 4210 | 2 | STANDARD | ALFANAR CO | SAR | 15475.75 | APPROVED |  |  | 2023-02-06 | 72.75 | 12 | Babic, Marian | -44951 | 12
105-10 | 8388-King Salman Park Project | 1028 | 8388-King Salman Park Project-Cable Y/G 1x240mm2- 8388 SS(2) | APPROVED | No | 2023-01-30 | Abas, Mohammed Fekry | 2023-02-02 | 2023-02-02 |  |  |  | 22844.5 | 4210 | 2 | STANDARD | ALFANAR CO | SAR | 22844.5 | APPROVED |  |  | 2023-02-06 | 0 | 4 | Babic, Marian | -44959 | 4
105-10 | 8388-King Salman Park Project | 1076 | 8388-King Salman Park Project-TPI for Bare copper conductor- 8388 SS | APPROVED | No | 2023-02-16 | Abas, Mohammed Fekry | 2023-02-19 | 2023-02-20 |  |  |  | 467 | 4358 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 466.67 | APPROVED |  |  | 2023-03-05 | 0.33 | 13 | Babic, Marian | -44977 | 13
105-10 | 8388-King Salman Park Project | 1093 | 8388-King Salman Park Project-OH Crane TPI-8388 SS | APPROVED | No | 2023-03-01 | Abas, Mohammed Fekry | 2023-03-02 | 2023-03-05 |  |  |  | 800 | 4369 | 0 | STANDARD | SGS INSPECTION SERVICES SA. LTD | SAR | 800 | APPROVED |  |  | 2023-03-12 | 0 | 7 | Babic, Marian | -44990 | 7
105-10 | 8388-King Salman Park Project | 1142 | 8388-King Salman Park Project-Power Transformer's Offloading -8388 SS | APPROVED | No | 2023-03-22 | Abas, Mohammed Fekry | 2023-03-27 | 2023-03-28 |  |  |  | 50000 | 4426 | 0 | STANDARD | MOHAMMED HAMAD AL-AHMADE FOR TRADING AND CONSTRACTION | SAR | 30000 | APPROVED |  |  | 2023-05-03 | 20000 | 36 | Abuhammad, Samir | -45013 | 36
105-10 | 8388-King Salman Park Project | 1211 | 8388-King Salman Park Project-Reactor TPI for 4 SS | APPROVED | No | 2023-04-20 | Abas, Mohammed Fekry | 2023-04-30 | 2023-04-30 |  |  |  | 4800 | 4448 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 4762.5 | APPROVED |  |  | 2023-05-15 | 37.5 | 15 | Babic, Marian | -45046 | 15
105-10 | 8388-King Salman Park Project | 1212 | 8388-King Salman Park Project-CT/VT TPI for 4 SS | APPROVED | No | 2023-04-20 | Abas, Mohammed Fekry | 2023-04-22 | 2023-04-30 |  |  |  | 4800 | 4449 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 4762.5 | APPROVED |  |  | 2023-05-15 | 37.5 | 15 | Babic, Marian | -45046 | 15
105-10 | 8388-King Salman Park Project | 1221 | 8388-King Salman Park Project-(25M)LIGHTNING MAST (LCLM)with accessories-8388 SS | APPROVED | No | 2023-05-01 | Abas, Mohammed Fekry | 2023-05-03 | 2023-05-08 |  |  |  | 58320 | 4485 | 0 | STANDARD | Hesham El-Sewedy Trading Co. LTD. | SAR | 58320 | APPROVED |  |  | 2023-07-19 | 0 | 72 | Babic, Marian | -45054 | 72
105-10 | 8388-King Salman Park Project | 1251 | 8388-King Salman Park Project-Services-Installation and configuration-8388 SS | APPROVED | No | 2023-05-11 | Abas, Mohammed Fekry | 2023-05-15 | 2023-05-15 |  |  |  | 1343800 | 5214 | 0 | STANDARD | Hussain Ali Hussain Contracting Company | SAR | 1343800 | APPROVED |  |  | 2024-03-18 | 0 | 308 | Babic, Marian | -45061 | 308
105-10 | 8388-King Salman Park Project | 1259 | 8388-King Salman Park Project-Protection and Control System TPI 8388 & 8389 | APPROVED | No | 2023-05-14 | Abas, Mohammed Fekry | 2023-05-17 | 2023-05-17 |  |  |  | 14000 | 4476 | 0 | STANDARD | Bureau Veritas Branch Saudi Arabia | SAR | 14000 | APPROVED |  |  | 2023-05-29 | 0 | 12 | Babic, Marian | -45063 | 12
105-10 | 8388-King Salman Park Project | 1273 | 8388-King Salman Park Project-Overhead Travelling Crane TPI-8388 | APPROVED | No | 2023-05-17 | Abas, Mohammed Fekry | 2023-05-23 | 2023-05-24 |  |  |  | 1600 | 4369 | 1 | STANDARD | SGS INSPECTION SERVICES SA. LTD | SAR | 800 | APPROVED |  |  | 2023-08-07 | 800 | 75 | Babic, Marian | -45070 | 75
105-10 | 8388-King Salman Park Project | 1284 | 8388-King Salman Park Project-Power Transformer Oil filteration-8388 S/S | APPROVED | No | 2023-05-25 | Abas, Mohammed Fekry | 2023-05-28 | 2023-05-28 |  |  |  | 100000 | 4551 | 0 | STANDARD | Al-Handasah Al-Namuudhajyyah Contracting Company | SAR | 57000 | APPROVED |  |  | 2023-07-27 | 43000 | 60 | Babic, Marian | -45074 | 60
105-10 | 8388-King Salman Park Project | 1356 | 8388-King Salman Park Project-TPI for SWGR FAT (to cover additional 1 day) | APPROVED | No | 2023-07-18 | Abas, Mohammed Fekry | 2023-07-21 | 2023-07-23 |  |  |  | 1500 | 4297 | 2 | STANDARD | INTERTEK SAUDI ARABIA LTD | SAR | 1500 | APPROVED |  |  | 2023-07-27 | 0 | 4 | Babic, Marian | -45130 | 4
105-10 | 8388-King Salman Park Project | 1419 | 8388-King Salman Park Project-THHN Wires (Lighting Cables) SS # 8388 | APPROVED | No | 2023-08-21 | Abas, Mohammed Fekry | 2023-08-24 | 2023-08-24 |  |  |  | 21300 | 4826 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 21300 | APPROVED |  |  | 2023-12-31 | 0 | 129 | Babic, Marian | -45162 | 129
105-10 | 8388-King Salman Park Project | 1553 | 8388-King Salman Park Project-TPI FAT for additional 1 day for CT/VT (under SS 8388) for all 4 KSP | INCOMPLETE | No |  | Almehmadi, Fahed | 2023-10-05 |  |  |  |  | 250 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-10 | 8388-King Salman Park Project | 1554 | 8388-King Salman Park Project-TPI FAT for additional 1 day for CT/VT (under SS 8388) for all 4 KSP | APPROVED | No | 2023-10-05 | Abas, Mohammed Fekry | 2023-10-09 | 2023-10-09 |  |  |  | 4800 | 4449 | 1 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 4762.5 | APPROVED |  |  | 2023-10-15 | 37.5 | 6 | Babic, Marian | -45208 | 6
105-10 | 8388-King Salman Park Project | 1589 | 8388-King Salman Park Project-TPI FAT Services for LV Power & Control Cables (8388 including 8390) | INCOMPLETE | No |  | Almehmadi, Fahed | 2023-10-12 |  |  |  |  | 2800 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-10 | 8388-King Salman Park Project | 1671 | 8388-King Salman Park Project-Lighting Fixture (indoor - Outdoor) Nardeen for SS 8388 | APPROVED | No | 2023-11-09 | Abas, Mohammed Fekry | 2023-11-14 | 2023-11-14 |  |  |  | 59566.1 | 4724 | 0 | STANDARD | Nardeen Lighting Company Ltd. | SAR | 59566.1 | APPROVED |  |  | 2023-11-26 | 0 | 12 | Babic, Marian | -45244 | 12
105-10 | 8388-King Salman Park Project | 1690 | 8388-King Salman Park Project-RGS Conduits and Accessories (Lighting works) 8388 | RETURNED | No | 2023-11-12 | Babic, Marian | 2024-03-26 | 2023-11-19 | 2024-03-26 |  | PO for this subject already issued, this PR is a balance which is not needed | 55353 | 4791 | 0 | STANDARD | ELECTRIC HOUSE EST. | SAR | 20076.6 | APPROVED |  |  | 2023-12-10 | 35276.4 |  | Babic, Marian | -45249 | 21
105-10 | 8388-King Salman Park Project | 1690 | 8388-King Salman Park Project-RGS Conduits and Accessories (Lighting works) 8388 | RETURNED | No | 2023-11-12 | Babic, Marian | 2024-03-26 | 2023-11-19 | 2024-03-26 |  | PO for this subject already issued, this PR is a balance which is not needed | 832.72 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45249 | -45249
105-10 | 8388-King Salman Park Project | 1694 | 8388-King Salman Park Project-Lighting Pole @ SS 8388 | APPROVED | No | 2023-11-12 | Abas, Mohammed Fekry | 2023-11-19 | 2023-11-19 |  |  |  | 12080 | 4805 | 0 | STANDARD | Hesham El-Sewedy Trading Co. LTD. | SAR | 12080 | APPROVED |  |  | 2023-12-13 | 0 | 24 | Babic, Marian | -45249 | 24
105-10 | 8388-King Salman Park Project | 1751 | 8388-King Salman Park Project- Power Receptacle for 8388 ( budget line item 1.21) | APPROVED | No | 2023-11-15 | Abas, Mohammed Fekry | 2023-11-22 | 2023-11-22 |  |  |  | 77024.06 | 4876 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 58690 | APPROVED |  |  | 2023-12-31 | 18334.06 | 39 | Babic, Marian | -45252 | 39
105-10 | 8388-King Salman Park Project | 2177 | 8388-King Salman Park Project-SIS FAT. TPI services SS 8388 | APPROVED | No | 2024-01-16 | Abas, Mohammed Fekry | 2024-01-16 | 2024-01-17 |  |  |  | 6225 | 5014 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | SAR | 6225 | APPROVED |  |  | 2024-02-01 | 0 | 15 | Babic, Marian | -45308 | 15
105-10 | 8388-King Salman Park Project | 2557 | 8388-King Salman Park Project-Diesel Supply for King Salman Parks Projects | APPROVED | No | 2024-02-13 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-18 |  |  |  | 40000 | 4232 | 1 | STANDARD | Othman Hammoud Al-Zaydi Est | SAR | 40000 | APPROVED |  |  | 2024-03-13 | 0 | 24 | Babic, Marian | -45340 | 24
105-10 | 8388-King Salman Park Project | 2570 | 8388-King Salman Park Project-perforated cable tray (from budget line item 1.22 ) | APPROVED | No | 2024-02-15 | Abas, Mohammed Fekry | 2024-02-19 | 2024-02-20 |  |  |  | 25775.74 | 5110 | 1 | STANDARD | AL-ASHOURY FACTORY FOR CABLE SUPPORTS COMPANY(S) | SAR | 23586.78 | APPROVED |  |  | 2024-03-26 | 2188.96 | 35 | Babic, Marian | -45342 | 35
105-10 | 8388-King Salman Park Project | 2570 | 8388-King Salman Park Project-perforated cable tray (from budget line item 1.22 ) | APPROVED | No | 2024-02-15 | Abas, Mohammed Fekry | 2024-02-19 | 2024-02-20 |  |  |  | 41543.94 | 5110 | 0 | STANDARD | AL-ASHOURY FACTORY FOR CABLE SUPPORTS COMPANY(S) | SAR | 41543.94 | APPROVED |  |  | 2024-03-24 | 0 | 33 | Babic, Marian | -45342 | 33
105-10 | 8388-King Salman Park Project | 2609 | 8388-King Salman Park Project-ACSR Connectors ( Budget Line Item 1.26) | RETURNED | No | 2024-02-19 | Babic, Marian | 2024-03-12 | 2024-02-26 | 2024-03-12 |  | please revise the price | 4752.3 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45348 | -45348
105-10 | 8388-King Salman Park Project | 2635 | 8388-King Salman Park Project-PDS System for SS 8388 | APPROVED | No | 2024-02-20 | Abas, Mohammed Fekry | 2024-02-25 | 2024-02-26 |  |  |  | 160000 | 5163 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 155500 | APPROVED |  |  | 2024-03-18 | 4500 | 21 | Babic, Marian | -45348 | 21
105-10 | 8388-King Salman Park Project | 2639 | 8388-King Salman Park Project-Installation of Capacitor Banks on Civil Foundation SS 8388 (Budget Line item 1.19) | APPROVED | No | 2024-02-21 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 30000 | 5172 | 0 | STANDARD | YASIR M ALI AL-ZAHRANI EST. | SAR | 30000 | APPROVED |  |  | 2024-03-12 | 0 | 15 | Babic, Marian | -45348 | 15
105-10 | 8388-King Salman Park Project | 2665 | 8388-King Salman Park Project-Lighitng Installation works for S/S 8388 (Budget Line item # 1.34) | APPROVED | No | 2024-02-25 | Abas, Mohammed Fekry | 2024-02-27 | 2024-02-28 |  |  |  | 200000 | 5214 | 0 | STANDARD | Hussain Ali Hussain Contracting Company | SAR | 200000 | APPROVED |  |  | 2024-03-18 | 0 | 19 | Babic, Marian | -45350 | 19
105-10 | 8388-King Salman Park Project | 2673 | 8388-King Salman Park Project-Testing & Commissioning Services for SS 8388 (Budget Line item # 1.36) | APPROVED | No | 2024-02-25 | Abas, Mohammed Fekry | 2024-02-27 | 2024-02-28 |  |  |  | 964701 | 5206 | 0 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 618539 | APPROVED |  |  | 2024-05-19 | 346162 | 81 | Babic, Marian | -45350 | 81
105-10 | 8388-King Salman Park Project | 2692 | 8388-King Salman Park Project-Rental Manpower for S/S # 8388 (Budget Line item 1.50) | APPROVED | No | 2024-02-26 | Abas, Mohammed Fekry | 2024-02-29 | 2024-03-03 |  |  |  | 380640 | 5147 | 0 | STANDARD | Jasem M.AlJasem Contracting Est. | SAR | 379860 | APPROVED |  |  | 2024-05-05 | 780 | 63 | Babic, Marian | -45354 | 63
105-10 | 8388-King Salman Park Project | 2698 | 8388-King Salman Park Project-Third party Testing for Precast Boundary Wall (Budget Item # 1.29) | APPROVED | No | 2024-02-26 | Abas, Mohammed Fekry | 2024-02-29 | 2024-03-03 |  |  |  | 30000 | 5250 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 30000 | APPROVED |  |  | 2024-03-26 | 0 | 23 | Babic, Marian | -45354 | 23
105-10 | 8388-King Salman Park Project | 2729 | 8388-King Salman Park Project-Building Precast SS # 8388 (Budget Line item 1.19. for the conversion of Manual PO # 8081 to Oracle PO) | APPROVED | No | 2024-03-03 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 1280470 | 5177 | 0 | STANDARD | EASTERN READYMIX CONCRETE COMPANY | SAR | 1280470 | APPROVED |  |  | 2024-03-18 | 0 | 11 | Babic, Marian | -45358 | 11
105-10 | 8388-King Salman Park Project | 2734 | 8388-King Salman Park Project-Boundary Wall Precast for SS # 8388 (Budget Line item 1.19) | APPROVED | No | 2024-03-03 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 437373.89 | 5224 | 0 | STANDARD | Prainsa Saudi for precast Concrete | SAR | 437373.89 | APPROVED |  |  | 2024-04-03 | 0 | 27 | Babic, Marian | -45358 | 27
105-10 | 8388-King Salman Park Project | 2741 | 8388-King Salman Park Project-Rental Diesel Generator SS # 8388 (Budget Line item 1.3) Conversion of Manual PO # 8257 | APPROVED | No | 2024-03-03 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 171000 | 5185 | 0 | STANDARD | SUDHIR EQUIPMENT RENTAL COMPANY | SAR | 171000 | APPROVED |  |  | 2024-03-18 | 0 | 11 | Babic, Marian | -45358 | 11
105-10 | 8388-King Salman Park Project | 2750 | 8388-King Salman Park Project-Outdoor Steel Structure for SIS & Capacitor Cable Support | APPROVED | No | 2024-03-04 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 83960 | 5182 | 0 | STANDARD | Energy Field Trading Est | SAR | 83960 | APPROVED |  |  | 2024-03-14 | 0 | 7 | Babic, Marian | -45358 | 7
105-10 | 8388-King Salman Park Project | 2790 | 8388-King Salman Park Project-Installation Services for SS # 8388 (Budget Line item 1.34) | APPROVED | No | 2024-03-05 | Abas, Mohammed Fekry | 2024-03-11 | 2024-03-11 |  |  |  | 195795 | 5214 | 0 | STANDARD | Hussain Ali Hussain Contracting Company | SAR | 195795 | APPROVED |  |  | 2024-03-18 | 0 | 7 | Babic, Marian | -45362 | 7
105-10 | 8388-King Salman Park Project | 2811 | 8388-King Salman Park Project-Cable Ladders for SS 8388 (Budget Line Item 1.22) | APPROVED | No | 2024-03-12 | Abas, Mohammed Fekry | 2024-03-12 | 2024-03-12 |  |  |  | 15506.7 | 5255 | 1 | STANDARD | AL-AMAL ELECTRICAL SWITCHBOARDS | SAR | 11747.5 | APPROVED |  |  | 2024-05-01 | 3759.2 | 50 | Babic, Marian | -45363 | 50
105-10 | 8388-King Salman Park Project | 2811 | 8388-King Salman Park Project-Cable Ladders for SS 8388 (Budget Line Item 1.22) | APPROVED | No | 2024-03-12 | Abas, Mohammed Fekry | 2024-03-12 | 2024-03-12 |  |  |  | 262277.73 | 5255 | 0 | STANDARD | AL-AMAL ELECTRICAL SWITCHBOARDS | SAR | 262106.56 | APPROVED |  |  | 2024-03-28 | 171.17 | 16 | Babic, Marian | -45363 | 16
105-10 | 8388-King Salman Park Project | 2823 | 8388-King Salman Park Project-Repair Services for damage Panel (Budget Line item 1.19) SWGR by Al-Fanar SS# 8388 | APPROVED | No | 2024-03-13 | Abas, Mohammed Fekry | 2024-03-17 | 2024-03-19 |  |  |  | 50000 | 5395 | 0 | STANDARD | ALFANAR CO | SAR | 25000 | APPROVED |  |  | 2024-04-21 | 25000 | 33 | Babic, Marian | -45370 | 33
105-10 | 8388-King Salman Park Project | 2987 | 8388-King Salman Park Project-Fire Fighitng Scope @ 8388 (from Budget Line item 1.18) Manual PO # 8122 conversion | APPROVED | No | 2024-04-03 | Abas, Mohammed Fekry | 2024-04-04 | 2024-04-04 |  |  |  | 1500000 | 5398 | 0 | STANDARD | Equipment & Technical Services Co.(ETECHS) | SAR | 1500000 | APPROVED |  |  | 2024-04-18 | 0 | 14 | Babic, Marian | -45386 | 14
105-10 | 8388-King Salman Park Project | 2992 | 8388-King Salman Park Project-Testing & Commissioning @ 8388. (Budget Line item # 1.36) | APPROVED | No | 2024-04-03 | Abas, Mohammed Fekry | 2024-04-04 | 2024-04-04 |  |  |  | 1000000 | 5206 | 0 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 1000000 | APPROVED |  |  | 2024-05-19 | 0 | 45 | Babic, Marian | -45386 | 45
105-10 | 8388-King Salman Park Project | 3062 | 8388-King Salman Park Project-Fiber Optic Patch Panel (budget line item 1.21) | APPROVED | No | 2024-04-19 | Abas, Mohammed Fekry | 2024-04-23 | 2024-04-23 |  |  |  | 49600 | 5471 | 0 | STANDARD | AMWAJ TELECOMMUNICATION MFG. CO. | SAR | 46300 | APPROVED |  |  | 2024-05-08 | 3300 | 15 | Babic, Marian | -45405 | 15
105-10 | 8388-King Salman Park Project | 3085 | 8388-King Salman Park Project-MV Termination Kits @ 8388 (for conversion of Manual PO# 8531) to oracle PO. Budget Line item # 1.20 (termination power Cables) and 1.29 service 1 item | APPROVED | No | 2024-04-21 | Abas, Mohammed Fekry | 2024-04-22 | 2024-04-23 |  |  |  | 47557 | 5445 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 44703.58 | APPROVED |  |  | 2024-05-05 | 2853.42 | 12 | Babic, Marian | -45405 | 12
105-10 | 8388-King Salman Park Project | 3088 | 8388-King Salman Park Project-150mm2, Soft annealed Copper conductor, Round Non compacted @ 8388 (for all 4 KSPs) Budget Line item # 1.24 (Cables -Control) | REJECTED | No | 2024-04-21 | Issa, Amr Ali | 2024-04-22 | 2024-04-22 |  | 2024-04-23 |  | 285000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45404 | -45404
105-10 | 8388-King Salman Park Project | 3110 | 8388-King Salman Park Project-SAS Furnitures @ 8388 (under Budget Line # 1.6) for conversion of Manual PO # 8252 | APPROVED | No | 2024-04-23 | Abas, Mohammed Fekry | 2024-04-28 | 2024-04-29 |  |  |  | 55000 | 5481 | 0 | STANDARD | ALFANAR CO | SAR | 55000 | APPROVED |  |  | 2024-05-08 | 0 | 9 | Babic, Marian | -45411 | 9
105-10 | 8388-King Salman Park Project | 3114 | 8388-King Salman Park Project-Cyber Security SS 8388 (Manual PO # 8169) Budget Line # 1.8 | APPROVED | No | 2024-04-23 | Abas, Mohammed Fekry | 2024-04-28 | 2024-04-29 |  |  |  | 1500000 | 5488 | 0 | STANDARD | ALFANAR CO | SAR | 1400000 | APPROVED |  |  | 2024-05-16 | 100000 | 17 | Kumar, Mr. Ranjan | -45411 | 17
105-10 | 8388-King Salman Park Project | 3285 | 8388-King Salman Park Project-Lighting Accessories (Budget Line Item 1.21) | APPROVED | No | 2024-05-04 | Abas, Mohammed Fekry | 2024-05-06 | 2024-05-07 |  |  |  | 24683.2 | 5507 | 0 | STANDARD | Current Makers For Contracting EST | SAR | 23280 | APPROVED |  |  | 2024-05-20 | 1403.2 | 13 | Babic, Marian | -45419 | 13
105-10 | 8388-King Salman Park Project | 3301 | 8388-King Salman Park Project- Fire Stop material ( Budget Line Item 1.19) | APPROVED | No | 2024-05-05 | Abas, Mohammed Fekry | 2024-05-06 | 2024-05-07 |  |  |  | 91980 | 5515 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 76210 | APPROVED |  |  | 2024-05-21 | 15770 | 14 | Babic, Marian | -45419 | 14
105-10 | 8388-King Salman Park Project | 3366 | 8388-King Salman Park Project-FAT Inspection charges for HVAC Units SS 8388 (SS # 8389 included) Budget Line # 1.29 | APPROVED | No | 2024-05-11 | Abas, Mohammed Fekry | 2024-05-13 | 2024-05-14 |  |  |  | 3600 | 5568 | 0 | STANDARD | Ramz Alataa Company for Trading | SAR | 3600 | APPROVED |  |  | 2024-05-27 | 0 | 13 | Babic, Marian | -45426 | 13
105-10 | 8388-King Salman Park Project | 3368 | 8388-King Salman Park Project-HV Connectors (for ACSR Conductor) (Budget Line item 1.26) | APPROVED | No | 2024-05-12 | Abas, Mohammed Fekry | 2024-05-13 | 2024-05-14 |  |  |  | 7129.65 | 5153 | 0 | STANDARD | Arruti Subestaciones , S.A.U | EUR | 7716.76 | APPROVED |  |  | 2024-05-26 | -587.11 | 12 | Babic, Marian | -45426 | 12
105-10 | 8388-King Salman Park Project | 3593 | 8388-King Salman Park Project-Third party Testing for Precast Boundary Wall (for SAFCO PO # 5250 amendment) (Budget Item # 1.29) | REJECTED | No | 2024-06-05 | Almehmadi, Fahed | 2024-06-05 |  |  | 2024-06-05 | To Increase the Amount, as per Site team feedback | 10000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-10 | 8388-King Salman Park Project | 3598 | 8388-King Salman Park Project-Third party Testing for Precast Boundary Wall (for SAFCO PO # 5250 amendment) (Budget Item # 1.29) | APPROVED | No | 2024-06-05 | Abas, Mohammed Fekry | 2024-06-05 | 2024-06-06 |  |  |  | 17000 | 5250 | 1 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 17000 | APPROVED |  |  | 2024-06-26 | 0 | 20 | Babic, Marian | -45449 | 20
105-10 | 8388-King Salman Park Project | 3663 | 8388-King Salman Park Project-TPI booking for SAS - FAT (SS 8388) | APPROVED | No | 2024-06-22 | Abas, Mohammed Fekry | 2024-06-25 | 2024-06-25 |  |  |  | 18000 | 5751 | 0 | STANDARD | Atlas Support and Services | SAR | 18000 | APPROVED |  |  | 2024-07-02 | 0 | 7 | Babic, Marian | -45468 | 7
105-10 | 8388-King Salman Park Project | 3689 | 8388-King Salman Park Project-Extend duration of rental Generateor (Sudhir) PO # 8257-Rev-2 Oracle PO # 5185 | APPROVED | No | 2024-06-29 | Abas, Mohammed Fekry | 2024-07-04 | 2024-07-07 |  |  |  | 38000 | 5185 | 1 | STANDARD | SUDHIR EQUIPMENT RENTAL COMPANY | SAR | 35600 | APPROVED |  |  | 2024-12-24 | 2400 | 170 | Babic, Marian | -45480 | 170
105-10 | 8388-King Salman Park Project | 3767 | 8388-King Salman Park Project-Final Inspection & Certification of Capacitor Bank Installation (optional Price in PO # 5172) | APPROVED | No | 2024-07-04 | Abas, Mohammed Fekry | 2024-07-06 | 2024-07-07 |  |  |  | 14500 | 5172 | 1 | STANDARD | YASIR M ALI AL-ZAHRANI EST. | SAR | 14500 | APPROVED |  |  | 2024-07-11 | 0 | 4 | Babic, Marian | -45480 | 4
105-10 | 8388-King Salman Park Project | 4513 | 8388-King Salman Park Project-FAT TPI booking for LV & Control Cables (POs Rev-01 all 4KSP) | RETURNED | No | 2024-09-24 | Babic, Marian | 2024-10-02 | 2024-10-01 | 2024-10-02 |  | not required | 2200 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45566 | -45566
105-10 | 8388-King Salman Park Project | 4604 | 8388-King Salman Park Project-AMI T&C budget line (1.36) | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-10 | 2024-10-12 |  |  |  | 60000 | 6340 | 0 | STANDARD | SYSTEM HOUSE FACTORY FOR ELECTRIC PANELS (SEP) | SAR | 53750 | APPROVED |  |  | 2024-10-30 | 6250 | 18 | Babic, Marian | -45577 | 18
105-10 | 8388-King Salman Park Project | 5008 | 8388-King Salman Park Project-Civil Works Variation Order for Al-Shibel (PO # 4142) KSP 8388 | REJECTED | No | 2024-11-21 | Alharbi, Atef Saud | 2024-11-21 | 2024-11-21 |  | 2024-11-25 | from Budget Line item # 1.19 (Civil Main Budget) | 400000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45617 | -45617
105-10 | 8388-King Salman Park Project | 5039 | 8388-King Salman Park Project-Diesel Supply for SS 8388 (Conversion of Manual PO # 8791 to Oracle) Budget Line # 1.3 | APPROVED | No | 2024-11-24 | Abas, Mohammed Fekry | 2024-11-26 | 2024-12-03 |  |  |  | 200000.32 | 6586 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 200000.32 | APPROVED |  |  | 2024-12-09 | 0 | 6 | Babic, Marian | -45629 | 6
105-10 | 8388-King Salman Park Project | 5039 | 8388-King Salman Park Project-Diesel Supply for SS 8388 (Conversion of Manual PO # 8791 to Oracle) Budget Line # 1.3 | APPROVED | No | 2024-11-24 | Abas, Mohammed Fekry | 2024-11-26 | 2024-12-03 |  |  |  | 200000.32 | 6586 | 3 | STANDARD | Talaea Alahlam Trading Company | SAR | 75505.04 | IN PROCESS |  |  |  | 124495.28 | 425 | Babic, Marian | -45629 | -45629
105-10 | 8388-King Salman Park Project | 5069 | 8388-King Salman Park Project-Fiber Optic Cable works 8388 (Converting Manual PO # 8535 to Oracle) Budget line # 1.20 (Fiber) | APPROVED | No | 2024-11-27 | Abas, Mohammed Fekry | 2024-12-02 | 2024-12-02 |  |  |  | 174000 | 6578 | 0 | STANDARD | SMART TECH | SAR | 174000 | APPROVED |  |  | 2024-12-05 | 0 | 3 | Babic, Marian | -45628 | 3
105-10 | 8388-King Salman Park Project | 5169 | 8388-King Salman Park Project-Conversion of Manual PO # 8153 (Rev-0) to Oracle PO. Budget Line # 1.24 Control | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-10 |  |  |  | 301265.95 | 6622 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 301265.95 | APPROVED |  |  | 2024-12-23 | 0 | 13 | Babic, Marian | -45636 | 13
105-10 | 8388-King Salman Park Project | 5170 | 8388-King Salman Park Project-Conversion of Manual PO # 8153 (Rev-0) to Oracle PO. Budget Line # 1.26 LV Power Cables | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-10 |  |  |  | 463390.64 | 6622 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 463390.64 | APPROVED |  |  | 2024-12-23 | 0 | 13 | Babic, Marian | -45636 | 13
105-10 | 8388-King Salman Park Project | 5171 | 8388-King Salman Park Project-Conversion of Manual PO # 8153 (Rev-1) to Oracle PO. Budget Line # 1.24 Control Cables | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-10 |  |  |  | 134288 | 6622 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 134288 | APPROVED |  |  | 2024-12-23 | 0 | 13 | Babic, Marian | -45636 | 13
105-10 | 8388-King Salman Park Project | 5172 | 8388-King Salman Park Project-Conversion of Manual PO # 8153 (Rev-1) to Oracle PO. Budget Line # 1.26 LV Power Cables | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-10 |  |  |  | 18728 | 6622 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 18728 | APPROVED |  |  | 2024-12-23 | 0 | 13 | Babic, Marian | -45636 | 13
105-10 | 8388-King Salman Park Project | 5185 | 8388-King Salman Park Project-Conversion of Manual PO # 8153 (Rev-0) to Oracle PO_ Budget Line # 1.25 MV Cable | APPROVED | No | 2024-12-08 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-10 |  |  |  | 187259.4 | 6622 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 187259.4 | APPROVED |  |  | 2024-12-23 | 0 | 13 | Babic, Marian | -45636 | 13
105-10 | 8388-King Salman Park Project | 5244 | 8388-King Salman Park Project-Adjustment (adding + de-scoping some items) of PO # 4274 (due to additional Qty Ordered previously before PO issuance) | APPROVED | No | 2024-12-19 | Abas, Mohammed Fekry | 2024-12-19 | 2024-12-19 |  |  |  | 5090.5 | 4274 | 1 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 5090.5 | APPROVED |  |  | 2025-01-16 | 0 | 28 | Babic, Marian | -45645 | 28
105-10 | 8388-King Salman Park Project | 5246 | 8388-King Salman Park Project-Conversion of Manual PO (# 8804) to Oracle PO. Lighting Accessories/Conduits (Budget Line Item # 1.21) | APPROVED | No | 2024-12-19 | Abas, Mohammed Fekry | 2024-12-29 | 2024-12-30 |  |  |  | 92712 | 6727 | 0 | STANDARD | Current Makers For Contracting EST | SAR | 91785 | APPROVED |  |  | 2025-01-13 | 927 | 14 | Alhadi, Khalid | -45656 | 14
105-10 | 8388-King Salman Park Project | 5336 | 8388-King Salman Park Project-Conversion of Manual PO # 8590 to Oracle PO (budget line item # 1.26) | APPROVED | No | 2025-01-02 | Abas, Mohammed Fekry | 2025-01-07 | 2025-01-07 |  |  |  | 5545 | 6761 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 5545 | APPROVED |  |  | 2025-01-16 | 0 | 9 | Babic, Marian | -45664 | 9
105-10 | 8388-King Salman Park Project | 5727 | 8388-King Salman Park Project-Lugs & Glands- Conversion of Manual PO # 8840 to Oracle PO (1.21) | APPROVED | No | 2025-01-29 | Abas, Mohammed Fekry | 2025-02-05 | 2025-02-05 |  |  |  | 28610 | 6872 | 0 | STANDARD | MOHAMMAD RASHID SARWAR EST. | SAR | 27610 | APPROVED |  |  | 2025-02-12 | 1000 | 7 | Babic, Marian | -45693 | 7
105-10 | 8388-King Salman Park Project | 5740 | 8388-King Salman Park Project-Bare Copper Tape @SEICO Conversion of Manual PO # 8821 to Oracle | APPROVED | No | 2025-01-30 | Abas, Mohammed Fekry | 2025-02-04 | 2025-02-05 |  |  |  | 28877.45 | 6874 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 28877.45 | APPROVED |  |  | 2025-02-12 | 0 | 7 | Babic, Marian | -45693 | 7
105-10 | 8388-King Salman Park Project | 5764 | 8388-King Salman Park Project-Black Green Blue Yellow & YellowGreen @THHN Wires @Bahra Cables@SESCO | APPROVED | No | 2025-02-03 | Abas, Mohammed Fekry | 2025-02-04 | 2025-02-05 |  |  |  | 37751 | 6882 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 36807 | APPROVED |  |  | 2025-02-17 | 944 | 12 | Babic, Marian | -45693 | 12
105-10 | 8388-King Salman Park Project | 5764 | 8388-King Salman Park Project-Black Green Blue Yellow & YellowGreen @THHN Wires @Bahra Cables@SESCO | APPROVED | No | 2025-02-03 | Abas, Mohammed Fekry | 2025-02-04 | 2025-02-05 |  |  |  | 37751 | 6882 | 1 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 36807 | REJECTED |  |  |  | 944 |  | Babic, Marian | -45693 | -45693
105-10 | 8388-King Salman Park Project | 5864 | 8388-King Salman Park Project-Additional Diesel Supply requirement for SS 8390 Budget Line #1.3 last oracle PO # 6586 | APPROVED | No | 2025-02-13 | Abas, Mohammed Fekry | 2025-02-18 | 2025-02-18 |  |  |  | 177600 | 7110 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 177600 | APPROVED |  |  | 2025-04-16 | 0 | 57 | Babic, Marian | -45706 | 57
105-10 | 8388-King Salman Park Project | 6055 | 8388-King Salman Park Project-Additional BARE COPPER CONDUCTOR for 8388/89 @ 500m for each SS | APPROVED | No | 2025-02-26 | Abas, Mohammed Fekry | 2025-03-02 | 2025-03-03 |  |  | Additional BARE COPPER CONDUCTOR for 8388/89 @ 500m for each SS | 55000 | 6994 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 51792.4 | APPROVED |  |  | 2025-03-16 | 3207.6 | 13 | Babic, Marian | -45719 | 13
105-10 | 8388-King Salman Park Project | 6221 | 8388-King Salman Park Project-Additional BARE COPPER CONDUCTOR for 8388/89 @ 238m for each SS 8388 Budget (1.23) | APPROVED | No | 2025-03-20 | Abas, Mohammed Fekry | 2025-03-25 | 2025-03-25 |  |  | Additional BARE COPPER CONDUCTOR for 8388/89 @ 238m for each SS 8388 Budget (1.23) | 13090 | 6994 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 12326.59 | APPROVED |  |  | 2025-04-08 | 763.41 | 14 | Babic, Marian | -45741 | 14
105-10 | 8388-King Salman Park Project | 6284 | 8388-King Salman Park Project-Earthing Material for Civil Works KSP 8388 | APPROVED | No | 2025-03-26 | Abas, Mohammed Fekry | 2025-03-27 | 2025-03-27 |  |  | Earthing Material for Civil Works KSP 8388 | 22556 | 7116 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 21365 | APPROVED |  |  | 2025-04-16 | 1191 | 20 | Babic, Marian | -45743 | 20
105-10 | 8388-King Salman Park Project | 6403 | 8388-King Salman Park Project-Y/G Cables @ ALFANAR- Conversion of Manual PO # 8814 to Oracle | APPROVED | No | 2025-04-21 | Abas, Mohammed Fekry | 2025-04-30 | 2025-04-30 |  |  | Y/G Cables @ ALFANAR- Conversion of Manual PO # 8814 to Oracle | 106782 | 7216 | 0 | STANDARD | ALFANAR CO | SAR | 106782 | APPROVED |  |  | 2025-05-06 | 0 | 6 | Babic, Marian | -45777 | 6
105-10 | 8388-King Salman Park Project | 6734 | 8388-King Salman Park Project-Additional #1000m - Y/G ( 1x120mm²) cables for SS- 8388 | APPROVED | No | 2025-05-27 | Abas, Mohammed Fekry | 2025-06-04 | 2025-06-04 |  |  | Additional #1000m - Y/G ( 1x120mm²) cables for SS- 8388 | 46542.3 | 6994 | 2 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 44950 | APPROVED |  |  | 2025-06-24 | 1592.3 | 20 | Babic, Marian | -45812 | 20
105-10 | 8388-King Salman Park Project | 6741 | 8388-King Salman Park Project-Pre-Energization Oil Sampling Tests (Power + Station Service Transformers) | APPROVED | No | 2025-05-28 | Abas, Mohammed Fekry | 2025-06-04 | 2025-06-04 |  |  | Pre-Energization Oil Sampling Tests (Power + Station Service Transformers) | 35585 | 7406 | 0 | STANDARD | Gulf Laboratory Technical Services (S) | SAR | 35585 | APPROVED |  |  | 2025-06-17 | 0 | 13 | Babic, Marian | -45812 | 13
105-10 | 8388-King Salman Park Project | 6872 | 8388-King Salman Park Project-Communication System- Modification works- GE Relay and other Panels | APPROVED | No | 2025-06-24 | Abas, Mohammed Fekry | 2025-06-30 | 2025-07-01 |  |  | Communication System- Modification works- GE Relay and other Panels | 30000 | 7698 | 0 | STANDARD | BRANCH OF COGELECX | SAR | 15000 | APPROVED |  |  | 2025-10-16 | 15000 | 107 | Babic, Marian | -45839 | 107
105-10 | 8388-King Salman Park Project | 7196 | 8388-King Salman Park Project-GRC & Aluminum Composite Panel_ Samples for 3D View & Technical Submittals | APPROVED | No | 2025-07-24 | Abas, Mohammed Fekry | 2025-07-30 | 2025-07-30 |  |  | GRC & Aluminum Composite Panel_ Samples for 3D View & Technical Submittals | 94350 | 7721 | 0 | STANDARD | Vision General Contracting | SAR | 94350 | APPROVED |  |  | 2025-11-11 | 0 | 104 | Babic, Marian | -45868 | 104
105-10 | 8388-King Salman Park Project | 7271 | 8388-King Salman Park Project-Aluminum _ cabel trays & Cable Covers | APPROVED | No | 2025-08-04 | Abas, Mohammed Fekry | 2025-08-11 | 2025-08-11 |  |  | Aluminum _ cabel trays & Cable Covers | 59945.84 | 7645 | 0 | STANDARD | AL-ASHOURY FACTORY FOR CABLE SUPPORTS COMPANY(S) | SAR | 58961.88 | APPROVED |  |  | 2025-09-09 | 983.96 | 29 | Babic, Marian | -45880 | 29
105-10 | 8388-King Salman Park Project | 7388 | LV Power & Control Cables | REJECTED | No | 2025-08-19 | Yasmin, Ahmed Elsayed Mohamed | 2025-08-19 | 2025-08-19 |  | 2025-08-21 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45888 | -45888
105-10 | 8388-King Salman Park Project | 7400 | LV Power & Control Cables | APPROVED | No | 2025-08-20 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | LV Power & Control Cables | 0 | 7728 | 0 | STANDARD | Hesham El-Sewedy Trading Co. LTD. | SAR | 215795 | APPROVED |  |  | 2025-10-05 | -215795 | 41 | Babic, Marian | -45894 | 41
105-10 | 8388-King Salman Park Project | 7400 | LV Power & Control Cables | APPROVED | No | 2025-08-20 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | LV Power & Control Cables | 0 | 7728 | 1 | STANDARD | Hesham El-Sewedy Trading Co. LTD. | SAR | 223605 | IN PROCESS |  |  |  | -223605 | 160 | Babic, Marian | -45894 | -45894
105-10 | 8388-King Salman Park Project | 7522 | Fuel Supply for Rental Generator- KSP SS 8388 | APPROVED | No | 2025-09-03 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-04 |  |  | Fuel Supply for Rental Generator- KSP SS 8388 | 0 | 6586 | 1 | STANDARD | Talaea Alahlam Trading Company | SAR | 177600 | APPROVED |  |  | 2025-09-24 | -177600 | 20 | Babic, Marian | -45904 | 20
105-10 | 8388-King Salman Park Project | 7522 | Fuel Supply for Rental Generator- KSP SS 8388 | APPROVED | No | 2025-09-03 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-04 |  |  | Fuel Supply for Rental Generator- KSP SS 8388 | 0 | 6586 | 3 | STANDARD | Talaea Alahlam Trading Company | SAR | 115622.04 | IN PROCESS |  |  |  | -115622.04 | 150 | Babic, Marian | -45904 | -45904
105-10 | 8388-King Salman Park Project | 7800 | Consultant for Estimation of BOQ for Civil Works | RETURNED | No | 2025-09-21 | Babic, Marian | 2025-12-16 | 2025-10-02 | 2025-12-16 |  | as discussed, please resubmit once it will be needed | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45932 | -45932
105-10 | 8388-King Salman Park Project | 7850 | Miscellaneous_Civil & Electrical Material | APPROVED | No | 2025-09-29 | Abas, Mohammed Fekry | 2025-10-02 | 2025-10-02 |  |  | Miscellaneous_Civil & Electrical Material | 0 | 7783 | 0 | STANDARD | Establishment AL-MASSAR For Electrical Tools(S) | SAR | 23734 | APPROVED |  |  | 2025-10-27 | -23734 | 25 | Babic, Marian | -45932 | 25
105-10 | 8388-King Salman Park Project | 8392 | Supply of Water Pumps | RETURNED | No | 2025-11-30 | Abdelraouf, Islam ِAdel Hanafy | 2025-12-28 | 2025-12-02 | 2025-12-28 |  | PR returned based on the email received on 28 Dec from PMT to revise the submitted budget. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelraouf, Islam ِAdel Hanafy | -45993 | -45993
105-10 | 8388-King Salman Park Project | 8589 | Supply Of Water Pumps | APPROVED | No | 2025-12-28 | Abas, Mohammed Fekry | 2026-01-06 | 2026-01-07 |  |  | Supply Of Water Pumps-KSP88 | 0 | 7961 | 0 | STANDARD | United Park Company | SAR | 49325 | APPROVED | 2026-01-07 | 2026-01-08 | 2026-01-19 | -49325 | 12 | Abdelraouf, Islam ِAdel Hanafy | 1 | 12
105-10 | 8388-King Salman Park Project | 8730 | Diesel Supply for Genset-KSP88 | APPROVED | No | 2026-01-19 | Abas, Mohammed Fekry | 2026-01-22 | 2026-01-25 |  |  | Diesel Supply for Genset- KSP88- New Rates | 0 | 6586 | 3 | STANDARD | Talaea Alahlam Trading Company | SAR | 78500 | IN PROCESS |  |  |  | -78500 | 7 | Babic, Marian | -46047 | -46047
105-10 | 8388-King Salman Park Project | 8730 | Diesel Supply for Genset-KSP88 | APPROVED | No | 2026-01-19 | Abas, Mohammed Fekry | 2026-01-22 | 2026-01-25 |  |  | Diesel Supply for Genset- KSP88- New Rates | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46047 | -46047
105-10 | 8388-King Salman Park Project | 8816 | Supply & Installation of Metal Works | IN PROCESS | No | 2026-01-28 | Yasmin, Ahmed Elsayed Mohamed | 2026-01-28 | 2026-01-28 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46050 | -46050
105-11 | 8389-King Salman Park Project | 197 | 8389-King Salman Park Project-Engineering & Design | APPROVED | No | 2021-11-18 | Abas, Mohammed Fekry | 2021-11-18 | 2021-11-21 |  |  |  | 200000 | 3872 | 0 | STANDARD | Fahd Alireza Engineering Consultants | SAR | 195000 | APPROVED |  |  | 2021-11-29 | 5000 | 8 | Babic, Marian | -44521 | 8
105-11 | 8389-King Salman Park Project | 197 | 8389-King Salman Park Project-Engineering & Design | APPROVED | No | 2021-11-18 | Abas, Mohammed Fekry | 2021-11-18 | 2021-11-21 |  |  |  | 200000 | 3872 | 1 | STANDARD | Fahd Alireza Engineering Consultants | SAR | 195000 | APPROVED |  |  | 2022-11-29 | 5000 | 373 | Babic, Marian | -44521 | 373
105-11 | 8389-King Salman Park Project | 253 | 8389-King Salman Park Project-8389-Panles-SCADA/SAS | APPROVED | No | 2021-11-22 | Abas, Mohammed Fekry | 2021-11-22 | 2021-11-24 |  |  |  | 1146623 | 3881 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 1146623 | APPROVED |  |  | 2021-12-01 | 0 | 7 | Babic, Marian | -44524 | 7
105-11 | 8389-King Salman Park Project | 257 | 8389-King Salman Park Project-8389-Communication Panels | APPROVED | No | 2021-11-22 | Abas, Mohammed Fekry | 2021-11-22 | 2021-11-24 |  |  |  | 1521930 | 3876 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 1521930 | APPROVED |  |  | 2021-12-01 | 0 | 7 | Babic, Marian | -44524 | 7
105-11 | 8389-King Salman Park Project | 260 | 8389-King Salman Park Project-8389-Panels-Control | APPROVED | No | 2021-11-22 | Abas, Mohammed Fekry | 2021-11-22 | 2021-11-24 |  |  |  | 280121 | 3881 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 280121 | APPROVED |  |  | 2021-12-01 | 0 | 7 | Babic, Marian | -44524 | 7
105-11 | 8389-King Salman Park Project | 263 | 8389-King Salman Park Project-8389-Panels-Protection | APPROVED | No | 2021-11-22 | Abas, Mohammed Fekry | 2021-11-22 | 2021-11-24 |  |  |  | 2070507 | 3881 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 2070507 | APPROVED |  |  | 2021-12-01 | 0 | 7 | Babic, Marian | -44524 | 7
105-11 | 8389-King Salman Park Project | 279 | 8389-King Salman Park Project-8389-Geo technical Investigation | APPROVED | No | 2021-11-23 | Abas, Mohammed Fekry | 2021-11-24 | 2021-11-28 |  |  |  | 25000 | 3918 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 15730 | APPROVED |  |  | 2021-12-22 | 9270 | 24 | Babic, Marian | -44528 | 24
105-11 | 8389-King Salman Park Project | 293 | 8389-King Salman Park Project-Capacitor bank 13.8kV, 7 MVAR | APPROVED | No | 2021-12-01 | Abas, Mohammed Fekry | 2021-12-05 | 2021-12-06 |  |  |  | 750000 | 3973 | 0 | STANDARD | EATON (COOPER POWER SYSTEMS) | USD | 736218.75 | APPROVED |  |  | 2022-03-09 | 13781.25 | 93 | Babic, Marian | -44536 | 93
105-11 | 8389-King Salman Park Project | 402 | 8389-King Salman Park Project-8389- 132kV GIS | APPROVED | No | 2022-01-20 | Abas, Mohammed Fekry | 2022-01-23 | 2022-01-24 |  |  |  | 6593250 | 3964 | 0 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 6593250 | APPROVED |  |  | 2022-02-10 | 0 | 17 | Babic, Marian | -44585 | 17
105-11 | 8389-King Salman Park Project | 403 | 8389-King Salman Park Project-8389- GIS Service & CIF | APPROVED | No | 2022-01-20 | Abas, Mohammed Fekry | 2022-01-23 | 2022-01-24 |  |  |  | 598500 | 3964 | 0 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 605981.25 | APPROVED |  |  | 2022-02-10 | -7481.25 | 17 | Babic, Marian | -44585 | 17
105-11 | 8389-King Salman Park Project | 405 | 8389-King Salman Park Project-8389- 67MVA Power Transformer Servicce & CIF | APPROVED | No | 2022-01-20 | Abas, Mohammed Fekry | 2022-01-23 | 2022-01-24 |  |  |  | 691162.5 | 4166 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 136500 | APPROVED |  |  | 2022-08-08 | 554662.5 | 196 | Babic, Marian | -44585 | 196
105-11 | 8389-King Salman Park Project | 407 | 8389-King Salman Park Project-8389- 67MVA Power Transformer | APPROVED | No | 2022-01-20 | Abas, Mohammed Fekry | 2022-01-23 | 2022-01-24 |  |  |  | 8716087.5 | 4166 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 8716087.5 | APPROVED |  |  | 2022-08-08 | 0 | 196 | Babic, Marian | -44585 | 196
105-11 | 8389-King Salman Park Project | 418 | 8389-King Salman Park Project-8389- 13.8kV NGR | APPROVED | No | 2022-01-24 | Abas, Mohammed Fekry | 2022-01-25 | 2022-01-26 |  |  |  | 75000 | 4020 | 0 | STANDARD | National Switchgears | USD | 63562.2 | APPROVED |  |  | 2022-03-17 | 11437.8 | 50 | AlQuraish, Sajjad Hazem | -44587 | 50
105-11 | 8389-King Salman Park Project | 422 | 8389-King Salman Park Project-8389- 132kV Surge arresters | APPROVED | No | 2022-01-24 | Abas, Mohammed Fekry | 2022-01-25 | 2022-01-26 |  |  |  | 51000 | 4002 | 0 | STANDARD | 2100698 Siemens Energy Global GmbH & Co. KG | EUR | 50991.52 | APPROVED |  |  | 2022-03-08 | 8.48 | 41 | AlQuraish, Sajjad Hazem | -44587 | 41
105-11 | 8389-King Salman Park Project | 429 | 8389-King Salman Park Project-8389- 13.8kV MV Switchgear Panels | APPROVED | No | 2022-01-24 | Abas, Mohammed Fekry | 2022-01-25 | 2022-01-26 |  |  |  | 5750000 | 3961 | 0 | STANDARD | ALFANAR CO | SAR | 5750000 | APPROVED |  |  | 2022-02-06 | 0 | 11 | Babic, Marian | -44587 | 11
105-11 | 8389-King Salman Park Project | 446 | 8389-King Salman Park Project-8389- 13.8kV RMU | APPROVED | No | 2022-01-31 | Abas, Mohammed Fekry | 2022-02-02 | 2022-02-02 |  |  |  | 150000 | 3986 | 0 | STANDARD | ALFANAR CO | SAR | 58000 | APPROVED |  |  | 2022-09-05 | 92000 | 215 | Babic, Marian | -44594 | 215
105-11 | 8389-King Salman Park Project | 461 | 8389-King Salman Park Project-8389 Porta cabin for site office (12x4 mtr) | APPROVED | No | 2022-02-01 | Abas, Mohammed Fekry | 2022-02-03 | 2022-02-07 |  |  |  | 50000 | 3999 | 0 | STANDARD | Allied General Contracting Est. | SAR | 41850 | APPROVED |  |  | 2022-03-08 | 8150 | 29 | AlQuraish, Sajjad Hazem | -44599 | 29
105-11 | 8389-King Salman Park Project | 461 | 8389-King Salman Park Project-8389 Porta cabin for site office (12x4 mtr) | APPROVED | No | 2022-02-01 | Abas, Mohammed Fekry | 2022-02-03 | 2022-02-07 |  |  |  | 50000 | 4081 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 44000 | APPROVED |  |  | 2022-04-14 | 6000 | 66 | Babic, Marian | -44599 | 66
105-11 | 8389-King Salman Park Project | 462 | 8389-King Salman Park Project-8389- Security Cabin for Site office (Delivery & Installation) | APPROVED | No | 2022-02-01 | Abas, Mohammed Fekry | 2022-02-03 | 2022-02-07 |  |  |  | 9000 | 3999 | 0 | STANDARD | Allied General Contracting Est. | SAR | 5850 | APPROVED |  |  | 2022-03-08 | 3150 | 29 | AlQuraish, Sajjad Hazem | -44599 | 29
105-11 | 8389-King Salman Park Project | 462 | 8389-King Salman Park Project-8389- Security Cabin for Site office (Delivery & Installation) | APPROVED | No | 2022-02-01 | Abas, Mohammed Fekry | 2022-02-03 | 2022-02-07 |  |  |  | 9000 | 4081 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 7200 | APPROVED |  |  | 2022-04-14 | 1800 | 66 | Babic, Marian | -44599 | 66
105-11 | 8389-King Salman Park Project | 463 | 8389-King Salman Park Project-8389 Sign Board with Digital counter ( Transportation, Foundation & Installation) | APPROVED | No | 2022-02-01 | Abas, Mohammed Fekry | 2022-02-03 | 2022-02-07 |  |  |  | 24000 | 4005 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 21800 | APPROVED |  |  | 2022-03-17 | 2200 | 38 | AlQuraish, Sajjad Hazem | -44599 | 38
105-11 | 8389-King Salman Park Project | 479 | 8389-King Salman Park Project-8389- Battery & Battery Charger | APPROVED | No | 2022-02-13 | Abas, Mohammed Fekry | 2022-02-13 | 2022-02-13 |  |  |  | 478250 | 4130 | 0 | STANDARD | Alassas Specialized Company Ltd | SAR | 459600 | APPROVED |  |  | 2022-06-22 | 18650 | 129 | Babic, Marian | -44605 | 129
105-11 | 8389-King Salman Park Project | 492 | 8389-King Salman Park Project-8389- SIS (Solid Insulated System) | APPROVED | No | 2022-02-17 | Abas, Mohammed Fekry | 2022-02-17 | 2022-02-17 |  |  |  | 1935759.38 | 4157 | 0 | STANDARD | RITZ INSTRUMENT TRANSFORMERS GMBH | EUR | 1800706.4 | APPROVED |  |  | 2022-08-08 | 135052.98 | 172 | Babic, Marian | -44609 | 172
105-11 | 8389-King Salman Park Project | 514 | 8389-King Salman Park Project-8389- Overhead electrical single girder crane complete with accessories | APPROVED | No | 2022-02-28 | Abas, Mohammed Fekry | 2022-03-07 | 2022-03-08 |  |  |  | 160000 | 4170 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 129650 | APPROVED |  |  | 2022-08-11 | 30350 | 156 | Babic, Marian | -44628 | 156
105-11 | 8389-King Salman Park Project | 533 | 8389-King Salman Park Project-8389- Outdoor AMI CT for Auxiliary Transformer details | APPROVED | No | 2022-03-07 | Abas, Mohammed Fekry | 2022-03-07 | 2022-03-08 |  |  |  | 100000 | 4220 | 0 | STANDARD | ELEQ B.V. | EUR | 82368 | APPROVED |  |  | 2022-09-11 | 17632 | 187 | Babic, Marian | -44628 | 187
105-11 | 8389-King Salman Park Project | 569 | 8389-King Salman Park Project-8389 Civil & structural works | APPROVED | No | 2022-03-20 | Abas, Mohammed Fekry | 2022-03-21 | 2022-03-21 |  |  |  | 7414270 | 4143 | 0 | STANDARD | Al Sahda Contracting Est. | SAR | 7100000 | APPROVED |  |  | 2022-09-19 | 314270 | 182 | Babic, Marian | -44641 | 182
105-11 | 8389-King Salman Park Project | 635 | 8389-King Salman Park Project-Auxiliary Transformers for 8389 | APPROVED | No | 2022-05-11 | Abas, Mohammed Fekry | 2022-05-15 | 2022-05-22 |  |  |  | 100000 | 4177 | 0 | STANDARD | ALFANAR CO | SAR | 100000 | APPROVED |  |  | 2022-09-12 | 0 | 113 | Babic, Marian | -44703 | 113
105-11 | 8389-King Salman Park Project | 646 | 8389-King Salman Park Project-ACDB, DCDB & Sub panels | APPROVED | No | 2022-05-22 | Abas, Mohammed Fekry | 2022-05-23 | 2022-05-23 |  |  |  | 600000 | 4184 | 0 | STANDARD | ALFANAR CO | SAR | 600000 | APPROVED |  |  | 2022-08-16 | 0 | 85 | Babic, Marian | -44704 | 85
105-11 | 8389-King Salman Park Project | 680 | 8389-King Salman Park Project-Supply and installation of DSM equipment for 8388 & 8389 S/S | APPROVED | No | 2022-06-06 | Abas, Mohammed Fekry | 2022-06-08 | 2022-06-12 |  |  |  | 200000 | 4285 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 165000 | APPROVED |  |  | 2022-12-01 | 35000 | 172 | Babic, Marian | -44724 | 172
105-11 | 8389-King Salman Park Project | 685 | 8389-King Salman Park Project-132kV GIS for 8389 S/S | APPROVED | No | 2022-06-08 | Abas, Mohammed Fekry | 2022-06-12 | 2022-06-13 |  |  |  | 375000 | 3964 | 1 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 375000 | APPROVED |  |  | 2022-06-22 | 0 | 9 | Babic, Marian | -44725 | 9
105-11 | 8389-King Salman Park Project | 690 | 8389-King Salman Park Project-Site Mobilization activity for 8389 S/S | APPROVED | No | 2022-06-09 | Abas, Mohammed Fekry | 2022-06-16 | 2022-06-16 |  |  |  | 279786 | 4149 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 272740 | APPROVED |  |  | 2022-07-05 | 7046 | 19 | Babic, Marian | -44728 | 19
105-11 | 8389-King Salman Park Project | 730 | 8389-King Salman Park Project-67MVA Power Transformer-8389 SS | APPROVED | No | 2022-07-17 | Abas, Mohammed Fekry | 2022-07-20 | 2022-07-21 |  |  |  | 2499772.54 | 4166 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 2499772.5 | APPROVED |  |  | 2022-08-08 | 0.04 | 18 | Babic, Marian | -44763 | 18
105-11 | 8389-King Salman Park Project | 735 | 8389-King Salman Park Project-Window/Split/Freestanding Ac's for 8389 & 8390 SS | APPROVED | No | 2022-07-24 | Abas, Mohammed Fekry | 2022-08-03 | 2022-08-07 |  |  |  | 92300 | 4194 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 78772.43 | APPROVED |  |  | 2022-08-30 | 13527.57 | 23 | Babic, Marian | -44780 | 23
105-11 | 8389-King Salman Park Project | 773 | 8389-King Salman Park Project-150sqmm, Soft annaled copper conductor round compacted | APPROVED | No | 2022-08-25 | Abas, Mohammed Fekry | 2022-08-30 | 2022-08-30 |  |  |  | 188726.38 | 4207 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 183726.37 | APPROVED |  |  | 2022-09-06 | 5000.01 | 7 | Babic, Marian | -44803 | 7
105-11 | 8389-King Salman Park Project | 797 | 8389-King Salman Park Project-Surge arrester TPI PR for 8389 SS | APPROVED | No | 2022-09-07 | Abas, Mohammed Fekry | 2022-09-11 | 2022-09-11 |  |  |  | 1250 | 4224 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 1125 | APPROVED |  |  | 2022-09-13 | 125 | 2 | Babic, Marian | -44815 | 2
105-11 | 8389-King Salman Park Project | 801 | 8389-King Salman Park Project-132kV GIS TPI PR for 8389 SS | APPROVED | No | 2022-09-07 | Abas, Mohammed Fekry | 2022-09-11 | 2022-09-11 |  |  |  | 3800 | 4225 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 3675 | APPROVED |  |  | 2022-09-19 | 125 | 8 | Babic, Marian | -44815 | 8
105-11 | 8389-King Salman Park Project | 805 | 8389-King Salman Park Project-NGR TPI PR for 8389 SS | APPROVED | No | 2022-09-07 | Abas, Mohammed Fekry | 2022-09-11 | 2022-09-11 |  |  |  | 750 | 4226 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 731.25 | APPROVED |  |  | 2022-09-15 | 18.75 | 4 | Babic, Marian | -44815 | 4
105-11 | 8389-King Salman Park Project | 825 | 8389-King Salman Park Project-Security Systems-8389 SS | APPROVED | No | 2022-09-13 | Abas, Mohammed Fekry | 2022-09-13 | 2022-09-18 |  |  |  | 550000 | 4302 | 0 | STANDARD | Equipment & Technical Services Co.(ETECHS) | SAR | 500000 | APPROVED |  |  | 2023-01-26 | 50000 | 130 | Babic, Marian | -44822 | 130
105-11 | 8389-King Salman Park Project | 829 | 8389-King Salman Park Project-Deisel supply for generators 8389 SS | APPROVED | No | 2022-09-13 | Abas, Mohammed Fekry | 2022-09-13 | 2022-09-14 |  |  |  | 29843.57 | 4232 | 0 | STANDARD | Othman Hammoud Al-Zaydi Est | SAR | 29843 | APPROVED |  |  | 2022-09-20 | 0.57 | 6 | Abuhammad, Samir | -44818 | 6
105-11 | 8389-King Salman Park Project | 834 | 8389-King Salman Park Project-HVAC System 8389 SS | APPROVED | No | 2022-09-14 | Abas, Mohammed Fekry | 2022-09-18 | 2022-09-25 |  |  |  | 1500000 | 4242 | 0 | STANDARD | Magna Contracting Co | SAR | 1500000 | APPROVED |  |  | 2022-10-05 | 0 | 10 | Babic, Marian | -44829 | 10
105-11 | 8389-King Salman Park Project | 873 | 8389-King Salman Park Project-Y/G cables for 8389 SS | RETURNED | No | 2022-10-11 | Babic, Marian | 2023-01-25 | 2022-10-16 | 2023-01-25 |  | Please modify the price to be 74.90 SAR, length 305m | 142903.19 | 4211 | 0 | STANDARD | ALFANAR CO | SAR | 67610 | APPROVED |  |  | 2022-10-19 | 75293.19 |  | Babic, Marian | -44850 | 3
105-11 | 8389-King Salman Park Project | 873 | 8389-King Salman Park Project-Y/G cables for 8389 SS | RETURNED | No | 2022-10-11 | Babic, Marian | 2023-01-25 | 2022-10-16 | 2023-01-25 |  | Please modify the price to be 74.90 SAR, length 305m | 112721.5 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44850 | -44850
105-11 | 8389-King Salman Park Project | 892 | 8389-King Salman Park Project-Earthing Materials-8389 SS | APPROVED | No | 2022-10-26 | Abas, Mohammed Fekry | 2022-10-31 | 2022-11-01 |  |  |  | 123198.5 | 4275 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 123198.5 | APPROVED |  |  | 2022-12-01 | 0 | 30 | Babic, Marian | -44866 | 30
105-11 | 8389-King Salman Park Project | 905 | 8389-King Salman Park Project-DSM for 8389 SS (addtional price for PR-680) | APPROVED | No | 2022-11-10 | Abas, Mohammed Fekry | 2022-11-13 | 2022-11-16 |  |  |  | 100000 | 4285 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 100000 | APPROVED |  |  | 2022-12-01 | 0 | 15 | Babic, Marian | -44881 | 15
105-11 | 8389-King Salman Park Project | 907 | 8389-King Salman Park Project-TPI Bare copper conductor for 3 SS | APPROVED | No | 2022-11-10 | Abas, Mohammed Fekry | 2022-11-13 | 2022-11-16 |  |  |  | 1400 | 4277 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 1400 | APPROVED |  |  | 2022-11-28 | 0 | 12 | Babic, Marian | -44881 | 12
105-11 | 8389-King Salman Park Project | 915 | 8389-King Salman Park Project-TPI for Power Transformer in 8389 SS | APPROVED | No | 2022-11-16 | Abas, Mohammed Fekry | 2022-11-17 | 2022-11-17 |  |  |  | 14300 | 4282 | 0 | STANDARD | VELOSI SAUDI ARABIA CO LTD | SAR | 14300 | APPROVED |  |  | 2022-11-28 | 0 | 11 | Babic, Marian | -44882 | 11
105-11 | 8389-King Salman Park Project | 939 | 8389-King Salman Park Project-DC-DC converter- 8389 SS | APPROVED | No | 2022-12-06 | Abas, Mohammed Fekry | 2022-12-11 | 2022-12-12 |  |  |  | 9150 | 4294 | 0 | STANDARD | SGS GULF LIMITED | USD | 4500 | APPROVED |  |  | 2022-12-19 | 4650 | 7 | Babic, Marian | -44907 | 7
105-11 | 8389-King Salman Park Project | 1017 | 8389-King Salman Park Project-Cable Y/G 1x240mm2- 8389 SS | APPROVED | No | 2023-01-24 | Abas, Mohammed Fekry | 2023-01-24 | 2023-01-25 |  |  |  | 15548.5 | 4211 | 2 | STANDARD | ALFANAR CO | SAR | 15475.75 | APPROVED |  |  | 2023-02-06 | 72.75 | 12 | Babic, Marian | -44951 | 12
105-11 | 8389-King Salman Park Project | 1029 | 8389-King Salman Park Project-Cable Y/G 1x240mm2- 8389 SS(2) | APPROVED | No | 2023-01-30 | Abas, Mohammed Fekry | 2023-02-02 | 2023-02-02 |  |  |  | 22844.5 | 4211 | 2 | STANDARD | ALFANAR CO | SAR | 22844.5 | APPROVED |  |  | 2023-02-06 | 0 | 4 | Babic, Marian | -44959 | 4
105-11 | 8389-King Salman Park Project | 1077 | 8389-King Salman Park Project-TPI for Bare copper conductor- 8389 SS | APPROVED | No | 2023-02-16 | Abas, Mohammed Fekry | 2023-02-19 | 2023-02-20 |  |  |  | 467 | 4359 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 466.67 | APPROVED |  |  | 2023-03-05 | 0.33 | 13 | Babic, Marian | -44977 | 13
105-11 | 8389-King Salman Park Project | 1094 | 8389-King Salman Park Project-OH Crane TPI-8389 SS | APPROVED | No | 2023-03-01 | Abas, Mohammed Fekry | 2023-03-02 | 2023-03-05 |  |  |  | 800 | 4370 | 0 | STANDARD | SGS INSPECTION SERVICES SA. LTD | SAR | 800 | APPROVED |  |  | 2023-03-12 | 0 | 7 | Babic, Marian | -44990 | 7
105-11 | 8389-King Salman Park Project | 1136 | 8389-King Salman Park Project-FAT-TPI Capacitor Bank and Related Equipment for 4 Substations | APPROVED | No | 2023-03-19 | Abas, Mohammed Fekry | 2023-03-21 | 2023-03-22 |  |  |  | 4500 | 4396 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 4500 | APPROVED |  |  | 2023-03-27 | 0 | 5 | Babic, Marian | -45007 | 5
105-11 | 8389-King Salman Park Project | 1143 | 8389-King Salman Park Project-Power Transformer's Offloading -8389 SS | APPROVED | No | 2023-03-22 | Abas, Mohammed Fekry | 2023-03-27 | 2023-03-28 |  |  |  | 50000 | 4436 | 0 | STANDARD | MOHAMMED HAMAD AL-AHMADE FOR TRADING AND CONSTRACTION | SAR | 30000 | APPROVED |  |  | 2023-05-03 | 20000 | 36 | Abuhammad, Samir | -45013 | 36
105-11 | 8389-King Salman Park Project | 1216 | 8389-King Salman Park Project-MV Switchgear-8389 SS | APPROVED | No | 2023-04-30 | Abas, Mohammed Fekry | 2023-05-02 | 2023-05-02 |  |  |  | 4500 | 4452 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | SAR | 4500 | APPROVED |  |  | 2023-05-15 | 0 | 13 | Babic, Marian | -45048 | 13
105-11 | 8389-King Salman Park Project | 1222 | 8389-King Salman Park Project-(25M)LIGHTNING MAST (LCLM)with accessories-8389 SS | APPROVED | No | 2023-05-01 | Abas, Mohammed Fekry | 2023-05-03 | 2023-05-08 |  |  |  | 58320 | 4486 | 0 | STANDARD | Hesham El-Sewedy Trading Co. LTD. | SAR | 58320 | APPROVED |  |  | 2023-07-19 | 0 | 72 | Babic, Marian | -45054 | 72
105-11 | 8389-King Salman Park Project | 1252 | 8389-King Salman Park Project-Services-Installation and configuration-8389 SS | APPROVED | No | 2023-05-11 | Abas, Mohammed Fekry | 2023-05-15 | 2023-05-15 |  |  |  | 1343800 | 5215 | 0 | STANDARD | Hussain Ali Hussain Contracting Company | SAR | 1343800 | APPROVED |  |  | 2024-03-18 | 0 | 308 | Babic, Marian | -45061 | 308
105-11 | 8389-King Salman Park Project | 1254 | 8389-King Salman Park Project-Reactor TPI for 8388 & 8389 SS | APPROVED | No | 2023-05-11 | Abas, Mohammed Fekry | 2023-05-15 | 2023-05-15 |  |  |  | 4800 | 4469 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 4762.5 | APPROVED |  |  | 2023-05-25 | 37.5 | 10 | Babic, Marian | -45061 | 10
105-11 | 8389-King Salman Park Project | 1274 | 8389-King Salman Park Project-Overhead Travelling Crane TPI-8389 | APPROVED | No | 2023-05-17 | Abas, Mohammed Fekry | 2023-05-23 | 2023-05-24 |  |  |  | 1600 | 4370 | 1 | STANDARD | SGS INSPECTION SERVICES SA. LTD | SAR | 800 | APPROVED |  |  | 2023-05-29 | 800 | 5 | Babic, Marian | -45070 | 5
105-11 | 8389-King Salman Park Project | 1285 | 8389-King Salman Park Project-Power Transformer Oil filteration -8389 SS | APPROVED | No | 2023-05-25 | Abas, Mohammed Fekry | 2023-05-28 | 2023-05-28 |  |  |  | 100000 | 4552 | 0 | STANDARD | Al-Handasah Al-Namuudhajyyah Contracting Company | SAR | 57000 | APPROVED |  |  | 2023-07-27 | 43000 | 60 | Babic, Marian | -45074 | 60
105-11 | 8389-King Salman Park Project | 1308 | 8389-King Salman Park Project-DSM TPI - King Salman Park- 8388 & 8389 SS | APPROVED | No | 2023-06-06 | Abas, Mohammed Fekry | 2023-06-13 | 2023-06-13 |  |  |  | 13000 | 4522 | 0 | STANDARD | SGS GULF LIMITED | USD | 12956.25 | APPROVED |  |  | 2023-06-15 | 43.75 | 2 | Babic, Marian | -45090 | 2
105-11 | 8389-King Salman Park Project | 1375 | 8389-King Salman Park Project-Supply & Installation of Security Cameras for site Surveillance (8389 & 8390) | RETURNED | No | 2023-07-26 | Babic, Marian | 2024-01-25 | 2023-08-01 | 2024-01-25 |  | As per phone conversation betweem Mr. Saeed and Mr. Ishfaq | 17260 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45139 | -45139
105-11 | 8389-King Salman Park Project | 1404 | 8389-King Salman Park Project-TPI (AC-DC Panels # SS 8389) | APPROVED | No | 2023-08-10 | Abas, Mohammed Fekry | 2023-08-14 | 2023-08-16 |  |  |  | 1400 | 4574 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 1400 | APPROVED |  |  | 2023-08-22 | 0 | 6 | Babic, Marian | -45154 | 6
105-11 | 8389-King Salman Park Project | 1420 | 8389-King Salman Park Project-THHN Wires (Lighting Cables) SS # 8389 | APPROVED | No | 2023-08-21 | Abas, Mohammed Fekry | 2023-08-24 | 2023-08-24 |  |  |  | 21000 | 4827 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 21000 | APPROVED |  |  | 2023-12-31 | 0 | 129 | Babic, Marian | -45162 | 129
105-11 | 8389-King Salman Park Project | 1433 | 8389-King Salman Park Project-TPI Services for LV Power & Control Cables (all KSP projects) | APPROVED | No | 2023-08-23 | Abas, Mohammed Fekry | 2023-08-28 | 2023-08-28 |  |  |  | 4200 | 4597 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 4200 | APPROVED |  |  | 2023-09-10 | 0 | 13 | Babic, Marian | -45166 | 13
105-11 | 8389-King Salman Park Project | 1673 | 8389-King Salman Park Project-Lighting Fixture (indoor - Outdoor) Nardeen for SS 8389 | APPROVED | No | 2023-11-09 | Abas, Mohammed Fekry | 2023-11-14 | 2023-11-15 |  |  |  | 58607.15 | 4725 | 0 | STANDARD | Nardeen Lighting Company Ltd. | SAR | 57810.65 | APPROVED |  |  | 2023-11-26 | 796.5 | 11 | Babic, Marian | -45245 | 11
105-11 | 8389-King Salman Park Project | 1691 | 8389-King Salman Park Project-RGS Conduits and Accessories (Lighting works) 8389 | RETURNED | No | 2023-11-12 | Babic, Marian | 2024-03-26 | 2023-11-14 | 2024-03-26 |  | PO for this subject already issued, this PR is a balance which is not needed | 55353 | 4792 | 0 | STANDARD | ELECTRIC HOUSE EST. | SAR | 20076.6 | APPROVED |  |  | 2023-12-10 | 35276.4 |  | Babic, Marian | -45244 | 26
105-11 | 8389-King Salman Park Project | 1691 | 8389-King Salman Park Project-RGS Conduits and Accessories (Lighting works) 8389 | RETURNED | No | 2023-11-12 | Babic, Marian | 2024-03-26 | 2023-11-14 | 2024-03-26 |  | PO for this subject already issued, this PR is a balance which is not needed | 832.72 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45244 | -45244
105-11 | 8389-King Salman Park Project | 1695 | 8389-King Salman Park Project-Lighting Poles @ SS 8389 | APPROVED | No | 2023-11-12 | Abas, Mohammed Fekry | 2023-11-14 | 2023-11-14 |  |  |  | 12080 | 4806 | 0 | STANDARD | Hesham El-Sewedy Trading Co. LTD. | SAR | 12080 | APPROVED |  |  | 2023-12-14 | 0 | 30 | Babic, Marian | -45244 | 30
105-11 | 8389-King Salman Park Project | 1749 | 8389-King Salman Park Project-Power Receptacle for 8389 ( budget line item 1.21) | APPROVED | No | 2023-11-15 | Abas, Mohammed Fekry | 2023-11-21 | 2023-11-21 |  |  |  | 77103.26 | 4877 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 58780 | APPROVED |  |  | 2023-12-31 | 18323.26 | 40 | Babic, Marian | -45251 | 40
105-11 | 8389-King Salman Park Project | 2178 | 8389-King Salman Park Project-SIS FAT. TPI services SS 8389 | INCOMPLETE | No |  | Almehmadi, Fahed | 2024-01-16 |  |  |  |  | 6225 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-11 | 8389-King Salman Park Project | 2180 | 8389-King Salman Park Project-SIS FAT. TPI services SS 8389 | APPROVED | No | 2024-01-16 | Abas, Mohammed Fekry | 2024-01-21 | 2024-01-21 |  |  |  | 6225 | 5015 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | SAR | 6225 | APPROVED |  |  | 2024-02-01 | 0 | 11 | Babic, Marian | -45312 | 11
105-11 | 8389-King Salman Park Project | 2571 | 8389-King Salman Park Project-perforated cable tray (from budget line item 1.22 ) | APPROVED | No | 2024-02-15 | Abas, Mohammed Fekry | 2024-02-19 | 2024-02-20 |  |  |  | 41438.89 | 5111 | 0 | STANDARD | AL-ASHOURY FACTORY FOR CABLE SUPPORTS COMPANY(S) | SAR | 43831.21 | APPROVED |  |  | 2024-03-24 | -2392.32 | 33 | Babic, Marian | -45342 | 33
105-11 | 8389-King Salman Park Project | 2610 | 8389-King Salman Park Project-ACSR Connectors ( Budget Line Item 1.26) | RETURNED | No | 2024-02-19 | Babic, Marian | 2024-03-12 | 2024-02-26 | 2024-03-12 |  | please revise the price | 4752.3 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45348 | -45348
105-11 | 8389-King Salman Park Project | 2641 | 8389-King Salman Park Project-Installation of Capacitor Banks on Civil Foundation SS 8389 (Budget Line item 1.19) | APPROVED | No | 2024-02-21 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 30000 | 5173 | 0 | STANDARD | YASIR M ALI AL-ZAHRANI EST. | SAR | 30000 | APPROVED |  |  | 2024-03-12 | 0 | 15 | Babic, Marian | -45348 | 15
105-11 | 8389-King Salman Park Project | 2666 | 8389-King Salman Park Project-Lighitng Installation works for S/S 8389 (Budget Line item # 1.34) | APPROVED | No | 2024-02-25 | Abas, Mohammed Fekry | 2024-02-27 | 2024-02-28 |  |  |  | 200000 | 5215 | 0 | STANDARD | Hussain Ali Hussain Contracting Company | SAR | 200000 | APPROVED |  |  | 2024-03-18 | 0 | 19 | Babic, Marian | -45350 | 19
105-11 | 8389-King Salman Park Project | 2675 | 8389-King Salman Park Project-Testing & Commissioning Services for SS 8389 (Budget Line item # 1.36) | APPROVED | No | 2024-02-25 | Abas, Mohammed Fekry | 2024-02-27 | 2024-02-28 |  |  |  | 964701 | 5207 | 0 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 618539 | APPROVED |  |  | 2024-05-19 | 346162 | 81 | Babic, Marian | -45350 | 81
105-11 | 8389-King Salman Park Project | 2693 | 8389-King Salman Park Project-Rental Manpower for S/S # 8389 (Budget Line item 1.50) | APPROVED | No | 2024-02-26 | Abas, Mohammed Fekry | 2024-02-29 | 2024-03-03 |  |  |  | 324480 | 5148 | 0 | STANDARD | Jasem M.AlJasem Contracting Est. | SAR | 324428 | APPROVED |  |  | 2024-03-25 | 52 | 22 | Babic, Marian | -45354 | 22
105-11 | 8389-King Salman Park Project | 2699 | 8389-King Salman Park Project-Third party Testing for Precast Boundary Wall (Budget Item # 1.29) | APPROVED | No | 2024-02-26 | Abas, Mohammed Fekry | 2024-02-29 | 2024-03-03 |  |  |  | 30000 | 5251 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 30000 | APPROVED |  |  | 2024-03-26 | 0 | 23 | Babic, Marian | -45354 | 23
105-11 | 8389-King Salman Park Project | 2727 | 8389-King Salman Park Project-Pumps for Civil Works SS # 8389 (Budget Line item 1.19) (to convert Manual PO # 8558) | APPROVED | No | 2024-03-03 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 65000 | 5175 | 0 | STANDARD | Lamah CO. LTD .for T | SAR | 65000 | APPROVED |  |  | 2024-04-24 | 0 | 48 | Babic, Marian | -45358 | 48
105-11 | 8389-King Salman Park Project | 2730 | 8389-King Salman Park Project-Building Precast SS # 8389 (Budget Line item 1.19. for the conversion of Manual PO # 8082 to Oracle PO) | APPROVED | No | 2024-03-03 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 1280470 | 5178 | 0 | STANDARD | EASTERN READYMIX CONCRETE COMPANY | SAR | 1280470 | APPROVED |  |  | 2024-03-18 | 0 | 11 | Babic, Marian | -45358 | 11
105-11 | 8389-King Salman Park Project | 2735 | 8389-King Salman Park Project-Boundary Wall Precast for SS # 8389 (Budget Line item 1.19) | APPROVED | No | 2024-03-03 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 427766.38 | 5225 | 0 | STANDARD | Prainsa Saudi for precast Concrete | SAR | 427766.38 | APPROVED |  |  | 2024-04-03 | 0 | 27 | Babic, Marian | -45358 | 27
105-11 | 8389-King Salman Park Project | 2751 | 8389-King Salman Park Project-Outdoor Steel Structure for SIS & Capacitor Cable Support | APPROVED | No | 2024-03-04 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 83810 | 5183 | 0 | STANDARD | Energy Field Trading Est | SAR | 83810 | APPROVED |  |  | 2024-03-17 | 0 | 10 | Babic, Marian | -45358 | 10
105-11 | 8389-King Salman Park Project | 2792 | 8389-King Salman Park Project-Installation Services for SS # 8389 (Budget Line item 1.34) | APPROVED | No | 2024-03-05 | Abas, Mohammed Fekry | 2024-03-11 | 2024-03-11 |  |  |  | 204840 | 5215 | 0 | STANDARD | Hussain Ali Hussain Contracting Company | SAR | 204840 | APPROVED |  |  | 2024-03-18 | 0 | 7 | Babic, Marian | -45362 | 7
105-11 | 8389-King Salman Park Project | 2988 | 8389-King Salman Park Project-Fire Fighitng Scope @ 8389 (from Budget Line item 1.18) Manual PO # 8123 conversion | APPROVED | No | 2024-04-03 | Abas, Mohammed Fekry | 2024-04-04 | 2024-04-04 |  |  |  | 1500000 | 5399 | 0 | STANDARD | Equipment & Technical Services Co.(ETECHS) | SAR | 1500000 | APPROVED |  |  | 2024-04-18 | 0 | 14 | Babic, Marian | -45386 | 14
105-11 | 8389-King Salman Park Project | 2993 | 8389-King Salman Park Project-Testing & Commissioning @ 8389. (Budget Line item # 1.36) | APPROVED | No | 2024-04-04 | Abas, Mohammed Fekry | 2024-04-04 | 2024-04-04 |  |  |  | 1000000 | 5207 | 0 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 1000000 | APPROVED |  |  | 2024-05-19 | 0 | 45 | Babic, Marian | -45386 | 45
105-11 | 8389-King Salman Park Project | 3063 | 8389-King Salman Park Project-Fiber Optic Patch Panel (budget line item 1.21) | APPROVED | No | 2024-04-19 | Abas, Mohammed Fekry | 2024-04-22 | 2024-04-23 |  |  |  | 49600 | 5472 | 0 | STANDARD | AMWAJ TELECOMMUNICATION MFG. CO. | SAR | 46300 | APPROVED |  |  | 2024-05-08 | 3300 | 15 | Babic, Marian | -45405 | 15
105-11 | 8389-King Salman Park Project | 3086 | 8389-King Salman Park Project-MV Termination Kits @ 8389 (for conversion of Manual PO# 8532) to oracle PO. Budget Line item # 1.20 (termination power Cables) and 1.29 service 1 item | APPROVED | No | 2024-04-21 | Abas, Mohammed Fekry | 2024-04-22 | 2024-04-23 |  |  |  | 47557 | 5446 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 44703.58 | APPROVED |  |  | 2024-05-05 | 2853.42 | 12 | Babic, Marian | -45405 | 12
105-11 | 8389-King Salman Park Project | 3111 | 8389-King Salman Park Project-SAS Furnitures @ 8389 (under Budget Line # 1.6) for conversion of Manual PO # 8253 | APPROVED | No | 2024-04-23 | Abas, Mohammed Fekry | 2024-04-28 | 2024-04-29 |  |  |  | 55000 | 5482 | 0 | STANDARD | ALFANAR CO | SAR | 55000 | APPROVED |  |  | 2024-05-12 | 0 | 13 | Babic, Marian | -45411 | 13
105-11 | 8389-King Salman Park Project | 3115 | 8389-King Salman Park Project-Cyber Security SS 8389 (Manual PO # 8170) Budget Line # 1.8 | APPROVED | No | 2024-04-23 | Abas, Mohammed Fekry | 2024-04-28 | 2024-04-29 |  |  |  | 1400000 | 5489 | 0 | STANDARD | ALFANAR CO | SAR | 1400000 | APPROVED |  |  | 2024-05-16 | 0 | 17 | Kumar, Mr. Ranjan | -45411 | 17
105-11 | 8389-King Salman Park Project | 3166 | 8389-King Salman Park Project-150.mm2 Bare Cu. Conductor SS 8389 | APPROVED | No | 2024-04-28 | Abas, Mohammed Fekry | 2024-04-30 | 2024-05-01 |  |  |  | 55000 | 5496 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 51821.1 | APPROVED |  |  | 2024-05-21 | 3178.9 | 20 | Babic, Marian | -45413 | 20
105-11 | 8389-King Salman Park Project | 3286 | 8389-King Salman Park Project-Lighting Accessories (Budget Line Item 1.21) | APPROVED | No | 2024-05-04 | Abas, Mohammed Fekry | 2024-05-06 | 2024-05-07 |  |  |  | 24683.2 | 5508 | 0 | STANDARD | Current Makers For Contracting EST | SAR | 23280 | APPROVED |  |  | 2024-05-21 | 1403.2 | 14 | Babic, Marian | -45419 | 14
105-11 | 8389-King Salman Park Project | 3302 | 8389-King Salman Park Project- Fire Stop material (Budget Line Item 1.19) | APPROVED | No | 2024-05-05 | Abas, Mohammed Fekry | 2024-05-06 | 2024-05-07 |  |  |  | 91980 | 5516 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 76210 | APPROVED |  |  | 2024-05-21 | 15770 | 14 | Babic, Marian | -45419 | 14
105-11 | 8389-King Salman Park Project | 3369 | 8389-King Salman Park Project-HV Connectors (for ACSR Conductor) (material from Budget Line item 1.26 & ) & (Shipment from line item #1.37) | APPROVED | No | 2024-05-12 | Abas, Mohammed Fekry | 2024-05-14 | 2024-05-14 |  |  |  | 7422.21 | 5154 | 0 | STANDARD | Arruti Subestaciones , S.A.U | EUR | 7716.76 | APPROVED |  |  | 2024-05-27 | -294.55 | 13 | Babic, Marian | -45426 | 13
105-11 | 8389-King Salman Park Project | 3594 | 8389-King Salman Park Project-Third party Testing for Precast Boundary Wall (for SAFCO PO # 5251 amendment) (Budget Item # 1.29) | REJECTED | No | 2024-06-05 | Almehmadi, Fahed | 2024-06-05 |  |  | 2024-06-05 | To Increase the Amount, as per Site team feedback | 10000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-11 | 8389-King Salman Park Project | 3600 | 8389-King Salman Park Project-Third party Testing for Precast Boundary Wall (for SAFCO PO # 5251 Amendment) (Budget Item # 1.29) | APPROVED | No | 2024-06-05 | Abas, Mohammed Fekry | 2024-06-05 | 2024-06-06 |  |  |  | 17000 | 5251 | 1 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 17000 | APPROVED |  |  | 2024-06-26 | 0 | 20 | Babic, Marian | -45449 | 20
105-11 | 8389-King Salman Park Project | 3688 | 8389-King Salman Park Project-Cable Ladder / Tray Material (Manual PO # 8240) Conversion to Oracle PO SS 8389 | APPROVED | No | 2024-06-29 | Abas, Mohammed Fekry | 2024-07-04 | 2024-07-07 |  |  |  | 275466.93 | 5788 | 0 | STANDARD | AL-AMAL ELECTRICAL SWITCHBOARDS | SAR | 275466.93 | APPROVED |  |  | 2024-07-17 | 0 | 10 | Babic, Marian | -45480 | 10
105-11 | 8389-King Salman Park Project | 3768 | 8389-King Salman Park Project-Final Inspection & Certification of Capacitor Bank Installation (optional Price in PO # 5173) | APPROVED | No | 2024-07-04 | Abas, Mohammed Fekry | 2024-07-07 | 2024-07-08 |  |  |  | 14500 | 5173 | 1 | STANDARD | YASIR M ALI AL-ZAHRANI EST. | SAR | 14500 | APPROVED |  |  | 2024-07-12 | 0 | 4 | Babic, Marian | -45481 | 4
105-11 | 8389-King Salman Park Project | 4606 | 8389-King Salman Park Project-AMI T&C budget line (1.36) | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-14 | 2024-10-14 |  |  |  | 60000 | 6341 | 0 | STANDARD | SYSTEM HOUSE FACTORY FOR ELECTRIC PANELS (SEP) | SAR | 53750 | APPROVED |  |  | 2024-10-30 | 6250 | 16 | Babic, Marian | -45579 | 16
105-11 | 8389-King Salman Park Project | 5053 | 8389-King Salman Park Project-PDS System for SS 8389 (Conversion of MAunal PO # 8703 to ORacle PO) Budget line # 1.7 | APPROVED | No | 2024-11-26 | Abas, Mohammed Fekry | 2024-12-02 | 2024-12-02 |  |  |  | 155500 | 6576 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 155500 | APPROVED |  |  | 2024-12-05 | 0 | 3 | Babic, Marian | -45628 | 3
105-11 | 8389-King Salman Park Project | 5070 | 8389-King Salman Park Project-Fiber Optic Cable works 8389 (Converting Manual PO # 8536 to Oracle) Budget line # 1.20 (Fiber) | APPROVED | No | 2024-11-27 | Abas, Mohammed Fekry | 2024-12-02 | 2024-12-02 |  |  |  | 174000 | 6579 | 0 | STANDARD | SMART TECH | SAR | 174000 | APPROVED |  |  | 2024-12-05 | 0 | 3 | Babic, Marian | -45628 | 3
105-11 | 8389-King Salman Park Project | 5173 | 8389-King Salman Park Project-Conversion of Manual PO # 8154 (Rev-0) to Oracle PO_ Budget Line # 1.24 Control Cables | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-10 |  |  |  | 303170.98 | 6623 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 303170.98 | APPROVED |  |  | 2024-12-23 | 0 | 13 | Babic, Marian | -45636 | 13
105-11 | 8389-King Salman Park Project | 5174 | 8389-King Salman Park Project-Conversion of Manual PO # 8154 (Rev-0) to Oracle PO_ Budget Line # 1.26 LV Power Cables | APPROVED | No | 2024-12-06 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-10 |  |  |  | 446868.65 | 6623 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 446868.65 | APPROVED |  |  | 2024-12-23 | 0 | 13 | Babic, Marian | -45636 | 13
105-11 | 8389-King Salman Park Project | 5175 | 8389-King Salman Park Project-Conversion of Manual PO # 8154 (Rev-1) to Oracle PO_ Budget Line # 1.24 Control Cables | REJECTED | No | 2024-12-06 | Shoujra, Ishfaq Yousef | 2024-12-06 |  |  | 2024-12-06 | 3rd line item to be corrected | 107200.6 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-11 | 8389-King Salman Park Project | 5176 | 8389-King Salman Park Project-Conversion of Manual PO # 8154 (Rev-1) to Oracle PO_ Budget Line # 1.24 Control Cables | APPROVED | No | 2024-12-06 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-10 |  |  |  | 113452.65 | 6623 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 113452.65 | APPROVED |  |  | 2024-12-23 | 0 | 13 | Babic, Marian | -45636 | 13
105-11 | 8389-King Salman Park Project | 5177 | 8389-King Salman Park Project-Conversion of Manual PO # 8154 (Rev-1) to Oracle PO_ Budget Line # 1.26 LV Power Cables | APPROVED | No | 2024-12-06 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-10 |  |  |  | 16258 | 6623 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 16258 | APPROVED |  |  | 2024-12-23 | 0 | 13 | Babic, Marian | -45636 | 13
105-11 | 8389-King Salman Park Project | 5186 | 8389-King Salman Park Project-Conversion of Manual PO # 8154 (Rev-0) to Oracle PO_ Budget Line # 1.25 MV Cable | APPROVED | No | 2024-12-08 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-10 |  |  |  | 178466.4 | 6623 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 178466.4 | APPROVED |  |  | 2024-12-23 | 0 | 13 | Babic, Marian | -45636 | 13
105-11 | 8389-King Salman Park Project | 5214 | 8389-King Salman Park Project-Adjustment (adding + de-scoping some items) of PO # 4275 (due to additional Qty Ordered previously before PO issuance) | APPROVED | No | 2024-12-10 | Abas, Mohammed Fekry | 2024-12-17 | 2024-12-17 |  |  |  | 14381.5 | 4275 | 1 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 5966.5 | APPROVED |  |  | 2025-01-16 | 8415 | 30 | Babic, Marian | -45643 | 30
105-11 | 8389-King Salman Park Project | 5556 | 8389-King Salman Park Project-Conversion of Manual PO # 8591 to Oracle PO (budget line item # 1.26) | APPROVED | No | 2025-01-23 | Abas, Mohammed Fekry | 2025-01-28 | 2025-01-30 |  |  |  | 6260 | 6859 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 6260 | APPROVED |  |  | 2025-02-06 | 0 | 7 | Babic, Marian | -45687 | 7
105-11 | 8389-King Salman Park Project | 5728 | 8389-King Salman Park Project-Lugs & Glands- Conversion of Manual PO # 8844 to Oracle PO (1.21) | APPROVED | No | 2025-01-29 | Abas, Mohammed Fekry | 2025-02-05 | 2025-02-05 |  |  |  | 26976 | 6873 | 0 | STANDARD | MOHAMMAD RASHID SARWAR EST. | SAR | 25976 | APPROVED |  |  | 2025-02-12 | 1000 | 7 | Babic, Marian | -45693 | 7
105-11 | 8389-King Salman Park Project | 5759 | 8389-King Salman Park Project-Red Blue Black Yellow & YellowGreen Bahara Cables @THHN WIRES | APPROVED | No | 2025-02-03 | Abas, Mohammed Fekry | 2025-02-04 | 2025-02-05 |  |  |  | 37751 | 6883 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 36807 | APPROVED |  |  | 2025-02-17 | 944 | 12 | Babic, Marian | -45693 | 12
105-11 | 8389-King Salman Park Project | 6220 | 8389-King Salman Park Project-Additional BARE COPPER CONDUCTOR for 8388/89 @ 353m from 8389 Budget (1.23) | APPROVED | No | 2025-03-20 | Abas, Mohammed Fekry | 2025-03-25 | 2025-03-25 |  |  | Additional BARE COPPER CONDUCTOR for 8388/89 @ 353m from 8389 Budget (1.23) | 19415 | 5496 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 18282.72 | APPROVED |  |  | 2025-04-08 | 1132.28 | 14 | Babic, Marian | -45741 | 14
105-11 | 8389-King Salman Park Project | 6279 | 8389-King Salman Park Project-Alu Cable Tray's and Accessories for SS 8389 (BIL #1.22) | APPROVED | No | 2025-03-25 | Abas, Mohammed Fekry | 2025-03-27 | 2025-03-27 |  |  | Alu Cable Tray's and Accessories for SS 8389 (BIL #1.22) | 12721.44 | 5112 | 1 | STANDARD | AL-ASHOURY FACTORY FOR CABLE SUPPORTS COMPANY(S) | SAR | 11449.3 | APPROVED |  |  | 2025-04-15 | 1272.14 | 19 | Babic, Marian | -45743 | 19
105-11 | 8389-King Salman Park Project | 6404 | 8389-King Salman Park Project-Y/G Cables @ ALFANAR- Conversion of Manual PO # 8815 to Oracle | APPROVED | No | 2025-04-21 | Abas, Mohammed Fekry | 2025-04-30 | 2025-05-04 |  |  | Y/G Cables @ ALFANAR- Conversion of Manual PO # 8815 to Oracle | 44620 | 7224 | 0 | STANDARD | ALFANAR CO | SAR | 44620 | APPROVED |  |  | 2025-05-12 | 0 | 8 | Babic, Marian | -45781 | 8
105-11 | 8389-King Salman Park Project | 6681 | 8389-King Salman Park Project-Additional #1000m -BARE COPPER Conductor for SS- 8389 | APPROVED | No | 2025-05-21 | Abas, Mohammed Fekry | 2025-05-27 | 2025-05-27 |  |  | Additional #1000m -BARE COPPER Conductor for SS- 8389 | 52000 | 5496 | 2 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 51821.1 | APPROVED |  |  | 2025-06-04 | 178.9 | 8 | Babic, Marian | -45804 | 8
105-11 | 8389-King Salman Park Project | 6743 | 8389-King Salman Park Project-Pre-Energization Oil Sampling Tests (Power + Station Service Transformers) | APPROVED | No | 2025-05-28 | Abas, Mohammed Fekry | 2025-06-04 | 2025-06-04 |  |  | Pre-Energization Oil Sampling Tests (Power + Station Service Transformers) | 35585 | 7407 | 0 | STANDARD | Gulf Laboratory Technical Services (S) | SAR | 35585 | APPROVED |  |  | 2025-06-17 | 0 | 13 | Babic, Marian | -45812 | 13
105-11 | 8389-King Salman Park Project | 7259 | 8389-King Salman Park Project-Earthing Material for Civil Works | APPROVED | No | 2025-08-03 | Abas, Mohammed Fekry | 2025-08-11 | 2025-08-11 |  |  | Earthing Material for Civil Works | 110545 | 7684 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 106442 | APPROVED |  |  | 2025-10-05 | 4103 | 55 | Babic, Marian | -45880 | 55
105-11 | 8389-King Salman Park Project | 7304 | Cu/Pvc _R-Blu-Blk-Y-Grey_Flexibile Wires | REJECTED | No | 2025-08-06 | Yasmin, Ahmed Elsayed Mohamed | 2025-08-10 | 2025-08-07 |  | 2025-08-12 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45876 | -45876
105-11 | 8389-King Salman Park Project | 7525 | Rental Safety Officer_SS 8389 | RETURNED | No | 2025-08-27 | Abuhammad, Samir | 2025-09-16 | 2025-09-04 |  |  | As per Management approval, we need rental Safety Officer for remote end activities temporarily for 6 months only. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45904 | -45904
105-11 | 8389-King Salman Park Project | 7909 | Supply & Installation of HVAC Platforms | REJECTED | No | 2025-10-06 | Yasmin, Ahmed Elsayed Mohamed | 2025-10-08 | 2025-10-08 |  | 2025-10-13 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45938 | -45938
105-11 | 8389-King Salman Park Project | 7961 | Maintenance Platforms | RETURNED | No | 2025-10-15 | Hegazy, Ayman | 2025-12-11 | 2025-12-09 |  |  | Maintenance Platforms | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -46000 | -46000
105-11 | 8389-King Salman Park Project | 8510 | Maintenance Platforms | APPROVED | No | 2025-12-11 | Abas, Mohammed Fekry | 2025-12-15 | 2025-12-17 |  |  | Maintenance Platforms | 0 | 7971 | 0 | STANDARD | Fursan Construction Industry Factory Industry Factory | SAR | 16800 | APPROVED |  |  | 2025-12-29 | -16800 | 12 | Hegazy, Ayman | -46008 | 12
105-12 | 8390-King Salman Park Project | 198 | 8390-King Salman Park Project-Engineering & Design | APPROVED | No | 2021-11-18 | Abas, Mohammed Fekry | 2021-11-18 | 2021-11-21 |  |  |  | 200000 | 3873 | 0 | STANDARD | Fahd Alireza Engineering Consultants | SAR | 195000 | APPROVED |  |  | 2021-11-29 | 5000 | 8 | Babic, Marian | -44521 | 8
105-12 | 8390-King Salman Park Project | 198 | 8390-King Salman Park Project-Engineering & Design | APPROVED | No | 2021-11-18 | Abas, Mohammed Fekry | 2021-11-18 | 2021-11-21 |  |  |  | 200000 | 3873 | 1 | STANDARD | Fahd Alireza Engineering Consultants | SAR | 195000 | APPROVED |  |  | 2022-11-29 | 5000 | 373 | Babic, Marian | -44521 | 373
105-12 | 8390-King Salman Park Project | 272 | 8390-King Salman Park Project-8390- Panels, SCADA/SAS | APPROVED | No | 2021-11-23 | Abas, Mohammed Fekry | 2021-11-23 | 2021-11-24 |  |  |  | 1295465 | 3882 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 1295465 | APPROVED |  |  | 2021-12-01 | 0 | 7 | Babic, Marian | -44524 | 7
105-12 | 8390-King Salman Park Project | 272 | 8390-King Salman Park Project-8390- Panels, SCADA/SAS | APPROVED | No | 2021-11-23 | Abas, Mohammed Fekry | 2021-11-23 | 2021-11-24 |  |  |  | 1295465 | 3882 | 1 | STANDARD | Hitachi Energy Ltd | SAR | 1295465 | REJECTED |  |  |  | 0 |  | Babic, Marian | -44524 | -44524
105-12 | 8390-King Salman Park Project | 273 | 8390-King Salman Park Project-8390- Panels- Control | APPROVED | No | 2021-11-23 | Abas, Mohammed Fekry | 2021-11-23 | 2021-11-24 |  |  |  | 280121 | 3882 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 280121 | APPROVED |  |  | 2021-12-01 | 0 | 7 | Babic, Marian | -44524 | 7
105-12 | 8390-King Salman Park Project | 273 | 8390-King Salman Park Project-8390- Panels- Control | APPROVED | No | 2021-11-23 | Abas, Mohammed Fekry | 2021-11-23 | 2021-11-24 |  |  |  | 280121 | 3882 | 1 | STANDARD | Hitachi Energy Ltd | SAR | 280121 | REJECTED |  |  |  | 0 |  | Babic, Marian | -44524 | -44524
105-12 | 8390-King Salman Park Project | 274 | 8390-King Salman Park Project-8390- Panels Protection | APPROVED | No | 2021-11-23 | Abas, Mohammed Fekry | 2021-11-23 | 2021-11-24 |  |  |  | 2181345 | 3882 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 2181345 | APPROVED |  |  | 2021-12-01 | 0 | 7 | Babic, Marian | -44524 | 7
105-12 | 8390-King Salman Park Project | 274 | 8390-King Salman Park Project-8390- Panels Protection | APPROVED | No | 2021-11-23 | Abas, Mohammed Fekry | 2021-11-23 | 2021-11-24 |  |  |  | 2181345 | 3882 | 1 | STANDARD | Hitachi Energy Ltd | SAR | 2181345 | REJECTED |  |  |  | 0 |  | Babic, Marian | -44524 | -44524
105-12 | 8390-King Salman Park Project | 276 | 8390-King Salman Park Project-8390-Communication panels | APPROVED | No | 2021-11-23 | Abas, Mohammed Fekry | 2021-11-23 | 2021-11-24 |  |  |  | 1918660 | 3877 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 1918660 | APPROVED |  |  | 2021-12-01 | 0 | 7 | Babic, Marian | -44524 | 7
105-12 | 8390-King Salman Park Project | 280 | 8390-King Salman Park Project-8390-Geo Technical Investigation | APPROVED | No | 2021-11-23 | Abas, Mohammed Fekry | 2021-11-24 | 2021-11-28 |  |  |  | 25000 | 3919 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 15730 | APPROVED |  |  | 2021-12-22 | 9270 | 24 | Babic, Marian | -44528 | 24
105-12 | 8390-King Salman Park Project | 294 | 8390-King Salman Park Project-Capacitor bank 13.8kV, 7 MVAR | APPROVED | No | 2021-12-01 | Abas, Mohammed Fekry | 2021-12-05 | 2021-12-06 |  |  |  | 750000 | 3974 | 0 | STANDARD | EATON (COOPER POWER SYSTEMS) | USD | 736218.75 | APPROVED |  |  | 2022-03-09 | 13781.25 | 93 | Babic, Marian | -44536 | 93
105-12 | 8390-King Salman Park Project | 408 | 8390-King Salman Park Project-8390- 132kV GIS | APPROVED | No | 2022-01-20 | Abas, Mohammed Fekry | 2022-01-23 | 2022-01-24 |  |  |  | 7790812.5 | 3963 | 0 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 7790812.5 | APPROVED |  |  | 2022-02-10 | 0 | 17 | Babic, Marian | -44585 | 17
105-12 | 8390-King Salman Park Project | 409 | 8390-King Salman Park Project-8390- 132kV GIS Service & CIF | APPROVED | No | 2022-01-20 | Abas, Mohammed Fekry | 2022-01-23 | 2022-01-24 |  |  |  | 697312.5 | 3963 | 0 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 706028.91 | APPROVED |  |  | 2022-02-10 | -8716.41 | 17 | Babic, Marian | -44585 | 17
105-12 | 8390-King Salman Park Project | 410 | 8390-King Salman Park Project-8390- 67MVA Power Transformer | APPROVED | No | 2022-01-20 | Abas, Mohammed Fekry | 2022-01-23 | 2022-01-24 |  |  |  | 8716087.5 | 4167 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 8716087.5 | APPROVED |  |  | 2022-07-31 | 0 | 188 | Babic, Marian | -44585 | 188
105-12 | 8390-King Salman Park Project | 411 | 8390-King Salman Park Project-8390- 67MVA Power Transformer Service & CIF | APPROVED | No | 2022-01-20 | Abas, Mohammed Fekry | 2022-01-23 | 2022-01-24 |  |  |  | 691162.5 | 4167 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 136500 | APPROVED |  |  | 2022-07-31 | 554662.5 | 188 | Babic, Marian | -44585 | 188
105-12 | 8390-King Salman Park Project | 419 | 8390-King Salman Park Project-8390- 13.8kV NGR | APPROVED | No | 2022-01-24 | Abas, Mohammed Fekry | 2022-01-25 | 2022-01-26 |  |  |  | 75000 | 4021 | 0 | STANDARD | National Switchgears | USD | 63562.2 | APPROVED |  |  | 2022-03-17 | 11437.8 | 50 | AlQuraish, Sajjad Hazem | -44587 | 50
105-12 | 8390-King Salman Park Project | 424 | 8390-King Salman Park Project-8390- 132kV Surge arresters | APPROVED | No | 2022-01-24 | Abas, Mohammed Fekry | 2022-01-25 | 2022-01-26 |  |  |  | 51000 | 4003 | 0 | STANDARD | 2100698 Siemens Energy Global GmbH & Co. KG | EUR | 50991.52 | APPROVED |  |  | 2022-03-08 | 8.48 | 41 | AlQuraish, Sajjad Hazem | -44587 | 41
105-12 | 8390-King Salman Park Project | 430 | 8390-King Salman Park Project-8390- 13.8kV MV Switchgear panels | APPROVED | No | 2022-01-24 | Abas, Mohammed Fekry | 2022-01-25 | 2022-01-26 |  |  |  | 5750000 | 3962 | 0 | STANDARD | ALFANAR CO | SAR | 5750000 | APPROVED |  |  | 2022-02-06 | 0 | 11 | Babic, Marian | -44587 | 11
105-12 | 8390-King Salman Park Project | 447 | 8390-King Salman Park Project-8390- 13.8kV RMU | APPROVED | No | 2022-01-31 | Abas, Mohammed Fekry | 2022-02-02 | 2022-02-02 |  |  |  | 150000 | 3987 | 0 | STANDARD | ALFANAR CO | SAR | 58000 | APPROVED |  |  | 2022-09-05 | 92000 | 215 | Babic, Marian | -44594 | 215
105-12 | 8390-King Salman Park Project | 464 | 8390-King Salman Park Project-8390 Porta cabins for Site Office (12x4mtr) Delivery & Installation | APPROVED | No | 2022-02-01 | Abas, Mohammed Fekry | 2022-02-03 | 2022-02-07 |  |  |  | 50000 | 4008 | 0 | STANDARD | Allied General Contracting Est. | SAR | 41850 | APPROVED |  |  | 2022-03-08 | 8150 | 29 | AlQuraish, Sajjad Hazem | -44599 | 29
105-12 | 8390-King Salman Park Project | 464 | 8390-King Salman Park Project-8390 Porta cabins for Site Office (12x4mtr) Delivery & Installation | APPROVED | No | 2022-02-01 | Abas, Mohammed Fekry | 2022-02-03 | 2022-02-07 |  |  |  | 50000 | 4082 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 44000 | APPROVED |  |  | 2022-04-14 | 6000 | 66 | Babic, Marian | -44599 | 66
105-12 | 8390-King Salman Park Project | 465 | 8390-King Salman Park Project-8390- Security Cabin for Site office (Delivery & Installation) | APPROVED | No | 2022-02-01 | Abas, Mohammed Fekry | 2022-02-03 | 2022-02-07 |  |  |  | 9000 | 4008 | 0 | STANDARD | Allied General Contracting Est. | SAR | 5850 | APPROVED |  |  | 2022-03-08 | 3150 | 29 | AlQuraish, Sajjad Hazem | -44599 | 29
105-12 | 8390-King Salman Park Project | 465 | 8390-King Salman Park Project-8390- Security Cabin for Site office (Delivery & Installation) | APPROVED | No | 2022-02-01 | Abas, Mohammed Fekry | 2022-02-03 | 2022-02-07 |  |  |  | 9000 | 4082 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 7200 | APPROVED |  |  | 2022-04-14 | 1800 | 66 | Babic, Marian | -44599 | 66
105-12 | 8390-King Salman Park Project | 466 | 8390-King Salman Park Project-8390- Sign board with digital counter as per SEC | APPROVED | No | 2022-02-01 | Abas, Mohammed Fekry | 2022-02-03 | 2022-02-07 |  |  |  | 24000 | 4004 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 21800 | APPROVED |  |  | 2022-03-17 | 2200 | 38 | AlQuraish, Sajjad Hazem | -44599 | 38
105-12 | 8390-King Salman Park Project | 480 | 8390-King Salman Park Project-8390- Battery & Battery Charger | APPROVED | No | 2022-02-13 | Abas, Mohammed Fekry | 2022-02-13 | 2022-02-13 |  |  |  | 478250 | 4131 | 0 | STANDARD | Alassas Specialized Company Ltd | SAR | 459600 | APPROVED |  |  | 2022-06-22 | 18650 | 129 | Babic, Marian | -44605 | 129
105-12 | 8390-King Salman Park Project | 493 | 8390-King Salman Park Project-8390 - Civil works | APPROVED | No | 2022-02-20 | Abas, Mohammed Fekry | 2022-02-26 | 2022-02-27 |  |  |  | 7414270 | 4172 | 0 | STANDARD | Inshat Al Awtan General Contracting Co | SAR | 6400000 | APPROVED |  |  | 2022-08-08 | 1014270 | 162 | Babic, Marian | -44619 | 162
105-12 | 8390-King Salman Park Project | 493 | 8390-King Salman Park Project-8390 - Civil works | APPROVED | No | 2022-02-20 | Abas, Mohammed Fekry | 2022-02-26 | 2022-02-27 |  |  |  | 7414270 | 4172 | 1 | STANDARD | Inshat Al Awtan General Contracting Co | SAR | 640000 | APPROVED |  |  | 2024-03-07 | 6774270 | 739 | Babic, Marian | -44619 | 739
105-12 | 8390-King Salman Park Project | 510 | 8390-King Salman Park Project-8390- SIS (Solid insulated System) | APPROVED | No | 2022-02-28 | Abas, Mohammed Fekry | 2022-02-28 | 2022-03-01 |  |  |  | 1935759.38 | 4159 | 0 | STANDARD | RITZ INSTRUMENT TRANSFORMERS GMBH | EUR | 1800706.4 | APPROVED |  |  | 2022-08-08 | 135052.98 | 160 | Babic, Marian | -44621 | 160
105-12 | 8390-King Salman Park Project | 515 | 8390-King Salman Park Project-8390- Overhead electrical single girder crane complete with accessories | APPROVED | No | 2022-02-28 | Abas, Mohammed Fekry | 2022-03-07 | 2022-03-08 |  |  |  | 160000 | 4171 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 130350 | APPROVED |  |  | 2022-08-08 | 29650 | 153 | Babic, Marian | -44628 | 153
105-12 | 8390-King Salman Park Project | 534 | 8390-King Salman Park Project-8390-Outdoor AMI CT for Auxiliary Transformer details | APPROVED | No | 2022-03-07 | Abas, Mohammed Fekry | 2022-03-07 | 2022-03-08 |  |  |  | 100000 | 4221 | 0 | STANDARD | ELEQ B.V. | EUR | 82368 | APPROVED |  |  | 2022-09-11 | 17632 | 187 | Babic, Marian | -44628 | 187
105-12 | 8390-King Salman Park Project | 536 | 8390-King Salman Park Project-Site Mobilization Activities | APPROVED | No | 2022-03-08 | Abas, Mohammed Fekry | 2022-03-08 | 2022-03-13 |  |  |  | 259328 | 4036 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 259328 | APPROVED |  |  | 2022-03-30 | 0 | 17 | AlQuraish, Sajjad Hazem | -44633 | 17
105-12 | 8390-King Salman Park Project | 636 | 8390-King Salman Park Project-Auxiliary Transformers for 8390 | APPROVED | No | 2022-05-11 | Abas, Mohammed Fekry | 2022-05-24 | 2022-05-24 |  |  |  | 100000 | 4178 | 0 | STANDARD | ALFANAR CO | SAR | 100000 | APPROVED |  |  | 2022-09-12 | 0 | 111 | Babic, Marian | -44705 | 111
105-12 | 8390-King Salman Park Project | 647 | 8390-King Salman Park Project-ACDB,DCDB & Sub panels | APPROVED | No | 2022-05-22 | Abas, Mohammed Fekry | 2022-05-23 | 2022-05-23 |  |  |  | 600000 | 4185 | 0 | STANDARD | ALFANAR CO | SAR | 600000 | APPROVED |  |  | 2022-08-17 | 0 | 86 | Babic, Marian | -44704 | 86
105-12 | 8390-King Salman Park Project | 686 | 8390-King Salman Park Project-132kV GIS- 8390 S/S | APPROVED | No | 2022-06-08 | Abas, Mohammed Fekry | 2022-06-12 | 2022-06-13 |  |  |  | 375000 | 3963 | 1 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 375000 | APPROVED |  |  | 2022-06-22 | 0 | 9 | Babic, Marian | -44725 | 9
105-12 | 8390-King Salman Park Project | 731 | 8390-King Salman Park Project-67MVA Power Transformer-8390 SS | APPROVED | No | 2022-07-17 | Abas, Mohammed Fekry | 2022-07-20 | 2022-07-21 |  |  |  | 2499772.54 | 4167 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 2499772.5 | APPROVED |  |  | 2022-07-31 | 0.04 | 10 | Babic, Marian | -44763 | 10
105-12 | 8390-King Salman Park Project | 774 | 8390-King Salman Park Project-150sqmm, Soft annaled copper conductor round compacted | APPROVED | No | 2022-08-25 | Abas, Mohammed Fekry | 2022-08-30 | 2022-08-30 |  |  |  | 188726.38 | 4208 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 183726.37 | APPROVED |  |  | 2022-09-06 | 5000.01 | 7 | Babic, Marian | -44803 | 7
105-12 | 8390-King Salman Park Project | 798 | 8390-King Salman Park Project-Surge arrester TPI PR for 8390 SS | APPROVED | No | 2022-09-07 | Abas, Mohammed Fekry | 2022-09-11 | 2022-09-11 |  |  |  | 1250 | 4224 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 1125 | APPROVED |  |  | 2022-09-13 | 125 | 2 | Babic, Marian | -44815 | 2
105-12 | 8390-King Salman Park Project | 802 | 8390-King Salman Park Project-132kV GIS TPI PR for 8390 SS | APPROVED | No | 2022-09-07 | Abas, Mohammed Fekry | 2022-09-11 | 2022-09-11 |  |  |  | 3800 | 4225 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 3675 | APPROVED |  |  | 2022-09-19 | 125 | 8 | Babic, Marian | -44815 | 8
105-12 | 8390-King Salman Park Project | 807 | 8390-King Salman Park Project-NGR TPI PR for 8390 SS | APPROVED | No | 2022-09-07 | Abas, Mohammed Fekry | 2022-09-11 | 2022-09-11 |  |  |  | 750 | 4226 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 731.25 | APPROVED |  |  | 2022-09-15 | 18.75 | 4 | Babic, Marian | -44815 | 4
105-12 | 8390-King Salman Park Project | 818 | 8390-King Salman Park Project-Bare copper conductor TPI PR | APPROVED | No | 2022-09-13 | Abas, Mohammed Fekry | 2022-09-13 | 2022-09-14 |  |  |  | 1400 | 4227 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 1400 | APPROVED |  |  | 2022-09-19 | 0 | 5 | Babic, Marian | -44818 | 5
105-12 | 8390-King Salman Park Project | 826 | 8390-King Salman Park Project-Security Systems-8390 SS | APPROVED | No | 2022-09-13 | Abas, Mohammed Fekry | 2022-09-13 | 2022-09-18 |  |  |  | 550000 | 4303 | 0 | STANDARD | Equipment & Technical Services Co.(ETECHS) | SAR | 500000 | APPROVED |  |  | 2023-01-26 | 50000 | 130 | Babic, Marian | -44822 | 130
105-12 | 8390-King Salman Park Project | 830 | 8390-King Salman Park Project-Deisel supply for generators 8390SS | APPROVED | No | 2022-09-13 | Abas, Mohammed Fekry | 2022-09-13 | 2022-09-14 |  |  |  | 12822 | 4232 | 0 | STANDARD | Othman Hammoud Al-Zaydi Est | SAR | 12822 | APPROVED |  |  | 2022-09-20 | 0 | 6 | Abuhammad, Samir | -44818 | 6
105-12 | 8390-King Salman Park Project | 835 | 8390-King Salman Park Project-HVAC System 8390 SS | APPROVED | No | 2022-09-14 | Abas, Mohammed Fekry | 2022-09-18 | 2022-09-25 |  |  |  | 1500000 | 4240 | 0 | STANDARD | Ramz Alataa Company for Trading | SAR | 1500000 | APPROVED |  |  | 2022-10-04 | 0 | 9 | Babic, Marian | -44829 | 9
105-12 | 8390-King Salman Park Project | 869 | 8390-King Salman Park Project-Y/G cables | RETURNED | No | 2022-10-06 | Babic, Marian | 2023-01-25 | 2022-10-10 | 2023-01-25 |  | Please modify the price to be 74.90 SAR, length 305m | 142903.19 | 4212 | 0 | STANDARD | ALFANAR CO | SAR | 67610 | APPROVED |  |  | 2022-10-17 | 75293.19 |  | Babic, Marian | -44844 | 7
105-12 | 8390-King Salman Park Project | 869 | 8390-King Salman Park Project-Y/G cables | RETURNED | No | 2022-10-06 | Babic, Marian | 2023-01-25 | 2022-10-10 | 2023-01-25 |  | Please modify the price to be 74.90 SAR, length 305m | 112721.5 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44844 | -44844
105-12 | 8390-King Salman Park Project | 890 | 8390-King Salman Park Project-Earthing materials-8390 SS | APPROVED | No | 2022-10-26 | Abas, Mohammed Fekry | 2022-10-31 | 2022-11-01 |  |  |  | 115310.5 | 4276 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 115310.5 | APPROVED |  |  | 2022-12-01 | 0 | 30 | Babic, Marian | -44866 | 30
105-12 | 8390-King Salman Park Project | 916 | 8390-King Salman Park Project-TPI for Power Transformer in 8390 SS | APPROVED | No | 2022-11-16 | Abas, Mohammed Fekry | 2022-11-17 | 2022-11-17 |  |  |  | 14300 | 4283 | 0 | STANDARD | VELOSI SAUDI ARABIA CO LTD | SAR | 14300 | APPROVED |  |  | 2022-11-28 | 0 | 11 | Babic, Marian | -44882 | 11
105-12 | 8390-King Salman Park Project | 940 | 8390-King Salman Park Project-DC-DC converter- 8390 SS | APPROVED | No | 2022-12-06 | Abas, Mohammed Fekry | 2022-12-12 | 2022-12-12 |  |  |  | 9150 | 4295 | 0 | STANDARD | SGS GULF LIMITED | USD | 4500 | APPROVED |  |  | 2022-12-19 | 4650 | 7 | Babic, Marian | -44907 | 7
105-12 | 8390-King Salman Park Project | 1018 | 8390-King Salman Park Project-Cable Y/G 1x240mm2- 8390 SS | APPROVED | No | 2023-01-24 | Abas, Mohammed Fekry | 2023-01-24 | 2023-01-25 |  |  |  | 15548.5 | 4212 | 2 | STANDARD | ALFANAR CO | SAR | 15475.75 | APPROVED |  |  | 2023-02-06 | 72.75 | 12 | Babic, Marian | -44951 | 12
105-12 | 8390-King Salman Park Project | 1030 | 8390-King Salman Park Project-Cable Y/G 1x240mm2- 8390 SS(2) | APPROVED | No | 2023-01-30 | Abas, Mohammed Fekry | 2023-02-02 | 2023-02-02 |  |  |  | 22844.5 | 4212 | 2 | STANDARD | ALFANAR CO | SAR | 22844.5 | APPROVED |  |  | 2023-02-06 | 0 | 4 | Babic, Marian | -44959 | 4
105-12 | 8390-King Salman Park Project | 1074 | 8390-King Salman Park Project-OH Crane TPI- 8390 SS | APPROVED | No | 2023-02-14 | Abas, Mohammed Fekry | 2023-02-15 | 2023-02-16 |  |  |  | 800 | 4353 | 0 | STANDARD | SGS INSPECTION SERVICES SA. LTD | SAR | 800 | APPROVED |  |  | 2023-02-26 | 0 | 10 | Babic, Marian | -44973 | 10
105-12 | 8390-King Salman Park Project | 1144 | 8390-King Salman Park Project-Power Transformer's Offloading -8390 SS | APPROVED | No | 2023-03-22 | Abas, Mohammed Fekry | 2023-03-27 | 2023-03-28 |  |  |  | 50000 | 4435 | 0 | STANDARD | MOHAMMED HAMAD AL-AHMADE FOR TRADING AND CONSTRACTION | SAR | 30000 | APPROVED |  |  | 2023-05-03 | 20000 | 36 | Abuhammad, Samir | -45013 | 36
105-12 | 8390-King Salman Park Project | 1148 | 8390-King Salman Park Project-OH Crane TPI-8390 SS | APPROVED | No | 2023-03-27 | Abas, Mohammed Fekry | 2023-03-28 | 2023-03-30 |  |  |  | 1600 | 4353 | 1 | STANDARD | SGS INSPECTION SERVICES SA. LTD | SAR | 800 | APPROVED |  |  | 2023-04-06 | 800 | 7 | Babic, Marian | -45015 | 7
105-12 | 8390-King Salman Park Project | 1151 | 8390-King Salman Park Project-Cuber security- 8390 SS | APPROVED | No | 2023-03-30 | Abas, Mohammed Fekry | 2023-04-01 | 2023-04-02 |  |  |  | 1700000 | 4555 | 0 | STANDARD | ALFANAR CO | SAR | 1400000 | APPROVED |  |  | 2023-10-17 | 300000 | 198 | Kumar, Mr. Ranjan | -45018 | 198
105-12 | 8390-King Salman Park Project | 1195 | 8390-King Salman Park Project-Capacitor bank TPI for 4 S/S | RETURNED | No | 2023-04-17 | Babic, Marian | 2024-06-26 | 2023-04-30 | 2024-06-26 |  | not required | 6900 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45046 | -45046
105-12 | 8390-King Salman Park Project | 1196 | 8390-King Salman Park Project-Ring Current Transformer TPI for 4 S/S | APPROVED | No | 2023-04-17 | Abas, Mohammed Fekry | 2023-04-22 | 2023-04-30 |  |  |  | 3200 | 4446 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 3187.5 | APPROVED |  |  | 2023-05-15 | 12.5 | 15 | Babic, Marian | -45046 | 15
105-12 | 8390-King Salman Park Project | 1217 | 8390-King Salman Park Project-MV Switchgear-8390 SS | APPROVED | No | 2023-04-30 | Abas, Mohammed Fekry | 2023-05-02 | 2023-05-02 |  |  |  | 4500 | 4453 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | SAR | 4500 | APPROVED |  |  | 2023-05-15 | 0 | 13 | Babic, Marian | -45048 | 13
105-12 | 8390-King Salman Park Project | 1223 | 8390-King Salman Park Project-(25M)LIGHTNING MAST (LCLM)with accessories-8390 SS | APPROVED | No | 2023-05-01 | Abas, Mohammed Fekry | 2023-05-03 | 2023-05-08 |  |  |  | 58320 | 4487 | 0 | STANDARD | Hesham El-Sewedy Trading Co. LTD. | SAR | 58320 | APPROVED |  |  | 2023-07-19 | 0 | 72 | Babic, Marian | -45054 | 72
105-12 | 8390-King Salman Park Project | 1228 | 8390-King Salman Park Project-Protection and Control System TPI 8390 | APPROVED | No | 2023-05-03 | Abas, Mohammed Fekry | 2023-05-04 | 2023-05-08 |  |  |  | 7000 | 4451 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 7000 | APPROVED |  |  | 2023-05-15 | 0 | 7 | Babic, Marian | -45054 | 7
105-12 | 8390-King Salman Park Project | 1230 | 8390-King Salman Park Project-Battery Charger FAT TPI-4 SS | APPROVED | No | 2023-05-07 | Abas, Mohammed Fekry | 2023-05-09 | 2023-05-10 |  |  |  | 10400 | 4454 | 0 | STANDARD | Bureau Veritas Branch Saudi Arabia | SAR | 10400 | APPROVED |  |  | 2023-06-05 | 0 | 26 | Babic, Marian | -45056 | 26
105-12 | 8390-King Salman Park Project | 1253 | 8390-King Salman Park Project-Services-Installation and configuration-8390 SS | APPROVED | No | 2023-05-11 | Abas, Mohammed Fekry | 2023-05-15 | 2023-05-15 |  |  |  | 1343800 | 5216 | 0 | STANDARD | Hussain Ali Hussain Contracting Company | SAR | 1343800 | APPROVED |  |  | 2024-03-18 | 0 | 308 | Babic, Marian | -45061 | 308
105-12 | 8390-King Salman Park Project | 1286 | 8390-King Salman Park Project-Power transformer Oil filteration-8390 SS | APPROVED | No | 2023-05-25 | Abas, Mohammed Fekry | 2023-05-28 | 2023-05-28 |  |  |  | 100000 | 4553 | 0 | STANDARD | Al-Handasah Al-Namuudhajyyah Contracting Company | SAR | 57000 | APPROVED |  |  | 2023-07-27 | 43000 | 60 | Babic, Marian | -45074 | 60
105-12 | 8390-King Salman Park Project | 1299 | 8390-King Salman Park Project-TELECOMMUNICATION EQUIPMENT (MPLS,DVM,MDF,DDF) and LAN TPI 8390 | APPROVED | No | 2023-07-04 | Abas, Mohammed Fekry | 2023-07-06 | 2023-07-09 |  |  |  | 4200 | 4541 | 0 | STANDARD | Bureau Veritas Branch Saudi Arabia | SAR | 4200 | APPROVED |  |  | 2023-07-12 | 0 | 3 | Babic, Marian | -45116 | 3
105-12 | 8390-King Salman Park Project | 1316 | 8390-King Salman Park Project-Battery Charger FAT TPI additional | APPROVED | No | 2023-06-11 | Abas, Mohammed Fekry | 2023-06-13 | 2023-06-14 |  |  |  | 3639 | 4454 | 1 | STANDARD | Bureau Veritas Branch Saudi Arabia | SAR | 3639 | APPROVED |  |  | 2023-07-09 | 0 | 25 | Babic, Marian | -45091 | 25
105-12 | 8390-King Salman Park Project | 1335 | 8390-King Salman Park Project-Capacitor bank TPI for 4 S/S for addtional Days | APPROVED | No | 2023-06-25 | Abas, Mohammed Fekry | 2023-07-06 | 2023-07-09 |  |  |  | 13000 | 4540 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 13000 | APPROVED |  |  | 2023-07-12 | 0 | 3 | Babic, Marian | -45116 | 3
105-12 | 8390-King Salman Park Project | 1388 | 8390-King Salman Park Project-SAS TPI (SS 8390) | APPROVED | No | 2023-08-08 | Abas, Mohammed Fekry | 2023-08-08 | 2023-08-13 |  |  |  | 7000 | 4568 | 0 | STANDARD | Bureau Veritas Branch Saudi Arabia | SAR | 7000 | APPROVED |  |  | 2023-08-15 | 0 | 2 | Babic, Marian | -45151 | 2
105-12 | 8390-King Salman Park Project | 1421 | 8390-King Salman Park Project-THHN Wires (Lighting Cables) SS # 8390 | APPROVED | No | 2023-08-21 | Abas, Mohammed Fekry | 2023-08-24 | 2023-08-24 |  |  |  | 21000 | 4592 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 21000 | APPROVED |  |  | 2023-12-31 | 0 | 129 | Babic, Marian | -45162 | 129
105-12 | 8390-King Salman Park Project | 1674 | 8390-King Salman Park Project-Lighting Fixture (indoor - Outdoor) Nardeen for SS 8390 | APPROVED | No | 2023-11-09 | Abas, Mohammed Fekry | 2023-11-14 | 2023-11-14 |  |  |  | 60362.6 | 4726 | 0 | STANDARD | Nardeen Lighting Company Ltd. | SAR | 60362.6 | APPROVED |  |  | 2023-12-03 | 0 | 19 | Babic, Marian | -45244 | 19
105-12 | 8390-King Salman Park Project | 1692 | 8390-King Salman Park Project-RGS Conduits and Accessories (Lighting works) 8390 | RETURNED | No | 2023-11-12 | Babic, Marian | 2024-03-26 | 2023-11-19 | 2024-03-26 |  | PO for this subject already issued, this PR is a balance which is not needed | 53958 | 4793 | 0 | STANDARD | ELECTRIC HOUSE EST. | SAR | 20076.6 | APPROVED |  |  | 2023-12-10 | 33881.4 |  | Babic, Marian | -45249 | 21
105-12 | 8390-King Salman Park Project | 1692 | 8390-King Salman Park Project-RGS Conduits and Accessories (Lighting works) 8390 | RETURNED | No | 2023-11-12 | Babic, Marian | 2024-03-26 | 2023-11-19 | 2024-03-26 |  | PO for this subject already issued, this PR is a balance which is not needed | 810.88 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45249 | -45249
105-12 | 8390-King Salman Park Project | 1696 | 8390-King Salman Park Project-Lighting Poles @ 8390 | APPROVED | No | 2023-11-12 | Abas, Mohammed Fekry | 2023-11-19 | 2023-11-19 |  |  |  | 12080 | 4807 | 0 | STANDARD | Hesham El-Sewedy Trading Co. LTD. | SAR | 12080 | APPROVED |  |  | 2023-12-14 | 0 | 25 | Babic, Marian | -45249 | 25
105-12 | 8390-King Salman Park Project | 1747 | 8390-King Salman Park Project-Power Receptacle for 8390 (budget line item 1.21) | APPROVED | No | 2023-11-15 | Abas, Mohammed Fekry | 2023-11-22 | 2023-11-22 |  |  |  | 78410 | 4878 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 60265 | APPROVED |  |  | 2023-12-31 | 18145 | 39 | Babic, Marian | -45252 | 39
105-12 | 8390-King Salman Park Project | 2179 | 8390-King Salman Park Project-SIS FAT. TPI services SS 8390 | APPROVED | No | 2024-01-16 | Abas, Mohammed Fekry | 2024-01-16 | 2024-01-17 |  |  |  | 6225 | 5016 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | SAR | 6225 | APPROVED |  |  | 2024-02-01 | 0 | 15 | Babic, Marian | -45308 | 15
105-12 | 8390-King Salman Park Project | 2556 | 8390-King Salman Park Project-Diesel supply for Generator at King Salman Parks projects | REJECTED | No | 2024-02-13 | Alnaeem, Rami Mayraghany alkaram | 2024-02-13 | 2024-02-13 |  | 2024-02-14 |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45335 | -45335
105-12 | 8390-King Salman Park Project | 2558 | 8390-King Salman Park Project-Diesel supply for Generator at King Salman Parks projects | APPROVED | No | 2024-02-13 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-18 |  |  |  | 29999 | 4232 | 1 | STANDARD | Othman Hammoud Al-Zaydi Est | SAR | 29999 | APPROVED |  |  | 2024-03-13 | 0 | 24 | Babic, Marian | -45340 | 24
105-12 | 8390-King Salman Park Project | 2574 | 8390-King Salman Park Project-perforated cable tray (from budget line item 1.22 ) | APPROVED | No | 2024-02-15 | Abas, Mohammed Fekry | 2024-02-19 | 2024-02-20 |  |  |  | 40649.03 | 5112 | 0 | STANDARD | AL-ASHOURY FACTORY FOR CABLE SUPPORTS COMPANY(S) | SAR | 40445.67 | APPROVED |  |  | 2024-03-24 | 203.36 | 33 | Babic, Marian | -45342 | 33
105-12 | 8390-King Salman Park Project | 2611 | 8390-King Salman Park Project-ACSR Connectors ( Budget Line Item 1.26) | RETURNED | No | 2024-02-19 | Babic, Marian | 2024-03-12 | 2024-02-26 | 2024-03-12 |  | please revise the price | 4752.3 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45348 | -45348
105-12 | 8390-King Salman Park Project | 2636 | 8390-King Salman Park Project-PDS System for SS 8390 | APPROVED | No | 2024-02-20 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 160000 | 5164 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 155500 | APPROVED |  |  | 2024-03-18 | 4500 | 21 | Babic, Marian | -45348 | 21
105-12 | 8390-King Salman Park Project | 2642 | 8390-King Salman Park Project-Installation of Capacitor Banks on Civil Foundation SS 8390 (Budget Line item 1.19) | APPROVED | No | 2024-02-21 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 30000 | 5174 | 0 | STANDARD | YASIR M ALI AL-ZAHRANI EST. | SAR | 30000 | APPROVED |  |  | 2024-03-12 | 0 | 15 | Babic, Marian | -45348 | 15
105-12 | 8390-King Salman Park Project | 2667 | 8390-King Salman Park Project-Lighitng Installation works for S/S 8390 (Budget Line item # 1.34) | APPROVED | No | 2024-02-25 | Abas, Mohammed Fekry | 2024-02-27 | 2024-02-28 |  |  |  | 200000 | 5216 | 0 | STANDARD | Hussain Ali Hussain Contracting Company | SAR | 200000 | APPROVED |  |  | 2024-03-18 | 0 | 19 | Babic, Marian | -45350 | 19
105-12 | 8390-King Salman Park Project | 2676 | 8390-King Salman Park Project-Testing & Commissioning Services for SS 8390 (Budget Line item # 1.36) | APPROVED | No | 2024-02-25 | Abas, Mohammed Fekry | 2024-02-27 | 2024-02-28 |  |  |  | 1195832 | 5208 | 0 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 808947 | APPROVED |  |  | 2024-05-19 | 386885 | 81 | Babic, Marian | -45350 | 81
105-12 | 8390-King Salman Park Project | 2695 | 8390-King Salman Park Project-Rental Manpower for S/S # 8390 (Budget Line item 1.50) | APPROVED | No | 2024-02-26 | Abas, Mohammed Fekry | 2024-02-29 | 2024-03-03 |  |  |  | 344988.75 | 5150 | 0 | STANDARD | Jasem M.AlJasem Contracting Est. | SAR | 344032 | APPROVED |  |  | 2024-03-25 | 956.75 | 22 | Babic, Marian | -45354 | 22
105-12 | 8390-King Salman Park Project | 2700 | 8390-King Salman Park Project-Third party Testing for Precast Boundary Wall (Budget Item # 1.29) | APPROVED | No | 2024-02-26 | Abas, Mohammed Fekry | 2024-02-29 | 2024-03-03 |  |  |  | 30000 | 5252 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 30000 | APPROVED |  |  | 2024-03-26 | 0 | 23 | Babic, Marian | -45354 | 23
105-12 | 8390-King Salman Park Project | 2728 | 8390-King Salman Park Project-Pumps for Civil Works SS # 8390 (Budget Line item 1.19) (to convert Manual PO # 8559) | APPROVED | No | 2024-03-03 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 65000 | 5176 | 0 | STANDARD | Lamah CO. LTD .for T | SAR | 65000 | APPROVED |  |  | 2024-04-24 | 0 | 48 | Babic, Marian | -45358 | 48
105-12 | 8390-King Salman Park Project | 2732 | 8390-King Salman Park Project-Building Precast SS # 8390 (Budget Line item 1.19. This PR is to convert the Manual PO # 8083 to Oracle PO as per CEO office instruction | APPROVED | No | 2024-03-03 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 1413950 | 5180 | 0 | STANDARD | EASTERN READYMIX CONCRETE COMPANY | SAR | 1413950 | APPROVED |  |  | 2024-03-18 | 0 | 11 | Babic, Marian | -45358 | 11
105-12 | 8390-King Salman Park Project | 2736 | 8390-King Salman Park Project-Boundary Wall Precast for SS # 8390 (Budget Line item 1.19) | APPROVED | No | 2024-03-03 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 438811.48 | 5226 | 0 | STANDARD | Prainsa Saudi for precast Concrete | SAR | 438811.48 | APPROVED |  |  | 2024-04-03 | 0 | 27 | Babic, Marian | -45358 | 27
105-12 | 8390-King Salman Park Project | 2752 | 8390-King Salman Park Project-Outdoor Steel Structure for SIS & Capacitor Cable Support | APPROVED | No | 2024-03-04 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 82960 | 5184 | 0 | STANDARD | Energy Field Trading Est | SAR | 82960 | APPROVED |  |  | 2024-03-14 | 0 | 7 | Babic, Marian | -45358 | 7
105-12 | 8390-King Salman Park Project | 2794 | 8390-King Salman Park Project-Installation Services for SS # 8390 (Budget Line item 1.34) | APPROVED | No | 2024-03-05 | Abas, Mohammed Fekry | 2024-03-11 | 2024-03-11 |  |  |  | 280207 | 5216 | 0 | STANDARD | Hussain Ali Hussain Contracting Company | SAR | 280207 | APPROVED |  |  | 2024-03-18 | 0 | 7 | Babic, Marian | -45362 | 7
105-12 | 8390-King Salman Park Project | 2805 | 8390-King Salman Park Project-Civil Works Subcontract SS # 8390 (Budget Line # 1.19) for conversion of Manual PO # 8232 to Oracle PO | APPROVED | No | 2024-03-09 | Abas, Mohammed Fekry | 2024-03-11 | 2024-03-11 |  |  |  | 7200000 | 5253 | 0 | STANDARD | Al Sahda Contracting Est. | SAR | 7200000 | APPROVED |  |  | 2024-03-26 | 0 | 15 | Babic, Marian | -45362 | 15
105-12 | 8390-King Salman Park Project | 2810 | 8390-King Salman Park Project-Cable Ladders / Trays for SS 8390 (Budget Line Item 1.22) | APPROVED | No | 2024-03-11 | Abas, Mohammed Fekry | 2024-03-12 | 2024-03-12 |  |  |  | 15585.6 | 5254 | 1 | STANDARD | AL-AMAL ELECTRICAL SWITCHBOARDS | SAR | 11918.4 | APPROVED |  |  | 2024-05-01 | 3667.2 | 50 | Babic, Marian | -45363 | 50
105-12 | 8390-King Salman Park Project | 2810 | 8390-King Salman Park Project-Cable Ladders / Trays for SS 8390 (Budget Line Item 1.22) | APPROVED | No | 2024-03-11 | Abas, Mohammed Fekry | 2024-03-12 | 2024-03-12 |  |  |  | 270754.9 | 5254 | 0 | STANDARD | AL-AMAL ELECTRICAL SWITCHBOARDS | SAR | 270754.9 | APPROVED |  |  | 2024-03-28 | 0 | 16 | Babic, Marian | -45363 | 16
105-12 | 8390-King Salman Park Project | 2989 | 8390-King Salman Park Project-Fire Fighitng Scope @ 8390 (from Budget Line item 1.18) Manual PO # 8124 conversion | APPROVED | No | 2024-04-03 | Abas, Mohammed Fekry | 2024-04-04 | 2024-04-04 |  |  |  | 1500000 | 5400 | 0 | STANDARD | Equipment & Technical Services Co.(ETECHS) | SAR | 1500000 | APPROVED |  |  | 2024-04-18 | 0 | 14 | Babic, Marian | -45386 | 14
105-12 | 8390-King Salman Park Project | 2994 | 8390-King Salman Park Project-Testing & Commissioning @ 8390. (Budget Line item # 1.36) | APPROVED | No | 2024-04-04 | Abas, Mohammed Fekry | 2024-04-04 | 2024-04-04 |  |  |  | 1000000 | 5208 | 0 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 1000000 | APPROVED |  |  | 2024-05-19 | 0 | 45 | Babic, Marian | -45386 | 45
105-12 | 8390-King Salman Park Project | 3064 | 8390-King Salman Park Project-Fiber Optic Patch Panel (budget line item 1.21) | APPROVED | No | 2024-04-19 | Abas, Mohammed Fekry | 2024-04-22 | 2024-04-23 |  |  |  | 42200 | 5473 | 0 | STANDARD | AMWAJ TELECOMMUNICATION MFG. CO. | SAR | 39500 | APPROVED |  |  | 2024-05-12 | 2700 | 19 | Babic, Marian | -45405 | 19
105-12 | 8390-King Salman Park Project | 3087 | 8390-King Salman Park Project-MV Termination Kits @ 8390 (for conversion of Manual PO# 8533) to oracle PO. Budget Line item # 1.20 (termination power Cables) and 1.29 service 1 item | APPROVED | No | 2024-04-21 | Abas, Mohammed Fekry | 2024-04-22 | 2024-04-23 |  |  |  | 47557 | 5447 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 44703.58 | APPROVED |  |  | 2024-04-29 | 2853.42 | 6 | Babic, Marian | -45405 | 6
105-12 | 8390-King Salman Park Project | 3112 | 8390-King Salman Park Project-SAS Furnitures @ 8390 (under Budget Line # 1.6) for conversion of Manual PO # 8254 | APPROVED | No | 2024-04-23 | Abas, Mohammed Fekry | 2024-04-28 | 2024-04-29 |  |  |  | 55000 | 5483 | 0 | STANDARD | ALFANAR CO | SAR | 55000 | APPROVED |  |  | 2024-05-12 | 0 | 13 | Babic, Marian | -45411 | 13
105-12 | 8390-King Salman Park Project | 3287 | 8390-King Salman Park Project-Lighting Accessories (Budget Line Item 1.21) | APPROVED | No | 2024-05-04 | Abas, Mohammed Fekry | 2024-05-06 | 2024-05-07 |  |  |  | 24683.2 | 5509 | 0 | STANDARD | Current Makers For Contracting EST | SAR | 23280 | APPROVED |  |  | 2024-05-21 | 1403.2 | 14 | Babic, Marian | -45419 | 14
105-12 | 8390-King Salman Park Project | 3304 | 8390-King Salman Park Project- Fire Stop material (Budget Line Item 1.19) | APPROVED | No | 2024-05-05 | Abas, Mohammed Fekry | 2024-05-06 | 2024-05-07 |  |  |  | 91980 | 5517 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 76210 | APPROVED |  |  | 2024-05-21 | 15770 | 14 | Babic, Marian | -45419 | 14
105-12 | 8390-King Salman Park Project | 3370 | 8390-King Salman Park Project-HV Connectors (for ACSR Conductor) (material from Budget Line item 1.26 & ) & (Shipment from line item #1.37) | APPROVED | No | 2024-05-12 | Abas, Mohammed Fekry | 2024-05-14 | 2024-05-14 |  |  |  | 7422.21 | 5155 | 0 | STANDARD | Arruti Subestaciones , S.A.U | EUR | 7716.76 | APPROVED |  |  | 2024-05-27 | -294.55 | 13 | Babic, Marian | -45426 | 13
105-12 | 8390-King Salman Park Project | 3595 | 8390-King Salman Park Project-Third party Testing for Precast Boundary Wall (for SAFCO PO # 5252 amendment) (Budget Item # 1.29) | REJECTED | No | 2024-06-05 | Almehmadi, Fahed | 2024-06-05 |  |  | 2024-06-05 | To Increase the Amount, as per Site team feedback | 10000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-12 | 8390-King Salman Park Project | 3601 | 8390-King Salman Park Project-Third party Testing for Precast Boundary Wall (for SAFCO PO # 5252 Amendment) (Budget Item # 1.29) | APPROVED | No | 2024-06-05 | Abas, Mohammed Fekry | 2024-06-05 | 2024-06-06 |  |  |  | 17000 | 5252 | 1 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 17000 | APPROVED |  |  | 2024-06-26 | 0 | 20 | Babic, Marian | -45449 | 20
105-12 | 8390-King Salman Park Project | 3719 | 8390-King Salman Park Project-FAT Inspection charges for HVAC Units SS 8390 (SS # 8387 included) Budget Line # 1.29 | APPROVED | No | 2024-07-01 | Abas, Mohammed Fekry | 2024-07-04 | 2024-07-07 |  |  |  | 4000 | 5797 | 0 | STANDARD | Magna Contracting Co | SAR | 4000 | APPROVED |  |  | 2024-07-14 | 0 | 7 | Babic, Marian | -45480 | 7
105-12 | 8390-King Salman Park Project | 3766 | 8390-King Salman Park Project-Final Inspection & Certification of Capacitor Bank Installation (optional Price in PO # 5174) | APPROVED | No | 2024-07-04 | Abas, Mohammed Fekry | 2024-07-07 | 2024-07-08 |  |  |  | 14500 | 5174 | 1 | STANDARD | YASIR M ALI AL-ZAHRANI EST. | SAR | 14500 | APPROVED |  |  | 2024-07-12 | 0 | 4 | Babic, Marian | -45481 | 4
105-12 | 8390-King Salman Park Project | 4607 | 8390-King Salman Park Project-AMI T&C budget line (1.36) | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-10 | 2024-10-12 |  |  |  | 60000 | 6342 | 0 | STANDARD | SYSTEM HOUSE FACTORY FOR ELECTRIC PANELS (SEP) | SAR | 53750 | APPROVED |  |  | 2024-10-30 | 6250 | 18 | Babic, Marian | -45577 | 18
105-12 | 8390-King Salman Park Project | 5016 | 8390-King Salman Park Project-Amednment in PO # 4159 (RITZ) for Bending issue (Budget Line Item # 1.38) | APPROVED | No | 2024-11-21 | Abas, Mohammed Fekry | 2024-11-27 | 2024-11-27 |  |  |  | 11000 | 4159 | 1 | STANDARD | RITZ INSTRUMENT TRANSFORMERS GMBH | EUR | 10204 | APPROVED |  |  | 2024-12-08 | 796 | 11 | Babic, Marian | -45623 | 11
105-12 | 8390-King Salman Park Project | 5040 | 8390-King Salman Park Project-Diesel Supply for SS 8390 (Conversion of Manual PO # 8792 to Oracle) Budget Line # 1.3 | APPROVED | No | 2024-11-24 | Shoujra, Ishfaq Yousef | 2024-11-27 | 2024-11-27 |  |  |  | 120000.4 | 6561 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 120000.4 | APPROVED |  |  | 2024-12-05 | 0 | 8 | Babic, Marian | -45623 | 8
105-12 | 8390-King Salman Park Project | 5071 | 8390-King Salman Park Project-Fiber Optic Cable works 8390 (Converting Manual PO # 8537 to Oracle) Budget line # 1.20 (Fiber) | APPROVED | No | 2024-11-27 | Abas, Mohammed Fekry | 2024-12-02 | 2024-12-02 |  |  |  | 174000 | 6580 | 0 | STANDARD | SMART TECH | SAR | 174000 | APPROVED |  |  | 2024-12-05 | 0 | 3 | Babic, Marian | -45628 | 3
105-12 | 8390-King Salman Park Project | 5178 | 8390-King Salman Park Project-Conversion of Manual PO # 8155 (Rev-0) to Oracle PO_ Budget Line # 1.24 Control Cable | APPROVED | No | 2024-12-07 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-10 |  |  |  | 312841.94 | 6624 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 312841.94 | APPROVED |  |  | 2024-12-23 | 0 | 13 | Babic, Marian | -45636 | 13
105-12 | 8390-King Salman Park Project | 5179 | 8390-King Salman Park Project-Conversion of Manual PO # 8155 (Rev-0) to Oracle PO_ Budget Line # 1.26 LV Power Cable | APPROVED | No | 2024-12-07 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-10 |  |  |  | 454720.48 | 6624 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 454720.48 | APPROVED |  |  | 2024-12-23 | 0 | 13 | Babic, Marian | -45636 | 13
105-12 | 8390-King Salman Park Project | 5180 | 8390-King Salman Park Project-Conversion of Manual PO # 8155 (Rev-1) to Oracle PO, Budget Line # 1.24 Control Cables | APPROVED | No | 2024-12-07 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-10 |  |  |  | 120856.5 | 6624 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 120856.5 | APPROVED |  |  | 2024-12-23 | 0 | 13 | Babic, Marian | -45636 | 13
105-12 | 8390-King Salman Park Project | 5181 | 8390-King Salman Park Project-Conversion of Manual PO # 8155 (Rev-1) to Oracle PO, Budget Line # 1.26 LV Power Cables | APPROVED | No | 2024-12-07 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-10 |  |  |  | 18211 | 6624 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 18211 | APPROVED |  |  | 2024-12-23 | 0 | 13 | Babic, Marian | -45636 | 13
105-12 | 8390-King Salman Park Project | 5187 | 8390-King Salman Park Project-Conversion of Manual PO # 8155 (Rev-0) to Oracle PO_ Budget Line # 1.25 MV Cables | APPROVED | No | 2024-12-08 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-10 |  |  |  | 199686.4 | 6624 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 199686.4 | APPROVED |  |  | 2024-12-23 | 0 | 13 | Babic, Marian | -45636 | 13
105-12 | 8390-King Salman Park Project | 5217 | 8390-King Salman Park Project-Adjustment (adding + de-scoping some items) of PO # 4276 (due to additional Qty Ordered previously before PO issuance) | APPROVED | No | 2024-12-11 | Abas, Mohammed Fekry | 2024-12-17 | 2024-12-17 |  |  |  | 6266 | 4276 | 1 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 6266 | APPROVED |  |  | 2025-02-17 | 0 | 62 | Babic, Marian | -45643 | 62
105-12 | 8390-King Salman Park Project | 5391 | 8390-King Salman Park Project-GENERATOR 350 kva for site electricity supply 8390 | APPROVED | No | 2025-01-13 | Abas, Mohammed Fekry | 2025-01-14 | 2025-01-16 |  |  |  | 54000 | 6806 | 0 | STANDARD | SUDHIR EQUIPMENT RENTAL COMPANY | SAR | 26700 | APPROVED |  |  | 2025-02-10 | 27300 | 25 | Babic, Marian | -45673 | 25
105-12 | 8390-King Salman Park Project | 5704 | 8390-King Salman Park Project-Steel Name Plates for Site equipments (task # 1.21) | APPROVED | No | 2025-01-28 | Abas, Mohammed Fekry | 2025-02-04 | 2025-02-05 |  |  |  | 30000 | 6922 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 19083 | APPROVED |  |  | 2025-02-25 | 10917 | 20 | Babic, Marian | -45693 | 20
105-12 | 8390-King Salman Park Project | 5706 | 8390-King Salman Park Project-Conversion of Manual PO # 8592 (Rev-0 & 1) to Oracle PO (task # 1.26) | APPROVED | No | 2025-01-28 | Abas, Mohammed Fekry | 2025-02-04 | 2025-02-05 |  |  |  | 17175 | 6871 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 17175 | APPROVED |  |  | 2025-02-12 | 0 | 7 | Babic, Marian | -45693 | 7
105-12 | 8390-King Salman Park Project | 5713 | 8390-King Salman Park Project-Conversion of Mnaual PO # 4276 Rev.01 to Oracle PO | APPROVED | No | 2025-01-29 | Abas, Mohammed Fekry | 2025-02-04 | 2025-02-05 |  |  |  | 41007.5 | 4276 | 1 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 41007.5 | APPROVED |  |  | 2025-02-17 | 0 | 12 | Babic, Marian | -45693 | 12
105-12 | 8390-King Salman Park Project | 5863 | 8390-King Salman Park Project-Additional Diesel Supply requirement for SS 8390 Budget Line # 1.3 PO # 6561 | APPROVED | No | 2025-02-13 | Abas, Mohammed Fekry | 2025-02-18 | 2025-02-18 |  |  |  | 177600 | 6561 | 1 | STANDARD | Talaea Alahlam Trading Company | SAR | 177600 | APPROVED |  |  | 2025-03-04 | 0 | 14 | Babic, Marian | -45706 | 14
105-12 | 8390-King Salman Park Project | 6192 | 8390-King Salman Park Project-Pre-Energization Oil Sampling Tests (Power + Station Service Transformers) | APPROVED | No | 2025-03-17 | Abas, Mohammed Fekry | 2025-03-25 | 2025-03-25 |  |  | Pre-Energization Oil Sampling Tests (Power + Station Service Transformers) | 35585 | 7082 | 0 | STANDARD | Gulf Laboratory Technical Services (S) | SAR | 35585 | APPROVED |  |  | 2025-04-08 | 0 | 14 | Babic, Marian | -45741 | 14
105-12 | 8390-King Salman Park Project | 6268 | 8390-King Salman Park Project-Multiple Lighting Materials & Accessories for SS 8390 (BIL-1.23) | APPROVED | No | 2025-03-25 | Abas, Mohammed Fekry | 2025-03-27 | 2025-03-27 |  |  | Multiple Lighting Materials & Accessories for SS 8390 (BIL-1.23) | 82979.5 | 7117 | 0 | STANDARD | Ahmed Essa Mohammed Al Muslim Est. | SAR | 80000 | APPROVED |  |  | 2025-04-16 | 2979.5 | 20 | Babic, Marian | -45743 | 20
105-12 | 8390-King Salman Park Project | 6439 | 8390-King Salman Park Project-Y/G Cables @ ALFANAR- Conversion of Manual PO # 8816 to Oracle | APPROVED | No | 2025-04-23 | Abas, Mohammed Fekry | 2025-04-30 | 2025-05-04 |  |  | Y/G Cables @ ALFANAR- Conversion of Manual PO # 8816 to Oracle | 44620 | 7225 | 0 | STANDARD | ALFANAR CO | SAR | 44620 | APPROVED |  |  | 2025-05-05 | 0 | 1 | Babic, Marian | -45781 | 1
105-12 | 8390-King Salman Park Project | 6977 | 8390-King Salman Park Project-Rental Generator- 350/400 KVA with Transportation- Sudhir Rental Generators | APPROVED | No | 2025-07-03 | Abas, Mohammed Fekry | 2025-07-08 | 2025-07-08 |  |  | Rental Generator- 350/400 KVA with Transportation- Sudhir Rental Generators | 29000 | 7466 | 0 | STANDARD | SUDHIR EQUIPMENT RENTAL COMPANY | SAR | 29000 | APPROVED |  |  | 2025-07-14 | 0 | 6 | Babic, Marian | -45846 | 6
105-12 | 8390-King Salman Park Project | 7321 | Alu_MV Cable Clamps | APPROVED | No | 2025-08-10 | Abas, Mohammed Fekry | 2025-08-18 | 2025-08-18 |  |  | Alu_MV Cable Clamps-plz approve | 0 | 6871 | 1 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 12900 | APPROVED |  |  | 2025-09-21 | -12900 | 34 | Babic, Marian | -45887 | 34
105-12 | 8390-King Salman Park Project | 7335 | Cu/Pvc _R-Blu-Blk-Y-Grey_Flexibile Wires | APPROVED | No | 2025-08-12 | Abas, Mohammed Fekry | 2025-08-18 | 2025-08-18 |  |  | Cu/Pvc _R-Blu-Blk-Y-Grey_Flexibile Wires | 0 | 7675 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 2645.65 | APPROVED |  |  | 2025-09-21 | -2645.65 | 34 | Babic, Marian | -45887 | 34
105-12 | 8390-King Salman Park Project | 7360 | Sudhir_Rental Generator 350/400 KVA | REJECTED | No | 2025-08-14 | Yasmin, Ahmed Elsayed Mohamed | 2025-08-17 | 2025-08-17 |  | 2025-08-17 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45886 | -45886
105-12 | 8390-King Salman Park Project | 7361 | Sudhir_Rental Generator-350/400 KVA | APPROVED | No | 2025-08-14 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | Sudhir_Rental Generator-350/400 KVA | 0 | 7466 | 1 | STANDARD | SUDHIR EQUIPMENT RENTAL COMPANY | SAR | 54000 | APPROVED |  |  | 2025-09-09 | -54000 | 15 | Babic, Marian | -45894 | 15
105-12 | 8390-King Salman Park Project | 7722 | Additional_Steel Name Plates | APPROVED | No | 2025-09-11 | Abas, Mohammed Fekry | 2025-09-28 | 2025-09-28 |  |  | Additional_Steel Name Plates | 0 | 6922 | 1 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 23226 | APPROVED |  |  | 2025-11-27 | -23226 | 60 | Babic, Marian | -45928 | 60
105-12 | 8390-King Salman Park Project | 7831 | Tools, Paint & Gounding Material | APPROVED | No | 2025-09-25 | Abas, Mohammed Fekry | 2025-10-02 | 2025-10-02 |  |  | Tools, Paint & Gounding Material | 0 | 7782 | 0 | STANDARD | Ahmed Essa Mohammed Al Muslim Est. | SAR | 40000 | APPROVED |  |  | 2025-10-15 | -40000 | 13 | Babic, Marian | -45932 | 13
105-12 | 8390-King Salman Park Project | 7873 | Trollies for SWGR | RETURNED | No | 2025-10-01 | Babic, Marian | 2025-10-26 | 2025-10-06 | 2025-10-26 |  | please resubmit after having confirmed CO with client | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45936 | -45936
105-12 | 8390-King Salman Park Project | 7916 | Supply of Adjustable Resistors | RETURNED | No | 2025-10-07 | Hegazy, Ayman | 2025-10-14 | 2025-10-13 | 2025-10-14 |  | To Update | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -45943 | -45943
105-12 | 8390-King Salman Park Project | 8467 | Diesel Supply for Rental Generator | RETURNED | No | 2025-12-07 | Babic, Marian | 2025-12-23 | 2025-12-17 | 2025-12-23 |  | over budget | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46008 | -46008
105-12 | 8390-King Salman Park Project | 8595 | Diesel Supply_Rental Genset_Civil Works | APPROVED | No | 2025-12-28 | Abas, Mohammed Fekry | 2026-01-13 | 2026-01-13 |  |  | Diesel Supply_Rental Genset-KSP90 | 0 | 6561 | 3 | STANDARD | Talaea Alahlam Trading Company | SAR | 54950 | APPROVED | 2026-01-20 | 2026-01-25 | 2026-01-28 | -54950 | 15 | Babic, Marian | 12 | 15
105-12 | 8390-King Salman Park Project | 8679 | OS | REJECTED | No | 2026-01-11 |  |  |  |  | 2026-01-11 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | 0 | 0
105-12 | 8390-King Salman Park Project | 8680 | GT & AUX. Transformer Oil Sampling | APPROVED | No | 2026-01-11 | Abas, Mohammed Fekry | 2026-01-22 | 2026-01-25 |  |  | GT & AUX. Transformer Oil Sampling-KSP90 | 0 | 7082 | 1 | STANDARD | Gulf Laboratory Technical Services (S) | SAR | 9800 | IN PROCESS | 2026-01-27 | 2026-01-28 |  | -9800 | 7 | Babic, Marian | 3 | -46047
105-12 | 8390-King Salman Park Project | 8680 | GT & AUX. Transformer Oil Sampling | APPROVED | No | 2026-01-11 | Abas, Mohammed Fekry | 2026-01-22 | 2026-01-25 |  |  | GT & AUX. Transformer Oil Sampling-KSP90 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46047 | -46047
105-13 | AI Platform and Solution | 133 | AI Platform and Solution-AI Platform and Solution | APPROVED | No | 2021-10-11 | Abas, Mohammed Fekry | 2021-10-12 | 2021-10-12 |  |  |  | 18281250.01 | 3836 | 0 | STANDARD | REDINGTON SAUDI ARABIA DISTRIBUTION CO. | SAR | 18281250.01 | APPROVED |  |  | 2021-11-08 | 0 | 27 | Abuhammad, Samir | -44481 | 27
105-15 | Saudia Participation In DAS | 177 | Saudia Participation In DAS-Payment against power generator | APPROVED | No | 2021-10-31 | Abas, Mohammed Fekry | 2021-10-31 | 2021-10-31 |  |  |  | 19732.87 | 3860 | 0 | STANDARD | F&E LLC FZE Trade License | USD | 19730.81 | APPROVED |  |  | 2021-11-14 | 2.06 | 14 | Alamri, Nedhal | -44500 | 14
105-15 | Saudia Participation In DAS | 178 | Saudia Participation In DAS-Payment Against project design | APPROVED | No | 2021-10-31 | Abas, Mohammed Fekry | 2021-10-31 | 2021-10-31 |  |  |  | 2860.32 | 3854 | 0 | STANDARD | Paulius Preimonas | EUR | 2863.5 | APPROVED |  |  | 2021-11-02 | -3.18 | 2 | Babic, Marian | -44500 | 2
105-15 | Saudia Participation In DAS | 431 | Saudia Participation In DAS-Payment Against Extra working hours | APPROVED | No | 2022-01-25 | Abas, Mohammed Fekry | 2022-01-25 | 2022-01-25 |  |  |  | 14027.89 | 3860 | 1 | STANDARD | F&E LLC FZE Trade License | USD | 14028.07 | APPROVED |  |  | 2022-02-17 | -0.18 | 23 | Babic, Marian | -44586 | 23
105-15 | Saudia Participation In DAS | 451 | Saudia Participation In DAS-Payment against event design and production | APPROVED | No | 2022-02-01 | Abas, Mohammed Fekry | 2022-02-01 | 2022-02-01 |  |  |  | 660140 | 3858 | 3 | STANDARD | Multilem Middle East Events LLC | SAR | 660140 | REJECTED |  |  |  | 0 |  | Babic, Marian | -44593 | -44593
105-15 | Saudia Participation In DAS | 451 | Saudia Participation In DAS-Payment against event design and production | APPROVED | No | 2022-02-01 | Abas, Mohammed Fekry | 2022-02-01 | 2022-02-01 |  |  |  | 660140 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44593 | -44593
105-16 | Unified Contract 36kV - Riyadh | 1172 | Unified Contract 36kV - Riyadh-TCIL (P.O 4252)- S.O | REJECTED | No | 2023-04-09 | BABEKAR, MOHAMMED HUSSAIN | 2023-04-09 |  |  | 2023-04-09 |  | 2500000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-16 | Unified Contract 36kV - Riyadh | 1173 | Unified Contract 36kV - Riyadh-Pulse (P.O4270).SO | APPROVED | No | 2023-04-09 | BABEKAR, MOHAMMED HUSSAIN | 2023-05-28 | 2023-04-13 |  |  |  | 2038926.96 | 4252 | 0 | BLANKET | Telecommunications Consultants India Ltd. | SAR | 0 | APPROVED |  |  | 2022-11-09 | 2038926.96 | -155 | Abuhammad, Samir | -45029 | -155
105-16 | Unified Contract 36kV - Riyadh | 1173 | Unified Contract 36kV - Riyadh-Pulse (P.O4270).SO | APPROVED | No | 2023-04-09 | BABEKAR, MOHAMMED HUSSAIN | 2023-05-28 | 2023-04-13 |  |  |  | 461073.04 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45029 | -45029
105-16 | Unified Contract 36kV - Riyadh | 1174 | Unified Contract 36kV - Riyadh-TCIL (P.O 4252)- S.O | APPROVED | No | 2023-04-09 | BABEKAR, MOHAMMED HUSSAIN | 2023-05-28 | 2023-04-13 |  |  |  | 365290.72 | 4252 | 0 | BLANKET | Telecommunications Consultants India Ltd. | SAR | 0 | APPROVED |  |  | 2022-11-09 | 365290.72 | -155 | Abuhammad, Samir | -45029 | -155
105-16 | Unified Contract 36kV - Riyadh | 1174 | Unified Contract 36kV - Riyadh-TCIL (P.O 4252)- S.O | APPROVED | No | 2023-04-09 | BABEKAR, MOHAMMED HUSSAIN | 2023-05-28 | 2023-04-13 |  |  |  | 2134709.28 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45029 | -45029
105-16 | Unified Contract 36kV - Riyadh | 1984 | Unified Contract 36kV - Riyadh-HDD blanket PO.4601 | APPROVED | No | 2023-12-17 | BABEKAR, MOHAMMED HUSSAIN | 2023-12-19 | 2023-12-19 |  |  |  | 194750 | 4601 | 0 | BLANKET | Saleh Mohammed Al Yahya Contracting Company | SAR | 0 | APPROVED |  |  | 2023-09-13 | 194750 | -97 | Abuhammad, Samir | -45279 | -97
105-16 | Unified Contract 36kV - Riyadh | 1984 | Unified Contract 36kV - Riyadh-HDD blanket PO.4601 | APPROVED | No | 2023-12-17 | BABEKAR, MOHAMMED HUSSAIN | 2023-12-19 | 2023-12-19 |  |  |  | 500000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45279 | -45279
105-16 | Unified Contract 36kV - Riyadh | 1984 | Unified Contract 36kV - Riyadh-HDD blanket PO.4601 | APPROVED | No | 2023-12-17 | BABEKAR, MOHAMMED HUSSAIN | 2023-12-19 | 2023-12-19 |  |  |  | 805250 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45279 | -45279
105-16 | Unified Contract 36kV - Riyadh | 1989 | Unified Contract 36kV - Riyadh-Barq Plus blanket P.O 4682 | RETURNED | No | 2023-12-18 | Abuhammad, Samir | 2025-11-13 | 2025-01-19 |  |  |  | 1200000 | 4682 | 0 | BLANKET | Barq Plus for Contracting | SAR | 0 | APPROVED |  |  | 2023-11-06 | 1200000 |  | Abuhammad, Samir | -45676 | -440
105-16 | Unified Contract 36kV - Riyadh | 1989 | Unified Contract 36kV - Riyadh-Barq Plus blanket P.O 4682 | RETURNED | No | 2023-12-18 | Abuhammad, Samir | 2025-11-13 | 2025-01-19 |  |  |  | 4800000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45676 | -45676
105-16 | Unified Contract 36kV - Riyadh | 1990 | Unified Contract 36kV - Riyadh-Al-Taimi blancket P.O 4598 | APPROVED | No | 2023-12-18 | Abas, Mohammed Fekry | 2025-01-13 | 2025-01-14 | 2024-05-01 |  | PM has to issue the SO. | 2500000 | 4598 | 0 | BLANKET | Mohammed Abdullah Al Tamimi Construction Est | SAR | 0 | APPROVED |  |  | 2023-09-11 | 2500000 | -491 | Abuhammad, Samir | -45671 | -491
105-16 | Unified Contract 36kV - Riyadh | 1990 | Unified Contract 36kV - Riyadh-Al-Taimi blancket P.O 4598 | APPROVED | No | 2023-12-18 | Abas, Mohammed Fekry | 2025-01-13 | 2025-01-14 | 2024-05-01 |  | PM has to issue the SO. | 2500000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45671 | -45671
105-16 | Unified Contract 36kV - Riyadh | 3676 | Unified Contract 36kV - Riyadh-buy 4 boom trucks with fully accessories (10&12 tons) | RETURNED | No | 2024-06-25 | Abuhammad, Samir | 2024-11-11 | 2024-07-02 | 2024-11-11 |  | not matching market price. | 1000000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45475 | -45475
105-16 | Unified Contract 36kV - Riyadh | 4111 | Unified Contract 36kV - Riyadh-Maintenance items | RETURNED | No | 2024-08-07 | Abuhammad, Samir | 2024-08-18 | 2024-08-08 | 2024-08-18 |  | No need PR for blanket agreemnt. | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45512 | -45512
105-19 | Development of AI Platform | 346 | Development of AI Platform-Supply and Development of AI Platform | APPROVED | No | 2021-12-23 | Abas, Mohammed Fekry | 2021-12-26 | 2021-12-26 | 2021-12-23 | 2021-12-23 | As discussed with PM, the PR should be in English , since the project documents and the manual PO by english , the english language is required internally. | 19062464.01 | 3924 | 0 | STANDARD | Gulf Application Co | SAR | 19062464.01 | APPROVED |  |  | 2022-01-05 | 0 | 10 | Abuhammad, Samir | -44556 | 10
105-20 | Big Data Analytics Tools Licen | 193 | Big Data Analytics Tools Licen-Cloudera Ddta Platform Licenses | APPROVED | No | 2021-11-16 | Abas, Mohammed Fekry | 2021-11-16 | 2021-11-16 |  |  |  | 1208308.11 | 3866 | 0 | STANDARD | Starlink Computer and Networks Company | SAR | 1208308.11 | APPROVED |  |  | 2021-11-23 | 0 | 7 | Abuhammad, Samir | -44516 | 7
105-21 | Data center facility for NEOM | 287 | Data center facility for NEOM-Site Survey | APPROVED | No | 2021-11-30 | Abas, Mohammed Fekry | 2021-11-30 | 2021-11-30 |  |  |  | 2061923.8 | 3885 | 0 | STANDARD | China Saudi Communication Service Co.Ltd | SAR | 2061923.8 | APPROVED |  |  | 2021-11-30 | 0 | 0 | Abuhammad, Samir | -44530 | 0
105-21 | Data center facility for NEOM | 350 | Data center facility for NEOM-Gulf Applications Co - NEOM-DC project | APPROVED | No | 2021-12-27 | Abas, Mohammed Fekry | 2021-12-27 | 2021-12-28 |  |  |  | 82696772.96 | 3928 | 0 | STANDARD | Gulf Application Co | SAR | 82696772.96 | APPROVED |  |  | 2022-01-05 | 0 | 8 | Abuhammad, Samir | -44558 | 8
105-24 | Realfiction Kaust | 288 | Realfiction Kaust-Realfiction Purchasing | APPROVED | No | 2021-11-30 | Abas, Mohammed Fekry | 2021-11-30 | 2021-11-30 |  |  |  | 35935.49 | 3893 | 0 | STANDARD | Realfiction APS | USD | 36399.11 | APPROVED |  |  | 2021-12-09 | -463.62 | 9 | Babic, Marian | -44530 | 9
105-26 | Neom Realfiction | 295 | Neom Realfiction-PR against project content development | APPROVED | No | 2021-12-02 | Abas, Mohammed Fekry | 2021-12-02 | 2021-12-05 |  |  |  | 206340.2 | 3912 | 0 | STANDARD | Realfiction APS | USD | 209010.82 | APPROVED |  |  | 2021-12-13 | -2670.62 | 8 | Babic, Marian | -44535 | 8
105-26 | Neom Realfiction | 509 | Neom Realfiction-Second Payment of Realfiction Content Creation | RETURNED | No | 2022-02-24 | Babic, Marian | 2022-02-28 | 2022-02-27 | 2022-02-28 |  | As discussed it is not required | 37500 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44619 | -44619
105-26 | Neom Realfiction | 651 | Neom Realfiction-NEOM - HD3 Vesa Mount IPAD | APPROVED | No | 2022-05-25 | Abas, Mohammed Fekry | 2022-05-25 | 2022-05-26 |  |  |  | 1717.5 | 4121 | 0 | STANDARD | Realfiction APS | USD | 1717.5 | APPROVED |  |  | 2022-05-30 | 0 | 4 | Babic, Marian | -44707 | 4
105-27 | Music Commission Midwam | 296 | Music Commission Midwam-Payment against project services | APPROVED | No | 2021-12-02 | Abas, Mohammed Fekry | 2021-12-02 | 2021-12-05 |  |  |  | 180000 | 3914 | 0 | STANDARD | Memco International | SAR | 180000 | APPROVED |  |  | 2021-12-13 | 0 | 8 | Babic, Marian | -44535 | 8
105-27 | Music Commission Midwam | 341 | Music Commission Midwam-Payment against additional invoice | APPROVED | No | 2021-12-22 | Abas, Mohammed Fekry | 2021-12-22 | 2021-12-22 |  |  |  | 28500 | 3914 | 1 | STANDARD | Memco International | SAR | 28500 | APPROVED |  |  | 2022-01-02 | 0 | 11 | Babic, Marian | -44552 | 11
105-31 | Streetlights Riyadh, Phase 3 | 499 | Streetlights Riyadh, Phase 3-Fuse, 6 Amps, 130/380 V, 50/60 Hz, Cylindrical type, Dimension: 8.5x31.5 mm | APPROVED | No | 2022-02-23 | Abas, Mohammed Fekry | 2022-02-24 | 2022-02-27 |  |  |  | 40000 | 4038 | 0 | STANDARD | Khubara Al-Emaar Trading Est. | SAR | 40000 | APPROVED |  |  | 2022-03-17 | 0 | 18 | AlQuraish, Sajjad Hazem | -44619 | 18
105-31 | Streetlights Riyadh, Phase 3 | 507 | Streetlights Riyadh, Phase 3-LED fixtures installation, testing, & Commisionning | APPROVED | No | 2022-02-24 | Abas, Mohammed Fekry | 2022-02-26 | 2022-02-28 |  |  |  | 1860000 | 4027 | 0 | STANDARD | EXPERIENCE&EXCELLENCE FOR CONTRACTING | SAR | 1860000 | APPROVED |  |  | 2022-03-09 | 0 | 9 | Babic, Marian | -44620 | 9
105-31 | Streetlights Riyadh, Phase 3 | 508 | Streetlights Riyadh, Phase 3-Street Survey for Engineering Studies | APPROVED | No | 2022-02-24 | Abas, Mohammed Fekry | 2022-02-26 | 2022-02-28 |  |  |  | 114000 | 4026 | 0 | STANDARD | EXPERIENCE&EXCELLENCE FOR CONTRACTING | SAR | 114000 | APPROVED |  |  | 2022-03-09 | 0 | 9 | Babic, Marian | -44620 | 9
105-31 | Streetlights Riyadh, Phase 3 | 601 | Streetlights Riyadh, Phase 3-Lighting | APPROVED | No | 2022-04-17 | Abas, Mohammed Fekry | 2022-04-18 | 2022-04-18 |  |  |  | 27171666.31 | 4024 | 12 | STANDARD | SCHREDER GULF LIGHTTING LLC. | USD | 27128367.6 | APPROVED |  |  | 2022-04-26 | 43298.71 | 8 | Babic, Marian | -44669 | 8
105-31 | Streetlights Riyadh, Phase 3 | 610 | Streetlights Riyadh, Phase 3-Streetlights Riyadh III, Fuse, from 2 to 6 Amps, 130/380 V, 50/60 Hz, Cylindrical type, Dimension: 10x38 mm | APPROVED | No | 2022-04-24 | Abas, Mohammed Fekry | 2022-04-27 | 2022-04-28 |  |  |  | 30000 | 4101 | 0 | STANDARD | Khubara Al-Emaar Trading Est. | SAR | 25000 | APPROVED |  |  | 2022-05-17 | 5000 | 19 | Abuhammad, Samir | -44679 | 19
105-31 | Streetlights Riyadh, Phase 3 | 611 | Streetlights Riyadh, Phase 3-Fuse Carrier, 500v-32A, 10*38 | APPROVED | No | 2022-04-24 | Abas, Mohammed Fekry | 2022-04-27 | 2022-04-28 |  |  |  | 130000 | 4101 | 0 | STANDARD | Khubara Al-Emaar Trading Est. | SAR | 130000 | APPROVED |  |  | 2022-05-17 | 0 | 19 | Abuhammad, Samir | -44679 | 19
105-31 | Streetlights Riyadh, Phase 3 | 674 | Streetlights Riyadh, Phase 3-LED Installation | APPROVED | No | 2022-06-03 | Abas, Mohammed Fekry | 2022-06-07 | 2022-06-07 |  |  |  | 1550000 | 4136 | 0 | STANDARD | MAHAR ALFANN FOR CONTRACTING | SAR | 1550000 | APPROVED |  |  | 2022-06-22 | 0 | 15 | Abuhammad, Samir | -44719 | 15
105-31 | Streetlights Riyadh, Phase 3 | 674 | Streetlights Riyadh, Phase 3-LED Installation | APPROVED | No | 2022-06-03 | Abas, Mohammed Fekry | 2022-06-07 | 2022-06-07 |  |  |  | 1550000 | 4136 | 1 | STANDARD | MAHAR ALFANN FOR CONTRACTING | SAR | 1316880 | APPROVED |  |  | 2022-11-16 | 233120 | 162 | Abuhammad, Samir | -44719 | 162
105-31 | Streetlights Riyadh, Phase 3 | 675 | Streetlights Riyadh, Phase 3-Drop wires | APPROVED | No | 2022-06-03 | Abas, Mohammed Fekry | 2022-06-28 | 2022-06-29 | 2022-06-26 |  | As discussed please increase the unit price | 10500 | 4174 | 0 | STANDARD | Power Solutions Co. for Electrical Equipements | SAR | 9600 | APPROVED |  |  | 2022-08-07 | 900 | 39 | Babic, Marian | -44741 | 39
105-31 | Streetlights Riyadh, Phase 3 | 702 | Streetlights Riyadh, Phase 3-Supply of Fuses Carrier for Tarshed Project Riyadh Ph3. | APPROVED | No | 2022-06-21 | Abas, Mohammed Fekry | 2022-06-26 | 2022-06-26 |  |  |  | 19500 | 4101 | 1 | STANDARD | Khubara Al-Emaar Trading Est. | SAR | 19500 | APPROVED |  |  | 2022-08-08 | 0 | 43 | Abuhammad, Samir | -44738 | 43
105-31 | Streetlights Riyadh, Phase 3 | 727 | Streetlights Riyadh, Phase 3-Female arms 50mm neck dia with nails | APPROVED | No | 2022-07-06 | Abas, Mohammed Fekry | 2022-07-07 | 2022-07-07 |  |  |  | 16500 | 4180 | 0 | STANDARD | factory for assenbly of Machanical and Electrical works | SAR | 15250 | APPROVED |  |  | 2022-08-15 | 1250 | 39 | Babic, Marian | -44749 | 39
105-31 | Streetlights Riyadh, Phase 3 | 755 | Streetlights Riyadh, Phase 3-Project Expansion-LED Supply | APPROVED | No | 2022-08-06 | Abas, Mohammed Fekry | 2022-08-14 | 2022-08-16 |  |  |  | 2997081.43 | 4024 | 13 | STANDARD | SCHREDER GULF LIGHTTING LLC. | USD | 2992308.86 | APPROVED |  |  | 2022-08-28 | 4772.57 | 12 | Babic, Marian | -44789 | 12
105-31 | Streetlights Riyadh, Phase 3 | 917 | Streetlights Riyadh, Phase 3-Change order-LED Installation-EECC PO#4027 | APPROVED | No | 2022-11-16 | Abas, Mohammed Fekry | 2023-01-11 | 2023-01-15 |  |  |  | 531898 | 4027 | 1 | STANDARD | EXPERIENCE&EXCELLENCE FOR CONTRACTING | SAR | 531898 | APPROVED |  |  | 2023-02-12 | 0 | 28 | Babic, Marian | -44941 | 28
105-32 | Streetlights Jeddah, Phase 5 | 504 | Streetlights Jeddah, Phase 5-Schreder | APPROVED | No | 2022-02-23 | Abas, Mohammed Fekry | 2022-03-06 | 2022-03-06 | 2022-02-28 |  | As discussed | 5203900.12 | 4032 | 2 | STANDARD | SCHREDER GULF LIGHTTING LLC. | USD | 4933687.76 | APPROVED |  |  | 2022-06-15 | 270212.36 | 101 | Babic, Marian | -44626 | 101
105-32 | Streetlights Jeddah, Phase 5 | 504 | Streetlights Jeddah, Phase 5-Schreder | APPROVED | No | 2022-02-23 | Abas, Mohammed Fekry | 2022-03-06 | 2022-03-06 | 2022-02-28 |  | As discussed | 11854917.12 | 4032 | 0 | STANDARD | SCHREDER GULF LIGHTTING LLC. | USD | 11822746.91 | APPROVED |  |  | 2022-03-17 | 32170.21 | 11 | Babic, Marian | -44626 | 11
105-32 | Streetlights Jeddah, Phase 5 | 518 | Streetlights Jeddah, Phase 5-MCB | APPROVED | No | 2022-03-06 | Abas, Mohammed Fekry | 2022-03-13 | 2022-03-13 |  |  |  | 225000 | 4094 | 0 | STANDARD | Supply Wings | SAR | 185000.1 | APPROVED |  |  | 2022-05-08 | 39999.9 | 56 | Babic, Marian | -44633 | 56
105-32 | Streetlights Jeddah, Phase 5 | 556 | Streetlights Jeddah, Phase 5-installation | APPROVED | No | 2022-03-14 | Abas, Mohammed Fekry | 2022-03-15 | 2022-03-16 |  |  |  | 1874756 | 4045 | 0 | STANDARD | MAHAR ALFANN FOR CONTRACTING | SAR | 1874756 | APPROVED |  |  | 2022-03-24 | 0 | 8 | Babic, Marian | -44636 | 8
105-32 | Streetlights Jeddah, Phase 5 | 556 | Streetlights Jeddah, Phase 5-installation | APPROVED | No | 2022-03-14 | Abas, Mohammed Fekry | 2022-03-15 | 2022-03-16 |  |  |  | 1874756 | 4045 | 1 | STANDARD | MAHAR ALFANN FOR CONTRACTING | SAR | 1564756 | APPROVED |  |  | 2022-07-20 | 310000 | 126 | Babic, Marian | -44636 | 126
105-32 | Streetlights Jeddah, Phase 5 | 597 | Streetlights Jeddah, Phase 5-Arms | REJECTED | No | 2022-04-10 | Chughtai, Sameer | 2022-04-10 | 2022-04-10 |  | 2022-04-10 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -44661 | -44661
105-32 | Streetlights Jeddah, Phase 5 | 598 | Streetlights Jeddah, Phase 5-Arms | RETURNED | No | 2022-04-10 | Babic, Marian | 2022-04-18 | 2022-04-13 | 2022-04-18 |  | The price needs to be changed | 35700 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44664 | -44664
105-32 | Streetlights Jeddah, Phase 5 | 603 | Streetlights Jeddah, Phase 5-Arms (Regular) | APPROVED | No | 2022-04-18 | Abas, Mohammed Fekry | 2022-04-20 | 2022-04-20 |  |  |  | 61625 | 4110 | 0 | STANDARD | factory for assenbly of Machanical and Electrical works | SAR | 59500 | APPROVED |  |  | 2022-05-17 | 2125 | 27 | Babic, Marian | -44671 | 27
105-32 | Streetlights Jeddah, Phase 5 | 629 | Streetlights Jeddah, Phase 5-schreder | APPROVED | No | 2022-05-05 | Abas, Mohammed Fekry | 2022-05-05 | 2022-05-05 |  |  |  | 903858.34 | 4032 | 2 | STANDARD | SCHREDER GULF LIGHTTING LLC. | USD | 668877.41 | APPROVED |  |  | 2022-06-15 | 234980.93 | 41 | Babic, Marian | -44686 | 41
105-32 | Streetlights Jeddah, Phase 5 | 629 | Streetlights Jeddah, Phase 5-schreder | APPROVED | No | 2022-05-05 | Abas, Mohammed Fekry | 2022-05-05 | 2022-05-05 |  |  |  | 6331567.54 | 4032 | 1 | STANDARD | SCHREDER GULF LIGHTTING LLC. | USD | 6314659.42 | APPROVED |  |  | 2022-05-17 | 16908.12 | 12 | Babic, Marian | -44686 | 12
105-32 | Streetlights Jeddah, Phase 5 | 630 | Streetlights Jeddah, Phase 5-MOT Arms | APPROVED | No | 2022-05-05 | Abas, Mohammed Fekry | 2022-05-09 | 2022-05-11 |  |  |  | 38724 | 4110 | 0 | STANDARD | factory for assenbly of Machanical and Electrical works | SAR | 38724 | APPROVED |  |  | 2022-05-17 | 0 | 6 | Babic, Marian | -44692 | 6
105-32 | Streetlights Jeddah, Phase 5 | 671 | Streetlights Jeddah, Phase 5-Arm adapter | APPROVED | No | 2022-06-02 | Abas, Mohammed Fekry | 2022-06-07 | 2022-06-12 |  |  |  | 8960 | 4110 | 1 | STANDARD | factory for assenbly of Machanical and Electrical works | SAR | 8960 | APPROVED |  |  | 2022-06-22 | 0 | 10 | Babic, Marian | -44724 | 10
105-32 | Streetlights Jeddah, Phase 5 | 733 | Streetlights Jeddah, Phase 5-HM installation | APPROVED | No | 2022-07-20 | Abas, Mohammed Fekry | 2022-07-24 | 2022-07-24 |  |  |  | 508000 | 4045 | 2 | STANDARD | MAHAR ALFANN FOR CONTRACTING | SAR | 508000 | APPROVED |  |  | 2022-08-11 | 0 | 18 | Babic, Marian | -44766 | 18
105-32 | Streetlights Jeddah, Phase 5 | 733 | Streetlights Jeddah, Phase 5-HM installation | APPROVED | No | 2022-07-20 | Abas, Mohammed Fekry | 2022-07-24 | 2022-07-24 |  |  |  | 508000 | 4045 | 3 | STANDARD | MAHAR ALFANN FOR CONTRACTING | SAR | 467840 | APPROVED |  |  | 2023-02-21 | 40160 | 212 | Babic, Marian | -44766 | 212
105-32 | Streetlights Jeddah, Phase 5 | 775 | Streetlights Jeddah, Phase 5-Cartons for MOT fixture | RETURNED | No | 2022-08-28 | Babic, Marian | 2024-03-26 | 2022-09-07 | 2024-03-26 |  | old PR, not required | 108500 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44811 | -44811
105-32 | Streetlights Jeddah, Phase 5 | 809 | Streetlights Jeddah, Phase 5-Arms- PO#4110 | APPROVED | No | 2022-09-07 | Abas, Mohammed Fekry | 2022-09-13 | 2022-09-14 |  |  |  | 27000 | 4110 | 2 | STANDARD | factory for assenbly of Machanical and Electrical works | SAR | 27000 | APPROVED |  |  | 2022-10-04 | 0 | 20 | Babic, Marian | -44818 | 20
105-32 | Streetlights Jeddah, Phase 5 | 1085 | Streetlights Jeddah, Phase 5-MOT_Highmast_Installation | APPROVED | No | 2023-02-26 | Abas, Mohammed Fekry | 2023-02-28 | 2023-03-01 |  |  |  | 58350 | 4045 | 4 | STANDARD | MAHAR ALFANN FOR CONTRACTING | SAR | 58350 | APPROVED |  |  | 2023-03-16 | 0 | 15 | Babic, Marian | -44986 | 15
105-32 | Streetlights Jeddah, Phase 5 | 1607 | Streetlights Jeddah, Phase 5-Mahar PR | APPROVED | No | 2023-10-18 | Abas, Mohammed Fekry | 2023-10-22 | 2023-10-22 |  |  |  | 466426 | 4045 | 5 | STANDARD | MAHAR ALFANN FOR CONTRACTING | SAR | 466426 | APPROVED |  |  | 2023-11-26 | 0 | 35 | Babic, Marian | -45221 | 35
105-32 | Streetlights Jeddah, Phase 5 | 1608 | Streetlights Jeddah, Phase 5-Mahar new PR2 | APPROVED | No | 2023-10-18 | Abas, Mohammed Fekry | 2023-10-22 | 2023-10-22 |  |  |  | 25650 | 4045 | 5 | STANDARD | MAHAR ALFANN FOR CONTRACTING | SAR | 25650 | APPROVED |  |  | 2023-11-26 | 0 | 35 | Babic, Marian | -45221 | 35
105-34 | RSAF Support PO# 75092-2022 | 401 | RSAF Support PO# 75092-2022-RSAF Support | RETURNED | No | 2022-01-20 | Abuhammad, Samir | 2022-04-13 | 2022-01-25 | 2022-04-13 |  | Due close by cash as per PM request. | 13010779 | 3959 | 0 | STANDARD | Tapestry Solutions Inc. | USD | 13173413.74 | APPROVED |  |  | 2022-01-26 | -162634.74 |  | Babic, Marian | -44586 | 1
105-34 | RSAF Support PO# 75092-2022 | 401 | RSAF Support PO# 75092-2022-RSAF Support | RETURNED | No | 2022-01-20 | Abuhammad, Samir | 2022-04-13 | 2022-01-25 | 2022-04-13 |  | Due close by cash as per PM request. | 4000000 | 3976 | 0 | STANDARD | Marakn Al Tanmyah For Trading | SAR | 4000000 | APPROVED |  |  | 2022-02-15 | 0 |  | Abuhammad, Samir | -44586 | 21
105-34 | RSAF Support PO# 75092-2022 | 401 | RSAF Support PO# 75092-2022-RSAF Support | RETURNED | No | 2022-01-20 | Abuhammad, Samir | 2022-04-13 | 2022-01-25 | 2022-04-13 |  | Due close by cash as per PM request. | 4000000 | 3976 | 1 | STANDARD | Marakn Al Tanmyah For Trading | SAR | 1008212.57 | APPROVED |  |  | 2022-07-24 | 2991787.43 |  | Abuhammad, Samir | -44586 | 180
105-34 | RSAF Support PO# 75092-2022 | 401 | RSAF Support PO# 75092-2022-RSAF Support | RETURNED | No | 2022-01-20 | Abuhammad, Samir | 2022-04-13 | 2022-01-25 | 2022-04-13 |  | Due close by cash as per PM request. | 734782.61 | 3980 | 0 | STANDARD | ALNAFITHA INTERNATIONAL FOR INFORMATION TECHNOLOGY | SAR | 338643 | APPROVED |  |  | 2022-02-10 | 396139.61 |  | Abuhammad, Samir | -44586 | 16
105-34 | RSAF Support PO# 75092-2022 | 752 | RSAF Support PO# 75092-2022-Docker Enterprise 3.0 | APPROVED | No | 2022-08-02 | Abas, Mohammed Fekry | 2022-08-02 | 2022-08-04 |  |  |  | 22443.75 | 4179 | 0 | STANDARD | Nuaware Ltd | USD | 22443.74 | APPROVED |  |  | 2022-08-13 | 0.01 | 9 | Babic, Marian | -44777 | 9
105-35 | NGHA-KSSH Taif & KASH-Qassim | 522 | NGHA-KSSH Taif & KASH-Qassim-NGHA-Taif & Qassim Project - Professional Services of Cisco Solutions | APPROVED | No | 2022-03-06 | Abas, Mohammed Fekry | 2022-03-06 | 2022-03-06 |  |  |  | 2500000 | 4033 | 0 | STANDARD | Advanced Industrial Solutions | SAR | 2500000 | APPROVED |  |  | 2022-03-09 | 0 | 3 | Abuhammad, Samir | -44626 | 3
105-35 | NGHA-KSSH Taif & KASH-Qassim | 537 | NGHA-KSSH Taif & KASH-Qassim-EMC-Dell - Storage system - Isilon - Unity- Data domain | APPROVED | No | 2022-03-08 | Abas, Mohammed Fekry | 2022-03-08 | 2022-03-13 |  |  |  | 6467973.89 | 4061 | 0 | STANDARD | APTEC Saudi Arabia LCC | SAR | 6400016.96 | APPROVED |  |  | 2022-04-21 | 67956.93 | 39 | Abuhammad, Samir | -44633 | 39
105-35 | NGHA-KSSH Taif & KASH-Qassim | 579 | NGHA-KSSH Taif & KASH-Qassim-NGHA Taif & Qassim - 105-35 - Fortinet ( Firewall ) | APPROVED | No | 2022-03-24 | Abas, Mohammed Fekry | 2022-03-29 | 2022-03-31 |  |  |  | 3003755 | 4075 | 0 | STANDARD | Distributor Solutions Trading Company | SAR | 3003755 | APPROVED |  |  | 2022-04-26 | 0 | 26 | Abuhammad, Samir | -44651 | 26
105-35 | NGHA-KSSH Taif & KASH-Qassim | 580 | NGHA-KSSH Taif & KASH-Qassim-NGHA Taif & Qassim - 105-35 - Symantec | APPROVED | No | 2022-03-24 | Abas, Mohammed Fekry | 2022-03-29 | 2022-03-31 |  |  |  | 2779720.13 | 4074 | 0 | STANDARD | Starlink Computer and Networks Company | SAR | 2779720.13 | APPROVED |  |  | 2022-05-08 | 0 | 38 | Abuhammad, Samir | -44651 | 38
105-35 | NGHA-KSSH Taif & KASH-Qassim | 581 | NGHA-KSSH Taif & KASH-Qassim-NGHA Taif & Qassim - 105-35 - Infoblox | APPROVED | No | 2022-03-24 | Abas, Mohammed Fekry | 2022-03-29 | 2022-03-31 |  |  |  | 3283088.73 | 4070 | 0 | STANDARD | Starlink MDMC Arabian Trading Co | SAR | 3282988 | APPROVED |  |  | 2022-06-19 | 100.73 | 80 | Abuhammad, Samir | -44651 | 80
105-35 | NGHA-KSSH Taif & KASH-Qassim | 599 | NGHA-KSSH Taif & KASH-Qassim-NGHA Taif & Qassim - 105-35 - Imagicle | APPROVED | No | 2022-04-11 | Abas, Mohammed Fekry | 2022-04-11 | 2022-04-12 |  |  |  | 942000 | 4090 | 0 | STANDARD | MDS FOR COMPUTER SYSTEMS | SAR | 941833 | APPROVED |  |  | 2022-05-26 | 167 | 44 | Abuhammad, Samir | -44663 | 44
105-35 | NGHA-KSSH Taif & KASH-Qassim | 602 | NGHA-KSSH Taif & KASH-Qassim-NGHA Taif & Qassim - Commscope - DC Cabling | APPROVED | No | 2022-04-18 | Abas, Mohammed Fekry | 2022-04-19 | 2022-04-20 |  |  |  | 2157480.34 | 4095 | 0 | STANDARD | Al-jammaz Technologies LTD. | SAR | 2061198 | APPROVED |  |  | 2022-06-05 | 96282.34 | 46 | Abuhammad, Samir | -44671 | 46
105-35 | NGHA-KSSH Taif & KASH-Qassim | 639 | NGHA-KSSH Taif & KASH-Qassim-NGHA Taif & Qassim - Copper Tape | REJECTED | No | 2022-05-15 | Mraish, Fahed Mhd Yaser | 2022-08-25 |  |  | 2022-08-25 |  | 5800 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-35 | NGHA-KSSH Taif & KASH-Qassim | 640 | NGHA-KSSH Taif & KASH-Qassim-NGHA Taif & Qassim - Copper Tape | APPROVED | No | 2022-05-15 | Abas, Mohammed Fekry | 2022-08-30 | 2022-08-31 | 2022-08-25 |  | as per PM request to correct the lines | 5800 | 4117 | 0 | STANDARD | Hardware Solutions Builders Co Ltd | SAR | 5800 | APPROVED |  |  | 2022-06-05 | 0 | -87 | Abuhammad, Samir | -44804 | -87
105-35 | NGHA-KSSH Taif & KASH-Qassim | 640 | NGHA-KSSH Taif & KASH-Qassim-NGHA Taif & Qassim - Copper Tape | APPROVED | No | 2022-05-15 | Abas, Mohammed Fekry | 2022-08-30 | 2022-08-31 | 2022-08-25 |  | as per PM request to correct the lines | 5800 | 4214 | 0 | STANDARD | Hardware Solutions Builders Co Ltd | SAR | 5800 | APPROVED |  |  | 2022-09-06 | 0 | 6 | Abuhammad, Samir | -44804 | 6
105-35 | NGHA-KSSH Taif & KASH-Qassim | 898 | NGHA-KSSH Taif & KASH-Qassim-NGHA Taif & Qassim - Passive Components | APPROVED | No | 2022-10-30 | Abas, Mohammed Fekry | 2022-11-19 | 2022-11-20 | 2022-11-16 |  | Due to change the budget. | 300750.86 | 4266 | 0 | STANDARD | MULTINET COMMUNICATION FZE | SAR | 300750.86 | APPROVED |  |  | 2022-12-01 | 0 | 11 | Abuhammad, Samir | -44885 | 11
105-35 | NGHA-KSSH Taif & KASH-Qassim | 921 | NGHA-KSSH Taif & KASH-Qassim-NGHA- Taif & Qassim 105-35- Cisco | APPROVED | No | 2022-11-27 | Abas, Mohammed Fekry | 2022-11-27 | 2022-11-27 |  |  |  | 41132882.92 | 4087 | 2 | STANDARD | MDS FOR COMPUTER SYSTEMS | SAR | 41132882.92 | APPROVED |  |  | 2022-12-08 | 0 | 11 | Abuhammad, Samir | -44892 | 11
105-35 | NGHA-KSSH Taif & KASH-Qassim | 926 | NGHA-KSSH Taif & KASH-Qassim-NGHA Taif & Qassim - 105-35 - A10 | APPROVED | No | 2022-11-28 | Abas, Mohammed Fekry | 2022-11-30 | 2022-12-04 |  |  |  | 1357807.77 | 4083 | 2 | STANDARD | APTEC Saudi Arabia LCC | SAR | 1357807.77 | APPROVED |  |  | 2022-12-13 | 0 | 9 | Abuhammad, Samir | -44899 | 9
105-35 | NGHA-KSSH Taif & KASH-Qassim | 1068 | NGHA-KSSH Taif & KASH-Qassim-Installation, Testing & commissioning, DC Cabling And patch cord installation, Access switches and Access point installation for Taif Site | APPROVED | No | 2023-02-13 | Abas, Mohammed Fekry | 2023-02-15 | 2023-02-16 |  |  |  | 250000 | 4349 | 0 | STANDARD | Axis Networks Est | SAR | 250000 | APPROVED |  |  | 2023-03-16 | 0 | 28 | Abuhammad, Samir | -44973 | 28
105-35 | NGHA-KSSH Taif & KASH-Qassim | 1271 | NGHA-KSSH Taif & KASH-Qassim-Service Renewal (Calibration for Fluke Device ) | APPROVED | No | 2023-05-17 | Abas, Mohammed Fekry | 2023-05-21 | 2023-05-22 |  |  |  | 14425 | 4478 | 0 | STANDARD | Bright Wire Company | SAR | 14425 | APPROVED |  |  | 2023-06-05 | 0 | 14 | Abuhammad, Samir | -45068 | 14
105-35 | NGHA-KSSH Taif & KASH-Qassim | 1385 | NGHA-KSSH Taif & KASH-Qassim-Installation,Testing & commissioning,DC Equipment's And patch cord installation,Access switches and Access point installation including labeling,racing and staking…Etc, for Qassim Site | APPROVED | No | 2023-08-07 | Abas, Mohammed Fekry | 2023-08-07 | 2023-08-08 |  |  |  | 300000 | 4566 | 0 | STANDARD | Omed Information Technology for Communicatioms | SAR | 300000 | APPROVED |  |  | 2023-08-20 | 0 | 12 | Abuhammad, Samir | -45146 | 12
105-35 | NGHA-KSSH Taif & KASH-Qassim | 1403 | NGHA-KSSH Taif & KASH-Qassim-Passive materials for NGHA Taif & Qassim project. | APPROVED | No | 2023-08-10 | Abas, Mohammed Fekry | 2023-08-14 | 2023-08-16 |  |  |  | 51580 | 4577 | 0 | STANDARD | Al-jammaz Technologies LTD. | SAR | 51580 | APPROVED |  |  | 2023-08-30 | 0 | 14 | Abuhammad, Samir | -45154 | 14
105-35 | NGHA-KSSH Taif & KASH-Qassim | 1403 | NGHA-KSSH Taif & KASH-Qassim-Passive materials for NGHA Taif & Qassim project. | APPROVED | No | 2023-08-10 | Abas, Mohammed Fekry | 2023-08-14 | 2023-08-16 |  |  |  | 51580 | 4646 | 0 | STANDARD | Hardware Solutions Builders Co Ltd | SAR | 49834 | APPROVED |  |  | 2023-10-11 | 1746 | 56 | Abuhammad, Samir | -45154 | 56
105-35 | NGHA-KSSH Taif & KASH-Qassim | 1498 | NGHA-KSSH Taif & KASH-Qassim-Fluke Test With report For UTP Cables | APPROVED | No | 2023-09-13 | Abas, Mohammed Fekry | 2023-09-17 | 2023-09-18 |  |  |  | 104000 | 4516 | 2 | STANDARD | Omed Information Technology for Communicatioms | SAR | 104000 | APPROVED |  |  | 2023-10-04 | 0 | 16 | Abuhammad, Samir | -45187 | 16
105-35 | NGHA-KSSH Taif & KASH-Qassim | 2264 | NGHA-KSSH Taif & KASH-Qassim-Supply of Passive Materials- Commscope - DC Cabling | APPROVED | No | 2024-01-23 | Abas, Mohammed Fekry | 2024-01-24 | 2024-01-25 |  |  |  | 37512.2 | 5026 | 0 | STANDARD | Hardware Solutions Builders Co Ltd | SAR | 37496 | APPROVED |  |  | 2024-02-15 | 16.2 | 21 | Abuhammad, Samir | -45316 | 21
105-35 | NGHA-KSSH Taif & KASH-Qassim | 4376 | NGHA-KSSH Taif & KASH-Qassim-Supply of IR Collaborate Cisco ( Including maintenance & PS ) | APPROVED | No | 2024-09-04 | Abas, Mohammed Fekry | 2024-09-25 | 2024-09-26 |  |  |  | 700308 | 6344 | 0 | STANDARD | Integrated research (SINGAPORE) PTE.Limited. | USD | 694743.75 | APPROVED |  |  | 2025-08-02 | 5564.25 | 310 | Abuhammad, Samir | -45561 | 310
105-35 | NGHA-KSSH Taif & KASH-Qassim | 4484 | NGHA-KSSH Taif & KASH-Qassim-Supply of patch cord, power cord & SFP | APPROVED | No | 2024-09-19 | Abas, Mohammed Fekry | 2024-09-24 | 2024-09-24 |  |  |  | 15831 | 6256 | 0 | STANDARD | Integrated Network Solutions Trading Est. | SAR | 15831 | APPROVED |  |  | 2024-10-07 | 0 | 13 | Abuhammad, Samir | -45559 | 13
105-35 | NGHA-KSSH Taif & KASH-Qassim | 5264 | NGHA-KSSH Taif & KASH-Qassim-Supply of SFP's for Qassim site | APPROVED | No | 2024-12-23 | Abas, Mohammed Fekry | 2024-12-30 | 2024-12-30 |  |  |  | 15760 | 6718 | 0 | STANDARD | Integrated Network Solutions Trading Est. | SAR | 15760 | APPROVED |  |  | 2025-01-12 | 0 | 13 | Abuhammad, Samir | -45656 | 13
105-35 | NGHA-KSSH Taif & KASH-Qassim | 5989 | NGHA-KSSH Taif & KASH-Qassim-PR For SFP Transceiver Module | APPROVED | No | 2025-02-19 | Abas, Mohammed Fekry | 2025-02-26 | 2025-02-26 |  |  | SFP transceiver module-Budget Task#1.19 (Other Equipment) | 6300 | 6962 | 0 | STANDARD | Integrated Network Solutions Trading Est. | SAR | 6300 | APPROVED |  |  | 2025-03-09 | 0 | 11 | Abuhammad, Samir | -45714 | 11
105-35 | NGHA-KSSH Taif & KASH-Qassim | 6717 | NGHA-KSSH Taif & KASH-Qassim-PR For SQL Server Standard with License and Software Assurance-NGHA | REJECTED | No | 2025-05-26 | Mraish, Fahed Mhd Yaser | 2025-05-26 |  |  | 2025-05-26 | 3 Year SQL Subscription-NGHA Project(Budget Task#1.17) | 4656426.96 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | 0 | 0
105-35 | NGHA-KSSH Taif & KASH-Qassim | 6727 | NGHA-KSSH Taif & KASH-Qassim-PR For Miscrosoft SQL License -3 Years | APPROVED | No | 2025-05-27 | Abas, Mohammed Fekry | 2025-05-28 | 2025-05-29 |  |  | Microsoft SQL Licence-3 Years(Task #1.17) | 4656105 | 7399 | 0 | STANDARD | Nesma Injazat Information Technology Company | SAR | 4656105 | APPROVED |  |  | 2025-06-23 | 0 | 25 | Abuhammad, Samir | -45806 | 25
105-35 | NGHA-KSSH Taif & KASH-Qassim | 7658 | IM-Vision Controllers Configuration | APPROVED | No | 2025-09-08 | Abas, Mohammed Fekry | 2025-09-09 | 2025-09-10 |  |  | IM-Vision Controller-Budget Task#1.24 | 0 | 7785 | 0 | STANDARD | Etihad Al Aseel Contracting Company. | SAR | 240000 | APPROVED |  |  | 2025-10-16 | -240000 | 36 | Abuhammad, Samir | -45910 | 36
105-35 | NGHA-KSSH Taif & KASH-Qassim | 8400 | PR for DC NVARM battery at NGHA Qassim | RETURNED | No | 2025-12-01 | Abuhammad, Samir | 2025-12-29 | 2025-12-03 | 2025-12-29 |  | open tiket with Dell to solve the issue. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45994 | -45994
105-35 | NGHA-KSSH Taif & KASH-Qassim | 8403 | PR For Telephone Accesories -Qassim& Taif Sites | RETURNED | No | 2025-12-01 | Abuhammad, Samir | 2025-12-29 | 2025-12-03 | 2025-12-29 |  | Once approved alternative items from KSA market from the client. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45994 | -45994
105-35 | NGHA-KSSH Taif & KASH-Qassim | 8612 | PR For Dell Calypso I/O PCIe Controller Card | APPROVED | No | 2025-12-30 | Abas, Mohammed Fekry | 2026-01-12 | 2026-01-13 |  |  | PR For Dell PCIe Controller Card-Budget Task#1.18 | 0 | 15040 | 0 | STANDARD | Excellence Arabia Trading Company | SAR | 780 | APPROVED | 2026-01-19 | 2026-01-20 | 2026-01-26 | -780 | 13 | Abuhammad, Samir | 7 | 13
105-36 | Bus Stops-Riyadh | 956 | Bus Stops-Riyadh-Passive materials for Bus Stop Project 105-36 | APPROVED | No | 2022-12-25 | Abas, Mohammed Fekry | 2022-12-30 | 2023-01-02 |  |  |  | 43752 | 4309 | 0 | STANDARD | Hardware Solutions Builders Co Ltd | SAR | 43752 | APPROVED |  |  | 2023-01-15 | 0 | 13 | Abuhammad, Samir | -44928 | 13
105-36 | Bus Stops-Riyadh | 961 | Bus Stops-Riyadh-Supply of Telecom Outdoor Cabinet ( Conteg ) | APPROVED | No | 2023-01-01 | Abas, Mohammed Fekry | 2023-01-07 | 2023-01-09 |  |  |  | 164574 | 4318 | 0 | STANDARD | Global Distribution | SAR | 164574 | APPROVED |  |  | 2023-01-26 | 0 | 17 | Abuhammad, Samir | -44935 | 17
105-36 | Bus Stops-Riyadh | 962 | Bus Stops-Riyadh-Temporary solution | APPROVED | No | 2023-01-01 | Abas, Mohammed Fekry | 2023-01-07 | 2023-01-09 |  |  |  | 18780 | 4319 | 0 | STANDARD | Bright Wire Company | SAR | 18780 | APPROVED |  |  | 2023-01-18 | 0 | 9 | Abuhammad, Samir | -44935 | 9
105-36 | Bus Stops-Riyadh | 1126 | Bus Stops-Riyadh-FOC Activities | APPROVED | No | 2023-03-13 | Abas, Mohammed Fekry | 2023-03-13 | 2023-03-13 |  |  |  | 51000 | 4378 | 0 | STANDARD | ORIENTALS TECHNOLOGY EST. FOR CONTRACTING | SAR | 51000 | APPROVED |  |  | 2023-03-22 | 0 | 9 | Abuhammad, Samir | -44998 | 9
105-36 | Bus Stops-Riyadh | 1269 | Bus Stops-Riyadh-Outdoor rack installation and fiber splicing. | APPROVED | No | 2023-05-17 | Abas, Mohammed Fekry | 2023-05-21 | 2023-05-22 |  |  |  | 17040 | 4479 | 0 | STANDARD | ORIENTALS TECHNOLOGY EST. FOR CONTRACTING | SAR | 15000 | APPROVED |  |  | 2023-08-01 | 2040 | 71 | Abuhammad, Samir | -45068 | 71
105-36 | Bus Stops-Riyadh | 1363 | Bus Stops-Riyadh-Supply of PDU's for Bus stops project | REJECTED | No | 2023-07-19 | Alameer, Waleed | 2023-07-19 | 2023-07-19 |  | 2023-07-20 |  | 840 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45126 | -45126
105-37 | Red Sea Wireless Network Proje | 520 | Red Sea Wireless Network Proje-PR for Securna Material Red Sea Project - Wire Less Equipment For Manual PO # 8047-CS187-0 | APPROVED | No | 2022-03-06 | Abas, Mohammed Fekry | 2022-03-06 | 2022-03-07 |  |  |  | 1490028.75 | 4034 | 0 | STANDARD | Securna DMCC | USD | 1490028.75 | APPROVED |  |  | 2022-03-15 | 0 | 8 | Abuhammad, Samir | -44627 | 8
105-37 | Red Sea Wireless Network Proje | 526 | Red Sea Wireless Network Proje-PR For 6m Pole and Hand Winch | APPROVED | No | 2022-03-06 | Abas, Mohammed Fekry | 2022-03-06 | 2022-03-07 |  |  |  | 32737.5 | 4052 | 0 | STANDARD | Zhejiang ZEC Import & Export Co LTD | USD | 31237.5 | APPROVED |  |  | 2022-03-24 | 1500 | 17 | Abuhammad, Samir | -44627 | 17
105-37 | Red Sea Wireless Network Proje | 564 | Red Sea Wireless Network Proje-supply Cabinet manual Po# 8046 | APPROVED | No | 2022-03-16 | Abas, Mohammed Fekry | 2022-03-20 | 2022-03-21 |  |  |  | 35310.68 | 4048 | 0 | STANDARD | Canford Audio Limite | USD | 35310.68 | APPROVED |  |  | 2022-03-22 | 0 | 1 | Abuhammad, Samir | -44641 | 1
105-37 | Red Sea Wireless Network Proje | 570 | Red Sea Wireless Network Proje-PR for manual PO # 8045 Scatletr | APPROVED | No | 2022-03-21 | Abas, Mohammed Fekry | 2022-03-22 | 2022-03-22 |  |  |  | 139046.25 | 4054 | 0 | STANDARD | Scarlet Tech CO.LTD | USD | 139046.25 | APPROVED |  |  | 2022-03-29 | 0 | 7 | Abuhammad, Samir | -44642 | 7
105-37 | Red Sea Wireless Network Proje | 571 | Red Sea Wireless Network Proje-PR for Eworld RedSea Project | APPROVED | No | 2022-03-21 | Abas, Mohammed Fekry | 2022-03-22 | 2022-03-22 |  |  |  | 337984 | 4051 | 0 | STANDARD | Easy World for Communications Est | SAR | 337984 | APPROVED |  |  | 2022-03-31 | 0 | 9 | Abuhammad, Samir | -44642 | 9
105-37 | Red Sea Wireless Network Proje | 572 | Red Sea Wireless Network Proje-PR for Trident Manual PO # 8044 | APPROVED | No | 2022-03-21 | Abas, Mohammed Fekry | 2022-03-22 | 2022-03-22 |  |  |  | 1500000 | 4053 | 0 | STANDARD | Trident Structures PVT LTD | SAR | 1500000 | APPROVED |  |  | 2022-03-31 | 0 | 9 | Abuhammad, Samir | -44642 | 9
105-37 | Red Sea Wireless Network Proje | 583 | Red Sea Wireless Network Proje-PR For Services of Design, Installation and Logistic. | APPROVED | No | 2022-03-27 | Abas, Mohammed Fekry | 2022-03-29 | 2022-03-30 |  |  |  | 1145655 | 4067 | 0 | STANDARD | Prime Gate for Communication and information Technology Co | SAR | 1145440 | APPROVED |  |  | 2022-04-18 | 215 | 19 | Abuhammad, Samir | -44650 | 19
105-37 | Red Sea Wireless Network Proje | 655 | Red Sea Wireless Network Proje-PR for AlBatain 25m Radar Tower for RedSea Project | APPROVED | No | 2022-05-27 | Abas, Mohammed Fekry | 2022-05-29 | 2022-05-29 |  |  |  | 98747 | 4122 | 0 | STANDARD | Al Babtain Leblanc Telecommunications co ltd | SAR | 98747 | APPROVED |  |  | 2022-05-31 | 0 | 2 | Abuhammad, Samir | -44710 | 2
105-37 | Red Sea Wireless Network Proje | 656 | Red Sea Wireless Network Proje-PR for additional work of 25m radar tower civil works | APPROVED | No | 2022-05-27 | Abas, Mohammed Fekry | 2022-05-29 | 2022-05-29 |  |  |  | 94371.33 | 4067 | 1 | STANDARD | Prime Gate for Communication and information Technology Co | SAR | 94371 | APPROVED |  |  | 2022-06-07 | 0.33 | 9 | Abuhammad, Samir | -44710 | 9
105-37 | Red Sea Wireless Network Proje | 857 | Red Sea Wireless Network Proje-PR for NVR and WorkStation | RETURNED | No | 2022-10-03 | Abuhammad, Samir | 2022-11-08 | 2022-10-09 | 2022-11-08 |  | As per PM request. | 16000.94 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44843 | -44843
105-37 | Red Sea Wireless Network Proje | 874 | Red Sea Wireless Network Proje-PR for Operation and Maintenance of RedSea Project for 24 Months - RedSea Project | RETURNED | No | 2022-10-11 | Abuhammad, Samir | 2023-08-24 | 2022-10-16 | 2023-08-24 |  | Due to change the scope. | 994992 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44850 | -44850
105-37 | Red Sea Wireless Network Proje | 927 | Red Sea Wireless Network Proje-PR For Battery Cabinet RedSea Project | RETURNED | No | 2022-12-01 | Abuhammad, Samir | 2023-08-24 | 2023-01-09 | 2023-08-24 |  | Due to change the scope. | 8400 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44935 | -44935
105-37 | Red Sea Wireless Network Proje | 994 | Red Sea Wireless Network Proje-PR for Additional misc work done by Prime Gate | APPROVED | No | 2023-01-10 | Abas, Mohammed Fekry | 2023-01-17 | 2023-01-18 |  |  |  | 111566 | 4067 | 2 | STANDARD | Prime Gate for Communication and information Technology Co | SAR | 111566 | APPROVED |  |  | 2023-02-19 | 0 | 32 | Abuhammad, Samir | -44944 | 32
105-39 | SW License Renewal | 904 | SW License Renewal-Automation Anywhere | APPROVED | No | 2022-11-10 | Abas, Mohammed Fekry | 2022-11-10 | 2022-11-13 |  |  |  | 446857.2 | 4273 | 0 | STANDARD | Automation ِAnywhere | USD | 445668.76 | APPROVED |  |  | 2022-12-08 | 1188.44 | 25 | Abuhammad, Samir | -44878 | 25
105-41 | King Faisal Air Academy | 691 | King Faisal Air Academy-MMC Passive Materials | APPROVED | No | 2022-06-12 | Abas, Mohammed Fekry | 2022-06-14 | 2022-06-15 |  |  |  | 1210808.54 | 4144 | 0 | STANDARD | Horizon Dimension Trading Est | SAR | 5593208.62 | APPROVED |  |  | 2022-06-30 | -4382400.08 | 15 | Abuhammad, Samir | -44727 | 15
105-41 | King Faisal Air Academy | 1256 | King Faisal Air Academy-Copper Termination, testing, and commissioning | APPROVED | No | 2023-05-11 | Abas, Mohammed Fekry | 2023-05-16 | 2023-05-16 |  |  |  | 172800 | 4465 | 0 | STANDARD | Omed Information Technology for Communicatioms | SAR | 172800 | APPROVED |  |  | 2023-05-29 | 0 | 13 | Abuhammad, Samir | -45062 | 13
105-41 | King Faisal Air Academy | 1256 | King Faisal Air Academy-Copper Termination, testing, and commissioning | APPROVED | No | 2023-05-11 | Abas, Mohammed Fekry | 2023-05-16 | 2023-05-16 |  |  |  | 172800 | 4465 | 1 | STANDARD | Omed Information Technology for Communicatioms | SAR | 95148 | APPROVED |  |  | 2024-03-03 | 77652 | 292 | Abuhammad, Samir | -45062 | 292
105-41 | King Faisal Air Academy | 2784 | King Faisal Air Academy-Copper Termination, testing, and commissioning for King Faisal Air Academy Project | APPROVED | No | 2024-03-05 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 36000 | 5171 | 0 | STANDARD | Nabea Al Gawdah Company | SAR | 36000 | APPROVED |  |  | 2024-03-18 | 0 | 11 | Abuhammad, Samir | -45358 | 11
105-41 | King Faisal Air Academy | 3371 | King Faisal Air Academy-Copper Termination, testing, and commissioning for King Faisal Air Academy Project | APPROVED | No | 2024-05-12 | Abas, Mohammed Fekry | 2024-05-15 | 2024-05-15 |  |  |  | 41400 | 5620 | 0 | STANDARD | Nabea Al Gawdah Company | SAR | 41400 | APPROVED |  |  | 2024-06-03 | 0 | 19 | Abuhammad, Samir | -45427 | 19
105-41 | King Faisal Air Academy | 4520 | King Faisal Air Academy-Copper Termination, testing, and commissioning for King Faisal Air Academy Project | APPROVED | No | 2024-09-26 | Abas, Mohammed Fekry | 2024-10-14 | 2024-10-14 |  |  |  | 21996 | 6346 | 0 | STANDARD | Nabea Al Gawdah Company | SAR | 21996 | APPROVED |  |  | 2024-10-22 | 0 | 8 | Abuhammad, Samir | -45579 | 8
105-42 | Blockchain Asset Traceability | 910 | Blockchain Asset Traceability-Blockchain Asset Traceability platform | APPROVED | No | 2022-11-15 | Abas, Mohammed Fekry | 2022-11-16 | 2022-11-17 |  |  |  | 14000000 | 4278 | 0 | STANDARD | Guardtime SA | SAR | 14000000 | APPROVED |  |  | 2022-11-29 | 0 | 12 | Abuhammad, Samir | -44882 | 12
105-44 | Kaust Talent Displays | 628 | Kaust Talent Displays-Payment against displays production | APPROVED | No | 2022-04-28 | Abas, Mohammed Fekry | 2022-05-08 | 2022-05-08 |  |  |  | 34450 | 4107 | 0 | STANDARD | Abdulrahman sultan alharthi factory | SAR | 34450 | APPROVED |  |  | 2022-05-15 | 0 | 7 | Babic, Marian | -44689 | 7
105-47 | CAD King Faisal Prize LED | 607 | CAD King Faisal Prize LED-Payment against LED screen rental 180 SQM | APPROVED | No | 2022-04-20 | Abas, Mohammed Fekry | 2022-04-20 | 2022-04-20 |  |  |  | 100000 | 4105 | 0 | STANDARD | Hilights Group | SAR | 100000 | APPROVED |  |  | 2022-05-11 | 0 | 21 | Abuhammad, Samir | -44671 | 21
105-47 | CAD King Faisal Prize LED | 607 | CAD King Faisal Prize LED-Payment against LED screen rental 180 SQM | APPROVED | No | 2022-04-20 | Abas, Mohammed Fekry | 2022-04-20 | 2022-04-20 |  |  |  | 40000 | 4151 | 0 | STANDARD | Golden Veneer Contracting | SAR | 40000 | APPROVED |  |  | 2022-07-24 | 0 | 95 | Abuhammad, Samir | -44671 | 95
105-50 | BAE Systems Saudi Development | 649 | BAE Systems Saudi Development-Payment Against | APPROVED | No | 2022-05-23 | Abas, Mohammed Fekry | 2022-05-24 | 2022-05-25 |  |  |  | 17495 | 4120 | 0 | STANDARD | CROWN PLAZA HOTEL Jeddah AlSalamah | SAR | 17494.13 | APPROVED |  |  | 2022-08-13 | 0.87 | 80 | Babic, Marian | -44706 | 80
105-50 | BAE Systems Saudi Development | 650 | BAE Systems Saudi Development-Advanced Payment against project production | APPROVED | No | 2022-05-24 | Abas, Mohammed Fekry | 2022-05-24 | 2022-05-24 |  |  |  | 70240 | 4119 | 0 | STANDARD | Smart link Est | SAR | 70240 | APPROVED |  |  | 2022-05-30 | 0 | 6 | Babic, Marian | -44705 | 6
105-50 | BAE Systems Saudi Development | 710 | BAE Systems Saudi Development-Touch Screen content | APPROVED | No | 2022-06-26 | Abas, Mohammed Fekry | 2022-06-26 | 2022-06-26 |  |  |  | 30912.98 | 4154 | 0 | STANDARD | Gluk Media | EUR | 30911.5 | APPROVED |  |  | 2022-06-30 | 1.48 | 4 | Babic, Marian | -44738 | 4
105-51 | Hardware Of The National AI Pl | 661 | Hardware Of The National AI Pl-Supply of FusionServer for SADAIA Project. | APPROVED | No | 2022-05-31 | Abas, Mohammed Fekry | 2022-05-31 | 2022-05-31 |  |  |  | 3807110 | 4127 | 0 | STANDARD | REDINGTON SAUDI ARABIA DISTRIBUTION CO. | SAR | 3807110 | APPROVED |  |  | 2022-06-12 | 0 | 12 | Abuhammad, Samir | -44712 | 12
105-51 | Hardware Of The National AI Pl | 662 | Hardware Of The National AI Pl-Supply of Commscope Materials. | APPROVED | No | 2022-05-31 | Abas, Mohammed Fekry | 2022-05-31 | 2022-05-31 |  |  |  | 183324.7 | 4126 | 0 | STANDARD | ANIXTER SAUDI ARABIA LIMITED. | SAR | 183324.7 | APPROVED |  |  | 2022-06-12 | 0 | 12 | Abuhammad, Samir | -44712 | 12
105-51 | Hardware Of The National AI Pl | 688 | Hardware Of The National AI Pl-Supply of AI Platform | APPROVED | No | 2022-06-08 | Abas, Mohammed Fekry | 2022-06-13 | 2022-06-15 |  |  |  | 11480472.92 | 4147 | 0 | STANDARD | Gulf Application Co | SAR | 11480472.92 | APPROVED |  |  | 2022-06-27 | 0 | 12 | Abuhammad, Samir | -44727 | 12
105-51 | Hardware Of The National AI Pl | 689 | Hardware Of The National AI Pl-Supply Of APC Materials | APPROVED | No | 2022-06-08 | Abas, Mohammed Fekry | 2022-06-12 | 2022-06-12 |  |  |  | 1566710.84 | 4140 | 1 | STANDARD | MEJDAF TRADING COMPANY | SAR | 1081672.32 | APPROVED |  |  | 2022-10-05 | 485038.52 | 115 | Abuhammad, Samir | -44724 | 115
105-51 | Hardware Of The National AI Pl | 689 | Hardware Of The National AI Pl-Supply Of APC Materials | APPROVED | No | 2022-06-08 | Abas, Mohammed Fekry | 2022-06-12 | 2022-06-12 |  |  |  | 1683983.99 | 4140 | 0 | STANDARD | MEJDAF TRADING COMPANY | SAR | 1683984 | APPROVED |  |  | 2022-06-19 | -0.01 | 7 | Abuhammad, Samir | -44724 | 7
105-51 | Hardware Of The National AI Pl | 693 | Hardware Of The National AI Pl-Supply of raised floor | APPROVED | No | 2022-06-13 | Abas, Mohammed Fekry | 2022-06-14 | 2022-06-15 |  |  |  | 21500 | 4146 | 0 | STANDARD | Tracking Systems For Info and Tech | SAR | 21000 | APPROVED |  |  | 2022-06-29 | 500 | 14 | Abuhammad, Samir | -44727 | 14
105-51 | Hardware Of The National AI Pl | 712 | Hardware Of The National AI Pl-UTP&MPO Comoscope | APPROVED | No | 2022-06-29 | Abas, Mohammed Fekry | 2022-06-29 | 2022-06-30 |  |  |  | 100000 | 4126 | 1 | STANDARD | ANIXTER SAUDI ARABIA LIMITED. | SAR | 100000 | APPROVED |  |  | 2022-07-04 | 0 | 4 | Abuhammad, Samir | -44742 | 4
105-51 | Hardware Of The National AI Pl | 713 | Hardware Of The National AI Pl-Power Cords APC | APPROVED | No | 2022-06-29 | Abas, Mohammed Fekry | 2022-06-29 | 2022-06-30 |  |  |  | 24992 | 4160 | 0 | STANDARD | MEJDAF TRADING COMPANY | SAR | 24992 | APPROVED |  |  | 2022-07-03 | 0 | 3 | Abuhammad, Samir | -44742 | 3
105-51 | Hardware Of The National AI Pl | 958 | Hardware Of The National AI Pl-Supply of services installation of power connectivity,cabinet,servers,switches and cables | RETURNED | No | 2022-12-28 | Abuhammad, Samir | 2024-05-15 | 2022-12-29 | 2024-05-15 |  | No need | 193000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44924 | -44924
105-54 | AI Digital Ambassador - NEOM | 925 | AI Digital Ambassador - NEOM-Supply of platfrom with services | APPROVED | No | 2022-11-28 | Abas, Mohammed Fekry | 2022-11-29 | 2022-11-30 |  |  |  | 16841522.45 | 4288 | 0 | STANDARD | Gulf Application Co | SAR | 16841522.45 | APPROVED |  |  | 2022-12-01 | 0 | 1 | Abuhammad, Samir | -44895 | 1
105-57 | BAE Systems Celebration Event | 875 | BAE Systems Celebration Event-Payment Against Project Expenses | APPROVED | No | 2022-10-13 | Abas, Mohammed Fekry | 2022-10-16 | 2022-10-16 |  |  |  | 40000 | 4255 | 0 | STANDARD | Smart link Est | SAR | 40000 | APPROVED |  |  | 2022-10-24 | 0 | 8 | Babic, Marian | -44850 | 8
105-61 | NEOM - O&M of Security Systems | 1014 | NEOM - O&M of Security Systems-ACS Image Resize server | APPROVED | No | 2023-01-23 | Abas, Mohammed Fekry | 2023-01-25 | 2023-01-26 |  |  |  | 56000 | 4334 | 0 | STANDARD | Bayt Al Egada for Trading and Technology | SAR | 56000 | APPROVED |  |  | 2023-02-07 | 0 | 12 | Abuhammad, Samir | -44952 | 12
105-61 | NEOM - O&M of Security Systems | 1021 | NEOM - O&M of Security Systems-Spare parts requested by customer / Huawei Active Equipments | APPROVED | No | 2023-01-24 | Abas, Mohammed Fekry | 2023-01-29 | 2023-01-29 |  |  |  | 33520 | 4332 | 0 | STANDARD | REDINGTON SAUDI ARABIA DISTRIBUTION CO. | SAR | 33491 | APPROVED |  |  | 2023-02-12 | 29 | 14 | Abuhammad, Samir | -44955 | 14
105-61 | NEOM - O&M of Security Systems | 1113 | NEOM - O&M of Security Systems-Spare Parets Based On Customer Request- Arm barrier smart gate For Neom O&M Project | APPROVED | No | 2023-03-07 | Abas, Mohammed Fekry | 2023-03-15 | 2023-03-16 |  |  |  | 10260 | 4387 | 0 | STANDARD | Bayt Al Egada for Trading and Technology | SAR | 10260 | APPROVED |  |  | 2023-03-20 | 0 | 4 | Abuhammad, Samir | -45001 | 4
105-61 | NEOM - O&M of Security Systems | 1132 | NEOM - O&M of Security Systems-High performance work station for Neom O&M project | APPROVED | No | 2023-03-15 | Abas, Mohammed Fekry | 2023-03-27 | 2023-03-28 |  |  |  | 48200 | 4402 | 0 | STANDARD | Fast Computers for Trading Est | SAR | 42750 | APPROVED |  |  | 2023-03-30 | 5450 | 2 | Abuhammad, Samir | -45013 | 2
105-61 | NEOM - O&M of Security Systems | 1154 | NEOM - O&M of Security Systems-Radar SFP & patch cord | APPROVED | No | 2023-04-03 | Abas, Mohammed Fekry | 2023-04-06 | 2023-04-09 |  |  |  | 25275 | 4423 | 0 | STANDARD | Integrated Network Solutions Trading Est. | SAR | 23500 | APPROVED |  |  | 2023-05-03 | 1775 | 24 | Abuhammad, Samir | -45025 | 24
105-61 | NEOM - O&M of Security Systems | 1155 | NEOM - O&M of Security Systems-Terma Radar Support | APPROVED | No | 2023-04-03 | Abas, Mohammed Fekry | 2023-04-06 | 2023-04-09 |  |  |  | 4476 | 4429 | 0 | STANDARD | TERMA A/S | EUR | 4455 | APPROVED |  |  | 2023-05-15 | 21 | 36 | Abuhammad, Samir | -45025 | 36
105-61 | NEOM - O&M of Security Systems | 1166 | NEOM - O&M of Security Systems-Supply Dahua Spare Parts V1 | APPROVED | No | 2023-04-06 | Abas, Mohammed Fekry | 2023-04-13 | 2023-04-13 |  |  |  | 164679 | 4421 | 0 | STANDARD | Bayt Al Egada for Trading and Technology | SAR | 164679 | APPROVED |  |  | 2023-05-04 | 0 | 21 | Abuhammad, Samir | -45029 | 21
105-61 | NEOM - O&M of Security Systems | 1240 | NEOM - O&M of Security Systems-Spare Parts Based on Customer request- Upgrade the Terma Radar | APPROVED | No | 2023-05-09 | Abas, Mohammed Fekry | 2023-05-15 | 2023-05-15 |  |  |  | 51329 | 4472 | 0 | STANDARD | TERMA A/S | EUR | 51251.7 | APPROVED |  |  | 2023-05-25 | 77.3 | 10 | Abuhammad, Samir | -45061 | 10
105-61 | NEOM - O&M of Security Systems | 1258 | NEOM - O&M of Security Systems-Manlift Rental | APPROVED | No | 2023-05-14 | Abas, Mohammed Fekry | 2023-05-16 | 2023-05-17 |  |  |  | 56000 | 4470 | 0 | STANDARD | Expertise Contracting Co. | SAR | 56000 | APPROVED |  |  | 2023-05-25 | 0 | 8 | Abuhammad, Samir | -45063 | 8
105-61 | NEOM - O&M of Security Systems | 1276 | NEOM - O&M of Security Systems-ITSM Profissional services | APPROVED | No | 2023-05-21 | Abas, Mohammed Fekry | 2023-05-23 | 2023-05-24 |  |  |  | 30000 | 4494 | 0 | STANDARD | EJADA Systems Co., Ltd. | SAR | 30000 | APPROVED |  |  | 2023-05-31 | 0 | 7 | Abuhammad, Samir | -45070 | 7
105-61 | NEOM - O&M of Security Systems | 1278 | NEOM - O&M of Security Systems-OTDR for Neom O&M Project | APPROVED | No | 2023-05-22 | Abas, Mohammed Fekry | 2023-05-23 | 2023-05-24 |  |  |  | 11000 | 4493 | 0 | STANDARD | Integrated Network Solutions Trading Est. | SAR | 11000 | APPROVED |  |  | 2023-05-31 | 0 | 7 | Abuhammad, Samir | -45070 | 7
105-61 | NEOM - O&M of Security Systems | 1279 | NEOM - O&M of Security Systems-Windows license for Neom O&M | APPROVED | No | 2023-05-22 | Abas, Mohammed Fekry | 2023-05-23 | 2023-05-24 |  |  |  | 3487 | 4492 | 0 | STANDARD | Golden Technology trading Company. | SAR | 3487 | APPROVED |  |  | 2023-05-31 | 0 | 7 | Abuhammad, Samir | -45070 | 7
105-61 | NEOM - O&M of Security Systems | 1282 | NEOM - O&M of Security Systems-Supply of fiber tools for Neom O&M project | APPROVED | No | 2023-05-24 | Abas, Mohammed Fekry | 2023-05-25 | 2023-05-25 |  |  |  | 22550 | 4491 | 0 | STANDARD | Fiber way Est. for Communications and Information Technology | SAR | 22550 | APPROVED |  |  | 2023-05-31 | 0 | 6 | Abuhammad, Samir | -45071 | 6
105-61 | NEOM - O&M of Security Systems | 1327 | NEOM - O&M of Security Systems-Rental of Manlift | APPROVED | No | 2023-06-20 | Abas, Mohammed Fekry | 2023-06-22 | 2023-06-25 |  |  |  | 204000 | 4546 | 0 | STANDARD | Expertise Contracting Co. | SAR | 204000 | APPROVED |  |  | 2023-07-24 | 0 | 29 | Babic, Marian | -45102 | 29
105-61 | NEOM - O&M of Security Systems | 1464 | NEOM - O&M of Security Systems-Supply of CCTV | APPROVED | No | 2023-09-06 | Abas, Mohammed Fekry | 2023-09-12 | 2023-09-14 |  |  |  | 33609.53 | 4613 | 0 | STANDARD | Advance International Company | SAR | 33609.53 | APPROVED |  |  | 2023-09-25 | 0 | 11 | Abuhammad, Samir | -45183 | 11
105-61 | NEOM - O&M of Security Systems | 1541 | NEOM - O&M of Security Systems-Arm barrier - Main gate for Neom O&M | APPROVED | No | 2023-10-02 | Abas, Mohammed Fekry | 2023-10-04 | 2023-10-06 |  |  |  | 16800 | 4653 | 0 | STANDARD | QUDRA COMMUNICATION AND INFORMATION TECHNOLOGY | SAR | 16800 | APPROVED |  |  | 2023-10-11 | 0 | 5 | Abuhammad, Samir | -45205 | 5
105-61 | NEOM - O&M of Security Systems | 2867 | NEOM - O&M of Security Systems-Supply of Spare Parts | APPROVED | No | 2024-03-20 | Abas, Mohammed Fekry | 2024-03-31 | 2024-03-31 |  |  |  | 99808.28 | 5319 | 0 | STANDARD | REDINGTON SAUDI ARABIA DISTRIBUTION CO. | SAR | 99808.28 | APPROVED |  |  | 2024-04-08 | 0 | 8 | Abuhammad, Samir | -45382 | 8
105-62 | ZATCA - Empty Quarter Port | 1162 | ZATCA - Empty Quarter Port-PR-Video Management System- Projects Equipment-Hardware, video & Services-Equipment installation | APPROVED | No | 2023-04-06 | Abas, Mohammed Fekry | 2023-04-10 | 2023-04-11 |  |  |  | 2500000 | 4413 | 0 | STANDARD | APTEC Saudi Arabia LCC | SAR | 2500000 | APPROVED |  |  | 2023-05-03 | 0 | 22 | Abuhammad, Samir | -45027 | 22
105-62 | ZATCA - Empty Quarter Port | 1163 | ZATCA - Empty Quarter Port-PR-CCTV- Projects Equipment-Security & Services-Equipment installation | APPROVED | No | 2023-04-06 | Abas, Mohammed Fekry | 2023-04-10 | 2023-04-11 |  |  |  | 2864287 | 4414 | 0 | STANDARD | ANIXTER SAUDI ARABIA LIMITED. | SAR | 2864287 | APPROVED |  |  | 2023-05-18 | 0 | 37 | Abuhammad, Samir | -45027 | 37
105-62 | ZATCA - Empty Quarter Port | 1164 | ZATCA - Empty Quarter Port-PR-Biometric Reader-Projects Equipment-Hardware-Services-Equipment installation | APPROVED | No | 2023-04-06 | Abas, Mohammed Fekry | 2023-04-10 | 2023-04-11 |  |  |  | 900506 | 4415 | 0 | STANDARD | SAUDISOFT CO LTD | SAR | 900506 | APPROVED |  |  | 2023-05-18 | 0 | 37 | Abuhammad, Samir | -45027 | 37
105-62 | ZATCA - Empty Quarter Port | 1165 | ZATCA - Empty Quarter Port-PR-Arm Barriers,Road Blockers,Tyre Killers,Speed Humps,Parking Manamgment System,Tickiting System -Services-Equipment installation | APPROVED | No | 2023-04-06 | Abas, Mohammed Fekry | 2023-04-10 | 2023-04-11 |  |  |  | 10434910 | 4416 | 0 | STANDARD | QUDRA COMMUNICATION AND INFORMATION TECHNOLOGY | SAR | 10434910 | APPROVED |  |  | 2023-05-18 | 0 | 37 | Abuhammad, Samir | -45027 | 37
105-62 | ZATCA - Empty Quarter Port | 1167 | ZATCA - Empty Quarter Port- PR For ICT installer and Passive scope | APPROVED | No | 2023-04-06 | Abas, Mohammed Fekry | 2023-04-08 | 2023-04-09 |  |  |  | 3103715.15 | 4407 | 0 | STANDARD | Omed Information Technology for Communicatioms | SAR | 3103715.15 | APPROVED |  |  | 2023-04-13 | 0 | 4 | Abuhammad, Samir | -45025 | 4
105-62 | ZATCA - Empty Quarter Port | 1169 | ZATCA - Empty Quarter Port-PR-Panic Alarm System-Projects Equipment-Hardware-Services-Equipment installation | APPROVED | No | 2023-04-06 | Abas, Mohammed Fekry | 2023-04-10 | 2023-04-11 |  |  |  | 1739067 | 4417 | 0 | STANDARD | ANIXTER SAUDI ARABIA LIMITED. | SAR | 1739067 | APPROVED |  |  | 2023-05-18 | 0 | 37 | Abuhammad, Samir | -45027 | 37
105-62 | ZATCA - Empty Quarter Port | 1170 | ZATCA - Empty Quarter Port-PR-Civil Works-Services-Civil works | APPROVED | No | 2023-04-06 | Abas, Mohammed Fekry | 2023-04-10 | 2023-04-11 |  |  |  | 14278911.52 | 4418 | 0 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 14278911.52 | APPROVED |  |  | 2023-05-18 | 0 | 37 | Abuhammad, Samir | -45027 | 37
105-62 | ZATCA - Empty Quarter Port | 1170 | ZATCA - Empty Quarter Port-PR-Civil Works-Services-Civil works | APPROVED | No | 2023-04-06 | Abas, Mohammed Fekry | 2023-04-10 | 2023-04-11 |  |  |  | 14278911.52 | 4418 | 1 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 2855782.31 | APPROVED |  |  | 2023-12-06 | 11423129.21 | 239 | Abuhammad, Samir | -45027 | 239
105-62 | ZATCA - Empty Quarter Port | 1170 | ZATCA - Empty Quarter Port-PR-Civil Works-Services-Civil works | APPROVED | No | 2023-04-06 | Abas, Mohammed Fekry | 2023-04-10 | 2023-04-11 |  |  |  | 14278911.52 | 4418 | 2 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 2121121 | APPROVED |  |  | 2023-12-10 | 12157790.52 | 243 | Abuhammad, Samir | -45027 | 243
105-62 | ZATCA - Empty Quarter Port | 1171 | ZATCA - Empty Quarter Port-PR-Incinerator & Shredder-Projects Equipment-Equipment & Services-Equipment installation | APPROVED | No | 2023-04-06 | Abas, Mohammed Fekry | 2023-04-10 | 2023-04-11 |  |  |  | 1825000 | 4419 | 0 | STANDARD | Matrix Systems for general contraction | SAR | 1825000 | APPROVED |  |  | 2023-05-17 | 0 | 36 | Abuhammad, Samir | -45027 | 36
105-62 | ZATCA - Empty Quarter Port | 1176 | ZATCA - Empty Quarter Port-Services for Camp-Empty Quarter Location | APPROVED | No | 2023-04-09 | Abas, Mohammed Fekry | 2023-04-10 | 2023-04-11 |  |  |  | 100000 | 4412 | 0 | STANDARD | Hamed Saud AlOtabi for Constriction est. | SAR | 100000 | APPROVED |  |  | 2023-05-10 | 0 | 29 | Abuhammad, Samir | -45027 | 29
105-62 | ZATCA - Empty Quarter Port | 1177 | ZATCA - Empty Quarter Port-PR-Supply and Installation Of Pota Cabin | APPROVED | No | 2023-04-09 | Abas, Mohammed Fekry | 2023-04-10 | 2023-04-11 |  |  |  | 3681759 | 4480 | 0 | STANDARD | ABDUL JABBAR AHMAD ALI SHARAHILI CONTRACTING EST. (AJASCO) | SAR | 3681759 | APPROVED |  |  | 2023-06-04 | 0 | 54 | Kumar, Mr. Ranjan | -45027 | 54
105-62 | ZATCA - Empty Quarter Port | 1178 | ZATCA - Empty Quarter Port-PR-Supply of Currency checking & Counter Device | APPROVED | No | 2023-04-09 | Abas, Mohammed Fekry | 2023-04-10 | 2023-04-11 |  |  |  | 19400 | 4411 | 0 | STANDARD | ABANA ENTERPRISES GROUP CO | SAR | 19400 | APPROVED |  |  | 2023-05-15 | 0 | 34 | Abuhammad, Samir | -45027 | 34
105-62 | ZATCA - Empty Quarter Port | 1179 | ZATCA - Empty Quarter Port-Exhaust Fans Equipment Supply (National Refrigeration House) | APPROVED | No | 2023-04-09 | Abas, Mohammed Fekry | 2023-04-10 | 2023-04-11 |  |  |  | 119581 | 4424 | 0 | STANDARD | SAMA Air Conditioning and Cooling Company | SAR | 119581 | APPROVED |  |  | 2023-06-11 | 0 | 61 | Abuhammad, Samir | -45027 | 61
105-62 | ZATCA - Empty Quarter Port | 1191 | ZATCA - Empty Quarter Port-PR- Isotope Identifier & Personal Dosimeter -Larsa- PO-8191 | APPROVED | No | 2023-04-12 | Abas, Mohammed Fekry | 2023-04-30 | 2023-05-01 |  |  |  | 226537.5 | 4433 | 0 | STANDARD | Larsa Scientific Treading L.L.C | USD | 226537.5 | APPROVED |  |  | 2023-05-17 | 0 | 16 | Abuhammad, Samir | -45047 | 16
105-62 | ZATCA - Empty Quarter Port | 1192 | ZATCA - Empty Quarter Port-PR-VIDEO INSPECT RECORDABLE Laserliner -Arab Engineer -PO#8212 | APPROVED | No | 2023-04-12 | Abas, Mohammed Fekry | 2023-04-30 | 2023-05-01 |  |  |  | 18768 | 4432 | 0 | STANDARD | Arab Engineers for Trading company limited | SAR | 18768 | APPROVED |  |  | 2023-05-15 | 0 | 14 | Abuhammad, Samir | -45047 | 14
105-62 | ZATCA - Empty Quarter Port | 1194 | ZATCA - Empty Quarter Port-PR-Body Security Screening System -PO-8188 | APPROVED | No | 2023-04-17 | Abas, Mohammed Fekry | 2023-04-30 | 2023-05-01 |  |  |  | 1177500 | 4430 | 0 | STANDARD | Linev Systems Equipment Trading LLC | USD | 1177500 | APPROVED |  |  | 2023-05-17 | 0 | 16 | Abuhammad, Samir | -45047 | 16
105-62 | ZATCA - Empty Quarter Port | 1197 | ZATCA - Empty Quarter Port-PR-Xray & Screening Equipments PO-8193 | APPROVED | No | 2023-04-17 | Abas, Mohammed Fekry | 2023-04-30 | 2023-05-01 |  |  |  | 55103164.72 | 4481 | 0 | STANDARD | Rapiscan Systems Limited | USD | 54956614.41 | APPROVED |  |  | 2023-06-04 | 146550.31 | 34 | Abuhammad, Samir | -45047 | 34
105-62 | ZATCA - Empty Quarter Port | 1198 | ZATCA - Empty Quarter Port-PR-Narcotics, Chemical & Explosive Detector -PO-8164 | REJECTED | No | 2023-04-18 | El Bouz, Baher | 2023-05-30 | 2023-05-01 | 2023-05-21 | 2023-05-30 | PR Bidget line doesn't match the manual PO,as per finance record. | 4500000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45047 | -45047
105-62 | ZATCA - Empty Quarter Port | 1202 | ZATCA - Empty Quarter Port-PR-Stabilizer auto stac 3phase regulators | REJECTED | No | 2023-04-19 | El Bouz, Baher | 2023-04-19 |  |  | 2023-04-19 |  | 217500 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-62 | ZATCA - Empty Quarter Port | 1203 | ZATCA - Empty Quarter Port-PR- Stabilizer Auto Stac 3phase Regulators | REJECTED | No | 2023-04-19 | El Bouz, Baher | 2023-05-23 | 2023-05-01 | 2023-05-23 | 2023-05-23 | As per PM request. | 217500 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45047 | -45047
105-62 | ZATCA - Empty Quarter Port | 1206 | ZATCA - Empty Quarter Port-PR-Supply of AEOS System PO-8190 | APPROVED | No | 2023-04-19 | Abas, Mohammed Fekry | 2023-04-30 | 2023-05-01 |  |  |  | 477317.73 | 4438 | 0 | STANDARD | NEDAP.N.V. | EUR | 954635.46 | APPROVED |  |  | 2023-05-17 | -477317.73 | 16 | Abuhammad, Samir | -45047 | 16
105-62 | ZATCA - Empty Quarter Port | 1208 | ZATCA - Empty Quarter Port-PR-Supply of CISCO Parts | APPROVED | No | 2023-04-19 | Abas, Mohammed Fekry | 2023-05-04 | 2023-05-08 |  |  |  | 2027004 | 4442 | 0 | STANDARD | APTEC Saudi Arabia LCC | SAR | 2027004 | APPROVED |  |  | 2023-05-18 | 0 | 10 | Abuhammad, Samir | -45054 | 10
105-62 | ZATCA - Empty Quarter Port | 1219 | ZATCA - Empty Quarter Port-PR-Supply of Parts Coming PO# -8210 | APPROVED | No | 2023-05-01 | Abas, Mohammed Fekry | 2023-05-04 | 2023-05-08 |  |  |  | 1594690 | 4443 | 0 | STANDARD | Hardware Solutions Builders Co Ltd | SAR | 1594690 | APPROVED |  |  | 2023-05-17 | 0 | 9 | Abuhammad, Samir | -45054 | 9
105-62 | ZATCA - Empty Quarter Port | 1233 | ZATCA - Empty Quarter Port-PR- Supply Of Planet Outdoor Industrial -4Port Poe Switches | APPROVED | No | 2023-05-07 | Abas, Mohammed Fekry | 2023-05-11 | 2023-05-14 |  |  |  | 417000 | 4457 | 0 | STANDARD | Bright Wire Company | SAR | 417000 | APPROVED |  |  | 2023-05-29 | 0 | 15 | Abuhammad, Samir | -45060 | 15
105-62 | ZATCA - Empty Quarter Port | 1242 | ZATCA - Empty Quarter Port-PR For Passport Scanner | APPROVED | No | 2023-05-10 | Abas, Mohammed Fekry | 2023-05-16 | 2023-05-16 |  |  |  | 473900 | 4462 | 0 | STANDARD | Alyam Technical Trading Company | SAR | 473900 | APPROVED |  |  | 2023-05-29 | 0 | 13 | Abuhammad, Samir | -45062 | 13
105-62 | ZATCA - Empty Quarter Port | 1243 | ZATCA - Empty Quarter Port-PR- for Diesel supply in EQ -Zatca | APPROVED | No | 2023-05-10 | Abas, Mohammed Fekry | 2023-05-15 | 2023-05-15 |  |  |  | 75000 | 4463 | 0 | STANDARD | Othman Hammoud Al-Zaydi Est | SAR | 75000 | APPROVED |  |  | 2023-05-24 | 0 | 9 | Abuhammad, Samir | -45061 | 9
105-62 | ZATCA - Empty Quarter Port | 1244 | ZATCA - Empty Quarter Port-PR For UVS,ISS SYSTEM PO# 8198 | APPROVED | No | 2023-05-10 | Abas, Mohammed Fekry | 2023-05-16 | 2023-05-16 |  |  |  | 2885068 | 4464 | 0 | STANDARD | APTEC Saudi Arabia LCC | SAR | 2885068 | APPROVED |  |  | 2023-05-29 | 0 | 13 | Abuhammad, Samir | -45062 | 13
105-62 | ZATCA - Empty Quarter Port | 1260 | ZATCA - Empty Quarter Port-PR for Weigh in Motion-Crosszlin- PO#8207 | APPROVED | No | 2023-05-15 | Abas, Mohammed Fekry | 2023-05-21 | 2023-05-22 |  |  |  | 1010320 | 4477 | 0 | STANDARD | Cross Line | EUR | 1010320 | APPROVED |  |  | 2023-06-04 | 0 | 13 | Abuhammad, Samir | -45068 | 13
105-62 | ZATCA - Empty Quarter Port | 1275 | ZATCA - Empty Quarter Port-PR For Genset | APPROVED | No | 2023-05-18 | Abas, Mohammed Fekry | 2023-05-23 | 2023-05-24 |  |  |  | 130000 | 4495 | 0 | STANDARD | ABDUL JABBAR AHMAD ALI SHARAHILI CONTRACTING EST. (AJASCO) | SAR | 130000 | APPROVED |  |  | 2023-06-11 | 0 | 18 | Abuhammad, Samir | -45070 | 18
105-62 | ZATCA - Empty Quarter Port | 1280 | ZATCA - Empty Quarter Port-PR For -External Illuminator -Raytec | APPROVED | No | 2023-05-23 | Abas, Mohammed Fekry | 2023-05-28 | 2023-05-28 |  |  |  | 184450 | 4497 | 0 | STANDARD | ANIXTER SAUDI ARABIA LIMITED. | SAR | 184300 | APPROVED |  |  | 2023-06-04 | 150 | 7 | Abuhammad, Samir | -45074 | 7
105-62 | ZATCA - Empty Quarter Port | 1281 | ZATCA - Empty Quarter Port-PR-Video Wall System | APPROVED | No | 2023-05-23 | Abas, Mohammed Fekry | 2023-05-28 | 2023-05-28 |  |  |  | 2312002.5 | 4500 | 0 | STANDARD | Samir Trading & Marketing | SAR | 2312002.5 | APPROVED |  |  | 2023-06-20 | 0 | 23 | Abuhammad, Samir | -45074 | 23
105-62 | ZATCA - Empty Quarter Port | 1287 | ZATCA - Empty Quarter Port-PR For Voltage Stabilizer | APPROVED | No | 2023-05-25 | Abas, Mohammed Fekry | 2023-05-28 | 2023-05-28 |  |  |  | 266650 | 4496 | 0 | STANDARD | Integrated Network Solutions Trading Est. | SAR | 266650 | APPROVED |  |  | 2023-06-11 | 0 | 14 | Abuhammad, Samir | -45074 | 14
105-62 | ZATCA - Empty Quarter Port | 1295 | ZATCA - Empty Quarter Port-PR for Supply of Handheld 908 Devices-PO#8164 | APPROVED | No | 2023-05-30 | Abas, Mohammed Fekry | 2023-06-14 | 2023-06-14 |  |  |  | 4500000 | 4431 | 0 | STANDARD | Overtech Est. | SAR | 4500000 | APPROVED |  |  | 2023-06-20 | 0 | 6 | Abuhammad, Samir | -45091 | 6
105-62 | ZATCA - Empty Quarter Port | 1300 | ZATCA - Empty Quarter Port-PR for 9U Cabinets-Supply | APPROVED | No | 2023-06-01 | Abas, Mohammed Fekry | 2023-06-13 | 2023-06-14 |  |  |  | 52680 | 4523 | 0 | STANDARD | Asari Operation and Maintenance | SAR | 52680 | APPROVED |  |  | 2023-07-09 | 0 | 25 | Abuhammad, Samir | -45091 | 25
105-62 | ZATCA - Empty Quarter Port | 1303 | ZATCA - Empty Quarter Port-PR for RFID Reader for EQ Project | REJECTED | No | 2023-06-04 | El Bouz, Baher | 2023-06-04 |  |  | 2023-06-04 |  | 1252800 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-62 | ZATCA - Empty Quarter Port | 1323 | ZATCA - Empty Quarter Port-Change Order Request(6F) -Hasoub-Fiber | REJECTED | No | 2023-06-18 | Malek, Warren | 2023-06-21 | 2023-06-21 |  | 2023-06-21 |  | 48231 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45098 | -45098
105-62 | ZATCA - Empty Quarter Port | 1331 | ZATCA - Empty Quarter Port-PR for Change Order for Fiber-PO#4443 | APPROVED | No | 2023-06-21 | Abas, Mohammed Fekry | 2023-07-10 | 2023-07-10 |  |  |  | 58949 | 4443 | 1 | STANDARD | Hardware Solutions Builders Co Ltd | SAR | 58949 | APPROVED |  |  | 2023-07-24 | 0 | 14 | Abuhammad, Samir | -45117 | 14
105-62 | ZATCA - Empty Quarter Port | 1355 | ZATCA - Empty Quarter Port-PR For Furniture Items Supplied by JASCO | APPROVED | No | 2023-07-18 | Abas, Mohammed Fekry | 2023-07-21 | 2023-07-23 |  |  |  | 24975 | 4480 | 1 | STANDARD | ABDUL JABBAR AHMAD ALI SHARAHILI CONTRACTING EST. (AJASCO) | SAR | 24975 | APPROVED |  |  | 2023-08-29 | 0 | 37 | Kumar, Mr. Ranjan | -45130 | 37
105-62 | ZATCA - Empty Quarter Port | 1373 | ZATCA - Empty Quarter Port-PR For Fire System-ZATCA | APPROVED | No | 2023-07-25 | Abas, Mohammed Fekry | 2023-07-27 | 2023-08-01 |  |  |  | 16900 | 4480 | 1 | STANDARD | ABDUL JABBAR AHMAD ALI SHARAHILI CONTRACTING EST. (AJASCO) | SAR | 16900 | APPROVED |  |  | 2023-08-29 | 0 | 28 | Kumar, Mr. Ranjan | -45139 | 28
105-62 | ZATCA - Empty Quarter Port | 1376 | ZATCA - Empty Quarter Port-PR for Furniture in XRAY Operation Room | APPROVED | No | 2023-07-27 | Abas, Mohammed Fekry | 2023-08-01 | 2023-08-01 |  |  |  | 50000 | 4587 | 0 | STANDARD | Riyadh House Branch of Jeraisy Group Company | SAR | 33592 | APPROVED |  |  | 2023-08-30 | 16408 | 29 | Abuhammad, Samir | -45139 | 29
105-62 | ZATCA - Empty Quarter Port | 1382 | ZATCA - Empty Quarter Port-Change Order Request for PO#4412 Camp Services | APPROVED | No | 2023-08-06 | Abas, Mohammed Fekry | 2023-08-07 | 2023-08-08 |  |  |  | 75000 | 4412 | 1 | STANDARD | Hamed Saud AlOtabi for Constriction est. | SAR | 75000 | APPROVED |  |  | 2023-09-06 | 0 | 29 | Abuhammad, Samir | -45146 | 29
105-62 | ZATCA - Empty Quarter Port | 1402 | ZATCA - Empty Quarter Port-Second Change Order For Hardware Solutions-6F Fiber | APPROVED | No | 2023-08-10 | Abas, Mohammed Fekry | 2023-08-14 | 2023-08-16 |  |  |  | 16500 | 4443 | 2 | STANDARD | Hardware Solutions Builders Co Ltd | SAR | 16500 | APPROVED |  |  | 2023-08-29 | 0 | 13 | Abuhammad, Samir | -45154 | 13
105-62 | ZATCA - Empty Quarter Port | 1424 | ZATCA - Empty Quarter Port-PR-Diesel supply in EQ | APPROVED | No | 2023-08-21 | Abas, Mohammed Fekry | 2023-08-24 | 2023-08-24 |  |  |  | 75000 | 4603 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 74800 | APPROVED |  |  | 2023-09-12 | 200 | 19 | Abuhammad, Samir | -45162 | 19
105-62 | ZATCA - Empty Quarter Port | 1443 | ZATCA - Empty Quarter Port-PR Create Door Accesories | APPROVED | No | 2023-08-31 | Abas, Mohammed Fekry | 2023-09-05 | 2023-09-05 |  |  |  | 34875 | 4604 | 0 | STANDARD | Advance International Company | SAR | 34875 | APPROVED |  |  | 2023-09-12 | 0 | 7 | Abuhammad, Samir | -45174 | 7
105-62 | ZATCA - Empty Quarter Port | 1451 | ZATCA - Empty Quarter Port-PR- for CIsco IP Telephone | APPROVED | No | 2023-09-04 | Abas, Mohammed Fekry | 2023-09-10 | 2023-09-10 |  |  |  | 38499.2 | 4611 | 0 | STANDARD | Fast Computers for Trading Est | SAR | 30000 | APPROVED |  |  | 2023-10-03 | 8499.2 | 23 | Abuhammad, Samir | -45179 | 23
105-62 | ZATCA - Empty Quarter Port | 1491 | ZATCA - Empty Quarter Port-PR for Network Switches - Cisco / DELL Desktop | APPROVED | No | 2023-09-12 | Abas, Mohammed Fekry | 2023-09-17 | 2023-09-18 |  |  |  | 178663.85 | 4619 | 0 | STANDARD | Fast Computers for Trading Est | SAR | 178663.85 | APPROVED |  |  | 2023-10-05 | 0 | 17 | Abuhammad, Samir | -45187 | 17
105-62 | ZATCA - Empty Quarter Port | 1560 | ZATCA - Empty Quarter Port-PR for Galvanized Steel Shutter Doors | APPROVED | No | 2023-10-08 | Abas, Mohammed Fekry | 2023-10-11 | 2023-10-11 |  |  |  | 163571 | 4659 | 0 | STANDARD | Rollc Factory for Metal Industries | SAR | 140000 | APPROVED |  |  | 2023-10-31 | 23571 | 20 | Abuhammad, Samir | -45210 | 20
105-62 | ZATCA - Empty Quarter Port | 1587 | ZATCA - Empty Quarter Port-PR-Diesel supply in EQ -ZOIL | APPROVED | No | 2023-10-12 | Abas, Mohammed Fekry | 2023-10-16 | 2023-10-17 |  |  |  | 50000 | 4664 | 0 | STANDARD | Qimet Al Riyadh Fuel Company. | SAR | 50000 | APPROVED |  |  | 2023-10-26 | 0 | 9 | Abuhammad, Samir | -45216 | 9
105-62 | ZATCA - Empty Quarter Port | 1637 | ZATCA - Empty Quarter Port-PR for Empty Quarter Port - PSIM | APPROVED | No | 2023-10-26 | Abas, Mohammed Fekry | 2023-10-30 | 2023-10-31 |  |  |  | 1740060 | 4618 | 0 | STANDARD | EVERBRIDGE EUROPE LIMITED - BRANCH | USD | 1740060 | APPROVED |  |  | 2023-12-14 | 0 | 44 | Abuhammad, Samir | -45230 | 44
105-62 | ZATCA - Empty Quarter Port | 1773 | ZATCA - Empty Quarter Port-PR- For ICT Data Nesma Alertus system V9 | APPROVED | No | 2023-11-16 | Abas, Mohammed Fekry | 2023-11-19 | 2023-11-20 |  |  |  | 1127651.5 | 4745 | 0 | STANDARD | Jadwa Al-Hayat for Telecom and Information Technology Company | SAR | 1022231.45 | APPROVED |  |  | 2023-12-11 | 105420.05 | 21 | Abuhammad, Samir | -45250 | 21
105-62 | ZATCA - Empty Quarter Port | 1801 | ZATCA - Empty Quarter Port-PR -For X-ray systems -Thermoluminescense dosimetry (TLD) | RETURNED | No | 2023-11-21 | Abuhammad, Samir | 2024-03-25 | 2023-11-23 | 2024-03-25 |  | No need this item. | 200000 | 4771 | 0 | STANDARD | Isotopes trading company | SAR | 198000 | APPROVED |  |  | 2023-12-04 | 2000 |  | Abuhammad, Samir | -45253 | 11
105-62 | ZATCA - Empty Quarter Port | 1801 | ZATCA - Empty Quarter Port-PR -For X-ray systems -Thermoluminescense dosimetry (TLD) | RETURNED | No | 2023-11-21 | Abuhammad, Samir | 2024-03-25 | 2023-11-23 | 2024-03-25 |  | No need this item. | 6600 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45253 | -45253
105-62 | ZATCA - Empty Quarter Port | 1862 | ZATCA - Empty Quarter Port-PR-Supply with installation of Generators | APPROVED | No | 2023-11-30 | Abas, Mohammed Fekry | 2023-11-30 | 2023-12-04 |  |  |  | 374484 | 4789 | 0 | STANDARD | Mohamad Samih Ghaddar Factory for Power | SAR | 374484 | APPROVED |  |  | 2023-12-14 | 0 | 10 | Abuhammad, Samir | -45264 | 10
105-62 | ZATCA - Empty Quarter Port | 1921 | ZATCA - Empty Quarter Port-PR- For Jadwa Civil work Manual PO-8236 | APPROVED | No | 2023-12-10 | Abas, Mohammed Fekry | 2023-12-12 | 2023-12-12 |  |  |  | 20299942.84 | 4831 | 0 | STANDARD | Jadwa Al-Hayat for Telecom and Information Technology Company | SAR | 20299942.84 | APPROVED |  |  | 2023-12-20 | 0 | 8 | Abuhammad, Samir | -45272 | 8
105-62 | ZATCA - Empty Quarter Port | 1981 | ZATCA - Empty Quarter Port-PR For - Anti Radiation Doors PO-8302 | APPROVED | No | 2023-12-17 | Abas, Mohammed Fekry | 2023-12-17 | 2023-12-18 |  |  |  | 1310000 | 4885 | 0 | STANDARD | Rollc Factory for Metal Industries | SAR | 1310000 | APPROVED |  |  | 2023-12-24 | 0 | 6 | Abuhammad, Samir | -45278 | 6
105-62 | ZATCA - Empty Quarter Port | 2017 | ZATCA - Empty Quarter Port-PR for Site Camp-Services- Hamed Saud Al-Otaiby -Change Order-4412 | APPROVED | No | 2023-12-20 | Abas, Mohammed Fekry | 2023-12-20 | 2023-12-21 |  |  |  | 75000 | 4412 | 2 | STANDARD | Hamed Saud AlOtabi for Constriction est. | SAR | 75000 | APPROVED |  |  | 2024-01-18 | 0 | 28 | Abuhammad, Samir | -45281 | 28
105-62 | ZATCA - Empty Quarter Port | 2055 | ZATCA - Empty Quarter Port-PR for Civil work -Change Order -PO -8236 | APPROVED | No | 2023-12-28 | Abas, Mohammed Fekry | 2024-01-01 | 2024-01-01 |  |  |  | 1288243.16 | 4831 | 1 | STANDARD | Jadwa Al-Hayat for Telecom and Information Technology Company | SAR | 2073874 | APPROVED |  |  | 2024-01-29 | -785630.84 | 28 | Abuhammad, Samir | -45292 | 28
105-62 | ZATCA - Empty Quarter Port | 2100 | ZATCA - Empty Quarter Port-PR for Diesel supply in EQ PO-4603 Change Order | APPROVED | No | 2024-01-08 | Abas, Mohammed Fekry | 2024-01-08 | 2024-01-09 |  |  |  | 100000 | 4603 | 1 | STANDARD | Talaea Alahlam Trading Company | SAR | 99999.8 | APPROVED |  |  | 2024-01-25 | 0.2 | 16 | Abuhammad, Samir | -45300 | 16
105-62 | ZATCA - Empty Quarter Port | 2101 | ZATCA - Empty Quarter Port-PR for Diesel supply in EQ PO-4664 | APPROVED | No | 2024-01-08 | Abas, Mohammed Fekry | 2024-01-08 | 2024-01-09 |  |  |  | 50000 | 4664 | 1 | STANDARD | Qimet Al Riyadh Fuel Company. | SAR | 49999.9 | APPROVED |  |  | 2024-01-21 | 0.1 | 12 | Abuhammad, Samir | -45300 | 12
105-62 | ZATCA - Empty Quarter Port | 2157 | ZATCA - Empty Quarter Port-PR for APTEC Saudi Arabia LLC-Dell -Manual PO#8194 | APPROVED | No | 2024-01-11 | Abas, Mohammed Fekry | 2024-01-14 | 2024-01-14 |  |  |  | 5623891 | 4994 | 0 | STANDARD | APTEC Saudi Arabia LCC | SAR | 5623891 | APPROVED |  |  | 2024-01-24 | 0 | 10 | Abuhammad, Samir | -45305 | 10
105-62 | ZATCA - Empty Quarter Port | 2224 | ZATCA - Empty Quarter Port-PR-Supply with installation of Generators -Change Order-PO#4789 | APPROVED | No | 2024-01-21 | Abas, Mohammed Fekry | 2024-01-22 | 2024-01-22 |  |  |  | 8400 | 4789 | 1 | STANDARD | Mohamad Samih Ghaddar Factory for Power | SAR | 8400 | APPROVED |  |  | 2024-01-31 | 0 | 9 | Abuhammad, Samir | -45313 | 9
105-62 | ZATCA - Empty Quarter Port | 2321 | ZATCA - Empty Quarter Port-PR-Operation Request for Rub al khali site | APPROVED | No | 2024-01-28 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 39679 | 5045 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 39679 | APPROVED |  |  | 2024-02-15 | 0 | 11 | Abuhammad, Samir | -45326 | 11
105-62 | ZATCA - Empty Quarter Port | 2651 | ZATCA - Empty Quarter Port- PR For Camp Water Service CO-4412 | APPROVED | No | 2024-02-21 | Abas, Mohammed Fekry | 2024-02-25 | 2024-02-26 |  |  |  | 75000 | 5160 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 75000 | APPROVED |  |  | 2024-03-24 | 0 | 27 | Abuhammad, Samir | -45348 | 27
105-62 | ZATCA - Empty Quarter Port | 2703 | ZATCA - Empty Quarter Port-PR for JOC connection and indoor and outdoor media converter | APPROVED | No | 2024-02-27 | Abas, Mohammed Fekry | 2024-02-28 | 2024-02-28 |  |  |  | 58800 | 4443 | 3 | STANDARD | Hardware Solutions Builders Co Ltd | SAR | 52800 | APPROVED |  |  | 2024-05-20 | 6000 | 82 | Abuhammad, Samir | -45350 | 82
105-62 | ZATCA - Empty Quarter Port | 2802 | ZATCA - Empty Quarter Port-PR For -Electrical Cable | APPROVED | No | 2024-03-07 | Abas, Mohammed Fekry | 2024-03-07 | 2024-03-10 |  |  |  | 454827.4 | 5132 | 0 | STANDARD | AL MOUSA SPECIALIZED CABLES | SAR | 454827.4 | APPROVED |  |  | 2024-03-17 | 0 | 7 | Abuhammad, Samir | -45361 | 7
105-62 | ZATCA - Empty Quarter Port | 2936 | ZATCA - Empty Quarter Port-PR- Diesel supply in EQ -Talaea Alahlam Trading Company | APPROVED | No | 2024-03-28 | Abas, Mohammed Fekry | 2024-04-01 | 2024-04-02 |  |  |  | 75000 | 5344 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 75000 | APPROVED |  |  | 2024-04-18 | 0 | 16 | Abuhammad, Samir | -45384 | 16
105-62 | ZATCA - Empty Quarter Port | 2980 | ZATCA - Empty Quarter Port-PR For ICT Works, CIVIL WORK -OMED Change Order-4407 | APPROVED | No | 2024-04-03 | Abas, Mohammed Fekry | 2024-04-07 | 2024-04-07 |  |  |  | 499063.4 | 4407 | 1 | STANDARD | Omed Information Technology for Communicatioms | SAR | 499063.4 | APPROVED |  |  | 2024-05-22 | 0 | 45 | Abuhammad, Samir | -45389 | 45
105-62 | ZATCA - Empty Quarter Port | 2980 | ZATCA - Empty Quarter Port-PR For ICT Works, CIVIL WORK -OMED Change Order-4407 | APPROVED | No | 2024-04-03 | Abas, Mohammed Fekry | 2024-04-07 | 2024-04-07 |  |  |  | 499063.4 | 4407 | 2 | STANDARD | Omed Information Technology for Communicatioms | SAR | 420632.26 | APPROVED |  |  | 2024-11-14 | 78431.14 | 221 | Abuhammad, Samir | -45389 | 221
105-62 | ZATCA - Empty Quarter Port | 3579 | ZATCA - Empty Quarter Port-New PR Request for Talaea Alahalam Company-Diesel Service | APPROVED | No | 2024-06-03 | Abas, Mohammed Fekry | 2024-06-04 | 2024-06-04 |  |  |  | 200000 | 5690 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 200000 | APPROVED |  |  | 2024-06-13 | 0 | 9 | Abuhammad, Samir | -45447 | 9
105-62 | ZATCA - Empty Quarter Port | 3580 | ZATCA - Empty Quarter Port-New PR Request for Al Hamda -Water Service ZATCA CAMP | APPROVED | No | 2024-06-03 | Abas, Mohammed Fekry | 2024-06-04 | 2024-06-04 |  |  |  | 200000 | 5689 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 200000 | APPROVED |  |  | 2024-07-25 | 0 | 51 | Abuhammad, Samir | -45447 | 51
105-62 | ZATCA - Empty Quarter Port | 3759 | ZATCA - Empty Quarter Port-PR For Talaea Ahlam Company-Diesel Supplier-New PO Request | APPROVED | No | 2024-07-03 | Abas, Mohammed Fekry | 2024-07-03 | 2024-07-03 |  |  |  | 200000 | 5775 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 200000 | APPROVED |  |  | 2024-07-25 | 0 | 22 | Abuhammad, Samir | -45476 | 22
105-62 | ZATCA - Empty Quarter Port | 4201 | ZATCA - Empty Quarter Port-PR For PPE Kits-ZATCA | REJECTED | No | 2024-08-19 | Sherif, Marwa | 2024-09-02 | 2024-08-25 |  | 2024-09-02 |  | 51340 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45529 | -45529
105-62 | ZATCA - Empty Quarter Port | 4330 | ZATCA - Empty Quarter Port-PR For PPE Kits-ZATCA Project | APPROVED | No | 2024-09-01 | Abas, Mohammed Fekry | 2024-09-05 | 2024-09-05 |  |  |  | 46200 | 5934 | 0 | STANDARD | Branch Bots Inc | SAR | 46200 | APPROVED |  |  | 2024-09-16 | 0 | 11 | Abuhammad, Samir | -45540 | 11
105-62 | ZATCA - Empty Quarter Port | 4424 | ZATCA - Empty Quarter Port-PR For Diesel Genrators-ZATCA EQ Project | APPROVED | No | 2024-09-12 | Abas, Mohammed Fekry | 2024-09-16 | 2024-09-17 |  |  |  | 187000 | 6225 | 0 | STANDARD | Saudi Technic Energy Co. | SAR | 181500 | APPROVED |  |  | 2024-10-09 | 5500 | 22 | Abuhammad, Samir | -45552 | 22
105-62 | ZATCA - Empty Quarter Port | 4727 | ZATCA - Empty Quarter Port-PR For Water service EQ - O&M Period | APPROVED | No | 2024-10-20 | Abas, Mohammed Fekry | 2024-10-23 | 2024-10-27 |  |  |  | 200000 | 6390 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 200000 | APPROVED |  |  | 2024-10-31 | 0 | 4 | Abuhammad, Samir | -45592 | 4
105-62 | ZATCA - Empty Quarter Port | 4728 | ZATCA - Empty Quarter Port-PR For Diesel supply in EQ - O&M Period | APPROVED | No | 2024-10-20 | Abas, Mohammed Fekry | 2024-10-23 | 2024-10-27 |  |  |  | 200000 | 6389 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 200000 | APPROVED |  |  | 2024-11-04 | 0 | 8 | Abuhammad, Samir | -45592 | 8
105-62 | ZATCA - Empty Quarter Port | 4874 | ZATCA - Empty Quarter Port-PR For Rapiscan-Third Party Services-Quotation In USD , PR Price Converted to SAR | APPROVED | No | 2024-11-10 | Abas, Mohammed Fekry | 2024-11-12 | 2024-11-12 |  |  |  | 85342.69 | 6487 | 0 | STANDARD | Rapiscan Systems Limited | USD | 85342.69 | APPROVED |  |  | 2024-12-04 | 0 | 22 | Abuhammad, Samir | -45608 | 22
105-62 | ZATCA - Empty Quarter Port | 5183 | ZATCA - Empty Quarter Port-PR For Jadwa Chage Order-Civil Works | APPROVED | No | 2024-12-08 | Abas, Mohammed Fekry | 2024-12-11 | 2024-12-12 |  |  |  | 433281 | 4831 | 2 | STANDARD | Jadwa Al-Hayat for Telecom and Information Technology Company | SAR | 433281 | APPROVED |  |  | 2025-01-15 | 0 | 34 | Abuhammad, Samir | -45638 | 34
105-62 | ZATCA - Empty Quarter Port | 5499 | ZATCA - Empty Quarter Port-PR For OTDR Machine-Supplier Brightwires | APPROVED | No | 2025-01-21 | Abas, Mohammed Fekry | 2025-01-22 | 2025-01-23 |  |  |  | 12900 | 6838 | 0 | STANDARD | Bright Wire Company | SAR | 12900 | APPROVED |  |  | 2025-02-10 | 0 | 18 | Abuhammad, Samir | -45680 | 18
105-62 | ZATCA - Empty Quarter Port | 5500 | ZATCA - Empty Quarter Port-PR For Splicer Machine-Supplier Mejdaf | APPROVED | No | 2025-01-21 | Abas, Mohammed Fekry | 2025-01-22 | 2025-01-23 |  |  |  | 11880 | 6837 | 0 | STANDARD | MEJDAF TRADING COMPANY | SAR | 11880 | APPROVED |  |  | 2025-02-06 | 0 | 14 | Abuhammad, Samir | -45680 | 14
105-62 | ZATCA - Empty Quarter Port | 5949 | ZATCA - Empty Quarter Port-PR For Diesel Supply-Tahlea Ahlam | APPROVED | No | 2025-02-18 | Abas, Mohammed Fekry | 2025-02-25 | 2025-02-25 |  |  | Diesel-Supply-ZATCA EQ -Budget Task#1.3.3 | 200000 | 6389 | 1 | STANDARD | Talaea Alahlam Trading Company | SAR | 200000 | APPROVED |  |  | 2025-03-05 | 0 | 8 | Abuhammad, Samir | -45713 | 8
105-62 | ZATCA - Empty Quarter Port | 6549 | ZATCA - Empty Quarter Port-PR For PSIM Devices Licences | APPROVED | No | 2025-05-07 | Abas, Mohammed Fekry | 2025-05-08 | 2025-05-08 |  |  | PSIM Devices Licences-Budget Item -1.2.14 | 35437.5 | 7252 | 0 | STANDARD | EVERBRIDGE EUROPE LIMITED - BRANCH | USD | 35437.5 | APPROVED |  |  | 2025-05-28 | 0 | 20 | Abuhammad, Samir | -45785 | 20
105-62 | ZATCA - Empty Quarter Port | 6726 | ZATCA - Empty Quarter Port-PR For iDRAC9 Enterprise,Perpetual,Digital License-ZATCA | APPROVED | No | 2025-05-27 | Abas, Mohammed Fekry | 2025-05-27 | 2025-05-27 |  |  | PR For Digital Licence-Task #1.2.14 | 9000 | 7377 | 0 | STANDARD | APTEC Saudi Arabia LCC | SAR | 9000 | APPROVED |  |  | 2025-06-15 | 0 | 19 | Abuhammad, Samir | -45804 | 19
105-62 | ZATCA - Empty Quarter Port | 7992 | Diesel Supply EQ Area-Change Order | APPROVED | No | 2025-10-19 | Abas, Mohammed Fekry | 2025-10-21 | 2025-10-21 |  |  | Deisel Supply-EQ Area- Task 1.3.3 | 0 | 6389 | 2 | STANDARD | Talaea Alahlam Trading Company | SAR | 200000 | APPROVED |  |  | 2025-11-02 | -200000 | 12 | Abuhammad, Samir | -45951 | 12
105-62 | ZATCA - Empty Quarter Port | 7993 | Supply of Water & Sewage-EQ Area- Task 1.3.3 | APPROVED | No | 2025-10-19 | Abas, Mohammed Fekry | 2025-10-21 | 2025-10-21 |  |  | Supply of Water & Sewage-EQ Area- Task 1.3.3 | 0 | 6390 | 1 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 200000 | APPROVED |  |  | 2025-11-02 | -200000 | 12 | Abuhammad, Samir | -45951 | 12
105-62 | ZATCA - Empty Quarter Port | 8471 | PR For Extension of Service and Maintenance for 1 P60 (S/N: P60-274), 1 CarView (S/N: CRVW-1038 and 1 | APPROVED | No | 2025-12-07 | Abas, Mohammed Fekry | 2025-12-17 | 2025-12-18 |  |  | Extension of Service and Maintenance- Budget Task#1.2.14 | 0 | 8001 | 0 | STANDARD | Rabiscan System Limited | USD | 173677.5 | IN PROCESS | 2025-12-30 | 2026-01-13 |  | -173677.5 | 45 | Abuhammad, Samir | 26 | -46009
105-62 | ZATCA - Empty Quarter Port | 8471 | PR For Extension of Service and Maintenance for 1 P60 (S/N: P60-274), 1 CarView (S/N: CRVW-1038 and 1 | APPROVED | No | 2025-12-07 | Abas, Mohammed Fekry | 2025-12-17 | 2025-12-18 |  |  | Extension of Service and Maintenance- Budget Task#1.2.14 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46009 | -46009
105-63 | Fiber Optic work Highway 55 | 1354 | Fiber Optic work Highway 55-PR for issuance of PO to M/S HAYAT AL QASIM-for HW55 project of NESMA PARTNER | APPROVED | No | 2023-07-17 | Abas, Mohammed Fekry | 2023-07-19 | 2023-07-23 |  |  |  | 1191473.5 | 4564 | 0 | STANDARD | Hayat Alqassim Est | SAR | 1191473.5 | APPROVED |  |  | 2023-09-06 | 0 | 45 | Abuhammad, Samir | -45130 | 45
105-64 | JAFURAH 380/230kV BSP (SEC) | 965 | JAFURAH 380/230kV BSP (SEC)-Telecom (Teleprotection & Telecommunication) System | APPROVED | No | 2023-01-01 | Abas, Mohammed Fekry | 2023-01-02 | 2023-01-02 |  |  |  | 10700000 | 4310 | 0 | STANDARD | Networks & System Integration S.A Co. Ltd | SAR | 10700000 | APPROVED |  |  | 2023-01-16 | 0 | 14 | Kumar, Mr. Ranjan | -44928 | 14
105-64 | JAFURAH 380/230kV BSP (SEC) | 966 | JAFURAH 380/230kV BSP (SEC)-HCIS Security system Consultancy & design | APPROVED | No | 2023-01-01 | Abas, Mohammed Fekry | 2023-01-02 | 2023-01-02 |  |  |  | 110000 | 4320 | 0 | STANDARD | Khaled Drewesh Office for Consulting Security (KDOCS) | SAR | 75000 | APPROVED |  |  | 2023-01-18 | 35000 | 16 | Kumar, Mr. Ranjan | -44928 | 16
105-64 | JAFURAH 380/230kV BSP (SEC) | 968 | JAFURAH 380/230kV BSP (SEC)-Engineering Services | APPROVED | No | 2023-01-02 | Abas, Mohammed Fekry | 2023-01-02 | 2023-01-02 |  |  |  | 1775000 | 4471 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 1775000 | APPROVED |  |  | 2023-05-28 | 0 | 146 | Kumar, Mr. Ranjan | -44928 | 146
105-64 | JAFURAH 380/230kV BSP (SEC) | 969 | JAFURAH 380/230kV BSP (SEC)-Soil Investigation | APPROVED | No | 2023-01-02 | Abas, Mohammed Fekry | 2023-01-02 | 2023-01-02 |  |  |  | 135355.5 | 4401 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 135355.5 | APPROVED |  |  | 2023-04-03 | 0 | 91 | Kumar, Mr. Ranjan | -44928 | 91
105-64 | JAFURAH 380/230kV BSP (SEC) | 970 | JAFURAH 380/230kV BSP (SEC)-Fence Supply & Installation | APPROVED | No | 2023-01-02 | Abas, Mohammed Fekry | 2023-01-02 | 2023-01-02 |  |  |  | 353400 | 4475 | 0 | STANDARD | ABDUL JABBAR AHMAD ALI SHARAHILI CONTRACTING EST. (AJASCO) | SAR | 353400 | APPROVED |  |  | 2023-05-28 | 0 | 146 | Kumar, Mr. Ranjan | -44928 | 146
105-64 | JAFURAH 380/230kV BSP (SEC) | 971 | JAFURAH 380/230kV BSP (SEC)-ESIA Study | APPROVED | No | 2023-01-02 | Abas, Mohammed Fekry | 2023-01-02 | 2023-01-02 |  |  |  | 46500 | 4317 | 0 | STANDARD | AL-MASADER AL-DUALIYAH FOR ENVIRONMENT & QUALITY SYSTEMS CO | SAR | 46500 | APPROVED |  |  | 2023-01-15 | 0 | 13 | Babic, Marian | -44928 | 13
105-64 | JAFURAH 380/230kV BSP (SEC) | 972 | JAFURAH 380/230kV BSP (SEC)-Civil Engineering Consultancy Services | APPROVED | No | 2023-01-02 | Abas, Mohammed Fekry | 2023-01-02 | 2023-01-02 |  |  |  | 81000 | 4307 | 0 | STANDARD | Holy Rock Consultant Engineers | SAR | 81000 | APPROVED |  |  | 2023-04-11 | 0 | 99 | Kumar, Mr. Ranjan | -44928 | 99
105-64 | JAFURAH 380/230kV BSP (SEC) | 973 | JAFURAH 380/230kV BSP (SEC)-Excavation works in 380kV,230kV, Control room buildings, Pumphouse & Cable tunnels | APPROVED | No | 2023-01-02 | Abas, Mohammed Fekry | 2023-01-02 | 2023-01-02 |  |  |  | 52080 | 4308 | 0 | STANDARD | RADI AHMED AL MANHAL CO. LTD | SAR | 52080 | APPROVED |  |  | 2023-01-09 | 0 | 7 | Kumar, Mr. Ranjan | -44928 | 7
105-64 | JAFURAH 380/230kV BSP (SEC) | 974 | JAFURAH 380/230kV BSP (SEC)-Station Service Transf_2000 Kva 13.8kV-400/230V. | APPROVED | No | 2023-01-02 | Abas, Mohammed Fekry | 2023-01-02 | 2023-01-02 |  |  |  | 420200 | 4324 | 0 | STANDARD | UNITED TRANSFORMERS ELECTRIC COMPANY (UTEC) | SAR | 298000 | APPROVED |  |  | 2023-02-08 | 122200 | 37 | Kumar, Mr. Ranjan | -44928 | 37
105-64 | JAFURAH 380/230kV BSP (SEC) | 980 | JAFURAH 380/230kV BSP (SEC)-Partial discharge monitoring System (PDMS) | APPROVED | No | 2023-01-03 | Abas, Mohammed Fekry | 2023-01-03 | 2023-01-04 |  |  |  | 1504000 | 4315 | 0 | STANDARD | APM Technologies, Inc. | USD | 1481250 | APPROVED |  |  | 2023-01-16 | 22750 | 12 | Kumar, Mr. Ranjan | -44930 | 12
105-64 | JAFURAH 380/230kV BSP (SEC) | 987 | JAFURAH 380/230kV BSP (SEC)-Mobile antenna, Fast Speed Internet Connection -50MBPS, 100MBPS | APPROVED | No | 2023-01-04 | Abas, Mohammed Fekry | 2023-01-05 | 2023-01-09 |  |  |  | 940000 | 4313 | 0 | STANDARD | INTERNATIONAL SUPPLY INFORMATION TECHNOLOGY | SAR | 676989 | APPROVED |  |  | 2023-01-26 | 263011 | 17 | Kumar, Mr. Ranjan | -44935 | 17
105-64 | JAFURAH 380/230kV BSP (SEC) | 988 | JAFURAH 380/230kV BSP (SEC)-Site Mobilization for 380kV Jafurah BSP SS. | APPROVED | No | 2023-01-04 | Abas, Mohammed Fekry | 2023-01-05 | 2023-01-09 |  |  |  | 1734350 | 4314 | 0 | STANDARD | ABDUL JABBAR AHMAD ALI SHARAHILI CONTRACTING EST. (AJASCO) | SAR | 1665713.84 | APPROVED |  |  | 2023-01-16 | 68636.16 | 7 | Kumar, Mr. Ranjan | -44935 | 7
105-64 | JAFURAH 380/230kV BSP (SEC) | 989 | JAFURAH 380/230kV BSP (SEC)-Supply of Furniture (Table & Chairs) | APPROVED | No | 2023-01-04 | Abas, Mohammed Fekry | 2023-01-05 | 2023-01-09 |  |  |  | 14880 | 4312 | 0 | STANDARD | Kassim M.A. Al Driweesh Sons co. Ltd | SAR | 14880 | APPROVED |  |  | 2023-01-15 | 0 | 6 | Babic, Marian | -44935 | 6
105-64 | JAFURAH 380/230kV BSP (SEC) | 990 | JAFURAH 380/230kV BSP (SEC)-13.8kV Switchgear | APPROVED | No | 2023-01-04 | Abas, Mohammed Fekry | 2023-01-05 | 2023-01-09 |  |  |  | 700000 | 4504 | 0 | STANDARD | ALFANAR CO | SAR | 700000 | APPROVED |  |  | 2023-06-07 | 0 | 149 | Kumar, Mr. Ranjan | -44935 | 149
105-64 | JAFURAH 380/230kV BSP (SEC) | 991 | JAFURAH 380/230kV BSP (SEC)-Levelling & Backfilling for temporary acess | APPROVED | No | 2023-01-04 | Abas, Mohammed Fekry | 2023-01-05 | 2023-01-09 |  |  |  | 88200 | 4505 | 0 | STANDARD | RADI AHMED AL MANHAL CO. LTD | SAR | 88200 | APPROVED |  |  | 2023-06-05 | 0 | 147 | Kumar, Mr. Ranjan | -44935 | 147
105-64 | JAFURAH 380/230kV BSP (SEC) | 997 | JAFURAH 380/230kV BSP (SEC)-Overhead Traveling Crane- 5T | APPROVED | No | 2023-01-11 | Abas, Mohammed Fekry | 2023-01-16 | 2023-01-17 |  |  |  | 550000 | 4346 | 0 | STANDARD | SAUDI CRANES & STEEL WORKS FACTORY LTD | SAR | 369000 | APPROVED |  |  | 2023-02-19 | 181000 | 33 | Kumar, Mr. Ranjan | -44943 | 33
105-64 | JAFURAH 380/230kV BSP (SEC) | 1009 | JAFURAH 380/230kV BSP (SEC)-Power Transformer- 752MVA | APPROVED | No | 2023-01-22 | Abas, Mohammed Fekry | 2023-01-24 | 2023-01-25 |  |  |  | 53332762.5 | 4502 | 0 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 53332762.5 | APPROVED |  |  | 2023-06-07 | 0 | 133 | Kumar, Mr. Ranjan | -44951 | 133
105-64 | JAFURAH 380/230kV BSP (SEC) | 1010 | JAFURAH 380/230kV BSP (SEC)-13.8kV Zig-zag Grounding Transformer | APPROVED | No | 2023-01-22 | Abas, Mohammed Fekry | 2023-01-24 | 2023-01-25 |  |  |  | 2354737.5 | 4502 | 0 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 2354737.5 | APPROVED |  |  | 2023-06-07 | 0 | 133 | Kumar, Mr. Ranjan | -44951 | 133
105-64 | JAFURAH 380/230kV BSP (SEC) | 1011 | JAFURAH 380/230kV BSP (SEC)-380kV GIS and 230kV GIS | APPROVED | No | 2023-01-22 | Abas, Mohammed Fekry | 2023-01-24 | 2023-01-25 |  |  |  | 74988000 | 4400 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 74988000 | APPROVED |  |  | 2023-04-03 | 0 | 68 | Kumar, Mr. Ranjan | -44951 | 68
105-64 | JAFURAH 380/230kV BSP (SEC) | 1012 | JAFURAH 380/230kV BSP (SEC)-380 kV Free Standing CT's + Marshalling boxes | APPROVED | No | 2023-01-23 | Abas, Mohammed Fekry | 2023-01-24 | 2023-01-24 |  |  |  | 1282890 | 4330 | 0 | STANDARD | KONCAR INSTRUMENT TRANSFORMERS | EUR | 1282890 | APPROVED |  |  | 2023-01-29 | 0 | 5 | Kumar, Mr. Ranjan | -44950 | 5
105-64 | JAFURAH 380/230kV BSP (SEC) | 1023 | JAFURAH 380/230kV BSP (SEC)-Protection Signalling Equipment (PSE) | APPROVED | No | 2023-01-26 | Abas, Mohammed Fekry | 2023-01-31 | 2023-02-01 |  |  |  | 1650000 | 4321 | 2 | STANDARD | Hitachi Energy Ltd | SAR | 1650000 | APPROVED |  |  | 2023-12-04 | 0 | 306 | Kumar, Mr. Ranjan | -44958 | 306
105-64 | JAFURAH 380/230kV BSP (SEC) | 1026 | JAFURAH 380/230kV BSP (SEC)-Protection, Control, Metering, AMI and SAS Panels | APPROVED | No | 2023-01-29 | Abas, Mohammed Fekry | 2023-01-31 | 2023-02-01 |  |  |  | 15000000 | 4503 | 0 | STANDARD | ALFANAR CO | SAR | 15000000 | APPROVED |  |  | 2023-06-07 | 0 | 126 | Kumar, Mr. Ranjan | -44958 | 126
105-64 | JAFURAH 380/230kV BSP (SEC) | 1031 | JAFURAH 380/230kV BSP (SEC)-HVAC System | APPROVED | No | 2023-01-30 | Abas, Mohammed Fekry | 2023-02-02 | 2023-02-02 |  |  |  | 5900000 | 4578 | 0 | STANDARD | Hamad Fahad Al Awad for Contracting Est | SAR | 5900000 | APPROVED |  |  | 2023-08-28 | 0 | 207 | Kumar, Mr. Ranjan | -44959 | 207
105-64 | JAFURAH 380/230kV BSP (SEC) | 1033 | JAFURAH 380/230kV BSP (SEC)-Fire Protection System | APPROVED | No | 2023-01-30 | Abas, Mohammed Fekry | 2023-02-02 | 2023-02-02 |  |  |  | 8960736 | 4533 | 0 | STANDARD | Al Majal Group Four S for Security & Safety | SAR | 7625000 | APPROVED |  |  | 2023-07-12 | 1335736 | 160 | Kumar, Mr. Ranjan | -44959 | 160
105-64 | JAFURAH 380/230kV BSP (SEC) | 1034 | JAFURAH 380/230kV BSP (SEC)-230kV Power Cable | APPROVED | No | 2023-02-01 | Abas, Mohammed Fekry | 2023-02-02 | 2023-02-02 |  |  |  | 4172388.29 | 4406 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 4159022.4 | APPROVED |  |  | 2023-04-13 | 13365.89 | 70 | Babic, Marian | -44959 | 70
105-64 | JAFURAH 380/230kV BSP (SEC) | 1034 | JAFURAH 380/230kV BSP (SEC)-230kV Power Cable | APPROVED | No | 2023-02-01 | Abas, Mohammed Fekry | 2023-02-02 | 2023-02-02 |  |  |  | 4172388.29 | 4406 | 1 | STANDARD | Riyadh Cables Group Company | SAR | 3980935.35 | APPROVED |  |  | 2023-08-28 | 191452.94 | 207 | Babic, Marian | -44959 | 207
105-64 | JAFURAH 380/230kV BSP (SEC) | 1035 | JAFURAH 380/230kV BSP (SEC)-Design, supply & erection of precast work for 380kV GIS bldg, Control bldg, 230kV GIS bldg, Pump room and Security bldg. | APPROVED | No | 2023-02-01 | Abas, Mohammed Fekry | 2023-02-02 | 2023-02-02 |  |  |  | 8681896 | 4439 | 0 | STANDARD | Prainsa Saudi for precast Concrete | SAR | 7429870.91 | APPROVED |  |  | 2023-05-29 | 1252025.09 | 116 | Kumar, Mr. Ranjan | -44959 | 116
105-64 | JAFURAH 380/230kV BSP (SEC) | 1036 | JAFURAH 380/230kV BSP (SEC)-230 kV Free Standing CT's + Marshalling boxes | APPROVED | No | 2023-02-01 | Abas, Mohammed Fekry | 2023-02-04 | 2023-02-05 |  |  |  | 535050 | 4333 | 0 | STANDARD | ELECTROTECNICA ARTECHE HERMANOS S.L. | EUR | 535050 | APPROVED |  |  | 2023-02-16 | 0 | 11 | Kumar, Mr. Ranjan | -44962 | 11
105-64 | JAFURAH 380/230kV BSP (SEC) | 1039 | JAFURAH 380/230kV BSP (SEC)-Supply, apply of General Backfilling Material - Jafurah BSP | APPROVED | No | 2023-02-01 | Abas, Mohammed Fekry | 2023-02-04 | 2023-02-05 |  |  |  | 1176000 | 4345 | 0 | STANDARD | RADI AHMED AL MANHAL CO. LTD | SAR | 1176000 | APPROVED |  |  | 2023-03-12 | 0 | 35 | Kumar, Mr. Ranjan | -44962 | 35
105-64 | JAFURAH 380/230kV BSP (SEC) | 1040 | JAFURAH 380/230kV BSP (SEC)-Third Party Lab Services | APPROVED | No | 2023-02-01 | Abas, Mohammed Fekry | 2023-02-04 | 2023-02-05 |  |  |  | 60960 | 4403 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 60960 | APPROVED |  |  | 2023-04-11 | 0 | 65 | Kumar, Mr. Ranjan | -44962 | 65
105-64 | JAFURAH 380/230kV BSP (SEC) | 1041 | JAFURAH 380/230kV BSP (SEC)-Supply, Apply & Testing of select fill material under foundation | APPROVED | No | 2023-02-02 | Abas, Mohammed Fekry | 2023-02-05 | 2023-02-05 |  |  |  | 142500 | 4337 | 0 | STANDARD | RADI AHMED AL MANHAL CO. LTD | SAR | 142500 | APPROVED |  |  | 2023-02-12 | 0 | 7 | Kumar, Mr. Ranjan | -44962 | 7
105-64 | JAFURAH 380/230kV BSP (SEC) | 1042 | JAFURAH 380/230kV BSP (SEC)-230kV Link Box | APPROVED | No | 2023-02-05 | Abas, Mohammed Fekry | 2023-02-06 | 2023-02-06 |  |  |  | 68400 | 4347 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 60000 | APPROVED |  |  | 2023-02-19 | 8400 | 13 | Babic, Marian | -44963 | 13
105-64 | JAFURAH 380/230kV BSP (SEC) | 1045 | JAFURAH 380/230kV BSP (SEC)-13.8kV Power Cable | APPROVED | No | 2023-02-05 | Abas, Mohammed Fekry | 2023-02-06 | 2023-02-06 |  |  |  | 454740 | 4405 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 198861.15 | APPROVED |  |  | 2023-05-22 | 255878.85 | 105 | Babic, Marian | -44963 | 105
105-64 | JAFURAH 380/230kV BSP (SEC) | 1045 | JAFURAH 380/230kV BSP (SEC)-13.8kV Power Cable | APPROVED | No | 2023-02-05 | Abas, Mohammed Fekry | 2023-02-06 | 2023-02-06 |  |  |  | 454740 | 4405 | 3 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 192506.46 | APPROVED |  |  | 2024-01-03 | 262233.54 | 331 | Babic, Marian | -44963 | 331
105-64 | JAFURAH 380/230kV BSP (SEC) | 1048 | JAFURAH 380/230kV BSP (SEC)-Supply, loading and unloading of Diesel Genset (1 year) | APPROVED | No | 2023-02-06 | Abas, Mohammed Fekry | 2023-02-08 | 2023-02-09 |  |  |  | 528000 | 4377 | 0 | STANDARD | SAUDI DIESEL EQUIPMENT CO.LTD | SAR | 454000 | APPROVED |  |  | 2023-04-06 | 74000 | 56 | Babic, Marian | -44966 | 56
105-64 | JAFURAH 380/230kV BSP (SEC) | 1049 | JAFURAH 380/230kV BSP (SEC)-230kV Power Cable Termination Kit | RETURNED | No | 2023-02-06 | Babic, Marian | 2023-04-06 | 2023-02-09 | 2023-04-06 |  | Please revise the prices | 591637.5 | 4404 | 0 | STANDARD | Brugg Kable AG | CHF | 468630 | APPROVED |  |  | 2023-04-13 | 123007.5 |  | Babic, Marian | -44966 | 63
105-64 | JAFURAH 380/230kV BSP (SEC) | 1050 | JAFURAH 380/230kV BSP (SEC)-13.8kV Power Cable Termination Kit | APPROVED | No | 2023-02-07 | Abas, Mohammed Fekry | 2023-02-08 | 2023-02-09 |  |  |  | 33684 | 4410 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 33636 | APPROVED |  |  | 2023-04-13 | 48 | 63 | Babic, Marian | -44966 | 63
105-64 | JAFURAH 380/230kV BSP (SEC) | 1053 | JAFURAH 380/230kV BSP (SEC)-Supply & Installation of NEW DSM at Jafurah 380/230kV BSP and Remote End Modifications | APPROVED | No | 2023-02-09 | Abas, Mohammed Fekry | 2023-02-10 | 2023-02-12 |  |  |  | 1114002.86 | 4718 | 0 | STANDARD | SAUDI ARABIAN INDUSTRIAL & TRADING Co. | SAR | 1114002.86 | APPROVED |  |  | 2023-11-21 | 0 | 282 | Kumar, Mr. Ranjan | -44969 | 282
105-64 | JAFURAH 380/230kV BSP (SEC) | 1059 | JAFURAH 380/230kV BSP (SEC)-Safety PPE's for Jafurah | APPROVED | No | 2023-02-12 | Abas, Mohammed Fekry | 2023-02-12 | 2023-02-13 |  |  |  | 27000 | 4343 | 0 | STANDARD | Reda Trading & Development Co. for Machinery & Equipment Ltd(S) | SAR | 26150.3 | APPROVED |  |  | 2023-02-15 | 849.7 | 2 | Kumar, Mr. Ranjan | -44970 | 2
105-64 | JAFURAH 380/230kV BSP (SEC) | 1060 | JAFURAH 380/230kV BSP (SEC)-Eathing Materials - Bare Copper Conductor | APPROVED | No | 2023-02-12 | Abas, Mohammed Fekry | 2023-02-12 | 2023-02-13 |  |  |  | 488650 | 4368 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 405562.31 | APPROVED |  |  | 2023-03-21 | 83087.69 | 36 | Babic, Marian | -44970 | 36
105-64 | JAFURAH 380/230kV BSP (SEC) | 1062 | JAFURAH 380/230kV BSP (SEC)-Supply of Reinforcement Earthing Materials | APPROVED | No | 2023-02-12 | Abas, Mohammed Fekry | 2023-02-15 | 2023-02-16 |  |  |  | 63942 | 4373 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 63640 | APPROVED |  |  | 2023-03-16 | 302 | 28 | Babic, Marian | -44973 | 28
105-64 | JAFURAH 380/230kV BSP (SEC) | 1064 | JAFURAH 380/230kV BSP (SEC)-Supply & Installation of NEW Transient Fault Recorder(TFR) & Fault Locator(FL) at Jafurah 380/230kV BSP and Saudi Aramco 230kV SS also Remote End Modification | APPROVED | No | 2023-02-12 | Abas, Mohammed Fekry | 2023-02-15 | 2023-02-16 |  |  |  | 1660000 | 4718 | 0 | STANDARD | SAUDI ARABIAN INDUSTRIAL & TRADING Co. | SAR | 1660000 | APPROVED |  |  | 2023-11-21 | 0 | 278 | Kumar, Mr. Ranjan | -44973 | 278
105-64 | JAFURAH 380/230kV BSP (SEC) | 1065 | JAFURAH 380/230kV BSP (SEC)-Supply & Installation of 125VDC System (Batteries & Chargers) | APPROVED | No | 2023-02-12 | Abas, Mohammed Fekry | 2023-02-15 | 2023-02-16 |  |  |  | 701220 | 4717 | 0 | STANDARD | Alassas Specialized Company Ltd | SAR | 701220 | APPROVED |  |  | 2023-11-21 | 0 | 278 | Kumar, Mr. Ranjan | -44973 | 278
105-64 | JAFURAH 380/230kV BSP (SEC) | 1066 | JAFURAH 380/230kV BSP (SEC)-Supply, apply of (Remaining) General Backfill Material | APPROVED | No | 2023-02-13 | Abas, Mohammed Fekry | 2023-02-15 | 2023-02-16 |  |  |  | 1200000 | 4350 | 0 | STANDARD | ABDULLAH SHEBAN ALDOSSARY & PARTNER CONT. CO. | SAR | 1200000 | APPROVED |  |  | 2023-04-11 | 0 | 54 | Kumar, Mr. Ranjan | -44973 | 54
105-64 | JAFURAH 380/230kV BSP (SEC) | 1067 | JAFURAH 380/230kV BSP (SEC)-Supply and installation of indoor AC units (as per attached BOQ) including copper pipes and stands for Outdoor units | APPROVED | No | 2023-02-13 | Abas, Mohammed Fekry | 2023-02-15 | 2023-02-16 |  |  |  | 93640 | 4371 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 88049.66 | APPROVED |  |  | 2023-03-16 | 5590.34 | 28 | Babic, Marian | -44973 | 28
105-64 | JAFURAH 380/230kV BSP (SEC) | 1079 | JAFURAH 380/230kV BSP (SEC)-Supply of 380kV & 230kV Post Insulators | APPROVED | No | 2023-02-19 | Abas, Mohammed Fekry | 2023-02-21 | 2023-02-23 |  |  |  | 917580 | 4363 | 0 | STANDARD | Power Trading T&D | EUR | 917580 | APPROVED |  |  | 2023-03-16 | 0 | 21 | Kumar, Mr. Ranjan | -44980 | 21
105-64 | JAFURAH 380/230kV BSP (SEC) | 1080 | JAFURAH 380/230kV BSP (SEC)-Security Services (1 year) | APPROVED | No | 2023-02-19 | Abas, Mohammed Fekry | 2023-02-21 | 2023-02-23 |  |  |  | 468000 | 4394 | 0 | STANDARD | Amnalawtan Security Company for civil security Guards | SAR | 468000 | APPROVED |  |  | 2023-04-02 | 0 | 38 | Abuhammad, Samir | -44980 | 38
105-64 | JAFURAH 380/230kV BSP (SEC) | 1081 | JAFURAH 380/230kV BSP (SEC)-Temporary Project Sign Board & Road Sign Boards | APPROVED | No | 2023-02-19 | Abas, Mohammed Fekry | 2023-02-21 | 2023-02-23 |  |  |  | 70300 | 4361 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 63270 | APPROVED |  |  | 2023-02-26 | 7030 | 3 | Babic, Marian | -44980 | 3
105-64 | JAFURAH 380/230kV BSP (SEC) | 1082 | JAFURAH 380/230kV BSP (SEC)-Surge Arrester | APPROVED | No | 2023-02-19 | Abas, Mohammed Fekry | 2023-02-21 | 2023-02-23 |  |  |  | 384190.5 | 4362 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 383022 | APPROVED |  |  | 2023-04-05 | 1168.5 | 41 | Kumar, Mr. Ranjan | -44980 | 41
105-64 | JAFURAH 380/230kV BSP (SEC) | 1084 | JAFURAH 380/230kV BSP (SEC)-Cyber Security for Jafurah BSP | APPROVED | No | 2023-02-21 | Abas, Mohammed Fekry | 2023-02-28 | 2023-02-28 |  |  |  | 2052750 | 4506 | 0 | STANDARD | ALFANAR CO | SAR | 2052750 | APPROVED |  |  | 2024-02-19 | 0 | 356 | Babic, Marian | -44985 | 356
105-64 | JAFURAH 380/230kV BSP (SEC) | 1092 | JAFURAH 380/230kV BSP (SEC)-Installation of AC units | APPROVED | No | 2023-03-01 | Abas, Mohammed Fekry | 2023-03-02 | 2023-03-05 |  |  |  | 17000 | 4371 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 16320 | APPROVED |  |  | 2023-03-16 | 680 | 11 | Babic, Marian | -44990 | 11
105-64 | JAFURAH 380/230kV BSP (SEC) | 1117 | JAFURAH 380/230kV BSP (SEC)-Supply and installation for water proofing work for substructure and roof works | APPROVED | No | 2023-03-09 | Abas, Mohammed Fekry | 2023-03-13 | 2023-03-13 |  |  |  | 1176199.5 | 4393 | 0 | STANDARD | ISAM kabbani & partners for construction & maintenance co.LTD | SAR | 1176199.5 | APPROVED |  |  | 2023-04-06 | 0 | 24 | Kumar, Mr. Ranjan | -44998 | 24
105-64 | JAFURAH 380/230kV BSP (SEC) | 1117 | JAFURAH 380/230kV BSP (SEC)-Supply and installation for water proofing work for substructure and roof works | APPROVED | No | 2023-03-09 | Abas, Mohammed Fekry | 2023-03-13 | 2023-03-13 |  |  |  | 1176199.5 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -44998 | -44998
105-64 | JAFURAH 380/230kV BSP (SEC) | 1130 | JAFURAH 380/230kV BSP (SEC)-Civil Subcontractor | APPROVED | No | 2023-03-14 | Abas, Mohammed Fekry | 2023-03-15 | 2023-03-16 |  |  |  | 26000000 | 4389 | 0 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 26000000 | APPROVED |  |  | 2023-04-05 | 0 | 20 | Babic, Marian | -45001 | 20
105-64 | JAFURAH 380/230kV BSP (SEC) | 1135 | JAFURAH 380/230kV BSP (SEC)-FAT for Surge Arrester | APPROVED | No | 2023-03-16 | Abas, Mohammed Fekry | 2023-03-21 | 2023-03-22 |  |  |  | 2050 | 4362 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 2050 | APPROVED |  |  | 2023-04-05 | 0 | 14 | Kumar, Mr. Ranjan | -45007 | 14
105-64 | JAFURAH 380/230kV BSP (SEC) | 1139 | JAFURAH 380/230kV BSP (SEC)-Remaining Excavation Works for PO# 4308-HV1393-0 | APPROVED | No | 2023-03-20 | Abas, Mohammed Fekry | 2023-03-22 | 2023-03-26 |  |  |  | 117730.39 | 4308 | 1 | STANDARD | RADI AHMED AL MANHAL CO. LTD | SAR | 117730.39 | APPROVED |  |  | 2023-04-13 | 0 | 18 | Kumar, Mr. Ranjan | -45011 | 18
105-64 | JAFURAH 380/230kV BSP (SEC) | 1149 | JAFURAH 380/230kV BSP (SEC)-Third Party Lab Services (Additional) | APPROVED | No | 2023-03-29 | Abas, Mohammed Fekry | 2023-04-01 | 2023-04-02 |  |  |  | 131040 | 4403 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 131040 | APPROVED |  |  | 2023-04-11 | 0 | 9 | Kumar, Mr. Ranjan | -45018 | 9
105-64 | JAFURAH 380/230kV BSP (SEC) | 1152 | JAFURAH 380/230kV BSP (SEC)-LV AC/DC Distribution Panels | APPROVED | No | 2023-04-03 | Abas, Mohammed Fekry | 2023-04-05 | 2023-04-09 |  |  |  | 2040000 | 4521 | 0 | STANDARD | Nour Industries Branch of Nour Communication | SAR | 2040000 | APPROVED |  |  | 2023-07-12 | 0 | 94 | Babic, Marian | -45025 | 94
105-64 | JAFURAH 380/230kV BSP (SEC) | 1159 | JAFURAH 380/230kV BSP (SEC)-Additional Select Fill for PO# 4337 | APPROVED | No | 2023-04-04 | Abas, Mohammed Fekry | 2023-04-08 | 2023-04-09 |  |  |  | 461586.5 | 4337 | 1 | STANDARD | RADI AHMED AL MANHAL CO. LTD | SAR | 461542 | APPROVED |  |  | 2023-04-13 | 44.5 | 4 | Kumar, Mr. Ranjan | -45025 | 4
105-64 | JAFURAH 380/230kV BSP (SEC) | 1160 | JAFURAH 380/230kV BSP (SEC)-Supply of Sweet Water | APPROVED | No | 2023-04-05 | Abas, Mohammed Fekry | 2023-04-08 | 2023-04-09 |  |  |  | 8400 | 4428 | 0 | STANDARD | HAMED ABDULLAH MOHAMMED AL-ALAWI FUEL CORPORATION | SAR | 6783 | APPROVED |  |  | 2023-05-29 | 1617 | 50 | Eranhikkal, Mr. Riyaz Mohammed | -45025 | 50
105-64 | JAFURAH 380/230kV BSP (SEC) | 1161 | JAFURAH 380/230kV BSP (SEC)-Supply of Diesel (1 year) | APPROVED | No | 2023-04-05 | Abas, Mohammed Fekry | 2023-04-08 | 2023-04-09 |  |  |  | 192000 | 4515 | 0 | STANDARD | Premium Service Station | SAR | 166956.52 | APPROVED |  |  | 2023-06-20 | 25043.48 | 72 | Eranhikkal, Mr. Riyaz Mohammed | -45025 | 72
105-64 | JAFURAH 380/230kV BSP (SEC) | 1168 | JAFURAH 380/230kV BSP (SEC)-TPI for Surge Arrester FAT | APPROVED | No | 2023-04-06 | Abas, Mohammed Fekry | 2023-04-07 | 2023-04-09 |  |  |  | 7072.5 | 4535 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 3900 | APPROVED |  |  | 2023-07-10 | 3172.5 | 92 | Eranhikkal, Mr. Riyaz Mohammed | -45025 | 92
105-64 | JAFURAH 380/230kV BSP (SEC) | 1185 | JAFURAH 380/230kV BSP (SEC)-Supply & Installation of Metal Doors and Hardwares | APPROVED | No | 2023-04-11 | Abas, Mohammed Fekry | 2023-04-12 | 2023-04-13 |  |  |  | 383125 | 4445 | 0 | STANDARD | Saudi Prefeb House Factory | SAR | 383125 | APPROVED |  |  | 2023-06-11 | 0 | 59 | Babic, Marian | -45029 | 59
105-64 | JAFURAH 380/230kV BSP (SEC) | 1190 | JAFURAH 380/230kV BSP (SEC)-Supply of Bonding and Grounding Cable | APPROVED | No | 2023-04-11 | Abas, Mohammed Fekry | 2023-04-12 | 2023-04-13 |  |  |  | 351745.99 | 4405 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 351745.99 | APPROVED |  |  | 2023-05-22 | 0 | 39 | Babic, Marian | -45029 | 39
105-64 | JAFURAH 380/230kV BSP (SEC) | 1190 | JAFURAH 380/230kV BSP (SEC)-Supply of Bonding and Grounding Cable | APPROVED | No | 2023-04-11 | Abas, Mohammed Fekry | 2023-04-12 | 2023-04-13 |  |  |  | 351745.99 | 4405 | 3 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 339721.26 | APPROVED |  |  | 2024-01-03 | 12024.72 | 265 | Babic, Marian | -45029 | 265
105-64 | JAFURAH 380/230kV BSP (SEC) | 1199 | JAFURAH 380/230kV BSP (SEC)-TPI for Grounding Cable FAT | APPROVED | No | 2023-04-18 | Abas, Mohammed Fekry | 2023-04-20 | 2023-04-30 |  |  |  | 1400 | 4425 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 1400 | APPROVED |  |  | 2023-05-02 | 0 | 2 | Kumar, Mr. Ranjan | -45046 | 2
105-64 | JAFURAH 380/230kV BSP (SEC) | 1210 | JAFURAH 380/230kV BSP (SEC)-230kV Power Cable Termination Kit (SF6/XLPE) | APPROVED | No | 2023-04-20 | Abas, Mohammed Fekry | 2023-04-22 | 2023-04-30 |  |  |  | 543204.9 | 4444 | 0 | STANDARD | SUDKABEL GmbH | EUR | 543204.9 | APPROVED |  |  | 2023-05-18 | 0 | 18 | Babic, Marian | -45046 | 18
105-64 | JAFURAH 380/230kV BSP (SEC) | 1210 | JAFURAH 380/230kV BSP (SEC)-230kV Power Cable Termination Kit (SF6/XLPE) | APPROVED | No | 2023-04-20 | Abas, Mohammed Fekry | 2023-04-22 | 2023-04-30 |  |  |  | 543204.9 | 4600 | 0 | STANDARD | LS Cable Systems Ltd | USD | 442125 | APPROVED |  |  | 2023-10-05 | 101079.9 | 158 | Babic, Marian | -45046 | 158
105-64 | JAFURAH 380/230kV BSP (SEC) | 1215 | JAFURAH 380/230kV BSP (SEC)-Supply of cable trays and ladders with accessories | RETURNED | No | 2023-04-27 | Babic, Marian | 2024-03-26 | 2023-05-02 | 2024-03-26 |  | PO for this subject already issued, this PR is a balance which is not needed | 394000.05 | 4437 | 0 | STANDARD | AL-AMAL ELECTRICAL SWITCHBOARDS | SAR | 394000.05 | APPROVED |  |  | 2023-05-18 | 0 |  | Babic, Marian | -45048 | 16
105-64 | JAFURAH 380/230kV BSP (SEC) | 1215 | JAFURAH 380/230kV BSP (SEC)-Supply of cable trays and ladders with accessories | RETURNED | No | 2023-04-27 | Babic, Marian | 2024-03-26 | 2023-05-02 | 2024-03-26 |  | PO for this subject already issued, this PR is a balance which is not needed | 214.59 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45048 | -45048
105-64 | JAFURAH 380/230kV BSP (SEC) | 1224 | JAFURAH 380/230kV BSP (SEC)-TPI for PDMS System FAT | APPROVED | No | 2023-05-02 | Abas, Mohammed Fekry | 2023-05-04 | 2023-05-08 |  |  |  | 2000 | 4455 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 1950 | APPROVED |  |  | 2023-05-21 | 50 | 13 | Kumar, Mr. Ranjan | -45054 | 13
105-64 | JAFURAH 380/230kV BSP (SEC) | 1225 | JAFURAH 380/230kV BSP (SEC)-Indoor & Outdoor Lighting Fixtures | APPROVED | No | 2023-05-02 | Abas, Mohammed Fekry | 2023-05-04 | 2023-05-08 |  |  |  | 398039.25 | 4530 | 0 | STANDARD | Integrated Lighting Co.,LED - Rayon | SAR | 398039.25 | APPROVED |  |  | 2023-07-12 | 0 | 65 | Babic, Marian | -45054 | 65
105-64 | JAFURAH 380/230kV BSP (SEC) | 1226 | JAFURAH 380/230kV BSP (SEC)-Clamps & Connectors for 380kV & 230kV Gantry Area | RETURNED | No | 2023-05-02 | Babic, Marian | 2024-04-16 | 2023-05-08 | 2024-04-16 |  | these lines are not needed, PO 4519 already issued | 171894.42 | 4519 | 0 | STANDARD | Arruti Subestaciones , S.A.U | EUR | 136079.98 | APPROVED |  |  | 2023-07-12 | 35814.44 |  | Babic, Marian | -45054 | 65
105-64 | JAFURAH 380/230kV BSP (SEC) | 1239 | JAFURAH 380/230kV BSP (SEC)-IT Materials for Site Office | APPROVED | No | 2023-05-09 | Abas, Mohammed Fekry | 2023-05-09 | 2023-05-10 |  |  |  | 53680 | 4474 | 0 | STANDARD | MAG Computer Trading Company S | SAR | 51630 | APPROVED |  |  | 2023-05-25 | 2050 | 15 | Babic, Marian | -45056 | 15
105-64 | JAFURAH 380/230kV BSP (SEC) | 1241 | JAFURAH 380/230kV BSP (SEC)-Supply of Raw Water | APPROVED | No | 2023-05-10 | Abas, Mohammed Fekry | 2023-05-15 | 2023-05-15 |  |  |  | 62500 | 4483 | 0 | STANDARD | World Green Engineering & Contracting Company | SAR | 62500 | APPROVED |  |  | 2023-05-29 | 0 | 14 | Kumar, Mr. Ranjan | -45061 | 14
105-64 | JAFURAH 380/230kV BSP (SEC) | 1257 | JAFURAH 380/230kV BSP (SEC)-TPI for Grounding Cable FAT (Additional 1 day) | APPROVED | No | 2023-05-14 | Abas, Mohammed Fekry | 2023-05-16 | 2023-05-16 |  |  |  | 1400 | 4482 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 1400 | APPROVED |  |  | 2023-05-25 | 0 | 9 | Kumar, Mr. Ranjan | -45062 | 9
105-64 | JAFURAH 380/230kV BSP (SEC) | 1262 | JAFURAH 380/230kV BSP (SEC)-Lightning Mast (LCM) & Outdoor Lighting Poles | RETURNED | No | 2023-05-16 | Babic, Marian | 2024-04-16 | 2023-05-17 | 2024-04-16 |  | these are lines from PO 4473 that are not required after change order | 180840 | 4473 | 4 | STANDARD | Omega Company for Luminaires , Poles & Galvnizing | SAR | 178100 | APPROVED |  |  | 2023-11-28 | 2740 |  | Babic, Marian | -45063 | 195
105-64 | JAFURAH 380/230kV BSP (SEC) | 1262 | JAFURAH 380/230kV BSP (SEC)-Lightning Mast (LCM) & Outdoor Lighting Poles | RETURNED | No | 2023-05-16 | Babic, Marian | 2024-04-16 | 2023-05-17 | 2024-04-16 |  | these are lines from PO 4473 that are not required after change order | 403360 | 4473 | 0 | STANDARD | Omega Company for Luminaires , Poles & Galvnizing | SAR | 403360 | APPROVED |  |  | 2023-06-20 | 0 |  | Babic, Marian | -45063 | 34
105-64 | JAFURAH 380/230kV BSP (SEC) | 1262 | JAFURAH 380/230kV BSP (SEC)-Lightning Mast (LCM) & Outdoor Lighting Poles | RETURNED | No | 2023-05-16 | Babic, Marian | 2024-04-16 | 2023-05-17 | 2024-04-16 |  | these are lines from PO 4473 that are not required after change order | 13600 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45063 | -45063
105-64 | JAFURAH 380/230kV BSP (SEC) | 1272 | JAFURAH 380/230kV BSP (SEC)-3rd Party lab test & quality control | APPROVED | No | 2023-05-17 | Abas, Mohammed Fekry | 2023-05-23 | 2023-05-24 |  |  |  | 146950 | 4489 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 146365 | APPROVED |  |  | 2023-06-06 | 585 | 13 | Kumar, Mr. Ranjan | -45070 | 13
105-64 | JAFURAH 380/230kV BSP (SEC) | 1277 | JAFURAH 380/230kV BSP (SEC)-Supply of Safety Signboards | APPROVED | No | 2023-05-21 | Abas, Mohammed Fekry | 2023-05-23 | 2023-05-24 |  |  |  | 53000 | 4490 | 0 | STANDARD | World Green Engineering & Contracting Company | SAR | 53000 | APPROVED |  |  | 2023-06-05 | 0 | 12 | Kumar, Mr. Ranjan | -45070 | 12
105-64 | JAFURAH 380/230kV BSP (SEC) | 1301 | JAFURAH 380/230kV BSP (SEC)-TPI for EOT Crane FAT | APPROVED | No | 2023-06-03 | Abas, Mohammed Fekry | 2023-06-04 | 2023-06-05 |  |  |  | 2400 | 4514 | 0 | STANDARD | Atlas Support and Services | SAR | 2200 | APPROVED |  |  | 2023-06-13 | 200 | 8 | Kumar, Mr. Ranjan | -45082 | 8
105-64 | JAFURAH 380/230kV BSP (SEC) | 1302 | JAFURAH 380/230kV BSP (SEC)-Catering & Accommodation Services | APPROVED | No | 2023-06-04 | Abas, Mohammed Fekry | 2023-06-05 | 2023-06-06 |  |  |  | 2258920 | 4518 | 0 | STANDARD | World Green Engineering & Contracting Company | SAR | 2258920 | APPROVED |  |  | 2023-06-26 | 0 | 20 | Kumar, Mr. Ranjan | -45083 | 20
105-64 | JAFURAH 380/230kV BSP (SEC) | 1306 | JAFURAH 380/230kV BSP (SEC)-Additional for TFR, DSM & FL for Jafurah BSP | APPROVED | No | 2023-06-04 | Abas, Mohammed Fekry | 2023-06-05 | 2023-06-06 |  |  |  | 65997.14 | 4718 | 0 | STANDARD | SAUDI ARABIAN INDUSTRIAL & TRADING Co. | SAR | 65997.14 | APPROVED |  |  | 2023-11-21 | 0 | 168 | Kumar, Mr. Ranjan | -45083 | 168
105-64 | JAFURAH 380/230kV BSP (SEC) | 1307 | JAFURAH 380/230kV BSP (SEC)-Additional for LV AC/DC Distribution Panels | APPROVED | No | 2023-06-04 | Abas, Mohammed Fekry | 2023-06-05 | 2023-06-06 |  |  |  | 377920.78 | 4521 | 0 | STANDARD | Nour Industries Branch of Nour Communication | SAR | 155000 | APPROVED |  |  | 2023-07-12 | 222920.78 | 36 | Babic, Marian | -45083 | 36
105-64 | JAFURAH 380/230kV BSP (SEC) | 1317 | JAFURAH 380/230kV BSP (SEC)-Additional Cost for Cyber Security System | APPROVED | No | 2023-06-11 | Abas, Mohammed Fekry | 2023-06-13 | 2023-06-14 |  |  |  | 47250 | 4506 | 0 | STANDARD | ALFANAR CO | SAR | 47250 | APPROVED |  |  | 2024-02-19 | 0 | 250 | Babic, Marian | -45091 | 250
105-64 | JAFURAH 380/230kV BSP (SEC) | 1318 | JAFURAH 380/230kV BSP (SEC)-Supply of LV Distribution Board, Cable Lugs and ATS | APPROVED | No | 2023-06-11 | Abas, Mohammed Fekry | 2023-06-13 | 2023-06-14 |  |  |  | 47750 | 4525 | 0 | STANDARD | Global Electrical Trd. Est.(S) | SAR | 45362.5 | APPROVED |  |  | 2023-07-09 | 2387.5 | 25 | Babic, Marian | -45091 | 25
105-64 | JAFURAH 380/230kV BSP (SEC) | 1319 | JAFURAH 380/230kV BSP (SEC)-Copper Tape for Jafurah BSP | APPROVED | No | 2023-06-12 | Abas, Mohammed Fekry | 2023-06-13 | 2023-06-14 |  |  |  | 156400 | 4528 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 156060 | APPROVED |  |  | 2023-07-16 | 340 | 32 | Babic, Marian | -45091 | 32
105-64 | JAFURAH 380/230kV BSP (SEC) | 1320 | JAFURAH 380/230kV BSP (SEC)-Steel Materials for Jafurah BSP Steel Works | APPROVED | No | 2023-06-13 | Abas, Mohammed Fekry | 2023-06-13 | 2023-06-14 |  |  |  | 1129403.69 | 4556 | 0 | STANDARD | Al Sharek Al Daem Est for Contracting | SAR | 1129403.69 | APPROVED |  |  | 2023-08-13 | 0 | 60 | Babic, Marian | -45091 | 60
105-64 | JAFURAH 380/230kV BSP (SEC) | 1322 | JAFURAH 380/230kV BSP (SEC)-48V DC-DC Converter | APPROVED | No | 2023-06-13 | Abas, Mohammed Fekry | 2023-06-19 | 2023-06-19 |  |  |  | 143500 | 4580 | 0 | STANDARD | BRAGA MORO SISTEMI DI ENERGIA | EUR | 139400 | APPROVED |  |  | 2023-08-31 | 4100 | 73 | Kumar, Mr. Ranjan | -45096 | 73
105-64 | JAFURAH 380/230kV BSP (SEC) | 1326 | JAFURAH 380/230kV BSP (SEC)-Tools and Equipment for Site | APPROVED | No | 2023-06-20 | Abas, Mohammed Fekry | 2023-06-21 | 2023-06-25 |  |  |  | 20000 | 4547 | 0 | STANDARD | Ahmed Essa Mohammed Al Muslim Est. | SAR | 20000 | APPROVED |  |  | 2023-07-27 | 0 | 32 | Babic, Marian | -45102 | 32
105-64 | JAFURAH 380/230kV BSP (SEC) | 1336 | JAFURAH 380/230kV BSP (SEC)-Gantry and Outdoor Equipment Support Structures | APPROVED | No | 2023-06-25 | Abas, Mohammed Fekry | 2023-07-06 | 2023-07-09 |  |  |  | 1964500 | 4667 | 0 | STANDARD | Hesham Helal Elsewedy & Partners for Construction Co., Ltd. | SAR | 1960000 | APPROVED |  |  | 2023-10-30 | 4500 | 113 | Babic, Marian | -45116 | 113
105-64 | JAFURAH 380/230kV BSP (SEC) | 1339 | JAFURAH 380/230kV BSP (SEC)-Additional Cost for Cable Tray and Ladders | APPROVED | No | 2023-07-06 | Abas, Mohammed Fekry | 2023-07-09 | 2023-07-10 |  |  |  | 40569.01 | 4437 | 1 | STANDARD | AL-AMAL ELECTRICAL SWITCHBOARDS | SAR | 40569.01 | APPROVED |  |  | 2023-08-13 | 0 | 34 | Babic, Marian | -45117 | 34
105-64 | JAFURAH 380/230kV BSP (SEC) | 1343 | JAFURAH 380/230kV BSP (SEC)-Air Condition & Other Furnitures for Jafurah Dammam Accomodation | APPROVED | No | 2023-07-06 | Abas, Mohammed Fekry | 2023-07-17 | 2023-07-17 |  |  |  | 16020 | 4565 | 0 | STANDARD | Kassim M.A. Al Driweesh Sons co. Ltd | SAR | 16020 | APPROVED |  |  | 2023-08-20 | 0 | 34 | Akhtar, Farhan | -45124 | 34
105-64 | JAFURAH 380/230kV BSP (SEC) | 1347 | JAFURAH 380/230kV BSP (SEC)-Aluminium Tubes | APPROVED | No | 2023-07-12 | Abas, Mohammed Fekry | 2023-07-17 | 2023-07-18 |  |  |  | 101912.64 | 4545 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 92000 | APPROVED |  |  | 2023-07-23 | 9912.64 | 5 | Babic, Marian | -45125 | 5
105-64 | JAFURAH 380/230kV BSP (SEC) | 1349 | JAFURAH 380/230kV BSP (SEC)-Male Nurse for Site | APPROVED | No | 2023-07-16 | Abas, Mohammed Fekry | 2023-07-17 | 2023-07-18 |  |  |  | 167760 | 4544 | 0 | STANDARD | Shifa Al Dammam Medical Company | SAR | 149760 | APPROVED |  |  | 2023-07-24 | 18000 | 6 | Babic, Marian | -45125 | 6
105-64 | JAFURAH 380/230kV BSP (SEC) | 1364 | JAFURAH 380/230kV BSP (SEC)-Medicines for Clinic | APPROVED | No | 2023-07-20 | Abas, Mohammed Fekry | 2023-07-25 | 2023-07-26 |  |  |  | 17610 | 4544 | 1 | STANDARD | Shifa Al Dammam Medical Company | SAR | 17160 | APPROVED |  |  | 2023-08-03 | 450 | 8 | Babic, Marian | -45133 | 8
105-64 | JAFURAH 380/230kV BSP (SEC) | 1372 | JAFURAH 380/230kV BSP (SEC)-TPI for MPLS-TP FAT | APPROVED | No | 2023-07-25 | Abas, Mohammed Fekry | 2023-07-27 | 2023-07-27 |  |  |  | 21375 | 4586 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 21375 | APPROVED |  |  | 2023-08-30 | 0 | 34 | Kumar, Mr. Ranjan | -45134 | 34
105-64 | JAFURAH 380/230kV BSP (SEC) | 1374 | JAFURAH 380/230kV BSP (SEC)-Remaining Medicines for Clinic | APPROVED | No | 2023-07-25 | Abas, Mohammed Fekry | 2023-07-26 | 2023-07-27 |  |  |  | 6257.73 | 4544 | 1 | STANDARD | Shifa Al Dammam Medical Company | SAR | 6257.73 | APPROVED |  |  | 2023-08-03 | 0 | 7 | Babic, Marian | -45134 | 7
105-64 | JAFURAH 380/230kV BSP (SEC) | 1378 | JAFURAH 380/230kV BSP (SEC)-Addtional budget for steel materials(PR no:1320) | APPROVED | No | 2023-07-31 | Abas, Mohammed Fekry | 2023-08-01 | 2023-08-01 |  |  |  | 65596.31 | 4556 | 0 | STANDARD | Al Sharek Al Daem Est for Contracting | SAR | 65596.31 | APPROVED |  |  | 2023-08-13 | 0 | 12 | Babic, Marian | -45139 | 12
105-64 | JAFURAH 380/230kV BSP (SEC) | 1380 | JAFURAH 380/230kV BSP (SEC)-Supply of Yellow/Green Cables (Updated) | APPROVED | No | 2023-08-01 | Abas, Mohammed Fekry | 2023-08-01 | 2023-08-03 |  |  |  | 877958.52 | 4567 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 877958.52 | APPROVED |  |  | 2023-08-15 | 0 | 12 | Babic, Marian | -45141 | 12
105-64 | JAFURAH 380/230kV BSP (SEC) | 1380 | JAFURAH 380/230kV BSP (SEC)-Supply of Yellow/Green Cables (Updated) | APPROVED | No | 2023-08-01 | Abas, Mohammed Fekry | 2023-08-01 | 2023-08-03 |  |  |  | 877958.52 | 4567 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 853150.48 | APPROVED |  |  | 2023-08-17 | 24808.04 | 14 | Babic, Marian | -45141 | 14
105-64 | JAFURAH 380/230kV BSP (SEC) | 1384 | JAFURAH 380/230kV BSP (SEC)-RTV Coating | APPROVED | No | 2023-08-06 | Abas, Mohammed Fekry | 2023-08-08 | 2023-08-13 |  |  |  | 300000 | 4882 | 0 | STANDARD | Desert World Company | SAR | 260532.49 | APPROVED |  |  | 2024-01-21 | 39467.51 | 161 | Kumar, Mr. Ranjan | -45151 | 161
105-64 | JAFURAH 380/230kV BSP (SEC) | 1394 | JAFURAH 380/230kV BSP (SEC)-Additional Cost for HVAC System (PR 1031) | APPROVED | No | 2023-08-09 | Abas, Mohammed Fekry | 2023-08-14 | 2023-08-16 |  |  |  | 200000 | 4578 | 0 | STANDARD | Hamad Fahad Al Awad for Contracting Est | SAR | 200000 | APPROVED |  |  | 2023-08-28 | 0 | 12 | Kumar, Mr. Ranjan | -45154 | 12
105-64 | JAFURAH 380/230kV BSP (SEC) | 1395 | JAFURAH 380/230kV BSP (SEC)-Additional Cost for 125V DC System (PR 1065) | APPROVED | No | 2023-08-09 | Abas, Mohammed Fekry | 2023-08-14 | 2023-08-16 |  |  |  | 213780 | 4717 | 0 | STANDARD | Alassas Specialized Company Ltd | SAR | 213780 | APPROVED |  |  | 2023-11-21 | 0 | 97 | Kumar, Mr. Ranjan | -45154 | 97
105-64 | JAFURAH 380/230kV BSP (SEC) | 1396 | JAFURAH 380/230kV BSP (SEC)-Additional Cost for Civil Works (JABCO PO# 4389) | REJECTED | No | 2023-08-09 | Khan, Muhammad Safdar | 2023-08-09 |  |  | 2023-08-16 |  | 826700 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-64 | JAFURAH 380/230kV BSP (SEC) | 1398 | JAFURAH 380/230kV BSP (SEC)-Additional cost for 3rd Party lab test & quality control (SAFCO PO# 4489) | REJECTED | No | 2023-08-09 | Khan, Muhammad Safdar | 2023-08-09 |  |  | 2023-08-09 |  | 30000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-64 | JAFURAH 380/230kV BSP (SEC) | 1399 | JAFURAH 380/230kV BSP (SEC)-DRAINAGE & PIT PUMPS | APPROVED | No | 2023-08-10 | Abas, Mohammed Fekry | 2023-08-14 | 2023-08-16 |  |  |  | 171500 | 4700 | 0 | STANDARD | Al-Wabel Trading & Maintenance | SAR | 171500 | APPROVED |  |  | 2023-11-28 | 0 | 104 | Kumar, Mr. Ranjan | -45154 | 104
105-64 | JAFURAH 380/230kV BSP (SEC) | 1400 | JAFURAH 380/230kV BSP (SEC)-Additional Cost, BCU and TMK Panels (Alfanar PO# 4503) | APPROVED | No | 2023-08-09 | Abas, Mohammed Fekry | 2023-08-14 | 2023-08-16 |  |  |  | 490000 | 4621 | 0 | STANDARD | ALFANAR CO | SAR | 480500 | APPROVED |  |  | 2023-10-04 | 9500 | 49 | Kumar, Mr. Ranjan | -45154 | 49
105-64 | JAFURAH 380/230kV BSP (SEC) | 1405 | JAFURAH 380/230kV BSP (SEC)-Grounding Enhancement Materials (SESCO) | APPROVED | No | 2023-08-13 | Abas, Mohammed Fekry | 2023-08-14 | 2023-08-16 |  |  |  | 18675 | 4572 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 18675 | APPROVED |  |  | 2023-08-22 | 0 | 6 | Babic, Marian | -45154 | 6
105-64 | JAFURAH 380/230kV BSP (SEC) | 1411 | JAFURAH 380/230kV BSP (SEC)-Cable Tray Accessories | APPROVED | No | 2023-08-14 | Abas, Mohammed Fekry | 2023-08-20 | 2023-08-21 |  |  |  | 365204.25 | 4594 | 0 | STANDARD | AL-AMAL ELECTRICAL SWITCHBOARDS | SAR | 356950.92 | APPROVED |  |  | 2023-09-11 | 8253.33 | 21 | Babic, Marian | -45159 | 21
105-64 | JAFURAH 380/230kV BSP (SEC) | 1412 | JAFURAH 380/230kV BSP (SEC)-Tools for Cable tray works | APPROVED | No | 2023-08-14 | Abas, Mohammed Fekry | 2023-08-20 | 2023-08-21 |  |  |  | 18234.5 | 4588 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 18234.5 | APPROVED |  |  | 2023-09-05 | 0 | 15 | Babic, Marian | -45159 | 15
105-64 | JAFURAH 380/230kV BSP (SEC) | 1414 | JAFURAH 380/230kV BSP (SEC)-Additional Cost for 48VDC system (PO# 8284) | APPROVED | No | 2023-08-16 | Abas, Mohammed Fekry | 2023-08-20 | 2023-08-20 |  |  |  | 524800 | 4580 | 0 | STANDARD | BRAGA MORO SISTEMI DI ENERGIA | EUR | 524800 | APPROVED |  |  | 2023-08-31 | 0 | 11 | Kumar, Mr. Ranjan | -45158 | 11
105-64 | JAFURAH 380/230kV BSP (SEC) | 1415 | JAFURAH 380/230kV BSP (SEC)-Additional Cost for Clamps & Connectors | RETURNED | No | 2023-08-16 | Babic, Marian | 2024-03-26 | 2023-08-20 | 2024-03-26 |  | PO for this subject already issued, this PR is a balance which is not needed | 87900.9 | 4519 | 1 | STANDARD | Arruti Subestaciones , S.A.U | EUR | 87900.9 | APPROVED |  |  | 2023-08-29 | 0 |  | Babic, Marian | -45158 | 9
105-64 | JAFURAH 380/230kV BSP (SEC) | 1416 | JAFURAH 380/230kV BSP (SEC)-Dammam Office Renovation | APPROVED | No | 2023-08-16 | Abas, Mohammed Fekry | 2023-08-20 | 2023-08-21 |  |  |  | 50000 | 4575 | 0 | STANDARD | Samcon Contracting Company LTD. | SAR | 50000 | APPROVED |  |  | 2023-09-21 | 0 | 31 | Babic, Marian | -45159 | 31
105-64 | JAFURAH 380/230kV BSP (SEC) | 1427 | JAFURAH 380/230kV BSP (SEC)-Supply of LV Control Cables | APPROVED | No | 2023-08-22 | Abas, Mohammed Fekry | 2023-08-22 | 2023-08-24 |  |  |  | 1654944.9 | 4596 | 0 | STANDARD | ALFANAR CO | SAR | 1654944.9 | APPROVED |  |  | 2023-09-05 | 0 | 12 | Babic, Marian | -45162 | 12
105-64 | JAFURAH 380/230kV BSP (SEC) | 1427 | JAFURAH 380/230kV BSP (SEC)-Supply of LV Control Cables | APPROVED | No | 2023-08-22 | Abas, Mohammed Fekry | 2023-08-22 | 2023-08-24 |  |  |  | 1654944.9 | 4596 | 1 | STANDARD | ALFANAR CO | SAR | 1575655 | APPROVED |  |  | 2023-10-26 | 79289.9 | 63 | Babic, Marian | -45162 | 63
105-64 | JAFURAH 380/230kV BSP (SEC) | 1428 | JAFURAH 380/230kV BSP (SEC)-Supply of LV Power and Control Cables | RETURNED | No | 2023-08-22 | Babic, Marian | 2024-04-16 | 2023-08-24 | 2024-04-16 |  | these lines are not required after issuance of change order 8266-2 | 5850291.2 | 4596 | 0 | STANDARD | ALFANAR CO | SAR | 5850291.2 | APPROVED |  |  | 2023-09-05 | 0 |  | Babic, Marian | -45162 | 12
105-64 | JAFURAH 380/230kV BSP (SEC) | 1428 | JAFURAH 380/230kV BSP (SEC)-Supply of LV Power and Control Cables | RETURNED | No | 2023-08-22 | Babic, Marian | 2024-04-16 | 2023-08-24 | 2024-04-16 |  | these lines are not required after issuance of change order 8266-2 | 5850291.2 | 4596 | 1 | STANDARD | ALFANAR CO | SAR | 5513373.97 | APPROVED |  |  | 2023-10-26 | 336917.23 |  | Babic, Marian | -45162 | 63
105-64 | JAFURAH 380/230kV BSP (SEC) | 1429 | JAFURAH 380/230kV BSP (SEC)-Supply of LV Control Cable for Jafurah | APPROVED | No | 2023-08-22 | Abas, Mohammed Fekry | 2023-08-22 | 2023-08-24 |  |  |  | 244840.8 | 4596 | 0 | STANDARD | ALFANAR CO | SAR | 244840.8 | APPROVED |  |  | 2023-09-05 | 0 | 12 | Babic, Marian | -45162 | 12
105-64 | JAFURAH 380/230kV BSP (SEC) | 1429 | JAFURAH 380/230kV BSP (SEC)-Supply of LV Control Cable for Jafurah | APPROVED | No | 2023-08-22 | Abas, Mohammed Fekry | 2023-08-22 | 2023-08-24 |  |  |  | 244840.8 | 4596 | 1 | STANDARD | ALFANAR CO | SAR | 236761.05 | APPROVED |  |  | 2023-10-26 | 8079.75 | 63 | Babic, Marian | -45162 | 63
105-64 | JAFURAH 380/230kV BSP (SEC) | 1430 | JAFURAH 380/230kV BSP (SEC)-Supply of LV Control Cable for Jafurah BSP | APPROVED | No | 2023-08-22 | Abas, Mohammed Fekry | 2023-08-22 | 2023-08-24 |  |  |  | 504563.4 | 4596 | 0 | STANDARD | ALFANAR CO | SAR | 504563.4 | APPROVED |  |  | 2023-09-05 | 0 | 12 | Babic, Marian | -45162 | 12
105-64 | JAFURAH 380/230kV BSP (SEC) | 1430 | JAFURAH 380/230kV BSP (SEC)-Supply of LV Control Cable for Jafurah BSP | APPROVED | No | 2023-08-22 | Abas, Mohammed Fekry | 2023-08-22 | 2023-08-24 |  |  |  | 504563.4 | 4596 | 1 | STANDARD | ALFANAR CO | SAR | 485053.62 | APPROVED |  |  | 2023-10-26 | 19509.78 | 63 | Babic, Marian | -45162 | 63
105-64 | JAFURAH 380/230kV BSP (SEC) | 1435 | JAFURAH 380/230kV BSP (SEC)-Dammam Office Renovation (PR# 2) | APPROVED | No | 2023-08-24 | Abas, Mohammed Fekry | 2023-08-27 | 2023-08-27 |  |  |  | 54000 | 4575 | 0 | STANDARD | Samcon Contracting Company LTD. | SAR | 50000 | APPROVED |  |  | 2023-09-21 | 4000 | 25 | Babic, Marian | -45165 | 25
105-64 | JAFURAH 380/230kV BSP (SEC) | 1436 | JAFURAH 380/230kV BSP (SEC)-TPI for Fault Recorder | APPROVED | No | 2023-08-24 | Abas, Mohammed Fekry | 2023-08-27 | 2023-08-27 |  |  |  | 3500 | 4589 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 3500 | APPROVED |  |  | 2023-09-05 | 0 | 9 | Kumar, Mr. Ranjan | -45165 | 9
105-64 | JAFURAH 380/230kV BSP (SEC) | 1437 | JAFURAH 380/230kV BSP (SEC)-TPI for 13.8kV Switchgear | APPROVED | No | 2023-08-24 | Abas, Mohammed Fekry | 2023-08-27 | 2023-08-27 |  |  |  | 2000 | 4590 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | SAR | 2000 | APPROVED |  |  | 2023-08-30 | 0 | 3 | Kumar, Mr. Ranjan | -45165 | 3
105-64 | JAFURAH 380/230kV BSP (SEC) | 1442 | JAFURAH 380/230kV BSP (SEC)-Lighting accessories | APPROVED | No | 2023-08-28 | Abas, Mohammed Fekry | 2023-08-30 | 2023-08-30 |  |  |  | 587784 | 4620 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 540000 | APPROVED |  |  | 2023-10-05 | 47784 | 36 | Eranhikkal, Mr. Riyaz Mohammed | -45168 | 36
105-64 | JAFURAH 380/230kV BSP (SEC) | 1446 | JAFURAH 380/230kV BSP (SEC)-Water proffing works- Jafurah SS | APPROVED | No | 2023-09-03 | Abas, Mohammed Fekry | 2023-09-04 | 2023-09-05 |  |  |  | 565951.75 | 4393 | 1 | STANDARD | ISAM kabbani & partners for construction & maintenance co.LTD | SAR | 564545.5 | APPROVED |  |  | 2023-10-30 | 1406.25 | 55 | Kumar, Mr. Ranjan | -45174 | 55
105-64 | JAFURAH 380/230kV BSP (SEC) | 1452 | JAFURAH 380/230kV BSP (SEC)-TPI for Power & Grounding Transformer | APPROVED | No | 2023-09-04 | Abas, Mohammed Fekry | 2023-09-10 | 2023-09-12 |  |  |  | 28350 | 4672 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 28350 | APPROVED |  |  | 2023-12-03 | 0 | 82 | Kumar, Mr. Ranjan | -45181 | 82
105-64 | JAFURAH 380/230kV BSP (SEC) | 1469 | JAFURAH 380/230kV BSP (SEC)-TPI for Protection & Control (Lot-1) | APPROVED | No | 2023-09-09 | Abas, Mohammed Fekry | 2023-09-10 | 2023-09-12 |  |  |  | 12500 | 4735 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 10000 | APPROVED |  |  | 2023-11-21 | 2500 | 70 | Kumar, Mr. Ranjan | -45181 | 70
105-64 | JAFURAH 380/230kV BSP (SEC) | 1476 | JAFURAH 380/230kV BSP (SEC)-TPI for PSE | APPROVED | No | 2023-09-10 | Abas, Mohammed Fekry | 2023-09-10 | 2023-09-12 |  |  |  | 4200 | 4642 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 4200 | APPROVED |  |  | 2023-10-09 | 0 | 27 | Kumar, Mr. Ranjan | -45181 | 27
105-64 | JAFURAH 380/230kV BSP (SEC) | 1501 | JAFURAH 380/230kV BSP (SEC)-TPI for 230kV Power Cable Termination Kit | APPROVED | No | 2023-09-13 | Abas, Mohammed Fekry | 2023-09-17 | 2023-09-17 |  |  |  | 4800 | 4672 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 4800 | APPROVED |  |  | 2023-12-03 | 0 | 77 | Kumar, Mr. Ranjan | -45186 | 77
105-64 | JAFURAH 380/230kV BSP (SEC) | 1502 | JAFURAH 380/230kV BSP (SEC)-TPI for 230kV GIB | APPROVED | No | 2023-09-17 | Abas, Mohammed Fekry | 2023-09-17 | 2023-09-18 |  |  |  | 15037.5 | 4628 | 0 | STANDARD | SGS GULF LIMITED | USD | 15037.5 | APPROVED |  |  | 2023-10-09 | 0 | 21 | Kumar, Mr. Ranjan | -45187 | 21
105-64 | JAFURAH 380/230kV BSP (SEC) | 1503 | JAFURAH 380/230kV BSP (SEC)-TPI for 230kV GIS LCC | APPROVED | No | 2023-09-17 | Abas, Mohammed Fekry | 2023-09-17 | 2023-09-18 |  |  |  | 5156.25 | 4628 | 0 | STANDARD | SGS GULF LIMITED | USD | 5156.25 | APPROVED |  |  | 2023-10-09 | 0 | 21 | Kumar, Mr. Ranjan | -45187 | 21
105-64 | JAFURAH 380/230kV BSP (SEC) | 1515 | JAFURAH 380/230kV BSP (SEC)-TPI for 230kV Link Box | APPROVED | No | 2023-09-19 | Abas, Mohammed Fekry | 2023-09-20 | 2023-09-20 |  |  |  | 1400 | 4708 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 1400 | APPROVED |  |  | 2023-11-09 | 0 | 50 | Kumar, Mr. Ranjan | -45189 | 50
105-64 | JAFURAH 380/230kV BSP (SEC) | 1517 | JAFURAH 380/230kV BSP (SEC)-Additional PR for LCLM and LP (PO# 4473) | APPROVED | No | 2023-09-19 | Abas, Mohammed Fekry | 2023-09-26 | 2023-09-26 |  |  |  | 380 | 4473 | 6 | STANDARD | Omega Company for Luminaires , Poles & Galvnizing | SAR | 380 | APPROVED |  |  | 2024-04-28 | 0 | 215 | Babic, Marian | -45195 | 215
105-64 | JAFURAH 380/230kV BSP (SEC) | 1517 | JAFURAH 380/230kV BSP (SEC)-Additional PR for LCLM and LP (PO# 4473) | APPROVED | No | 2023-09-19 | Abas, Mohammed Fekry | 2023-09-26 | 2023-09-26 |  |  |  | 43780 | 4473 | 4 | STANDARD | Omega Company for Luminaires , Poles & Galvnizing | SAR | 43780 | APPROVED |  |  | 2023-11-28 | 0 | 63 | Babic, Marian | -45195 | 63
105-64 | JAFURAH 380/230kV BSP (SEC) | 1518 | JAFURAH 380/230kV BSP (SEC)-Grounding Accessories (PVC Conduit and others) | APPROVED | No | 2023-09-20 | Abas, Mohammed Fekry | 2023-09-26 | 2023-09-26 |  |  |  | 57860 | 4660 | 0 | STANDARD | Jahaz Ayed Al-Rashidi and Partner for Trad and count | SAR | 56490.5 | APPROVED |  |  | 2023-10-15 | 1369.5 | 19 | Babic, Marian | -45195 | 19
105-64 | JAFURAH 380/230kV BSP (SEC) | 1520 | JAFURAH 380/230kV BSP (SEC)-TPI for 230kV GIS | APPROVED | No | 2023-09-23 | Abas, Mohammed Fekry | 2023-09-25 | 2023-09-26 |  |  |  | 10500 | 4628 | 0 | STANDARD | SGS GULF LIMITED | USD | 10500 | APPROVED |  |  | 2023-10-09 | 0 | 13 | Kumar, Mr. Ranjan | -45195 | 13
105-64 | JAFURAH 380/230kV BSP (SEC) | 1521 | JAFURAH 380/230kV BSP (SEC)-TPI - 13.8kV Switchgear, (Additional to PO# 4590) | APPROVED | No | 2023-09-23 | Abas, Mohammed Fekry | 2023-09-25 | 2023-09-26 |  |  |  | 2000 | 4590 | 1 | STANDARD | INTERTEK SAUDI ARABIA LTD | SAR | 2000 | APPROVED |  |  | 2024-01-14 | 0 | 110 | Kumar, Mr. Ranjan | -45195 | 110
105-64 | JAFURAH 380/230kV BSP (SEC) | 1522 | JAFURAH 380/230kV BSP (SEC)-TPI for 230kV Free Standing CT | APPROVED | No | 2023-09-25 | Abas, Mohammed Fekry | 2023-09-27 | 2023-09-27 |  |  |  | 17625 | 4628 | 0 | STANDARD | SGS GULF LIMITED | USD | 17625 | APPROVED |  |  | 2023-10-09 | 0 | 12 | Kumar, Mr. Ranjan | -45196 | 12
105-64 | JAFURAH 380/230kV BSP (SEC) | 1528 | JAFURAH 380/230kV BSP (SEC)-TPI - 230kV GIS, additional courrier & administration cost | APPROVED | No | 2023-09-27 | Abas, Mohammed Fekry | 2023-09-30 | 2023-10-02 |  |  |  | 675 | 4628 | 0 | STANDARD | SGS GULF LIMITED | USD | 675 | APPROVED |  |  | 2023-10-09 | 0 | 7 | Kumar, Mr. Ranjan | -45201 | 7
105-64 | JAFURAH 380/230kV BSP (SEC) | 1529 | JAFURAH 380/230kV BSP (SEC)-TPI - 230kV GIB, additional courrier & administration cost | APPROVED | No | 2023-09-27 | Abas, Mohammed Fekry | 2023-09-30 | 2023-10-02 |  |  |  | 375 | 4628 | 0 | STANDARD | SGS GULF LIMITED | USD | 375 | APPROVED |  |  | 2023-10-09 | 0 | 7 | Kumar, Mr. Ranjan | -45201 | 7
105-64 | JAFURAH 380/230kV BSP (SEC) | 1530 | JAFURAH 380/230kV BSP (SEC)-TPI - 230kV LCC & 380kV GIS, additional courrier & administration cost | APPROVED | No | 2023-09-27 | Abas, Mohammed Fekry | 2023-09-30 | 2023-10-02 |  |  |  | 375 | 4628 | 0 | STANDARD | SGS GULF LIMITED | USD | 375 | APPROVED |  |  | 2023-10-09 | 0 | 7 | Kumar, Mr. Ranjan | -45201 | 7
105-64 | JAFURAH 380/230kV BSP (SEC) | 1532 | JAFURAH 380/230kV BSP (SEC)-Supply of Rail Support Structure | APPROVED | No | 2023-09-28 | Abas, Mohammed Fekry | 2023-10-02 | 2023-10-02 |  |  |  | 206250 | 4699 | 0 | STANDARD | Al Sharek Al Daem Est for Contracting | SAR | 206250 | APPROVED |  |  | 2023-12-11 | 0 | 70 | Kumar, Mr. Ranjan | -45201 | 70
105-64 | JAFURAH 380/230kV BSP (SEC) | 1540 | JAFURAH 380/230kV BSP (SEC)-Supply of Miscellaneous Materials+Air conditions | APPROVED | No | 2023-10-02 | Abas, Mohammed Fekry | 2023-10-04 | 2023-10-06 |  |  |  | 650000 | 4661 | 0 | STANDARD | Essa Al Asmakh Trading Est. | SAR | 604263.07 | APPROVED |  |  | 2023-11-06 | 45736.93 | 31 | Kumar, Mr. Ranjan | -45205 | 31
105-64 | JAFURAH 380/230kV BSP (SEC) | 1542 | JAFURAH 380/230kV BSP (SEC)-Supply, Install and Testing of FOC | APPROVED | No | 2023-10-02 | Abas, Mohammed Fekry | 2023-10-04 | 2023-10-06 |  |  |  | 278781 | 4691 | 0 | STANDARD | INNOVATIVE SYSTEMS COMPANY LTD. | SAR | 211000 | APPROVED |  |  | 2023-11-06 | 67781 | 31 | Babic, Marian | -45205 | 31
105-64 | JAFURAH 380/230kV BSP (SEC) | 1546 | JAFURAH 380/230kV BSP (SEC)-Installation of 230kV SF6/XLPE Termination Kit | APPROVED | No | 2023-10-04 | Abas, Mohammed Fekry | 2023-10-04 | 2023-10-06 |  |  |  | 567000 | 4777 | 0 | STANDARD | LS Cable Systems Ltd | USD | 567000 | APPROVED |  |  | 2023-12-09 | 0 | 64 | Babic, Marian | -45205 | 64
105-64 | JAFURAH 380/230kV BSP (SEC) | 1547 | JAFURAH 380/230kV BSP (SEC)-4P Control Cable | APPROVED | No | 2023-10-04 | Abas, Mohammed Fekry | 2023-10-04 | 2023-10-06 |  |  |  | 50908.54 | 4675 | 0 | STANDARD | Middle East Specialized Cables Mesc | SAR | 37656.49 | APPROVED |  |  | 2023-10-25 | 13252.06 | 19 | Babic, Marian | -45205 | 19
105-64 | JAFURAH 380/230kV BSP (SEC) | 1547 | JAFURAH 380/230kV BSP (SEC)-4P Control Cable | APPROVED | No | 2023-10-04 | Abas, Mohammed Fekry | 2023-10-04 | 2023-10-06 |  |  |  | 50908.54 | 5008 | 0 | STANDARD | Tekab Company LLC. | SAR | 41867.66 | APPROVED |  |  | 2024-02-15 | 9040.89 | 132 | Babic, Marian | -45205 | 132
105-64 | JAFURAH 380/230kV BSP (SEC) | 1586 | JAFURAH 380/230kV BSP (SEC)-MATERIAL & TOOLS REQUIREMENT FOR JAFRUAH BSP | APPROVED | No | 2023-10-12 | Abas, Mohammed Fekry | 2023-10-12 | 2023-10-12 |  |  |  | 47507.5 | 4712 | 0 | STANDARD | Jahaz Ayed Al-Rashidi and Partner for Trad and count | SAR | 31336.7 | APPROVED |  |  | 2023-11-19 | 16170.8 | 38 | Babic, Marian | -45211 | 38
105-64 | JAFURAH 380/230kV BSP (SEC) | 1590 | JAFURAH 380/230kV BSP (SEC)-Additional PR for LV AC/DC Power Cables (PO# 4596) | APPROVED | No | 2023-10-12 | Abas, Mohammed Fekry | 2023-10-15 | 2023-10-17 |  |  |  | 88817.82 | 4596 | 1 | STANDARD | ALFANAR CO | SAR | 88817.82 | APPROVED |  |  | 2023-10-26 | 0 | 9 | Babic, Marian | -45216 | 9
105-64 | JAFURAH 380/230kV BSP (SEC) | 1596 | JAFURAH 380/230kV BSP (SEC)-380kV & 230kV OUTDOOR FREE STANDING CT MARSHALLING BOX | APPROVED | No | 2023-10-15 | Abas, Mohammed Fekry | 2023-10-15 | 2023-10-17 |  |  |  | 140529.31 | 4942 | 0 | STANDARD | Energy Tracks For Contracting | SAR | 121500.01 | APPROVED |  |  | 2024-01-30 | 19029.3 | 105 | Kumar, Mr. Ranjan | -45216 | 105
105-64 | JAFURAH 380/230kV BSP (SEC) | 1610 | JAFURAH 380/230kV BSP (SEC)-CCTV CAMERA SUPPLY AND INSTALLATION | APPROVED | No | 2023-10-19 | Abas, Mohammed Fekry | 2023-11-14 | 2023-11-14 | 2023-11-01 |  | Reference to the final agreed price with vendor (76,000), please adjust the PR amount. | 76600 | 4779 | 0 | STANDARD | Construction Expertise Est. | SAR | 76600 | APPROVED |  |  | 2023-12-10 | 0 | 26 | Alhadi, Khalid | -45244 | 26
105-64 | JAFURAH 380/230kV BSP (SEC) | 1616 | JAFURAH 380/230kV BSP (SEC)-Roof Gravel and Precast Roof Tiles | APPROVED | No | 2023-10-21 | Abas, Mohammed Fekry | 2023-10-22 | 2023-10-22 |  |  |  | 59150 | 4720 | 0 | STANDARD | Construction Expertise Est. | SAR | 59150 | APPROVED |  |  | 2023-11-23 | 0 | 32 | Kumar, Mr. Ranjan | -45221 | 32
105-64 | JAFURAH 380/230kV BSP (SEC) | 1619 | JAFURAH 380/230kV BSP (SEC)-Additional One Day for TPI - Power Transformer (PR# 1452) | APPROVED | No | 2023-10-22 | Abas, Mohammed Fekry | 2023-10-22 | 2023-10-23 |  |  |  | 1575 | 4672 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 1575 | APPROVED |  |  | 2023-12-03 | 0 | 41 | Kumar, Mr. Ranjan | -45222 | 41
105-64 | JAFURAH 380/230kV BSP (SEC) | 1620 | JAFURAH 380/230kV BSP (SEC)-Protection, Control & SAS, FO patch panel addiotnal scope | APPROVED | No | 2023-10-23 | Abas, Mohammed Fekry | 2023-10-25 | 2023-10-25 |  |  |  | 175500 | 4503 | 1 | STANDARD | ALFANAR CO | SAR | 100000 | APPROVED |  |  | 2023-11-12 | 75500 | 18 | Kumar, Mr. Ranjan | -45224 | 18
105-64 | JAFURAH 380/230kV BSP (SEC) | 1640 | JAFURAH 380/230kV BSP (SEC)-INSTALLATION TOOLS FOR GIS | APPROVED | No | 2023-10-29 | Abas, Mohammed Fekry | 2023-10-29 | 2023-10-30 |  |  |  | 100000 | 4770 | 0 | STANDARD | Jahaz Ayed Al-Rashidi and Partner for Trad and count | SAR | 84485 | APPROVED |  |  | 2023-12-04 | 15515 | 35 | Babic, Marian | -45229 | 35
105-64 | JAFURAH 380/230kV BSP (SEC) | 1640 | JAFURAH 380/230kV BSP (SEC)-INSTALLATION TOOLS FOR GIS | APPROVED | No | 2023-10-29 | Abas, Mohammed Fekry | 2023-10-29 | 2023-10-30 |  |  |  | 84290.7 | 4935 | 0 | STANDARD | Jahaz Ayed Al-Rashidi and Partner for Trad and count | SAR | 46500 | APPROVED |  |  | 2024-01-14 | 37790.7 | 76 | Babic, Marian | -45229 | 76
105-64 | JAFURAH 380/230kV BSP (SEC) | 1641 | JAFURAH 380/230kV BSP (SEC)-INSTALLATION TOOLS FOR POWER TRANSFORMER | APPROVED | No | 2023-10-29 | Abas, Mohammed Fekry | 2023-10-29 | 2023-10-30 |  |  |  | 43134.6 | 4770 | 0 | STANDARD | Jahaz Ayed Al-Rashidi and Partner for Trad and count | SAR | 26204 | APPROVED |  |  | 2023-12-04 | 16930.6 | 35 | Babic, Marian | -45229 | 35
105-64 | JAFURAH 380/230kV BSP (SEC) | 1657 | JAFURAH 380/230kV BSP (SEC)-Additional PR for GIS Rail | APPROVED | No | 2023-11-05 | Abas, Mohammed Fekry | 2023-11-07 | 2023-11-07 |  |  |  | 47750 | 4699 | 0 | STANDARD | Al Sharek Al Daem Est for Contracting | SAR | 23608.55 | APPROVED |  |  | 2023-12-11 | 24141.45 | 34 | Kumar, Mr. Ranjan | -45237 | 34
105-64 | JAFURAH 380/230kV BSP (SEC) | 1659 | JAFURAH 380/230kV BSP (SEC)-Additional PR for Pumps (PO# 4700) | APPROVED | No | 2023-11-05 | Abas, Mohammed Fekry | 2023-11-07 | 2023-11-07 |  |  |  | 26385 | 4700 | 0 | STANDARD | Al-Wabel Trading & Maintenance | SAR | 26385 | APPROVED |  |  | 2023-11-28 | 0 | 21 | Kumar, Mr. Ranjan | -45237 | 21
105-64 | JAFURAH 380/230kV BSP (SEC) | 1670 | JAFURAH 380/230kV BSP (SEC)-RECEPTACLES & SWITCHES FOR JAFURAH | APPROVED | No | 2023-11-09 | Abas, Mohammed Fekry | 2023-11-09 | 2023-11-09 |  |  |  | 137960.5 | 4715 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 137960.5 | APPROVED |  |  | 2023-11-22 | 0 | 13 | Badhman, Saeed | -45239 | 13
105-64 | JAFURAH 380/230kV BSP (SEC) | 1675 | JAFURAH 380/230kV BSP (SEC)-Removal of Waste Water and General Light Waste | APPROVED | No | 2023-11-11 | Abas, Mohammed Fekry | 2023-11-11 | 2023-11-12 |  |  |  | 57600 | 4828 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 57600 | APPROVED |  |  | 2024-01-01 | 0 | 50 | Abuhammad, Samir | -45242 | 50
105-64 | JAFURAH 380/230kV BSP (SEC) | 1676 | JAFURAH 380/230kV BSP (SEC)-Grounding Tools & Materials (Consumables) for Jafurah (Revised Offer) | APPROVED | No | 2023-11-11 | Abas, Mohammed Fekry | 2023-11-11 | 2023-11-12 |  |  |  | 198510 | 4743 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 197645 | APPROVED |  |  | 2023-11-28 | 865 | 16 | Babic, Marian | -45242 | 16
105-64 | JAFURAH 380/230kV BSP (SEC) | 1677 | JAFURAH 380/230kV BSP (SEC)-Supply of Bare Copper Conductor 240mm Sq. (Manual PO-8539) | APPROVED | No | 2023-11-12 | Abas, Mohammed Fekry | 2023-11-12 | 2023-11-12 |  |  |  | 35250 | 4737 | 0 | STANDARD | Essa Al Asmakh Trading Est. | SAR | 35250 | APPROVED |  |  | 2023-12-06 | 0 | 24 | Babic, Marian | -45242 | 24
105-64 | JAFURAH 380/230kV BSP (SEC) | 1712 | JAFURAH 380/230kV BSP (SEC)-Additional (3) days for TPI 380kV GIS LCC (PO# 4628) | APPROVED | No | 2023-11-14 | Abas, Mohammed Fekry | 2023-11-14 | 2023-11-14 |  |  |  | 15468.75 | 4628 | 1 | STANDARD | SGS GULF LIMITED | USD | 15468.75 | APPROVED |  |  | 2023-12-14 | 0 | 30 | Kumar, Mr. Ranjan | -45244 | 30
105-64 | JAFURAH 380/230kV BSP (SEC) | 1723 | JAFURAH 380/230kV BSP (SEC)-Roof Gravel and Precast Roof Tiles (Additional) | APPROVED | No | 2023-11-14 | Abas, Mohammed Fekry | 2023-11-14 | 2023-11-14 |  |  |  | 40765 | 4720 | 0 | STANDARD | Construction Expertise Est. | SAR | 40765 | APPROVED |  |  | 2023-11-23 | 0 | 9 | Kumar, Mr. Ranjan | -45244 | 9
105-64 | JAFURAH 380/230kV BSP (SEC) | 1772 | JAFURAH 380/230kV BSP (SEC)-Additional (1) day for TPI 380kV GIS LCC (PO# 4628) | APPROVED | No | 2023-11-16 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-19 |  |  |  | 5156.25 | 4628 | 1 | STANDARD | SGS GULF LIMITED | USD | 5156.25 | APPROVED |  |  | 2023-12-14 | 0 | 25 | Kumar, Mr. Ranjan | -45249 | 25
105-64 | JAFURAH 380/230kV BSP (SEC) | 1784 | JAFURAH 380/230kV BSP (SEC)-Supply of Cable Clamps (MV & HV) | APPROVED | No | 2023-11-19 | Abas, Mohammed Fekry | 2023-11-19 | 2023-11-19 |  |  |  | 75600 | 4883 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 68190.06 | APPROVED |  |  | 2024-01-03 | 7409.94 | 45 | Kumar, Mr. Ranjan | -45249 | 45
105-64 | JAFURAH 380/230kV BSP (SEC) | 1826 | JAFURAH 380/230kV BSP (SEC)-Installation of 230 kV Transformer Termination Kit | APPROVED | No | 2023-11-28 | Abas, Mohammed Fekry | 2023-11-28 | 2023-11-28 |  |  |  | 201600 | 4948 | 0 | STANDARD | BRUGG CABLES COMAPNY | SAR | 180000 | APPROVED |  |  | 2024-01-15 | 21600 | 48 | Babic, Marian | -45258 | 48
105-64 | JAFURAH 380/230kV BSP (SEC) | 1845 | JAFURAH 380/230kV BSP (SEC)-Additional Supply of Bare Copper Conductor 1Cx240mm (300 M) | APPROVED | No | 2023-11-28 | Abas, Mohammed Fekry | 2023-11-28 | 2023-11-28 |  |  |  | 35250 | 4737 | 0 | STANDARD | Essa Al Asmakh Trading Est. | SAR | 35250 | APPROVED |  |  | 2023-12-06 | 0 | 8 | Babic, Marian | -45258 | 8
105-64 | JAFURAH 380/230kV BSP (SEC) | 1848 | JAFURAH 380/230kV BSP (SEC)-Additional Supply of Bare Copper Conductor 1Cx240mm (200 M) | APPROVED | No | 2023-11-29 | Abas, Mohammed Fekry | 2023-11-29 | 2023-11-29 |  |  |  | 21400 | 4778 | 0 | STANDARD | ARABIAN RELIANCE COMPANY(S) | SAR | 21400 | APPROVED |  |  | 2023-12-06 | 0 | 7 | Babic, Marian | -45259 | 7
105-64 | JAFURAH 380/230kV BSP (SEC) | 1878 | JAFURAH 380/230kV BSP (SEC)-Additional Four (4) Days for TPI - Power & Grounding Transformer (PO# 4672) | APPROVED | No | 2023-12-03 | Abas, Mohammed Fekry | 2023-12-04 | 2023-12-05 |  |  |  | 6300 | 4672 | 1 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 6300 | APPROVED |  |  | 2023-12-10 | 0 | 5 | Kumar, Mr. Ranjan | -45265 | 5
105-64 | JAFURAH 380/230kV BSP (SEC) | 1896 | JAFURAH 380/230kV BSP (SEC)-TPI - 380kV LCC, additional courrier & administration cost (PO# 4628) | APPROVED | No | 2023-12-05 | Abas, Mohammed Fekry | 2023-12-06 | 2023-12-07 |  |  |  | 375 | 4628 | 1 | STANDARD | SGS GULF LIMITED | USD | 375 | APPROVED |  |  | 2023-12-14 | 0 | 7 | Kumar, Mr. Ranjan | -45267 | 7
105-64 | JAFURAH 380/230kV BSP (SEC) | 1951 | JAFURAH 380/230kV BSP (SEC)-Power Transformer Oil Treatment | APPROVED | No | 2023-12-13 | Abas, Mohammed Fekry | 2023-12-13 | 2023-12-13 |  |  |  | 285000 | 4884 | 0 | STANDARD | MASEERAT AL NAMA CONT.EST. | SAR | 207000 | APPROVED |  |  | 2024-01-30 | 78000 | 48 | Kumar, Mr. Ranjan | -45273 | 48
105-64 | JAFURAH 380/230kV BSP (SEC) | 1961 | JAFURAH 380/230kV BSP (SEC)-Additional PR for Waste Container & Waste Water and Sweet Water | APPROVED | No | 2023-12-14 | Abas, Mohammed Fekry | 2023-12-15 | 2023-12-17 |  |  |  | 99720 | 4828 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 79200 | APPROVED |  |  | 2024-01-01 | 20520 | 15 | Abuhammad, Samir | -45277 | 15
105-64 | JAFURAH 380/230kV BSP (SEC) | 2016 | JAFURAH 380/230kV BSP (SEC)-Supply & Delivery of Porta cabin | APPROVED | No | 2023-12-20 | Abas, Mohammed Fekry | 2023-12-20 | 2023-12-21 |  |  |  | 56150 | 4917 | 0 | STANDARD | Ahmed Essa Mohammed Al Muslim Est. | SAR | 56150 | APPROVED |  |  | 2023-12-31 | 0 | 10 | Abuhammad, Samir | -45281 | 10
105-64 | JAFURAH 380/230kV BSP (SEC) | 2021 | JAFURAH 380/230kV BSP (SEC)-Site Required Materilas (Vinyl sheet & other materials) | APPROVED | No | 2023-12-20 | Abas, Mohammed Fekry | 2023-12-24 | 2023-12-25 |  |  |  | 90310 | 4930 | 0 | STANDARD | Essa Al Asmakh Trading Est. | SAR | 84800 | APPROVED |  |  | 2024-01-11 | 5510 | 17 | Kumar, Mr. Ranjan | -45285 | 17
105-64 | JAFURAH 380/230kV BSP (SEC) | 2077 | JAFURAH 380/230kV BSP (SEC)-TPI for Gantry and Outdoor Steel Support Structures | APPROVED | No | 2024-01-02 | Abas, Mohammed Fekry | 2024-01-02 | 2024-01-02 |  |  |  | 3000 | 4997 | 0 | STANDARD | Atlas Support and Services | SAR | 6000 | APPROVED |  |  | 2024-01-31 | -3000 | 29 | Babic, Marian | -45293 | 29
105-64 | JAFURAH 380/230kV BSP (SEC) | 2079 | JAFURAH 380/230kV BSP (SEC)-Diesel for Site for 6 Months | APPROVED | No | 2024-01-02 | Abas, Mohammed Fekry | 2024-01-02 | 2024-01-04 |  |  |  | 700000 | 4953 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 697950 | APPROVED |  |  | 2024-01-28 | 2050 | 24 | Abuhammad, Samir | -45295 | 24
105-64 | JAFURAH 380/230kV BSP (SEC) | 2181 | JAFURAH 380/230kV BSP (SEC)-Transformer transportation and offloading - Jafurah | APPROVED | No | 2024-01-16 | Abas, Mohammed Fekry | 2024-01-16 | 2024-01-17 |  |  |  | 710500 | 5278 | 0 | STANDARD | Al-majdouie Logistics Company | SAR | 710500 | APPROVED |  |  | 2024-03-28 | 0 | 71 | Badhman, Saeed | -45308 | 71
105-64 | JAFURAH 380/230kV BSP (SEC) | 2249 | JAFURAH 380/230kV BSP (SEC)-Supply of cable roller for Misc. Electrical Installation works | APPROVED | No | 2024-01-22 | Abas, Mohammed Fekry | 2024-01-22 | 2024-01-22 |  |  |  | 35329 | 5012 | 0 | STANDARD | Alzain Towers Contracting Est. | SAR | 35329 | APPROVED |  |  | 2024-02-06 | 0 | 15 | Kumar, Mr. Ranjan | -45313 | 15
105-64 | JAFURAH 380/230kV BSP (SEC) | 2272 | JAFURAH 380/230kV BSP (SEC)-Gantry Installation Works | APPROVED | No | 2024-01-24 | Abas, Mohammed Fekry | 2024-01-24 | 2024-01-24 |  |  |  | 295000 | 5039 | 0 | STANDARD | Development Lines for Trading & Contracting | SAR | 295000 | APPROVED |  |  | 2024-05-05 | 0 | 102 | Basha, Syed Kafeel | -45315 | 102
105-64 | JAFURAH 380/230kV BSP (SEC) | 2279 | JAFURAH 380/230kV BSP (SEC)-PDS System for Jafurah | APPROVED | No | 2024-01-25 | Abas, Mohammed Fekry | 2024-05-07 | 2024-05-12 | 2024-04-16 |  | this PR not required, PO 5280 already issued | 450000 | 5280 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 355060 | APPROVED |  |  | 2024-04-09 | 94940 | -33 | Babic, Marian | -45424 | -33
105-64 | JAFURAH 380/230kV BSP (SEC) | 2280 | JAFURAH 380/230kV BSP (SEC)-Copper Tape | APPROVED | No | 2024-01-25 | Abas, Mohammed Fekry | 2024-01-29 | 2024-01-29 |  |  |  | 59650 | 5030 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 59650 | APPROVED |  |  | 2024-02-12 | 0 | 14 | Babic, Marian | -45320 | 14
105-64 | JAFURAH 380/230kV BSP (SEC) | 2281 | JAFURAH 380/230kV BSP (SEC)-Earthing Lugs | APPROVED | No | 2024-01-25 | Abas, Mohammed Fekry | 2024-01-29 | 2024-01-29 |  |  |  | 78427.5 | 5031 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 78427.5 | APPROVED |  |  | 2024-02-06 | 0 | 8 | Babic, Marian | -45320 | 8
105-64 | JAFURAH 380/230kV BSP (SEC) | 2325 | JAFURAH 380/230kV BSP (SEC)-MODIFICATION WORK TOOLS | APPROVED | No | 2024-01-28 | Abas, Mohammed Fekry | 2024-01-30 | 2024-01-31 |  |  |  | 121416.46 | 5116 | 0 | STANDARD | Jahaz Ayed Al-Rashidi and Partner for Trad and count | SAR | 119000 | APPROVED |  |  | 2024-03-06 | 2416.46 | 35 | Babic, Marian | -45322 | 35
105-64 | JAFURAH 380/230kV BSP (SEC) | 2327 | JAFURAH 380/230kV BSP (SEC)-Safety Requirements | APPROVED | No | 2024-01-28 | Abas, Mohammed Fekry | 2024-01-29 | 2024-01-29 |  |  |  | 15366 | 5044 | 0 | STANDARD | Coating Application Company Ltd., | SAR | 11977.5 | APPROVED |  |  | 2024-02-15 | 3388.5 | 17 | Akhtar, Farhan | -45320 | 17
105-64 | JAFURAH 380/230kV BSP (SEC) | 2342 | JAFURAH 380/230kV BSP (SEC)-Additional PR for AC/DC Panels Change Order (PO# 4521) | APPROVED | No | 2024-01-29 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 20120.76 | 4521 | 1 | STANDARD | Nour Industries Branch of Nour Communication | SAR | 20120.76 | APPROVED |  |  | 2024-02-18 | 0 | 14 | Babic, Marian | -45326 | 14
105-64 | JAFURAH 380/230kV BSP (SEC) | 2367 | JAFURAH 380/230kV BSP (SEC)-Rental of Scaffolding | APPROVED | No | 2024-01-30 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 260000 | 5117 | 0 | STANDARD | Al Batin Advanced Contracting Company Ltd. | SAR | 237726.4 | APPROVED |  |  | 2024-03-11 | 22273.6 | 36 | Babic, Marian | -45326 | 36
105-64 | JAFURAH 380/230kV BSP (SEC) | 2399 | JAFURAH 380/230kV BSP (SEC)-LIGHTING & PDMS CABLE TRAY & ACCESSORIES | APPROVED | No | 2024-02-04 | Abas, Mohammed Fekry | 2024-02-04 | 2024-02-04 |  |  |  | 440330.08 | 5077 | 0 | STANDARD | AL-AMAL ELECTRICAL SWITCHBOARDS | SAR | 440330.08 | APPROVED |  |  | 2024-03-21 | 0 | 46 | Badhman, Saeed | -45326 | 46
105-64 | JAFURAH 380/230kV BSP (SEC) | 2411 | JAFURAH 380/230kV BSP (SEC)-Additional PR for Transportation of Cable Trays to Jafurah Site | APPROVED | No | 2024-02-05 | Abas, Mohammed Fekry | 2024-02-05 | 2024-02-05 |  |  |  | 7500 | 5077 | 0 | STANDARD | AL-AMAL ELECTRICAL SWITCHBOARDS | SAR | 7500 | APPROVED |  |  | 2024-03-21 | 0 | 45 | Badhman, Saeed | -45327 | 45
105-64 | JAFURAH 380/230kV BSP (SEC) | 2487 | JAFURAH 380/230kV BSP (SEC)-Repair of Coolant Leakage for Generator | APPROVED | No | 2024-02-07 | Abas, Mohammed Fekry | 2024-02-07 | 2024-02-10 |  |  |  | 16130 | 5093 | 0 | STANDARD | SAUDI DIESEL EQUIPMENT CO.LTD | SAR | 15130.43 | APPROVED |  |  | 2024-02-27 | 999.57 | 17 | Babic, Marian | -45332 | 17
105-64 | JAFURAH 380/230kV BSP (SEC) | 2508 | JAFURAH 380/230kV BSP (SEC)-Steel Monorail for Pump Room | APPROVED | No | 2024-02-08 | Abas, Mohammed Fekry | 2024-02-09 | 2024-02-10 |  |  |  | 34000 | 5144 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 18000 | APPROVED |  |  | 2024-03-10 | 16000 | 29 | Babic, Marian | -45332 | 29
105-64 | JAFURAH 380/230kV BSP (SEC) | 2547 | JAFURAH 380/230kV BSP (SEC)-SPECIAL WASHER - For 380kV GIS outdoor support structure | APPROVED | No | 2024-02-13 | Abas, Mohammed Fekry | 2024-02-20 | 2024-02-21 |  |  |  | 39525 | 5096 | 0 | STANDARD | Al Sharek Al Daem Est for Contracting | SAR | 38734.5 | APPROVED |  |  | 2024-03-18 | 790.5 | 26 | Akhtar, Farhan | -45343 | 26
105-64 | JAFURAH 380/230kV BSP (SEC) | 2553 | JAFURAH 380/230kV BSP (SEC)-Manpower for Installation activities (fitter)- jafurah BSP | APPROVED | No | 2024-02-13 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-19 |  |  |  | 514800 | 5133 | 0 | STANDARD | Alzain Towers Contracting Est. | SAR | 514800 | APPROVED |  |  | 2024-03-21 | 0 | 31 | Babic, Marian | -45341 | 31
105-64 | JAFURAH 380/230kV BSP (SEC) | 2554 | JAFURAH 380/230kV BSP (SEC)-Manpower for Installation activities (Labours)- jafurah BSP | APPROVED | No | 2024-02-13 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-19 |  |  |  | 202800 | 5133 | 0 | STANDARD | Alzain Towers Contracting Est. | SAR | 202800 | APPROVED |  |  | 2024-03-21 | 0 | 31 | Babic, Marian | -45341 | 31
105-64 | JAFURAH 380/230kV BSP (SEC) | 2559 | JAFURAH 380/230kV BSP (SEC)-Bus Service on Rent - Jafurah BSP | APPROVED | No | 2024-02-13 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-19 |  |  |  | 136000 | 5126 | 0 | STANDARD | Al Arabiya For Operational Solutions | SAR | 112000 | APPROVED |  |  | 2024-03-17 | 24000 | 27 | Abuhammad, Samir | -45341 | 27
105-64 | JAFURAH 380/230kV BSP (SEC) | 2562 | JAFURAH 380/230kV BSP (SEC)-Dry Air Cylinder on Rental- Jafurah BSP | APPROVED | No | 2024-02-14 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-18 |  |  |  | 24000 | 5413 | 0 | STANDARD | Nauras Al- Sharq Industrial Gas Factory | SAR | 11200 | APPROVED |  |  | 2024-04-28 | 12800 | 70 | Muhammad, Muhammad Atif | -45340 | 70
105-64 | JAFURAH 380/230kV BSP (SEC) | 2689 | JAFURAH 380/230kV BSP (SEC)-Supply of Cable Glands | APPROVED | No | 2024-02-26 | Abas, Mohammed Fekry | 2024-02-26 | 2024-02-28 |  |  |  | 19912.52 | 5202 | 0 | STANDARD | Ahmed Essa Mohammed Al Muslim Est. | SAR | 19865.7 | APPROVED |  |  | 2024-03-18 | 46.82 | 19 | Babic, Marian | -45350 | 19
105-64 | JAFURAH 380/230kV BSP (SEC) | 2690 | JAFURAH 380/230kV BSP (SEC)-Supply of Heat Shrinkable Sleeves | APPROVED | No | 2024-02-26 | Abas, Mohammed Fekry | 2024-02-26 | 2024-02-28 |  |  |  | 8089.6 | 5202 | 0 | STANDARD | Ahmed Essa Mohammed Al Muslim Est. | SAR | 8089.6 | APPROVED |  |  | 2024-03-18 | 0 | 19 | Babic, Marian | -45350 | 19
105-64 | JAFURAH 380/230kV BSP (SEC) | 2691 | JAFURAH 380/230kV BSP (SEC)-Supply of Cable Ties | APPROVED | No | 2024-02-26 | Abas, Mohammed Fekry | 2024-02-26 | 2024-02-28 |  |  |  | 20597.4 | 5202 | 0 | STANDARD | Ahmed Essa Mohammed Al Muslim Est. | SAR | 20597.4 | APPROVED |  |  | 2024-03-18 | 0 | 19 | Babic, Marian | -45350 | 19
105-64 | JAFURAH 380/230kV BSP (SEC) | 2694 | JAFURAH 380/230kV BSP (SEC)-Supply of Cable Lugs | APPROVED | No | 2024-02-26 | Abas, Mohammed Fekry | 2024-02-26 | 2024-02-28 |  |  |  | 48473 | 5202 | 0 | STANDARD | Ahmed Essa Mohammed Al Muslim Est. | SAR | 48473 | APPROVED |  |  | 2024-03-18 | 0 | 19 | Babic, Marian | -45350 | 19
105-64 | JAFURAH 380/230kV BSP (SEC) | 2779 | JAFURAH 380/230kV BSP (SEC)-Supply of Welding Powder | APPROVED | No | 2024-03-05 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 130900 | 5230 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 126500 | APPROVED |  |  | 2024-03-25 | 4400 | 18 | Babic, Marian | -45358 | 18
105-64 | JAFURAH 380/230kV BSP (SEC) | 2814 | JAFURAH 380/230kV BSP (SEC)-Supply of Stationaries for T&C | APPROVED | No | 2024-03-12 | Abas, Mohammed Fekry | 2024-03-12 | 2024-03-12 |  |  |  | 28507 | 5288 | 0 | STANDARD | Ahmed Essa Mohammed Al Muslim Est. | SAR | 20017 | APPROVED |  |  | 2024-03-31 | 8490 | 19 | Kumar, Mr. Ranjan | -45363 | 19
105-64 | JAFURAH 380/230kV BSP (SEC) | 2846 | JAFURAH 380/230kV BSP (SEC)-Additional tunnel Doors, hardware supply & Installation- Jafurah BSP | APPROVED | No | 2024-03-19 | Abas, Mohammed Fekry | 2024-03-23 | 2024-03-24 |  |  |  | 60000 | 4445 | 1 | STANDARD | Saudi Prefeb House Factory | SAR | 59141.5 | APPROVED |  |  | 2024-05-26 | 858.5 | 63 | Kumar, Mr. Ranjan | -45375 | 63
105-64 | JAFURAH 380/230kV BSP (SEC) | 2848 | JAFURAH 380/230kV BSP (SEC)-Additional PR for Scaffolding | APPROVED | No | 2024-03-19 | Abas, Mohammed Fekry | 2024-03-19 | 2024-03-24 |  |  |  | 42138 | 5293 | 0 | STANDARD | Al Batin Advanced Contracting Company Ltd. | SAR | 42062 | APPROVED |  |  | 2024-04-04 | 76 | 11 | Babic, Marian | -45375 | 11
105-64 | JAFURAH 380/230kV BSP (SEC) | 2902 | JAFURAH 380/230kV BSP (SEC)-Manpower for Cable Pulling & Termination works | APPROVED | No | 2024-03-26 | Abas, Mohammed Fekry | 2024-03-28 | 2024-03-28 |  |  |  | 2000000 | 5275 | 0 | STANDARD | MASEERAT AL NAMA CONT.EST. | SAR | 2000000 | APPROVED |  |  | 2024-05-06 | 0 | 39 | Kumar, Mr. Ranjan | -45379 | 39
105-64 | JAFURAH 380/230kV BSP (SEC) | 2946 | JAFURAH 380/230kV BSP (SEC)-C Channel and other items | APPROVED | No | 2024-03-30 | Abas, Mohammed Fekry | 2024-03-31 | 2024-03-31 |  |  |  | 62295 | 5316 | 0 | STANDARD | Jahaz Ayed Al-Rashidi and Partner for Trad and count | SAR | 89985 | APPROVED |  |  | 2024-04-06 | -27690 | 6 | Babic, Marian | -45382 | 6
105-64 | JAFURAH 380/230kV BSP (SEC) | 2947 | JAFURAH 380/230kV BSP (SEC)-Panel Baseframe Material | APPROVED | No | 2024-03-30 | Abas, Mohammed Fekry | 2024-03-31 | 2024-03-31 |  |  |  | 36620 | 5316 | 0 | STANDARD | Jahaz Ayed Al-Rashidi and Partner for Trad and count | SAR | 84915 | APPROVED |  |  | 2024-04-06 | -48295 | 6 | Babic, Marian | -45382 | 6
105-64 | JAFURAH 380/230kV BSP (SEC) | 2954 | JAFURAH 380/230kV BSP (SEC)-New PR for Steel Monorail for Pump Room | APPROVED | No | 2024-03-31 | Abas, Mohammed Fekry | 2024-04-01 | 2024-04-02 |  |  |  | 34000 | 5416 | 0 | STANDARD | Construction Expertise Est. | SAR | 30000 | APPROVED |  |  | 2024-05-08 | 4000 | 36 | Babic, Marian | -45384 | 36
105-64 | JAFURAH 380/230kV BSP (SEC) | 2960 | JAFURAH 380/230kV BSP (SEC)-Supply & Installation of pole mounted Sign board incl.Transporation. | APPROVED | No | 2024-04-01 | Abas, Mohammed Fekry | 2024-04-03 | 2024-04-04 |  |  |  | 37500 | 5572 | 0 | STANDARD | Brand Cube (S) | SAR | 37500 | APPROVED |  |  | 2024-05-26 | 0 | 52 | Babic, Marian | -45386 | 52
105-64 | JAFURAH 380/230kV BSP (SEC) | 3011 | JAFURAH 380/230kV BSP (SEC)-Type V and Type IV Fence | APPROVED | No | 2024-04-08 | Abas, Mohammed Fekry | 2024-04-10 | 2024-04-15 |  |  |  | 281400 | 5520 | 0 | STANDARD | ABDUL JABBAR AHMAD ALI SHARAHILI CONTRACTING EST. (AJASCO) | SAR | 268800 | APPROVED |  |  | 2024-05-23 | 12600 | 38 | Kumar, Mr. Ranjan | -45397 | 38
105-64 | JAFURAH 380/230kV BSP (SEC) | 3034 | JAFURAH 380/230kV BSP (SEC)-Jafurah Camp - Ramadan Food 2024 | APPROVED | No | 2024-04-16 | Abas, Mohammed Fekry | 2024-12-12 | 2024-12-15 | 2024-07-29 |  | As informed via email. PR is already more than 60 days old, Please issue the PR once one vendor memo is approved. | 42698 | 6723 | 0 | STANDARD | World Green Engineering & Contracting Company | SAR | 42698 | APPROVED |  |  | 2025-01-15 | 0 | 31 | Kumar, Mr. Ranjan | -45641 | 31
105-64 | JAFURAH 380/230kV BSP (SEC) | 3297 | JAFURAH 380/230kV BSP (SEC)-Additional PR for Steel works (PO# 4556) | APPROVED | No | 2024-05-05 | Abas, Mohammed Fekry | 2024-05-06 | 2024-05-06 |  |  |  | 399250.4 | 4556 | 1 | STANDARD | Al Sharek Al Daem Est for Contracting | SAR | 399250.4 | APPROVED |  |  | 2024-06-26 | 0 | 51 | Babic, Marian | -45418 | 51
105-64 | JAFURAH 380/230kV BSP (SEC) | 3300 | JAFURAH 380/230kV BSP (SEC)-Additional PR for Security Guards (PO# 4394) - 6 months | APPROVED | No | 2024-05-05 | Abas, Mohammed Fekry | 2024-05-06 | 2024-05-06 |  |  |  | 234000 | 4394 | 1 | STANDARD | Amnalawtan Security Company for civil security Guards | SAR | 234000 | APPROVED |  |  | 2024-05-26 | 0 | 20 | Abuhammad, Samir | -45418 | 20
105-64 | JAFURAH 380/230kV BSP (SEC) | 3311 | JAFURAH 380/230kV BSP (SEC)-Additional PR for Dry Air Cylinder (PO# 5413) | APPROVED | No | 2024-05-06 | Abas, Mohammed Fekry | 2024-05-06 | 2024-05-12 |  |  |  | 30000 | 5546 | 0 | STANDARD | Nauras Al- Sharq Industrial Gas Factory | SAR | 30000 | APPROVED |  |  | 2024-05-26 | 0 | 14 | Muhammad, Muhammad Atif | -45424 | 14
105-64 | JAFURAH 380/230kV BSP (SEC) | 3397 | JAFURAH 380/230kV BSP (SEC)-for Additional Supply of Sweet Water (PO# 4394) | APPROVED | No | 2024-05-14 | Abas, Mohammed Fekry | 2024-05-14 | 2024-05-14 |  |  |  | 3632 | 4428 | 1 | STANDARD | HAMED ABDULLAH MOHAMMED AL-ALAWI FUEL CORPORATION | SAR | 3360 | APPROVED |  |  | 2024-05-27 | 272 | 13 | Eranhikkal, Mr. Riyaz Mohammed | -45426 | 13
105-64 | JAFURAH 380/230kV BSP (SEC) | 3492 | JAFURAH 380/230kV BSP (SEC)-Additional PR for Steel works for (PO# 4556) | APPROVED | No | 2024-05-27 | Abas, Mohammed Fekry | 2024-06-02 | 2024-06-03 |  |  |  | 40000 | 4556 | 1 | STANDARD | Al Sharek Al Daem Est for Contracting | SAR | 40000 | APPROVED |  |  | 2024-06-26 | 0 | 23 | Babic, Marian | -45446 | 23
105-64 | JAFURAH 380/230kV BSP (SEC) | 3496 | JAFURAH 380/230kV BSP (SEC)-Optional Scope for PDS (PO# 5280) | APPROVED | No | 2024-05-27 | Abas, Mohammed Fekry | 2024-05-27 | 2024-05-27 |  |  |  | 85652 | 5280 | 1 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 85652 | APPROVED |  |  | 2024-06-30 | 0 | 34 | Babic, Marian | -45439 | 34
105-64 | JAFURAH 380/230kV BSP (SEC) | 3541 | JAFURAH 380/230kV BSP (SEC)-Cable Lugs & Glands | APPROVED | No | 2024-05-30 | Abas, Mohammed Fekry | 2024-05-30 | 2024-05-31 |  |  |  | 135009.19 | 5675 | 0 | STANDARD | Jahaz Ayed Al-Rashidi and Partner for Trad and count | SAR | 135000.03 | APPROVED |  |  | 2024-07-10 | 9.16 | 40 | Kumar, Mr. Ranjan | -45443 | 40
105-64 | JAFURAH 380/230kV BSP (SEC) | 3582 | JAFURAH 380/230kV BSP (SEC)-Genset Rental for 6 months | APPROVED | No | 2024-06-03 | Abas, Mohammed Fekry | 2024-06-11 | 2024-06-11 |  |  |  | 38700 | 5731 | 0 | STANDARD | Nour Communications Co. | SAR | 72000 | APPROVED |  |  | 2024-06-26 | -33300 | 15 | Akhtar, Farhan | -45454 | 15
105-64 | JAFURAH 380/230kV BSP (SEC) | 3618 | JAFURAH 380/230kV BSP (SEC)-DILO MACHINE DN20 HOSE-ASSET | APPROVED | No | 2024-06-06 | Abas, Mohammed Fekry | 2024-06-11 | 2024-06-11 |  |  |  | 23000 | 5750 | 0 | STANDARD | CIVIL ELECT.PROJECTS CONTG.CO | SAR | 22000 | APPROVED |  |  | 2024-07-02 | 1000 | 21 | Kumar, Mr. Ranjan | -45454 | 21
105-64 | JAFURAH 380/230kV BSP (SEC) | 3623 | JAFURAH 380/230kV BSP (SEC)-Miscellaneous Hardware, Tools & Accessories | APPROVED | No | 2024-06-09 | Abas, Mohammed Fekry | 2024-06-10 | 2024-06-10 |  |  |  | 171850.54 | 5691 | 0 | STANDARD | Ahmed Essa Mohammed Al Muslim Est. | SAR | 171850.54 | APPROVED |  |  | 2024-07-25 | 0 | 45 | Kumar, Mr. Ranjan | -45453 | 45
105-64 | JAFURAH 380/230kV BSP (SEC) | 3807 | JAFURAH 380/230kV BSP (SEC)-SCAFFOLDING FOR 380KV GIB INSTALLATION WORK | APPROVED | No | 2024-07-09 | Abas, Mohammed Fekry | 2024-07-09 | 2024-07-10 |  |  |  | 16424 | 5801 | 0 | STANDARD | Al Batin Advanced Contracting Company Ltd. | SAR | 16424 | APPROVED |  |  | 2024-07-12 | 0 | 2 | Babic, Marian | -45483 | 2
105-64 | JAFURAH 380/230kV BSP (SEC) | 3888 | JAFURAH 380/230kV BSP (SEC)-CABLE GLANDS, LUGS, TIES & SLEEVES (SHORTFALL MATERIALS) | APPROVED | No | 2024-07-14 | Abas, Mohammed Fekry | 2024-07-14 | 2024-07-14 |  |  |  | 40000 | 5814 | 0 | STANDARD | Jahaz Ayed Al-Rashidi and Partner for Trad and count | SAR | 40000 | APPROVED |  |  | 2024-07-18 | 0 | 4 | Kumar, Mr. Ranjan | -45487 | 4
105-64 | JAFURAH 380/230kV BSP (SEC) | 3888 | JAFURAH 380/230kV BSP (SEC)-CABLE GLANDS, LUGS, TIES & SLEEVES (SHORTFALL MATERIALS) | APPROVED | No | 2024-07-14 | Abas, Mohammed Fekry | 2024-07-14 | 2024-07-14 |  |  |  | 40000 | 6173 | 0 | STANDARD | Jahaz Ayed Al-Rashidi and Partner for Trad and count | SAR | 40000 | APPROVED |  |  | 2024-09-16 | 0 | 64 | Kumar, Mr. Ranjan | -45487 | 64
105-64 | JAFURAH 380/230kV BSP (SEC) | 3938 | JAFURAH 380/230kV BSP (SEC)-LIGHTING SWITCHES & PUSH BUTTONS | RETURNED | No | 2024-07-16 | Kumar, Mr. Ranjan | 2024-09-09 | 2024-07-21 | 2024-09-09 |  | Po for switches PO 6105 is issued, Please submit the PR push button technical details are approved. | 15000 | 6105 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 2770.45 | APPROVED |  |  | 2024-09-05 | 12229.55 |  | Kumar, Mr. Ranjan | -45494 | 46
105-64 | JAFURAH 380/230kV BSP (SEC) | 3951 | JAFURAH 380/230kV BSP (SEC)-Extension of Site Internet at Jafurah Site (12-months, PO#4313) | APPROVED | No | 2024-07-18 | Abas, Mohammed Fekry | 2024-07-21 | 2024-07-22 |  |  |  | 270000 | 4313 | 1 | STANDARD | INTERNATIONAL SUPPLY INFORMATION TECHNOLOGY | SAR | 270000 | APPROVED |  |  | 2024-09-16 | 0 | 56 | Kumar, Mr. Ranjan | -45495 | 56
105-64 | JAFURAH 380/230kV BSP (SEC) | 3952 | JAFURAH 380/230kV BSP (SEC)-Extension of Site Internet at Jafurah Camp (12-months, PO#4313) | APPROVED | No | 2024-07-18 | Abas, Mohammed Fekry | 2024-07-21 | 2024-07-22 |  |  |  | 270000 | 4313 | 1 | STANDARD | INTERNATIONAL SUPPLY INFORMATION TECHNOLOGY | SAR | 270000 | APPROVED |  |  | 2024-09-16 | 0 | 56 | Kumar, Mr. Ranjan | -45495 | 56
105-64 | JAFURAH 380/230kV BSP (SEC) | 3993 | JAFURAH 380/230kV BSP (SEC)-Water cooler at Jafurah Site | APPROVED | No | 2024-07-23 | Abas, Mohammed Fekry | 2024-07-24 | 2024-07-25 |  |  |  | 8160 | 5868 | 0 | STANDARD | Jahaz Ayed Al-Rashidi and Partner for Trad and count | SAR | 8160 | APPROVED |  |  | 2024-08-06 | 0 | 12 | Akhtar, Farhan | -45498 | 12
105-64 | JAFURAH 380/230kV BSP (SEC) | 3994 | JAFURAH 380/230kV BSP (SEC)-Supply and Delivery of Porta Cabin (3x3) | APPROVED | No | 2024-07-24 | Abas, Mohammed Fekry | 2024-07-24 | 2024-07-25 |  |  |  | 21400 | 5928 | 0 | STANDARD | Ahmed Essa Mohammed Al Muslim Est. | SAR | 18400 | APPROVED |  |  | 2024-08-27 | 3000 | 33 | Akhtar, Farhan | -45498 | 33
105-64 | JAFURAH 380/230kV BSP (SEC) | 4128 | JAFURAH 380/230kV BSP (SEC)-Power Transformers Oil Analysis Test | APPROVED | No | 2024-08-11 | Abas, Mohammed Fekry | 2024-08-12 | 2024-08-13 |  |  |  | 43353 | 6107 | 0 | STANDARD | Energy Distributor Co. Ltd | SAR | 41308 | APPROVED |  |  | 2024-09-05 | 2045 | 23 | Kumar, Mr. Ranjan | -45517 | 23
105-64 | JAFURAH 380/230kV BSP (SEC) | 4162 | JAFURAH 380/230kV BSP (SEC)-Equipment Rent of Another 350kVA Genset, 6 months (Including Local Transportation) | APPROVED | No | 2024-08-15 | Abas, Mohammed Fekry | 2024-08-17 | 2024-08-17 |  |  |  | 60850 | 6010 | 0 | STANDARD | SUDHIR EQUIPMENT RENTAL COMPANY | SAR | 36500 | APPROVED |  |  | 2024-08-27 | 24350 | 10 | Akhtar, Farhan | -45521 | 10
105-64 | JAFURAH 380/230kV BSP (SEC) | 4215 | JAFURAH 380/230kV BSP (SEC)-JABCO Variation Order- Civil works | APPROVED | No | 2024-08-19 | Abas, Mohammed Fekry | 2024-08-24 | 2024-08-25 |  |  |  | 10263506.19 | 4389 | 1 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 10263506.19 | APPROVED |  |  | 2024-09-17 | 0 | 23 | Babic, Marian | -45529 | 23
105-64 | JAFURAH 380/230kV BSP (SEC) | 4216 | JAFURAH 380/230kV BSP (SEC)-Asphalt works- Jafurah BSP | APPROVED | No | 2024-08-19 | Abas, Mohammed Fekry | 2024-08-22 | 2024-08-22 |  |  |  | 5831850 | 6052 | 0 | STANDARD | Al Samah Est. for General Contracting | SAR | 5831850 | APPROVED |  |  | 2024-08-29 | 0 | 7 | Kumar, Mr. Ranjan | -45526 | 7
105-64 | JAFURAH 380/230kV BSP (SEC) | 4218 | JAFURAH 380/230kV BSP (SEC)-Testing & Commissioning for Jafurah (ApprovedManual PO# 5211) | APPROVED | No | 2024-08-19 | Abas, Mohammed Fekry | 2024-08-22 | 2024-08-22 |  |  |  | 2920267 | 5211 | 0 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 2920267 | APPROVED |  |  | 2024-08-28 | 0 | 6 | Babic, Marian | -45526 | 6
105-64 | JAFURAH 380/230kV BSP (SEC) | 4219 | JAFURAH 380/230kV BSP (SEC)-Additional 240mm SQ. Bare Copper Conductor (3,500m) | APPROVED | No | 2024-08-19 | Abas, Mohammed Fekry | 2024-08-22 | 2024-08-22 |  |  |  | 289511.6 | 6051 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 264159.7 | APPROVED |  |  | 2024-10-17 | 25351.9 | 56 | Kumar, Mr. Ranjan | -45526 | 56
105-64 | JAFURAH 380/230kV BSP (SEC) | 4220 | JAFURAH 380/230kV BSP (SEC)-Supply and apply cable coating MVL for 230kV, 1X2500mm2 power cable and 13.8kV , 1X185mm2 power cable | APPROVED | No | 2024-08-19 | Abas, Mohammed Fekry | 2024-08-22 | 2024-08-22 |  |  |  | 228890 | 6054 | 0 | STANDARD | Construction Expertise Est. | SAR | 218803 | APPROVED |  |  | 2024-09-26 | 10087 | 35 | Abdulqader, Ahmed Abdulhalim | -45526 | 35
105-64 | JAFURAH 380/230kV BSP (SEC) | 4223 | JAFURAH 380/230kV BSP (SEC)-Galvanized steel PVC coated conduit, U-Bolt & Cap | APPROVED | No | 2024-08-20 | Abas, Mohammed Fekry | 2024-08-22 | 2024-08-22 |  |  |  | 19150 | 6053 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 19150 | APPROVED |  |  | 2024-08-27 | 0 | 5 | Kumar, Mr. Ranjan | -45526 | 5
105-64 | JAFURAH 380/230kV BSP (SEC) | 4224 | JAFURAH 380/230kV BSP (SEC)-General back fill- PO change order- M/s Radi | APPROVED | No | 2024-08-20 | Abas, Mohammed Fekry | 2024-08-22 | 2024-08-22 |  |  |  | 960000 | 4345 | 1 | STANDARD | RADI AHMED AL MANHAL CO. LTD | SAR | 960000 | APPROVED |  |  | 2024-09-04 | 0 | 13 | Kumar, Mr. Ranjan | -45526 | 13
105-64 | JAFURAH 380/230kV BSP (SEC) | 4265 | JAFURAH 380/230kV BSP (SEC)-3rd Party Lab Test (Additional PR for PO# 4403) | APPROVED | No | 2024-08-25 | Abas, Mohammed Fekry | 2024-08-28 | 2024-09-01 |  |  |  | 64000 | 4403 | 1 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 64000 | APPROVED |  |  | 2024-09-18 | 0 | 17 | Kumar, Mr. Ranjan | -45536 | 17
105-64 | JAFURAH 380/230kV BSP (SEC) | 4272 | JAFURAH 380/230kV BSP (SEC)-PO#4308 Excvation PO | APPROVED | No | 2024-08-26 | Abas, Mohammed Fekry | 2024-08-28 | 2024-09-01 |  |  |  | 365505 | 4308 | 2 | STANDARD | RADI AHMED AL MANHAL CO. LTD | SAR | 365505 | APPROVED |  |  | 2024-09-16 | 0 | 15 | Kumar, Mr. Ranjan | -45536 | 15
105-64 | JAFURAH 380/230kV BSP (SEC) | 4273 | JAFURAH 380/230kV BSP (SEC)-PO#4393WATERPROOFING WORKS | APPROVED | No | 2024-08-26 | Abas, Mohammed Fekry | 2024-08-28 | 2024-09-01 |  |  |  | 283455 | 4393 | 2 | STANDARD | ISAM kabbani & partners for construction & maintenance co.LTD | SAR | 283455 | APPROVED |  |  | 2024-09-17 | 0 | 16 | Kumar, Mr. Ranjan | -45536 | 16
105-64 | JAFURAH 380/230kV BSP (SEC) | 4278 | JAFURAH 380/230kV BSP (SEC)-DILO MACHINE, HOSE & ADAPTER ON MONTHLY RENTAL BASIS | APPROVED | No | 2024-08-27 | Abas, Mohammed Fekry | 2024-08-27 | 2024-08-27 |  |  |  | 30000 | 6096 | 0 | STANDARD | Jahaz Ayed Al-Rashidi and Partner for Trad and count | SAR | 30000 | APPROVED |  |  | 2024-09-03 | 0 | 7 | Kumar, Mr. Ranjan | -45531 | 7
105-64 | JAFURAH 380/230kV BSP (SEC) | 4281 | JAFURAH 380/230kV BSP (SEC)-Select fill revised HCIS quantity- Jafurah BSP(PO4377) | APPROVED | No | 2024-08-27 | Abas, Mohammed Fekry | 2024-08-28 | 2024-09-01 |  |  |  | 97980 | 4337 | 2 | STANDARD | RADI AHMED AL MANHAL CO. LTD | SAR | 97980 | APPROVED |  |  | 2024-09-18 | 0 | 17 | Kumar, Mr. Ranjan | -45536 | 17
105-64 | JAFURAH 380/230kV BSP (SEC) | 4306 | JAFURAH 380/230kV BSP (SEC)-Supply and Delivery of Bolts & Nuts | APPROVED | No | 2024-08-29 | Abas, Mohammed Fekry | 2024-08-29 | 2024-09-01 |  |  |  | 9100 | 6108 | 0 | STANDARD | Branch AL-Khamisain Hardware Trading Co.(S) | SAR | 9011.5 | APPROVED |  |  | 2024-09-10 | 88.5 | 9 | Abuhammad, Samir | -45536 | 9
105-64 | JAFURAH 380/230kV BSP (SEC) | 4334 | JAFURAH 380/230kV BSP (SEC)-Additional PR for PO# 4930-Supply of Temporary Vinyl Carpet | APPROVED | No | 2024-09-02 | Abas, Mohammed Fekry | 2024-09-03 | 2024-09-04 |  |  |  | 1060 | 4930 | 1 | STANDARD | Essa Al Asmakh Trading Est. | SAR | 1060 | APPROVED |  |  | 2024-12-04 | 0 | 91 | Kumar, Mr. Ranjan | -45539 | 91
105-64 | JAFURAH 380/230kV BSP (SEC) | 4381 | JAFURAH 380/230kV BSP (SEC)-Bolts and Nuts for GIS Steel Structure | APPROVED | No | 2024-09-05 | Abas, Mohammed Fekry | 2024-09-09 | 2024-09-09 |  |  |  | 8907.5 | 6163 | 0 | STANDARD | Jahaz Ayed Al-Rashidi and Partner for Trad and count | SAR | 8907.5 | APPROVED |  |  | 2024-10-29 | 0 | 50 | Abuhammad, Samir | -45544 | 50
105-64 | JAFURAH 380/230kV BSP (SEC) | 4406 | JAFURAH 380/230kV BSP (SEC)-Additional PR for DGA (Desolve Gas Analizer) - Power Transformer | APPROVED | No | 2024-09-11 | Abas, Mohammed Fekry | 2024-09-12 | 2024-09-14 |  |  |  | 112500 | 4502 | 1 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 112500 | APPROVED |  |  | 2024-10-09 | 0 | 25 | Kumar, Mr. Ranjan | -45549 | 25
105-64 | JAFURAH 380/230kV BSP (SEC) | 4420 | JAFURAH 380/230kV BSP (SEC)-Mobilization & De-mobilization of Engineer for DGA (Desolve Gas Analizer) | APPROVED | No | 2024-09-12 | Abas, Mohammed Fekry | 2024-09-12 | 2024-09-14 |  |  |  | 11250 | 4502 | 1 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 11250 | APPROVED |  |  | 2024-10-09 | 0 | 25 | Kumar, Mr. Ranjan | -45549 | 25
105-64 | JAFURAH 380/230kV BSP (SEC) | 4422 | JAFURAH 380/230kV BSP (SEC)-HV Test bushing, gassing and degassing services | APPROVED | No | 2024-09-12 | Abas, Mohammed Fekry | 2024-09-12 | 2024-09-14 |  |  |  | 226000 | 6352 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 105500 | APPROVED |  |  | 2024-11-05 | 120500 | 52 | Babic, Marian | -45549 | 52
105-64 | JAFURAH 380/230kV BSP (SEC) | 4551 | JAFURAH 380/230kV BSP (SEC)-Security System - HCIS Class-1 | APPROVED | No | 2024-09-29 | Abas, Mohammed Fekry | 2024-09-29 | 2024-09-30 |  |  |  | 8998261 | 5271 | 0 | STANDARD | CEGELEC NETWORK AND SECURITY SYSTEMS | SAR | 8998261 | APPROVED |  |  | 2024-10-01 | 0 | 1 | Kumar, Mr. Ranjan | -45565 | 1
105-64 | JAFURAH 380/230kV BSP (SEC) | 4564 | JAFURAH 380/230kV BSP (SEC)-Additional LV Power Cables 1x300mm & 1x240mm (PO# 6198) | APPROVED | No | 2024-09-30 | Abas, Mohammed Fekry | 2024-10-08 | 2024-10-08 |  |  |  | 98775 | 6198 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 98775 | APPROVED |  |  | 2024-10-13 | 0 | 5 | Kumar, Mr. Ranjan | -45573 | 5
105-64 | JAFURAH 380/230kV BSP (SEC) | 4585 | JAFURAH 380/230kV BSP (SEC)-Rental Manpower- AEMCO | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-09 |  |  |  | 270000 | 6433 | 0 | STANDARD | Ahmed Essa Mohammed Al Muslim Est. | SAR | 270000 | APPROVED |  |  | 2024-12-17 | 0 | 69 | Babic, Marian | -45574 | 69
105-64 | JAFURAH 380/230kV BSP (SEC) | 4798 | JAFURAH 380/230kV BSP (SEC)-Equipment Rent - 300kVA Genset, 6 months (Including Local Transportation) | APPROVED | No | 2024-10-27 | Abas, Mohammed Fekry | 2024-10-28 | 2024-10-28 |  |  |  | 60850 | 6463 | 0 | STANDARD | SAUDI DIESEL EQUIPMENT CO.LTD | SAR | 59600 | APPROVED |  |  | 2024-12-18 | 1250 | 51 | Akhtar, Farhan | -45593 | 51
105-64 | JAFURAH 380/230kV BSP (SEC) | 4881 | JAFURAH 380/230kV BSP (SEC)-Optical Fiber Amplifier (OFA) - Manual PO# 8393 Approved | APPROVED | No | 2024-11-10 | Abas, Mohammed Fekry | 2024-11-13 | 2024-11-13 |  |  |  | 1491500 | 6533 | 0 | STANDARD | BAUD TELECOM COMPANY | SAR | 1491500 | APPROVED |  |  | 2024-12-10 | 0 | 27 | Kumar, Mr. Ranjan | -45609 | 27
105-64 | JAFURAH 380/230kV BSP (SEC) | 5018 | JAFURAH 380/230kV BSP (SEC)-Fire Hydrant Trench (PO8625) | APPROVED | No | 2024-11-21 | Abas, Mohammed Fekry | 2024-11-24 | 2024-11-24 |  |  |  | 2462721.3 | 6604 | 0 | STANDARD | JEDDAH AOIMS CONTRACTING COMPANY | SAR | 2462721.3 | APPROVED |  |  | 2024-12-16 | 0 | 22 | Kumar, Mr. Ranjan | -45620 | 22
105-64 | JAFURAH 380/230kV BSP (SEC) | 5019 | JAFURAH 380/230kV BSP (SEC)-GIS C05 GIB (8098-1) | APPROVED | No | 2024-11-21 | Abas, Mohammed Fekry | 2024-11-24 | 2024-11-24 |  |  |  | 208000 | 4400 | 1 | STANDARD | Hitachi Energy Ltd | SAR | 208000 | APPROVED |  |  | 2024-12-24 | 0 | 30 | Kumar, Mr. Ranjan | -45620 | 30
105-64 | JAFURAH 380/230kV BSP (SEC) | 5020 | JAFURAH 380/230kV BSP (SEC)-Indication Lamps & Terminal Blocks (Manul PO 7862) | APPROVED | No | 2024-11-21 | Abas, Mohammed Fekry | 2024-11-24 | 2024-11-24 |  |  |  | 32699 | 6575 | 0 | STANDARD | Essa Al Asmakh Trading Est. | SAR | 32699 | APPROVED |  |  | 2024-12-04 | 0 | 10 | Abuhammad, Samir | -45620 | 10
105-64 | JAFURAH 380/230kV BSP (SEC) | 5021 | JAFURAH 380/230kV BSP (SEC)-Rental of Scafflolding -3 months (PO#7863) | APPROVED | No | 2024-11-21 | Abas, Mohammed Fekry | 2024-11-24 | 2024-11-24 |  |  |  | 31546.5 | 6550 | 0 | STANDARD | Al Batin Advanced Contracting Company Ltd. | SAR | 31545 | APPROVED |  |  | 2024-11-27 | 1.5 | 3 | Abuhammad, Samir | -45620 | 3
105-64 | JAFURAH 380/230kV BSP (SEC) | 5022 | JAFURAH 380/230kV BSP (SEC)-Additional for Security Guards, PO# 4394 | APPROVED | No | 2024-11-21 | Abas, Mohammed Fekry | 2024-11-24 | 2024-11-24 |  |  |  | 117000 | 4394 | 2 | STANDARD | Amnalawtan Security Company for civil security Guards | SAR | 117000 | APPROVED |  |  | 2025-01-14 | 0 | 51 | Abuhammad, Samir | -45620 | 51
105-64 | JAFURAH 380/230kV BSP (SEC) | 5023 | JAFURAH 380/230kV BSP (SEC)-Waste water Management (4820) | APPROVED | No | 2024-11-21 | Abas, Mohammed Fekry | 2024-11-24 | 2024-11-24 |  |  |  | 88000 | 4828 | 1 | STANDARD | Cebent for General Cont. Est. | SAR | 88000 | APPROVED |  |  | 2024-12-29 | 0 | 35 | Abuhammad, Samir | -45620 | 35
105-64 | JAFURAH 380/230kV BSP (SEC) | 5029 | JAFURAH 380/230kV BSP (SEC)-Additional amounts for BUS Rental (PO# 5126) | APPROVED | No | 2024-11-23 | Abas, Mohammed Fekry | 2024-11-24 | 2024-11-24 |  |  |  | 130000 | 5126 | 1 | STANDARD | Al Arabiya For Operational Solutions | SAR | 129869 | APPROVED |  |  | 2025-02-20 | 131 | 88 | Abuhammad, Samir | -45620 | 88
105-64 | JAFURAH 380/230kV BSP (SEC) | 5055 | JAFURAH 380/230kV BSP (SEC)-Additional LV Power & Control Cables, (PO# 6485) | APPROVED | No | 2024-11-26 | Abas, Mohammed Fekry | 2024-11-28 | 2024-11-28 |  |  |  | 345300 | 6485 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 345300 | APPROVED |  |  | 2024-12-15 | 0 | 17 | Babic, Marian | -45624 | 17
105-64 | JAFURAH 380/230kV BSP (SEC) | 5067 | JAFURAH 380/230kV BSP (SEC)-Additional Amounts for Rent of Male Nurse (PO# 4544) | APPROVED | No | 2024-11-27 | Abas, Mohammed Fekry | 2024-11-28 | 2024-11-28 |  |  |  | 48377.73 | 4544 | 2 | STANDARD | Shifa Al Dammam Medical Company | SAR | 48377.73 | APPROVED |  |  | 2024-12-02 | 0 | 4 | Babic, Marian | -45624 | 4
105-64 | JAFURAH 380/230kV BSP (SEC) | 5119 | JAFURAH 380/230kV BSP (SEC)-Genset Repair & Maintenance | APPROVED | No | 2024-12-03 | Abas, Mohammed Fekry | 2024-12-04 | 2024-12-04 |  |  |  | 6520 | 6611 | 0 | STANDARD | SAUDI DIESEL EQUIPMENT CO.LTD | SAR | 6520 | APPROVED |  |  | 2024-12-16 | 0 | 12 | Abuhammad, Samir | -45630 | 12
105-64 | JAFURAH 380/230kV BSP (SEC) | 5233 | JAFURAH 380/230kV BSP (SEC)-Additional LV Power Cable | APPROVED | No | 2024-12-16 | Abas, Mohammed Fekry | 2024-12-16 | 2024-12-16 |  |  |  | 169950 | 6662 | 0 | STANDARD | ARABIAN RELIANCE COMPANY(S) | SAR | 144500 | APPROVED |  |  | 2025-01-16 | 25450 | 31 | Babic, Marian | -45642 | 31
105-64 | JAFURAH 380/230kV BSP (SEC) | 5265 | JAFURAH 380/230kV BSP (SEC)-Additional LV Cable (PR# 5233) | APPROVED | No | 2024-12-23 | Abas, Mohammed Fekry | 2024-12-24 | 2024-12-25 |  |  |  | 19110 | 6662 | 0 | STANDARD | ARABIAN RELIANCE COMPANY(S) | SAR | 19110 | APPROVED |  |  | 2025-01-16 | 0 | 22 | Babic, Marian | -45651 | 22
105-64 | JAFURAH 380/230kV BSP (SEC) | 5805 | JAFURAH 380/230kV BSP (SEC)-Fiberoptic & CAT 6 cable supply & termination, Testing | REJECTED | No | 2025-02-06 | Sherif, Marwa | 2025-02-06 | 2025-02-06 |  | 2025-02-09 |  | 51000.3 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45694 | -45694
105-64 | JAFURAH 380/230kV BSP (SEC) | 5807 | JAFURAH 380/230kV BSP (SEC)-Station Furniture- Jafurah BSP | APPROVED | No | 2025-02-06 | Abas, Mohammed Fekry | 2025-02-10 | 2025-02-11 |  |  |  | 42420 | 6958 | 0 | STANDARD | ALISMAIL INDUSTRIAL CO.(S) | SAR | 39518 | APPROVED |  |  | 2025-03-16 | 2902 | 33 | Babic, Marian | -45699 | 33
105-64 | JAFURAH 380/230kV BSP (SEC) | 5812 | JAFURAH 380/230kV BSP (SEC)-Fiberoptic &CAT6 cable supply & termination, T&C | APPROVED | No | 2025-02-06 | Abas, Mohammed Fekry | 2025-02-10 | 2025-02-11 |  |  |  | 51000 | 6898 | 0 | STANDARD | Awan Al-Zahabia Contracting Co One person company(S) | SAR | 50000 | APPROVED |  |  | 2025-02-26 | 1000 | 15 | Abuhammad, Samir | -45699 | 15
105-64 | JAFURAH 380/230kV BSP (SEC) | 5829 | JAFURAH 380/230kV BSP (SEC)-Accommodation Arrangement for PMD & Staff at HUGRS | APPROVED | No | 2025-02-09 | Abas, Mohammed Fekry | 2025-02-10 | 2025-02-11 |  |  |  | 42600 | 6976 | 0 | STANDARD | Tamimi Global Co.Ltd for Services & Maintenance(S) | SAR | 42600 | APPROVED |  |  | 2025-03-09 | 0 | 26 | Abuhammad, Samir | -45699 | 26
105-64 | JAFURAH 380/230kV BSP (SEC) | 6063 | JAFURAH 380/230kV BSP (SEC)-Genset Repair | APPROVED | No | 2025-02-26 | Abas, Mohammed Fekry | 2025-03-01 | 2025-03-02 |  |  | Budget line 1.9.2.1.1.6 , offer attached. | 6957.68 | 6985 | 0 | STANDARD | SAUDI DIESEL EQUIPMENT CO.LTD | SAR | 6957 | APPROVED |  |  | 2025-03-09 | 0.68 | 7 | Abuhammad, Samir | -45718 | 7
105-64 | JAFURAH 380/230kV BSP (SEC) | 6237 | JAFURAH 380/230kV BSP (SEC)-Tools & Consumbales (PO# 8841) | APPROVED | No | 2025-03-23 | Abas, Mohammed Fekry | 2025-03-24 | 2025-03-25 |  |  | Budget line 1.9.2.1.3.5 | 48897.4 | 7087 | 0 | STANDARD | Jahaz Ayed Al-Rashidi and Partner for Trad and count | SAR | 48897.4 | APPROVED |  |  | 2025-04-06 | 0 | 12 | Abuhammad, Samir | -45741 | 12
105-64 | JAFURAH 380/230kV BSP (SEC) | 6238 | JAFURAH 380/230kV BSP (SEC)-Step-up transfromer Including Mobilization & De-mobilization (PO# 8822) | APPROVED | No | 2025-03-23 | Abas, Mohammed Fekry | 2025-03-24 | 2025-03-25 |  |  | Budget line 1.8.1 | 36000 | 7081 | 0 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 36000 | APPROVED |  |  | 2025-04-06 | 0 | 12 | Babic, Marian | -45741 | 12
105-64 | JAFURAH 380/230kV BSP (SEC) | 6241 | JAFURAH 380/230kV BSP (SEC)-Rent of Boom Truck (PO# 8858) | APPROVED | No | 2025-03-23 | Abas, Mohammed Fekry | 2025-03-24 | 2025-03-25 |  |  | budget line 1.12.3 | 18200 | 7088 | 0 | STANDARD | World Green Engineering & Contracting Company | SAR | 18200 | APPROVED |  |  | 2025-04-06 | 0 | 12 | Abuhammad, Samir | -45741 | 12
105-64 | JAFURAH 380/230kV BSP (SEC) | 6242 | JAFURAH 380/230kV BSP (SEC)-Supply of Labels for SS | APPROVED | No | 2025-03-23 | Abas, Mohammed Fekry | 2025-03-24 | 2025-03-25 |  |  | Budget line 1.8.1 | 47431 | 7091 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 47431 | APPROVED |  |  | 2025-04-06 | 0 | 12 | Abuhammad, Samir | -45741 | 12
105-64 | JAFURAH 380/230kV BSP (SEC) | 6243 | JAFURAH 380/230kV BSP (SEC)-Steel Washers (PO# 8863) | APPROVED | No | 2025-03-23 | Abas, Mohammed Fekry | 2025-03-24 | 2025-03-25 |  |  | Budget line 1.4.4 | 17416 | 7089 | 0 | STANDARD | Al Sharek Al Daem Est for Contracting | SAR | 17416 | APPROVED |  |  | 2025-04-06 | 0 | 12 | Abuhammad, Samir | -45741 | 12
105-64 | JAFURAH 380/230kV BSP (SEC) | 6243 | JAFURAH 380/230kV BSP (SEC)-Steel Washers (PO# 8863) | APPROVED | No | 2025-03-23 | Abas, Mohammed Fekry | 2025-03-24 | 2025-03-25 |  |  | Budget line 1.4.4 | 17416 | 7089 | 1 | STANDARD | Al Sharek Al Daem Est for Contracting | SAR | 17416 | REQUIRES REAPPROVAL |  |  |  | 0 | 313 | Abuhammad, Samir | -45741 | -45741
105-64 | JAFURAH 380/230kV BSP (SEC) | 6244 | JAFURAH 380/230kV BSP (SEC)-Genset Repair & Maintenance (PO# 8855) | APPROVED | No | 2025-03-23 | Abas, Mohammed Fekry | 2025-03-25 | 2025-03-27 |  |  | Budget line 1.9.1.5.6 | 13787.74 | 7127 | 0 | STANDARD | SAUDI DIESEL EQUIPMENT CO.LTD | SAR | 13787 | APPROVED |  |  | 2025-04-13 | 0.74 | 17 | Abuhammad, Samir | -45743 | 17
105-64 | JAFURAH 380/230kV BSP (SEC) | 6250 | JAFURAH 380/230kV BSP (SEC)-Additional PR-Supply of Manpower (PO# 5133) (M/s ATCO) | RETURNED | No | 2025-03-24 | Babic, Marian | 2025-10-06 | 2025-03-25 | 2025-10-06 |  | Returned because POCR not provided since 6 months | 1396980 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45741 | -45741
105-64 | JAFURAH 380/230kV BSP (SEC) | 6251 | JAFURAH 380/230kV BSP (SEC)-Genset Rent PO# 643 (M/s Saudi Peax) | APPROVED | No | 2025-03-24 | Abas, Mohammed Fekry | 2025-03-24 | 2025-03-25 |  |  | Budget line 1.9.1.5.7 | 47500 | 6463 | 1 | STANDARD | SAUDI DIESEL EQUIPMENT CO.LTD | SAR | 47500 | APPROVED |  |  | 2025-04-29 | 0 | 35 | Akhtar, Farhan | -45741 | 35
105-64 | JAFURAH 380/230kV BSP (SEC) | 6252 | JAFURAH 380/230kV BSP (SEC)-Genset Rent PO# 6010 (M/s Sudhir Rentals) | APPROVED | No | 2025-03-24 | Abas, Mohammed Fekry | 2025-03-25 | 2025-03-27 |  |  | Budget line 1.9.1.5.6, 1.9.1.5.7 & 1.9.2.1.1.6 | 45000 | 6010 | 1 | STANDARD | SUDHIR EQUIPMENT RENTAL COMPANY | SAR | 42100 | APPROVED |  |  | 2025-04-24 | 2900 | 28 | Akhtar, Farhan | -45743 | 28
105-64 | JAFURAH 380/230kV BSP (SEC) | 6256 | JAFURAH 380/230kV BSP (SEC)-Additional PR amounts for BUS Rental (PO# 5126) | APPROVED | No | 2025-03-24 | Abas, Mohammed Fekry | 2025-03-25 | 2025-03-27 |  |  | Budget line 1.9.1.4.5 | 36080 | 5126 | 2 | STANDARD | Al Arabiya For Operational Solutions | SAR | 36076.92 | APPROVED |  |  | 2025-04-13 | 3.08 | 17 | Abuhammad, Samir | -45743 | 17
105-64 | JAFURAH 380/230kV BSP (SEC) | 6290 | JAFURAH 380/230kV BSP (SEC)-Additional Lighting Materials | RETURNED | No | 2025-04-03 | Mohammed, Mohammed Adel Fahmy | 2025-12-24 | 2025-11-23 | 2025-12-24 |  | material already delivered by vendor from one year, such that can't issued this pr | 42639 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Mohammed Adel Fahmy | -45984 | -45984
105-64 | JAFURAH 380/230kV BSP (SEC) | 6293 | JAFURAH 380/230kV BSP (SEC)-Additional PR for Accomodation & Catering (PO# 4518) | RETURNED | No | 2025-04-05 | Kumar, Mr. Ranjan | 2025-06-23 | 2025-04-08 | 2025-06-23 |  | POCR not received, Please raise the PR once POCR is approved. | 4363200 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45755 | -45755
105-64 | JAFURAH 380/230kV BSP (SEC) | 6314 | JAFURAH 380/230kV BSP (SEC)-Metrosils (Brand M&I) | RETURNED | No | 2025-04-10 | Babic, Marian | 2025-10-26 | 2025-04-13 | 2025-10-26 |  | please resubmit after providing all the necessary documents | 160200 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45760 | -45760
105-64 | JAFURAH 380/230kV BSP (SEC) | 6317 | JAFURAH 380/230kV BSP (SEC)-Additional Termination Kit Jointers POCO# 4777-1 | APPROVED | No | 2025-04-10 | Abas, Mohammed Fekry | 2025-04-13 | 2025-04-13 |  |  | Budget line 1.2.1.7.1 | 50625 | 4777 | 1 | STANDARD | LS Cable Systems Ltd | USD | 50625 | APPROVED |  |  | 2025-04-29 | 0 | 16 | Babic, Marian | -45760 | 16
105-64 | JAFURAH 380/230kV BSP (SEC) | 6318 | JAFURAH 380/230kV BSP (SEC)-Additional Termination Kit Jointers (Idling Charges) POCO# 4777-2 | APPROVED | No | 2025-04-10 | Abas, Mohammed Fekry | 2025-04-13 | 2025-04-13 |  |  | Budget line 1.2.1.7.1 | 30937.5 | 4777 | 1 | STANDARD | LS Cable Systems Ltd | USD | 30937.5 | APPROVED |  |  | 2025-04-29 | 0 | 16 | Babic, Marian | -45760 | 16
105-64 | JAFURAH 380/230kV BSP (SEC) | 6427 | JAFURAH 380/230kV BSP (SEC)-Additional PR for PO CO# 4953-1 - Diesel Fuel | APPROVED | No | 2025-04-23 | Abas, Mohammed Fekry | 2025-04-23 | 2025-04-24 |  |  | Budget line 1.9.1.5.6 | 258500 | 4953 | 1 | STANDARD | Talaea Alahlam Trading Company | SAR | 258500 | APPROVED |  |  | 2025-04-28 | 0 | 4 | Abuhammad, Samir | -45771 | 4
105-64 | JAFURAH 380/230kV BSP (SEC) | 6484 | JAFURAH 380/230kV BSP (SEC)-Additional Diesel Fuel for Jafurah Site (15,000 Liters) | APPROVED | No | 2025-04-29 | Abas, Mohammed Fekry | 2025-04-30 | 2025-05-04 |  |  | Budget line 1.8.1 | 27000 | 7229 | 0 | STANDARD | World Green Engineering & Contracting Company | SAR | 27000 | APPROVED |  |  | 2025-05-07 | 0 | 3 | Akhtar, Farhan | -45781 | 3
105-64 | JAFURAH 380/230kV BSP (SEC) | 6540 | JAFURAH 380/230kV BSP (SEC)-Fiber optic works "Testing FOC" (Manual PO# 8854-0) | RETURNED | No | 2025-05-06 | Abuhammad, Samir | 2025-06-22 | 2025-05-08 | 2025-06-22 |  | As per PM request to consider the scope as cash. | 8340 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45785 | -45785
105-64 | JAFURAH 380/230kV BSP (SEC) | 6541 | JAFURAH 380/230kV BSP (SEC)-Fiber Optic Works "Patch Cord & Splicing" | APPROVED | No | 2025-05-06 | Abas, Mohammed Fekry | 2025-05-08 | 2025-05-08 |  |  | Budget line 1.2.1.7.4. For approved manual PO# 8825. | 46672 | 7262 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 46672 | APPROVED |  |  | 2025-05-12 | 0 | 4 | Abuhammad, Samir | -45785 | 4
105-64 | JAFURAH 380/230kV BSP (SEC) | 6542 | JAFURAH 380/230kV BSP (SEC)-Supply of FOC 96F (Manual PO# 8820, already paid) | APPROVED | No | 2025-05-06 | Abas, Mohammed Fekry | 2025-05-08 | 2025-05-08 |  |  | budget line 1.2.1.7.4 | 30000 | 7261 | 0 | STANDARD | Al-Haider Company For Cont.- Hadi Saleh Al-Haider & Partner Co. | SAR | 30000 | APPROVED |  |  | 2025-05-12 | 0 | 4 | Abuhammad, Samir | -45785 | 4
105-64 | JAFURAH 380/230kV BSP (SEC) | 6590 | JAFURAH 380/230kV BSP (SEC)-230kV Power Termination Kit (Xformer side) - Supply & Delivery | APPROVED | No | 2025-05-12 | Abas, Mohammed Fekry | 2025-05-15 | 2025-05-15 |  |  | Budget line 1.2.1.7.4 | 45463.89 | 4404 | 1 | STANDARD | Brugg Kable AG | CHF | 34235 | APPROVED |  |  | 2025-06-02 | 11228.89 | 18 | Babic, Marian | -45792 | 18
105-64 | JAFURAH 380/230kV BSP (SEC) | 6591 | JAFURAH 380/230kV BSP (SEC)-230kV Power Termination Kit (Xformer side) - Installation | APPROVED | No | 2025-05-12 | Abas, Mohammed Fekry | 2025-05-12 | 2025-05-14 |  |  | budget line 1.9.1.3.1 | 35000 | 4948 | 1 | STANDARD | BRUGG CABLES COMAPNY | SAR | 20000 | APPROVED |  |  | 2025-06-02 | 15000 | 19 | Babic, Marian | -45791 | 19
105-64 | JAFURAH 380/230kV BSP (SEC) | 6628 | JAFURAH 380/230kV BSP (SEC)-PR for LS Cable 230kV Power Termination Kit (GIS side) - Supply & Delivery | RETURNED | No | 2025-05-15 | Mohammed, Faisal Ansari | 2025-09-24 | 2025-05-27 | 2025-09-24 |  | The PR is not sufficient to cover the PO value. Kindly revise it as per the PO. | 33937.5 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45804 | -45804
105-64 | JAFURAH 380/230kV BSP (SEC) | 6689 | JAFURAH 380/230kV BSP (SEC)-PR for 230kV Power Termination Kit (Xformer side) - FAT Charges (3,500 CHF) | APPROVED | No | 2025-05-22 | Abas, Mohammed Fekry | 2025-05-25 | 2025-05-25 |  |  | budget line 1.12.2 | 16000 | 4404 | 1 | STANDARD | Brugg Kable AG | CHF | 14350 | APPROVED |  |  | 2025-06-02 | 1650 | 8 | Babic, Marian | -45802 | 8
105-64 | JAFURAH 380/230kV BSP (SEC) | 6700 | JAFURAH 380/230kV BSP (SEC)-Supply of 230kV HV cable (Revised Offer) | APPROVED | No | 2025-05-25 | Abas, Mohammed Fekry | 2025-05-25 | 2025-05-26 |  |  | Budget line 1.2.1.7.1 | 297000 | 7258 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 297000 | APPROVED |  |  | 2025-05-29 | 0 | 3 | Babic, Marian | -45803 | 3
105-64 | JAFURAH 380/230kV BSP (SEC) | 7090 | JAFURAH 380/230kV BSP (SEC)-PR for Hand Holes | APPROVED | No | 2025-07-14 | Abas, Mohammed Fekry | 2025-07-20 | 2025-07-20 |  |  | Budget line 1.3.1 | 70000 | 7635 | 0 | STANDARD | JEDDAH AOIMS CONTRACTING COMPANY | SAR | 64000 | APPROVED |  |  | 2025-09-07 | 6000 | 49 | Hegazy, Ayman | -45858 | 49
105-64 | JAFURAH 380/230kV BSP (SEC) | 7630 | Consumable Items/Materials for Closing Punch List | APPROVED | No | 2025-09-03 | Abas, Mohammed Fekry | 2025-09-08 | 2025-09-08 |  |  | Budget line 1.9.2.1.3.5 | 0 | 7691 | 0 | STANDARD | Essa Al Asmakh Trading Est. | SAR | 41722.5 | APPROVED |  |  | 2025-09-29 | -41722.5 | 21 | Abuhammad, Samir | -45908 | 21
105-64 | JAFURAH 380/230kV BSP (SEC) | 7632 | New Waste Water Management & Supply of Water to Jafurah Site | REJECTED | No | 2025-09-03 | Sherif, Marwa | 2025-09-03 | 2025-09-03 |  | 2025-10-07 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45903 | -45903
105-64 | JAFURAH 380/230kV BSP (SEC) | 7855 | PR for Security Guards New PO | REJECTED | No | 2025-09-29 | Sherif, Marwa | 2025-09-29 | 2025-09-29 |  | 2025-10-07 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45929 | -45929
105-64 | JAFURAH 380/230kV BSP (SEC) | 7866 | PR for LS Cable 230kV Power Termination Kit (GIS side) - Supply & Installation (PO# 7702) | APPROVED | No | 2025-09-30 | Abas, Mohammed Fekry | 2025-10-05 | 2025-10-06 |  |  | Budget line 1.2.1.7.1 | 0 | 7702 | 0 | STANDARD | LS Cable Systems Ltd | USD | 384000 | APPROVED |  |  | 2025-10-15 | -384000 | 9 | Mohammed, Faisal Ansari | -45936 | 9
105-64 | JAFURAH 380/230kV BSP (SEC) | 8284 | PR for Precast Works PO# 4439 Change Order | RETURNED | No | 2025-11-19 | Tananeh, Khalid Jamal | 2025-12-22 | 2025-12-04 | 2025-12-22 |  | Return of PR 8284 Due to do not receive the POCR as per email sent to Mr. Raza / Mr. Khaja in Mon 15/12/2025 10:15 AM | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45995 | -45995
105-64 | JAFURAH 380/230kV BSP (SEC) | 8288 | Additional PR for Genset Rent PO# 6010 (M/s Sudhir Rentals) | APPROVED | No | 2025-11-19 | Khan, Muhammad Safdar | 2025-12-22 | 2025-12-22 |  |  | Budget line 1.9.1.5.6 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -46013 | -46013
105-64 | JAFURAH 380/230kV BSP (SEC) | 8289 | Additional PR amounts for waste water management (PO# 4828) Change Order | APPROVED | No | 2025-11-19 | Abas, Mohammed Fekry | 2025-12-01 | 2025-12-02 |  |  | Budget line 1.9.1.5.11 | 0 | 4828 | 2 | STANDARD | Cebent for General Cont. Est. | SAR | 152600 | APPROVED | 2025-12-21 | 2025-12-26 | 2026-01-04 | -152600 | 33 | Abuhammad, Samir | 24 | 33
105-64 | JAFURAH 380/230kV BSP (SEC) | 8291 | Security Guards Services (PO# 8957) | APPROVED | No | 2025-11-20 | Abas, Mohammed Fekry | 2025-11-20 | 2025-11-23 |  |  | Budget line 1.9.1.1.15 | 0 | 7935 | 0 | STANDARD | Al-Nufuth Al-Mutamayiza For Security Company | SAR | 145000 | APPROVED | 2025-12-21 | 2025-12-26 | 2026-01-04 | -145000 | 42 | Abuhammad, Samir | 33 | 42
105-64 | JAFURAH 380/230kV BSP (SEC) | 8296 | Additional PR amounts for Diesel (PO# 4953) | APPROVED | No | 2025-11-20 | Abas, Mohammed Fekry | 2025-11-26 | 2025-11-29 |  |  | Budget line 1.9.1.5.6 | 0 | 4953 | 2 | STANDARD | Talaea Alahlam Trading Company | SAR | 370000 | APPROVED |  |  | 2025-12-17 | -370000 | 18 | Abuhammad, Samir | -45990 | 18
105-64 | JAFURAH 380/230kV BSP (SEC) | 8297 | PR for Genset Rent PO# 6463 -Remaining Invoices (M/s Peax Saudi Diesel) | RETURNED | No | 2025-11-20 | Akhtar, Farhan | 2025-12-07 | 2025-11-29 | 2025-12-07 |  | Resubmit the PR once POCR is approved | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45990 | -45990
105-64 | JAFURAH 380/230kV BSP (SEC) | 8298 | Additional PR for Accomodation & Catering (PO# 4518) | INCOMPLETE | No | [6 empty] | Resubmit the PR once POCR is approved | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
105-64 | JAFURAH 380/230kV BSP (SEC) | 8305 | Additional PR-Supply of Manpower (PO# 5133) (M/s ATCO) | APPROVED | No | 2025-11-20 | Abas, Mohammed Fekry | 2025-12-01 | 2025-12-02 |  |  | budget line 1.9.1.3.1 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45993 | -45993
105-64 | JAFURAH 380/230kV BSP (SEC) | 8306 | PR for Backfilling materials PO# 4337 Change Order | RETURNED | No | 2025-11-20 | Kumar, Mr. Ranjan | 2025-12-08 | 2025-11-29 | 2025-12-08 |  | PR 8306 is superseded by new PR 8475, hence as confirmed by PMT PR 8306 is returned | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45990 | -45990
105-64 | JAFURAH 380/230kV BSP (SEC) | 8307 | PR for Asphlat Works PO# 6052 Change Order | RETURNED | No | 2025-11-20 | Kumar, Mr. Ranjan | 2025-12-15 | 2025-11-29 | 2025-12-15 |  | Approved PO CR and Change order details, details of the scope to be added requested from PMT on 30/11/2025. PMT is requested to submit the PR attaching approved POCR and details of change order... | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45990 | -45990
105-64 | JAFURAH 380/230kV BSP (SEC) | 8308 | Additional PR amounts for PO# 4489-1, SAFCO, 3rd Party Lab Test, Change Order | RETURNED | No | 2025-11-20 | Kumar, Mr. Ranjan | 2025-12-15 | 2025-11-29 | 2025-12-15 |  | Approved PO CR and Change order details, details of the scope to be added requested from PMT on 30/11/2025. PMT is requested to submit the PR attaching approved POCR and details of change order... | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45990 | -45990
105-64 | JAFURAH 380/230kV BSP (SEC) | 8309 | PR for Sunshades (PO# 7074) | APPROVED | No | 2025-11-20 | Abas, Mohammed Fekry | 2025-11-26 | 2025-11-27 |  |  | budget line 1.3.1 | 0 | 7074 | 0 | STANDARD | Al Sharek Al Daem Est for Contracting | SAR | 465000 | APPROVED |  |  | 2025-12-16 | -465000 | 19 | Mohammed, Faisal Ansari | -45988 | 19
105-64 | JAFURAH 380/230kV BSP (SEC) | 8310 | PR for Traffic Signages (Draft PO prepared) | APPROVED | No | 2025-11-20 | Abas, Mohammed Fekry | 2025-11-26 | 2025-11-29 |  |  | Budget line 1.3.1 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45990 | -45990
105-64 | JAFURAH 380/230kV BSP (SEC) | 8311 | Metrosils for Jafurah | APPROVED | No | 2025-11-20 | Abas, Mohammed Fekry | 2025-12-01 | 2025-12-02 |  |  | budget line 1.2.1.4.1 | 0 | 15008 | 0 | STANDARD |  | SAR | 0 | INCOMPLETE |  |  |  | 0 | 61 | Mohammed, Mohammed Adel Fahmy | -45993 | -45993
105-64 | JAFURAH 380/230kV BSP (SEC) | 8311 | Metrosils for Jafurah | APPROVED | No | 2025-11-20 | Abas, Mohammed Fekry | 2025-12-01 | 2025-12-02 |  |  | budget line 1.2.1.4.1 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Mohammed Adel Fahmy | -45993 | -45993
105-64 | JAFURAH 380/230kV BSP (SEC) | 8312 | Testing & Commissioning (PO# 5211) Change Order | APPROVED | No | 2025-11-20 | Abas, Mohammed Fekry | 2025-11-26 | 2025-11-29 |  |  | BUDGET LINE 1.10.1 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45990 | -45990
105-64 | JAFURAH 380/230kV BSP (SEC) | 8475 | PR for Excavation and Backfilling | IN PROCESS | No | 2025-12-08 | Khan, Muhammad Safdar | 2025-12-11 | 2025-12-08 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45999 | -45999
105-64 | JAFURAH 380/230kV BSP (SEC) | 8694 | PR for Supervisor (GIS-Hitachi), installation of new 230kV Power Cable | APPROVED | No | 2026-01-13 | Abas, Mohammed Fekry | 2026-01-20 | 2026-01-21 |  |  | BUDGET LINE 1.2.1.7.1 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46043 | -46043
105-64 | JAFURAH 380/230kV BSP (SEC) | 8695 | PR for Dismantling of Damaged Cable & Installation of New Power Cable | APPROVED | No | 2026-01-13 | Abas, Mohammed Fekry | 2026-01-20 | 2026-01-21 |  |  | Budget line 1.2.1.7.1 as per approved CTC | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46043 | -46043
105-64 | JAFURAH 380/230kV BSP (SEC) | 8696 | PR for Supervisor (P.Transformer-Hyundai), installation of new 230kV Power Cable | APPROVED | No | 2026-01-13 | Abas, Mohammed Fekry | 2026-01-20 | 2026-01-21 |  |  | Budget line 1.2.1.7.1 as per approved CTC, (offer to be finalize by procurement team) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46043 | -46043
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1095 | AL SHARFIYAH, 132kV S/S # 8386-GIS equipment | REJECTED | No | 2023-03-01 | Alharbi, Meshal | 2023-03-01 |  |  | 2023-03-01 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1096 | AL SHARFIYAH, 132kV S/S # 8386-GIS Equipment | RETURNED | No | 2023-03-01 | Babic, Marian | 2023-03-09 | 2023-03-08 | 2023-03-09 |  | Please revise the budget to match the PO value, then issue new PR | 11378617.28 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44993 | -44993
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1100 | AL SHARFIYAH, 132kV S/S # 8386-subcontractor of Civil works | APPROVED | No | 2023-03-06 | Abas, Mohammed Fekry | 2023-03-09 | 2023-03-12 |  |  |  | 9000000 | 4375 | 0 | STANDARD | Al Sahda Contracting Est. | SAR | 6550000 | APPROVED |  |  | 2023-04-11 | 2450000 | 30 | Kumar, Mr. Ranjan | -44997 | 30
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1101 | AL SHARFIYAH, 132kV S/S # 8386-Auxiliary Transformers | INCOMPLETE | No |  | Alharbi, Meshal | 2023-03-06 |  |  |  |  | 3 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1102 | AL SHARFIYAH, 132kV S/S # 8386-RMU | RETURNED | No | 2023-03-06 | Babic, Marian | 2024-04-15 | 2023-03-12 | 2024-04-15 |  | as discussed | 160000 | 4498 | 0 | STANDARD | ALFANAR CO | SAR | 150000 | APPROVED |  |  | 2023-06-11 | 10000 |  | Babic, Marian | -44997 | 91
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1102 | AL SHARFIYAH, 132kV S/S # 8386-RMU | RETURNED | No | 2023-03-06 | Babic, Marian | 2024-04-15 | 2023-03-12 | 2024-04-15 |  | as discussed | 6950000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -44997 | -44997
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1109 | AL SHARFIYAH, 132kV S/S # 8386-Auxiliary transformers | REJECTED | No | 2023-03-07 | Alharbi, Meshal | 2023-03-07 |  |  | 2023-03-07 |  | 1700000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1110 | AL SHARFIYAH, 132kV S/S # 8386-Auxiliary transformers | RETURNED | No | 2023-03-07 | Babic, Marian | 2023-03-12 | 2023-03-12 | 2023-03-12 |  | Please make quantity 2, and for the price please check with Mr. Ranjan | 89471 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44997 | -44997
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1111 | AL SHARFIYAH, 132kV S/S # 8386- Cyber Security | APPROVED | No | 2023-03-07 | Abas, Mohammed Fekry | 2023-03-09 | 2023-03-12 |  |  |  | 1700000 | 4538 | 0 | STANDARD | ALFANAR CO | SAR | 1700000 | APPROVED |  |  | 2023-07-12 | 0 | 122 | Kumar, Mr. Ranjan | -44997 | 122
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1115 | AL SHARFIYAH, 132kV S/S # 8386-Renew license Municipality of land | APPROVED | No | 2023-03-09 | Abas, Mohammed Fekry | 2023-03-09 | 2023-03-12 |  |  |  | 18000 | 4388 | 0 | STANDARD | AlGhanem Engineering Co | SAR | 18000 | APPROVED |  |  | 2023-04-09 | 0 | 28 | Abuhammad, Samir | -44997 | 28
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1157 | AL SHARFIYAH, 132kV S/S # 8386-Sign board & Fence | APPROVED | No | 2023-04-03 | Abas, Mohammed Fekry | 2023-04-18 | 2023-04-19 |  |  |  | 54700 | 4458 | 0 | STANDARD | Al-Kayan Al-Zahi General Contracting | SAR | 48700 | APPROVED |  |  | 2023-05-21 | 6000 | 32 | Kumar, Mr. Ranjan | -45035 | 32
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1180 | AL SHARFIYAH, 132kV S/S # 8386-Auxiliary transformer | APPROVED | No | 2023-04-11 | Abas, Mohammed Fekry | 2023-04-12 | 2023-04-13 |  |  |  | 190000 | 4537 | 0 | STANDARD | UNITED TRANSFORMERS ELECTRIC COMPANY (UTEC) | SAR | 158800 | APPROVED |  |  | 2023-07-12 | 31200 | 90 | Eranhikkal, Mr. Riyaz Mohammed | -45029 | 90
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1182 | AL SHARFIYAH, 132kV S/S # 8386-Overhead Crane | APPROVED | No | 2023-04-11 | Abas, Mohammed Fekry | 2023-04-12 | 2023-04-13 |  |  |  | 425000 | 4460 | 0 | STANDARD | SAUDI CRANES & STEEL WORKS FACTORY LTD | SAR | 153500 | APPROVED |  |  | 2023-05-29 | 271500 | 46 | Kumar, Mr. Ranjan | -45029 | 46
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1188 | AL SHARFIYAH, 132kV S/S # 8386-Precast | REJECTED | No | 2023-04-11 | Al-Asmi, Ibrahim Abdulkhaliq | 2023-04-11 | 2023-04-11 |  | 2023-04-19 |  | 2450000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45027 | -45027
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1204 | AL SHARFIYAH, 132kV S/S # 8386-JIB crane | APPROVED | No | 2023-04-19 | Abas, Mohammed Fekry | 2023-05-02 | 2023-05-02 |  |  |  | 100000 | 4460 | 0 | STANDARD | SAUDI CRANES & STEEL WORKS FACTORY LTD | SAR | 70000 | APPROVED |  |  | 2023-05-29 | 30000 | 27 | Kumar, Mr. Ranjan | -45048 | 27
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1235 | AL SHARFIYAH, 132kV S/S # 8386-Mobilization offices | RETURNED | No | 2023-05-07 | Kumar, Mr. Ranjan | 2023-11-23 | 2023-05-10 | 2023-11-23 |  | Please mention quantity as per BOQ - Without quantity invetory can not be managed | 118500 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45056 | -45056
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1238 | AL SHARFIYAH, 132kV S/S # 8386-RMU | RETURNED | No | 2023-05-09 | Babic, Marian | 2024-03-26 | 2023-05-10 | 2024-03-26 |  | this PO was issed from another PR | 200000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45056 | -45056
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1266 | AL SHARFIYAH, 132kV S/S # 8386-FF&FA | APPROVED | No | 2023-05-16 | Abas, Mohammed Fekry | 2023-05-23 | 2023-05-24 |  |  |  | 1600000 | 4716 | 0 | STANDARD | Equipment & Technical Services Co.(ETECHS) | SAR | 1575000 | APPROVED |  |  | 2023-11-27 | 25000 | 187 | Kumar, Mr. Ranjan | -45070 | 187
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1270 | AL SHARFIYAH, 132kV S/S # 8386-Batteries & Charger | REJECTED | No | 2023-05-16 | Almutairi, Yasser Aied | 2024-07-10 | 2023-05-24 | 2023-12-18 | 2024-07-10 | PR value is less than PO value, Please revise. Manual PO issued | 420000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45070 | -45070
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1328 | AL SHARFIYAH, 132kV S/S # 8386-TPI for PTR | APPROVED | No | 2023-06-20 | Abas, Mohammed Fekry | 2023-07-05 | 2023-07-05 |  |  |  | 34500 | 4542 | 0 | STANDARD | VELOSI SAUDI ARABIA CO LTD | SAR | 14300 | APPROVED |  |  | 2023-07-13 | 20200 | 8 | Akhtar, Farhan | -45112 | 8
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1351 | AL SHARFIYAH, 132kV S/S # 8386-Bare Copper Conductor | APPROVED | No | 2023-07-16 | Abas, Mohammed Fekry | 2023-07-21 | 2023-07-23 |  |  |  | 90854.55 | 4576 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 88627.5 | APPROVED |  |  | 2023-08-28 | 2227.05 | 36 | Babic, Marian | -45130 | 36
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1351 | AL SHARFIYAH, 132kV S/S # 8386-Bare Copper Conductor | APPROVED | No | 2023-07-16 | Abas, Mohammed Fekry | 2023-07-21 | 2023-07-23 |  |  |  | 90854.55 | 4576 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 86062.47 | APPROVED |  |  | 2023-09-10 | 4792.08 | 49 | Babic, Marian | -45130 | 49
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1357 | AL SHARFIYAH, 132kV S/S # 8386-TPI FOR DC -DC Converter | APPROVED | No | 2023-07-19 | Abas, Mohammed Fekry | 2023-07-21 | 2023-07-23 |  |  |  | 3000 | 4548 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 2606.25 | APPROVED |  |  | 2023-07-30 | 393.75 | 7 | Akhtar, Farhan | -45130 | 7
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1391 | AL SHARFIYAH, 132kV S/S # 8386-Testing& Comissioning-8386 | APPROVED | No | 2023-08-08 | Abas, Mohammed Fekry | 2023-08-14 | 2023-08-16 |  |  |  | 1500000 | 4571 | 0 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 1500000 | APPROVED |  |  | 2024-05-26 | 0 | 284 | Babic, Marian | -45154 | 284
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1407 | AL SHARFIYAH, 132kV S/S # 8386-Earthing Materials | RETURNED | No | 2023-08-13 | Babic, Marian | 2024-03-26 | 2023-08-16 | 2024-03-26 |  | this PO was issued from another PR | 277236.59 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45154 | -45154
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1408 | AL SHARFIYAH, 132kV S/S # 8386-Civil Subcontractor Change order AL-Sharafyah | APPROVED | No | 2023-08-13 | Abas, Mohammed Fekry | 2023-08-14 | 2023-08-16 |  |  |  | 350000 | 4375 | 1 | STANDARD | Al Sahda Contracting Est. | SAR | 350000 | APPROVED |  |  | 2023-09-14 | 0 | 29 | Kumar, Mr. Ranjan | -45154 | 29
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1409 | AL SHARFIYAH, 132kV S/S # 8386-Bare Copper remaning Iteams | APPROVED | No | 2023-08-14 | Abas, Mohammed Fekry | 2023-08-14 | 2023-08-16 |  |  |  | 184072.5 | 4576 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 184072.5 | APPROVED |  |  | 2023-08-28 | 0 | 12 | Babic, Marian | -45154 | 12
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1409 | AL SHARFIYAH, 132kV S/S # 8386-Bare Copper remaning Iteams | APPROVED | No | 2023-08-14 | Abas, Mohammed Fekry | 2023-08-14 | 2023-08-16 |  |  |  | 184072.5 | 4576 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 178745.13 | APPROVED |  |  | 2023-09-10 | 5327.37 | 25 | Babic, Marian | -45154 | 25
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1434 | AL SHARFIYAH, 132kV S/S # 8386-TPI-ALsharafyah Telecom Panels | RETURNED | No | 2023-08-23 | Akhtar, Farhan | 2024-05-06 | 2023-08-28 | 2024-05-06 |  | reassign buyer | 8000 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45166 | -45166
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1441 | AL SHARFIYAH, 132kV S/S # 8386-TPI for ALsharafyah (Telecom ) | APPROVED | No | 2023-08-28 | Abas, Mohammed Fekry | 2023-08-30 | 2023-08-30 |  |  |  | 14500 | 4593 | 0 | STANDARD | Atlas Support and Services | SAR | 8700 | APPROVED |  |  | 2023-09-10 | 5800 | 11 | Akhtar, Farhan | -45168 | 11
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1509 | AL SHARFIYAH, 132kV S/S # 8386-Safety Requirment for AL-Sharafyah | APPROVED | No | 2023-09-17 | Abas, Mohammed Fekry | 2023-09-20 | 2023-09-20 |  |  |  | 72000 | 4656 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 28028 | APPROVED |  |  | 2023-10-26 | 43972 | 36 | Badhman, Saeed | -45189 | 36
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1514 | AL SHARFIYAH, 132kV S/S # 8386-TPI in Korea GIS AL-Sharafyah SS | APPROVED | No | 2023-09-18 | Abas, Mohammed Fekry | 2023-09-20 | 2023-09-20 |  |  |  | 40000 | 4627 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 7800 | APPROVED |  |  | 2023-10-02 | 32200 | 12 | Akhtar, Farhan | -45189 | 12
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1527 | AL SHARFIYAH, 132kV S/S # 8386-Alsharfiyah - Site Team Training | REJECTED | No | 2023-09-27 | Almutairi, Yasser Aied | 2023-09-27 |  |  | 2023-09-27 |  | 15000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1557 | AL SHARFIYAH, 132kV S/S # 8386-Desno Tape for AL-Sharafyah | RETURNED | No | 2023-10-05 | Babic, Marian | 2024-05-15 | 2023-10-09 | 2024-05-15 |  | please make all earthing for PO 8347 under 1 PR as per the final BOQ | 15000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45208 | -45208
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1558 | AL SHARFIYAH, 132kV S/S # 8386-Printer | APPROVED | No | 2023-10-05 | Abas, Mohammed Fekry | 2023-10-09 | 2023-10-09 |  |  |  | 10000 | 4666 | 0 | STANDARD | Fast Computers for Trading Est | SAR | 9815 | APPROVED |  |  | 2023-11-02 | 185 | 24 | Babic, Marian | -45208 | 24
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1571 | AL SHARFIYAH, 132kV S/S # 8386-Site Safety training | RETURNED | No | 2023-10-10 | Badhman, Saeed | 2024-05-22 | 2023-10-11 | 2024-05-22 |  | Not Needed | 17000 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45210 | -45210
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1622 | AL SHARFIYAH, 132kV S/S # 8386-TPI For AL-Sharafyah C&P | APPROVED | No | 2023-10-24 | Abas, Mohammed Fekry | 2023-11-02 | 2023-11-02 |  |  |  | 10000 | 4698 | 0 | STANDARD | Atlas Support and Services | SAR | 10000 | APPROVED |  |  | 2023-11-07 | 0 | 5 | Babic, Marian | -45232 | 5
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1649 | AL SHARFIYAH, 132kV S/S # 8386-AC DC Panels -AL-Sharafyah | APPROVED | No | 2023-11-01 | Abas, Mohammed Fekry | 2023-11-06 | 2023-11-06 |  |  |  | 592725 | 4702 | 0 | STANDARD | ALFANAR CO | SAR | 592725 | APPROVED |  |  | 2023-11-26 | 0 | 20 | Babic, Marian | -45236 | 20
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1650 | AL SHARFIYAH, 132kV S/S # 8386-Bare Copper Conductor For AL-sharafyah SS | APPROVED | No | 2023-11-01 | Abas, Mohammed Fekry | 2023-11-07 | 2023-11-09 |  |  |  | 138000 | 4576 | 2 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 136350 | APPROVED |  |  | 2023-11-22 | 1650 | 13 | Babic, Marian | -45239 | 13
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1650 | AL SHARFIYAH, 132kV S/S # 8386-Bare Copper Conductor For AL-sharafyah SS | APPROVED | No | 2023-11-01 | Abas, Mohammed Fekry | 2023-11-07 | 2023-11-09 |  |  |  | 138000 | 4576 | 3 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 133422.6 | APPROVED |  |  | 2023-11-26 | 4577.4 | 17 | Babic, Marian | -45239 | 17
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1651 | AL SHARFIYAH, 132kV S/S # 8386-LV Cables and control -AL-Sharafyah SS | REJECTED | No | 2023-11-01 | Almutairi, Yasser Aied | 2023-11-01 |  |  | 2023-11-01 |  | 838256.15 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1656 | AL SHARFIYAH, 132kV S/S # 8386-NGR for AL-sharafyah Project Manual PO (8137) | APPROVED | No | 2023-11-05 | Abas, Mohammed Fekry | 2023-11-08 | 2023-11-09 |  |  |  | 61042.5 | 4719 | 0 | STANDARD | National Switchgears | USD | 61042.5 | APPROVED |  |  | 2023-11-19 | 0 | 10 | Kumar, Mr. Ranjan | -45239 | 10
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1662 | AL SHARFIYAH, 132kV S/S # 8386-Lighting panels | APPROVED | No | 2023-11-06 | Abas, Mohammed Fekry | 2023-11-08 | 2023-11-09 |  |  |  | 200000 | 4702 | 0 | STANDARD | ALFANAR CO | SAR | 127275 | APPROVED |  |  | 2023-11-26 | 72725 | 17 | Babic, Marian | -45239 | 17
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1796 | AL SHARFIYAH, 132kV S/S # 8386-TPI Surge Arrestor - AL SHARFIYAH (8386) SS | REJECTED | No | 2023-11-20 | Almutairi, Yasser Aied | 2023-11-20 |  |  | 2023-11-20 |  | 10000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1810 | AL SHARFIYAH, 132kV S/S # 8386-e | REJECTED | No | 2025-02-18 | Elmeligy, Usama Shaban Gomaa | 2025-02-18 |  |  | 2025-02-18 |  | 3750000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1890 | AL SHARFIYAH, 132kV S/S # 8386-PTR manual po to be in oracle 8007-AL-Sharafyah | RETURNED | No | 2023-12-04 | Kumar, Mr. Ranjan | 2024-05-21 | 2023-12-07 | 2024-05-21 |  | PO 5497 is already in system forAL SHARFIYAH, 132kV S/S # 8386-PTR to be in the system-Manual PO 8077 | 15744000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45267 | -45267
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1907 | AL SHARFIYAH, 132kV S/S # 8386-HVAC-AL-Sharafyah | APPROVED | No | 2023-12-06 | Abas, Mohammed Fekry | 2023-12-10 | 2023-12-11 |  |  |  | 100000 | 4933 | 0 | STANDARD | Ramz Alataa Company for Trading | SAR | 50000 | APPROVED |  |  | 2024-01-08 | 50000 | 28 | Alhadi, Khalid | -45271 | 28
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1909 | AL SHARFIYAH, 132kV S/S # 8386-Fire Fighting PO-ALSharafyah | INCOMPLETE | No |  | Almutairi, Yasser Aied | 2023-12-06 |  |  |  |  | 11473 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1958 | AL SHARFIYAH, 132kV S/S # 8386-PDS System subcontractor For Al-Sharfia 8386 | APPROVED | No | 2023-12-14 | Abas, Mohammed Fekry | 2023-12-17 | 2023-12-17 |  |  |  | 208400 | 4915 | 0 | STANDARD | SMART TECH | SAR | 208400 | APPROVED |  |  | 2024-01-01 | 0 | 15 | Kumar, Mr. Ranjan | -45277 | 15
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1959 | AL SHARFIYAH, 132kV S/S # 8386-Security system -AL-sharafyah -Remaning Value of old PR before Approve budget | REJECTED | No | 2023-12-14 | Almutairi, Yasser Aied | 2023-12-14 |  |  | 2023-12-14 |  | 311053 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 1967 | AL SHARFIYAH, 132kV S/S # 8386-Precast -AL-Sharafyah | APPROVED | No | 2023-12-14 | Abas, Mohammed Fekry | 2023-12-17 | 2023-12-18 |  |  |  | 2030074.1 | 4916 | 0 | STANDARD | Prainsa Saudi for precast Concrete | SAR | 2030074.1 | APPROVED |  |  | 2024-01-01 | 0 | 14 | Kumar, Mr. Ranjan | -45278 | 14
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2009 | AL SHARFIYAH, 132kV S/S # 8386-AL-SHARAFIYAH SS#8386-Over Head Traveling Crane-TPI -27 DEC 2023 | REJECTED | No | 2023-12-19 | Almutairi, Yasser Aied | 2023-12-19 |  |  | 2023-12-19 |  | 2500 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2010 | AL SHARFIYAH, 132kV S/S # 8386-AL-SHARAFIYAH SS#8386-Over Head Traveling Crane-TPI -27 DEC 2023 | INCOMPLETE | No |  | Almutairi, Yasser Aied | 2023-12-19 |  |  |  |  | 2500 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2011 | AL SHARFIYAH, 132kV S/S # 8386-AL-SHARAFIYAH SS#8386-Over Head Traveling Crane-TPI -27 DEC 2023 | APPROVED | No | 2023-12-19 | Abas, Mohammed Fekry | 2023-12-24 | 2023-12-24 |  |  |  | 2500 | 4919 | 0 | STANDARD | Atlas Support and Services | SAR | 2500 | APPROVED |  |  | 2023-12-31 | 0 | 7 | Kumar, Mr. Ranjan | -45284 | 7
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2038 | AL SHARFIYAH, 132kV S/S # 8386-HVAC For AL-Sharafyah SS | APPROVED | No | 2023-12-25 | Abas, Mohammed Fekry | 2023-12-26 | 2023-12-26 |  |  |  | 1600000 | 4933 | 0 | STANDARD | Ramz Alataa Company for Trading | SAR | 1600000 | APPROVED |  |  | 2024-01-08 | 0 | 13 | Alhadi, Khalid | -45286 | 13
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2056 | AL SHARFIYAH, 132kV S/S # 8386-Telecom PO 8144 to be in oracle | APPROVED | No | 2023-12-28 | Abas, Mohammed Fekry | 2024-01-01 | 2024-01-01 |  |  |  | 2850000 | 4952 | 0 | STANDARD | COGELEX CO. | SAR | 2850000 | APPROVED |  |  | 2024-01-16 | 0 | 15 | Kumar, Mr. Ranjan | -45292 | 15
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2085 | AL SHARFIYAH, 132kV S/S # 8386-Security System AL-Sharafyah | RETURNED | No | 2024-01-03 | Mohammed, Faisal Ansari | 2024-03-28 | 2024-01-07 | 2024-03-28 |  | PO already taken against PR No. 2128. This duplicate PR must be cancelled/deleted. | 861053 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45298 | -45298
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2128 | AL SHARFIYAH, 132kV S/S # 8386-Security system | APPROVED | No | 2024-01-09 | Abas, Mohammed Fekry | 2024-01-10 | 2024-01-10 |  |  |  | 861053 | 4984 | 0 | STANDARD | Reda Trading & Development Co. for Machinery & Equipment Ltd(S) | SAR | 613573 | APPROVED |  |  | 2024-01-25 | 247480 | 15 | Mohammed, Faisal Ansari | -45301 | 15
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2144 | AL SHARFIYAH, 132kV S/S # 8386-SWGR 13.8KV PO 8107 to be in oracle | RETURNED | No | 2024-01-09 | Kumar, Mr. Ranjan | 2025-01-27 | 2024-01-10 | 2025-01-27 |  | This PR is duplicated henece returning, PR 2174 and PO 5004 is already approved | 7128800 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45301 | -45301
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2174 | AL SHARFIYAH, 132kV S/S # 8386-8107-HV1388-0 MV Switchgear for Al Sharyiyah - ALFANAR | APPROVED | No | 2024-01-15 | Abas, Mohammed Fekry | 2024-01-21 | 2024-01-21 |  |  |  | 7100000 | 5004 | 0 | STANDARD | ALFANAR CO | SAR | 6970000 | APPROVED |  |  | 2024-01-30 | 130000 | 9 | Kumar, Mr. Ranjan | -45312 | 9
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2175 | AL SHARFIYAH, 132kV S/S # 8386-8075-HV1388-0 signed by NIT-GIS -AL-Sharafyah | APPROVED | No | 2024-01-15 | Abas, Mohammed Fekry | 2024-01-21 | 2024-01-21 |  |  |  | 11412525 | 5013 | 0 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 11412525 | APPROVED |  |  | 2024-02-01 | 0 | 11 | Babic, Marian | -45312 | 11
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2182 | AL SHARFIYAH, 132kV S/S # 8386-INDOOR & OUTDOOR Lighting Fixtures - Al Sharfiyah | RETURNED | No | 2024-01-16 | Kumar, Mr. Ranjan | 2025-09-11 | 2024-01-21 | 2025-09-11 |  | PO 5029 issued, in this PR only one item was used (Photo cell). Rest returned. | 220 | 5029 | 1 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 0 | APPROVED |  |  | 2025-03-04 | 220 |  | Kumar, Mr. Ranjan | -45312 | 408
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2182 | AL SHARFIYAH, 132kV S/S # 8386-INDOOR & OUTDOOR Lighting Fixtures - Al Sharfiyah | RETURNED | No | 2024-01-16 | Kumar, Mr. Ranjan | 2025-09-11 | 2024-01-21 | 2025-09-11 |  | PO 5029 issued, in this PR only one item was used (Photo cell). Rest returned. | 44265 | 5029 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 39838.5 | APPROVED |  |  | 2024-03-18 | 4426.5 |  | Basha, Syed Kafeel | -45312 | 57
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2182 | AL SHARFIYAH, 132kV S/S # 8386-INDOOR & OUTDOOR Lighting Fixtures - Al Sharfiyah | RETURNED | No | 2024-01-16 | Kumar, Mr. Ranjan | 2025-09-11 | 2024-01-21 | 2025-09-11 |  | PO 5029 issued, in this PR only one item was used (Photo cell). Rest returned. | 44045 | [5 empty] | 0 |  |  |  |  | 0 |  | Basha, Syed Kafeel | -45312 | -45312
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2482 | AL SHARFIYAH, 132kV S/S # 8386-MV Cables Armor Type | APPROVED | No | 2024-02-06 | Abas, Mohammed Fekry | 2024-02-07 | 2024-02-10 |  |  |  | 813150 | 5310 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 810881.25 | APPROVED |  |  | 2024-07-21 | 2268.75 | 162 | Muhammad, Muhammad Atif | -45332 | 162
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2580 | AL SHARFIYAH, 132kV S/S # 8386-compeleted amount of the power transformer of alsharafyah ss to be in oracle | RETURNED | No | 2024-02-18 | Babic, Marian | 2024-04-15 | 2024-02-20 | 2024-04-15 |  | as discussed | 75000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45342 | -45342
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2581 | AL SHARFIYAH, 132kV S/S # 8386-Electrical Subcontractor-full amount to be merged with previous PR due to the approved Budget -task number -17131 | APPROVED | No | 2024-02-18 | Abas, Mohammed Fekry | 2024-02-19 | 2024-02-20 |  |  |  | 160000 | 5129 | 0 | STANDARD | City Crowns Energy | SAR | 160000 | APPROVED |  |  | 2024-06-03 | 0 | 104 | Kumar, Mr. Ranjan | -45342 | 104
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2582 | AL SHARFIYAH, 132kV S/S # 8386-AUX-Trans-Full amount to be merged with previous PR due to the Change order and approved budget | APPROVED | No | 2024-02-18 | Abas, Mohammed Fekry | 2024-02-19 | 2024-02-20 |  |  |  | 186000 | 4537 | 1 | STANDARD | UNITED TRANSFORMERS ELECTRIC COMPANY (UTEC) | SAR | 27200 | APPROVED |  |  | 2024-06-09 | 158800 | 110 | Eranhikkal, Mr. Riyaz Mohammed | -45342 | 110
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2583 | AL SHARFIYAH, 132kV S/S # 8386-patch panel-for alsharafyah SS PO 8112 | RETURNED | No | 2024-02-18 | Mohammed, Faisal Ansari | 2024-03-31 | 2024-02-20 | 2024-03-31 |  | PO has already been taken by the concerned engineer with another PR. Please cancel/delete this PR as it is not required. | 175000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45342 | -45342
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2590 | AL SHARFIYAH, 132kV S/S # 8386-crane 500 Tones or more or less | RETURNED | No | 2024-02-19 | Badhman, Saeed | 2024-05-14 | 2024-02-20 | 2024-05-14 |  | Not needed, po issued | 70000 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45342 | -45342
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2663 | AL SHARFIYAH, 132kV S/S # 8386-added amount to PR of Crane 2590-Crane | APPROVED | No | 2024-02-24 | Abas, Mohammed Fekry | 2024-02-25 | 2024-02-26 |  |  |  | 100000 | 5190 | 0 | STANDARD | MOHAMMED HAMAD AL-AHMADE FOR TRADING AND CONSTRACTION | SAR | 50000 | APPROVED |  |  | 2024-03-24 | 50000 | 27 | Badhman, Saeed | -45348 | 27
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2684 | AL SHARFIYAH, 132kV S/S # 8386-Electrical instaltion | APPROVED | No | 2024-02-26 | Abas, Mohammed Fekry | 2024-02-26 | 2024-02-26 |  |  |  | 1500000 | 5129 | 0 | STANDARD | City Crowns Energy | SAR | 1500000 | APPROVED |  |  | 2024-06-03 | 0 | 98 | Kumar, Mr. Ranjan | -45348 | 98
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2753 | AL SHARFIYAH, 132kV S/S # 8386-Alsharfiyah - RFQ- Sockets/ receptacles | INCOMPLETE | No |  | Almutairi, Yasser Aied | 2024-03-04 |  |  |  |  | 446.25 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2759 | AL SHARFIYAH, 132kV S/S # 8386-manual PO to be in system-8112 | APPROVED | No | 2024-03-04 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 6665500 | 5231 | 0 | STANDARD | ALFANAR CO | SAR | 6580000 | APPROVED |  |  | 2024-03-19 | 85500 | 12 | Basha, Syed Kafeel | -45358 | 12
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2770 | AL SHARFIYAH, 132kV S/S # 8386-MV Cable single Core *50mm | APPROVED | No | 2024-03-04 | Abas, Mohammed Fekry | 2024-03-13 | 2024-03-13 |  |  |  | 67500 | 5310 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 40623.6 | APPROVED |  |  | 2024-07-21 | 26876.4 | 130 | Muhammad, Muhammad Atif | -45364 | 130
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2815 | AL SHARFIYAH, 132kV S/S # 8386-MV Cables Termination Kits BOQ | REJECTED | No | 2024-03-12 | Almutairi, Yasser Aied | 2024-03-12 |  |  | 2024-03-12 |  | 145000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2817 | AL SHARFIYAH, 132kV S/S # 8386-Design Agency | REJECTED | No | 2024-03-13 | Almutairi, Yasser Aied | 2024-03-13 |  |  | 2024-03-13 |  | 163620 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2820 | AL SHARFIYAH, 132kV S/S # 8386-MV Termnation kit 13.8KV ALSharafyah | APPROVED | No | 2024-03-13 | Abas, Mohammed Fekry | 2024-03-17 | 2024-03-19 |  |  |  | 139262 | 5327 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 125350 | APPROVED |  |  | 2024-04-28 | 13912 | 40 | Muhammad, Muhammad Atif | -45370 | 40
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2825 | AL SHARFIYAH, 132kV S/S # 8386-Cable Tray and Support-Manual PO to be in oracle | RETURNED | No | 2024-03-14 | Badhman, Saeed | 2024-03-27 | 2024-03-19 | 2024-03-27 |  | Please resubmit it with the right figures as per vendor's qoutation | 92963.73 | 5279 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 92963.73 | APPROVED |  |  | 2024-12-22 | 0 |  | Badhman, Saeed | -45370 | 278
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2826 | AL SHARFIYAH, 132kV S/S # 8386-Cable Tray for AL-sharafyah SS | RETURNED | No | 2024-03-14 | Badhman, Saeed | 2024-03-27 | 2024-03-19 | 2024-03-27 |  | Please resubmit it as per vendor's qoutaiton. | 114697.77 | 5279 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 114697.77 | APPROVED |  |  | 2024-12-22 | 0 |  | Badhman, Saeed | -45370 | 278
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2832 | AL SHARFIYAH, 132kV S/S # 8386-Cable Tray and Ledder | APPROVED | No | 2024-03-17 | Abas, Mohammed Fekry | 2024-03-19 | 2024-03-19 |  |  |  | 29647.8 | 5279 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 29647.8 | APPROVED |  |  | 2024-12-22 | 0 | 278 | Badhman, Saeed | -45370 | 278
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2870 | AL SHARFIYAH, 132kV S/S # 8386-Design Agency Manual PO to be in oracle | APPROVED | No | 2024-03-20 | Abas, Mohammed Fekry | 2024-03-23 | 2024-03-24 |  |  |  | 349998.75 | 5286 | 0 | STANDARD | Bahrawy Consultancy Group B.C.G | USD | 349998.75 | APPROVED |  |  | 2024-03-28 | 0 | 4 | Kumar, Mr. Ranjan | -45375 | 4
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2871 | AL SHARFIYAH, 132kV S/S # 8386-CT-Split Core | REJECTED | No | 2024-03-20 | Almutairi, Yasser Aied | 2024-03-20 |  |  | 2024-03-20 |  | 163620 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2872 | AL SHARFIYAH, 132kV S/S # 8386-CT Split Core -1.2.1.5.6-Signed-4654-HV1388-0 | APPROVED | No | 2024-03-20 | Abas, Mohammed Fekry | 2024-03-23 | 2024-03-24 |  |  |  | 177120 | 4654 | 2 | STANDARD | Power Trading T&D | EUR | 177120 | APPROVED |  |  | 2024-03-28 | 0 | 4 | Babic, Marian | -45375 | 4
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 2945 | AL SHARFIYAH, 132kV S/S # 8386-ACSR | RETURNED | No | 2024-03-28 | Kumar, Mr. Ranjan | 2024-04-04 | 2024-04-02 | 2024-04-04 |  | PR value is SAR to be corrected | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45384 | -45384
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 3066 | AL SHARFIYAH, 132kV S/S # 8386-Fiber optic Scope for AL-sharafyah -Supply and installtion and testing -subm lump trunkey | APPROVED | No | 2024-04-21 | Abas, Mohammed Fekry | 2024-04-22 | 2024-04-23 |  |  |  | 270000 | 5712 | 0 | STANDARD | MIDDLE EAST FIBER CABLE MANUFACTURING CO. | SAR | 140000 | APPROVED |  |  | 2024-07-10 | 130000 | 78 | Abdulqader, Ahmed Abdulhalim | -45405 | 78
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 3090 | AL SHARFIYAH, 132kV S/S # 8386-Tray-ladders | APPROVED | No | 2024-04-22 | Abas, Mohammed Fekry | 2024-04-22 | 2024-04-23 |  |  |  | 44753.99 | 5279 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 44753.99 | APPROVED |  |  | 2024-12-22 | 0 | 243 | Badhman, Saeed | -45405 | 243
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 3127 | AL SHARFIYAH, 132kV S/S # 8386-AC units-3 Tones Capacity= BTU 36000 | APPROVED | No | 2024-04-24 | Abas, Mohammed Fekry | 2024-04-30 | 2024-04-30 |  |  |  | 8000 | 5486 | 0 | STANDARD | Current Makers For Contracting EST | SAR | 7900 | APPROVED |  |  | 2024-05-23 | 100 | 23 | Babic, Marian | -45412 | 23
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 3128 | AL SHARFIYAH, 132kV S/S # 8386-AC Units | APPROVED | No | 2024-04-24 | Abas, Mohammed Fekry | 2024-04-30 | 2024-04-30 |  |  |  | 150000 | 5486 | 0 | STANDARD | Current Makers For Contracting EST | SAR | 118500 | APPROVED |  |  | 2024-05-23 | 31500 | 23 | Babic, Marian | -45412 | 23
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 3129 | AL SHARFIYAH, 132kV S/S # 8386-PTR to be in the system-Manual PO 8077 | APPROVED | No | 2024-04-24 | Abas, Mohammed Fekry | 2024-04-30 | 2024-04-30 |  |  |  | 15819000 | 5497 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 15819000 | APPROVED |  |  | 2024-05-20 | 0 | 20 | Babic, Marian | -45412 | 20
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 3231 | AL SHARFIYAH, 132kV S/S # 8386-LIGHTNING CUM LIGHTING MASTS | APPROVED | No | 2024-04-30 | Abas, Mohammed Fekry | 2024-05-01 | 2024-05-01 |  |  |  | 58300 | 5510 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 58300 | APPROVED |  |  | 2024-07-02 | 0 | 62 | Muhammad, Muhammad Atif | -45413 | 62
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 3402 | AL SHARFIYAH, 132kV S/S # 8386-AL-Shrafyah SS-Testing | APPROVED | No | 2024-05-15 | Abas, Mohammed Fekry | 2024-05-15 | 2024-05-16 |  |  |  | 1000000 | 4571 | 0 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 577613 | APPROVED |  |  | 2024-05-26 | 422387 | 10 | Babic, Marian | -45428 | 10
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 3424 | AL SHARFIYAH, 132kV S/S # 8386-Precast lab test & inspection | REJECTED | No | 2024-05-16 | Almutairi, Yasser Aied | 2024-05-16 |  |  | 2024-05-16 |  | 20145 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 3425 | AL SHARFIYAH, 132kV S/S # 8386-Precast lab test & inspection | REJECTED | No | 2024-05-16 | Almutairi, Yasser Aied | 2024-05-16 |  |  | 2024-05-16 |  | 20145 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 3526 | AL SHARFIYAH, 132kV S/S # 8386-FAT for SAS Panles Atlas PO- | APPROVED | No | 2024-05-29 | Abas, Mohammed Fekry | 2024-05-31 | 2024-05-31 |  |  |  | 14000 | 4936 | 0 | STANDARD | Atlas Support and Services | SAR | 14000 | APPROVED |  |  | 2024-06-10 | 0 | 10 | Kumar, Mr. Ranjan | -45443 | 10
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 3548 | AL SHARFIYAH, 132kV S/S # 8386-Y/G | INCOMPLETE | No |  | Almutairi, Yasser Aied | 2024-06-02 |  |  |  |  | 24000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 3608 | AL SHARFIYAH, 132kV S/S # 8386-PR-DOUBLE METALLIC FUSE BOX | REJECTED | No | 2024-06-06 | Almutairi, Yasser Aied | 2024-06-06 |  |  | 2024-06-06 |  | 651455.22 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 3609 | AL SHARFIYAH, 132kV S/S # 8386--Lightning PO- added with 3231 -DOUBLE METALLIC FUSE BOX | APPROVED | No | 2024-06-06 | Abas, Mohammed Fekry | 2024-06-12 | 2024-06-13 |  |  |  | 250 | 5510 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 250 | APPROVED |  |  | 2024-07-02 | 0 | 19 | Muhammad, Muhammad Atif | -45456 | 19
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 3645 | AL SHARFIYAH, 132kV S/S # 8386-LV-Cables | RETURNED | No | 2024-06-12 | Muhammad, Muhammad Atif | 2024-07-28 | 2024-06-13 | 2024-07-28 |  | These are remaining Lines with wrong price. PO already issued and approved in the system with new PRs for these items. No need for these lines. | 832615.62 | 5767 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 832615.62 | APPROVED |  |  | 2024-07-17 | 0 |  | Muhammad, Muhammad Atif | -45456 | 34
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 3645 | AL SHARFIYAH, 132kV S/S # 8386-LV-Cables | RETURNED | No | 2024-06-12 | Muhammad, Muhammad Atif | 2024-07-28 | 2024-06-13 | 2024-07-28 |  | These are remaining Lines with wrong price. PO already issued and approved in the system with new PRs for these items. No need for these lines. | 8806.3 | [5 empty] | 0 |  |  |  |  | 0 |  | Muhammad, Muhammad Atif | -45456 | -45456
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 3646 | AL SHARFIYAH, 132kV S/S # 8386-Cables | APPROVED | No | 2024-06-12 | Abas, Mohammed Fekry | 2024-06-12 | 2024-06-13 |  |  |  | 7253.4 | 5767 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 7253.4 | APPROVED |  |  | 2024-07-17 | 0 | 34 | Muhammad, Muhammad Atif | -45456 | 34
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 3664 | AL SHARFIYAH, 132kV S/S # 8386-Precast Lab& Inspection | APPROVED | No | 2024-06-23 | Abas, Mohammed Fekry | 2024-06-27 | 2024-06-27 |  |  |  | 26285 | 5760 | 0 | STANDARD | Al Muhandis Nizar Al Kurdi Al Milli Engineering Consultants | SAR | 26285 | APPROVED |  |  | 2024-08-05 | 0 | 39 | Abdulqader, Ahmed Abdulhalim | -45470 | 39
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 3694 | AL SHARFIYAH, 132kV S/S # 8386-LV Cables | APPROVED | No | 2024-06-30 | Abas, Mohammed Fekry | 2024-07-01 | 2024-07-01 |  |  |  | 17145.72 | 5767 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 17145.72 | APPROVED |  |  | 2024-07-17 | 0 | 16 | Muhammad, Muhammad Atif | -45474 | 16
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 3695 | AL SHARFIYAH, 132kV S/S # 8386-Cables | APPROVED | No | 2024-06-30 | Abas, Mohammed Fekry | 2024-07-01 | 2024-07-01 |  |  |  | 8533.7 | 5767 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 8533.7 | APPROVED |  |  | 2024-07-17 | 0 | 16 | Muhammad, Muhammad Atif | -45474 | 16
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 3739 | AL SHARFIYAH, 132kV S/S # 8386-Surge arrestor | REJECTED | No | 2024-07-02 | Almutairi, Yasser Aied | 2024-07-02 |  |  | 2024-07-02 |  | 12042 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 4332 | AL SHARFIYAH, 132kV S/S # 8386-Manual PO to be in the system -Optical Fiber Management Rack-6011 | APPROVED | No | 2024-09-01 | Abas, Mohammed Fekry | 2024-09-04 | 2024-09-05 |  |  |  | 36000 | 6011 | 0 | STANDARD | AMWAJ TELECOMMUNICATION MFG. CO. | SAR | 36000 | APPROVED |  |  | 2024-09-11 | 0 | 6 | Abdulqader, Ahmed Abdulhalim | -45540 | 6
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 4333 | AL SHARFIYAH, 132kV S/S # 8386-8386 - Clamps & connectors Manual PO-1.2.1.6.3 | RETURNED | No | 2024-09-01 | Kumar, Mr. Ranjan | 2024-12-08 | 2024-09-05 | 2024-12-08 |  | Please change the PR as per Aruthi details | 30255 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45540 | -45540
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 4394 | AL SHARFIYAH, 132kV S/S # 8386-ACSR-Coneector | RETURNED | No | 2024-09-09 | Kumar, Mr. Ranjan | 2024-11-18 | 2024-09-11 | 2024-11-18 |  | PR 4333 already received and PO 6175 already created, this is duplicate PR hence returning. | 10000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45546 | -45546
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 4658 | AL SHARFIYAH, 132kV S/S # 8386-Oil | REJECTED | No | 2024-10-13 | Elmeligy, Usama Shaban Gomaa | 2024-10-13 |  |  | 2024-10-13 |  | 55000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 4700 | AL SHARFIYAH, 132kV S/S # 8386-Oil Filteration | APPROVED | No | 2024-10-16 | Abas, Mohammed Fekry | 2024-10-17 | 2024-10-17 |  |  |  | 55000 | 5695 | 0 | STANDARD | PetroZone International Constructing Company - 27976 | SAR | 55000 | APPROVED |  |  | 2024-11-03 | 0 | 17 | Kumar, Mr. Ranjan | -45582 | 17
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 4716 | AL SHARFIYAH, 132kV S/S # 8386-132 KV Surge Arrester | APPROVED | No | 2024-10-17 | Abas, Mohammed Fekry | 2024-10-20 | 2024-10-21 |  |  |  | 50215.14 | 6197 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 49372.2 | APPROVED |  |  | 2024-10-29 | 842.94 | 8 | Kumar, Mr. Ranjan | -45586 | 8
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 5000 | AL SHARFIYAH, 132kV S/S # 8386-LV&MV Cable Accessories | APPROVED | No | 2024-11-20 | Abas, Mohammed Fekry | 2024-12-11 | 2024-12-12 |  |  |  | 86248.5 | 6539 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 76192.5 | APPROVED |  |  | 2024-12-24 | 10056 | 12 | Alqadhi, Abdulrahman Abdulghani | -45638 | 12
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 5136 | AL SHARFIYAH, 132kV S/S # 8386-Lighting Installation Subcontractor | REJECTED | No | 2024-12-04 | Elmeligy, Usama Shaban Gomaa | 2024-12-04 |  |  | 2024-12-04 | to modify | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 5137 | AL SHARFIYAH, 132kV S/S # 8386-Lighting Installation Subcontractor | APPROVED | No | 2024-12-04 | Abas, Mohammed Fekry | 2024-12-08 | 2024-12-09 |  |  |  | 280000 | 5129 | 1 | STANDARD | City Crowns Energy | SAR | 280000 | APPROVED |  |  | 2025-03-03 | 0 | 84 | Kumar, Mr. Ranjan | -45635 | 84
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 5138 | AL SHARFIYAH, 132kV S/S # 8386-Lighting Material | APPROVED | No | 2024-12-04 | Abas, Mohammed Fekry | 2024-12-08 | 2024-12-09 |  |  |  | 110256 | 6599 | 0 | STANDARD | Jahaz Ayed Al-Rashidi and Partner for Trad and count | SAR | 110256 | APPROVED |  |  | 2025-01-14 | 0 | 36 | Kumar, Mr. Ranjan | -45635 | 36
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 5276 | AL SHARFIYAH, 132kV S/S # 8386-Ami Testing and Comissioning | APPROVED | No | 2024-12-26 | Abas, Mohammed Fekry | 2024-12-29 | 2024-12-30 |  |  |  | 40000 | 5231 | 1 | STANDARD | ALFANAR CO | SAR | 40000 | APPROVED |  |  | 2025-03-24 | 0 | 84 | Kumar, Mr. Ranjan | -45656 | 84
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 5277 | AL SHARFIYAH, 132kV S/S # 8386-Oil Sample | APPROVED | No | 2024-12-26 | Abas, Mohammed Fekry | 2024-12-29 | 2024-12-30 |  |  |  | 29007 | 6706 | 0 | STANDARD | Energy Distributor Co. Ltd | SAR | 29007 | APPROVED |  |  | 2025-01-26 | 0 | 27 | Kumar, Mr. Ranjan | -45656 | 27
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 5847 | AL SHARFIYAH, 132kV S/S # 8386-Fire Stop Material | APPROVED | No | 2025-02-11 | Abas, Mohammed Fekry | 2025-02-18 | 2025-02-18 |  |  |  | 95800 | 6737 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 95800 | APPROVED |  |  | 2025-02-20 | 0 | 2 | Kumar, Mr. Ranjan | -45706 | 2
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 5848 | AL SHARFIYAH, 132kV S/S # 8386-Batteries & Battery Charger Service For Testing and Comissioning. | RETURNED | No | 2025-02-11 | Kumar, Mr. Ranjan | 2025-07-13 | 2025-02-18 | 2025-07-13 |  | Vendor consider this scope as discount while finalization of PO 7493 for Rumah Project 125 VDC System. | 19000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45706 | -45706
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 5849 | AL SHARFIYAH, 132kV S/S # 8386-Civil Subcontractor Additional Work | APPROVED | No | 2025-02-11 | Abas, Mohammed Fekry | 2025-02-19 | 2025-02-19 |  |  |  | 110000 | 4375 | 2 | STANDARD | Al Sahda Contracting Est. | SAR | 110000 | APPROVED |  |  | 2025-03-24 | 0 | 33 | Kumar, Mr. Ranjan | -45707 | 33
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 5856 | AL SHARFIYAH, 132kV S/S # 8386-Lighting Fixtures | APPROVED | No | 2025-02-12 | Abas, Mohammed Fekry | 2025-02-18 | 2025-02-18 |  |  |  | 50224 | 5029 | 1 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 50224 | APPROVED |  |  | 2025-03-04 | 0 | 14 | Kumar, Mr. Ranjan | -45706 | 14
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 5953 | AL SHARFIYAH, 132kV S/S # 8386-Grounding Material | APPROVED | No | 2025-02-18 | Abas, Mohammed Fekry | 2025-02-20 | 2025-02-22 |  |  |  | 174528.67 | 6944 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 174528.67 | APPROVED |  |  | 2025-03-03 | 0 | 9 | Abdulqader, Ahmed Abdulhalim | -45710 | 9
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 5997 | AL SHARFIYAH, 132kV S/S # 8386-Indoor & Outdoor Sockets and Disconnectors. | APPROVED | No | 2025-02-19 | Abas, Mohammed Fekry | 2025-02-20 | 2025-02-22 |  |  |  | 91227 | 6598 | 0 | STANDARD | Tawasul International Trad.Est. | SAR | 91227 | APPROVED |  |  | 2025-03-05 | 0 | 11 | Kumar, Mr. Ranjan | -45710 | 11
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 6000 | AL SHARFIYAH, 132kV S/S # 8386-Lighting Switches | APPROVED | No | 2025-02-19 | Abas, Mohammed Fekry | 2025-02-20 | 2025-02-22 |  |  |  | 7218.9 | 6733 | 0 | STANDARD | Tawasul International Trad.Est. | SAR | 7218.9 | APPROVED |  |  | 2025-03-02 | 0 | 8 | Alqadhi, Abdulrahman Abdulghani | -45710 | 8
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 6001 | AL SHARFIYAH, 132kV S/S # 8386-Pumps | APPROVED | No | 2025-02-19 | Abas, Mohammed Fekry | 2025-02-20 | 2025-02-22 |  |  |  | 85200 | 5484 | 4 | STANDARD | United Park Company | SAR | 85200 | APPROVED |  |  | 2025-02-27 | 0 | 5 | Mohammed, Faisal Ansari | -45710 | 5
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 6014 | AL SHARFIYAH, 132kV S/S # 8386-Yellow Green Cables | APPROVED | No | 2025-02-20 | Abas, Mohammed Fekry | 2025-02-26 | 2025-02-26 |  |  |  | 496654.63 | 6968 | 0 | STANDARD | ALFANAR CO | SAR | 496654.63 | APPROVED |  |  | 2025-03-17 | 0 | 19 | Kumar, Mr. Ranjan | -45714 | 19
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 6047 | AL SHARFIYAH, 132kV S/S # 8386-SS Grounding Accessories material- to replace Cancelled PR#5324 | APPROVED | No | 2025-02-25 | Abas, Mohammed Fekry | 2025-03-02 | 2025-03-03 |  |  | SS Grounding Accessories material- to replace Cancelled PR#5324 | 79722 | 6700 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 79722 | APPROVED |  |  | 2025-03-09 | 0 | 6 | Mohammed, Faisal Ansari | -45719 | 6
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 6489 | AL SHARFIYAH, 132kV S/S # 8386-Supply Of Clamps and Connectors | APPROVED | No | 2025-05-01 | Abas, Mohammed Fekry | 2025-05-18 | 2025-05-18 |  |  |  | 8093.4 | 6175 | 0 | STANDARD | Arruti Subestaciones , S.A.U | EUR | 8093.4 | APPROVED |  |  | 2025-05-26 | 0 | 8 | Kumar, Mr. Ranjan | -45795 | 8
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 6490 | AL SHARFIYAH, 132kV S/S # 8386-Cable Accessories | RETURNED | No | 2025-05-01 | Kumar, Mr. Ranjan | 2025-07-29 | 2025-05-18 | 2025-07-29 |  | Incomplete PR | 23253.12 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45795 | -45795
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 7060 | AL SHARFIYAH, 132kV S/S # 8386-TFR and DSM Re-configuration and Testing | APPROVED | No | 2025-07-10 | Abas, Mohammed Fekry | 2025-07-14 | 2025-07-14 |  |  |  | 80000 | 7532 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 70000 | APPROVED |  |  | 2025-08-25 | 10000 | 42 | Kumar, Mr. Ranjan | -45852 | 42
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 7533 | %construction of alsherfya | RETURNED | No | 2025-08-27 | Akhtar, Farhan | 2025-10-13 | 2025-08-28 | 2025-10-13 |  | No Budget in the system | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45897 | -45897
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 7947 | Substation Furniture | APPROVED | No | 2025-10-13 | Abas, Mohammed Fekry | 2025-10-16 | 2025-10-17 |  |  | Substation Furniture | 0 | 7779 | 0 | STANDARD | ALISMAIL INDUSTRIAL CO.(S) | SAR | 29360 | APPROVED |  |  | 2025-11-06 | -29360 | 20 | Akhtar, Farhan | -45947 | 20
105-65 | AL SHARFIYAH, 132kV S/S # 8386 | 8416 | Battery System-Convert Manual PO No. 8336 to orcale PO | APPROVED | No | 2025-12-03 | Abas, Mohammed Fekry | 2025-12-09 | 2025-12-09 |  |  |  | 0 | 8021 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 515000 | APPROVED | 2025-12-15 | 2026-01-08 | 2026-01-13 | -515000 | 35 | Kumar, Mr. Ranjan | 30 | 35
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 1129 | AL-HADA, 132/13.8kV S/S # 8246-Civil subcontractor | APPROVED | No | 2023-03-13 | Abas, Mohammed Fekry | 2023-03-13 | 2023-03-13 |  |  |  | 9000000 | 4379 | 0 | STANDARD | Al Sahda Contracting Est. | SAR | 7450000 | APPROVED |  |  | 2023-04-11 | 1550000 | 29 | Kumar, Mr. Ranjan | -44998 | 29
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 1129 | AL-HADA, 132/13.8kV S/S # 8246-Civil subcontractor | APPROVED | No | 2023-03-13 | Abas, Mohammed Fekry | 2023-03-13 | 2023-03-13 |  |  |  | 9000000 | 4379 | 1 | STANDARD | Al Sahda Contracting Est. | SAR | 8500000 | REQUIRES REAPPROVAL |  |  |  | 500000 | 1056 | Abdelraouf, Islam ِAdel Hanafy | -44998 | -44998
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 1183 | AL-HADA, 132/13.8kV S/S # 8246-Overhead Crane | INCOMPLETE | No |  | Alharbi, Meshal | 2023-04-11 |  |  |  |  | 50000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 1184 | AL-HADA, 132/13.8kV S/S # 8246-overhead crane | APPROVED | No | 2023-04-11 | Abas, Mohammed Fekry | 2023-04-12 | 2023-04-13 |  |  |  | 500000 | 4461 | 0 | STANDARD | SAUDI CRANES & STEEL WORKS FACTORY LTD | SAR | 152500 | APPROVED |  |  | 2023-05-25 | 347500 | 42 | Kumar, Mr. Ranjan | -45029 | 42
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 1187 | AL-HADA, 132/13.8kV S/S # 8246-RMU | APPROVED | No | 2023-04-11 | Abas, Mohammed Fekry | 2023-04-12 | 2023-04-13 |  |  |  | 200000 | 4499 | 0 | STANDARD | ALFANAR CO | SAR | 150000 | APPROVED |  |  | 2023-06-11 | 50000 | 59 | Babic, Marian | -45029 | 59
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 1189 | AL-HADA, 132/13.8kV S/S # 8246-PRECAST | REJECTED | No | 2023-04-11 | Al-Asmi, Ibrahim Abdulkhaliq | 2023-04-11 | 2023-04-11 |  | 2023-04-19 |  | 1500000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45027 | -45027
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 1229 | AL-HADA, 132/13.8kV S/S # 8246-Jib Crane | APPROVED | No | 2023-05-07 | Abas, Mohammed Fekry | 2023-05-08 | 2023-05-08 |  |  |  | 100000 | 4461 | 0 | STANDARD | SAUDI CRANES & STEEL WORKS FACTORY LTD | SAR | 70000 | APPROVED |  |  | 2023-05-25 | 30000 | 17 | Kumar, Mr. Ranjan | -45054 | 17
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 1232 | AL-HADA, 132/13.8kV S/S # 8246-Mobilization Offices | REJECTED | No | 2023-05-07 | Alharbi, Meshal | 2023-05-07 |  |  | 2023-05-07 |  | 369600 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 1245 | AL-HADA, 132/13.8kV S/S # 8246-Sign board and Fence | APPROVED | No | 2023-05-10 | Abas, Mohammed Fekry | 2023-05-11 | 2023-05-14 |  |  |  | 57500 | 4459 | 0 | STANDARD | Al-Kayan Al-Zahi General Contracting | SAR | 54700 | APPROVED |  |  | 2023-05-21 | 2800 | 7 | Kumar, Mr. Ranjan | -45060 | 7
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 1267 | AL-HADA, 132/13.8kV S/S # 8246-FF&FA | APPROVED | No | 2023-05-16 | Abas, Mohammed Fekry | 2023-05-23 | 2023-05-24 |  |  |  | 1600000 | 4714 | 0 | STANDARD | Equipment & Technical Services Co.(ETECHS) | SAR | 1575000 | APPROVED |  |  | 2023-11-27 | 25000 | 187 | Kumar, Mr. Ranjan | -45070 | 187
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 1329 | AL-HADA, 132/13.8kV S/S # 8246-TPI for PTR for AL-HADA | APPROVED | No | 2023-06-20 | Abas, Mohammed Fekry | 2023-07-05 | 2023-07-05 |  |  |  | 33350 | 4543 | 0 | STANDARD | VELOSI SAUDI ARABIA CO LTD | SAR | 14300 | APPROVED |  |  | 2023-07-13 | 19050 | 8 | Akhtar, Farhan | -45112 | 8
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 1344 | AL-HADA, 132/13.8kV S/S # 8246-AUX 13.8KV | REJECTED | No | 2023-07-08 | Abas, Mohammed Fekry | 2023-07-11 | 2023-07-09 |  | 2023-07-11 |  | 156000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45116 | -45116
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 1348 | AL-HADA, 132/13.8kV S/S # 8246-AUX 13.8KV | APPROVED | No | 2023-07-12 | Abas, Mohammed Fekry | 2023-07-21 | 2023-07-23 |  |  |  | 170000 | 4570 | 0 | STANDARD | UNITED TRANSFORMERS ELECTRIC COMPANY (UTEC) | SAR | 158800 | APPROVED |  |  | 2023-08-29 | 11200 | 37 | Kumar, Mr. Ranjan | -45130 | 37
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 1358 | AL-HADA, 132/13.8kV S/S # 8246-TPI FOR DC DC Convertor AL-Hada | APPROVED | No | 2023-07-19 | Abas, Mohammed Fekry | 2023-07-21 | 2023-07-23 |  |  |  | 3000 | 4549 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 2606.25 | APPROVED |  |  | 2023-07-30 | 393.75 | 7 | Akhtar, Farhan | -45130 | 7
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 1379 | AL-HADA, 132/13.8kV S/S # 8246-Under Grounding uitilty AL-Hada SS | RETURNED | No | 2023-08-01 | Badhman, Saeed | 2024-05-14 | 2023-08-07 | 2024-05-14 |  | Hold up | 100000 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45145 | -45145
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 1392 | AL-HADA, 132/13.8kV S/S # 8246-SIS | RETURNED | No | 2023-08-08 | Babic, Marian | 2024-03-26 | 2023-10-09 | 2024-03-26 |  | this scope is not required | 3672500 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45208 | -45208
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 1413 | AL-HADA, 132/13.8kV S/S # 8246-Mobilization Site offcies | RETURNED | No | 2023-08-15 | Babic, Marian | 2024-04-15 | 2023-08-21 | 2024-04-15 |  | as discussed | 117500 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45159 | -45159
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 1462 | AL-HADA, 132/13.8kV S/S # 8246-TPI for AL-Hada SS Telecom | INCOMPLETE | No |  | Almutairi, Yasser Aied | 2023-09-06 |  |  |  | as discussed | 8700 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 1463 | AL-HADA, 132/13.8kV S/S # 8246-TPI for AL-Hada SS Telecom | APPROVED | No | 2023-09-06 | Abas, Mohammed Fekry | 2023-09-09 | 2023-09-10 |  |  |  | 8700 | 4606 | 0 | STANDARD | Atlas Support and Services | SAR | 8700 | APPROVED |  |  | 2023-09-25 | 0 | 15 | Akhtar, Farhan | -45179 | 15
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 1556 | AL-HADA, 132/13.8kV S/S # 8246-CT Split Core -AL-Hada | APPROVED | No | 2023-10-05 | Abas, Mohammed Fekry | 2023-10-09 | 2023-10-09 |  |  |  | 180000 | 4655 | 0 | STANDARD | Power Trading T&D | EUR | 177120 | APPROVED |  |  | 2023-10-17 | 2880 | 8 | Babic, Marian | -45208 | 8
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 2368 | AL-HADA, 132/13.8kV S/S # 8246-Telecom Panels for AL-hada SS | APPROVED | No | 2024-01-30 | Abas, Mohammed Fekry | 2024-04-01 | 2024-04-02 |  |  |  | 2150000 | 5478 | 0 | STANDARD | COGELEX CO. | SAR | 2150000 | APPROVED |  |  | 2024-05-16 | 0 | 44 | Kumar, Mr. Ranjan | -45384 | 44
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 2928 | AL-HADA, 132/13.8kV S/S # 8246-Telecom Panels - 75% OF THE TOTAL PO VALUE | REJECTED | No | 2024-03-28 | Almutairi, Yasser Aied | 2024-03-28 |  |  | 2024-03-28 |  | 2167500 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 4873 | AL-HADA, 132/13.8kV S/S # 8246-13.8kV Switchgear - Manual P.O 8108 - HV - 1388 -0 | APPROVED | No | 2024-11-10 | Abas, Mohammed Fekry | 2024-11-13 | 2024-11-13 |  |  |  | 7470000 | 6491 | 0 | STANDARD | ALFANAR CO | SAR | 7470000 | APPROVED |  |  | 2024-11-17 | 0 | 4 | Kumar, Mr. Ranjan | -45609 | 4
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 4876 | AL-HADA, 132/13.8kV S/S # 8246-Neutral Grounding Resistors - Manual P.O. 8138 - HV 1388 - 0 | APPROVED | No | 2024-11-10 | Abas, Mohammed Fekry | 2024-11-13 | 2024-11-13 |  |  |  | 61042.5 | 6496 | 0 | STANDARD | National Switchgears | USD | 61042.5 | APPROVED |  |  | 2024-11-20 | 0 | 7 | Kumar, Mr. Ranjan | -45609 | 7
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 4882 | AL-HADA, 132/13.8kV S/S # 8246-Power Transformer -Manual PO -8076-HV-1388-0 | REJECTED | No | 2024-11-10 | Yasmin, Ahmed Elsayed Mohamed | 2024-11-11 | 2024-11-10 |  | 2024-11-13 |  | 15084000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45606 | -45606
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 4889 | AL-HADA, 132/13.8kV S/S # 8246-Protection, Control and SAS - Manual P.O. 8113 - HV 1388-0 | APPROVED | No | 2024-11-10 | Abas, Mohammed Fekry | 2024-11-13 | 2024-11-13 |  |  |  | 5500000 | 6492 | 0 | STANDARD | ALFANAR CO | SAR | 5500000 | APPROVED |  |  | 2024-11-17 | 0 | 4 | Kumar, Mr. Ranjan | -45609 | 4
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 4899 | AL-HADA, 132/13.8kV S/S # 8246-GIS - Manual P.O. 8074-HV-1388-0 | APPROVED | No | 2024-11-11 | Abas, Mohammed Fekry | 2024-11-14 | 2024-11-17 |  |  |  | 9436275 | 6830 | 0 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 9128775 | APPROVED |  |  | 2025-02-05 | 307500 | 80 | Babic, Marian | -45613 | 80
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 4904 | AL-HADA, 132/13.8kV S/S # 8246-PR FOR CYBERSECURTY AL-HADA 8246 | APPROVED | No | 2024-11-11 | Abas, Mohammed Fekry | 2024-11-14 | 2024-11-17 |  |  |  | 1700000 | 6844 | 0 | STANDARD | ACET SOLUTIONS LLC | SAR | 800000 | APPROVED |  |  | 2025-03-18 | 900000 | 121 | Kumar, Mr. Ranjan | -45613 | 121
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 4940 | AL-HADA, 132/13.8kV S/S # 8246-Power Transformer - Manual P.O. 8078 HV 1388-0 | APPROVED | No | 2024-11-14 | Abas, Mohammed Fekry | 2024-11-17 | 2024-11-17 |  |  |  | 15294000 | 6536 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 15294000 | APPROVED |  |  | 2024-11-27 | 0 | 10 | Babic, Marian | -45613 | 10
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 5038 | AL-HADA, 132/13.8kV S/S # 8246-Battery and Battery Chargers. | APPROVED | No | 2024-11-24 | Abas, Mohammed Fekry | 2025-01-21 | 2025-01-23 | 2025-01-05 |  | Amount is not suffeciant, please revise the PR amount | 465000 | 6841 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 465000 | APPROVED |  |  | 2025-02-26 | 0 | 34 | Alqadhi, Abdulrahman Abdulghani | -45680 | 34
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 5042 | AL-HADA, 132/13.8kV S/S # 8246-AC and DC Distribution Boards + Lighting Panels | APPROVED | No | 2024-11-24 | Siddiqui, Imran Mabood | 2024-11-27 | 2024-11-27 |  |  |  | 982000 | 6794 | 0 | STANDARD | ALFANAR CO | SAR | 900000 | IN PROCESS |  |  |  | 82000 | 431 | Babic, Marian | -45623 | -45623
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 5042 | AL-HADA, 132/13.8kV S/S # 8246-AC and DC Distribution Boards + Lighting Panels | APPROVED | No | 2024-11-24 | Siddiqui, Imran Mabood | 2024-11-27 | 2024-11-27 |  |  |  | 982000 | [5 empty] | 0 |  |  |  |  | 0 |  | Alqadhi, Abdulrahman Abdulghani | -45623 | -45623
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 5075 | AL-HADA, 132/13.8kV S/S # 8246-Civil & Structural Works - Scope addition of GIS basement + MV Tunnels | RETURNED | No | 2024-11-28 | Tananeh, Khalid Jamal | 2025-08-20 | 2025-02-05 | 2025-08-20 |  | It's not required; the site is still not ready | 900000 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45693 | -45693
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 6704 | AL-HADA, 132/13.8kV S/S # 8246-Engineering Design Services- Manual PO 8095 HV-1388 | APPROVED | No | 2025-05-25 | Abas, Mohammed Fekry | 2025-06-17 | 2025-06-17 |  |  | 2.1 BCG Design Services Manual Purchase Order | 350000 | 7277 | 1 | STANDARD | Bahrawy Consultancy Group B.C.G | USD | 349998.75 | APPROVED |  |  | 2025-06-26 | 1.25 | 9 | Kumar, Mr. Ranjan | -45825 | 9
105-66 | AL-HADA, 132/13.8kV S/S # 8246 | 8800 | Civil and Architectural works | IN PROCESS | No | 2026-01-27 | Yasmin, Ahmed Elsayed Mohamed | 2026-01-27 | 2026-01-27 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46049 | -46049
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1001 | NIC NR & NIC EV-2 132/33kV S/S-TPI for FAT of Power Transformers at NIC Project | APPROVED | No | 2023-01-15 | Abas, Mohammed Fekry | 2023-01-18 | 2023-01-18 |  |  |  | 44200 | 4323 | 0 | STANDARD | VELOSI SAUDI ARABIA CO LTD | SAR | 44200 | APPROVED |  |  | 2023-01-25 | 0 | 7 | Kumar, Mr. Ranjan | -44944 | 7
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1055 | NIC NR & NIC EV-2 132/33kV S/S-Services -Soil investigation works | APPROVED | No | 2023-02-11 | Abas, Mohammed Fekry | 2023-02-12 | 2023-02-13 |  |  |  | 113200 | 5240 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 113200 | APPROVED |  |  | 2024-03-27 | 0 | 408 | Kumar, Mr. Ranjan | -44970 | 408
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1070 | NIC NR & NIC EV-2 132/33kV S/S-cyber security | APPROVED | No | 2023-02-13 | Abas, Mohammed Fekry | 2023-02-15 | 2023-02-16 |  |  |  | 3400000 | 4355 | 0 | STANDARD | ALFANAR CO | SAR | 3400000 | APPROVED |  |  | 2023-03-16 | 0 | 28 | Kumar, Mr. Ranjan | -44973 | 28
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1071 | NIC NR & NIC EV-2 132/33kV S/S-Crane | RETURNED | No | 2023-02-13 | Kumar, Mr. Ranjan | 2023-02-20 | 2023-02-16 | 2023-02-20 |  | PR value is less the Final offer, Please revised PR value - Final discounted offer from Vendor is SAR 376,000 | 315580 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -44973 | -44973
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1086 | NIC NR & NIC EV-2 132/33kV S/S-Excavation work | APPROVED | No | 2023-02-26 | Abas, Mohammed Fekry | 2023-02-28 | 2023-03-01 |  |  |  | 1123520 | 4335 | 0 | STANDARD | Sam OG Construction | SAR | 1123520 | APPROVED |  |  | 2023-03-16 | 0 | 15 | Kumar, Mr. Ranjan | -44986 | 15
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1087 | NIC NR & NIC EV-2 132/33kV S/S-Overhead Crane | RETURNED | No | 2023-02-26 | Kumar, Mr. Ranjan | 2024-03-14 | 2023-03-01 | 2024-03-14 |  | PO 4354 for Crane is already created in Oracle, this seems PR from old system | 379500 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -44986 | -44986
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1107 | NIC NR & NIC EV-2 132/33kV S/S-furniture for site office | APPROVED | No | 2023-03-07 | Abas, Mohammed Fekry | 2023-03-09 | 2023-03-12 |  |  |  | 66000 | 4351 | 0 | STANDARD | DANAH AL RAYEDA ESTABLISHMENT | SAR | 66000 | APPROVED |  |  | 2023-03-16 | 0 | 4 | Babic, Marian | -44997 | 4
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1127 | NIC NR & NIC EV-2 132/33kV S/S-Power Transformer | APPROVED | No | 2023-03-13 | Abas, Mohammed Fekry | 2023-03-13 | 2023-03-13 |  |  |  | 65370000 | 4818 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 65370000 | APPROVED |  |  | 2023-12-20 | 0 | 282 | Kumar, Mr. Ranjan | -44998 | 282
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1310 | NIC NR & NIC EV-2 132/33kV S/S-FAT for NER | APPROVED | No | 2023-06-07 | Abas, Mohammed Fekry | 2023-06-13 | 2023-06-14 |  |  |  | 3300 | 4531 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 3300 | APPROVED |  |  | 2023-07-23 | 0 | 39 | Kumar, Mr. Ranjan | -45091 | 39
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1311 | NIC NR & NIC EV-2 132/33kV S/S-FAT TPI for DC-DC Convertor | APPROVED | No | 2023-06-07 | Abas, Mohammed Fekry | 2023-06-13 | 2023-06-14 |  |  |  | 2607 | 4532 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 5212.5 | APPROVED |  |  | 2023-07-19 | -2605.5 | 35 | Kumar, Mr. Ranjan | -45091 | 35
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1312 | NIC NR & NIC EV-2 132/33kV S/S-FAT TPI For Capacitor Bank (CT, VT, Reactor & Surge Arrester) | APPROVED | No | 2023-06-07 | Abas, Mohammed Fekry | 2023-06-13 | 2023-06-14 |  |  |  | 23930 | 4585 | 0 | STANDARD | SGS GULF LIMITED | USD | 20325 | APPROVED |  |  | 2023-08-30 | 3605 | 77 | Kumar, Mr. Ranjan | -45091 | 77
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1313 | NIC NR & NIC EV-2 132/33kV S/S-FAT TPI for HV & MV Surge Arrester | APPROVED | No | 2023-06-08 | Abas, Mohammed Fekry | 2023-06-13 | 2023-06-14 |  |  |  | 4500 | 4536 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 4500 | APPROVED |  |  | 2023-07-10 | 0 | 26 | Kumar, Mr. Ranjan | -45091 | 26
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1332 | NIC NR & NIC EV-2 132/33kV S/S-TPI for FAT of 125V DC-DC Converter | RETURNED | No | 2023-06-22 | Kumar, Mr. Ranjan | 2024-04-01 | 2023-07-03 | 2024-04-01 |  | FAT done by Blanket agreement, so this old PR is returned | 2607 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45110 | -45110
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1401 | NIC NR & NIC EV-2 132/33kV S/S-HVAC System | APPROVED | No | 2023-08-09 | Abas, Mohammed Fekry | 2023-08-14 | 2023-08-15 |  |  |  | 5550000 | 4569 | 0 | STANDARD | Magna Contracting Co | SAR | 5140000 | APPROVED |  |  | 2023-08-28 | 410000 | 13 | Kumar, Mr. Ranjan | -45153 | 13
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1444 | NIC NR & NIC EV-2 132/33kV S/S-Furniture | APPROVED | No | 2023-09-03 | Abas, Mohammed Fekry | 2023-09-04 | 2023-09-05 |  |  |  | 9136.75 | 4351 | 1 | STANDARD | DANAH AL RAYEDA ESTABLISHMENT | SAR | 7945 | APPROVED |  |  | 2023-09-10 | 1191.75 | 5 | Babic, Marian | -45174 | 5
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1454 | NIC NR & NIC EV-2 132/33kV S/S-TPI for FAT of Capcitor Units for NIC NR & NIC EV2 | APPROVED | No | 2023-09-04 | Abas, Mohammed Fekry | 2023-09-10 | 2023-09-12 |  |  |  | 7687.55 | 4879 | 0 | STANDARD | SGS GULF LIMITED | USD | 7687.55 | APPROVED |  |  | 2024-01-21 | 0 | 131 | Kumar, Mr. Ranjan | -45181 | 131
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1461 | NIC NR & NIC EV-2 132/33kV S/S-TPI for FAT of 132KV GIS LCC - NIC NORTH & EV2 Substations | APPROVED | No | 2023-09-06 | Abas, Mohammed Fekry | 2023-09-10 | 2023-09-12 |  |  |  | 25312.5 | 4812 | 0 | STANDARD | SGS GULF LIMITED | USD | 25312.5 | APPROVED |  |  | 2024-01-03 | 0 | 113 | Kumar, Mr. Ranjan | -45181 | 113
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1513 | NIC NR & NIC EV-2 132/33kV S/S-Supply of Lightning Masts with Accessories for NIC NORTH & EV2 Substations | RETURNED | No | 2023-09-18 | Kumar, Mr. Ranjan | 2024-06-09 | 2023-09-21 | 2024-06-09 |  | Budget line reference error, new PR received in exchange of this PR. | 240000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45190 | -45190
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1516 | NIC NR & NIC EV-2 132/33kV S/S-TPI for FAT of Overhead Travelling Crane for NIC NORTH & NIC EV2 Substations | APPROVED | No | 2023-09-19 | Abas, Mohammed Fekry | 2023-09-26 | 2023-09-26 |  |  |  | 4000 | 4709 | 0 | STANDARD | ARAB INSPECTION & Q.A.CO. | SAR | 4000 | APPROVED |  |  | 2023-11-19 | 0 | 54 | Kumar, Mr. Ranjan | -45195 | 54
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1519 | NIC NR & NIC EV-2 132/33kV S/S-TPI of FAT of Protection System for NIC NORTH & NIC EV2 Substations | RETURNED | No | 2023-09-20 | Kumar, Mr. Ranjan | 2024-04-01 | 2023-09-26 | 2024-04-01 |  | FAT done by Blanket agreement, so this old PR is returned | 23200 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45195 | -45195
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1539 | NIC NR & NIC EV-2 132/33kV S/S-Safety observation and welfare facilities closure at NIC EV2 & NIC north | RETURNED | No | 2023-10-02 | Kumar, Mr. Ranjan | 2025-04-06 | 2023-10-06 | 2025-04-06 |  | PO rejected by finance for budget line. PO issued manually. | 324700 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45205 | -45205
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1545 | NIC NR & NIC EV-2 132/33kV S/S-FAT of Capcitor Bank Units for NIC North & NIC Ev2 Substations | APPROVED | No | 2023-10-03 | Abas, Mohammed Fekry | 2023-10-04 | 2023-10-06 |  |  |  | 9225 | 4879 | 0 | STANDARD | SGS GULF LIMITED | USD | 9225 | APPROVED |  |  | 2024-01-21 | 0 | 107 | Kumar, Mr. Ranjan | -45205 | 107
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1551 | NIC NR & NIC EV-2 132/33kV S/S-Security System for NIC NORTH & NIC EV2 Substations | APPROVED | No | 2023-10-04 | Abas, Mohammed Fekry | 2023-10-04 | 2023-10-06 |  |  |  | 2233855 | 4961 | 0 | STANDARD | Reda Trading & Development Co. for Machinery & Equipment Ltd(S) | SAR | 1756535 | APPROVED |  |  | 2024-01-25 | 477320 | 111 | Mohammed, Faisal Ansari | -45205 | 111
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1561 | NIC NR & NIC EV-2 132/33kV S/S-Power Transformer offloading | APPROVED | No | 2023-10-08 | Abas, Mohammed Fekry | 2023-10-14 | 2023-10-15 |  |  |  | 270000 | 4663 | 0 | STANDARD | Global Union Alliance Company Ltd | SAR | 270000 | APPROVED |  |  | 2023-10-31 | 0 | 16 | Babic, Marian | -45214 | 16
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1638 | NIC NR & NIC EV-2 132/33kV S/S-Soil Resistivity Measurement for NIC EV2 Substation | APPROVED | No | 2023-10-28 | Abas, Mohammed Fekry | 2023-10-29 | 2023-10-30 |  |  |  | 20000 | 4722 | 0 | STANDARD | International Agent Commercial Company(S) | SAR | 5500 | APPROVED |  |  | 2023-12-11 | 14500 | 42 | Kumar, Mr. Ranjan | -45229 | 42
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1639 | NIC NR & NIC EV-2 132/33kV S/S-Container for Site | APPROVED | No | 2023-10-29 | Abas, Mohammed Fekry | 2023-11-07 | 2023-11-07 |  |  |  | 34800 | 4705 | 0 | STANDARD | NAMMA CARGO SERVICES CO LTD - Khobar | SAR | 34800 | APPROVED |  |  | 2023-11-21 | 0 | 14 | Abuhammad, Samir | -45237 | 14
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1642 | NIC NR & NIC EV-2 132/33kV S/S-Fire System | APPROVED | No | 2023-10-30 | Abas, Mohammed Fekry | 2023-10-30 | 2023-10-31 |  |  |  | 6595291 | 4704 | 0 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 6595291 | APPROVED |  |  | 2023-12-03 | 0 | 33 | Kumar, Mr. Ranjan | -45230 | 33
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1642 | NIC NR & NIC EV-2 132/33kV S/S-Fire System | APPROVED | No | 2023-10-30 | Abas, Mohammed Fekry | 2023-10-30 | 2023-10-31 |  |  |  | 6595291 | 4704 | 1 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 6595291 | REQUIRES REAPPROVAL |  |  |  | 0 | 824 | Kumar, Mr. Ranjan | -45230 | -45230
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1693 | NIC NR & NIC EV-2 132/33kV S/S-Supply of ACSR Conductors | APPROVED | No | 2023-11-12 | Abas, Mohammed Fekry | 2023-11-14 | 2023-11-14 |  |  |  | 9284.68 | 4747 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 9284.68 | APPROVED |  |  | 2023-11-23 | 0 | 9 | Babic, Marian | -45244 | 9
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1702 | NIC NR & NIC EV-2 132/33kV S/S-Electrical Installation Subcontract for NIC NORTH & NIC EV2 | APPROVED | No | 2023-11-13 | Abas, Mohammed Fekry | 2023-11-14 | 2023-11-14 |  |  |  | 7800000 | 4839 | 0 | STANDARD | City Crowns Energy | SAR | 7150000 | APPROVED |  |  | 2023-12-28 | 650000 | 44 | Kumar, Mr. Ranjan | -45244 | 44
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1725 | NIC NR & NIC EV-2 132/33kV S/S-Supply of 33KV MV Termination, Heat Shrinkable type for NIC NR & NIC EV2 Substations | APPROVED | No | 2023-11-14 | Abas, Mohammed Fekry | 2023-11-15 | 2023-11-16 |  |  |  | 218419.25 | 4732 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 209222.25 | APPROVED |  |  | 2024-01-07 | 9197 | 52 | Babic, Marian | -45246 | 52
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1727 | NIC NR & NIC EV-2 132/33kV S/S-Supply of ACSR Fittings, Clambs & Connectors for NIC NR & NIC EV2 Substations | APPROVED | No | 2023-11-14 | Abas, Mohammed Fekry | 2023-11-14 | 2023-11-15 |  |  |  | 18749.19 | 4721 | 0 | STANDARD | Arruti Subestaciones , S.A.U | EUR | 18682.8 | APPROVED |  |  | 2023-11-26 | 66.39 | 11 | Babic, Marian | -45245 | 11
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1745 | NIC NR & NIC EV-2 132/33kV S/S-civil subcontractor | REJECTED | No | 2023-11-14 | Aseri, Amir | 2023-11-14 |  |  | 2023-11-14 |  | 51262539.09 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1746 | NIC NR & NIC EV-2 132/33kV S/S-Civil works for NIC NR & EV2 | APPROVED | No | 2023-11-14 | Abas, Mohammed Fekry | 2023-11-15 | 2023-11-16 |  |  |  | 51780342.52 | 4754 | 0 | STANDARD | Randa Izzat Ibrahim Raydan for Construction Company | SAR | 51780342.52 | APPROVED |  |  | 2023-12-03 | 0 | 17 | Kumar, Mr. Ranjan | -45246 | 17
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1762 | NIC NR & NIC EV-2 132/33kV S/S-safety Requirements (Completed Scope) | APPROVED | No | 2023-11-15 | Abas, Mohammed Fekry | 2023-11-15 | 2023-11-16 |  |  |  | 160942.7 | 4927 | 0 | STANDARD | Construction Expertise Est. | SAR | 445847.7 | APPROVED |  |  | 2024-05-13 | -284905 | 179 | Kumar, Mr. Ranjan | -45246 | 179
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1763 | NIC NR & NIC EV-2 132/33kV S/S-Safety Requirements (Completed Scope) | APPROVED | No | 2023-11-15 | Abas, Mohammed Fekry | 2023-11-15 | 2023-11-16 |  |  |  | 181927.09 | 4927 | 0 | STANDARD | Construction Expertise Est. | SAR | 445847.7 | APPROVED |  |  | 2024-05-13 | -263920.61 | 179 | Kumar, Mr. Ranjan | -45246 | 179
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1764 | NIC NR & NIC EV-2 132/33kV S/S-Safety Requirments (Completed Scope) | APPROVED | No | 2023-11-15 | Abas, Mohammed Fekry | 2023-11-15 | 2023-11-16 |  |  |  | 115870 | 4927 | 0 | STANDARD | Construction Expertise Est. | SAR | 445847.7 | APPROVED |  |  | 2024-05-13 | -329977.7 | 179 | Kumar, Mr. Ranjan | -45246 | 179
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1919 | NIC NR & NIC EV-2 132/33kV S/S-TPI for FAT of Capacitor Banks | REJECTED | No | 2023-12-10 | Aseri, Amir | 2023-12-10 |  |  | 2023-12-10 |  | 3083.12 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1920 | NIC NR & NIC EV-2 132/33kV S/S-TPI for FAT of Capacitor Banks for NIC NORTH & NIC EV2 Substations | APPROVED | No | 2023-12-10 | Abas, Mohammed Fekry | 2023-12-13 | 2023-12-13 |  |  |  | 3083.12 | 4879 | 0 | STANDARD | SGS GULF LIMITED | USD | 3083.14 | APPROVED |  |  | 2024-01-21 | -0.02 | 39 | Kumar, Mr. Ranjan | -45273 | 39
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1962 | NIC NR & NIC EV-2 132/33kV S/S-TPI for FAT of 132KV GIS LCC Panels - NIC NORTH & NIC EV2 | APPROVED | No | 2023-12-14 | Abas, Mohammed Fekry | 2023-12-15 | 2023-12-17 |  |  |  | 375 | 4812 | 0 | STANDARD | SGS GULF LIMITED | USD | 375 | APPROVED |  |  | 2024-01-03 | 0 | 17 | Kumar, Mr. Ranjan | -45277 | 17
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 1963 | NIC NR & NIC EV-2 132/33kV S/S-LV Power Cables - NIC NORTH & EV2 Substations | REJECTED | No | 2023-12-14 | Aseri, Amir | 2023-12-14 |  |  | 2023-12-14 |  | 2154378 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 2008 | NIC NR & NIC EV-2 132/33kV S/S-TPI for FAT of Capacitor Banks | APPROVED | No | 2023-12-18 | Abas, Mohammed Fekry | 2023-12-20 | 2023-12-21 |  |  |  | 586.54 | 4879 | 0 | STANDARD | SGS GULF LIMITED | USD | 586.54 | APPROVED |  |  | 2024-01-21 | 0 | 31 | Kumar, Mr. Ranjan | -45281 | 31
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 2046 | NIC NR & NIC EV-2 132/33kV S/S-NDT Test for Crane Runway Beam - NIC NORTH & EV2 Substations | APPROVED | No | 2023-12-28 | Abas, Mohammed Fekry | 2024-01-01 | 2024-01-01 |  |  |  | 8400 | 4949 | 0 | STANDARD | TUV Rheinland Arabia LLC | SAR | 8400 | APPROVED |  |  | 2024-01-14 | 0 | 13 | Kumar, Mr. Ranjan | -45292 | 13
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 2222 | NIC NR & NIC EV-2 132/33kV S/S-Steel lighitning Masts & Lighting Poles | REJECTED | No | 2024-01-20 | Aseri, Amir | 2024-01-20 |  |  | 2024-01-20 |  | 2200000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 2251 | NIC NR & NIC EV-2 132/33kV S/S-Supply of Fuel (Diesel) to project Construction of Neom Project Site | APPROVED | No | 2024-01-22 | Abas, Mohammed Fekry | 2024-02-11 | 2024-02-12 |  |  |  | 226086.95 | 5017 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 226086.95 | APPROVED |  |  | 2024-02-25 | 0 | 13 | Akhtar, Farhan | -45334 | 13
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 2295 | NIC NR & NIC EV-2 132/33kV S/S-Overhead Travelling Crane for NIC NORTH & EV2 Substations | APPROVED | No | 2024-01-27 | Abas, Mohammed Fekry | 2024-01-29 | 2024-01-29 |  |  |  | 376000 | 4354 | 0 | STANDARD | SAUDI CRANES & STEEL WORKS FACTORY LTD | SAR | 376000 | APPROVED |  |  | 2024-02-25 | 0 | 27 | Babic, Marian | -45320 | 27
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 2296 | NIC NR & NIC EV-2 132/33kV S/S-TPI for FAT of MV Cables - NIC NORTH & EV2 Substations | APPROVED | No | 2024-01-27 | Abas, Mohammed Fekry | 2024-01-29 | 2024-01-29 |  |  |  | 12000 | 5236 | 0 | STANDARD | Atlas Support and Services | SAR | 6000 | APPROVED |  |  | 2024-03-25 | 6000 | 56 | Kumar, Mr. Ranjan | -45320 | 56
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 2340 | NIC NR & NIC EV-2 132/33kV S/S-Supply of Consumable Stationery | APPROVED | No | 2024-01-29 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 20056.76 | 5036 | 0 | STANDARD | TALABAT AL MAKTAB CO.LTD | SAR | 20056.76 | APPROVED |  |  | 2024-02-15 | 0 | 11 | Akhtar, Farhan | -45326 | 11
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 2548 | NIC NR & NIC EV-2 132/33kV S/S-Site safety Requirement for Management Visit | RETURNED | No | 2024-02-13 | Kumar, Mr. Ranjan | 2024-05-22 | 2024-02-15 | 2024-05-22 |  | During negotiating for PO 4927, 4928 & 8618, Vendor considred SAR 43,977 as discount hence it was agreed to to cancel this PR and PO 5271. | 43977 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45337 | -45337
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 2709 | NIC NR & NIC EV-2 132/33kV S/S-Printers - NIC NR & EV2 | APPROVED | No | 2024-02-28 | Abas, Mohammed Fekry | 2024-02-29 | 2024-03-03 |  |  |  | 24008.55 | 5667 | 0 | STANDARD | Fast Computers for Trading Est | SAR | 24008.55 | APPROVED |  |  | 2024-06-05 | 0 | 94 | Badhman, Saeed | -45354 | 94
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 2809 | NIC NR & NIC EV-2 132/33kV S/S-AC Units | APPROVED | No | 2024-03-10 | Abas, Mohammed Fekry | 2024-03-13 | 2024-03-13 |  |  |  | 444400 | 5232 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 396000 | APPROVED |  |  | 2024-04-02 | 48400 | 20 | Abuhammad, Samir | -45364 | 20
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 2816 | NIC NR & NIC EV-2 132/33kV S/S-Supply of 33kV MV Termination, Heat Shrinkable Type for NIC NORTH NIC EV2 Substations | APPROVED | No | 2024-03-12 | Abas, Mohammed Fekry | 2024-03-13 | 2024-03-14 |  |  | Please confirm if Lugs to be included and share the BOQ, Cable Data sheet via email to Mr. Ranjan | 75632.75 | 4732 | 1 | STANDARD | Nima Arabia Company Limited | SAR | 67437.75 | APPROVED |  |  | 2024-06-03 | 8195 | 81 | Babic, Marian | -45365 | 81
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 2843 | NIC NR & NIC EV-2 132/33kV S/S-132KV GIS Equipement for NIC NORTH Substation | APPROVED | No | 2024-03-18 | Abas, Mohammed Fekry | 2024-03-19 | 2024-03-19 |  |  |  | 31781250 | 4508 | 1 | STANDARD | Hitachi Energy Ltd | SAR | 31781250 | APPROVED |  |  | 2024-04-03 | 0 | 15 | Kumar, Mr. Ranjan | -45370 | 15
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 2844 | NIC NR & NIC EV-2 132/33kV S/S-132KV GIS Equipment for NIC EV2 Substation | APPROVED | No | 2024-03-18 | Abas, Mohammed Fekry | 2024-03-19 | 2024-03-19 |  |  |  | 30093750 | 4509 | 1 | STANDARD | Hitachi Energy Ltd | SAR | 30093750 | APPROVED |  |  | 2024-04-02 | 0 | 14 | Kumar, Mr. Ranjan | -45370 | 14
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 2930 | NIC NR & NIC EV-2 132/33kV S/S-Rental temporary charger 125V ,100 A=2 Nos | APPROVED | No | 2024-03-28 | Abas, Mohammed Fekry | 2024-03-31 | 2024-03-31 |  |  |  | 61000 | 5326 | 0 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 61000 | APPROVED |  |  | 2024-04-21 | 0 | 21 | Babic, Marian | -45382 | 21
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 2939 | NIC NR & NIC EV-2 132/33kV S/S-Earthing Materials for NIC NORTH & EV2 Substations | REJECTED | No | 2025-05-15 | Taha, Mohammed Alfadhel Alsayed | 2025-05-15 |  |  | 2025-05-15 |  | 480666.59 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 3037 | NIC NR & NIC EV-2 132/33kV S/S-New Supply of Consumable Stationery | APPROVED | No | 2024-04-16 | Abas, Mohammed Fekry | 2024-04-20 | 2024-04-22 |  |  |  | 55000 | 5448 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 35011 | APPROVED |  |  | 2024-05-14 | 19989 | 22 | Akhtar, Farhan | -45404 | 22
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 3058 | NIC NR & NIC EV-2 132/33kV S/S-Rental Ambulance for Job site | REJECTED | No | 2024-04-18 | Issa, Amr Ali | 2024-04-25 | 2024-04-22 |  | 2024-04-25 |  | 262200 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45404 | -45404
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 3060 | NIC NR & NIC EV-2 132/33kV S/S-TPI for FAT of HVAC PACU for NIC NORTH SS | APPROVED | No | 2024-04-18 | Abas, Mohammed Fekry | 2024-04-23 | 2024-04-23 |  |  |  | 2500 | 5431 | 0 | STANDARD | Atlas Support and Services | SAR | 2500 | APPROVED |  |  | 2024-04-29 | 0 | 6 | Kumar, Mr. Ranjan | -45405 | 6
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 3123 | NIC NR & NIC EV-2 132/33kV S/S-Re-Location for site office - NIC North | APPROVED | No | 2024-04-24 | Abas, Mohammed Fekry | 2024-04-25 | 2024-04-25 |  |  |  | 100000 | 5628 | 0 | STANDARD | Construction Expertise Est. | SAR | 72500 | APPROVED |  |  | 2024-08-25 | 27500 | 122 | Kumar, Mr. Ranjan | -45407 | 122
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 3125 | NIC NR & NIC EV-2 132/33kV S/S-Supply for Capacitor Bank (Manual PO - 8133 NIC North) | APPROVED | No | 2024-04-24 | Abas, Mohammed Fekry | 2024-04-25 | 2024-04-28 |  |  |  | 5023600 | 5491 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 5023600 | APPROVED |  |  | 2024-05-13 | 0 | 15 | Kumar, Mr. Ranjan | -45410 | 15
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 3126 | NIC NR & NIC EV-2 132/33kV S/S-Supply for Capacitor Bank (Manual PO - 8134 NIC EV2) | APPROVED | No | 2024-04-24 | Abas, Mohammed Fekry | 2024-04-25 | 2024-04-28 |  |  |  | 4323600 | 5490 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 4323600 | APPROVED |  |  | 2024-05-13 | 0 | 15 | Kumar, Mr. Ranjan | -45410 | 15
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 3184 | NIC NR & NIC EV-2 132/33kV S/S-SAS Console / Furniture for NIC NORTH & EV2 Substations | APPROVED | No | 2024-04-28 | Abas, Mohammed Fekry | 2024-04-28 | 2024-04-29 |  |  |  | 120000 | 5548 | 0 | STANDARD | ALFANAR CO | SAR | 110000 | APPROVED |  |  | 2024-06-24 | 10000 | 56 | Babic, Marian | -45411 | 56
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 3320 | NIC NR & NIC EV-2 132/33kV S/S-Earthing Materials for NIC NORTH & EV2 Substations | RETURNED | No | 2024-05-07 | Babic, Marian | 2024-05-28 | 2024-05-12 | 2024-05-28 |  | Please revise the unit price to be 101 SAR | 272642.01 | 5635 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 259462.56 | APPROVED |  |  | 2024-06-09 | 13179.45 |  | Babic, Marian | -45424 | 28
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 3385 | NIC NR & NIC EV-2 132/33kV S/S-Rental Ambulance for Job site | APPROVED | No | 2024-05-12 | Abas, Mohammed Fekry | 2024-05-16 | 2024-05-17 |  |  |  | 57000 | 5584 | 0 | STANDARD | CAPITAL AMBULANCE FOR MEDICAL SERVICES | SAR | 57000 | APPROVED |  |  | 2024-05-26 | 0 | 9 | Kumar, Mr. Ranjan | -45429 | 9
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 3427 | NIC NR & NIC EV-2 132/33kV S/S-TESTING ENGINEER | RETURNED | No | 2024-05-19 | Kumar, Mr. Ranjan | 2024-07-17 | 2024-05-20 | 2024-07-17 |  | PMT is planning to hire Testing Engineer so this PR to renting manpower is not required. Once the requirement is firmed then you are requested to raise a new PR. | 60000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45432 | -45432
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 3452 | NIC NR & NIC EV-2 132/33kV S/S-Re-Location for site office - NIC North | APPROVED | No | 2024-05-21 | Abas, Mohammed Fekry | 2024-05-22 | 2024-05-22 |  |  |  | 100000 | 5628 | 0 | STANDARD | Construction Expertise Est. | SAR | 100000 | APPROVED |  |  | 2024-08-25 | 0 | 95 | Kumar, Mr. Ranjan | -45434 | 95
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 3472 | NIC NR & NIC EV-2 132/33kV S/S-SECURITY CONSULTANCY SERVICES | APPROVED | No | 2024-05-22 | Abas, Mohammed Fekry | 2024-05-22 | 2024-05-23 |  |  |  | 250000 | 5629 | 0 | STANDARD | Khaled Drewesh Office for Consulting Security (KDOCS) | SAR | 207000 | APPROVED |  |  | 2024-08-11 | 43000 | 80 | Kumar, Mr. Ranjan | -45435 | 80
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 3490 | NIC NR & NIC EV-2 132/33kV S/S-Supply MV Termination Kit | APPROVED | No | 2024-05-26 | Abas, Mohammed Fekry | 2024-05-26 | 2024-05-26 |  |  |  | 650000 | 5684 | 0 | STANDARD | CONSTRUCTION MATERIAL Valley EST | EUR | 633486.9 | APPROVED |  |  | 2024-07-25 | 16513.1 | 60 | Babic, Marian | -45438 | 60
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 3507 | NIC NR & NIC EV-2 132/33kV S/S-Supply & Installation of FOC for SAS System | APPROVED | No | 2024-05-28 | Abas, Mohammed Fekry | 2024-05-28 | 2024-05-28 |  |  |  | 1000000 | 5692 | 0 | STANDARD | MIDDLE EAST FIBER CABLE MANUFACTURING CO. | SAR | 777000 | APPROVED |  |  | 2024-07-18 | 223000 | 51 | Babic, Marian | -45440 | 51
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 3512 | NIC NR & NIC EV-2 132/33kV S/S-TPI for FAT of HVAC DDC Panels - NIC NORTH SS | APPROVED | No | 2024-05-28 | Abas, Mohammed Fekry | 2024-05-29 | 2024-05-30 |  |  |  | 2500 | 5670 | 0 | STANDARD | ARAB INSPECTION & Q.A.CO. | SAR | 2500 | APPROVED |  |  | 2024-06-05 | 0 | 6 | Kumar, Mr. Ranjan | -45442 | 6
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 3514 | NIC NR & NIC EV-2 132/33kV S/S-Manpower rental | APPROVED | No | 2024-05-28 | Abas, Mohammed Fekry | 2024-05-29 | 2024-05-29 |  |  |  | 109200 | 5762 | 0 | STANDARD | City Crowns Energy | SAR | 327600 | APPROVED |  |  | 2025-02-02 | -218400 | 249 | Babic, Marian | -45441 | 249
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 3519 | NIC NR & NIC EV-2 132/33kV S/S-Earthing | APPROVED | No | 2024-05-28 | Abas, Mohammed Fekry | 2024-05-29 | 2024-05-30 |  |  |  | 262600 | 5635 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 262600 | APPROVED |  |  | 2024-06-09 | 0 | 10 | Babic, Marian | -45442 | 10
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 3583 | NIC NR & NIC EV-2 132/33kV S/S-Lightning Masts & Lighting Poles (as per issued PO #5305) for NIC NORTH & EV2 Substations | APPROVED | No | 2024-06-03 | Abas, Mohammed Fekry | 2024-06-04 | 2024-06-04 |  |  |  | 172200 | 5305 | 0 | STANDARD | Hesham El-Sewedy Trading Co. LTD. | SAR | 172200 | APPROVED |  |  | 2024-07-01 | 0 | 27 | Kumar, Mr. Ranjan | -45447 | 27
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 3661 | NIC NR & NIC EV-2 132/33kV S/S-TPI for FAT of HVAC PACU - NIC NORTH SS | RETURNED | No | 2024-06-13 | Kumar, Mr. Ranjan | 2024-07-29 | 2024-06-23 | 2024-07-29 |  | Blancket agreement issued to Atls | 2500 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45466 | -45466
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 3720 | NIC NR & NIC EV-2 132/33kV S/S-Supply for Stationery & Pantry | APPROVED | No | 2024-07-01 | Abas, Mohammed Fekry | 2024-07-03 | 2024-07-03 |  |  |  | 50000 | 5773 | 0 | STANDARD | TALABAT AL MAKTAB CO.LTD | SAR | 41000 | APPROVED |  |  | 2024-07-12 | 9000 | 9 | Akhtar, Farhan | -45476 | 9
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 3806 | NIC NR & NIC EV-2 132/33kV S/S-TPI for FAT of HVAC DDC Panels for NIC EV2 SS | RETURNED | No | 2024-07-09 | Kumar, Mr. Ranjan | 2024-07-14 | 2024-07-10 | 2024-07-14 |  | Blanket agreeent to Atls is issued, Individual PO not required | 2000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45483 | -45483
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 4072 | NIC NR & NIC EV-2 132/33kV S/S-CONSTRUCTION WASTE MATERIAL REMOVAL DISPOSAL REQUEST | REJECTED | No | 2024-08-01 | Yamama, Loai Mohamed | 2024-08-14 | 2024-08-01 |  |  |  | 96000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45505 | -45505
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 4156 | NIC NR & NIC EV-2 132/33kV S/S-Supply and Apply of Fence & Gates Works for Dumping Area as per ENOWA/SEC Requirement at NIC EV2 Substation | REJECTED | No | 2024-08-14 | Yamama, Loai Mohamed | 2024-08-18 | 2024-08-18 |  | 2024-08-18 |  | 29550 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45522 | -45522
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 4261 | NIC NR & NIC EV-2 132/33kV S/S-Air Emission Test for Generators - NIC NR & EV2 | REJECTED | No | 2024-08-25 | Yamama, Loai Mohamed | 2024-09-02 | 2024-08-25 |  | 2024-09-02 |  | 1200 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45529 | -45529
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 4339 | NIC NR & NIC EV-2 132/33kV S/S-Supply of Lighting Receptacles for NIC NORTH & EV2 Substations | APPROVED | No | 2024-09-03 | Abas, Mohammed Fekry | 2024-09-05 | 2024-09-08 |  |  |  | 160500.01 | 6191 | 0 | STANDARD | Power House Company | SAR | 160500.01 | APPROVED |  |  | 2024-09-26 | 0 | 18 | Babic, Marian | -45543 | 18
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 4421 | NIC NR & NIC EV-2 132/33kV S/S-MV Cable Clamps - NIC NORTH & EV2 Substations | APPROVED | No | 2024-09-12 | Abas, Mohammed Fekry | 2025-01-22 | 2025-01-23 |  |  |  | 260000 | 7234 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 260000 | APPROVED |  |  | 2025-05-13 | 0 | 110 | Babic, Marian | -45680 | 110
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 4460 | NIC NR & NIC EV-2 132/33kV S/S-Supply of Lighting Receptacles for NIC NORTH & EV2 Substations (2) | APPROVED | No | 2024-09-15 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 160500.01 | 6191 | 0 | STANDARD | Power House Company | SAR | 160500.01 | APPROVED |  |  | 2024-09-26 | 0 | 4 | Babic, Marian | -45557 | 4
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 4465 | NIC NR & NIC EV-2 132/33kV S/S-Supply of Indoor & Outdoor Lighting fixtures with lamp for NIC NORTH & EV2 Substations | APPROVED | No | 2024-09-17 | Abas, Mohammed Fekry | 2025-01-21 | 2025-01-23 |  |  |  | 284340 | 7237 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 230315.4 | APPROVED |  |  | 2025-05-13 | 54024.6 | 110 | Babic, Marian | -45680 | 110
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 4561 | NIC NR & NIC EV-2 132/33kV S/S-Supply and Apply of Fence & Gates Works for Dumping Area as per ENOWA/SEC Requirement at NIC EV2 Substation | APPROVED | No | 2024-09-30 | Abas, Mohammed Fekry | 2024-10-03 | 2024-10-04 |  |  |  | 29550 | 5973 | 0 | STANDARD | Sam OG Construction | SAR | 29550 | APPROVED |  |  | 2024-10-29 | 0 | 25 | Kumar, Mr. Ranjan | -45569 | 25
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 4609 | NIC NR & NIC EV-2 132/33kV S/S-Excavation Works for NIC NORTH & EV2 Substations | APPROVED | No | 2024-10-05 | Abas, Mohammed Fekry | 2024-10-14 | 2024-10-14 |  |  |  | 1200000 | 4335 | 1 | STANDARD | Sam OG Construction | SAR | 1200000 | APPROVED |  |  | 2024-12-26 | 0 | 73 | Kumar, Mr. Ranjan | -45579 | 73
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 4647 | NIC NR & NIC EV-2 132/33kV S/S-Oil Filtration and Vacuum Machines Services - NIC NORTH & EV2 Substations | APPROVED | No | 2024-10-09 | Abas, Mohammed Fekry | 2024-10-16 | 2024-10-16 |  |  |  | 39500 | 6360 | 0 | STANDARD | Delta Energy Contracting Company | SAR | 35000 | APPROVED |  |  | 2024-10-30 | 4500 | 14 | Babic, Marian | -45581 | 14
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 4670 | NIC NR & NIC EV-2 132/33kV S/S-Civil construction works for NIC NORTH & EV2 (Amendment PO#8202-HV1401-R-01) | APPROVED | No | 2024-10-14 | Abas, Mohammed Fekry | 2024-10-16 | 2024-10-16 |  |  |  | 7480218.6 | 4754 | 1 | STANDARD | Randa Izzat Ibrahim Raydan for Construction Company | SAR | 7480218.6 | APPROVED |  |  | 2024-11-03 | 0 | 18 | Kumar, Mr. Ranjan | -45581 | 18
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 4753 | NIC NR & NIC EV-2 132/33kV S/S-Transformer Oil Analysis for NIC NORTH & EV2 Substations | APPROVED | No | 2024-10-21 | Abas, Mohammed Fekry | 2024-10-24 | 2024-10-27 |  |  |  | 150000 | 6593 | 0 | STANDARD | Saudi Arabian Engineering Company | SAR | 77420 | APPROVED |  |  | 2024-12-16 | 72580 | 50 | Babic, Marian | -45592 | 50
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 4766 | NIC NR & NIC EV-2 132/33kV S/S-Testing & Comissioning Services for NIC NORTH & EV2 Substations (Manual PO #8654-HV1401-0) | APPROVED | No | 2024-10-22 | Abas, Mohammed Fekry | 2024-10-27 | 2024-10-27 |  |  |  | 6034420 | 6392 | 0 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 6034420 | APPROVED |  |  | 2024-11-05 | 0 | 9 | Babic, Marian | -45592 | 9
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 4766 | NIC NR & NIC EV-2 132/33kV S/S-Testing & Comissioning Services for NIC NORTH & EV2 Substations (Manual PO #8654-HV1401-0) | APPROVED | No | 2024-10-22 | Abas, Mohammed Fekry | 2024-10-27 | 2024-10-27 |  |  |  | 6034420 | 6392 | 1 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 6034420 | REQUIRES REAPPROVAL |  |  |  | 0 | 462 | Babic, Marian | -45592 | -45592
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 4786 | NIC NR & NIC EV-2 132/33kV S/S-Optional Scope: Spare Parts & Cladding for HVAC System as per the PO4569-HV1401-0 | REJECTED | No | 2024-10-24 | Aseri, Amir | 2024-10-24 |  |  | 2024-10-24 | Remove 160,000 | 580000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 4787 | NIC NR & NIC EV-2 132/33kV S/S-Optional Scope: Spare Parts & Cladding for HVAC System as per the PO4569-HV1401-0 | APPROVED | No | 2024-10-24 | Abas, Mohammed Fekry | 2024-10-27 | 2024-10-27 |  |  |  | 420000 | 4569 | 1 | STANDARD | Magna Contracting Co | SAR | 420000 | APPROVED |  |  | 2024-11-04 | 0 | 8 | Kumar, Mr. Ranjan | -45592 | 8
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 4822 | NIC NR & NIC EV-2 132/33kV S/S-Supply & Apply of RTV Coating - NIC North & EV2 (Manual PO#8739-HV1401-0) | APPROVED | No | 2024-11-03 | Abas, Mohammed Fekry | 2024-11-07 | 2024-11-07 |  |  |  | 178004 | 6497 | 0 | STANDARD | Desert World Company | SAR | 178004 | APPROVED |  |  | 2024-12-09 | 0 | 32 | Kumar, Mr. Ranjan | -45603 | 32
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 4864 | NIC NR & NIC EV-2 132/33kV S/S-TPI for FAT of Surge Arrester of NIC EV2 | APPROVED | No | 2024-11-07 | Abas, Mohammed Fekry | 2024-11-10 | 2024-11-11 |  |  |  | 8362.5 | 6528 | 0 | STANDARD | SGS GULF LIMITED | USD | 8362.5 | APPROVED |  |  | 2024-12-01 | 0 | 20 | Kumar, Mr. Ranjan | -45607 | 20
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 4866 | NIC NR & NIC EV-2 132/33kV S/S- Rental of Temporary Chargers - NIC NORTH SS (Amendment for PO # 5326) | APPROVED | No | 2024-11-07 | Abas, Mohammed Fekry | 2024-11-10 | 2024-11-11 |  |  |  | 23750 | 5326 | 1 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 23750 | APPROVED |  |  | 2025-02-25 | 0 | 106 | Babic, Marian | -45607 | 106
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 4890 | NIC NR & NIC EV-2 132/33kV S/S-Supply of 132kV BBP Metrosils for NIC NORTH SS | APPROVED | No | 2024-11-10 | Abas, Mohammed Fekry | 2024-11-14 | 2024-11-14 |  |  |  | 56000 | 6483 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 56000 | APPROVED |  |  | 2024-12-01 | 0 | 17 | Kumar, Mr. Ranjan | -45610 | 17
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 4900 | NIC NR & NIC EV-2 132/33kV S/S-Office Stationery for NIC North & EV2 | REJECTED | No | 2024-11-11 | Yamama, Loai Mohamed | 2025-02-03 | 2024-11-11 |  | 2025-02-03 | 1.6.1 | 21585 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45607 | -45607
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 5230 | NIC NR & NIC EV-2 132/33kV S/S-Rental of Temporary Chargers - NIC NORTH SS (Amendment for PO # 5326) | APPROVED | No | 2024-12-15 | Abas, Mohammed Fekry | 2024-12-17 | 2024-12-17 |  |  |  | 23750 | 5326 | 1 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 23750 | APPROVED |  |  | 2025-02-25 | 0 | 70 | Babic, Marian | -45643 | 70
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 5267 | NIC NR & NIC EV-2 132/33kV S/S-Oil Filteration for 2 set of Auxilury tranformer 1000 kVA 33/0.4kV - NIC North & EV2 | APPROVED | No | 2024-12-24 | Abas, Mohammed Fekry | 2024-12-29 | 2024-12-29 |  |  |  | 27000 | 6707 | 0 | STANDARD | MASEERAT AL NAMA CONT.EST. | SAR | 27000 | APPROVED |  |  | 2025-01-27 | 0 | 29 | Kumar, Mr. Ranjan | -45655 | 29
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 5422 | NIC NR & NIC EV-2 132/33kV S/S-Installation, T&C of lighting Material (Manual PO#8753-HV1401-0) | APPROVED | No | 2025-01-14 | Abas, Mohammed Fekry | 2025-01-21 | 2025-01-23 |  |  |  | 1900000 | 6814 | 0 | STANDARD | Eram Specialized Projects Company | SAR | 1900000 | APPROVED |  |  | 2025-01-28 | 0 | 5 | Babic, Marian | -45680 | 5
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 5423 | NIC NR & NIC EV-2 132/33kV S/S-Security Services as per the Manaul PO#8743-0 | APPROVED | No | 2025-01-14 | Abas, Mohammed Fekry | 2025-01-21 | 2025-01-23 |  |  |  | 507800 | 6842 | 0 | STANDARD | Rukn Al Kateibah Company for Security Guards. | SAR | 243000 | APPROVED |  |  | 2025-02-05 | 264800 | 13 | Abuhammad, Samir | -45680 | 13
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 5423 | NIC NR & NIC EV-2 132/33kV S/S-Security Services as per the Manaul PO#8743-0 | APPROVED | No | 2025-01-14 | Abas, Mohammed Fekry | 2025-01-21 | 2025-01-23 |  |  |  | 507800 | 6842 | 1 | STANDARD | Rukn Al Kateibah Company for Security Guards. | SAR | 243000 | IN PROCESS |  |  |  | 264800 | 374 | Abuhammad, Samir | -45680 | -45680
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 5461 | NIC NR & NIC EV-2 132/33kV S/S-PDS System for NIC NORTH & EV2 Substations | REJECTED | No | 2025-01-19 | Yamama, Loai Mohamed | 2025-01-23 | 2025-01-21 |  | 2025-01-23 |  | 303800 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45678 | -45678
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 5471 | NIC NR & NIC EV-2 132/33kV S/S-LV Control Cables (Manual PO#8655-HV1401-0) | APPROVED | No | 2025-01-20 | Abas, Mohammed Fekry | 2025-01-22 | 2025-01-23 |  |  |  | 1535700.5 | 6868 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 1535700.5 | APPROVED |  |  | 2025-02-17 | 0 | 25 | Alhadi, Khalid | -45680 | 25
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 5628 | NIC NR & NIC EV-2 132/33kV S/S-PDS System for NIC NORTH Substation | REJECTED | No | 2025-01-26 | Taha, Mohammed Alfadhel Alsayed | 2025-07-31 | 2025-01-26 |  | 2025-08-28 |  | 151900 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45683 | -45683
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 5629 | NIC NR & NIC EV-2 132/33kV S/S-PDS System for NIC EV2 Substation | REJECTED | No | 2025-01-26 | Taha, Mohammed Alfadhel Alsayed | 2025-07-31 | 2025-01-26 |  | 2025-08-28 |  | 151900 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45683 | -45683
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 5634 | NIC NR & NIC EV-2 132/33kV S/S-LV AC, DC, YG Cables (Manual PO#8655-HV1401-0) | APPROVED | No | 2025-01-27 | Abas, Mohammed Fekry | 2025-01-28 | 2025-01-30 |  |  |  | 3482911.09 | 6868 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 3482911.09 | APPROVED |  |  | 2025-02-17 | 0 | 18 | Alhadi, Khalid | -45687 | 18
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 5700 | NIC NR & NIC EV-2 132/33kV S/S-Fire Retardent Paint for MV Cables - NIC North & EV2 | REJECTED | No | 2025-01-28 | Taha, Mohammed Alfadhel Alsayed | 2025-07-31 | 2025-01-29 |  | 2025-08-28 |  | 100000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45686 | -45686
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6253 | NIC NR & NIC EV-2 132/33kV S/S-Civil construction works amendment for PO#8202 (ERP PO #4754) | APPROVED | No | 2025-03-24 | Abas, Mohammed Fekry | 2025-04-14 | 2025-04-15 |  |  |  | 6439438.88 | 4754 | 2 | STANDARD | Randa Izzat Ibrahim Raydan for Construction Company | SAR | 6439438.88 | APPROVED |  |  | 2025-04-29 | 0 | 14 | Kumar, Mr. Ranjan | -45762 | 14
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6333 | NIC NR & NIC EV-2 132/33kV S/S-33KV SWGR for NIC NORTH & EV2 SS - (Manual PO #8109 & PO #8110) | APPROVED | No | 2025-04-14 | Abas, Mohammed Fekry | 2025-04-17 | 2025-04-21 |  |  | this is to reflect the manual PO's #8109 & #8110 issued for NIC NORTH & NIC EV2 Substations | 32209249 | 7189 | 0 | STANDARD | SIEMENS LIMITED | SAR | 32209249 | APPROVED |  |  | 2025-05-06 | 0 | 15 | Kumar, Mr. Ranjan | -45768 | 15
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6342 | NIC NR & NIC EV-2 132/33kV S/S-Control, Protection, SAS, Metering for NIC NORTH & EV2 Substations - Manual PO #8109 & PO #8110 | APPROVED | No | 2025-04-15 | Abas, Mohammed Fekry | 2025-04-17 | 2025-04-21 |  |  | this is to reflect the manual PO's #8109 & #8110 issued for NIC NORTH & NIC EV2 Substations | 26290751 | 7189 | 0 | STANDARD | SIEMENS LIMITED | SAR | 26290751 | APPROVED |  |  | 2025-05-06 | 0 | 15 | Kumar, Mr. Ranjan | -45768 | 15
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6343 | NIC NR & NIC EV-2 132/33kV S/S-Communication System for NIC NORTH & EV2 Substations - Manual PO #8109 & PO #8110 | APPROVED | No | 2025-04-15 | Abas, Mohammed Fekry | 2025-04-17 | 2025-04-21 |  |  | this is to reflect the manual PO's #8109 & #8110 issued for NIC NORTH & NIC EV2 Substations | 9000000 | 7189 | 0 | STANDARD | SIEMENS LIMITED | SAR | 9000000 | APPROVED |  |  | 2025-05-06 | 0 | 15 | Kumar, Mr. Ranjan | -45768 | 15
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6352 | NIC NR & NIC EV-2 132/33kV S/S-Fire Retardent Paint for MV Cables for NIC NORTH & EV2 Substations | APPROVED | No | 2025-04-16 | Abas, Mohammed Fekry | 2025-04-17 | 2025-04-21 |  |  |  | 78000 | 7194 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 57300 | APPROVED |  |  | 2025-05-05 | 20700 | 14 | Kumar, Mr. Ranjan | -45768 | 14
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6353 | NIC NR & NIC EV-2 132/33kV S/S-Supply, Installation, Testing and comissioning of PDS System for NIC NORTH Substation (Manual PO #6766) | APPROVED | No | 2025-04-16 | Abas, Mohammed Fekry | 2025-04-17 | 2025-04-21 |  |  | Top Urgent - to reflect the maual PO #6766 and release the pending payments | 151900 | 6766 | 0 | STANDARD | Procomme Technology Co | SAR | 151900 | APPROVED |  |  | 2025-04-28 | 0 | 7 | Abdulqader, Ahmed Abdulhalim | -45768 | 7
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6354 | NIC NR & NIC EV-2 132/33kV S/S-Supply, Installation, Testing and comissioning of PDS System for NIC EV2 Substation (Manual PO #6798) | APPROVED | No | 2025-04-16 | Abas, Mohammed Fekry | 2025-04-17 | 2025-04-21 |  |  | Top Urgent - to reflect the maual PO #6798 and release the pending payments | 151900 | 6798 | 0 | STANDARD | Procomme Technology Co | SAR | 151900 | APPROVED |  |  | 2025-04-28 | 0 | 7 | Abdulqader, Ahmed Abdulhalim | -45768 | 7
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6359 | NIC NR & NIC EV-2 132/33kV S/S-AC & DC Distribution Panels for NIC NORTH & EV2 Substations - Manual PO #8633 | APPROVED | No | 2025-04-16 | Abas, Mohammed Fekry | 2025-04-17 | 2025-04-21 |  |  | This is to reflect the Manual PO # 8633 | 2300000 | 7195 | 0 | STANDARD | ALFANAR CO | SAR | 2300000 | APPROVED |  |  | 2025-04-29 | 0 | 8 | Babic, Marian | -45768 | 8
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6480 | NIC NR & NIC EV-2 132/33kV S/S-Engineering Design Service for NIC NORTH SS - Manual PO#8096 | APPROVED | No | 2025-04-29 | Abas, Mohammed Fekry | 2025-05-04 | 2025-05-04 |  |  |  | 385001.25 | 7226 | 0 | STANDARD | Bahrawy Consultancy Group B.C.G | USD | 385001.25 | APPROVED |  |  | 2025-05-13 | 0 | 9 | Babic, Marian | -45781 | 9
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6481 | NIC NR & NIC EV-2 132/33kV S/S-Engineering Design Service for NIC EV-2 SS - Manual PO#8097 | APPROVED | No | 2025-04-29 | Abas, Mohammed Fekry | 2025-05-04 | 2025-05-04 |  |  |  | 385001.25 | 7227 | 0 | STANDARD | Bahrawy Consultancy Group B.C.G | USD | 385001.25 | APPROVED |  |  | 2025-05-07 | 0 | 3 | Babic, Marian | -45781 | 3
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6500 | NIC NR & NIC EV-2 132/33kV S/S-Revised Manpower Rental PO (Amendment for Manual PO#8686-HV1401-0, ERP PO-5762) | APPROVED | No | 2025-05-04 | Abas, Mohammed Fekry | 2025-05-05 | 2025-05-05 |  |  | TOP URGENT | 55520 | 5762 | 1 | STANDARD | City Crowns Energy | SAR | 55520 | APPROVED |  |  | 2025-05-15 | 0 | 10 | Babic, Marian | -45782 | 10
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6539 | NIC NR & NIC EV-2 132/33kV S/S-Site Facility (Portcabin, Furniture) Shifting, installation, and necessary connections | APPROVED | No | 2025-05-06 | Abas, Mohammed Fekry | 2025-05-11 | 2025-05-11 |  |  | TOP URGENT | 37500 | 7283 | 0 | STANDARD | Sam OG Construction | SAR | 37500 | APPROVED |  |  | 2025-05-26 | 0 | 15 | Kumar, Mr. Ranjan | -45788 | 15
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6567 | NIC NR & NIC EV-2 132/33kV S/S-1000kVA Station service transformer - Manual PO#8255-HV1401-0 | APPROVED | No | 2025-05-07 | Abas, Mohammed Fekry | 2025-05-11 | 2025-05-11 |  |  |  | 474000 | 7270 | 0 | STANDARD | ALFANAR CO | SAR | 474000 | APPROVED |  |  | 2025-05-21 | 0 | 10 | Babic, Marian | -45788 | 10
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6623 | NIC NR & NIC EV-2 132/33kV S/S-Supply of Site facility / office - NIC North & EV-2 (T&C Stage) | APPROVED | No | 2025-05-15 | Abas, Mohammed Fekry | 2025-05-19 | 2025-05-20 |  |  |  | 156522 | 7658 | 0 | STANDARD | ABDUL JABBAR AHMAD ALI SHARAHILI CONTRACTING EST. (AJASCO) | SAR | 122000 | APPROVED |  |  | 2025-09-30 | 34522 | 133 | Kumar, Mr. Ranjan | -45797 | 133
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6624 | NIC NR & NIC EV-2 132/33kV S/S-Site Facility (Portcabin, Furniture) Shifting, installation, and necessary connections (2) | APPROVED | No | 2025-05-15 | Abas, Mohammed Fekry | 2025-05-19 | 2025-05-20 |  |  | This is to cover the final price of PO#7283 | 27500 | 7283 | 0 | STANDARD | Sam OG Construction | SAR | 27500 | APPROVED |  |  | 2025-05-26 | 0 | 6 | Kumar, Mr. Ranjan | -45797 | 6
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6626 | NIC NR & NIC EV-2 132/33kV S/S-Site Funiture - NIC NORTH & EV2 | APPROVED | No | 2025-05-15 | Abas, Mohammed Fekry | 2025-05-19 | 2025-05-20 |  |  |  | 34000 | 7396 | 0 | STANDARD | ALISMAIL INDUSTRIAL CO.(S) | SAR | 32880 | APPROVED |  |  | 2025-07-16 | 1120 | 57 | Akhtar, Farhan | -45797 | 57
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6642 | NIC NR & NIC EV-2 132/33kV S/S-Rental Dilo Machine with all accessories for NIC North SS & EV2 | APPROVED | No | 2025-05-19 | Abas, Mohammed Fekry | 2025-05-26 | 2025-05-26 |  |  | Final pricess will be adjusted as per final offer will be received | 10000 | 7409 | 0 | STANDARD | Jahaz Ayed Al-Rashidi and Partner for Trad and count | SAR | 10000 | APPROVED |  |  | 2025-06-25 | 0 | 30 | Babic, Marian | -45803 | 30
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6643 | NIC NR & NIC EV-2 132/33kV S/S-Grounding Materials for NIC NORTH & EV2 Substations | APPROVED | No | 2025-05-19 | Abas, Mohammed Fekry | 2025-06-10 | 2025-06-12 |  |  |  | 14987.3 | 5635 | 1 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 14551.1 | APPROVED |  |  | 2025-06-24 | 436.2 | 12 | Babic, Marian | -45820 | 12
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6668 | NIC NR & NIC EV-2 132/33kV S/S-SAS Filed Service Overtime - Amendment for ERP PO#7189 | APPROVED | No | 2025-05-20 | Abas, Mohammed Fekry | 2025-05-21 | 2025-05-21 |  |  |  | 471572 | 7189 | 1 | STANDARD | SIEMENS LIMITED | SAR | 471572 | APPROVED |  |  | 2025-05-29 | 0 | 8 | Kumar, Mr. Ranjan | -45798 | 8
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6669 | NIC NR & NIC EV-2 132/33kV S/S-SAS Modification of Renaming at NIC Circle BSP & Duba Green BSP - (Manual PO#8846-HV1401-0) | APPROVED | No | 2025-05-20 | Abas, Mohammed Fekry | 2025-05-21 | 2025-05-21 |  |  |  | 2240000 | 7352 | 0 | STANDARD | SYSTEM HOUSE FACTORY FOR ELECTRIC PANELS (SEP) | SAR | 2240000 | APPROVED |  |  | 2025-05-28 | 0 | 7 | Babic, Marian | -45798 | 7
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6756 | NIC NR & NIC EV-2 132/33kV S/S-Cable Ladder & Tray Fitting - NIC EV-2 SS | REJECTED | No | 2025-05-29 | Yamama, Loai Mohamed | 2025-06-15 | 2025-06-01 |  | 2025-06-15 |  | 432859.36 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45809 | -45809
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6767 | NIC NR & NIC EV-2 132/33kV S/S-Rental Dilo Machine with all accessories for NIC North SS & EV2 | APPROVED | No | 2025-06-03 | Abas, Mohammed Fekry | 2025-06-11 | 2025-06-12 |  |  |  | 30000 | 7409 | 0 | STANDARD | Jahaz Ayed Al-Rashidi and Partner for Trad and count | SAR | 28333.33 | APPROVED |  |  | 2025-06-25 | 1666.67 | 13 | Babic, Marian | -45820 | 13
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6775 | NIC NR & NIC EV-2 132/33kV S/S-Rental of ambulance Amendment PO# 5584-HV1401-0 | APPROVED | No | 2025-06-11 | Abas, Mohammed Fekry | 2025-06-15 | 2025-06-15 |  |  |  | 300000 | 5584 | 1 | STANDARD | CAPITAL AMBULANCE FOR MEDICAL SERVICES | SAR | 285000 | IN PROCESS | 2025-06-22 | 2026-01-28 |  | 15000 | 231 | Kumar, Mr. Ranjan | 227 | -45823
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6775 | NIC NR & NIC EV-2 132/33kV S/S-Rental of ambulance Amendment PO# 5584-HV1401-0 | APPROVED | No | 2025-06-11 | Abas, Mohammed Fekry | 2025-06-15 | 2025-06-15 |  |  |  | 300000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45823 | -45823
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6824 | NIC NR & NIC EV-2 132/33kV S/S-Supply of Diesel fuel for NIC NR & EV2 (Amendment ERP PO#5017) | APPROVED | No | 2025-06-18 | Abas, Mohammed Fekry | 2025-06-23 | 2025-06-25 |  |  |  | 280324.81 | 5017 | 1 | STANDARD | Talaea Alahlam Trading Company | SAR | 280324.81 | APPROVED |  |  | 2025-07-24 | 0 | 29 | Akhtar, Farhan | -45833 | 29
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6825 | NIC NR & NIC EV-2 132/33kV S/S-Supply of Diesel fuel for NIC NR & EV2 | APPROVED | No | 2025-06-18 | Abas, Mohammed Fekry | 2025-06-23 | 2025-06-25 |  |  | 2025 Diesel New unit Price - 1.57 | 355250.18 | 7449 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 355250.18 | APPROVED |  |  | 2025-07-10 | 0 | 15 | Akhtar, Farhan | -45833 | 15
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6834 | NIC NR & NIC EV-2 132/33kV S/S-Supply, Installation, T&C of 125V DC system (Manual PO#8627-HV1401-0) | APPROVED | No | 2025-06-19 | Abas, Mohammed Fekry | 2025-06-23 | 2025-06-25 |  |  | Currancy rate 4.2 as per the vendor | 3093720 | 7428 | 0 | STANDARD | Sela for Power, Automation & Safety Systems Co | EUR | 2946400 | APPROVED |  |  | 2025-06-29 | 147320 | 4 | Babic, Marian | -45833 | 4
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6850 | NIC NR & NIC EV-2 132/33kV S/S-Supply of Cable Ladders and Trays with Accessories (Manual PO 84354-HV1401-0) | REJECTED | No | 2025-06-22 | Taha, Mohammed Alfadhel Alsayed | 2025-06-22 |  |  | 2025-06-22 |  | 2340000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | 0 | 0
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6851 | NIC NR & NIC EV-2 132/33kV S/S-Supply of Cable Ladders and Trays with Accessories (Manual PO 84354-HV1401-0) | APPROVED | No | 2025-06-22 | Abas, Mohammed Fekry | 2025-06-24 | 2025-06-25 |  |  |  | 2340000 | 7402 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 2340000 | APPROVED |  |  | 2025-07-10 | 0 | 15 | Badhman, Saeed | -45833 | 15
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6853 | NIC NR & NIC EV-2 132/33kV S/S-Supply of Cable Ladders and Trays with Accessories Amedment to Manual PO 84354-HV1401-0 | REJECTED | No | 2025-06-22 | Taha, Mohammed Alfadhel Alsayed | 2025-06-22 |  |  | 2025-06-22 |  | 94204.4 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | 0 | 0
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6854 | NIC NR & NIC EV-2 132/33kV S/S-Supply of Cable Ladders and Trays with Accessories (IKK) | APPROVED | No | 2025-06-22 | Abas, Mohammed Fekry | 2025-06-23 | 2025-06-25 |  |  |  | 94204.4 | 7403 | 0 | STANDARD | ISAM kabbani & partners for construction & maintenance co.LTD | SAR | 94204.4 | APPROVED |  |  | 2025-10-05 | 0 | 102 | Badhman, Saeed | -45833 | 102
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6855 | NIC NR & NIC EV-2 132/33kV S/S-Cable Ladders and Trays with Accessories Amendment Manual PO 84354-HV1401-0 | APPROVED | No | 2025-06-22 | Abas, Mohammed Fekry | 2025-06-24 | 2025-06-25 |  |  |  | 106244.3 | 7402 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 106244.3 | APPROVED |  |  | 2025-07-10 | 0 | 15 | Badhman, Saeed | -45833 | 15
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6864 | NIC NR & NIC EV-2 132/33kV S/S-Supply of Power & Control Cables | APPROVED | No | 2025-06-23 | Abas, Mohammed Fekry | 2025-06-24 | 2025-06-25 |  |  |  | 51950 | 7433 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 51950 | APPROVED |  |  | 2025-07-09 | 0 | 14 | Muaz, Alaa | -45833 | 14
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6925 | NIC NR & NIC EV-2 132/33kV S/S-Indoor & Outdoor Receptacles Amendment ERP PO#6191-HV1401-0 | REJECTED | No | 2025-06-29 | Taha, Mohammed Alfadhel Alsayed | 2025-06-29 |  |  | 2025-06-29 |  | 10120 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | 0 | 0
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 6926 | NIC NR & NIC EV-2 132/33kV S/S-Lightting Receptacles Accessories Amendment ERP PO#6191-HV1401-0 | APPROVED | No | 2025-06-29 | Abas, Mohammed Fekry | 2025-07-03 | 2025-07-04 |  |  | This Accessories was not consider vendor initial offer in Previous PO Rev 0 | 10120 | 6191 | 1 | STANDARD | Power House Company | SAR | 10120 | APPROVED |  |  | 2025-07-10 | 0 | 6 | Babic, Marian | -45842 | 6
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 7203 | NIC NR & NIC EV-2 132/33kV S/S-Security services Amendment PO#6842 | APPROVED | No | 2025-07-24 | Abas, Mohammed Fekry | 2025-07-28 | 2025-07-29 |  |  |  | 620000 | 6842 | 1 | STANDARD | Rukn Al Kateibah Company for Security Guards. | SAR | 620000 | IN PROCESS |  |  |  | 0 | 187 | Abuhammad, Samir | -45867 | -45867
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 7203 | NIC NR & NIC EV-2 132/33kV S/S-Security services Amendment PO#6842 | APPROVED | No | 2025-07-24 | Abas, Mohammed Fekry | 2025-07-28 | 2025-07-29 |  |  |  | 620000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45867 | -45867
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 7289 | Fire system replacement panel Amendment PO#4704-HV1401-0 | REJECTED | No | 2025-08-05 | Yamama, Loai Mohamed | 2025-08-11 | 2025-08-07 |  | 2025-08-11 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45876 | -45876
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 7325 | Fire system replacement panel Amendment PO#4704-HV1401-0 | RETURNED | No | 2025-08-11 | Kumar, Mr. Ranjan | 2025-12-21 | 2025-11-23 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45984 | -45984
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 7527 | Supply of Lighting Fixtures (Amendment PO #8722) | APPROVED | No | 2025-08-28 | Abas, Mohammed Fekry | 2025-08-28 | 2025-08-28 |  |  |  | 0 | 7237 | 1 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 85045.5 | APPROVED |  |  | 2025-09-14 | -85045.5 | 17 | Babic, Marian | -45897 | 17
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 7592 | Excavation Works for NIC NORTH & EV2 Substations (4335-HV1401-03) | APPROVED | No | 2025-08-31 | Abas, Mohammed Fekry | 2025-09-01 | 2025-09-01 |  |  |  | 0 | 4335 | 2 | STANDARD | Sam OG Construction | SAR | 200000 | APPROVED |  |  | 2025-09-17 | -200000 | 16 | Kumar, Mr. Ranjan | -45901 | 16
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 7701 | PTW LOA services | REJECTED | No | 2025-09-09 | Yamama, Loai Mohamed | 2025-09-11 | 2025-09-11 |  | 2025-09-14 |  | 100000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45911 | -45911
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 7725 | PTW LOA services | RETURNED | No | 2025-09-11 | Babic, Marian | 2025-10-26 | 2025-09-21 | 2025-10-26 |  | please resubmit after the budget issues are resolved | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45921 | -45921
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 7816 | Skilled Technician (Qty: 8) for Testing of NIC NORTH & EV2 SS | REJECTED | No | 2025-09-24 | Yamama, Loai Mohamed | 2025-09-25 | 2025-09-25 |  | 2025-09-25 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45925 | -45925
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 7829 | Skilled Technician (Qty: 8) for Testing of NIC NORTH & EV2 SS | RETURNED | No | 2025-09-25 | Babic, Marian | 2025-12-02 | 2025-09-28 | 2025-12-02 |  | there is no response about this requirement | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45928 | -45928
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 8050 | Rental of Ambulance Amendment PO#5584 | REJECTED | No | 2025-10-26 | Alharbi, Atef Saud | 2025-10-26 | 2025-10-26 |  | 2025-10-26 | Task No 1.7.1.4.5 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45956 | -45956
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 8099 | Cable tray accessories materials for NIC EV02 Substation | REJECTED | No | 2025-10-30 | Yamama, Loai Mohamed | 2025-11-16 | 2025-11-13 |  | 2025-11-16 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45974 | -45974
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 8130 | Supply of Earthing Material - Amendment PO#8698-HV1401-0 | APPROVED | No | 2025-11-04 | Abas, Mohammed Fekry | 2025-12-31 | 2026-01-01 | 2025-12-29 |  | please add task number and resubmit | 0 | 5635 | 2 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 61612.4 | APPROVED | 2026-01-01 | 2026-01-06 | 2026-01-12 | -61612.4 | 11 | Babic, Marian | 5 | 11
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 8179 | Supply of Substation Furniture for NIC EV2 (Amendment PO#7396) | APPROVED | No | 2025-11-11 | Abas, Mohammed Fekry | 2026-01-27 | 2026-01-28 | 2025-12-17 |  | PR is not amount is not budgeted | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -46050 | -46050
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 8229 | Service order for installation of two Surge arrestors | REJECTED | No | 2025-11-16 | Yamama, Loai Mohamed | 2025-11-18 | 2025-11-17 |  | 2025-11-18 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45978 | -45978
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 8479 | SAS T&C RE-Works For HIRSHMAN SWITCHES PASSWORD | REJECTED | No | 2025-12-08 | Taha, Mohammed Alfadhel Alsayed | 2025-12-08 | 2025-12-08 |  | 2025-12-08 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45999 | -45999
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 8481 | SAS T&C RE-Works For HIRSHMAN SWITCHES PASSWORD | REJECTED | No | 2025-12-08 | Yamama, Loai Mohamed | 2025-12-10 | 2025-12-08 |  | 2025-12-10 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45999 | -45999
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 8489 | Oil Filtration services | APPROVED | No | 2025-12-10 | Abas, Mohammed Fekry | 2025-12-31 | 2026-01-01 | 2025-12-25 |  | Please add task line to the PR and resubmit | 0 | 8002 | 0 | STANDARD | Delta Energy Contracting Company | SAR | 22500 | APPROVED | 2026-01-08 | 2026-01-13 | 2026-01-15 | -22500 | 14 | Babic, Marian | 12 | 14
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 8545 | Cable trays accessories required materials at NIC EV02 SS | APPROVED | No | 2025-12-17 | Abas, Mohammed Fekry | 2025-12-23 | 2025-12-24 |  |  | Task No 1.2.2.6 | 0 | 7890 | 0 | STANDARD | ISAM KABBANI &Partners | SAR | 77550 | APPROVED | 2025-12-25 | 2025-12-26 | 2026-01-22 | -77550 | 29 | Babic, Marian | 2 | 29
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 8545 | Cable trays accessories required materials at NIC EV02 SS | APPROVED | No | 2025-12-17 | Abas, Mohammed Fekry | 2025-12-23 | 2025-12-24 |  |  | Task No 1.2.2.6 | 0 | 15002 | 0 | STANDARD |  | SAR | 0 | INCOMPLETE |  |  |  | 0 | 39 | Babic, Marian | -46015 | -46015
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 8545 | Cable trays accessories required materials at NIC EV02 SS | APPROVED | No | 2025-12-17 | Abas, Mohammed Fekry | 2025-12-23 | 2025-12-24 |  |  | Task No 1.2.2.6 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46015 | -46015
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 8661 | Cable trays accessories - NIC EV2 | APPROVED | No | 2026-01-07 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-11 |  |  |  | 0 | 7890 | 1 | STANDARD | ISAM KABBANI &Partners | SAR | 17680 | IN PROCESS | 2026-01-25 | 2026-01-26 |  | -17680 | 21 | Babic, Marian | 15 | -46033
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 8661 | Cable trays accessories - NIC EV2 | APPROVED | No | 2026-01-07 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-11 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46033 | -46033
105-69 | NIC NR & NIC EV-2 132/33kV S/S | 8834 | Indoor & Outdoor Receptacles - PO Amendment #6191 Rev02 | IN PROCESS | No | 2026-01-29 | Yamama, Loai Mohamed | 2026-01-30 | 2026-01-30 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46052 | -46052
105-74 | NEOM Large-Scale Arabic Unders | 918 | NEOM Large-Scale Arabic Unders-Professional services | APPROVED | No | 2022-11-16 | Abas, Mohammed Fekry | 2022-11-16 | 2022-11-17 |  |  |  | 40356117.81 | 4279 | 0 | STANDARD | Gulf Application Co | SAR | 40356117.81 | APPROVED |  |  | 2022-11-28 | 0 | 11 | Abuhammad, Samir | -44882 | 11
105-79 | Fixed Optical Network Core Rou | 1000 | Fixed Optical Network Core Rou-PR For Router Upgrade Material & Services | APPROVED | No | 2023-01-15 | Abas, Mohammed Fekry | 2023-01-23 | 2023-01-24 |  |  |  | 24478100.73 | 4329 | 0 | STANDARD | Gulf Application Co | SAR | 24478100.73 | APPROVED |  |  | 2023-02-12 | 0 | 19 | Abuhammad, Samir | -44950 | 19
105-88 | AI Digital Ambassador Phase 3 | 1019 | AI Digital Ambassador Phase 3-Services for Neom Phase 3 | APPROVED | No | 2023-01-24 | Abas, Mohammed Fekry | 2023-01-24 | 2023-01-25 |  |  |  | 13086393 | 4331 | 0 | STANDARD | REDINGTON SAUDI ARABIA DISTRIBUTION CO. | SAR | 22246868.1 | APPROVED |  |  | 2023-01-31 | -9160475.1 | 6 | Abuhammad, Samir | -44951 | 6
105-91 | TONOMUS fiber cable relocation | 1369 | TONOMUS fiber cable relocation-PR- For-NEOM-FOC diversion VIP HOSPITAL Done By CCS | APPROVED | No | 2023-07-25 | Abas, Mohammed Fekry | 2023-07-26 | 2023-08-01 |  |  |  | 103963.32 | 4563 | 0 | STANDARD | China Saudi Communication Service Co.Ltd | SAR | 103963.32 | APPROVED |  |  | 2023-09-11 | 0 | 41 | Abuhammad, Samir | -45139 | 41
105-92 | HAMDANIYAH 110/13.8kV S/S | 1661 | HAMDANIYAH 110/13.8kV S/S-Enginmeering Design Services (For Manual PO-8260) | APPROVED | No | 2023-11-06 | Abas, Mohammed Fekry | 2023-11-08 | 2023-11-09 |  |  |  | 475000 | 4887 | 0 | STANDARD | Bahrawy Consultancy Group B.C.G | SAR | 475000 | APPROVED |  |  | 2024-01-01 | 0 | 53 | Kumar, Mr. Ranjan | -45239 | 53
105-92 | HAMDANIYAH 110/13.8kV S/S | 1663 | HAMDANIYAH 110/13.8kV S/S-Soil Investigation (For Manual PO-8262) | APPROVED | No | 2023-11-06 | Abas, Mohammed Fekry | 2023-11-08 | 2023-11-09 |  |  |  | 30526.75 | 4752 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 26545 | APPROVED |  |  | 2023-11-23 | 3981.75 | 14 | Kumar, Mr. Ranjan | -45239 | 14
105-92 | HAMDANIYAH 110/13.8kV S/S | 1664 | HAMDANIYAH 110/13.8kV S/S-ESIA Study (For Manaul PO-8319) | APPROVED | No | 2023-11-07 | Abas, Mohammed Fekry | 2023-11-09 | 2023-11-12 |  |  |  | 37375 | 4751 | 0 | STANDARD | Aran Aljazeera Enviromental Consultant | SAR | 32500 | APPROVED |  |  | 2023-11-26 | 4875 | 14 | Kumar, Mr. Ranjan | -45242 | 14
105-92 | HAMDANIYAH 110/13.8kV S/S | 1665 | HAMDANIYAH 110/13.8kV S/S-Hyundai Electric-110KV GIS (For Manual PO-8264) | APPROVED | No | 2023-11-07 | Abas, Mohammed Fekry | 2023-11-09 | 2023-11-12 |  |  |  | 11062500 | 4728 | 0 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 10293750 | APPROVED |  |  | 2023-12-17 | 768750 | 35 | Kumar, Mr. Ranjan | -45242 | 35
105-92 | HAMDANIYAH 110/13.8kV S/S | 1734 | HAMDANIYAH 110/13.8kV S/S-13.8KV Switchgear-Alfanar (For Manual PO-8278) | APPROVED | No | 2023-11-14 | Abas, Mohammed Fekry | 2023-11-15 | 2023-11-16 |  |  |  | 8810000 | 5301 | 0 | STANDARD | ALFANAR CO | SAR | 8800000 | APPROVED |  |  | 2024-04-02 | 10000 | 138 | Kumar, Mr. Ranjan | -45246 | 138
105-92 | HAMDANIYAH 110/13.8kV S/S | 1735 | HAMDANIYAH 110/13.8kV S/S-Cyber Security-Alfanar (For Manual PO#8332) | APPROVED | No | 2023-11-14 | Abas, Mohammed Fekry | 2023-11-15 | 2023-11-16 |  |  |  | 1525000 | 5300 | 0 | STANDARD | ALFANAR CO | SAR | 1525000 | APPROVED |  |  | 2024-04-02 | 0 | 138 | Kumar, Mr. Ranjan | -45246 | 138
105-92 | HAMDANIYAH 110/13.8kV S/S | 1753 | HAMDANIYAH 110/13.8kV S/S-OHTC Crane-5T (For Manual PO-8334) | APPROVED | No | 2023-11-15 | Abas, Mohammed Fekry | 2023-11-15 | 2023-11-16 |  |  |  | 138500 | 4750 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 138500 | APPROVED |  |  | 2023-11-28 | 0 | 12 | Kumar, Mr. Ranjan | -45246 | 12
105-92 | HAMDANIYAH 110/13.8kV S/S | 1785 | HAMDANIYAH 110/13.8kV S/S-SUPPLY OF POWER TRANSFORMERS (FOR SPTC MANUAL PO-8280) | APPROVED | No | 2023-11-19 | Abas, Mohammed Fekry | 2023-11-22 | 2023-11-22 |  |  |  | 18592500 | 4773 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 18592500 | APPROVED |  |  | 2023-12-04 | 0 | 12 | Kumar, Mr. Ranjan | -45252 | 12
105-92 | HAMDANIYAH 110/13.8kV S/S | 1787 | HAMDANIYAH 110/13.8kV S/S-Civil and Architectural Works Subcontracting | APPROVED | No | 2023-11-19 | Abas, Mohammed Fekry | 2023-11-22 | 2023-11-22 |  |  |  | 12650000 | 4775 | 0 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 12650000 | APPROVED |  |  | 2023-12-06 | 0 | 14 | Kumar, Mr. Ranjan | -45252 | 14
105-92 | HAMDANIYAH 110/13.8kV S/S | 1792 | HAMDANIYAH 110/13.8kV S/S-Supply of IT Requirements-Golden Technology (For Manual PO-8472) | APPROVED | No | 2023-11-20 | Abas, Mohammed Fekry | 2023-11-22 | 2023-11-22 |  |  |  | 23500 | 4756 | 0 | STANDARD | Golden Technology trading Company. | SAR | 23500 | APPROVED |  |  | 2023-12-03 | 0 | 11 | Abuhammad, Samir | -45252 | 11
105-92 | HAMDANIYAH 110/13.8kV S/S | 1793 | HAMDANIYAH 110/13.8kV S/S-Site Mobilization Works | APPROVED | No | 2023-11-20 | Abas, Mohammed Fekry | 2023-11-22 | 2023-11-22 |  |  |  | 225765 | 4774 | 0 | STANDARD | Construction Expertise Est. | SAR | 225765 | APPROVED |  |  | 2023-12-04 | 0 | 12 | Kumar, Mr. Ranjan | -45252 | 12
105-92 | HAMDANIYAH 110/13.8kV S/S | 1795 | HAMDANIYAH 110/13.8kV S/S-MV Cables | APPROVED | No | 2023-11-20 | Abas, Mohammed Fekry | 2023-11-22 | 2023-11-23 |  |  |  | 921011.54 | 5087 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 921011.54 | APPROVED |  |  | 2024-02-28 | 0 | 97 | Badhman, Saeed | -45253 | 97
105-92 | HAMDANIYAH 110/13.8kV S/S | 1797 | HAMDANIYAH 110/13.8kV S/S-Surge Arrester-96 KV | APPROVED | No | 2023-11-20 | Abas, Mohammed Fekry | 2023-11-22 | 2023-11-23 |  |  |  | 51356.25 | 5296 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | USD | 51356.36 | APPROVED |  |  | 2024-03-31 | -0.11 | 129 | Kumar, Mr. Ranjan | -45253 | 129
105-92 | HAMDANIYAH 110/13.8kV S/S | 1804 | HAMDANIYAH 110/13.8kV S/S-Supply of Auxilary Transformer | APPROVED | No | 2023-11-22 | Abas, Mohammed Fekry | 2023-11-22 | 2023-11-23 |  |  |  | 202000 | 5298 | 0 | STANDARD | ALFANAR CO | SAR | 202000 | APPROVED |  |  | 2024-04-02 | 0 | 131 | Kumar, Mr. Ranjan | -45253 | 131
105-92 | HAMDANIYAH 110/13.8kV S/S | 1806 | HAMDANIYAH 110/13.8kV S/S-Supply of Protection & Control Panels & SAS Systems | APPROVED | No | 2023-11-22 | Abas, Mohammed Fekry | 2023-11-22 | 2023-11-23 |  |  |  | 9467000 | 5302 | 0 | STANDARD | ALFANAR CO | SAR | 9321000 | APPROVED |  |  | 2024-04-02 | 146000 | 131 | Kumar, Mr. Ranjan | -45253 | 131
105-92 | HAMDANIYAH 110/13.8kV S/S | 1807 | HAMDANIYAH 110/13.8kV S/S-Supply/ Installation Supervision/ Testing of Telecom System | APPROVED | No | 2023-11-22 | Abas, Mohammed Fekry | 2023-11-22 | 2023-11-23 |  |  |  | 2400000 | 5303 | 0 | STANDARD | ALFANAR CO | SAR | 2400000 | APPROVED |  |  | 2024-04-02 | 0 | 131 | Kumar, Mr. Ranjan | -45253 | 131
105-92 | HAMDANIYAH 110/13.8kV S/S | 1813 | HAMDANIYAH 110/13.8kV S/S-Supply of Neutral Earthing Resistor (NER) | APPROVED | No | 2023-11-26 | Abas, Mohammed Fekry | 2023-11-27 | 2023-11-28 |  |  |  | 114750 | 4888 | 0 | STANDARD | National Switchgears | USD | 114750 | APPROVED |  |  | 2024-01-01 | 0 | 34 | Kumar, Mr. Ranjan | -45258 | 34
105-92 | HAMDANIYAH 110/13.8kV S/S | 1816 | HAMDANIYAH 110/13.8kV S/S-Supply/Testing & Commsioning of 125V DC System | APPROVED | No | 2023-11-26 | Abas, Mohammed Fekry | 2023-11-27 | 2023-11-28 |  |  |  | 584000 | 4889 | 0 | STANDARD | Alassas Specialized Company Ltd | SAR | 570000 | APPROVED |  |  | 2024-01-01 | 14000 | 34 | Kumar, Mr. Ranjan | -45258 | 34
105-92 | HAMDANIYAH 110/13.8kV S/S | 1847 | HAMDANIYAH 110/13.8kV S/S-Design, Supply, Installiation & Testing of HVAC System | APPROVED | No | 2023-11-29 | Abas, Mohammed Fekry | 2023-11-30 | 2023-11-30 |  |  |  | 1750000 | 4816 | 0 | STANDARD | MARINE SERVICES CO LTD. | SAR | 1750000 | APPROVED |  |  | 2023-12-21 | 0 | 21 | Alhadi, Khalid | -45260 | 21
105-92 | HAMDANIYAH 110/13.8kV S/S | 1861 | HAMDANIYAH 110/13.8kV S/S-Supply of Yellow and Green Cables, Tinned Copper | APPROVED | No | 2023-11-30 | Abas, Mohammed Fekry | 2023-11-30 | 2023-11-30 |  |  |  | 270339.03 | 4786 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 270339.03 | APPROVED |  |  | 2023-12-11 | 0 | 11 | Babic, Marian | -45260 | 11
105-92 | HAMDANIYAH 110/13.8kV S/S | 1916 | HAMDANIYAH 110/13.8kV S/S-AC, DC Distribution and Lighting Panels | APPROVED | No | 2023-12-07 | Abas, Mohammed Fekry | 2023-12-10 | 2023-12-11 |  |  |  | 787000 | 4924 | 0 | STANDARD | ALFANAR CO | SAR | 787000 | APPROVED |  |  | 2024-01-07 | 0 | 27 | Kumar, Mr. Ranjan | -45271 | 27
105-92 | HAMDANIYAH 110/13.8kV S/S | 1918 | HAMDANIYAH 110/13.8kV S/S-Fire alarm & Fire Protection System | APPROVED | No | 2023-12-07 | Abas, Mohammed Fekry | 2023-12-10 | 2023-12-11 |  |  |  | 2100000 | 5048 | 0 | STANDARD | Reda Trading & Development Co. for Machinery & Equipment Ltd(S) | SAR | 1950000 | APPROVED |  |  | 2024-03-21 | 150000 | 101 | Kumar, Mr. Ranjan | -45271 | 101
105-92 | HAMDANIYAH 110/13.8kV S/S | 1932 | HAMDANIYAH 110/13.8kV S/S-Supply Installation/Testing of Security System | APPROVED | No | 2023-12-12 | Abas, Mohammed Fekry | 2023-12-17 | 2023-12-18 |  |  |  | 1100000 | 4939 | 0 | STANDARD | Reda Trading & Development Co. for Machinery & Equipment Ltd(S) | SAR | 711712 | APPROVED |  |  | 2024-01-25 | 388288 | 38 | Mohammed, Faisal Ansari | -45278 | 38
105-92 | HAMDANIYAH 110/13.8kV S/S | 1938 | HAMDANIYAH 110/13.8kV S/S-Supply of HV clamps - Connectors | APPROVED | No | 2023-12-12 | Abas, Mohammed Fekry | 2023-12-17 | 2023-12-18 |  |  |  | 10920 | 5108 | 0 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 10212.3 | APPROVED |  |  | 2024-03-11 | 707.7 | 84 | Mohammed, Faisal Ansari | -45278 | 84
105-92 | HAMDANIYAH 110/13.8kV S/S | 1980 | HAMDANIYAH 110/13.8kV S/S-Earthing Materials- Reyazat | APPROVED | No | 2023-12-17 | Abas, Mohammed Fekry | 2023-12-19 | 2023-12-19 |  |  |  | 54632.9 | 4908 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 54632.9 | APPROVED |  |  | 2023-12-31 | 0 | 12 | Babic, Marian | -45279 | 12
105-92 | HAMDANIYAH 110/13.8kV S/S | 1982 | HAMDANIYAH 110/13.8kV S/S-Building Permit | APPROVED | No | 2023-12-17 | Abas, Mohammed Fekry | 2023-12-19 | 2023-12-19 |  |  |  | 40000 | 4911 | 0 | STANDARD | Emad A.A.Nadreen for Engineering Consultation | SAR | 40000 | APPROVED |  |  | 2023-12-31 | 0 | 12 | Kumar, Mr. Ranjan | -45279 | 12
105-92 | HAMDANIYAH 110/13.8kV S/S | 1983 | HAMDANIYAH 110/13.8kV S/S-Supply Of MV Termination Kit | APPROVED | No | 2023-12-17 | Abas, Mohammed Fekry | 2023-12-19 | 2023-12-19 |  |  |  | 175000 | 4956 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 81008.2 | APPROVED |  |  | 2024-01-21 | 93991.8 | 33 | Kumar, Mr. Ranjan | -45279 | 33
105-92 | HAMDANIYAH 110/13.8kV S/S | 2022 | HAMDANIYAH 110/13.8kV S/S-Supply/Installation testing & commissioning of 2 Ton wall mounted JIB crane | APPROVED | No | 2023-12-21 | Abas, Mohammed Fekry | 2023-12-24 | 2023-12-25 |  |  |  | 180000 | 4982 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 163000 | APPROVED |  |  | 2024-04-18 | 17000 | 115 | Kumar, Mr. Ranjan | -45285 | 115
105-92 | HAMDANIYAH 110/13.8kV S/S | 2026 | HAMDANIYAH 110/13.8kV S/S-Supply Of Lighting Panels | APPROVED | No | 2023-12-21 | Abas, Mohammed Fekry | 2023-12-24 | 2023-12-25 |  |  |  | 80000 | 4924 | 0 | STANDARD | ALFANAR CO | SAR | 50000 | APPROVED |  |  | 2024-01-07 | 30000 | 13 | Kumar, Mr. Ranjan | -45285 | 13
105-92 | HAMDANIYAH 110/13.8kV S/S | 2196 | HAMDANIYAH 110/13.8kV S/S-Supply Of Lighting Fixtures Indoor & Outdoor | APPROVED | No | 2024-01-17 | Abas, Mohammed Fekry | 2024-01-21 | 2024-01-21 |  |  |  | 54805 | 5043 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 49324.5 | APPROVED |  |  | 2024-03-14 | 5480.5 | 53 | Kumar, Mr. Ranjan | -45312 | 53
105-92 | HAMDANIYAH 110/13.8kV S/S | 2221 | HAMDANIYAH 110/13.8kV S/S-Substation Electrical Equipment Installation Services | APPROVED | No | 2024-01-18 | Abas, Mohammed Fekry | 2024-01-22 | 2024-01-22 |  |  |  | 2400000 | 5145 | 0 | STANDARD | Hussain Ali Hussain Contracting Company | SAR | 1675000 | APPROVED |  |  | 2024-03-21 | 725000 | 59 | Kumar, Mr. Ranjan | -45313 | 59
105-92 | HAMDANIYAH 110/13.8kV S/S | 2269 | HAMDANIYAH 110/13.8kV S/S-Supply of cable trays and ladders with accessories | RETURNED | No | 2024-01-23 | Badhman, Saeed | 2024-03-12 | 2024-01-25 | 2024-03-12 |  | Unit price is less that the received offer | 301540.86 | 5222 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 269773.46 | APPROVED |  |  | 2024-04-18 | 31767.4 |  | Kumar, Mr. Ranjan | -45316 | 84
105-92 | HAMDANIYAH 110/13.8kV S/S | 2269 | HAMDANIYAH 110/13.8kV S/S-Supply of cable trays and ladders with accessories | RETURNED | No | 2024-01-23 | Badhman, Saeed | 2024-03-12 | 2024-01-25 | 2024-03-12 |  | Unit price is less that the received offer | 200 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45316 | -45316
105-92 | HAMDANIYAH 110/13.8kV S/S | 2274 | HAMDANIYAH 110/13.8kV S/S-Supply of cable trays and ladders with accessories -2 | APPROVED | No | 2024-01-24 | Abas, Mohammed Fekry | 2024-01-29 | 2024-01-29 |  |  |  | 84958.72 | 5222 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 76462.94 | APPROVED |  |  | 2024-04-18 | 8495.78 | 80 | Kumar, Mr. Ranjan | -45320 | 80
105-92 | HAMDANIYAH 110/13.8kV S/S | 2509 | HAMDANIYAH 110/13.8kV S/S-LV Cabels | REJECTED | No | 2024-02-08 | Abdelrahman, Ahmed Shaaban | 2024-02-08 |  |  | 2024-02-08 |  | 466830.55 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-92 | HAMDANIYAH 110/13.8kV S/S | 2513 | HAMDANIYAH 110/13.8kV S/S-LV and control Cable 1 | APPROVED | No | 2024-02-08 | Abas, Mohammed Fekry | 2024-02-11 | 2024-02-12 |  |  |  | 594543.67 | 5102 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 594543.67 | APPROVED |  |  | 2024-03-06 | 0 | 23 | Badhman, Saeed | -45334 | 23
105-92 | HAMDANIYAH 110/13.8kV S/S | 2517 | HAMDANIYAH 110/13.8kV S/S-Hamdaniyah - Supply of Termination Kit (Lugs) | APPROVED | No | 2024-02-11 | Abas, Mohammed Fekry | 2024-02-11 | 2024-02-12 |  |  |  | 33000 | 4956 | 1 | STANDARD | Nima Arabia Company Limited | SAR | 31748.1 | APPROVED |  |  | 2024-02-25 | 1251.9 | 13 | Babic, Marian | -45334 | 13
105-92 | HAMDANIYAH 110/13.8kV S/S | 2527 | HAMDANIYAH 110/13.8kV S/S-Lv Cable and Control Cable -2 | APPROVED | No | 2024-02-11 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-18 |  |  |  | 499901.18 | 5102 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 499901.18 | APPROVED |  |  | 2024-03-06 | 0 | 17 | Badhman, Saeed | -45340 | 17
105-92 | HAMDANIYAH 110/13.8kV S/S | 2560 | HAMDANIYAH 110/13.8kV S/S-Lightning mast | REJECTED | No | 2024-02-14 | Abdelrahman, Ahmed Shaaban | 2024-02-14 |  |  | 2024-02-14 |  | 105025 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-92 | HAMDANIYAH 110/13.8kV S/S | 2564 | HAMDANIYAH 110/13.8kV S/S-HMD Lightning mast | APPROVED | No | 2024-02-15 | Abas, Mohammed Fekry | 2024-02-19 | 2024-02-21 |  |  |  | 130000 | 5455 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 58750 | APPROVED |  |  | 2024-05-14 | 71250 | 83 | Muhammad, Muhammad Atif | -45343 | 83
105-92 | HAMDANIYAH 110/13.8kV S/S | 2851 | HAMDANIYAH 110/13.8kV S/S-Stand Split Unit | REJECTED | No | 2024-03-20 | Abdelrahman, Ahmed Shaaban | 2024-03-20 |  |  | 2024-03-20 |  | 150 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-92 | HAMDANIYAH 110/13.8kV S/S | 2865 | HAMDANIYAH 110/13.8kV S/S-Stand Split Unit | APPROVED | No | 2024-03-20 | Abas, Mohammed Fekry | 2024-03-28 | 2024-03-28 |  |  |  | 150000 | 5315 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 126000 | APPROVED |  |  | 2024-04-18 | 24000 | 21 | Abuhammad, Samir | -45379 | 21
105-92 | HAMDANIYAH 110/13.8kV S/S | 2905 | HAMDANIYAH 110/13.8kV S/S-HMD cable raceway Cross Tray | INCOMPLETE | No |  | Abdelrahman, Ahmed Shaaban | 2024-03-26 |  |  |  |  | 20000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-92 | HAMDANIYAH 110/13.8kV S/S | 2906 | HAMDANIYAH 110/13.8kV S/S-HMD Raceway transportation | APPROVED | No | 2024-03-26 | Abas, Mohammed Fekry | 2024-03-28 | 2024-03-28 |  |  |  | 22000 | 5222 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 21372.83 | APPROVED |  |  | 2024-04-18 | 627.17 | 21 | Kumar, Mr. Ranjan | -45379 | 21
105-92 | HAMDANIYAH 110/13.8kV S/S | 2907 | HAMDANIYAH 110/13.8kV S/S-HMD Horizontal Equal cross tray | APPROVED | No | 2024-03-26 | Abas, Mohammed Fekry | 2024-03-28 | 2024-03-28 |  |  |  | 200 | 5222 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 175.77 | APPROVED |  |  | 2024-04-18 | 24.23 | 21 | Kumar, Mr. Ranjan | -45379 | 21
105-92 | HAMDANIYAH 110/13.8kV S/S | 3313 | HAMDANIYAH 110/13.8kV S/S-HMD SAS Furniture | APPROVED | No | 2024-05-06 | Abas, Mohammed Fekry | 2024-05-08 | 2024-05-12 |  |  |  | 55000 | 5302 | 1 | STANDARD | ALFANAR CO | SAR | 55000 | APPROVED |  |  | 2024-07-21 | 0 | 70 | Kumar, Mr. Ranjan | -45424 | 70
105-92 | HAMDANIYAH 110/13.8kV S/S | 3401 | HAMDANIYAH 110/13.8kV S/S-HMD Temporary Charger | REJECTED | No | 2024-05-14 | Issa, Amr Ali | 2024-05-15 | 2024-05-14 |  | 2024-05-15 |  | 40000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45426 | -45426
105-92 | HAMDANIYAH 110/13.8kV S/S | 3450 | HAMDANIYAH 110/13.8kV S/S-HMD ligthing control system | RETURNED | No | 2024-05-20 | Kumar, Mr. Ranjan | 2025-09-11 | 2024-05-21 | 2025-09-11 |  | PO 5619 was prepared, later it was cancelled as confirmed by PMT via email dated 20 May 2025 | 105000 | 5619 | 0 | STANDARD | Smart wise Contracting Est | SAR | 104348 | APPROVED |  |  | 2024-07-02 | 652 |  | Muhammad, Muhammad Atif | -45433 | 42
105-92 | HAMDANIYAH 110/13.8kV S/S | 3450 | HAMDANIYAH 110/13.8kV S/S-HMD ligthing control system | RETURNED | No | 2024-05-20 | Kumar, Mr. Ranjan | 2025-09-11 | 2024-05-21 | 2025-09-11 |  | PO 5619 was prepared, later it was cancelled as confirmed by PMT via email dated 20 May 2025 | 105000 | [5 empty] | 0 |  |  |  |  | 0 |  | Muhammad, Muhammad Atif | -45433 | -45433
105-92 | HAMDANIYAH 110/13.8kV S/S | 3451 | HAMDANIYAH 110/13.8kV S/S-HMD Fiber Optic Supply installation and testing | APPROVED | No | 2024-05-20 | Abas, Mohammed Fekry | 2024-05-21 | 2024-05-21 |  |  |  | 300000 | 5870 | 0 | STANDARD | Arabian Power Trading Est. | SAR | 170000 | APPROVED |  |  | 2024-08-27 | 130000 | 98 | Abdulqader, Ahmed Abdulhalim | -45433 | 98
105-92 | HAMDANIYAH 110/13.8kV S/S | 3497 | HAMDANIYAH 110/13.8kV S/S-HMD lighting fixtures installtion | APPROVED | No | 2024-05-27 | Abas, Mohammed Fekry | 2024-05-28 | 2024-05-28 |  |  |  | 215000 | 5145 | 1 | STANDARD | Hussain Ali Hussain Contracting Company | SAR | 215000 | APPROVED |  |  | 2024-07-17 | 0 | 50 | Kumar, Mr. Ranjan | -45440 | 50
105-92 | HAMDANIYAH 110/13.8kV S/S | 3498 | HAMDANIYAH 110/13.8kV S/S-TPI for FAT of HV connectors | APPROVED | No | 2024-05-27 | Abas, Mohammed Fekry | 2024-05-28 | 2024-05-28 |  |  |  | 15000 | 5764 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 6000 | APPROVED |  |  | 2024-07-14 | 9000 | 47 | Kumar, Mr. Ranjan | -45440 | 47
105-92 | HAMDANIYAH 110/13.8kV S/S | 3591 | HAMDANIYAH 110/13.8kV S/S-HMD 13.8Kv SWGR Tarining | REJECTED | No | 2024-06-04 | Issa, Amr Ali | 2024-06-05 | 2024-06-04 |  | 2024-06-05 |  | 10000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45447 | -45447
105-92 | HAMDANIYAH 110/13.8kV S/S | 3606 | HAMDANIYAH 110/13.8kV S/S-HMD 13.8Kv SWGR Tarining | APPROVED | No | 2024-06-06 | Abas, Mohammed Fekry | 2024-06-06 | 2024-06-06 |  |  |  | 10000 | 5301 | 1 | STANDARD | ALFANAR CO | SAR | 10000 | APPROVED |  |  | 2024-07-17 | 0 | 41 | Kumar, Mr. Ranjan | -45449 | 41
105-92 | HAMDANIYAH 110/13.8kV S/S | 3616 | HAMDANIYAH 110/13.8kV S/S-HMD MV Cables Clamps | REJECTED | No | 2024-06-06 | Issa, Amr Ali | 2024-06-09 | 2024-06-06 |  | 2024-06-09 |  | 115325 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45449 | -45449
105-92 | HAMDANIYAH 110/13.8kV S/S | 3667 | HAMDANIYAH 110/13.8kV S/S-HMD Testing and commissioning contractor | APPROVED | No | 2024-06-23 | Abas, Mohammed Fekry | 2024-06-25 | 2024-06-25 |  |  |  | 1875515 | 6012 | 0 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 1810318 | APPROVED |  |  | 2024-10-06 | 65197 | 103 | Kumar, Mr. Ranjan | -45468 | 103
105-92 | HAMDANIYAH 110/13.8kV S/S | 3797 | HAMDANIYAH 110/13.8kV S/S-HMD RTV coating | REJECTED | No | 2024-07-08 | Ghith, Saad Gamal | 2024-07-14 | 2024-07-10 |  | 2024-07-15 |  | 250000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45483 | -45483
105-92 | HAMDANIYAH 110/13.8kV S/S | 3896 | HAMDANIYAH 110/13.8kV S/S-conduits accessories and supports | APPROVED | No | 2024-07-15 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 154174.65 | 5860 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 140158.77 | APPROVED |  |  | 2024-08-27 | 14015.88 | 42 | Abdulqader, Ahmed Abdulhalim | -45489 | 42
105-92 | HAMDANIYAH 110/13.8kV S/S | 3897 | HAMDANIYAH 110/13.8kV S/S-RTV coating | APPROVED | No | 2024-07-15 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 80000 | 6190 | 0 | STANDARD | Y.S.G Global Arabia Contracting Co. | SAR | 44998 | APPROVED |  |  | 2024-10-29 | 35002 | 105 | Muaz, Alaa | -45489 | 105
105-92 | HAMDANIYAH 110/13.8kV S/S | 3930 | HAMDANIYAH 110/13.8kV S/S-MV clamps | APPROVED | No | 2024-07-16 | Abas, Mohammed Fekry | 2024-07-17 | 2024-07-18 |  |  |  | 89848 | 5866 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 74275 | APPROVED |  |  | 2024-08-06 | 15573 | 19 | Abdulqader, Ahmed Abdulhalim | -45491 | 19
105-92 | HAMDANIYAH 110/13.8kV S/S | 3961 | HAMDANIYAH 110/13.8kV S/S-Moblizaion Phase 2 | APPROVED | No | 2024-07-21 | Abas, Mohammed Fekry | 2024-07-23 | 2024-07-25 |  |  |  | 52000 | 6100 | 0 | STANDARD | Construction Expertise Est. | SAR | 39000 | APPROVED |  |  | 2024-09-05 | 13000 | 42 | Kumar, Mr. Ranjan | -45498 | 42
105-92 | HAMDANIYAH 110/13.8kV S/S | 4020 | HAMDANIYAH 110/13.8kV S/S-HMD Power Transformer and AccessoriesTransportation and Offloading | APPROVED | No | 2024-07-25 | Abas, Mohammed Fekry | 2024-07-29 | 2024-07-29 |  |  |  | 168000 | 5876 | 0 | STANDARD | MOHAMMED HAMAD AL-AHMADE FOR TRADING AND CONSTRACTION | SAR | 168000 | APPROVED |  |  | 2024-08-19 | 0 | 21 | Badhman, Saeed | -45502 | 21
105-92 | HAMDANIYAH 110/13.8kV S/S | 4061 | HAMDANIYAH 110/13.8kV S/S-HMD Rental Power testing and commissioning with alafanar. | RETURNED | No | 2024-07-31 | Kumar, Mr. Ranjan | 2025-06-15 | 2024-08-01 | 2025-06-15 |  | PO cancelled, hence PR is returned | 150000 | 6311 | 0 | STANDARD | ZAT for Contracting Est. | SAR | 149500 | APPROVED |  |  | 2024-10-29 | 500 |  | Kumar, Mr. Ranjan | -45505 | 89
105-92 | HAMDANIYAH 110/13.8kV S/S | 4061 | HAMDANIYAH 110/13.8kV S/S-HMD Rental Power testing and commissioning with alafanar. | RETURNED | No | 2024-07-31 | Kumar, Mr. Ranjan | 2025-06-15 | 2024-08-01 | 2025-06-15 |  | PO cancelled, hence PR is returned | 150000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45505 | -45505
105-92 | HAMDANIYAH 110/13.8kV S/S | 4153 | HAMDANIYAH 110/13.8kV S/S-Rental Protection Engineer | RETURNED | No | 2024-08-14 | Kumar, Mr. Ranjan | 2024-12-04 | 2024-08-19 | 2024-12-04 |  | Manpower will be from NIT | 85652 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45523 | -45523
105-92 | HAMDANIYAH 110/13.8kV S/S | 4154 | HAMDANIYAH 110/13.8kV S/S-LUGS and Glands | RETURNED | No | 2024-08-14 | Muaz, Alaa | 2024-09-25 | 2024-08-20 | 2024-09-25 |  | The PR isn't itemized | 50000 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -45524 | -45524
105-92 | HAMDANIYAH 110/13.8kV S/S | 4155 | HAMDANIYAH 110/13.8kV S/S-HMD cable Tray 3 | RETURNED | No | 2024-08-14 | Badhman, Saeed | 2024-09-09 | 2024-08-19 | 2024-09-09 |  | Please provide the change order form signed | 49712.9 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45523 | -45523
105-92 | HAMDANIYAH 110/13.8kV S/S | 4177 | HAMDANIYAH 110/13.8kV S/S-Earthing Matrials-2 | APPROVED | No | 2024-08-18 | Abas, Mohammed Fekry | 2024-08-24 | 2024-08-25 |  |  |  | 15725 | 4908 | 1 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 15365 | APPROVED |  |  | 2024-09-10 | 360 | 16 | Babic, Marian | -45529 | 16
105-92 | HAMDANIYAH 110/13.8kV S/S | 4516 | HAMDANIYAH 110/13.8kV S/S-CSD office furniture | APPROVED | No | 2024-09-25 | Abas, Mohammed Fekry | 2024-09-29 | 2024-09-29 |  |  |  | 15000 | 6282 | 0 | STANDARD | Excellence Area Trading Est.(S) | SAR | 7350 | APPROVED |  |  | 2024-10-06 | 7650 | 7 | Kumar, Mr. Ranjan | -45564 | 7
105-92 | HAMDANIYAH 110/13.8kV S/S | 4605 | HAMDANIYAH 110/13.8kV S/S-HMD 4 lightning Mast Duplex painting | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-07 | 2024-10-07 |  |  |  | 19156 | 6303 | 0 | STANDARD | Zamil Industrial Coatings Factory Ltd. Company | SAR | 19156 | APPROVED |  |  | 2024-10-17 | 0 | 10 | Eliwa, Mahmoud | -45572 | 10
105-92 | HAMDANIYAH 110/13.8kV S/S | 4722 | HAMDANIYAH 110/13.8kV S/S-Copper Tape | APPROVED | No | 2024-10-18 | Abas, Mohammed Fekry | 2024-10-21 | 2024-10-22 |  |  |  | 17500 | 4786 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 16887.5 | APPROVED |  |  | 2024-11-13 | 612.5 | 22 | Babic, Marian | -45587 | 22
105-92 | HAMDANIYAH 110/13.8kV S/S | 4737 | HAMDANIYAH 110/13.8kV S/S-Cabe Tary and supports | APPROVED | No | 2024-10-20 | Abas, Mohammed Fekry | 2024-10-21 | 2024-10-22 |  |  |  | 74637.1 | 5222 | 1 | STANDARD | Mid-East Cable Support Solutions | SAR | 73144.95 | APPROVED |  |  | 2024-11-26 | 1492.15 | 35 | Badhman, Saeed | -45587 | 35
105-92 | HAMDANIYAH 110/13.8kV S/S | 4742 | HAMDANIYAH 110/13.8kV S/S-LUGS and Glands | APPROVED | No | 2024-10-20 | Abas, Mohammed Fekry | 2024-10-27 | 2024-10-27 |  |  |  | 72170 | 6391 | 0 | STANDARD | Ahmed Essa Mohammed Al Muslim Est. | SAR | 64998.5 | APPROVED |  |  | 2024-11-11 | 7171.5 | 15 | Muaz, Alaa | -45592 | 15
105-92 | HAMDANIYAH 110/13.8kV S/S | 4952 | HAMDANIYAH 110/13.8kV S/S-HMD Fire Stop Matrials | APPROVED | No | 2024-11-14 | Abas, Mohammed Fekry | 2024-11-20 | 2024-11-21 |  |  |  | 92200 | 6540 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 88200 | APPROVED |  |  | 2024-12-15 | 4000 | 24 | Kumar, Mr. Ranjan | -45617 | 24
105-92 | HAMDANIYAH 110/13.8kV S/S | 5085 | HAMDANIYAH 110/13.8kV S/S-HMD Recepticals | APPROVED | No | 2024-11-28 | Abas, Mohammed Fekry | 2024-12-03 | 2024-12-03 |  |  |  | 148416 | 6616 | 0 | STANDARD | Tawasul International Trad.Est. | SAR | 148416 | APPROVED |  |  | 2025-01-16 | 0 | 44 | Kumar, Mr. Ranjan | -45629 | 44
105-92 | HAMDANIYAH 110/13.8kV S/S | 5139 | HAMDANIYAH 110/13.8kV S/S-Grounding Cables and Y/G | RETURNED | No | 2024-12-12 | Badhman, Saeed | 2025-04-06 | 2025-01-12 |  |  |  | 31500 | 4786 | 2 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 29000 | APPROVED |  |  | 2025-04-16 | 2500 |  | Babic, Marian | -45669 | 94
105-92 | HAMDANIYAH 110/13.8kV S/S | 5139 | HAMDANIYAH 110/13.8kV S/S-Grounding Cables and Y/G | RETURNED | No | 2024-12-12 | Badhman, Saeed | 2025-04-06 | 2025-01-12 |  |  |  | 4200 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45669 | -45669
105-92 | HAMDANIYAH 110/13.8kV S/S | 5215 | HAMDANIYAH 110/13.8kV S/S-HMD PDS system | APPROVED | No | 2024-12-11 | Abas, Mohammed Fekry | 2024-12-16 | 2024-12-19 |  |  |  | 220000 | 6807 | 0 | STANDARD | Procomme Technology Co | SAR | 168000 | APPROVED |  |  | 2025-01-28 | 52000 | 40 | Kumar, Mr. Ranjan | -45645 | 40
105-92 | HAMDANIYAH 110/13.8kV S/S | 5300 | HAMDANIYAH 110/13.8kV S/S-HMD Lighting wires | RETURNED | No | 2024-12-30 | Kumar, Mr. Ranjan | 2025-03-13 | 2025-03-13 |  |  | budge line 3.3 | 44915 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45729 | -45729
105-92 | HAMDANIYAH 110/13.8kV S/S | 5344 | HAMDANIYAH 110/13.8kV S/S-HMD Motion sensor | APPROVED | No | 2025-01-02 | Abas, Mohammed Fekry | 2025-01-12 | 2025-01-12 |  |  |  | 9860 | 6724 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 9851.3 | APPROVED |  |  | 2025-01-21 | 8.7 | 9 | Muaz, Alaa | -45669 | 9
105-92 | HAMDANIYAH 110/13.8kV S/S | 5414 | HAMDANIYAH 110/13.8kV S/S-Transformer Oil Sampling and test | APPROVED | No | 2025-03-08 | Abas, Mohammed Fekry | 2025-03-12 | 2025-03-13 |  |  | 4.27 | 42000 | 7022 | 0 | STANDARD | Energy Distributor Co. Ltd | SAR | 35161.5 | APPROVED |  |  | 2025-03-18 | 6838.5 | 5 | Kumar, Mr. Ranjan | -45729 | 5
105-92 | HAMDANIYAH 110/13.8kV S/S | 5478 | HAMDANIYAH 110/13.8kV S/S-Push buttons for light | APPROVED | No | 2025-01-20 | Abas, Mohammed Fekry | 2025-01-22 | 2025-01-23 |  |  |  | 10780 | 6815 | 0 | STANDARD | Tawasul International Trad.Est. | SAR | 10594.02 | APPROVED |  |  | 2025-02-12 | 185.98 | 20 | Alqadhi, Abdulrahman Abdulghani | -45680 | 20
105-92 | HAMDANIYAH 110/13.8kV S/S | 5692 | HAMDANIYAH 110/13.8kV S/S-substation furnitures | APPROVED | No | 2025-01-27 | Abas, Mohammed Fekry | 2025-06-04 | 2025-06-12 | 2025-06-02 |  | Please revise the amount | 40000 | 7415 | 0 | STANDARD | ALISMAIL INDUSTRIAL CO.(S) | SAR | 26500 | APPROVED |  |  | 2025-07-17 | 13500 | 35 | Akhtar, Farhan | -45820 | 35
105-92 | HAMDANIYAH 110/13.8kV S/S | 5707 | HAMDANIYAH 110/13.8kV S/S-HMD Lighting wires | APPROVED | No | 2025-01-28 | Abas, Mohammed Fekry | 2025-01-29 | 2025-01-30 |  |  |  | 34545 | 6828 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 34545 | APPROVED |  |  | 2025-02-06 | 0 | 7 | Kumar, Mr. Ranjan | -45687 | 7
105-92 | HAMDANIYAH 110/13.8kV S/S | 6168 | HAMDANIYAH 110/13.8kV S/S-HMD Lighting wires-2 | APPROVED | No | 2025-03-11 | Abas, Mohammed Fekry | 2025-03-13 | 2025-03-13 |  |  | budget line 3.3 | 31200 | 7012 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 30550 | APPROVED |  |  | 2025-03-18 | 650 | 5 | Kumar, Mr. Ranjan | -45729 | 5
105-92 | HAMDANIYAH 110/13.8kV S/S | 6184 | HAMDANIYAH 110/13.8kV S/S-MV Clamps 2 | APPROVED | No | 2025-03-14 | Abas, Mohammed Fekry | 2025-03-18 | 2025-03-20 |  |  | budget line 2.1.9.9 | 13500 | 5866 | 1 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 11250 | APPROVED |  |  | 2025-04-28 | 2250 | 39 | Abdulqader, Ahmed Abdulhalim | -45736 | 39
105-92 | HAMDANIYAH 110/13.8kV S/S | 6269 | HAMDANIYAH 110/13.8kV S/S-Modification For Fault recorder at HHR-2 | APPROVED | No | 2025-03-25 | Abas, Mohammed Fekry | 2025-03-27 | 2025-03-27 |  |  | budget line 6.1 | 65000 | 7132 | 0 | STANDARD | SAUDI ARABIAN INDUSTRIAL & TRADING Co. | SAR | 59000 | APPROVED |  |  | 2025-04-29 | 6000 | 33 | Babic, Marian | -45743 | 33
105-92 | HAMDANIYAH 110/13.8kV S/S | 6923 | HAMDANIYAH 110/13.8kV S/S-Oil Sample test After Energization | APPROVED | No | 2025-06-29 | Abas, Mohammed Fekry | 2025-07-02 | 2025-07-03 |  |  | budget line 4.27 | 30000 | 7022 | 1 | STANDARD | Energy Distributor Co. Ltd | SAR | 28627.5 | APPROVED |  |  | 2025-08-05 | 1372.5 | 33 | Kumar, Mr. Ranjan | -45841 | 33
105-92 | HAMDANIYAH 110/13.8kV S/S | 7010 | HAMDANIYAH 110/13.8kV S/S-Demoblization Scope | RETURNED | No | 2025-07-08 | Kumar, Mr. Ranjan | 2025-09-07 | 2025-07-12 | 2025-09-07 |  | PR 7624 is considered | 20000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45850 | -45850
105-92 | HAMDANIYAH 110/13.8kV S/S | 7624 | Demoblization | APPROVED | No | 2025-09-02 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-03 |  |  |  | 0 | 7680 | 0 | STANDARD | Sam OG Construction | SAR | 24000 | APPROVED |  |  | 2025-09-10 | -24000 | 7 | Kumar, Mr. Ranjan | -45903 | 7
105-93 | BUHAIYRAT 110/13.8kV S/S | 1600 | BUHAIYRAT 110/13.8kV S/S-Design & Engeering services (For Manual PO-8259) | APPROVED | No | 2023-10-16 | Abas, Mohammed Fekry | 2023-10-17 | 2023-10-17 |  |  |  | 475000 | 4681 | 0 | STANDARD | Bahrawy Consultancy Group B.C.G | SAR | 475000 | APPROVED |  |  | 2023-11-05 | 0 | 19 | Kumar, Mr. Ranjan | -45216 | 19
105-93 | BUHAIYRAT 110/13.8kV S/S | 1647 | BUHAIYRAT 110/13.8kV S/S-Soil improvement by stone columns | APPROVED | No | 2023-11-01 | Abas, Mohammed Fekry | 2023-11-05 | 2023-11-05 |  |  |  | 1820000 | 4734 | 0 | STANDARD | Akam Gulf Contracting Est. | SAR | 1676600 | APPROVED |  |  | 2023-11-28 | 143400 | 23 | Kumar, Mr. Ranjan | -45235 | 23
105-93 | BUHAIYRAT 110/13.8kV S/S | 1652 | BUHAIYRAT 110/13.8kV S/S-Environmental & Social Impact Study (ESIA) | APPROVED | No | 2023-11-01 | Abas, Mohammed Fekry | 2023-11-05 | 2023-11-05 |  |  |  | 32500 | 4711 | 0 | STANDARD | Aran Aljazeera Enviromental Consultant | SAR | 32500 | APPROVED |  |  | 2023-11-19 | 0 | 14 | Kumar, Mr. Ranjan | -45235 | 14
105-93 | BUHAIYRAT 110/13.8kV S/S | 1687 | BUHAIYRAT 110/13.8kV S/S-Supply of IT materials (Desktops and printers) for site offices | APPROVED | No | 2023-11-12 | Abas, Mohammed Fekry | 2023-11-14 | 2023-11-15 |  |  |  | 22790 | 4727 | 0 | STANDARD | Golden Technology trading Company. | SAR | 22790 | APPROVED |  |  | 2023-11-19 | 0 | 4 | Abuhammad, Samir | -45245 | 4
105-93 | BUHAIYRAT 110/13.8kV S/S | 1689 | BUHAIYRAT 110/13.8kV S/S-Site Moblization (Ofices and Misceallanous Items) | APPROVED | No | 2023-11-12 | Abas, Mohammed Fekry | 2023-11-14 | 2023-11-15 |  |  |  | 390950 | 5304 | 0 | STANDARD | Construction Expertise Est. | SAR | 390950 | APPROVED |  |  | 2024-04-02 | 0 | 139 | Kumar, Mr. Ranjan | -45245 | 139
105-93 | BUHAIYRAT 110/13.8kV S/S | 1698 | BUHAIYRAT 110/13.8kV S/S-Civil & architectural works subcontracting | APPROVED | No | 2023-11-13 | Abas, Mohammed Fekry | 2023-11-15 | 2023-11-16 |  |  |  | 12000000 | 4729 | 0 | STANDARD | Intelligent System General Contracting Company | SAR | 12000000 | APPROVED |  |  | 2023-11-27 | 0 | 11 | Kumar, Mr. Ranjan | -45246 | 11
105-93 | BUHAIYRAT 110/13.8kV S/S | 1730 | BUHAIYRAT 110/13.8kV S/S-Grounding Material Accessories | APPROVED | No | 2023-11-14 | Abas, Mohammed Fekry | 2023-11-14 | 2023-11-15 |  |  |  | 29065 | 4723 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 29065 | APPROVED |  |  | 2023-11-19 | 0 | 4 | Babic, Marian | -45245 | 4
105-93 | BUHAIYRAT 110/13.8kV S/S | 1732 | BUHAIYRAT 110/13.8kV S/S-MV Cables | APPROVED | No | 2023-11-14 | Abas, Mohammed Fekry | 2023-11-15 | 2023-11-16 |  |  |  | 921011.54 | 5088 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 921011.54 | APPROVED |  |  | 2024-02-27 | 0 | 103 | Badhman, Saeed | -45246 | 103
105-93 | BUHAIYRAT 110/13.8kV S/S | 1741 | BUHAIYRAT 110/13.8kV S/S-Grounding Cables and Copper Tape | APPROVED | No | 2023-11-14 | Abas, Mohammed Fekry | 2023-11-15 | 2023-11-16 |  |  |  | 207281.32 | 4739 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 207281.32 | APPROVED |  |  | 2023-11-28 | 0 | 12 | Babic, Marian | -45246 | 12
105-93 | BUHAIYRAT 110/13.8kV S/S | 1742 | BUHAIYRAT 110/13.8kV S/S-Supply / Installation / Testing / Supervision of Power Transformer | APPROVED | No | 2023-11-14 | Abas, Mohammed Fekry | 2023-11-15 | 2023-11-16 |  |  |  | 18592500 | 4766 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 18592500 | APPROVED |  |  | 2023-12-04 | 0 | 18 | Kumar, Mr. Ranjan | -45246 | 18
105-93 | BUHAIYRAT 110/13.8kV S/S | 1757 | BUHAIYRAT 110/13.8kV S/S-Supply / Installation supervision of 13.8KV MV SWGR | APPROVED | No | 2023-11-15 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 8800000 | 5290 | 0 | STANDARD | ALFANAR CO | SAR | 8800000 | APPROVED |  |  | 2024-04-02 | 0 | 138 | Kumar, Mr. Ranjan | -45246 | 138
105-93 | BUHAIYRAT 110/13.8kV S/S | 1758 | BUHAIYRAT 110/13.8kV S/S-Supply of Auxilliary Transformer | APPROVED | No | 2023-11-15 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 202000 | 5297 | 0 | STANDARD | ALFANAR CO | SAR | 202000 | APPROVED |  |  | 2024-04-02 | 0 | 138 | Kumar, Mr. Ranjan | -45246 | 138
105-93 | BUHAIYRAT 110/13.8kV S/S | 1760 | BUHAIYRAT 110/13.8kV S/S-Supply of Protection & Control Panels & SAS system | APPROVED | No | 2023-11-15 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 8767000 | 5291 | 0 | STANDARD | ALFANAR CO | SAR | 8511000 | APPROVED |  |  | 2024-04-02 | 256000 | 138 | Kumar, Mr. Ranjan | -45246 | 138
105-93 | BUHAIYRAT 110/13.8kV S/S | 1761 | BUHAIYRAT 110/13.8kV S/S-Supply / Installation Supervision / Testing of Telecom System | APPROVED | No | 2023-11-15 | Abas, Mohammed Fekry | 2023-11-20 | 2023-11-20 |  |  |  | 2400000 | 5292 | 0 | STANDARD | ALFANAR CO | SAR | 2400000 | APPROVED |  |  | 2024-04-02 | 0 | 134 | Kumar, Mr. Ranjan | -45250 | 134
105-93 | BUHAIYRAT 110/13.8kV S/S | 1774 | BUHAIYRAT 110/13.8kV S/S-Supply / Installation / Testing of Overhead Travelling Crane | APPROVED | No | 2023-11-16 | Abas, Mohammed Fekry | 2023-11-20 | 2023-11-20 |  |  |  | 138500 | 4767 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 138500 | APPROVED |  |  | 2023-12-04 | 0 | 14 | Kumar, Mr. Ranjan | -45250 | 14
105-93 | BUHAIYRAT 110/13.8kV S/S | 1775 | BUHAIYRAT 110/13.8kV S/S-Supply Installation / Testing and Integration of Cyber Security System | APPROVED | No | 2023-11-16 | Abas, Mohammed Fekry | 2023-11-20 | 2023-11-20 |  |  |  | 1525000 | 5294 | 0 | STANDARD | ALFANAR CO | SAR | 1525000 | APPROVED |  |  | 2024-04-02 | 0 | 134 | Kumar, Mr. Ranjan | -45250 | 134
105-93 | BUHAIYRAT 110/13.8kV S/S | 1776 | BUHAIYRAT 110/13.8kV S/S- Supply / Installation Supervision and Testing of 125V Battery and Charger | APPROVED | No | 2023-11-16 | Abas, Mohammed Fekry | 2023-11-20 | 2023-11-20 |  |  |  | 584000 | 5299 | 0 | STANDARD | Alassas Specialized Company Ltd | SAR | 570000 | APPROVED |  |  | 2024-04-02 | 14000 | 134 | Kumar, Mr. Ranjan | -45250 | 134
105-93 | BUHAIYRAT 110/13.8kV S/S | 1776 | BUHAIYRAT 110/13.8kV S/S- Supply / Installation Supervision and Testing of 125V Battery and Charger | APPROVED | No | 2023-11-16 | Abas, Mohammed Fekry | 2023-11-20 | 2023-11-20 |  |  |  | 584000 | 5299 | 1 | STANDARD | Alassas Specialized Company Ltd | SAR | 570000 | REQUIRES REAPPROVAL |  |  |  | 14000 | 804 | Kumar, Mr. Ranjan | -45250 | -45250
105-93 | BUHAIYRAT 110/13.8kV S/S | 1777 | BUHAIYRAT 110/13.8kV S/S-Supply of Neutral Earthing Resistor (NER) | APPROVED | No | 2023-11-16 | Abas, Mohammed Fekry | 2023-11-20 | 2023-11-20 |  |  |  | 114750 | 5289 | 0 | STANDARD | National Switchgears | USD | 114750 | APPROVED |  |  | 2024-04-02 | 0 | 134 | Kumar, Mr. Ranjan | -45250 | 134
105-93 | BUHAIYRAT 110/13.8kV S/S | 1778 | BUHAIYRAT 110/13.8kV S/S-Supply / Installation Supervision and Testing and of 110KV GIS | APPROVED | No | 2023-11-16 | Abas, Mohammed Fekry | 2023-11-20 | 2023-11-20 |  |  |  | 11463750 | 4768 | 0 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 11062500 | APPROVED |  |  | 2023-12-04 | 401250 | 14 | Kumar, Mr. Ranjan | -45250 | 14
105-93 | BUHAIYRAT 110/13.8kV S/S | 1798 | BUHAIYRAT 110/13.8kV S/S-Supply of surge arrestor & accessories | APPROVED | No | 2023-11-20 | Abas, Mohammed Fekry | 2023-11-22 | 2023-11-23 |  |  |  | 51356.25 | 5295 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | USD | 51356.36 | APPROVED |  |  | 2024-03-31 | -0.11 | 129 | Kumar, Mr. Ranjan | -45253 | 129
105-93 | BUHAIYRAT 110/13.8kV S/S | 1814 | BUHAIYRAT 110/13.8kV S/S-Supply of MV Termination Kits | REJECTED | No | 2023-11-26 | Ilyas, Mohammed | 2023-11-26 |  |  | 2023-11-26 |  | 217000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-93 | BUHAIYRAT 110/13.8kV S/S | 1820 | BUHAIYRAT 110/13.8kV S/S-Supply Installation / Testing and Integration of Security System | APPROVED | No | 2023-11-27 | Abas, Mohammed Fekry | 2023-11-28 | 2023-11-28 |  |  |  | 900000 | 4960 | 0 | STANDARD | Reda Trading & Development Co. for Machinery & Equipment Ltd(S) | SAR | 769306 | APPROVED |  |  | 2024-01-30 | 130694 | 63 | Mohammed, Faisal Ansari | -45258 | 63
105-93 | BUHAIYRAT 110/13.8kV S/S | 1821 | BUHAIYRAT 110/13.8kV S/S-Supply / Installation and Testing of Fire Protection & Alarm System | APPROVED | No | 2023-11-27 | Abas, Mohammed Fekry | 2023-11-28 | 2023-11-28 |  |  |  | 2100000 | 5047 | 0 | STANDARD | Reda Trading & Development Co. for Machinery & Equipment Ltd(S) | SAR | 1952000 | APPROVED |  |  | 2024-03-21 | 148000 | 114 | Kumar, Mr. Ranjan | -45258 | 114
105-93 | BUHAIYRAT 110/13.8kV S/S | 1823 | BUHAIYRAT 110/13.8kV S/S-Supply of HV Clamps (Connectors) | REJECTED | No | 2023-11-27 | Ilyas, Mohammed | 2023-11-27 |  |  | 2023-11-27 |  | 6120 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-93 | BUHAIYRAT 110/13.8kV S/S | 1835 | BUHAIYRAT 110/13.8kV S/S-Supply of HV Clamps - Connectors | REJECTED | No | 2023-11-28 | Ilyas, Mohammed | 2023-11-28 |  |  | 2023-11-28 |  | 6120 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-93 | BUHAIYRAT 110/13.8kV S/S | 1846 | BUHAIYRAT 110/13.8kV S/S-Design / Supply Installation and Testing of HVAC System | APPROVED | No | 2023-11-28 | Abas, Mohammed Fekry | 2023-11-30 | 2023-11-30 |  |  |  | 1800000 | 4817 | 0 | STANDARD | MARINE SERVICES CO LTD. | SAR | 1750000 | APPROVED |  |  | 2023-12-26 | 50000 | 26 | Alhadi, Khalid | -45260 | 26
105-93 | BUHAIYRAT 110/13.8kV S/S | 1846 | BUHAIYRAT 110/13.8kV S/S-Design / Supply Installation and Testing of HVAC System | APPROVED | No | 2023-11-28 | Abas, Mohammed Fekry | 2023-11-30 | 2023-11-30 |  |  |  | 1800000 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45260 | -45260
105-93 | BUHAIYRAT 110/13.8kV S/S | 1852 | BUHAIYRAT 110/13.8kV S/S-Supply of HV Clamps - Connectors | APPROVED | No | 2023-11-29 | Abas, Mohammed Fekry | 2023-11-30 | 2023-11-30 |  |  |  | 10920 | 5109 | 0 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 8196.3 | APPROVED |  |  | 2024-02-28 | 2723.7 | 90 | Mohammed, Faisal Ansari | -45260 | 90
105-93 | BUHAIYRAT 110/13.8kV S/S | 1853 | BUHAIYRAT 110/13.8kV S/S-Supply of AC DC DB and Lighting Panels | APPROVED | No | 2023-11-29 | Abas, Mohammed Fekry | 2023-11-30 | 2023-11-30 |  |  |  | 787000 | 4803 | 0 | STANDARD | ALFANAR CO | SAR | 787000 | APPROVED |  |  | 2024-01-18 | 0 | 49 | Kumar, Mr. Ranjan | -45260 | 49
105-93 | BUHAIYRAT 110/13.8kV S/S | 1876 | BUHAIYRAT 110/13.8kV S/S-Building Permit | APPROVED | No | 2023-11-30 | Abas, Mohammed Fekry | 2023-12-06 | 2023-12-07 | 2023-12-05 |  | Please specify the scope of work. Attach related drawings so that RFQ can be innitiated. | 40000 | 4912 | 0 | STANDARD | Emad A.A.Nadreen for Engineering Consultation | SAR | 40000 | APPROVED |  |  | 2023-12-31 | 0 | 24 | Kumar, Mr. Ranjan | -45267 | 24
105-93 | BUHAIYRAT 110/13.8kV S/S | 1883 | BUHAIYRAT 110/13.8kV S/S-200KVA Diesel Rental Generator & 30KVA Diesel Rental Generator | APPROVED | No | 2023-12-03 | Abas, Mohammed Fekry | 2023-12-04 | 2023-12-05 |  |  |  | 64600 | 4907 | 0 | STANDARD | Deyar United Advance Contracting Company | SAR | 64600 | APPROVED |  |  | 2023-12-31 | 0 | 26 | Badhman, Saeed | -45265 | 26
105-93 | BUHAIYRAT 110/13.8kV S/S | 1946 | BUHAIYRAT 110/13.8kV S/S-Supply/Installation testing & commissioning of 2 Ton wall mounted JIB crane | APPROVED | No | 2023-12-12 | Abas, Mohammed Fekry | 2023-12-13 | 2023-12-14 |  |  |  | 180000 | 4981 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 163000 | APPROVED |  |  | 2024-05-19 | 17000 | 157 | Kumar, Mr. Ranjan | -45274 | 157
105-93 | BUHAIYRAT 110/13.8kV S/S | 2024 | BUHAIYRAT 110/13.8kV S/S-Supply of lighting panels | APPROVED | No | 2023-12-21 | Abas, Mohammed Fekry | 2023-12-24 | 2023-12-25 |  |  |  | 70000 | 4803 | 0 | STANDARD | ALFANAR CO | SAR | 50000 | APPROVED |  |  | 2024-01-18 | 20000 | 24 | Kumar, Mr. Ranjan | -45285 | 24
105-93 | BUHAIYRAT 110/13.8kV S/S | 2163 | BUHAIYRAT 110/13.8kV S/S-Supply of Termination Kits for MV Cables | APPROVED | No | 2024-01-14 | Abas, Mohammed Fekry | 2024-01-15 | 2024-01-16 |  |  |  | 80000 | 4957 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 80000 | APPROVED |  |  | 2024-01-29 | 0 | 13 | Kumar, Mr. Ranjan | -45307 | 13
105-93 | BUHAIYRAT 110/13.8kV S/S | 2189 | BUHAIYRAT 110/13.8kV S/S-Supply of Termination Kit for MV Cables | APPROVED | No | 2024-01-17 | Abas, Mohammed Fekry | 2024-01-21 | 2024-01-21 |  |  |  | 1050 | 4957 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 1008.2 | APPROVED |  |  | 2024-01-29 | 41.8 | 8 | Kumar, Mr. Ranjan | -45312 | 8
105-93 | BUHAIYRAT 110/13.8kV S/S | 2516 | BUHAIYRAT 110/13.8kV S/S-Buhaiyrat- Supply of Termination Kit for MV Cables (Lugs) | APPROVED | No | 2024-02-11 | Abas, Mohammed Fekry | 2024-02-11 | 2024-02-12 |  |  |  | 33000 | 4957 | 1 | STANDARD | Nima Arabia Company Limited | SAR | 31748.1 | APPROVED |  |  | 2024-02-27 | 1251.9 | 15 | Babic, Marian | -45334 | 15
105-93 | BUHAIYRAT 110/13.8kV S/S | 2613 | BUHAIYRAT 110/13.8kV S/S-Lightning Masts - BHT | REJECTED | No | 2024-10-23 | Abdelrahman, Ahmed Shaaban | 2024-10-23 |  |  | 2024-10-23 |  | 130000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-93 | BUHAIYRAT 110/13.8kV S/S | 2614 | BUHAIYRAT 110/13.8kV S/S-BHT- Lightning Masts | APPROVED | No | 2024-02-19 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 130000 | 5454 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 58750 | APPROVED |  |  | 2024-05-14 | 71250 | 78 | Muhammad, Muhammad Atif | -45348 | 78
105-93 | BUHAIYRAT 110/13.8kV S/S | 2725 | BUHAIYRAT 110/13.8kV S/S-Substation Electrical Equipment Installation Services | APPROVED | No | 2024-02-29 | Abas, Mohammed Fekry | 2024-02-29 | 2024-03-03 |  |  |  | 1800000 | 5149 | 0 | STANDARD | Hussain Ali Hussain Contracting Company | SAR | 1675000 | APPROVED |  |  | 2024-03-21 | 125000 | 18 | Kumar, Mr. Ranjan | -45354 | 18
105-93 | BUHAIYRAT 110/13.8kV S/S | 3057 | BUHAIYRAT 110/13.8kV S/S-Diesel for site Generator | APPROVED | No | 2024-04-18 | Abas, Mohammed Fekry | 2024-04-18 | 2024-04-24 |  |  |  | 95399.46 | 5442 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 95399.46 | APPROVED |  |  | 2024-05-14 | 0 | 20 | Abuhammad, Samir | -45406 | 20
105-93 | BUHAIYRAT 110/13.8kV S/S | 3395 | BUHAIYRAT 110/13.8kV S/S-BHT-SAS Furniture | APPROVED | No | 2024-05-14 | Abas, Mohammed Fekry | 2024-05-14 | 2024-05-14 |  |  |  | 55000 | 5291 | 1 | STANDARD | ALFANAR CO | SAR | 55000 | APPROVED |  |  | 2024-07-21 | 0 | 68 | Kumar, Mr. Ranjan | -45426 | 68
105-93 | BUHAIYRAT 110/13.8kV S/S | 3448 | BUHAIYRAT 110/13.8kV S/S-BHT- GIS Factory training (PO optional Item) | APPROVED | No | 2024-05-20 | Abas, Mohammed Fekry | 2024-05-21 | 2024-05-21 |  |  |  | 150000 | 4768 | 3 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 150000 | APPROVED |  |  | 2024-06-24 | 0 | 34 | Kumar, Mr. Ranjan | -45433 | 34
105-93 | BUHAIYRAT 110/13.8kV S/S | 3494 | BUHAIYRAT 110/13.8kV S/S-BHT- Fiber Optic Supply installation and testing | APPROVED | No | 2024-05-27 | Abas, Mohammed Fekry | 2024-10-21 | 2024-10-22 | 2024-08-06 |  | As disuessed with Eng. Ahmed SHaban this PR will re initated once the subject request is finalized | 300000 | 6891 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 140000 | APPROVED |  |  | 2025-02-17 | 160000 | 118 | Alqadhi, Abdulrahman Abdulghani | -45587 | 118
105-93 | BUHAIYRAT 110/13.8kV S/S | 3643 | BUHAIYRAT 110/13.8kV S/S-BHT LV and control cables -1 | RETURNED | No | 2024-06-11 | Badhman, Saeed | 2025-11-16 | 2024-06-12 | 2025-11-16 |  | PR not needed, PO AND CO are issued and approved | 491838.11 | 6103 | 0 | STANDARD | ALFANAR CO | SAR | 326659.8 | APPROVED |  |  | 2024-09-26 | 165178.31 |  | Badhman, Saeed | -45455 | 106
105-93 | BUHAIYRAT 110/13.8kV S/S | 3643 | BUHAIYRAT 110/13.8kV S/S-BHT LV and control cables -1 | RETURNED | No | 2024-06-11 | Badhman, Saeed | 2025-11-16 | 2024-06-12 | 2025-11-16 |  | PR not needed, PO AND CO are issued and approved | 147766.34 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45455 | -45455
105-93 | BUHAIYRAT 110/13.8kV S/S | 3655 | BUHAIYRAT 110/13.8kV S/S-BHT LV and control cables -2 | APPROVED | No | 2024-06-13 | Abas, Mohammed Fekry | 2024-06-20 | 2024-06-23 |  |  |  | 52282.57 | 6103 | 0 | STANDARD | ALFANAR CO | SAR | 35472 | APPROVED |  |  | 2024-09-26 | 16810.57 | 95 | Badhman, Saeed | -45466 | 95
105-93 | BUHAIYRAT 110/13.8kV S/S | 3657 | BUHAIYRAT 110/13.8kV S/S-BHT LV and control cables -3 | APPROVED | No | 2024-06-13 | Abas, Mohammed Fekry | 2024-06-20 | 2024-06-23 |  |  |  | 598268.89 | 6103 | 0 | STANDARD | ALFANAR CO | SAR | 410454.26 | APPROVED |  |  | 2024-09-26 | 187814.63 | 95 | Badhman, Saeed | -45466 | 95
105-93 | BUHAIYRAT 110/13.8kV S/S | 4144 | BUHAIYRAT 110/13.8kV S/S-Ladders & Trays-1 | APPROVED | No | 2024-08-12 | Abas, Mohammed Fekry | 2024-08-13 | 2024-08-13 |  |  |  | 127747.56 | 6247 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 127747.56 | APPROVED |  |  | 2024-10-16 | 0 | 64 | Badhman, Saeed | -45517 | 64
105-93 | BUHAIYRAT 110/13.8kV S/S | 4147 | BUHAIYRAT 110/13.8kV S/S-Ladders & Trays-2 | APPROVED | No | 2024-08-12 | Abas, Mohammed Fekry | 2024-08-13 | 2024-08-13 |  |  |  | 225337.94 | 6247 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 225337.94 | APPROVED |  |  | 2024-10-16 | 0 | 64 | Badhman, Saeed | -45517 | 64
105-93 | BUHAIYRAT 110/13.8kV S/S | 4166 | BUHAIYRAT 110/13.8kV S/S-BHT LV and control cables -4 | APPROVED | No | 2024-08-15 | Abas, Mohammed Fekry | 2024-08-24 | 2024-08-25 |  |  |  | 7738.98 | 6103 | 0 | STANDARD | ALFANAR CO | SAR | 5280.4 | APPROVED |  |  | 2024-09-26 | 2458.58 | 32 | Badhman, Saeed | -45529 | 32
105-93 | BUHAIYRAT 110/13.8kV S/S | 4608 | BUHAIYRAT 110/13.8kV S/S-BHT- 4 Lightning Mast Duplex Painting | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-07 | 2024-10-07 |  |  |  | 19156 | 6304 | 0 | STANDARD | Zamil Industrial Coatings Factory Ltd. Company | SAR | 19156 | APPROVED |  |  | 2024-10-17 | 0 | 10 | Eliwa, Mahmoud | -45572 | 10
105-93 | BUHAIYRAT 110/13.8kV S/S | 4775 | BUHAIYRAT 110/13.8kV S/S-BHT-Site Moblization (Ofices, Fencing and Misceallanous Items for Rental Land) | APPROVED | No | 2024-10-23 | Abas, Mohammed Fekry | 2024-10-27 | 2024-10-27 |  |  |  | 200000 | 6459 | 0 | STANDARD | Al Arab Modern Contracting Est | SAR | 147495 | APPROVED |  |  | 2024-11-17 | 52505 | 21 | Kumar, Mr. Ranjan | -45592 | 21
105-93 | BUHAIYRAT 110/13.8kV S/S | 4931 | BUHAIYRAT 110/13.8kV S/S-BHT- Cables (Wires) | APPROVED | No | 2024-11-13 | Abas, Mohammed Fekry | 2024-11-14 | 2024-11-17 |  |  |  | 39250 | 6479 | 0 | STANDARD | ALFANAR CO | SAR | 31518.01 | APPROVED |  |  | 2025-01-12 | 7731.99 | 56 | Badhman, Saeed | -45613 | 56
105-93 | BUHAIYRAT 110/13.8kV S/S | 5004 | BUHAIYRAT 110/13.8kV S/S-BHT Power Transformer and AccessoriesTransportation and Offloading | APPROVED | No | 2024-11-20 | Ilyas, Mohammed | 2024-12-12 | 2024-11-27 |  |  |  | 190000 | 6651 | 0 | STANDARD | MOHAMMED HAMAD AL-AHMADE FOR TRADING AND CONSTRACTION | SAR | 163000 | APPROVED |  |  | 2024-12-26 | 27000 | 14 | Alhadi, Khalid | -45623 | 29
105-93 | BUHAIYRAT 110/13.8kV S/S | 5112 | BUHAIYRAT 110/13.8kV S/S-BHT LV and control cables -5 | APPROVED | No | 2024-12-02 | Abas, Mohammed Fekry | 2024-12-04 | 2024-12-08 |  |  |  | 137546.98 | 6103 | 1 | STANDARD | ALFANAR CO | SAR | 137546.98 | APPROVED |  |  | 2025-05-06 | 0 | 149 | Badhman, Saeed | -45634 | 149
105-93 | BUHAIYRAT 110/13.8kV S/S | 5241 | BUHAIYRAT 110/13.8kV S/S-BHT- Indoor & Outdoor Lighting Fixtures | APPROVED | No | 2024-12-18 | Abas, Mohammed Fekry | 2024-12-19 | 2024-12-19 |  |  |  | 67849 | 6696 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 50878 | APPROVED |  |  | 2024-12-30 | 16971 | 11 | Alqadhi, Abdulrahman Abdulghani | -45645 | 11
105-93 | BUHAIYRAT 110/13.8kV S/S | 5242 | BUHAIYRAT 110/13.8kV S/S-BHT- Indoor Lighting Sensors | APPROVED | No | 2024-12-18 | Abas, Mohammed Fekry | 2024-12-19 | 2024-12-19 |  |  |  | 23200 | 6696 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 9860 | APPROVED |  |  | 2024-12-30 | 13340 | 11 | Alqadhi, Abdulrahman Abdulghani | -45645 | 11
105-93 | BUHAIYRAT 110/13.8kV S/S | 5381 | BUHAIYRAT 110/13.8kV S/S-Desgin, Supply and Install PDS system -BHT | APPROVED | No | 2025-01-09 | Abas, Mohammed Fekry | 2025-01-12 | 2025-01-12 |  |  |  | 325000 | 6891 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 165000 | APPROVED |  |  | 2025-02-17 | 160000 | 36 | Alqadhi, Abdulrahman Abdulghani | -45669 | 36
105-93 | BUHAIYRAT 110/13.8kV S/S | 5382 | BUHAIYRAT 110/13.8kV S/S-Supply of RTV Coating -BHT | APPROVED | No | 2025-01-09 | Abas, Mohammed Fekry | 2025-01-12 | 2025-01-12 |  |  |  | 250000 | 7045 | 0 | STANDARD | Y.S.G Global Arabia Contracting Co. | SAR | 47999 | APPROVED |  |  | 2025-04-16 | 202001 | 94 | Muaz, Alaa | -45669 | 94
105-93 | BUHAIYRAT 110/13.8kV S/S | 5383 | BUHAIYRAT 110/13.8kV S/S-Testing & Commissioning Work-BHT | APPROVED | No | 2025-01-09 | Abas, Mohammed Fekry | 2025-01-12 | 2025-01-12 |  |  |  | 2000000 | 6764 | 0 | STANDARD | Al Fanar Technical Services | SAR | 1810318 | APPROVED |  |  | 2025-02-17 | 189682 | 36 | Babic, Marian | -45669 | 36
105-93 | BUHAIYRAT 110/13.8kV S/S | 5501 | BUHAIYRAT 110/13.8kV S/S-MV Clamps- BHT | RETURNED | No | 2025-01-21 | Alqadhi, Abdulrahman Abdulghani | 2025-02-13 | 2025-01-23 | 2025-02-13 |  | Please revise the QTY. | 23150 | 6833 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 21175 | APPROVED |  |  | 2025-03-04 | 1975 |  | Alqadhi, Abdulrahman Abdulghani | -45680 | 40
105-93 | BUHAIYRAT 110/13.8kV S/S | 5947 | BUHAIYRAT 110/13.8kV S/S-MV Clamps 2 -BHT | APPROVED | No | 2025-02-17 | Abas, Mohammed Fekry | 2025-02-20 | 2025-02-22 |  |  | PR CREATED FOR RETURNED ITEMS ON PERIVOIS PR | 59900 | 6833 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 59900 | APPROVED |  |  | 2025-03-04 | 0 | 10 | Alqadhi, Abdulrahman Abdulghani | -45710 | 10
105-93 | BUHAIYRAT 110/13.8kV S/S | 5959 | BUHAIYRAT 110/13.8kV S/S-MV & LV Cable Clamps & Glands - Buhaiyrat | APPROVED | No | 2025-02-18 | Abas, Mohammed Fekry | 2025-02-20 | 2025-02-22 |  |  | 2.2.9 - MV & LV Cable Clamps & Glands | 13060 | 6953 | 0 | STANDARD | ELECTRIC POINT TRADING EST | SAR | 12110 | APPROVED |  |  | 2025-06-24 | 950 | 122 | Kumar, Mr. Ranjan | -45710 | 122
105-93 | BUHAIYRAT 110/13.8kV S/S | 5970 | BUHAIYRAT 110/13.8kV S/S-OUTDOOR RECEPTACLES | APPROVED | No | 2025-02-19 | Abas, Mohammed Fekry | 2025-02-20 | 2025-02-22 |  |  | Meet budget required | 65395 | 6948 | 0 | STANDARD | BAKHUT AL - GHUFRANI GEN. CONT. EST. | SAR | 79722.26 | APPROVED |  |  | 2025-03-28 | -14327.26 | 34 | Alqadhi, Abdulrahman Abdulghani | -45710 | 34
105-93 | BUHAIYRAT 110/13.8kV S/S | 5977 | BUHAIYRAT 110/13.8kV S/S-Outdoor Switches | APPROVED | No | 2025-02-19 | Abas, Mohammed Fekry | 2025-02-20 | 2025-02-22 |  |  | Meet the budget requirement. | 15219.2 | 6948 | 0 | STANDARD | BAKHUT AL - GHUFRANI GEN. CONT. EST. | SAR | 15514.4 | APPROVED |  |  | 2025-03-28 | -295.2 | 34 | Alqadhi, Abdulrahman Abdulghani | -45710 | 34
105-93 | BUHAIYRAT 110/13.8kV S/S | 5978 | BUHAIYRAT 110/13.8kV S/S-Indoor Push buttons | APPROVED | No | 2025-02-19 | Abas, Mohammed Fekry | 2025-02-20 | 2025-02-22 |  |  | Meet the budget requirement | 4546.08 | 6948 | 0 | STANDARD | BAKHUT AL - GHUFRANI GEN. CONT. EST. | SAR | 4546.08 | APPROVED |  |  | 2025-03-28 | 0 | 34 | Alqadhi, Abdulrahman Abdulghani | -45710 | 34
105-93 | BUHAIYRAT 110/13.8kV S/S | 5979 | BUHAIYRAT 110/13.8kV S/S-Indoor Switches | REJECTED | No | 2025-02-19 | Chaudhry, Shahid Bashir | 2025-02-19 |  |  | 2025-02-19 |  | 1661.32 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
105-93 | BUHAIYRAT 110/13.8kV S/S | 5980 | BUHAIYRAT 110/13.8kV S/S-Indoor Disconnector | APPROVED | No | 2025-02-19 | Abas, Mohammed Fekry | 2025-02-20 | 2025-02-22 |  |  | Meet the budget requirement. | 1603.1 | 6948 | 0 | STANDARD | BAKHUT AL - GHUFRANI GEN. CONT. EST. | SAR | 2931.5 | APPROVED |  |  | 2025-03-28 | -1328.4 | 34 | Alqadhi, Abdulrahman Abdulghani | -45710 | 34
105-93 | BUHAIYRAT 110/13.8kV S/S | 5987 | BUHAIYRAT 110/13.8kV S/S-Push Button DC Switches | APPROVED | No | 2025-02-19 | Abas, Mohammed Fekry | 2025-02-24 | 2025-02-25 |  |  | Meet the budget requirement. | 20882.49 | 6948 | 0 | STANDARD | BAKHUT AL - GHUFRANI GEN. CONT. EST. | SAR | 34019.85 | APPROVED |  |  | 2025-03-28 | -13137.36 | 31 | Alqadhi, Abdulrahman Abdulghani | -45713 | 31
105-93 | BUHAIYRAT 110/13.8kV S/S | 5990 | BUHAIYRAT 110/13.8kV S/S-Indoor Switches | APPROVED | No | 2025-02-19 | Abas, Mohammed Fekry | 2025-02-24 | 2025-02-25 |  |  | Meet the budget requirement. | 2030.32 | 6948 | 0 | STANDARD | BAKHUT AL - GHUFRANI GEN. CONT. EST. | SAR | 3088.12 | APPROVED |  |  | 2025-03-28 | -1057.8 | 31 | Alqadhi, Abdulrahman Abdulghani | -45713 | 31
105-93 | BUHAIYRAT 110/13.8kV S/S | 5994 | BUHAIYRAT 110/13.8kV S/S-Push Button DC Switches #2 | APPROVED | No | 2025-02-19 | Abas, Mohammed Fekry | 2025-02-24 | 2025-02-25 |  |  | budget item 3.4, please consider this PR and return the item number 5 from PR ( 5987) | 344.4 | 6948 | 0 | STANDARD | BAKHUT AL - GHUFRANI GEN. CONT. EST. | SAR | 756 | APPROVED |  |  | 2025-03-28 | -411.6 | 31 | Alqadhi, Abdulrahman Abdulghani | -45713 | 31
105-93 | BUHAIYRAT 110/13.8kV S/S | 6108 | BUHAIYRAT 110/13.8kV S/S-Indoor Lighting Conduits, Junction Boxes & Accessories - Buhaiyrat | APPROVED | No | 2025-03-04 | Abas, Mohammed Fekry | 2025-04-27 | 2025-04-28 |  |  | Meet budget required. | 191627.5 | 6953 | 0 | STANDARD | ELECTRIC POINT TRADING EST | SAR | 191627.5 | APPROVED |  |  | 2025-06-24 | 0 | 57 | Kumar, Mr. Ranjan | -45775 | 57
105-93 | BUHAIYRAT 110/13.8kV S/S | 6436 | BUHAIYRAT 110/13.8kV S/S-BHT- 4 Lightning Mast Duplex Painting (Transportation) | RETURNED | No | 2025-04-23 | Kumar, Mr. Ranjan | 2025-08-03 | 2025-04-24 | 2025-08-03 |  | Shall be paid by Cash | 500 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45771 | -45771
105-93 | BUHAIYRAT 110/13.8kV S/S | 6459 | BUHAIYRAT 110/13.8kV S/S-Substation Electrical Equipment Installation Services (Optional Scope Activation) | APPROVED | No | 2025-04-27 | Abas, Mohammed Fekry | 2025-04-28 | 2025-04-28 |  |  | Budget item #5.1.18- To activate Optional scope of PO ( lighting installation) | 276000 | 5149 | 1 | STANDARD | Hussain Ali Hussain Contracting Company | SAR | 275500 | APPROVED |  |  | 2025-05-08 | 500 | 10 | Kumar, Mr. Ranjan | -45775 | 10
105-93 | BUHAIYRAT 110/13.8kV S/S | 6460 | BUHAIYRAT 110/13.8kV S/S- Supply of 125V Battery and Charger ( Battery Recharging for inspection) | APPROVED | No | 2025-04-27 | Abas, Mohammed Fekry | 2025-04-28 | 2025-04-28 |  |  | Budget item 2.1.7.3- For PO ammenment to include Battries Recharging Expenses | 15750 | 5299 | 1 | STANDARD | Alassas Specialized Company Ltd | SAR | 15750 | REQUIRES REAPPROVAL |  |  |  | 0 | 279 | Kumar, Mr. Ranjan | -45775 | -45775
105-93 | BUHAIYRAT 110/13.8kV S/S | 6460 | BUHAIYRAT 110/13.8kV S/S- Supply of 125V Battery and Charger ( Battery Recharging for inspection) | APPROVED | No | 2025-04-27 | Abas, Mohammed Fekry | 2025-04-28 | 2025-04-28 |  |  | Budget item 2.1.7.3- For PO ammenment to include Battries Recharging Expenses | 15750 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45775 | -45775
105-93 | BUHAIYRAT 110/13.8kV S/S | 6466 | BUHAIYRAT 110/13.8kV S/S-Diesel for site Generator (PO Amendment) | APPROVED | No | 2025-04-27 | Abas, Mohammed Fekry | 2025-04-29 | 2025-04-30 |  |  | PO ammendment for Pending payments (INV of March & April 2025) + additional 5 months supply for the project site generators as there is no avilible power source (2 Generators on site + 1 Temporary for PT installation) - Budget item #4.1.7 | 128566.55 | 5442 | 1 | STANDARD | Talaea Alahlam Trading Company | SAR | 128566.55 | APPROVED |  |  | 2025-05-13 | 0 | 13 | Abuhammad, Samir | -45777 | 13
105-93 | BUHAIYRAT 110/13.8kV S/S | 6509 | BUHAIYRAT 110/13.8kV S/S-Fire Stop materials - BHT | REJECTED | No | 2025-05-05 | Ghith, Saad Gamal | 2025-06-18 | 2025-05-11 |  | 2025-06-19 |  | 120600 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45788 | -45788
105-93 | BUHAIYRAT 110/13.8kV S/S | 6794 | BUHAIYRAT 110/13.8kV S/S-Soil Investigation - Buhaiyrat | APPROVED | No | 2025-06-12 | Abas, Mohammed Fekry | 2025-06-15 | 2025-06-15 |  |  | 3.6 | 26545 | 7695 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 26545 | APPROVED |  |  | 2025-09-25 | 0 | 102 | Kumar, Mr. Ranjan | -45823 | 102
105-93 | BUHAIYRAT 110/13.8kV S/S | 6833 | BUHAIYRAT 110/13.8kV S/S-Fire Stop Materials - Buhaiyrat | APPROVED | No | 2025-06-19 | Abas, Mohammed Fekry | 2025-06-23 | 2025-06-25 |  |  | 2.1.6.9 | 97560 | 7430 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 85800 | APPROVED |  |  | 2025-07-02 | 11760 | 7 | Kumar, Mr. Ranjan | -45833 | 7
105-93 | BUHAIYRAT 110/13.8kV S/S | 6852 | BUHAIYRAT 110/13.8kV S/S-LV & Control Cables Ladders, F.O Trays, Supports & Accessories - Buhaiyrat | REJECTED | No | 2025-06-22 | Ghith, Saad Gamal | 2025-07-16 | 2025-06-24 |  | 2025-07-16 |  | 54354.4 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45832 | -45832
105-93 | BUHAIYRAT 110/13.8kV S/S | 6861 | BUHAIYRAT 110/13.8kV S/S-Fiber optic cables supply and installation 2 | APPROVED | No | 2025-06-23 | Abas, Mohammed Fekry | 2025-07-24 | 2025-07-27 |  |  | budget item 5.1.18 | 138127 | 6891 | 1 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 137250 | APPROVED |  |  | 2025-11-20 | 877 | 116 | Kumar, Mr. Ranjan | -45865 | 116
105-93 | BUHAIYRAT 110/13.8kV S/S | 7083 | BUHAIYRAT 110/13.8kV S/S-Technicians for Testing and Commissioning-BHT | APPROVED | No | 2025-07-14 | Abas, Mohammed Fekry | 2025-07-20 | 2025-07-20 |  |  | Buddget line item#6.1 , please note that 4 Technicians are needed for T&C, for a perioud of 4 months (10Hrs- 26 days Per month)- Calculated Daily rate for this PR is 20 SAR/ hr. | 124800 | 7831 | 0 | STANDARD | Modern Technical Fields Contracting Est | SAR | 113100 | APPROVED |  |  | 2025-12-08 | 11700 | 141 | Babic, Marian | -45858 | 141
105-93 | BUHAIYRAT 110/13.8kV S/S | 7125 | BUHAIYRAT 110/13.8kV S/S-Supply of Cable Tray and ladders with Accessories - Buhaiyrat | APPROVED | No | 2025-07-17 | Abas, Mohammed Fekry | 2025-08-05 | 2025-08-06 |  |  | 2.2.6 | 52896.48 | 6247 | 1 | STANDARD | Mid-East Cable Support Solutions | SAR | 52896.48 | APPROVED |  |  | 2025-09-04 | 0 | 29 | Badhman, Saeed | -45875 | 29
105-93 | BUHAIYRAT 110/13.8kV S/S | 7133 | BUHAIYRAT 110/13.8kV S/S-MV Cable Clamps Epoxy Coating 1 | APPROVED | No | 2025-07-17 | Abas, Mohammed Fekry | 2025-08-05 | 2025-08-06 |  |  | 2.2.9 | 26810 | 6833 | 1 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 26810 | APPROVED |  |  | 2025-08-26 | 0 | 20 | Kumar, Mr. Ranjan | -45875 | 20
105-93 | BUHAIYRAT 110/13.8kV S/S | 7134 | BUHAIYRAT 110/13.8kV S/S-MV Cable Clamps Epoxy Coating 2 | APPROVED | No | 2025-07-17 | Abas, Mohammed Fekry | 2025-08-05 | 2025-08-06 |  |  | 2.1.6.10 | 14595 | 6833 | 1 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 14595 | APPROVED |  |  | 2025-08-26 | 0 | 20 | Kumar, Mr. Ranjan | -45875 | 20
105-93 | BUHAIYRAT 110/13.8kV S/S | 7272 | BUHAIYRAT 110/13.8kV S/S-Diesel Rental Generators 200KVA & 30 KVA | REJECTED | No | 2025-08-04 | Ghith, Saad Gamal | 2025-08-04 | 2025-08-04 |  | 2025-08-05 |  | 5600 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45873 | -45873
105-93 | BUHAIYRAT 110/13.8kV S/S | 7295 | BUHAIYRAT 110/13.8kV S/S-Diesel Rental Generators 200KVA & 30 KVA - BHT | APPROVED | No | 2025-08-06 | Abas, Mohammed Fekry | 2025-08-10 | 2025-08-10 |  |  | 4.1.7 Please approve | 16100 | 4907 | 1 | STANDARD | Deyar United Advance Contracting Company | SAR | 16100 | APPROVED |  |  | 2025-08-26 | 0 | 16 | Badhman, Saeed | -45879 | 16
105-93 | BUHAIYRAT 110/13.8kV S/S | 7642 | Supply of Furnitures - BHT | RETURNED | No | 2025-09-04 | Akhtar, Farhan | 2025-11-12 | 2025-09-08 | 2025-11-12 |  | PR has no Budget | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45908 | -45908
105-93 | BUHAIYRAT 110/13.8kV S/S | 7671 | LV Control Cables Lot 3 - Buhaiyrat | RETURNED | No | 2025-09-08 | Badhman, Saeed | 2025-10-27 | 2025-09-13 | 2025-10-27 |  | Please provide the approved POCR | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45913 | -45913
105-93 | BUHAIYRAT 110/13.8kV S/S | 8034 | Grounding Conductor | RETURNED | No | 2025-10-22 |  |  | 2025-10-27 | 2026-01-11 |  | Not have Original PO in the Oracle system (manual PO) | 42050 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Mohammed Adel Fahmy | -45957 | -45957
105-93 | BUHAIYRAT 110/13.8kV S/S | 8091 | Bare Copper Strip | RETURNED | No | 2025-10-29 |  |  | 2025-11-06 | 2026-01-11 |  | Not have Original PO in the Oracle system (manual PO) | 5708 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Mohammed Adel Fahmy | -45967 | -45967
105-93 | BUHAIYRAT 110/13.8kV S/S | 8300 | LV Cables for Lighting - Wires | APPROVED | No | 2025-11-20 | Abas, Mohammed Fekry | 2025-11-25 | 2025-11-29 |  |  | 2.1.9.3 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45990 | -45990
105-93 | BUHAIYRAT 110/13.8kV S/S | 8671 | Supply and Re-filling fuel at Location | REJECTED | No | 2026-01-08 | Chaudhry, Shahid Bashir | 2026-01-08 |  |  | 2026-01-08 | Urgent | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
105-93 | BUHAIYRAT 110/13.8kV S/S | 8672 | Supply of Fuel (Diesel for Generator) | APPROVED | No | 2026-01-08 | Abas, Mohammed Fekry | 2026-01-19 | 2026-01-21 |  |  | Urgent!!! | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46043 | -46043
105-94 | CONSTRUCTION OF AL-MURJAN | 1683 | CONSTRUCTION OF AL-MURJAN-GIS EXTENSION | APPROVED | No | 2023-11-12 | Abas, Mohammed Fekry | 2023-11-14 | 2023-11-14 |  |  |  | 4700000 | 4744 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 4700000 | APPROVED |  |  | 2023-12-04 | 0 | 20 | Babic, Marian | -45244 | 20
105-94 | CONSTRUCTION OF AL-MURJAN | 1701 | CONSTRUCTION OF AL-MURJAN-13.8 KV SWITCHGEAR | APPROVED | No | 2023-11-13 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 8800000 | 4760 | 0 | STANDARD | ALFANAR CO | SAR | 8800000 | APPROVED |  |  | 2023-12-03 | 0 | 17 | Babic, Marian | -45246 | 17
105-94 | CONSTRUCTION OF AL-MURJAN | 1703 | CONSTRUCTION OF AL-MURJAN-SUPPLY OF 50/67 MVA 132/13.8 KV POWER TRANSFORMER | INCOMPLETE | No |  | Syed, Dastageer Pasha | 2024-12-10 |  |  |  |  | 53805750 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-94 | CONSTRUCTION OF AL-MURJAN | 1704 | CONSTRUCTION OF AL-MURJAN-SUPPLY OF 50/67 MVA 132/13.8 KV POWER TRANSFORMER | APPROVED | No | 2023-11-13 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 53805750 | 4757 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 17935250 | APPROVED |  |  | 2023-12-04 | 35870500 | 18 | Babic, Marian | -45246 | 18
105-94 | CONSTRUCTION OF AL-MURJAN | 1706 | CONSTRUCTION OF AL-MURJAN-132KV GIS | INCOMPLETE | No |  | Ammari, Omar Mohammed | 2023-11-13 |  |  |  |  | 2936000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-94 | CONSTRUCTION OF AL-MURJAN | 1709 | CONSTRUCTION OF AL-MURJAN-AC, DC DISTRIBUTION & LIGHTING PANELS | INCOMPLETE | No |  | Ammari, Omar Mohammed | 2023-11-13 |  |  |  |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-94 | CONSTRUCTION OF AL-MURJAN | 1710 | CONSTRUCTION OF AL-MURJAN-AC, DC DISTRIBUTION & LIGHTING PANELS | APPROVED | No | 2023-11-13 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 825000 | 5308 | 0 | STANDARD | ALFANAR CO | SAR | 825000 | APPROVED |  |  | 2024-04-04 | 0 | 140 | Mohammed, Faisal Ansari | -45246 | 140
105-94 | CONSTRUCTION OF AL-MURJAN | 1713 | CONSTRUCTION OF AL-MURJAN-132KV GIS | INCOMPLETE | No |  | Ammari, Omar Mohammed | 2023-11-14 |  |  |  |  | 2936000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-94 | CONSTRUCTION OF AL-MURJAN | 1715 | CONSTRUCTION OF AL-MURJAN-CYBER SECURITY | APPROVED | No | 2023-11-14 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 1475000 | 4759 | 0 | STANDARD | ALFANAR CO | SAR | 1475000 | APPROVED |  |  | 2023-12-03 | 0 | 17 | Babic, Marian | -45246 | 17
105-94 | CONSTRUCTION OF AL-MURJAN | 1716 | CONSTRUCTION OF AL-MURJAN-ENVIRONMENTAL STUDY (ESIA) | APPROVED | No | 2023-11-14 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 20000 | 4763 | 0 | STANDARD | Aran Aljazeera Enviromental Consultant | SAR | 20000 | APPROVED |  |  | 2023-12-03 | 0 | 17 | Babic, Marian | -45246 | 17
105-94 | CONSTRUCTION OF AL-MURJAN | 1718 | CONSTRUCTION OF AL-MURJAN-RMU | APPROVED | No | 2023-11-14 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 139000 | 5307 | 0 | STANDARD | ALFANAR CO | SAR | 139000 | APPROVED |  |  | 2024-04-04 | 0 | 140 | Mohammed, Faisal Ansari | -45246 | 140
105-94 | CONSTRUCTION OF AL-MURJAN | 1719 | CONSTRUCTION OF AL-MURJAN-SOIL INVESTIGATION | APPROVED | No | 2023-11-14 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 17910 | 4764 | 0 | STANDARD | International Agent Commercial Company(S) | SAR | 17910 | APPROVED |  |  | 2023-12-03 | 0 | 17 | Babic, Marian | -45246 | 17
105-94 | CONSTRUCTION OF AL-MURJAN | 1720 | CONSTRUCTION OF AL-MURJAN-STATION TRANSFORMER | APPROVED | No | 2023-11-14 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 225000 | 4758 | 0 | STANDARD | ALFANAR CO | SAR | 225000 | APPROVED |  |  | 2023-12-03 | 0 | 17 | Babic, Marian | -45246 | 17
105-94 | CONSTRUCTION OF AL-MURJAN | 1724 | CONSTRUCTION OF AL-MURJAN-PROTECTION CONTROL & SAS | APPROVED | No | 2023-11-14 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 8950000 | 4761 | 0 | STANDARD | ALFANAR CO | SAR | 8950000 | APPROVED |  |  | 2023-12-03 | 0 | 17 | Babic, Marian | -45246 | 17
105-94 | CONSTRUCTION OF AL-MURJAN | 1728 | CONSTRUCTION OF AL-MURJAN-DETAILED SURVEY/ROUTE TOPOGRAPHIC SURVEY | APPROVED | No | 2023-11-14 | Abas, Mohammed Fekry | 2023-11-14 | 2023-11-15 |  |  |  | 54500 | 4802 | 0 | STANDARD | Al Muhandis Nizar Al Kurdi Al Milli Engineering Consultants | SAR | 47500 | APPROVED |  |  | 2023-12-21 | 7000 | 36 | Babic, Marian | -45245 | 36
105-94 | CONSTRUCTION OF AL-MURJAN | 1728 | CONSTRUCTION OF AL-MURJAN-DETAILED SURVEY/ROUTE TOPOGRAPHIC SURVEY | APPROVED | No | 2023-11-14 | Abas, Mohammed Fekry | 2023-11-14 | 2023-11-15 |  |  |  | 54500 | 4802 | 1 | STANDARD | Al Muhandis Nizar Al Kurdi Al Milli Engineering Consultants | SAR | 25000 | APPROVED |  |  | 2024-01-10 | 29500 | 56 | Babic, Marian | -45245 | 56
105-94 | CONSTRUCTION OF AL-MURJAN | 1733 | CONSTRUCTION OF AL-MURJAN-TELECOM SYSTEM | APPROVED | No | 2023-11-14 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 5000000 | 4762 | 0 | STANDARD | ALFANAR CO | SAR | 5000000 | APPROVED |  |  | 2023-12-03 | 0 | 17 | Babic, Marian | -45246 | 17
105-94 | CONSTRUCTION OF AL-MURJAN | 1739 | CONSTRUCTION OF AL-MURJAN-132KV GIS | INCOMPLETE | No |  | Ammari, Omar Mohammed | 2023-11-14 |  |  |  |  | 2936000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-94 | CONSTRUCTION OF AL-MURJAN | 1750 | CONSTRUCTION OF AL-MURJAN-132KV GIS | INCOMPLETE | No |  | Ammari, Omar Mohammed | 2023-11-15 |  |  |  |  | 2936000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-94 | CONSTRUCTION OF AL-MURJAN | 1790 | CONSTRUCTION OF AL-MURJAN-120 kv oudoor surge arrestor | APPROVED | No | 2023-11-19 | Abas, Mohammed Fekry | 2023-11-22 | 2023-11-22 |  |  |  | 46249251.48 | 4798 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 62475.01 | APPROVED |  |  | 2023-12-14 | 46186776.47 | 22 | Kumar, Mr. Ranjan | -45252 | 22
105-94 | CONSTRUCTION OF AL-MURJAN | 1794 | CONSTRUCTION OF AL-MURJAN-(1). 1OO KVA GENERATOR. (2). 300 KVA GENERATOR. | APPROVED | No | 2023-11-20 | Abas, Mohammed Fekry | 2023-11-22 | 2023-11-22 |  |  |  | 250000 | 4772 | 0 | STANDARD | Mohammed A. AlFaddaghi & Partners | SAR | 250000 | APPROVED |  |  | 2023-12-06 | 0 | 14 | Badhman, Saeed | -45252 | 14
105-94 | CONSTRUCTION OF AL-MURJAN | 1799 | CONSTRUCTION OF AL-MURJAN-FIRE FIGHTING SYSTEM | APPROVED | No | 2023-11-21 | Abas, Mohammed Fekry | 2023-11-22 | 2023-11-22 |  |  |  | 5138805.72 | 4934 | 0 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 1777668 | APPROVED |  |  | 2024-01-10 | 3361137.72 | 49 | Babic, Marian | -45252 | 49
105-94 | CONSTRUCTION OF AL-MURJAN | 1800 | CONSTRUCTION OF AL-MURJAN-UGC | REJECTED | No | 2023-11-21 | Ammari, Omar Mohammed | 2023-11-21 |  |  | 2023-11-21 |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-94 | CONSTRUCTION OF AL-MURJAN | 1803 | CONSTRUCTION OF AL-MURJAN-13.8 KV NGR | APPROVED | No | 2023-11-21 | Abas, Mohammed Fekry | 2023-11-22 | 2023-11-23 |  |  |  | 525000 | 4799 | 0 | STANDARD | National Switchgears | USD | 63675 | APPROVED |  |  | 2023-12-14 | 461325 | 21 | Kumar, Mr. Ranjan | -45253 | 21
105-94 | CONSTRUCTION OF AL-MURJAN | 1851 | CONSTRUCTION OF AL-MURJAN-CIVIL WORKS | APPROVED | No | 2023-11-29 | Abas, Mohammed Fekry | 2023-11-30 | 2023-11-30 |  |  |  | 7900000 | 4780 | 0 | STANDARD | Al Sahda Contracting Est. | SAR | 7900000 | APPROVED |  |  | 2023-12-11 | 0 | 11 | Mohammed, Faisal Ansari | -45260 | 11
105-94 | CONSTRUCTION OF AL-MURJAN | 1864 | CONSTRUCTION OF AL-MURJAN-ODF | APPROVED | No | 2023-11-30 | Abas, Mohammed Fekry | 2023-12-25 | 2023-12-26 | 2023-12-14 |  | PR value is SAR 1. PR value must be equal to or greater than the PO value. please revise. | 15000 | 4926 | 0 | STANDARD | AMWAJ TELECOMMUNICATION MFG. CO. | SAR | 13680 | APPROVED |  |  | 2024-01-29 | 1320 | 34 | Mohammed, Faisal Ansari | -45286 | 34
105-94 | CONSTRUCTION OF AL-MURJAN | 1867 | CONSTRUCTION OF AL-MURJAN-LINK BOXES | REJECTED | No | 2023-11-30 | Abas, Mohammed Fekry | 2023-12-04 | 2023-12-04 |  | 2023-12-05 |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45264 | -45264
105-94 | CONSTRUCTION OF AL-MURJAN | 1874 | CONSTRUCTION OF AL-MURJAN-PRECAST | APPROVED | No | 2023-11-30 | Abas, Mohammed Fekry | 2023-12-04 | 2023-12-05 |  |  |  | 2000000 | 4788 | 0 | STANDARD | Kifah Precast Company | SAR | 1797939 | APPROVED |  |  | 2023-12-19 | 202061 | 14 | Mohammed, Faisal Ansari | -45265 | 14
105-94 | CONSTRUCTION OF AL-MURJAN | 1884 | CONSTRUCTION OF AL-MURJAN-OHTC-Overhead travelling crane | APPROVED | No | 2023-12-03 | Abas, Mohammed Fekry | 2023-12-04 | 2023-12-05 |  |  |  | 5138805.72 | 4800 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 138500 | APPROVED |  |  | 2023-12-19 | 5000305.72 | 14 | Kumar, Mr. Ranjan | -45265 | 14
105-94 | CONSTRUCTION OF AL-MURJAN | 1885 | CONSTRUCTION OF AL-MURJAN-JIB CRANES | APPROVED | No | 2023-12-03 | Abas, Mohammed Fekry | 2023-12-04 | 2023-12-05 |  |  |  | 5138805.72 | 4800 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 81500 | APPROVED |  |  | 2023-12-19 | 5057305.72 | 14 | Kumar, Mr. Ranjan | -45265 | 14
105-94 | CONSTRUCTION OF AL-MURJAN | 1904 | CONSTRUCTION OF AL-MURJAN-Security System | APPROVED | No | 2023-12-06 | Abas, Mohammed Fekry | 2023-12-11 | 2023-12-11 |  |  |  | 2460000 | 4987 | 0 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 782924 | APPROVED |  |  | 2024-01-25 | 1677076 | 45 | Babic, Marian | -45271 | 45
105-94 | CONSTRUCTION OF AL-MURJAN | 1904 | CONSTRUCTION OF AL-MURJAN-Security System | APPROVED | No | 2023-12-06 | Abas, Mohammed Fekry | 2023-12-11 | 2023-12-11 |  |  |  | 2460000 | 5396 | 0 | STANDARD | Equipment & Technical Services Co.(ETECHS) | SAR | 650000 | APPROVED |  |  | 2024-05-20 | 1810000 | 161 | Mohammed, Faisal Ansari | -45271 | 161
105-94 | CONSTRUCTION OF AL-MURJAN | 1915 | CONSTRUCTION OF AL-MURJAN-HV CABLE | APPROVED | No | 2023-12-07 | Abas, Mohammed Fekry | 2023-12-10 | 2023-12-11 |  |  |  | 200900 | 4914 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 167000 | APPROVED |  |  | 2024-01-07 | 33900 | 27 | Mohammed, Faisal Ansari | -45271 | 27
105-94 | CONSTRUCTION OF AL-MURJAN | 2000 | CONSTRUCTION OF AL-MURJAN-125 V /2500 AH Battery & charger | APPROVED | No | 2023-12-18 | Abas, Mohammed Fekry | 2023-12-20 | 2023-12-21 |  |  |  | 710000 | 5042 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 472500 | APPROVED |  |  | 2024-02-20 | 237500 | 61 | Mohammed, Faisal Ansari | -45281 | 61
105-94 | CONSTRUCTION OF AL-MURJAN | 2018 | CONSTRUCTION OF AL-MURJAN-MV cables | INCOMPLETE | No |  | Ammari, Omar Mohammed | 2023-12-20 |  |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-94 | CONSTRUCTION OF AL-MURJAN | 2033 | CONSTRUCTION OF AL-MURJAN-OFMR | APPROVED | No | 2023-12-25 | Abas, Mohammed Fekry | 2023-12-25 | 2023-12-26 |  |  |  | 20000 | 4926 | 0 | STANDARD | AMWAJ TELECOMMUNICATION MFG. CO. | SAR | 18600 | APPROVED |  |  | 2024-01-29 | 1400 | 34 | Mohammed, Faisal Ansari | -45286 | 34
105-94 | CONSTRUCTION OF AL-MURJAN | 2073 | CONSTRUCTION OF AL-MURJAN-site mobilizatuon works (additional) | APPROVED | No | 2024-01-01 | Abas, Mohammed Fekry | 2024-01-02 | 2024-01-04 |  |  |  | 124393 | 5187 | 0 | STANDARD | Construction Expertise Est. | SAR | 124393 | APPROVED |  |  | 2024-04-06 | 0 | 93 | Mohammed, Faisal Ansari | -45295 | 93
105-94 | CONSTRUCTION OF AL-MURJAN | 2152 | CONSTRUCTION OF AL-MURJAN-control cable | APPROVED | No | 2024-01-10 | Abas, Mohammed Fekry | 2024-01-14 | 2024-01-14 |  |  |  | 527900 | 5318 | 1 | STANDARD | Middle East Specialized Cables Mesc | SAR | 320403.64 | APPROVED |  |  | 2024-06-24 | 207496.36 | 162 | Mohammed, Faisal Ansari | -45305 | 162
105-94 | CONSTRUCTION OF AL-MURJAN | 2152 | CONSTRUCTION OF AL-MURJAN-control cable | APPROVED | No | 2024-01-10 | Abas, Mohammed Fekry | 2024-01-14 | 2024-01-14 |  |  |  | 786750 | 5318 | 0 | STANDARD | Middle East Specialized Cables Mesc | SAR | 530576.13 | APPROVED |  |  | 2024-04-18 | 256173.87 | 95 | Mohammed, Faisal Ansari | -45305 | 95
105-94 | CONSTRUCTION OF AL-MURJAN | 2160 | CONSTRUCTION OF AL-MURJAN-Grounding & Shielding system | APPROVED | No | 2024-01-14 | Abas, Mohammed Fekry | 2024-01-14 | 2024-01-14 |  |  |  | 604000 | 5168 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 131953.75 | APPROVED |  |  | 2024-04-03 | 472046.25 | 80 | Mohammed, Faisal Ansari | -45305 | 80
105-94 | CONSTRUCTION OF AL-MURJAN | 2365 | CONSTRUCTION OF AL-MURJAN-Supervision & consulting services | APPROVED | No | 2024-01-29 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 11849029.76 | 5243 | 0 | STANDARD | Bold Engineering Consulting Office | SAR | 42000 | APPROVED |  |  | 2024-03-25 | 11807029.76 | 50 | Alhadi, Khalid | -45326 | 50
105-94 | CONSTRUCTION OF AL-MURJAN | 2365 | CONSTRUCTION OF AL-MURJAN-Supervision & consulting services | APPROVED | No | 2024-01-29 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 11849029.76 | 5243 | 2 | STANDARD | Bold Engineering Consulting Office | SAR | 42000 | IN PROCESS |  |  |  | 11807029.76 | 728 | Alhadi, Khalid | -45326 | -45326
105-94 | CONSTRUCTION OF AL-MURJAN | 2366 | CONSTRUCTION OF AL-MURJAN-Soil , compaction , &asphalt testing Laboratory | APPROVED | No | 2024-01-29 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 2049213 | 5166 | 0 | STANDARD | URS Saudi Arabia | SAR | 135000 | APPROVED |  |  | 2024-03-27 | 1914213 | 52 | Alhadi, Khalid | -45326 | 52
105-94 | CONSTRUCTION OF AL-MURJAN | 2483 | CONSTRUCTION OF AL-MURJAN- RFQ for the Link Boxes to PTE | RETURNED | No | 2024-02-07 | Mohammed, Faisal Ansari | 2024-02-21 | 2024-02-10 | 2024-02-21 |  | Not Required. You may delete this PR for Transportation. | 16800 | 4914 | 1 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 15200 | APPROVED |  |  | 2024-03-03 | 1600 |  | Mohammed, Faisal Ansari | -45332 | 22
105-94 | CONSTRUCTION OF AL-MURJAN | 2507 | CONSTRUCTION OF AL-MURJAN-radar scanning | APPROVED | No | 2024-02-08 | Abas, Mohammed Fekry | 2024-02-11 | 2024-02-12 |  |  |  | 212750 | 5273 | 0 | STANDARD | International Agent Commercial Company(S) | SAR | 91000 | APPROVED |  |  | 2024-04-01 | 121750 | 49 | Babic, Marian | -45334 | 49
105-94 | CONSTRUCTION OF AL-MURJAN | 2644 | CONSTRUCTION OF AL-MURJAN-HAVC | APPROVED | No | 2024-02-21 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 1950000 | 5260 | 0 | STANDARD | Ramz Alataa Company for Trading | SAR | 1660000 | APPROVED |  |  | 2024-04-15 | 290000 | 49 | Mohammed, Faisal Ansari | -45348 | 49
105-94 | CONSTRUCTION OF AL-MURJAN | 2726 | CONSTRUCTION OF AL-MURJAN-Diesel Supplier | APPROVED | No | 2024-02-29 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 60284.67 | 5221 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 60230.08 | APPROVED |  |  | 2024-04-02 | 54.59 | 26 | Abuhammad, Samir | -45358 | 26
105-94 | CONSTRUCTION OF AL-MURJAN | 2747 | CONSTRUCTION OF AL-MURJAN-MV cable termination kits | APPROVED | No | 2024-03-04 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 751635.51 | 5441 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 129058 | APPROVED |  |  | 2024-05-23 | 622577.51 | 77 | Mohammed, Faisal Ansari | -45358 | 77
105-94 | CONSTRUCTION OF AL-MURJAN | 2818 | CONSTRUCTION OF AL-MURJAN-Grounding Conductors | APPROVED | No | 2024-03-13 | Abas, Mohammed Fekry | 2024-03-17 | 2024-03-19 |  |  |  | 333000 | 5233 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 332414.16 | APPROVED |  |  | 2024-03-28 | 585.84 | 9 | Mohammed, Faisal Ansari | -45370 | 9
105-94 | CONSTRUCTION OF AL-MURJAN | 2833 | CONSTRUCTION OF AL-MURJAN- Safety requirements for substation | APPROVED | No | 2024-03-17 | Abas, Mohammed Fekry | 2024-03-23 | 2024-03-24 |  |  |  | 60000 | 5518 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 35579 | APPROVED |  |  | 2024-05-26 | 24421 | 63 | Akhtar, Farhan | -45375 | 63
105-94 | CONSTRUCTION OF AL-MURJAN | 2834 | CONSTRUCTION OF AL-MURJAN-site mobilization | APPROVED | No | 2024-03-18 | Abas, Mohammed Fekry | 2024-03-28 | 2024-03-28 | 2024-03-24 |  | PR value should be 501500 and quantity should be 1. Please correct and submit. | 501500 | 5187 | 0 | STANDARD | Construction Expertise Est. | SAR | 501077 | APPROVED |  |  | 2024-04-06 | 423 | 9 | Mohammed, Faisal Ansari | -45379 | 9
105-94 | CONSTRUCTION OF AL-MURJAN | 2845 | CONSTRUCTION OF AL-MURJAN-MV CABLES | APPROVED | No | 2024-03-19 | Abas, Mohammed Fekry | 2024-03-23 | 2024-03-24 |  |  |  | 1152643.21 | 5314 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 1106494 | APPROVED |  |  | 2024-05-26 | 46149.21 | 63 | Mohammed, Faisal Ansari | -45375 | 63
105-94 | CONSTRUCTION OF AL-MURJAN | 2953 | CONSTRUCTION OF AL-MURJAN-Y/G CONDUCTORS | APPROVED | No | 2024-03-31 | Abas, Mohammed Fekry | 2024-04-01 | 2024-04-02 |  |  |  | 139632.09 | 5418 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 139465.23 | APPROVED |  |  | 2024-05-14 | 166.86 | 42 | Mohammed, Faisal Ansari | -45384 | 42
105-94 | CONSTRUCTION OF AL-MURJAN | 3230 | CONSTRUCTION OF AL-MURJAN-Additional PR for MV cable | APPROVED | No | 2024-04-30 | Abas, Mohammed Fekry | 2024-05-01 | 2024-05-01 |  |  |  | 114168.58 | 5314 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 107760 | APPROVED |  |  | 2024-05-26 | 6408.58 | 25 | Mohammed, Faisal Ansari | -45413 | 25
105-94 | CONSTRUCTION OF AL-MURJAN | 3336 | CONSTRUCTION OF AL-MURJAN-Engineering & Design | APPROVED | No | 2024-05-07 | Abas, Mohammed Fekry | 2024-05-09 | 2024-05-12 |  |  |  | 820000 | 5567 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 820000 | APPROVED |  |  | 2024-05-25 | 0 | 13 | Babic, Marian | -45424 | 13
105-94 | CONSTRUCTION OF AL-MURJAN | 3346 | CONSTRUCTION OF AL-MURJAN-civil subcontractor for UGC portion(civil materials and section activity) | APPROVED | No | 2024-05-08 | Abas, Mohammed Fekry | 2024-05-09 | 2024-05-12 |  |  |  | 2600000 | 5536 | 0 | STANDARD | RAWIYAH EAST GENERAL CONTRACTING | SAR | 2375000 | APPROVED |  |  | 2024-11-17 | 225000 | 189 | Tananeh, Khalid Jamal | -45424 | 189
105-94 | CONSTRUCTION OF AL-MURJAN | 3347 | CONSTRUCTION OF AL-MURJAN-civil subcontractor for UGC portion(civil materials and section activity) | APPROVED | No | 2024-05-08 | Abas, Mohammed Fekry | 2024-05-09 | 2024-05-12 |  |  |  | 2600000 | 5537 | 0 | STANDARD | Digital Cables Contracting Co | SAR | 2375000 | APPROVED |  |  | 2024-11-17 | 225000 | 189 | Tananeh, Khalid Jamal | -45424 | 189
105-94 | CONSTRUCTION OF AL-MURJAN | 3475 | CONSTRUCTION OF AL-MURJAN-SVL/NLR | APPROVED | No | 2024-05-22 | Abas, Mohammed Fekry | 2024-05-23 | 2024-05-26 |  |  |  | 3408805.2 | 5671 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 11760 | APPROVED |  |  | 2024-06-11 | 3397045.2 | 16 | Mohammed, Faisal Ansari | -45438 | 16
105-94 | CONSTRUCTION OF AL-MURJAN | 3475 | CONSTRUCTION OF AL-MURJAN-SVL/NLR | APPROVED | No | 2024-05-22 | Abas, Mohammed Fekry | 2024-05-23 | 2024-05-26 |  |  |  | 3408805.2 | 5671 | 1 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 11760 | REQUIRES REAPPROVAL |  |  |  | 3397045.2 | 616 | Mohammed, Faisal Ansari | -45438 | -45438
105-94 | CONSTRUCTION OF AL-MURJAN | 3637 | CONSTRUCTION OF AL-MURJAN-cable tray | REJECTED | No | 2024-06-10 | Ammari, Omar Mohammed | 2024-06-10 |  |  | 2024-06-10 |  | 3408805.2 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-94 | CONSTRUCTION OF AL-MURJAN | 3638 | CONSTRUCTION OF AL-MURJAN-cable support | REJECTED | No | 2024-06-10 | Ammari, Omar Mohammed | 2024-06-10 |  |  | 2024-06-10 |  | 3270275.76 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-94 | CONSTRUCTION OF AL-MURJAN | 3945 | CONSTRUCTION OF AL-MURJAN-Revised PR to allign the value of change order # 5314-1 | APPROVED | No | 2024-07-17 | Abas, Mohammed Fekry | 2024-07-22 | 2024-07-23 |  |  |  | 170794 | 5314 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 170793 | APPROVED |  |  | 2024-09-12 | 1 | 51 | Mohammed, Faisal Ansari | -45496 | 51
105-94 | CONSTRUCTION OF AL-MURJAN | 3946 | CONSTRUCTION OF AL-MURJAN-transformer | REJECTED | No | 2024-07-17 | Ammari, Omar Mohammed | 2024-07-17 |  |  | 2024-07-17 |  | 1000000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-94 | CONSTRUCTION OF AL-MURJAN | 4078 | CONSTRUCTION OF AL-MURJAN-HV & FO Cables pulling | APPROVED | No | 2024-08-01 | Abas, Mohammed Fekry | 2024-08-05 | 2024-08-05 |  |  |  | 862500 | 6135 | 0 | STANDARD | Digital Cables Contracting Co | SAR | 750000 | APPROVED |  |  | 2024-09-17 | 112500 | 43 | Alhadi, Khalid | -45509 | 43
105-94 | CONSTRUCTION OF AL-MURJAN | 4160 | CONSTRUCTION OF AL-MURJAN-Temporary storage for HV UGC & Accessories at Murjan site office. | APPROVED | No | 2024-08-15 | Abas, Mohammed Fekry | 2024-08-17 | 2024-08-17 |  |  |  | 100000 | 6021 | 0 | STANDARD | Al Arab Modern Contracting Est | SAR | 68383 | APPROVED |  |  | 2024-08-27 | 31617 | 10 | Kumar, Mr. Ranjan | -45521 | 10
105-94 | CONSTRUCTION OF AL-MURJAN | 4571 | CONSTRUCTION OF AL-MURJAN-TPI for FAT of additional Bay of 132 KV GIS | REJECTED | No | 2024-10-02 | Ammari, Omar Mohammed | 2024-10-02 |  |  | 2024-10-02 |  | 8000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-94 | CONSTRUCTION OF AL-MURJAN | 4572 | CONSTRUCTION OF AL-MURJAN-TPI for FAT of additional 132kV GIS Bay | APPROVED | No | 2024-10-02 | Abas, Mohammed Fekry | 2024-10-06 | 2024-10-07 |  |  |  | 4000 | 6315 | 0 | STANDARD | Germanischer Lloyd Industrial Services Saudi Arabian Co Ltd | SAR | 3400 | APPROVED |  |  | 2024-10-21 | 600 | 14 | Akhtar, Farhan | -45572 | 14
105-94 | CONSTRUCTION OF AL-MURJAN | 4622 | CONSTRUCTION OF AL-MURJAN-Subcontract Agreement for Electrical Installation Services | APPROVED | No | 2024-10-08 | Abas, Mohammed Fekry | 2024-10-15 | 2024-10-15 |  |  |  | 2275600 | 6348 | 0 | STANDARD | City Crowns Energy | SAR | 2275600 | APPROVED |  |  | 2024-10-31 | 0 | 16 | Mohammed, Faisal Ansari | -45580 | 16
105-94 | CONSTRUCTION OF AL-MURJAN | 4691 | CONSTRUCTION OF AL-MURJAN-Precast Sampling Lab Hiring | REJECTED | No | 2024-10-15 | Yasmin, Ahmed Elsayed Mohamed | 2024-10-20 | 2024-10-15 |  | 2024-10-20 |  | 24960 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45580 | -45580
105-94 | CONSTRUCTION OF AL-MURJAN | 4711 | CONSTRUCTION OF AL-MURJAN-Lightning Mast and Lighting Poles to Al Babtain | APPROVED | No | 2024-10-17 | Abas, Mohammed Fekry | 2024-10-20 | 2024-10-20 |  |  |  | 106300 | 6385 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 94700 | APPROVED |  |  | 2024-11-03 | 11600 | 14 | Mohammed, Faisal Ansari | -45585 | 14
105-94 | CONSTRUCTION OF AL-MURJAN | 4711 | CONSTRUCTION OF AL-MURJAN-Lightning Mast and Lighting Poles to Al Babtain | APPROVED | No | 2024-10-17 | Abas, Mohammed Fekry | 2024-10-20 | 2024-10-20 |  |  |  | 106300 | 6385 | 1 | STANDARD | Al-Babtain Power & Telecom | SAR | 81700 | APPROVED |  |  | 2024-12-25 | 24600 | 66 | Mohammed, Faisal Ansari | -45585 | 66
105-94 | CONSTRUCTION OF AL-MURJAN | 4738 | CONSTRUCTION OF AL-MURJAN-Supplu of UGC Safety Material | REJECTED | No | 2024-10-20 | Yasmin, Ahmed Elsayed Mohamed | 2024-10-24 | 2024-10-20 |  | 2024-10-24 |  | 302000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45585 | -45585
105-94 | CONSTRUCTION OF AL-MURJAN | 4739 | CONSTRUCTION OF AL-MURJAN-UGC-Concrete Mix Material | APPROVED | No | 2024-10-20 | Abas, Mohammed Fekry | 2024-11-10 | 2024-11-10 | 2024-11-03 |  | till date We have not received any DATA regarding this purchase order. | 120000 | 6558 | 0 | STANDARD | AlFALWA Co LTD | SAR | 105300 | APPROVED |  |  | 2024-12-15 | 14700 | 35 | Hegazy, Ayman | -45606 | 35
105-94 | CONSTRUCTION OF AL-MURJAN | 4744 | CONSTRUCTION OF AL-MURJAN-Thrust Boring Horizontal Directional Drilling SC Hiring | APPROVED | No | 2024-10-20 | Abas, Mohammed Fekry | 2024-10-23 | 2024-10-23 |  |  |  | 200000 | 6589 | 0 | STANDARD | Digital Cables Contracting Co | SAR | 135000 | APPROVED |  |  | 2024-12-26 | 65000 | 64 | Hegazy, Ayman | -45588 | 64
105-94 | CONSTRUCTION OF AL-MURJAN | 4752 | CONSTRUCTION OF AL-MURJAN-FAT for the Link Boxes | APPROVED | No | 2024-10-21 | Abas, Mohammed Fekry | 2024-10-27 | 2024-10-27 |  |  |  | 2000 | 6401 | 0 | STANDARD | Germanischer Lloyd Industrial Services Saudi Arabian Co Ltd | SAR | 1700 | APPROVED |  |  | 2024-11-03 | 300 | 7 | Akhtar, Farhan | -45592 | 7
105-94 | CONSTRUCTION OF AL-MURJAN | 4768 | CONSTRUCTION OF AL-MURJAN-civil subcontractor for UGC portion(civil section activity) | APPROVED | No | 2024-10-22 | Abas, Mohammed Fekry | 2024-10-27 | 2024-10-27 |  |  |  | 3802061 | 5514 | 0 | STANDARD | NSCON NEU CONTRACTING | SAR | 3040000 | APPROVED |  |  | 2024-11-19 | 762061 | 23 | Tananeh, Khalid Jamal | -45592 | 23
105-94 | CONSTRUCTION OF AL-MURJAN | 4768 | CONSTRUCTION OF AL-MURJAN-civil subcontractor for UGC portion(civil section activity) | APPROVED | No | 2024-10-22 | Abas, Mohammed Fekry | 2024-10-27 | 2024-10-27 |  |  |  | 3802061 | 5514 | 1 | STANDARD | NSCON NEU CONTRACTING | SAR | 3040000 | IN PROCESS |  |  |  | 762061 | 462 | Tananeh, Khalid Jamal | -45592 | -45592
105-94 | CONSTRUCTION OF AL-MURJAN | 4769 | CONSTRUCTION OF AL-MURJAN-3rd Party Lab Inspector for Precast Trial Mix Test | APPROVED | No | 2024-10-22 | Abas, Mohammed Fekry | 2024-10-27 | 2024-10-27 |  |  |  | 24960 | 6400 | 0 | STANDARD | Al Muhandis Nizar Al Kurdi Al Milli Engineering Consultants | SAR | 24960 | APPROVED |  |  | 2024-11-03 | 0 | 7 | Tananeh, Khalid Jamal | -45592 | 7
105-94 | CONSTRUCTION OF AL-MURJAN | 4770 | CONSTRUCTION OF AL-MURJAN-Cable raceway with the required hardware and fitting-1 | APPROVED | No | 2024-10-22 | Abas, Mohammed Fekry | 2024-10-27 | 2024-10-27 |  |  |  | 249553 | 6325 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 215158.53 | APPROVED |  |  | 2024-11-19 | 34394.47 | 23 | Mohammed, Faisal Ansari | -45592 | 23
105-94 | CONSTRUCTION OF AL-MURJAN | 4771 | CONSTRUCTION OF AL-MURJAN-Cable raceway with the required hardware and fitting-2 | APPROVED | No | 2024-10-22 | Abas, Mohammed Fekry | 2024-10-27 | 2024-10-27 |  |  |  | 169807.4 | 6325 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 143819.93 | APPROVED |  |  | 2024-11-19 | 25987.47 | 23 | Mohammed, Faisal Ansari | -45592 | 23
105-94 | CONSTRUCTION OF AL-MURJAN | 4772 | CONSTRUCTION OF AL-MURJAN-Supply of UGC Safety Material | APPROVED | No | 2024-10-22 | Abas, Mohammed Fekry | 2024-10-27 | 2024-10-27 |  |  |  | 460745 | 5601 | 0 | STANDARD | Construction Expertise Est. | SAR | 302000 | APPROVED |  |  | 2024-11-05 | 158745 | 9 | Akhtar, Farhan | -45592 | 9
105-94 | CONSTRUCTION OF AL-MURJAN | 4806 | CONSTRUCTION OF AL-MURJAN-UGC Scope Safety Material_Lot-2 | APPROVED | No | 2024-10-28 | Abas, Mohammed Fekry | 2024-11-03 | 2024-11-03 |  |  |  | 233850 | 6494 | 0 | STANDARD | RAMOZ ALMASA Contracting Company | SAR | 223357.5 | APPROVED |  |  | 2024-12-24 | 10492.5 | 51 | Akhtar, Farhan | -45599 | 51
105-94 | CONSTRUCTION OF AL-MURJAN | 4810 | CONSTRUCTION OF AL-MURJAN-Bare Copper-Grounding Matrial Change order | APPROVED | No | 2024-10-30 | Abas, Mohammed Fekry | 2024-11-03 | 2024-11-03 |  |  |  | 55000 | 5233 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 54666.8 | APPROVED |  |  | 2024-11-12 | 333.2 | 9 | Mohammed, Faisal Ansari | -45599 | 9
105-94 | CONSTRUCTION OF AL-MURJAN | 4811 | CONSTRUCTION OF AL-MURJAN-Y/G Cables-Grounding Matrial Change order | APPROVED | No | 2024-10-30 | Abas, Mohammed Fekry | 2024-11-03 | 2024-11-03 |  |  |  | 20200 | 5418 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 20138.77 | APPROVED |  |  | 2024-11-12 | 61.23 | 9 | Mohammed, Faisal Ansari | -45599 | 9
105-94 | CONSTRUCTION OF AL-MURJAN | 4816 | CONSTRUCTION OF AL-MURJAN-LV cables | APPROVED | No | 2024-10-31 | Abas, Mohammed Fekry | 2024-11-10 | 2024-11-10 |  |  |  | 1004736.62 | 5771 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 1004734 | APPROVED |  |  | 2024-11-17 | 2.62 | 7 | Mohammed, Faisal Ansari | -45606 | 7
105-94 | CONSTRUCTION OF AL-MURJAN | 4842 | CONSTRUCTION OF AL-MURJAN-Installation of concrete and sand duct bank (450 LM)_UGC Scope | RETURNED | No | 2024-11-05 | Tananeh, Khalid Jamal | 2025-04-20 | 2024-11-10 | 2025-04-20 |  | as per email Wednesday, March 19, 2025 11:40 AM sent to project manager | 292500 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45606 | -45606
105-94 | CONSTRUCTION OF AL-MURJAN | 4843 | CONSTRUCTION OF AL-MURJAN-Manual Excavation work for 6 LM-UGC route | RETURNED | No | 2024-11-05 | Tananeh, Khalid Jamal | 2025-04-20 | 2024-11-10 | 2025-04-20 |  | as per email Wednesday, March 19, 2025 11:40 AM sent to project manager | 35400 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45606 | -45606
105-94 | CONSTRUCTION OF AL-MURJAN | 4844 | CONSTRUCTION OF AL-MURJAN-Indoor & Outdoor Power Receptacles | APPROVED | No | 2024-11-05 | Abas, Mohammed Fekry | 2024-11-13 | 2024-11-13 |  |  |  | 108648.48 | 6489 | 0 | STANDARD | Power House Company | SAR | 104928.26 | APPROVED |  |  | 2024-11-20 | 3720.22 | 7 | Babic, Marian | -45609 | 7
105-94 | CONSTRUCTION OF AL-MURJAN | 4845 | CONSTRUCTION OF AL-MURJAN-Indoor & Outdoor Lighting Receptacles | APPROVED | No | 2024-11-06 | Abas, Mohammed Fekry | 2024-11-13 | 2024-11-13 |  |  |  | 74000 | 6490 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 74000 | APPROVED |  |  | 2024-11-19 | 0 | 6 | Babic, Marian | -45609 | 6
105-94 | CONSTRUCTION OF AL-MURJAN | 4877 | CONSTRUCTION OF AL-MURJAN-Indoor & Outdoor Lighting Receiptacles- Missing Items | APPROVED | No | 2024-11-10 | Abas, Mohammed Fekry | 2024-11-13 | 2024-11-13 |  |  |  | 1000 | 6490 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 954 | APPROVED |  |  | 2024-11-19 | 46 | 6 | Babic, Marian | -45609 | 6
105-94 | CONSTRUCTION OF AL-MURJAN | 4917 | CONSTRUCTION OF AL-MURJAN-UGC-Supply and install asphalt with required material | APPROVED | No | 2024-11-13 | Abas, Mohammed Fekry | 2025-01-14 | 2025-01-14 | 2024-12-10 |  | due to a lack of response and collaboration concerning our request for the review of contracts and quotes | 1589300 | 6741 | 0 | STANDARD | AL-Fayd AL Jazeera Contracting Company | SAR | 1589300 | APPROVED |  |  | 2025-02-11 | 0 | 28 | Hegazy, Ayman | -45671 | 28
105-94 | CONSTRUCTION OF AL-MURJAN | 4925 | CONSTRUCTION OF AL-MURJAN-UGC-Supply of cable sealing ends and joints | APPROVED | No | 2024-11-13 | Abas, Mohammed Fekry | 2024-11-17 | 2024-11-17 |  |  |  | 806550 | 6520 | 0 | STANDARD | PFISTERER Switzerland AG | EUR | 806548.97 | APPROVED |  |  | 2024-11-28 | 1.03 | 11 | Mohammed, Faisal Ansari | -45613 | 11
105-94 | CONSTRUCTION OF AL-MURJAN | 4928 | CONSTRUCTION OF AL-MURJAN-UGC-Installation of cable sealing ends and joints | APPROVED | No | 2024-11-13 | Abas, Mohammed Fekry | 2024-11-17 | 2024-11-17 |  |  |  | 113500 | 6520 | 0 | STANDARD | PFISTERER Switzerland AG | EUR | 113488 | APPROVED |  |  | 2024-11-28 | 12 | 11 | Mohammed, Faisal Ansari | -45613 | 11
105-94 | CONSTRUCTION OF AL-MURJAN | 4945 | CONSTRUCTION OF AL-MURJAN-UGC-supply of NMFOC- non metallic fiber obtics | APPROVED | No | 2024-11-14 | Abas, Mohammed Fekry | 2024-11-20 | 2024-11-21 |  |  |  | 111538.5 | 6529 | 0 | STANDARD | MIDDLE EAST FIBER CABLE MANUFACTURING CO. | SAR | 110310 | APPROVED |  |  | 2024-11-28 | 1228.5 | 7 | Mohammed, Faisal Ansari | -45617 | 7
105-94 | CONSTRUCTION OF AL-MURJAN | 4954 | CONSTRUCTION OF AL-MURJAN-Supply of concrete tiles R/G 20*40*8 cm | APPROVED | No | 2024-11-14 | Abas, Mohammed Fekry | 2024-11-20 | 2024-11-21 |  |  |  | 507400 | 6676 | 0 | STANDARD | Constriction Company Limited ( AL NASHAA LTD) | SAR | 507400 | APPROVED |  |  | 2025-01-07 | 0 | 47 | Tananeh, Khalid Jamal | -45617 | 47
105-94 | CONSTRUCTION OF AL-MURJAN | 4955 | CONSTRUCTION OF AL-MURJAN-Supply of PVC pipes 6&8 inch | APPROVED | No | 2024-11-14 | Abas, Mohammed Fekry | 2024-11-20 | 2024-11-21 |  |  |  | 101320 | 5534 | 0 | STANDARD | National Marketing Est. Co. Ltd.(S) | SAR | 101320 | APPROVED |  |  | 2024-11-28 | 0 | 7 | Tananeh, Khalid Jamal | -45617 | 7
105-94 | CONSTRUCTION OF AL-MURJAN | 4956 | CONSTRUCTION OF AL-MURJAN-supply of steel wire mesh/wire protection | APPROVED | No | 2024-11-14 | Abas, Mohammed Fekry | 2024-11-20 | 2024-11-21 |  |  |  | 146002.5 | 6562 | 0 | STANDARD | Modern Factory For Steel Industries Company | SAR | 146000 | APPROVED |  |  | 2024-12-08 | 2.5 | 17 | Tananeh, Khalid Jamal | -45617 | 17
105-94 | CONSTRUCTION OF AL-MURJAN | 4957 | CONSTRUCTION OF AL-MURJAN-Supply of precast linkbox for FOC handhole | APPROVED | No | 2024-11-14 | Abas, Mohammed Fekry | 2024-11-20 | 2024-11-21 |  |  |  | 373800 | 6563 | 0 | STANDARD | Product Art Est | SAR | 373800 | APPROVED |  |  | 2024-12-08 | 0 | 17 | Tananeh, Khalid Jamal | -45617 | 17
105-94 | CONSTRUCTION OF AL-MURJAN | 4975 | CONSTRUCTION OF AL-MURJAN-SS-testing and commissioing services | APPROVED | No | 2024-11-17 | Abas, Mohammed Fekry | 2024-11-20 | 2024-11-21 |  |  |  | 1903300 | 6495 | 0 | STANDARD | Al Fanar Technical Services | SAR | 1903295 | APPROVED |  |  | 2025-02-17 | 5 | 88 | Mohammed, Faisal Ansari | -45617 | 88
105-94 | CONSTRUCTION OF AL-MURJAN | 4985 | CONSTRUCTION OF AL-MURJAN-Supply of UGC-HV Cables ( Due to completed PO#8289) | APPROVED | No | 2024-11-18 | Abas, Mohammed Fekry | 2024-11-20 | 2024-11-21 |  |  |  | 34048351.6 | 6538 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 34048351.6 | APPROVED |  |  | 2024-11-28 | 0 | 7 | Babic, Marian | -45617 | 7
105-94 | CONSTRUCTION OF AL-MURJAN | 5059 | CONSTRUCTION OF AL-MURJAN-Split core CT (for replacing PO#4838 due to cancelled PR#1934) | APPROVED | No | 2024-11-27 | Abas, Mohammed Fekry | 2024-12-02 | 2024-12-03 |  |  |  | 233700 | 4838 | 0 | STANDARD | Power Trading T&D | EUR | 233700 | APPROVED |  |  | 2024-12-15 | 0 | 12 | Mohammed, Faisal Ansari | -45629 | 12
105-94 | CONSTRUCTION OF AL-MURJAN | 5063 | CONSTRUCTION OF AL-MURJAN-UGC-HV cable supports | APPROVED | No | 2024-11-27 | Abas, Mohammed Fekry | 2024-12-02 | 2024-12-03 |  |  |  | 36435 | 6564 | 0 | STANDARD | ABDULLAH M. AL-SHAHRANI FACTORY | SAR | 27750 | APPROVED |  |  | 2024-12-12 | 8685 | 9 | Mohammed, Faisal Ansari | -45629 | 9
105-94 | CONSTRUCTION OF AL-MURJAN | 5063 | CONSTRUCTION OF AL-MURJAN-UGC-HV cable supports | APPROVED | No | 2024-11-27 | Abas, Mohammed Fekry | 2024-12-02 | 2024-12-03 |  |  |  | 36435 | 6564 | 1 | STANDARD | ABDULLAH M. AL-SHAHRANI FACTORY | SAR | 23384 | APPROVED |  |  | 2025-11-19 | 13051 | 351 | Mohammed, Faisal Ansari | -45629 | 351
105-94 | CONSTRUCTION OF AL-MURJAN | 5064 | CONSTRUCTION OF AL-MURJAN-UGC Warnning Tape Red and green (Due to PO#7875) | APPROVED | No | 2024-11-27 | Abas, Mohammed Fekry | 2024-12-02 | 2024-12-03 |  |  |  | 37500 | 6605 | 0 | STANDARD | Mas Adhesive Tape Manufacturer Company | SAR | 37500 | APPROVED |  |  | 2024-12-16 | 0 | 13 | Tananeh, Khalid Jamal | -45629 | 13
105-94 | CONSTRUCTION OF AL-MURJAN | 5118 | CONSTRUCTION OF AL-MURJAN-UGC-Supply of PVC Pipes Bell Ends and PVC Pipe Base Spacer | APPROVED | No | 2024-12-03 | Abas, Mohammed Fekry | 2024-12-08 | 2024-12-09 |  |  |  | 44184.22 | 6613 | 0 | STANDARD | National Marketing Est. Co. Ltd.(S) | SAR | 44182.83 | APPROVED |  |  | 2024-12-22 | 1.39 | 13 | Tananeh, Khalid Jamal | -45635 | 13
105-94 | CONSTRUCTION OF AL-MURJAN | 5162 | CONSTRUCTION OF AL-MURJAN-3rd Party Inspector hiring for AMI&remaining Protection Panels(DNV) | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-12 |  |  |  | 5100 | 6683 | 0 | STANDARD | Germanischer Lloyd Industrial Services Saudi Arabian Co Ltd | SAR | 5100 | APPROVED |  |  | 2025-01-28 | 0 | 47 | Akhtar, Farhan | -45638 | 47
105-94 | CONSTRUCTION OF AL-MURJAN | 5189 | CONSTRUCTION OF AL-MURJAN-Power Transformer Transportation, Loading-Transport-offloading | APPROVED | No | 2024-12-08 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-12 |  |  |  | 125000 | 6649 | 0 | STANDARD | MOHAMMED HAMAD AL-AHMADE FOR TRADING AND CONSTRACTION | SAR | 125000 | APPROVED |  |  | 2024-12-26 | 0 | 14 | Alhadi, Khalid | -45638 | 14
105-94 | CONSTRUCTION OF AL-MURJAN | 5204 | CONSTRUCTION OF AL-MURJAN-UGC-Supply of corrugated Pipes due to PO#7876 | APPROVED | No | 2024-12-10 | Abas, Mohammed Fekry | 2024-12-11 | 2024-12-12 |  |  |  | 236250 | 6660 | 0 | STANDARD | National Marketing Est. Co. Ltd.(S) | SAR | 236250 | APPROVED |  |  | 2024-12-26 | 0 | 14 | Tananeh, Khalid Jamal | -45638 | 14
105-94 | CONSTRUCTION OF AL-MURJAN | 5220 | CONSTRUCTION OF AL-MURJAN-SS Precast Sealant work (Material supply & Installation) 3500M | APPROVED | No | 2024-12-11 | Abas, Mohammed Fekry | 2024-12-17 | 2024-12-18 |  |  |  | 112000 | 6677 | 0 | STANDARD | ATTON ANSHAIYA For General Contracting Establishment | SAR | 87500 | APPROVED |  |  | 2025-03-23 | 24500 | 95 | Tananeh, Khalid Jamal | -45644 | 95
105-94 | CONSTRUCTION OF AL-MURJAN | 5261 | CONSTRUCTION OF AL-MURJAN-to amend PO#6401 ( ITP for Link Boxes)_ 4 hours OT | APPROVED | No | 2024-12-23 | Abas, Mohammed Fekry | 2025-03-20 | 2025-03-20 |  |  | Increased to include Hotel and Air-ticket Fees | 2930.8 | 6401 | 1 | STANDARD | Germanischer Lloyd Industrial Services Saudi Arabian Co Ltd | SAR | 2930.8 | APPROVED |  |  | 2025-04-28 | 0 | 39 | Akhtar, Farhan | -45736 | 39
105-94 | CONSTRUCTION OF AL-MURJAN | 5262 | CONSTRUCTION OF AL-MURJAN-to amend DNV-TPI PO due to PR#5162 for AMI&remaining Protection panels FAT PO ( 4hours OT) | APPROVED | No | 2024-12-23 | Abas, Mohammed Fekry | 2025-01-06 | 2025-01-06 | 2024-12-30 |  | Please revise the amount beacuse total OT shall be 8 hours (Total Amount 1275x2 = 2550) | 2550 | 6683 | 0 | STANDARD | Germanischer Lloyd Industrial Services Saudi Arabian Co Ltd | SAR | 2550 | APPROVED |  |  | 2025-01-28 | 0 | 22 | Akhtar, Farhan | -45663 | 22
105-94 | CONSTRUCTION OF AL-MURJAN | 5269 | CONSTRUCTION OF AL-MURJAN-IT services ( Annual router and intrenet services) for site usage | APPROVED | No | 2024-12-24 | Abas, Mohammed Fekry | 2024-12-30 | 2024-12-30 |  |  |  | 12000 | 6721 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 9000 | APPROVED |  |  | 2025-01-28 | 3000 | 29 | Akhtar, Farhan | -45656 | 29
105-94 | CONSTRUCTION OF AL-MURJAN | 5338 | CONSTRUCTION OF AL-MURJAN-Change order ( Quantaties Modification) for PO#6494_UGC Saety Material linked W PR#4806 | APPROVED | No | 2025-01-02 | Abas, Mohammed Fekry | 2025-01-06 | 2025-01-06 |  |  |  | 246020 | 6494 | 3 | STANDARD | RAMOZ ALMASA Contracting Company | SAR | 232500 | APPROVED |  |  | 2025-01-15 | 13520 | 9 | Akhtar, Farhan | -45663 | 9
105-94 | CONSTRUCTION OF AL-MURJAN | 5393 | CONSTRUCTION OF AL-MURJAN-Supply of Drainage pumps and accessories (Excluding Aux TR pump) | REJECTED | No | 2025-01-13 | Yasmin, Ahmed Elsayed Mohamed | 2025-01-19 | 2025-01-19 | 2025-01-19 | 2025-01-20 | Please change the quantity and the prices as per the latest PO value. | 87400 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45676 | -45676
105-94 | CONSTRUCTION OF AL-MURJAN | 5394 | CONSTRUCTION OF AL-MURJAN-Supply of ACSR/ AW "CONDOR" Conductor | APPROVED | No | 2025-01-13 | Abas, Mohammed Fekry | 2025-01-16 | 2025-01-19 |  |  |  | 3300 | 6743 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 3300 | APPROVED |  |  | 2025-01-20 | 0 | 1 | Mohammed, Faisal Ansari | -45676 | 1
105-94 | CONSTRUCTION OF AL-MURJAN | 5397 | CONSTRUCTION OF AL-MURJAN-to Amend TPI For AMI and prot panels PO (Increased accomendation) | APPROVED | No | 2025-01-13 | Abas, Mohammed Fekry | 2025-01-14 | 2025-01-16 |  |  |  | 426.1 | 6683 | 0 | STANDARD | Germanischer Lloyd Industrial Services Saudi Arabian Co Ltd | SAR | 426.1 | APPROVED |  |  | 2025-01-28 | 0 | 12 | Akhtar, Farhan | -45673 | 12
105-94 | CONSTRUCTION OF AL-MURJAN | 5467 | CONSTRUCTION OF AL-MURJAN-Supply of Drainage pumpsand accessories (Replacment for PR#5393) | APPROVED | No | 2025-01-20 | Abas, Mohammed Fekry | 2025-01-23 | 2025-01-23 |  |  |  | 112200 | 5806 | 0 | STANDARD | First Western Pumps | SAR | 112200 | APPROVED |  |  | 2025-01-28 | 0 | 5 | Mohammed, Faisal Ansari | -45680 | 5
105-94 | CONSTRUCTION OF AL-MURJAN | 5475 | CONSTRUCTION OF AL-MURJAN-Manufacturing, Fabrication, Supply and Installation of Steel Decorative Fence Gate | APPROVED | No | 2025-01-20 | Abas, Mohammed Fekry | 2025-01-23 | 2025-01-23 |  |  |  | 544790 | 6866 | 0 | STANDARD | Fursan Construction Industry Factory Industry Factory | SAR | 544790 | APPROVED |  |  | 2025-03-03 | 0 | 39 | Hegazy, Ayman | -45680 | 39
105-94 | CONSTRUCTION OF AL-MURJAN | 5792 | CONSTRUCTION OF AL-MURJAN-ACSR conectors and clamps | APPROVED | No | 2025-02-05 | Abas, Mohammed Fekry | 2025-02-12 | 2025-02-12 |  |  |  | 8100 | 6864 | 0 | STANDARD | Arruti Subestaciones , S.A.U | EUR | 5948.82 | APPROVED |  |  | 2025-02-17 | 2151.18 | 5 | Mohammed, Faisal Ansari | -45700 | 5
105-94 | CONSTRUCTION OF AL-MURJAN | 5988 | CONSTRUCTION OF AL-MURJAN-ACSR conectors and clamps-PO Amdedment | APPROVED | No | 2025-02-19 | Abas, Mohammed Fekry | 2025-03-02 | 2025-03-03 | 2025-02-24 |  | Please add shipping charges as discussed. | 2100 | 6864 | 1 | STANDARD | Arruti Subestaciones , S.A.U | EUR | 1931.21 | APPROVED |  |  | 2025-03-09 | 168.79 | 6 | Mohammed, Faisal Ansari | -45719 | 6
105-94 | CONSTRUCTION OF AL-MURJAN | 6036 | CONSTRUCTION OF AL-MURJAN-MV cable Accessories-Cable Clamps | APPROVED | No | 2025-02-24 | Abas, Mohammed Fekry | 2025-03-02 | 2025-03-03 |  |  | MV cable clamps due to PTE offer | 64587 | 6943 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 64585 | APPROVED |  |  | 2025-03-09 | 2 | 6 | Mohammed, Faisal Ansari | -45719 | 6
105-94 | CONSTRUCTION OF AL-MURJAN | 6156 | CONSTRUCTION OF AL-MURJAN-Diesel fuling for generators | APPROVED | No | 2025-03-11 | Abas, Mohammed Fekry | 2025-03-13 | 2025-03-13 |  |  |  | 120000 | 7049 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 119880 | APPROVED |  |  | 2025-04-09 | 120 | 27 | Abuhammad, Samir | -45729 | 27
105-94 | CONSTRUCTION OF AL-MURJAN | 6239 | CONSTRUCTION OF AL-MURJAN-Indoor/outdoor lighting conduits and fittings | APPROVED | No | 2025-03-23 | Abas, Mohammed Fekry | 2025-03-25 | 2025-03-25 |  |  | Instead of cancelled PR#6186 | 445000 | 7033 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 384000 | APPROVED |  |  | 2025-04-09 | 61000 | 15 | Mohammed, Faisal Ansari | -45741 | 15
105-94 | CONSTRUCTION OF AL-MURJAN | 6240 | CONSTRUCTION OF AL-MURJAN-Supply and Installation of FOC Cables for SS&Remote end | APPROVED | No | 2025-03-23 | Abas, Mohammed Fekry | 2025-03-27 | 2025-03-27 |  |  |  | 220500 | 7032 | 0 | STANDARD | RASHID SAEED AHMED AL GHAMDI COMM INFO TRAD EST | SAR | 215000 | APPROVED |  |  | 2025-04-09 | 5500 | 13 | Mohammed, Faisal Ansari | -45743 | 13
105-94 | CONSTRUCTION OF AL-MURJAN | 6254 | CONSTRUCTION OF AL-MURJAN-to amend UGC Consultancy Services PO#5243 Bold engineering | APPROVED | No | 2025-03-24 | Abas, Mohammed Fekry | 2025-03-27 | 2025-03-27 |  |  |  | 42000 | 5243 | 1 | STANDARD | Bold Engineering Consulting Office | SAR | 42000 | APPROVED |  |  | 2025-04-21 | 0 | 25 | Alhadi, Khalid | -45743 | 25
105-94 | CONSTRUCTION OF AL-MURJAN | 6254 | CONSTRUCTION OF AL-MURJAN-to amend UGC Consultancy Services PO#5243 Bold engineering | APPROVED | No | 2025-03-24 | Abas, Mohammed Fekry | 2025-03-27 | 2025-03-27 |  |  |  | 42000 | 5243 | 2 | STANDARD | Bold Engineering Consulting Office | SAR | 42000 | IN PROCESS |  |  |  | 0 | 311 | Alhadi, Khalid | -45743 | -45743
105-94 | CONSTRUCTION OF AL-MURJAN | 6257 | CONSTRUCTION OF AL-MURJAN-change prder to PO#6563_Supply of CHH due to price variation | APPROVED | No | 2025-03-24 | Abas, Mohammed Fekry | 2025-03-27 | 2025-03-27 |  |  |  | 21000 | 6563 | 1 | STANDARD | Product Art Est | SAR | 21000 | APPROVED |  |  | 2025-04-22 | 0 | 26 | Tananeh, Khalid Jamal | -45743 | 26
105-94 | CONSTRUCTION OF AL-MURJAN | 6325 | CONSTRUCTION OF AL-MURJAN-SWG Panel Repair- CO for PO#4760 | REJECTED | No | 2025-04-13 | Yasmin, Ahmed Elsayed Mohamed | 2025-06-02 | 2025-06-02 | 2025-05-19 | 2025-06-15 | More info is required or cancel the PR if not required. | 36000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45810 | -45810
105-94 | CONSTRUCTION OF AL-MURJAN | 6562 | CONSTRUCTION OF AL-MURJAN-Accessories of cable trays and additional quantaties of cable ladders | APPROVED | No | 2025-05-07 | Abas, Mohammed Fekry | 2025-05-15 | 2025-05-15 |  |  | PR initiated for settling cable tray accessoreis and additional 25% of missed cable tray as per previous issued PO before approval of design | 200000 | 7326 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 169800 | APPROVED |  |  | 2025-05-28 | 30200 | 13 | Mohammed, Faisal Ansari | -45792 | 13
105-94 | CONSTRUCTION OF AL-MURJAN | 6640 | CONSTRUCTION OF AL-MURJAN-Lugs and Glands | APPROVED | No | 2025-05-19 | Abas, Mohammed Fekry | 2025-05-27 | 2025-05-27 |  |  |  | 46500 | 7284 | 0 | STANDARD | Ahmed Essa Mohammed Al Muslim Est. | SAR | 46260 | APPROVED |  |  | 2025-06-29 | 240 | 33 | Mohammed, Faisal Ansari | -45804 | 33
105-94 | CONSTRUCTION OF AL-MURJAN | 6641 | CONSTRUCTION OF AL-MURJAN-Change order for UGC Security Guards PO#5514-1-4 | REJECTED | No | 2025-05-19 | Yasmin, Ahmed Elsayed Mohamed | 2025-06-30 | 2025-05-20 |  | 2025-07-02 |  | 432000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45797 | -45797
105-94 | CONSTRUCTION OF AL-MURJAN | 6735 | CONSTRUCTION OF AL-MURJAN-RMU Termination KIT | APPROVED | No | 2025-05-27 | Abas, Mohammed Fekry | 2025-06-04 | 2025-06-12 |  |  | For RMU Termination Kit | 25000 | 7556 | 0 | STANDARD | AlHedab Contractin Works Est. | SAR | 8200 | APPROVED |  |  | 2025-08-12 | 16800 | 61 | Muaz, Alaa | -45820 | 61
105-94 | CONSTRUCTION OF AL-MURJAN | 6776 | CONSTRUCTION OF AL-MURJAN-Diesel supply for Al Murjan # 8274 | APPROVED | No | 2025-06-12 | Abas, Mohammed Fekry | 2025-06-15 | 2025-06-15 |  |  |  | 240000 | 7484 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 239998.77 | APPROVED |  |  | 2025-07-24 | 1.23 | 39 | Akhtar, Farhan | -45823 | 39
105-94 | CONSTRUCTION OF AL-MURJAN | 6988 | CONSTRUCTION OF AL-MURJAN-Fire stop and fire rated material PR | REJECTED | No | 2025-07-06 | Yasmin, Ahmed Elsayed Mohamed | 2025-07-15 | 2025-07-07 |  | 2025-07-16 |  | 87100 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45845 | -45845
105-94 | CONSTRUCTION OF AL-MURJAN | 7047 | CONSTRUCTION OF AL-MURJAN-Change order of door and panel (H52) repair | APPROVED | No | 2025-07-15 | Abas, Mohammed Fekry | 2025-07-20 | 2025-07-20 |  |  |  | 36000 | 4760 | 1 | STANDARD | ALFANAR CO | SAR | 35000 | APPROVED |  |  | 2025-07-24 | 1000 | 4 | Mohammed, Faisal Ansari | -45858 | 4
105-94 | CONSTRUCTION OF AL-MURJAN | 7194 | CONSTRUCTION OF AL-MURJAN-PR for LV Cables - Al Murjan | RETURNED | No | 2025-07-23 | Mohammed, Faisal Ansari | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-08-31 | Not Required. | 0 | 7834 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 209415.38 | APPROVED |  |  | 2025-12-01 | -209415.38 |  | Mohammed, Faisal Ansari | -45960 | 32
105-94 | CONSTRUCTION OF AL-MURJAN | 7194 | CONSTRUCTION OF AL-MURJAN-PR for LV Cables - Al Murjan | RETURNED | No | 2025-07-23 | Mohammed, Faisal Ansari | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-08-31 | Not Required. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45960 | -45960
105-94 | CONSTRUCTION OF AL-MURJAN | 7232 | CONSTRUCTION OF AL-MURJAN-SAS (Blue Sheath) include 25% spare | APPROVED | No | 2025-07-28 | Abas, Mohammed Fekry | 2025-08-10 | 2025-08-10 |  |  |  | 0 | 7613 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 39758 | APPROVED |  |  | 2025-09-04 | -39758 | 25 | Mohammed, Faisal Ansari | -45879 | 25
105-94 | CONSTRUCTION OF AL-MURJAN | 7288 | CONSTRUCTION OF AL-MURJAN-PR for the installation of HV Cable joints and termination | RETURNED | No | 2025-08-05 | Mohammed, Faisal Ansari | 2025-09-07 | 2025-08-18 | 2025-09-07 |  | Please include Link Boxes installation as well. | 420000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45887 | -45887
105-94 | CONSTRUCTION OF AL-MURJAN | 7323 | CONSTRUCTION OF AL-MURJAN-Fire rated material PR | REJECTED | No | 2025-08-11 | Yasmin, Ahmed Elsayed Mohamed | 2025-08-12 | 2025-08-12 |  | 2025-08-24 |  | 382000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45881 | -45881
105-94 | CONSTRUCTION OF AL-MURJAN | 7474 | Fire Rated Material | REJECTED | No | 2025-08-25 | Elfarra, Essam Eldin Mohamad | 2025-08-27 | 2025-08-25 |  | 2025-08-26 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45894 | -45894
105-94 | CONSTRUCTION OF AL-MURJAN | 7480 | construction of AlMurjan | RETURNED | No | 2025-08-25 | Mohammed, Faisal Ansari | 2025-09-07 | 2025-08-28 | 2025-09-07 |  | This PR is not required, as the PO has already been closed. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45897 | -45897
105-94 | CONSTRUCTION OF AL-MURJAN | 7481 | Construction of AlMurjan | APPROVED | No | 2025-08-25 | Abas, Mohammed Fekry | 2025-08-27 | 2025-08-28 |  |  | SAS Control Cables (Blue sheeth) | 0 | 7613 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 49600 | APPROVED |  |  | 2025-09-04 | -49600 | 7 | Mohammed, Faisal Ansari | -45897 | 7
105-94 | CONSTRUCTION OF AL-MURJAN | 7514 | construction of Al Murjan | REJECTED | No | 2025-08-26 | Yasmin, Ahmed Elsayed Mohamed | 2025-08-27 | 2025-08-27 |  | 2025-08-28 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45896 | -45896
105-94 | CONSTRUCTION OF AL-MURJAN | 7622 | % | RETURNED | No | 2025-09-02 | Mohammed, Faisal Ansari | 2025-10-02 | 2025-09-04 | 2025-10-02 |  | Please correct the quantity as per the Annex-1 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45904 | -45904
105-94 | CONSTRUCTION OF AL-MURJAN | 7638 | Construction of Al Murjan | RETURNED | No | 2025-09-04 | Alhadi, Khalid | 2025-09-25 | 2025-09-04 | 2025-09-25 |  | The requirements are not accurate. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45904 | -45904
105-94 | CONSTRUCTION OF AL-MURJAN | 7734 | Construction of Al Murjan | REJECTED | No | 2025-09-14 | Yasmin, Ahmed Elsayed Mohamed | 2025-09-16 | 2025-09-16 |  | 2025-09-21 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45916 | -45916
105-94 | CONSTRUCTION OF AL-MURJAN | 7792 | LV Cables | REJECTED | No | 2025-09-18 | Elfarra, Essam Eldin Mohamad | 2025-10-26 | 2025-09-21 | 2025-10-23 | 2025-10-26 | Please create the PR as per the latest agreed quantities. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45921 | -45921
105-94 | CONSTRUCTION OF AL-MURJAN | 7793 | Construction of Al Murjan | RETURNED | No | 2025-09-18 | Mohammed, Faisal Ansari | 2025-10-23 | 2025-09-21 | 2025-10-23 |  | Please create the PR as per the latest agreed quantities. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45921 | -45921
105-94 | CONSTRUCTION OF AL-MURJAN | 7824 | Construction of Al Murjan | APPROVED | No | 2025-09-25 | Abas, Mohammed Fekry | 2025-10-02 | 2025-10-02 |  |  | Communications handholes (CHH) - (Product Art) - Quantity 4 CHH | 0 | 6563 | 2 | STANDARD | Product Art Est | SAR | 18800 | APPROVED |  |  | 2025-11-11 | -18800 | 40 | Tananeh, Khalid Jamal | -45932 | 40
105-94 | CONSTRUCTION OF AL-MURJAN | 7825 | Construction of Al Murjan | APPROVED | No | 2025-09-25 | Abas, Mohammed Fekry | 2025-10-02 | 2025-10-02 |  |  | Concrete Tiles - (ALNASHAA) - quantity (34,000) | 0 | 6676 | 1 | STANDARD | Constriction Company Limited ( AL NASHAA LTD) | SAR | 73100 | APPROVED |  |  | 2025-11-11 | -73100 | 40 | Tananeh, Khalid Jamal | -45932 | 40
105-94 | CONSTRUCTION OF AL-MURJAN | 7826 | % | APPROVED | No | 2025-09-25 | Abas, Mohammed Fekry | 2025-10-02 | 2025-10-02 |  |  | Green UPVC steel wire mesh - (Modern Factory) - Quantity 280 roll | 0 | 6562 | 1 | STANDARD | Modern Factory For Steel Industries Company | SAR | 38934 | APPROVED |  |  | 2025-11-04 | -38934 | 33 | Tananeh, Khalid Jamal | -45932 | 33
105-94 | CONSTRUCTION OF AL-MURJAN | 7848 | Construction of Al Murjan | APPROVED | No | 2025-09-29 | Abas, Mohammed Fekry | 2025-10-23 | 2025-10-25 | 2025-10-13 |  | Shows exceeding budget. Kindly revise and resubmit. | 0 | 7597 | 0 | STANDARD | Advanced Destination Company | SAR | 880 | APPROVED |  |  | 2025-11-04 | -880 | 10 | Mohammed, Faisal Ansari | -45955 | 10
105-94 | CONSTRUCTION OF AL-MURJAN | 7875 | onstruction of Al Murjan | RETURNED | No | 2025-10-01 | Mohammed, Faisal Ansari | 2025-10-26 | 2025-10-25 |  |  |  | 0 | 7792 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 28050 | APPROVED |  |  | 2025-10-30 | -28050 |  | Mohammed, Faisal Ansari | -45955 | 5
105-94 | CONSTRUCTION OF AL-MURJAN | 7875 | onstruction of Al Murjan | RETURNED | No | 2025-10-01 | Mohammed, Faisal Ansari | 2025-10-26 | 2025-10-25 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45955 | -45955
105-94 | CONSTRUCTION OF AL-MURJAN | 7878 | % | RETURNED | No | 2025-10-01 | Mohammed, Faisal Ansari | 2025-11-20 | 2025-10-08 | 2025-11-20 |  | We cannot enter the PO value. Please check and reissue the PR corerctly. | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45938 | -45938
105-94 | CONSTRUCTION OF AL-MURJAN | 7887 | Construction of Al Murjan | APPROVED | No | 2025-10-20 | Abas, Mohammed Fekry | 2025-10-21 | 2025-10-21 |  |  | Civil work - UGC | 0 | 7813 | 0 | STANDARD | Anhar Alyhari Contracting Co | SAR | 2627000 | APPROVED |  |  | 2025-11-16 | -2627000 | 26 | Tananeh, Khalid Jamal | -45951 | 26
105-94 | CONSTRUCTION OF AL-MURJAN | 7888 | Construction of Al Murjan | RETURNED | No | 2025-10-02 | Tananeh, Khalid Jamal | 2025-10-23 | 2025-10-08 | 2025-10-23 |  | return as per email From: Abdelrahman Mohamed Ghazy , 21 October 2025 09:31 , that to to create a new PR with the correct value that corresponds to the PO. | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45938 | -45938
105-94 | CONSTRUCTION OF AL-MURJAN | 7889 | Construction of Al Murjan | INCOMPLETE | No | [6 empty] | return as per email From: Abdelrahman Mohamed Ghazy , 21 October 2025 09:31 , that to to create a new PR with the correct value that corresponds to the PO. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | 0 | 0
105-94 | CONSTRUCTION OF AL-MURJAN | 7890 | Construction of Al Murjan | RETURNED | No | 2025-10-02 | Alhadi, Khalid | 2025-11-11 | 2025-10-12 | 2025-11-11 |  | Budget is not sufficent | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45942 | -45942
105-94 | CONSTRUCTION OF AL-MURJAN | 7892 | Construction of Al Murjan | RETURNED | No | 2025-10-02 | Tananeh, Khalid Jamal | 2025-10-28 | 2025-10-08 | 2025-10-28 |  | "The reason for the return is the mismatch with the approved change order, as there is a shortage in quantities and the warning colors are different from the approved change order. You can refer to the email sent to Mr.Abdulrahman. Tue 10/28/2025 12:46 PM" | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45938 | -45938
105-94 | CONSTRUCTION OF AL-MURJAN | 7895 | Construction of Al Murjan | RETURNED | No | 2025-10-02 | Tananeh, Khalid Jamal | 2025-10-26 | 2025-10-08 | 2025-10-26 |  | return as per email from Abdelrahman Ghazy Sun 10/26/2025 3:10 PM , this PR was requests under a different PR numbers. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45938 | -45938
105-94 | CONSTRUCTION OF AL-MURJAN | 7896 | Construction of Al Murjan | RETURNED | No | 2025-10-02 | Mohammed, Faisal Ansari | 2025-10-23 | 2025-10-08 | 2025-10-23 |  | Description is not clear. Please revise the PR with the clear description. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45938 | -45938
105-94 | CONSTRUCTION OF AL-MURJAN | 7897 | Construction of Al Murjan | RETURNED | No | 2025-10-02 | Tananeh, Khalid Jamal | 2025-10-26 | 2025-10-08 | 2025-10-26 |  | return as per email from Abdelrahman Ghazy Sun 10/26/2025 3:10 PM , this PR was requests under a different PR numbers. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45938 | -45938
105-94 | CONSTRUCTION OF AL-MURJAN | 7905 | % | INCOMPLETE | No | [6 empty] | return as per email from Abdelrahman Ghazy Sun 10/26/2025 3:10 PM , this PR was requests under a different PR numbers. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | 0 | 0
105-94 | CONSTRUCTION OF AL-MURJAN | 7906 | Construction of Al Murjan | APPROVED | No | 2025-10-06 | Abas, Mohammed Fekry | 2025-10-13 | 2025-10-13 |  |  | Fire rated material | 0 | 7597 | 0 | STANDARD | Advanced Destination Company | SAR | 116300 | APPROVED |  |  | 2025-11-04 | -116300 | 22 | Mohammed, Faisal Ansari | -45943 | 22
105-94 | CONSTRUCTION OF AL-MURJAN | 8024 | Nescon PR | APPROVED | No | 2025-10-21 | Abas, Mohammed Fekry | 2026-01-27 | 2026-01-28 | 2025-10-27 |  | The reason for returning this PR is that it exceeds the allocated budget. As per the Procurement Department's instructions, any PR that exceeds the budget must be returned. Therefore, please adjust the budget amount accordingly and create a new PR after the budget has been updated. ( as per email sent in 27-10-2025 to Abdelrahman Mohamed Ghazy) | 0 | 5514 | 1 | STANDARD | NSCON NEU CONTRACTING | SAR | 584000 | IN PROCESS |  |  |  | -584000 | 4 | Tananeh, Khalid Jamal | -46050 | -46050
105-94 | CONSTRUCTION OF AL-MURJAN | 8024 | Nescon PR | APPROVED | No | 2025-10-21 | Abas, Mohammed Fekry | 2026-01-27 | 2026-01-28 | 2025-10-27 |  | The reason for returning this PR is that it exceeds the allocated budget. As per the Procurement Department's instructions, any PR that exceeds the budget must be returned. Therefore, please adjust the budget amount accordingly and create a new PR after the budget has been updated. ( as per email sent in 27-10-2025 to Abdelrahman Mohamed Ghazy) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -46050 | -46050
105-94 | CONSTRUCTION OF AL-MURJAN | 8059 | PDS System | RETURNED | No | 2025-10-26 | Mohammed, Faisal Ansari | 2025-10-30 | 2025-10-30 | 2025-10-30 |  | Please issue PR along with the approved PR acceptance criteria form and relevant docs. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45960 | -45960
105-94 | CONSTRUCTION OF AL-MURJAN | 8088 | Disconnect switch | REJECTED | No | 2025-10-29 | Elfarra, Essam Eldin Mohamad | 2025-12-02 | 2025-11-01 | 2025-11-06 | 2025-12-04 | Can be procured locally thru petty cash. PO is not required. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45962 | -45962
105-94 | CONSTRUCTION OF AL-MURJAN | 8245 | Waring tape | APPROVED | No | 2025-11-17 | Abas, Mohammed Fekry | 2025-12-09 | 2025-12-09 |  | 2025-12-02 | Waring tape for Al Murjan project | 0 | 6605 | 1 | STANDARD | Mas Adhesive Tape Manufacturer Company | SAR | 33000 | APPROVED |  |  | 2025-12-29 | -33000 | 20 | Tananeh, Khalid Jamal | -46000 | 20
105-94 | CONSTRUCTION OF AL-MURJAN | 8347 | consultant for the UGC activities and permits | RETURNED | No | 2025-11-25 | Alhadi, Khalid | 2025-12-11 | 2025-12-02 | 2025-12-11 |  | POCR is not approved yet. PR was not returned earlier since Project team advised POCR is in the final approval. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45993 | -45993
105-94 | CONSTRUCTION OF AL-MURJAN | 8404 | Cable support for Al Murjan | RETURNED | No | 2025-12-01 | Mohammed, Faisal Ansari | 2026-01-27 | 2026-01-08 | 2026-01-27 | 2025-12-01 | This is an old PR and does not include all quantities as per the latest BOQ. Kindly revise it at the time of PO finalization to avoid any wastage of time. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46030 | -46030
105-94 | CONSTRUCTION OF AL-MURJAN | 8425 | Cable support for Al Murjan | APPROVED | No | 2025-12-02 | Abas, Mohammed Fekry | 2026-01-06 | 2026-01-08 |  |  | Cable support for Al Murjan | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -46030 | -46030
105-94 | CONSTRUCTION OF AL-MURJAN | 8426 | HV Support for Al Murjan | RETURNED | No | 2025-12-02 | Hegazy, Ayman | 2026-01-13 | 2025-12-09 | 2026-01-13 |  | to update to match the ack. PO | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -46000 | -46000
105-94 | CONSTRUCTION OF AL-MURJAN | 8428 | HV Support of Al Murjan | APPROVED | No | 2025-12-02 | Abas, Mohammed Fekry | 2026-01-06 | 2026-01-08 |  |  | HV Support of Al Murjan | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -46030 | -46030
105-94 | CONSTRUCTION OF AL-MURJAN | 8430 | HV Support of Al Murjan | APPROVED | No | 2025-12-02 | Abas, Mohammed Fekry | 2026-01-06 | 2026-01-08 |  |  | HV Support of Al Murjan | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -46030 | -46030
105-94 | CONSTRUCTION OF AL-MURJAN | 8434 | Flat Bare for AL Murjan | REJECTED | No | 2025-12-03 | Elfarra, Essam Eldin Mohamad | 2025-12-03 |  |  | 2025-12-04 | Flat Bare of Al Murjan | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | 0 | 0
105-94 | CONSTRUCTION OF AL-MURJAN | 8443 | Bare Copper Tape (40*6mm) | APPROVED | No | 2025-12-04 | Abas, Mohammed Fekry | 2025-12-09 | 2025-12-09 |  |  | Bare copper tape 40 X 6 mm (25M/ROLL) | 0 | 7995 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 18056.5 | APPROVED |  |  | 2025-12-15 | -18056.5 | 6 | Mohammed, Faisal Ansari | -46000 | 6
105-94 | CONSTRUCTION OF AL-MURJAN | 8445 | 132 KV GIS, 40 KA (1S) ,2000 A at 40c | APPROVED | No | 2025-12-04 | Abas, Mohammed Fekry | 2025-12-09 | 2025-12-09 |  |  | Related to the manual PO # 8315 | 0 | 4731 | 0 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 11010000 | APPROVED |  |  | 2025-12-17 | -11010000 | 8 | Babic, Marian | -46000 | 8
105-94 | CONSTRUCTION OF AL-MURJAN | 8558 | HV Cable entry hanging system | RETURNED | No | 2025-12-18 | Mohammed, Faisal Ansari | 2026-01-27 | 2026-01-01 | 2026-01-27 |  | Please issue the PR when this subject is finalized. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46023 | -46023
105-94 | CONSTRUCTION OF AL-MURJAN | 8588 | Rental Manpower | APPROVED | No | 2025-12-28 | Abas, Mohammed Fekry | 2025-12-29 | 2026-01-01 |  |  | Rental Manpower - PO issued # 7845 - Al Murjan project | 0 | 7845 | 0 | STANDARD | Jasem M.AlJasem Contracting Est. | SAR | 405600 | APPROVED | 2026-01-01 | 2026-01-08 | 2026-01-28 | -405600 | 27 | Alhadi, Khalid | 7 | 27
105-94 | CONSTRUCTION OF AL-MURJAN | 8626 | consultant for the UGC activities and permits | APPROVED | No | 2026-01-01 | Abas, Mohammed Fekry | 2026-01-13 | 2026-01-13 |  |  | consultant for the UGC activities and permits(Bold) - POCR Approved | 0 | 5243 | 2 | STANDARD | Bold Engineering Consulting Office | SAR | 42000 | IN PROCESS |  |  |  | -42000 | 19 | Alhadi, Khalid | -46035 | -46035
105-94 | CONSTRUCTION OF AL-MURJAN | 8626 | consultant for the UGC activities and permits | APPROVED | No | 2026-01-01 | Abas, Mohammed Fekry | 2026-01-13 | 2026-01-13 |  |  | consultant for the UGC activities and permits(Bold) - POCR Approved | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46035 | -46035
105-94 | CONSTRUCTION OF AL-MURJAN | 8634 | Fiber optic cable | IN PROCESS | No | 2026-01-04 | Yasmin, Ahmed Elsayed Mohamed | 2026-01-26 | 2026-01-26 | 2026-01-13 |  | Shows budget exceeded. Please resolve the issue. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46048 | -46048
105-94 | CONSTRUCTION OF AL-MURJAN | 8635 | JIB Crane | APPROVED | No | 2026-01-04 | Abas, Mohammed Fekry | 2026-01-12 | 2026-01-13 |  |  | JIB Crane | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46035 | -46035
105-94 | CONSTRUCTION OF AL-MURJAN | 8750 | NESCON - Gurads | APPROVED | No | 2026-01-20 | Abas, Mohammed Fekry | 2026-01-22 | 2026-01-25 |  |  | UGC - NESCON - increase time line scopeforGuards provided foreachsection | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -46047 | -46047
105-94 | CONSTRUCTION OF AL-MURJAN | 8779 | Civil work for joint installation | IN PROCESS | No | 2026-01-25 | Yasmin, Ahmed Elsayed Mohamed | 2026-01-25 | 2026-01-25 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46047 | -46047
105-94 | CONSTRUCTION OF AL-MURJAN | 8803 | Gassing and degassing for GIS | IN PROCESS | No | 2026-01-27 | Yasmin, Ahmed Elsayed Mohamed | 2026-01-28 | 2026-01-28 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46050 | -46050
105-94 | CONSTRUCTION OF AL-MURJAN | 8819 | Asphalt - Fayed Al jazeera | IN PROCESS | No | 2026-01-28 | Yasmin, Ahmed Elsayed Mohamed | 2026-01-29 | 2026-01-29 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46051 | -46051
105-94 | CONSTRUCTION OF AL-MURJAN | 8820 | % | REJECTED | No | 2026-01-28 | Elfarra, Essam Eldin Mohamad | 2026-01-28 |  |  | 2026-01-28 | Diesel supply for Al Murjan | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | 0 | 0
105-94 | CONSTRUCTION OF AL-MURJAN | 8821 | Diesel supply for Al Murjan | IN PROCESS | No | 2026-01-28 | Yasmin, Ahmed Elsayed Mohamed | 2026-01-29 | 2026-01-29 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46051 | -46051
105-94 | CONSTRUCTION OF AL-MURJAN | 8824 | Disel supply for Al Murjan | REJECTED | No | 2026-01-28 | Elfarra, Essam Eldin Mohamad | 2026-01-28 |  |  | 2026-01-28 | Diesel supply for Al Murjan | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | 0 | 0
105-94 | CONSTRUCTION OF AL-MURJAN | 8825 | Supply Diesel for Al Murjan | IN PROCESS | No | 2026-01-28 | Yasmin, Ahmed Elsayed Mohamed | 2026-01-29 | 2026-01-29 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46051 | -46051
105-95 | Modon Hafar Al Batin | 1601 | Modon Hafar Al Batin-132kv GIS | APPROVED | No | 2023-10-16 | Abas, Mohammed Fekry | 2023-10-19 | 2023-10-22 |  |  |  | 13200833 | 4755 | 0 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 12300000 | APPROVED |  |  | 2023-12-03 | 900833 | 42 | Kumar, Mr. Ranjan | -45221 | 42
105-95 | Modon Hafar Al Batin | 1604 | Modon Hafar Al Batin-Power transformer for hafar al batin | APPROVED | No | 2023-10-17 | Abas, Mohammed Fekry | 2023-10-25 | 2023-10-25 |  |  |  | 14502000 | 5095 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 13827750 | APPROVED |  |  | 2024-03-06 | 674250 | 133 | Mohammed, Faisal Ansari | -45224 | 133
105-95 | Modon Hafar Al Batin | 1627 | Modon Hafar Al Batin-Engineerign & Design | APPROVED | No | 2023-10-24 | Abas, Mohammed Fekry | 2023-10-25 | 2023-10-25 |  |  |  | 350000 | 4679 | 0 | STANDARD | Saudi Designers Engineering Consultants | SAR | 335000 | APPROVED |  |  | 2023-11-06 | 15000 | 12 | Mohammed, Faisal Ansari | -45224 | 12
105-95 | Modon Hafar Al Batin | 1628 | Modon Hafar Al Batin-ACDC & Lighting Panels | APPROVED | No | 2023-10-25 | Abas, Mohammed Fekry | 2023-10-25 | 2023-10-25 |  |  |  | 798000 | 4680 | 0 | STANDARD | ALFANAR CO | SAR | 798000 | APPROVED |  |  | 2023-11-05 | 0 | 11 | Mohammed, Faisal Ansari | -45224 | 11
105-95 | Modon Hafar Al Batin | 1666 | Modon Hafar Al Batin-100kVA & 300kVA Generators for Project Site | APPROVED | No | 2023-11-07 | Abas, Mohammed Fekry | 2023-11-15 | 2023-11-16 | 2023-11-13 |  | line item descreption in the PR is not matching with the actual inventory item | 250000 | 4730 | 0 | STANDARD | Mohammed A. AlFaddaghi & Partners | SAR | 250000 | APPROVED |  |  | 2023-11-27 | 0 | 11 | Badhman, Saeed | -45246 | 11
105-95 | Modon Hafar Al Batin | 1767 | Modon Hafar Al Batin-Site moblization-Hafar Al batin | APPROVED | No | 2023-11-16 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-19 |  |  |  | 905000 | 4746 | 0 | STANDARD | Coating Application Company Ltd., | SAR | 904528.6 | APPROVED |  |  | 2023-12-11 | 471.4 | 22 | Mohammed, Faisal Ansari | -45249 | 22
105-95 | Modon Hafar Al Batin | 2156 | Modon Hafar Al Batin-Soil investigation | APPROVED | No | 2024-01-11 | Abas, Mohammed Fekry | 2024-01-11 | 2024-01-11 |  |  |  | 20095 | 5130 | 0 | STANDARD | International Agent Commercial Company(S) | SAR | 20095 | APPROVED |  |  | 2024-03-03 | 0 | 52 | Mohammed, Faisal Ansari | -45302 | 52
105-95 | Modon Hafar Al Batin | 2194 | Modon Hafar Al Batin-Communciation System | APPROVED | No | 2024-01-17 | Abas, Mohammed Fekry | 2024-02-11 | 2024-02-12 |  |  |  | 6450000 | 5001 | 0 | STANDARD | ALFANAR CO | SAR | 6450000 | APPROVED |  |  | 2024-12-24 | 0 | 316 | Mohammed, Faisal Ansari | -45334 | 316
105-95 | Modon Hafar Al Batin | 2195 | Modon Hafar Al Batin-33kV Capacitor Bank | APPROVED | No | 2024-01-17 | Abas, Mohammed Fekry | 2024-02-07 | 2024-02-10 |  |  |  | 1287500 | 4880 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 1287500 | APPROVED |  |  | 2024-02-25 | 0 | 15 | Mohammed, Faisal Ansari | -45332 | 15
105-95 | Modon Hafar Al Batin | 2205 | Modon Hafar Al Batin-Excavation Works for Building | APPROVED | No | 2024-01-18 | Abas, Mohammed Fekry | 2024-01-21 | 2024-01-21 |  |  |  | 75000 | 5242 | 0 | STANDARD | AlSema Alola for General Contracting Est.(S) | SAR | 50000 | APPROVED |  |  | 2024-03-20 | 25000 | 59 | Alhadi, Khalid | -45312 | 59
105-95 | Modon Hafar Al Batin | 2225 | Modon Hafar Al Batin-Safety Requirements | APPROVED | No | 2024-01-21 | Abas, Mohammed Fekry | 2024-01-21 | 2024-01-21 |  |  |  | 110000 | 5125 | 0 | STANDARD | Ahmed Essa Mohammed Al Muslim Est. | SAR | 96114 | APPROVED |  |  | 2024-03-24 | 13886 | 63 | Akhtar, Farhan | -45312 | 63
105-95 | Modon Hafar Al Batin | 2244 | Modon Hafar Al Batin-108kV Surge Arrester | APPROVED | No | 2024-01-21 | Abas, Mohammed Fekry | 2024-01-22 | 2024-01-22 |  |  |  | 108000 | 4993 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 104622.01 | APPROVED |  |  | 2024-01-30 | 3377.99 | 8 | Kumar, Mr. Ranjan | -45313 | 8
105-95 | Modon Hafar Al Batin | 2670 | Modon Hafar Al Batin-Protection, Control, Metering & SAS System | APPROVED | No | 2024-02-25 | Abas, Mohammed Fekry | 2024-02-27 | 2024-02-28 |  |  |  | 7200000 | 5493 | 0 | STANDARD | ALFANAR CO | SAR | 7200000 | APPROVED |  |  | 2024-05-13 | 0 | 75 | Mohammed, Faisal Ansari | -45350 | 75
105-95 | Modon Hafar Al Batin | 2679 | Modon Hafar Al Batin-33kV SF6 MV SWGR | APPROVED | No | 2024-02-25 | Abas, Mohammed Fekry | 2024-02-27 | 2024-02-28 |  |  |  | 5650000 | 5269 | 0 | STANDARD | ALFANAR CO | SAR | 5650000 | APPROVED |  |  | 2024-03-26 | 0 | 27 | Mohammed, Faisal Ansari | -45350 | 27
105-95 | Modon Hafar Al Batin | 2706 | Modon Hafar Al Batin-Station Transformers-500kVA | APPROVED | No | 2024-02-28 | Abas, Mohammed Fekry | 2024-02-29 | 2024-03-03 |  |  |  | 126000 | 5309 | 0 | STANDARD | ALFANAR CO | SAR | 126000 | APPROVED |  |  | 2024-04-04 | 0 | 32 | Mohammed, Faisal Ansari | -45354 | 32
105-95 | Modon Hafar Al Batin | 2706 | Modon Hafar Al Batin-Station Transformers-500kVA | APPROVED | No | 2024-02-28 | Abas, Mohammed Fekry | 2024-02-29 | 2024-03-03 |  |  |  | 126000 | 5309 | 1 | STANDARD | ALFANAR CO | SAR | 126000 | REQUIRES REAPPROVAL |  |  |  | 0 | 700 | Mohammed, Faisal Ansari | -45354 | -45354
105-95 | Modon Hafar Al Batin | 2707 | Modon Hafar Al Batin-Cyber Security System | APPROVED | No | 2024-02-28 | Abas, Mohammed Fekry | 2024-02-29 | 2024-03-03 |  |  |  | 1525000 | 5492 | 0 | STANDARD | ALFANAR CO | SAR | 1525000 | APPROVED |  |  | 2024-05-13 | 0 | 71 | Mohammed, Faisal Ansari | -45354 | 71
105-95 | Modon Hafar Al Batin | 2891 | Modon Hafar Al Batin-Complete Civil Works including Plumbing System & Gantry | RETURNED | No | 2024-03-24 | Tananeh, Khalid Jamal | 2025-10-20 | 2024-03-28 | 2025-10-20 |  | return as requested in the email from Arnie on Mon 10/20/2025 at 12:37 PM." | 11479865 | 5765 | 1 | STANDARD | Ektbarat Engineering Co | SAR | 6549851 | APPROVED |  |  | 2025-10-15 | 4930014 |  | Tananeh, Khalid Jamal | -45379 | 566
105-95 | Modon Hafar Al Batin | 2891 | Modon Hafar Al Batin-Complete Civil Works including Plumbing System & Gantry | RETURNED | No | 2024-03-24 | Tananeh, Khalid Jamal | 2025-10-20 | 2024-03-28 | 2025-10-20 |  | return as requested in the email from Arnie on Mon 10/20/2025 at 12:37 PM." | 11926865 | 5765 | 0 | STANDARD | Ektbarat Engineering Co | SAR | 11900000 | APPROVED |  |  | 2024-07-21 | 26865 |  | Tananeh, Khalid Jamal | -45379 | 115
105-95 | Modon Hafar Al Batin | 2891 | Modon Hafar Al Batin-Complete Civil Works including Plumbing System & Gantry | RETURNED | No | 2024-03-24 | Tananeh, Khalid Jamal | 2025-10-20 | 2024-03-28 | 2025-10-20 |  | return as requested in the email from Arnie on Mon 10/20/2025 at 12:37 PM." | 447000 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45379 | -45379
105-95 | Modon Hafar Al Batin | 2893 | Modon Hafar Al Batin-Grounding Material & Accessories | APPROVED | No | 2024-03-24 | Abas, Mohammed Fekry | 2024-03-28 | 2024-03-28 |  |  |  | 150000 | 5415 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 140782 | APPROVED |  |  | 2024-05-07 | 9218 | 40 | Mohammed, Faisal Ansari | -45379 | 40
105-95 | Modon Hafar Al Batin | 2893 | Modon Hafar Al Batin-Grounding Material & Accessories | APPROVED | No | 2024-03-24 | Abas, Mohammed Fekry | 2024-03-28 | 2024-03-28 |  |  |  | 150000 | 5415 | 1 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 128882 | APPROVED |  |  | 2024-06-06 | 21118 | 70 | Mohammed, Faisal Ansari | -45379 | 70
105-95 | Modon Hafar Al Batin | 2927 | Modon Hafar Al Batin-EOT Crane 5T | APPROVED | No | 2024-03-28 | Abas, Mohammed Fekry | 2024-03-31 | 2024-03-31 |  |  |  | 200000 | 5363 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 174000 | APPROVED |  |  | 2024-04-28 | 26000 | 28 | Mohammed, Faisal Ansari | -45382 | 28
105-95 | Modon Hafar Al Batin | 2973 | Modon Hafar Al Batin-Fire Alarm & Fire Fighting System | APPROVED | No | 2024-04-02 | Abas, Mohammed Fekry | 2024-04-03 | 2024-04-04 |  |  |  | 2072000 | 5422 | 0 | STANDARD | Conexus Contracting Company | SAR | 1790936 | APPROVED |  |  | 2024-06-11 | 281064 | 68 | Mohammed, Faisal Ansari | -45386 | 68
105-95 | Modon Hafar Al Batin | 3012 | Modon Hafar Al Batin-125V DC System | APPROVED | No | 2024-04-08 | Abas, Mohammed Fekry | 2024-04-10 | 2024-04-15 |  |  |  | 486000 | 5328 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 472500 | APPROVED |  |  | 2024-04-28 | 13500 | 13 | Mohammed, Faisal Ansari | -45397 | 13
105-95 | Modon Hafar Al Batin | 3013 | Modon Hafar Al Batin-Grounding Conductor | APPROVED | No | 2024-04-08 | Abas, Mohammed Fekry | 2024-04-10 | 2024-04-15 |  |  |  | 550000 | 5419 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 483088.4 | APPROVED |  |  | 2024-05-26 | 66911.6 | 41 | Mohammed, Faisal Ansari | -45397 | 41
105-95 | Modon Hafar Al Batin | 3013 | Modon Hafar Al Batin-Grounding Conductor | APPROVED | No | 2024-04-08 | Abas, Mohammed Fekry | 2024-04-10 | 2024-04-15 |  |  |  | 550000 | 5419 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 539266.73 | APPROVED |  |  | 2024-07-09 | 10733.27 | 85 | Mohammed, Faisal Ansari | -45397 | 85
105-95 | Modon Hafar Al Batin | 3624 | Modon Hafar Al Batin-Printer for Projet Site - A3 size laser color all in one (Wifi, Print, Copy, Scan) | APPROVED | No | 2024-06-09 | Abas, Mohammed Fekry | 2024-06-11 | 2024-06-12 |  |  |  | 15000 | 5749 | 0 | STANDARD | Golden Technology trading Company. | SAR | 13500 | APPROVED |  |  | 2024-07-01 | 1500 | 19 | Akhtar, Farhan | -45455 | 19
105-95 | Modon Hafar Al Batin | 3771 | Modon Hafar Al Batin-33kV Termination Kits | APPROVED | No | 2024-07-04 | Abas, Mohammed Fekry | 2024-07-07 | 2024-07-08 |  |  |  | 300000 | 5844 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 99495 | APPROVED |  |  | 2024-08-18 | 200505 | 41 | Mohammed, Faisal Ansari | -45481 | 41
105-95 | Modon Hafar Al Batin | 3771 | Modon Hafar Al Batin-33kV Termination Kits | APPROVED | No | 2024-07-04 | Abas, Mohammed Fekry | 2024-07-07 | 2024-07-08 |  |  |  | 300000 | 5844 | 1 | STANDARD | Nima Arabia Company Limited | SAR | 55688 | APPROVED |  |  | 2025-01-07 | 244312 | 183 | Mohammed, Faisal Ansari | -45481 | 183
105-95 | Modon Hafar Al Batin | 4044 | Modon Hafar Al Batin-33kV MV Cables | APPROVED | No | 2024-07-29 | Abas, Mohammed Fekry | 2024-07-30 | 2024-07-30 |  |  |  | 181716.77 | 6168 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 169263.55 | APPROVED |  |  | 2024-10-09 | 12453.22 | 71 | Badhman, Saeed | -45503 | 71
105-95 | Modon Hafar Al Batin | 4653 | Modon Hafar Al Batin-Supply,Installation,Testing and Commissioning of Security System | APPROVED | No | 2024-10-10 | Abas, Mohammed Fekry | 2024-10-13 | 2024-10-14 |  |  |  | 670000 | 6307 | 0 | STANDARD | ALFANAR CO | SAR | 670000 | APPROVED |  |  | 2024-10-24 | 0 | 10 | Mohammed, Faisal Ansari | -45579 | 10
105-95 | Modon Hafar Al Batin | 4841 | Modon Hafar Al Batin-Cable Ladder | APPROVED | No | 2024-11-05 | Abas, Mohammed Fekry | 2024-11-10 | 2024-11-11 |  |  |  | 107251.35 | 6155 | 0 | STANDARD | Power Solution Industries | SAR | 107251.35 | APPROVED |  |  | 2024-12-26 | 0 | 45 | Badhman, Saeed | -45607 | 45
105-95 | Modon Hafar Al Batin | 4863 | Modon Hafar Al Batin-Cable tray | REJECTED | No | 2024-11-07 | Ibrahim, Mahmoud Hassan Ali | 2024-11-13 | 2024-11-10 |  |  |  | 157985.98 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45606 | -45606
105-95 | Modon Hafar Al Batin | 4868 | Modon Hafar Al Batin-Control Cable | REJECTED | No | 2024-11-07 | Ibrahim, Mahmoud Hassan Ali | 2024-11-13 | 2024-11-10 |  | 2024-11-13 |  | 376158.87 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45606 | -45606
105-95 | Modon Hafar Al Batin | 4869 | Modon Hafar Al Batin-Control Cable LME # 9538 | REJECTED | No | 2024-11-07 | Asif, Mohammed | 2024-11-07 |  |  | 2024-11-07 |  | 81974.66 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-95 | Modon Hafar Al Batin | 4870 | Modon Hafar Al Batin-Control Cable # LME-9538 | REJECTED | No | 2024-11-07 | Asif, Mohammed | 2024-11-07 |  |  | 2024-11-10 |  | 81974.66 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-95 | Modon Hafar Al Batin | 4901 | Modon Hafar Al Batin-Cable Tray | APPROVED | No | 2024-11-11 | Abas, Mohammed Fekry | 2024-11-12 | 2024-11-12 |  |  |  | 157985.98 | 6155 | 0 | STANDARD | Power Solution Industries | SAR | 157985.98 | APPROVED |  |  | 2024-12-26 | 0 | 44 | Badhman, Saeed | -45608 | 44
105-95 | Modon Hafar Al Batin | 4979 | Modon Hafar Al Batin-LV & Control Cable # LME-8830.50 | APPROVED | No | 2024-11-18 | Abas, Mohammed Fekry | 2024-11-19 | 2024-11-19 |  |  |  | 400680.08 | 6275 | 0 | STANDARD | ALFANAR CO | SAR | 400680.08 | APPROVED |  |  | 2024-12-15 | 0 | 26 | Badhman, Saeed | -45615 | 26
105-95 | Modon Hafar Al Batin | 4980 | Modon Hafar Al Batin-LV & Control Cable # LME-9538 | APPROVED | No | 2024-11-18 | Abas, Mohammed Fekry | 2024-11-19 | 2024-11-19 |  |  |  | 101678.77 | 6275 | 0 | STANDARD | ALFANAR CO | SAR | 101678.77 | APPROVED |  |  | 2024-12-15 | 0 | 26 | Badhman, Saeed | -45615 | 26
105-95 | Modon Hafar Al Batin | 5014 | Modon Hafar Al Batin-Cable Ladder | APPROVED | No | 2024-11-21 | Abas, Mohammed Fekry | 2024-12-04 | 2024-12-04 |  |  |  | 1823.36 | 6155 | 0 | STANDARD | Power Solution Industries | SAR | 1823.36 | APPROVED |  |  | 2024-12-26 | 0 | 22 | Badhman, Saeed | -45630 | 22
105-95 | Modon Hafar Al Batin | 5236 | Modon Hafar Al Batin-ACSR Conductor | APPROVED | No | 2024-12-16 | Abas, Mohammed Fekry | 2024-12-19 | 2024-12-19 |  |  |  | 3050 | 6663 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 2500 | APPROVED |  |  | 2024-12-25 | 550 | 6 | Mohammed, Faisal Ansari | -45645 | 6
105-95 | Modon Hafar Al Batin | 5337 | Modon Hafar Al Batin-MV Cable remaining QTTY # 02 | APPROVED | No | 2025-01-02 | Abas, Mohammed Fekry | 2025-01-07 | 2025-01-07 |  |  |  | 36459.25 | 6168 | 2 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 36459.25 | APPROVED |  |  | 2025-01-14 | 0 | 7 | Mohammed, Faisal Ansari | -45664 | 7
105-95 | Modon Hafar Al Batin | 5343 | Modon Hafar Al Batin-Lighting Fixtures | APPROVED | No | 2025-01-02 | Abas, Mohammed Fekry | 2025-01-07 | 2025-01-07 |  |  |  | 110132 | 6698 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 80396 | APPROVED |  |  | 2025-01-13 | 29736 | 6 | Mohammed, Faisal Ansari | -45664 | 6
105-95 | Modon Hafar Al Batin | 5505 | Modon Hafar Al Batin-1x1000SQMM | APPROVED | No | 2025-01-21 | Abas, Mohammed Fekry | 2025-01-23 | 2025-01-23 |  |  |  | 499671 | 6769 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 468147.5 | APPROVED |  |  | 2025-01-28 | 31523.5 | 5 | Mohammed, Faisal Ansari | -45680 | 5
105-95 | Modon Hafar Al Batin | 5505 | Modon Hafar Al Batin-1x1000SQMM | APPROVED | No | 2025-01-21 | Abas, Mohammed Fekry | 2025-01-23 | 2025-01-23 |  |  |  | 499671 | 6769 | 1 | STANDARD | Riyadh Cables Group Company | SAR | 455218 | APPROVED |  |  | 2025-02-13 | 44453 | 21 | Mohammed, Faisal Ansari | -45680 | 21
105-95 | Modon Hafar Al Batin | 5688 | Modon Hafar Al Batin-Lv Cable Termination | REJECTED | No | 2025-01-27 | Ibrahim, Mahmoud Hassan Ali | 2025-01-30 | 2025-01-29 |  | 2025-01-30 |  | 133501.7 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45686 | -45686
105-95 | Modon Hafar Al Batin | 5983 | Modon Hafar Al Batin-Testing & Commisssioning (PO#6892) | APPROVED | No | 2025-02-19 | Abas, Mohammed Fekry | 2025-02-20 | 2025-02-20 |  |  | Budegt Lines 7.1, 7.2, 7.3, 7.4 & 7.7. | 1649771 | 6892 | 0 | STANDARD | Al Fanar Technical Services | SAR | 1649771 | APPROVED |  |  | 2025-02-27 | 0 | 7 | Mohammed, Faisal Ansari | -45708 | 7
105-95 | Modon Hafar Al Batin | 6031 | Modon Hafar Al Batin-MV Cable Clamps | APPROVED | No | 2025-02-24 | Abas, Mohammed Fekry | 2025-02-25 | 2025-02-25 |  |  | Line Item # 3.1.9.2. | 40550 | 6894 | 0 | STANDARD | ABDULLAH M. AL-SHAHRANI FACTORY | SAR | 32000 | APPROVED |  |  | 2025-03-02 | 8550 | 5 | Mohammed, Faisal Ansari | -45713 | 5
105-95 | Modon Hafar Al Batin | 6032 | Modon Hafar Al Batin-Clamps & Connectors | REJECTED | No | 2025-02-24 | Ibrahim, Mahmoud Hassan Ali | 2025-03-11 | 2025-02-26 |  | 2025-03-11 |  | 24475.34 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45714 | -45714
105-95 | Modon Hafar Al Batin | 6052 | Modon Hafar Al Batin-For HVAC Balance amount | REJECTED | No | 2025-02-25 | Ibrahim, Mahmoud Hassan Ali | 2025-02-27 | 2025-02-26 |  | 2025-02-27 |  | 155000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45714 | -45714
105-95 | Modon Hafar Al Batin | 6154 | Modon Hafar Al Batin-Switches & Sockets | APPROVED | No | 2025-03-11 | Abas, Mohammed Fekry | 2025-03-13 | 2025-03-16 |  |  | Line Item # 4.3 | 176456.8 | 6896 | 0 | STANDARD | Tawasul International Trad.Est. | SAR | 176456.8 | APPROVED |  |  | 2025-03-23 | 0 | 7 | Mohammed, Faisal Ansari | -45732 | 7
105-95 | Modon Hafar Al Batin | 6155 | Modon Hafar Al Batin-Clamps & Connectors | REJECTED | No | 2025-03-11 | Ibrahim, Mahmoud Hassan Ali | 2025-03-17 | 2025-03-12 |  | 2025-03-17 |  | 24475.34 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45728 | -45728
105-95 | Modon Hafar Al Batin | 6178 | Modon Hafar Al Batin-Conduit & Fitting P.O # 6793 | APPROVED | No | 2025-03-12 | Abas, Mohammed Fekry | 2025-03-13 | 2025-03-16 |  |  | Line Item # 4.3. | 132000 | 6793 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 132000 | APPROVED |  |  | 2025-03-23 | 0 | 7 | Mohammed, Faisal Ansari | -45732 | 7
105-95 | Modon Hafar Al Batin | 6263 | Modon Hafar Al Batin-HVAC | APPROVED | No | 2025-03-25 | Abas, Mohammed Fekry | 2025-03-25 | 2025-03-26 |  |  | Line Item # 3.2.1. | 1980000 | 6708 | 0 | STANDARD | Ramz Alataa Company for Trading | SAR | 1980000 | APPROVED |  |  | 2025-04-09 | 0 | 14 | Mohammed, Faisal Ansari | -45742 | 14
105-95 | Modon Hafar Al Batin | 6266 | Modon Hafar Al Batin-Clamps & Connectors | APPROVED | No | 2025-03-25 | Abas, Mohammed Fekry | 2025-03-25 | 2025-03-26 |  |  | Line Item # 3.1.3.2 | 24475.34 | 6895 | 0 | STANDARD | Arruti Subestaciones , S.A.U | EUR | 24443.24 | APPROVED |  |  | 2025-04-07 | 32.1 | 12 | Mohammed, Faisal Ansari | -45742 | 12
105-95 | Modon Hafar Al Batin | 6280 | Modon Hafar Al Batin-Termination Kit | APPROVED | No | 2025-03-26 | Abas, Mohammed Fekry | 2025-03-27 | 2025-03-27 |  |  | Item Line # 3.1.3.2. | 77100 | 6983 | 0 | STANDARD | Bright Wire Company | SAR | 77100 | APPROVED |  |  | 2025-04-13 | 0 | 17 | Mohammed, Faisal Ansari | -45743 | 17
105-95 | Modon Hafar Al Batin | 6299 | Modon Hafar Al Batin-LV ACDC Cables | REJECTED | No | 2025-04-08 | Asif, Mohammed | 2025-04-08 |  |  | 2025-04-08 | lv acdc cable | 913758.92 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | 0 | 0
105-95 | Modon Hafar Al Batin | 6306 | Modon Hafar Al Batin-LC AVDC Cables | APPROVED | No | 2025-04-08 | Abas, Mohammed Fekry | 2025-04-09 | 2025-04-09 |  |  | 3.1.9.3, LV AC DC CABLE | 913759 | 6763 | 0 | STANDARD | Hesham El-Sewedy Trading Co. LTD. | SAR | 913759 | APPROVED |  |  | 2025-04-22 | 0 | 13 | Mohammed, Faisal Ansari | -45756 | 13
105-95 | Modon Hafar Al Batin | 6327 | Modon Hafar Al Batin-Tools & material | REJECTED | No | 2025-04-13 | Ibrahim, Mahmoud Hassan Ali | 2025-04-16 | 2025-04-14 |  | 2025-04-16 |  | 105000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45761 | -45761
105-95 | Modon Hafar Al Batin | 6340 | Modon Hafar Al Batin-Fuel for Site | APPROVED | No | 2025-04-15 | Abas, Mohammed Fekry | 2025-04-16 | 2025-04-17 |  |  | Line Item # 6.1.4.2. | 221634.49 | 7178 | 0 | STANDARD | New Innovation Company LtD | SAR | 221634.49 | APPROVED |  |  | 2025-04-24 | 0 | 7 | Abuhammad, Samir | -45764 | 7
105-95 | Modon Hafar Al Batin | 6361 | Modon Hafar Al Batin-Tools & Material for Installation | APPROVED | No | 2025-04-17 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-21 |  |  | Line Item 3.1.3.2. for Electrical Equipments Installation. | 110000 | 7275 | 0 | STANDARD | Global Arab One Trading Est (S) | SAR | 102548.35 | APPROVED |  |  | 2025-05-25 | 7451.65 | 34 | Akhtar, Farhan | -45768 | 34
105-95 | Modon Hafar Al Batin | 6491 | Modon Hafar Al Batin-Dilo Machine | APPROVED | No | 2025-05-01 | Abas, Mohammed Fekry | 2025-05-04 | 2025-05-04 |  |  | Line Item # 6.1.6.7 | 125200 | 7236 | 0 | STANDARD | Jahaz Ayed Al-Rashidi and Partner for Trad and count | SAR | 105150 | APPROVED |  |  | 2025-05-29 | 20050 | 25 | Akhtar, Farhan | -45781 | 25
105-95 | Modon Hafar Al Batin | 6499 | Modon Hafar Al Batin-scaffolding for Electrical Activities | REJECTED | No | 2025-05-04 | Ibrahim, Mahmoud Hassan Ali | 2025-05-11 | 2025-05-04 |  | 2025-05-11 |  | 50000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45781 | -45781
105-95 | Modon Hafar Al Batin | 6508 | Modon Hafar Al Batin-RTV Coating | APPROVED | No | 2025-05-05 | Abas, Mohammed Fekry | 2025-05-06 | 2025-05-06 |  |  | Line Item # 4.7 | 120000 | 7362 | 0 | STANDARD | SAUDI CONDUIT COATING CO. (S3C) | SAR | 64888 | APPROVED |  |  | 2025-06-29 | 55112 | 54 | Mohammed, Faisal Ansari | -45783 | 54
105-95 | Modon Hafar Al Batin | 6695 | Modon Hafar Al Batin-Free Standing A/C Units. | APPROVED | No | 2025-05-25 | Abas, Mohammed Fekry | 2025-05-27 | 2025-05-27 |  |  | Line Item # 6.1.4.9. | 135000 | 7240 | 0 | STANDARD | Voltage Professionals contracting establishment | SAR | 134400 | APPROVED |  |  | 2025-06-30 | 600 | 34 | Mohammed, Faisal Ansari | -45804 | 34
105-95 | Modon Hafar Al Batin | 6810 | Modon Hafar Al Batin-Dilo Machine, for PO # 02 | APPROVED | No | 2025-06-16 | Abas, Mohammed Fekry | 2025-06-19 | 2025-06-19 |  |  | LINE ITEM 6.1.6.7 | 15000 | 7236 | 1 | STANDARD | Jahaz Ayed Al-Rashidi and Partner for Trad and count | SAR | 8000 | APPROVED |  |  | 2025-07-14 | 7000 | 25 | Akhtar, Farhan | -45827 | 25
105-95 | Modon Hafar Al Batin | 7056 | Modon Hafar Al Batin-Lugs & Glands (PO# 7372-HV1406) | APPROVED | No | 2025-07-10 | Abas, Mohammed Fekry | 2025-07-10 | 2025-07-12 |  |  | budget line 3.1.9.3 | 44000 | 7372 | 0 | STANDARD | Aswar Electrical Trading Est. | SAR | 44000 | APPROVED |  |  | 2025-07-15 | 0 | 3 | Mohammed, Faisal Ansari | -45850 | 3
105-95 | Modon Hafar Al Batin | 7058 | Modon Hafar Al Batin-Additional PR for PO# 7240 Change Order | APPROVED | No | 2025-07-10 | Abas, Mohammed Fekry | 2025-07-10 | 2025-07-12 |  |  | Budget line 6.1.4.9 | 7290 | 7240 | 1 | STANDARD | Voltage Professionals contracting establishment | SAR | 7290 | APPROVED |  |  | 2025-07-18 | 0 | 6 | Mohammed, Faisal Ansari | -45850 | 6
105-95 | Modon Hafar Al Batin | 7236 | Modon Hafar Al Batin-Site Electrical Materials-(PO# 7545-HV1406) | APPROVED | No | 2025-07-29 | Abas, Mohammed Fekry | 2025-07-29 | 2025-07-29 |  |  | Budget line 3.1.9.3 | 139725 | 7545 | 0 | STANDARD | Roadwey Trading Company | SAR | 139725 | APPROVED |  |  | 2025-09-04 | 0 | 37 | Mohammed, Faisal Ansari | -45867 | 37
105-95 | Modon Hafar Al Batin | 7633 | GIB Steel Support Structure (Approved Manual PO# 7483) | APPROVED | No | 2025-09-03 | Abas, Mohammed Fekry | 2025-09-07 | 2025-09-08 |  |  | Budget line 4.5-Gantry & Dead End Steel Structures | 0 | 7483 | 0 | STANDARD | Fursan Construction Industry Factory Industry Factory | SAR | 20165.6 | APPROVED |  |  | 2025-09-24 | -20165.6 | 16 | Hegazy, Ayman | -45908 | 16
105-95 | Modon Hafar Al Batin | 7695 | Supply, Installation, Splicing, Testing & Commissioning of FO Cables | RETURNED | No | 2025-09-10 | Muaz, Alaa | 2025-10-15 | 2025-09-16 | 2025-10-15 |  | There is an issue while trying to upload the PO on Oracle. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -45916 | -45916
105-95 | Modon Hafar Al Batin | 7699 | Oil Filtration for 115/33kV, 80/100MVA Transformer | APPROVED | No | 2025-09-09 | Abas, Mohammed Fekry | 2025-12-01 | 2025-12-01 | 2025-10-15 |  | No Budget. | 0 | 7802 | 0 | STANDARD | MASEERAT AL NAMA CONT.EST. | SAR | 55500 | APPROVED |  |  | 2025-12-07 | -55500 | 6 | Mohammed, Faisal Ansari | -45992 | 6
105-95 | Modon Hafar Al Batin | 7713 | Additional PR for PO# 7372 Change Order | APPROVED | No | 2025-09-10 | Abas, Mohammed Fekry | 2025-09-14 | 2025-09-16 |  |  | budget line 3.1.9.3 | 0 | 7372 | 1 | STANDARD | Aswar Electrical Trading Est. | SAR | 5500 | APPROVED |  |  | 2025-09-25 | -5500 | 9 | Mohammed, Faisal Ansari | -45916 | 9
105-95 | Modon Hafar Al Batin | 7881 | PR for PO# 7462 - Supply & Installation of Raised Floor Materials | REJECTED | No | 2025-10-02 | Ibrahim, Mahmoud Hassan Ali | 2025-10-02 | 2025-10-02 |  | 2025-10-02 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45932 | -45932
105-95 | Modon Hafar Al Batin | 7967 | PR for Tamim PO# 7165 (Remaining Civil & Architectural Works) | APPROVED | No | 2025-10-15 | Abas, Mohammed Fekry | 2025-10-19 | 2025-10-19 |  |  | Budget line 4.1 & 4.2 | 0 | 7165 | 0 | STANDARD | Tamim Company (PVT) LTD | SAR | 5682850 | APPROVED |  |  | 2025-10-20 | -5682850 | 1 | Tananeh, Khalid Jamal | -45949 | 1
105-95 | Modon Hafar Al Batin | 7967 | PR for Tamim PO# 7165 (Remaining Civil & Architectural Works) | APPROVED | No | 2025-10-15 | Abas, Mohammed Fekry | 2025-10-19 | 2025-10-19 |  |  | Budget line 4.1 & 4.2 | 0 | 7165 | 1 | STANDARD | Tamim Company (PVT) LTD | SAR | 2798343.7 | APPROVED |  |  | 2025-12-23 | -2798343.7 | 65 | Tananeh, Khalid Jamal | -45949 | 65
105-95 | Modon Hafar Al Batin | 8141 | PR for Additional Clamp & Connector (PO# 6895) | APPROVED | No | 2025-11-05 | Abas, Mohammed Fekry | 2025-11-06 | 2025-11-09 |  |  | Budget line 3.1.3.2 | 0 | 7880 | 0 | STANDARD | Arruti Subestaciones , S.A.U | EUR | 6301.68 | APPROVED |  |  | 2025-11-12 | -6301.68 | 3 | Mohammed, Faisal Ansari | -45970 | 3
105-95 | Modon Hafar Al Batin | 8180 | PO# 7543 PDS | APPROVED | No | 2025-11-11 | Abas, Mohammed Fekry | 2025-11-12 | 2025-11-13 |  |  | Budget line 3.1.1.3 | 0 | 7543 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 385000 | APPROVED | 2026-01-12 | 2026-01-19 | 2026-01-21 | -161000 | 69 | Muaz, Alaa | 67 | 69
105-95 | Modon Hafar Al Batin | 8227 | PR for PO# 7462 - Supply & Installation of Raised Floor Materials (Avayo) | APPROVED | No | 2025-11-16 | Abas, Mohammed Fekry | 2025-11-18 | 2025-11-19 |  |  | Budget line 4.1 | 0 | 7462 | 0 | STANDARD | AVAYO Middle East Co. Ltd | SAR | 79050 | APPROVED |  |  | 2025-12-03 | -79050 | 14 | Hegazy, Ayman | -45980 | 14
105-95 | Modon Hafar Al Batin | 8228 | Oil Filtration for 115/33kV, 80/100MVA Transformer (PO# 7802 | RETURNED | No | 2025-11-18 | Mohammed, Faisal Ansari | 2025-11-23 | 2025-11-23 | 2025-11-23 |  | Shows exceeding the budget. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45984 | -45984
105-95 | Modon Hafar Al Batin | 8350 | backfilling civil works | APPROVED | No | 2025-11-26 | Abas, Mohammed Fekry | 2025-12-01 | 2025-12-02 |  |  |  | 0 | 7996 | 0 | STANDARD | The Giant Dam Contracting Est. | SAR | 142680 | APPROVED | 2025-12-15 | 2026-01-14 | 2026-01-20 | -142680 | 49 | Tananeh, Khalid Jamal | 43 | 49
105-95 | Modon Hafar Al Batin | 8363 | Civil Works | APPROVED | No | 2025-11-26 | Abas, Mohammed Fekry | 2025-12-01 | 2025-12-02 |  |  |  | 0 | 8008 | 0 | STANDARD | Mashael Aseer Contracting Company. | SAR | 721000 | APPROVED | 2025-12-25 | 2026-01-01 | 2026-01-06 | -721000 | 35 | Tananeh, Khalid Jamal | 30 | 35
105-95 | Modon Hafar Al Batin | 8364 | Civil Works | APPROVED | No | 2025-11-26 | Abas, Mohammed Fekry | 2025-12-01 | 2025-12-02 |  |  |  | 0 | 8020 | 0 | STANDARD | Saden Specialized Company for Geological Consulting | SAR | 70830 | APPROVED | 2025-12-30 | 2026-01-01 | 2026-01-06 | -70830 | 35 | Tananeh, Khalid Jamal | 30 | 35
105-95 | Modon Hafar Al Batin | 8373 | Steel Monopole Gantry | RETURNED | No | 2025-11-27 | Tananeh, Khalid Jamal | 2025-12-15 | 2025-12-02 | 2025-12-15 |  | Return PR 8373 Due to Budget Exceedance as per email sent to Mr. Raza in Mon 15/12/2025 9:22 AM | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45993 | -45993
105-95 | Modon Hafar Al Batin | 8374 | Plumbing Materials | APPROVED | No | 2025-11-27 | Abas, Mohammed Fekry | 2025-12-01 | 2025-12-02 |  |  | Line item 1 - Plumbing Materials | 0 | 8013 | 0 | STANDARD | SARAH PRIME COMPANY | SAR | 160887 | APPROVED | 2025-12-28 | 2026-01-01 | 2026-01-15 | -160887 | 44 | Tananeh, Khalid Jamal | 30 | 44
105-95 | Modon Hafar Al Batin | 8422 | IFC Drawings, Printing, Scanning & Binding | IN PROCESS | No | 2025-12-02 | Khan, Muhammad Safdar | 2025-12-03 | 2025-12-02 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45993 | -45993
105-95 | Modon Hafar Al Batin | 8435 | Transformer Grating | IN PROCESS | No | 2025-12-03 | Khan, Muhammad Safdar | 2025-12-07 | 2025-12-03 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45994 | -45994
105-95 | Modon Hafar Al Batin | 8470 | Activation of Optional Scope for PO# 8502 | RETURNED | No | 2025-12-07 | Mohammed, Faisal Ansari | 2025-12-29 | 2025-12-09 | 2025-12-29 |  | Shows budget exceeded when taking the PO. Kindly resolve. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46000 | -46000
105-95 | Modon Hafar Al Batin | 8511 | PR for Manholes | RETURNED | No | 2025-12-11 | Tananeh, Khalid Jamal | 2026-01-08 | 2025-12-23 | 2026-01-08 |  | return as per my email to Project Manager Qaiser and Mr. Mohamed Kharbouch on Tue 12/30/2025 at 11:49 AM and the reply received from Mr. Mohamed Kharbouch on Tue 1/6/2026 at 4:24 PM." | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -46014 | -46014
105-95 | Modon Hafar Al Batin | 8596 | Termination Kits for MV Cables (PO# 8028) | APPROVED | No | 2025-12-28 | Abas, Mohammed Fekry | 2025-12-30 | 2026-01-01 |  |  | Budget line 3.1.9.2 - MV Cable with Termination&ACSR | 0 | 8028 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 48000 | APPROVED | 2026-01-01 | 2026-01-06 | 2026-01-06 | -48000 | 5 | Mohammed, Faisal Ansari | 5 | 5
105-95 | Modon Hafar Al Batin | 8620 | Transport of Power Transformer (PO# 15011) | APPROVED | No | 2026-01-01 | Abas, Mohammed Fekry | 2026-01-04 | 2026-01-06 |  |  | Budget line 10.8 | 0 | 15011 | 0 | STANDARD | MOHAMMED HAMAD AL-AHMADE FOR TRADING AND CONSTRACTION | SAR | 275000 | INCOMPLETE |  |  |  | -275000 | 26 | Badhman, Saeed | -46028 | -46028
105-95 | Modon Hafar Al Batin | 8620 | Transport of Power Transformer (PO# 15011) | APPROVED | No | 2026-01-01 | Abas, Mohammed Fekry | 2026-01-04 | 2026-01-06 |  |  | Budget line 10.8 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -46028 | -46028
105-95 | Modon Hafar Al Batin | 8621 | Chain Link Fence | APPROVED | No | 2026-01-01 | Abas, Mohammed Fekry | 2026-01-04 | 2026-01-06 |  |  | Budget line 4.1 | 0 | 15029 | 0 | STANDARD | Fursan Construction Industry Factory Industry Factory | SAR | 345300 | APPROVED | 2026-01-11 | 2026-01-14 | 2026-01-21 | -345300 | 15 | Abdelraouf, Islam ِAdel Hanafy | 8 | 15
105-95 | Modon Hafar Al Batin | 8677 | PR for Additional LV Power Cable | APPROVED | No | 2026-01-11 | Abas, Mohammed Fekry | 2026-01-14 | 2026-01-14 |  |  | 3.1.9.3-LV Cable with Termination | 0 | 7827 | 0 | STANDARD | Hesham El-Sewedy Trading Co. LTD. | SAR | 448567.05 | APPROVED | 2026-01-14 | 2026-01-19 | 2026-01-22 | -448567.05 | 8 | Mohammed, Faisal Ansari | 5 | 8
105-95 | Modon Hafar Al Batin | 8678 | PR for Additional Control Cables | APPROVED | No | 2026-01-11 | Abas, Mohammed Fekry | 2026-01-14 | 2026-01-14 |  |  | Budget line 3.1.9.4-Control&F.O Cable | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -46036 | -46036
105-95 | Modon Hafar Al Batin | 8749 | PR for Waterproofing Activities | APPROVED | No | 2026-01-22 | Abas, Mohammed Fekry | 2026-01-27 | 2026-01-28 |  |  | Budget line 4.1 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -46050 | -46050
105-95 | Modon Hafar Al Batin | 8773 | PR for Communication Handholes | APPROVED | No | 2026-01-22 | Abas, Mohammed Fekry | 2026-01-27 | 2026-01-28 |  |  | Budget line 4.1 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -46050 | -46050
105-95 | Modon Hafar Al Batin | 8774 | PR for Balance of aluminum flashing metal with sealant | APPROVED | No | 2026-01-22 | Abas, Mohammed Fekry | 2026-01-27 | 2026-01-28 |  |  | Budget line 4.1 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -46050 | -46050
105-96 | Modon Aseer S/S | 1591 | Modon Aseer S/S-132kV GIS | RETURNED | No | 2023-10-14 | Kumar, Mr. Ranjan | 2024-04-04 | 2023-10-17 | 2024-04-04 |  | PR 2843 & 2844 already received and GIS PO issued 4508 & 4509 | 12520800 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45216 | -45216
105-96 | Modon Aseer S/S | 1592 | Modon Aseer S/S-Power Transformer- Asser Modon | APPROVED | No | 2023-10-14 | Abas, Mohammed Fekry | 2023-10-15 | 2023-10-17 |  |  |  | 15123000 | 5018 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 14852750 | APPROVED |  |  | 2024-01-30 | 270250 | 105 | Kumar, Mr. Ranjan | -45216 | 105
105-96 | Modon Aseer S/S | 1593 | Modon Aseer S/S-Engineering & design- Asser Modon | APPROVED | No | 2023-10-14 | Abas, Mohammed Fekry | 2023-10-15 | 2023-10-17 |  |  |  | 500000 | 4696 | 0 | STANDARD | Design Tech Engineering Consultants Company /Simplified | SAR | 405000 | APPROVED |  |  | 2023-11-12 | 95000 | 26 | Kumar, Mr. Ranjan | -45216 | 26
105-96 | Modon Aseer S/S | 1594 | Modon Aseer S/S-33kV MV Switchgear- Asser Modon | APPROVED | No | 2023-10-14 | Abas, Mohammed Fekry | 2023-10-15 | 2023-10-17 |  |  |  | 8000000 | 4665 | 0 | STANDARD | ALFANAR CO | SAR | 8000000 | APPROVED |  |  | 2023-10-26 | 0 | 9 | Akhtar, Farhan | -45216 | 9
105-96 | Modon Aseer S/S | 1599 | Modon Aseer S/S-Soil Investigation-Asser Modon | APPROVED | No | 2023-10-15 | Abas, Mohammed Fekry | 2023-10-19 | 2023-10-19 |  |  |  | 90000 | 4695 | 0 | STANDARD | International Agent Commercial Company(S) | SAR | 20095 | APPROVED |  |  | 2023-11-07 | 69905 | 19 | Kumar, Mr. Ranjan | -45218 | 19
105-96 | Modon Aseer S/S | 1603 | Modon Aseer S/S-NGR- Asser Modon | RETURNED | No | 2023-10-17 | Kumar, Mr. Ranjan | 2023-12-18 | 2023-10-19 | 2023-12-18 |  | PR value is less than PO value | 75000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45218 | -45218
105-96 | Modon Aseer S/S | 1611 | Modon Aseer S/S-Telecommunocation System -Aseer Modon | APPROVED | No | 2023-10-19 | Abas, Mohammed Fekry | 2023-10-22 | 2023-10-22 |  |  |  | 4300000 | 4951 | 0 | STANDARD | ALFANAR CO | SAR | 4000000 | APPROVED |  |  | 2024-03-10 | 300000 | 140 | Mohammed, Faisal Ansari | -45221 | 140
105-96 | Modon Aseer S/S | 1612 | Modon Aseer S/S-AC & DC DB 400V/110V 3ph with Sub Panels including reomte ends- Asser Modon | APPROVED | No | 2023-10-19 | Abas, Mohammed Fekry | 2023-10-22 | 2023-10-22 |  |  |  | 798000 | 4674 | 0 | STANDARD | ALFANAR CO | SAR | 798000 | APPROVED |  |  | 2023-11-05 | 0 | 14 | Mohammed, Faisal Ansari | -45221 | 14
105-96 | Modon Aseer S/S | 1613 | Modon Aseer S/S-Cyber security- Asser Modon | APPROVED | No | 2023-10-19 | Abas, Mohammed Fekry | 2023-10-22 | 2023-10-22 |  |  |  | 1600000 | 4673 | 0 | STANDARD | ALFANAR CO | SAR | 1350000 | APPROVED |  |  | 2023-11-05 | 250000 | 14 | Mohammed, Faisal Ansari | -45221 | 14
105-96 | Modon Aseer S/S | 1614 | Modon Aseer S/S-Station Transformers- Asser Modon | APPROVED | No | 2023-10-19 | Abas, Mohammed Fekry | 2023-10-22 | 2023-10-22 |  |  |  | 202000 | 4670 | 0 | STANDARD | ALFANAR CO | SAR | 202000 | APPROVED |  |  | 2023-10-26 | 0 | 4 | Mohammed, Faisal Ansari | -45221 | 4
105-96 | Modon Aseer S/S | 1615 | Modon Aseer S/S-Control, Protection & SAS-Asser Modon | APPROVED | No | 2023-10-19 | Abas, Mohammed Fekry | 2023-10-22 | 2023-10-22 |  |  |  | 7200000 | 4671 | 0 | STANDARD | ALFANAR CO | SAR | 7200000 | APPROVED |  |  | 2023-10-26 | 0 | 4 | Mohammed, Faisal Ansari | -45221 | 4
105-96 | Modon Aseer S/S | 1897 | Modon Aseer S/S-Genset for Site Mobilization | APPROVED | No | 2023-12-05 | Abas, Mohammed Fekry | 2023-12-07 | 2023-12-10 |  |  |  | 250000 | 4809 | 0 | STANDARD | Mohammed A. AlFaddaghi & Partners | SAR | 250000 | APPROVED |  |  | 2024-01-29 | 0 | 50 | Badhman, Saeed | -45270 | 50
105-96 | Modon Aseer S/S | 1988 | Modon Aseer S/S-Capacitor banks- Asser Modon | APPROVED | No | 2023-12-18 | Abas, Mohammed Fekry | 2024-04-03 | 2024-04-04 | 2024-03-25 |  | PR value is less than the PO value. Please change the PR value to SAR. 2,687,000 to proceed further | 2600000 | 4881 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 2587500 | APPROVED |  |  | 2024-05-16 | 12500 | 42 | Mohammed, Faisal Ansari | -45386 | 42
105-96 | Modon Aseer S/S | 2007 | Modon Aseer S/S-Site Mobilization- Asser Modon | APPROVED | No | 2023-12-18 | Abas, Mohammed Fekry | 2023-12-20 | 2023-12-20 |  |  |  | 998000 | 4910 | 0 | STANDARD | ABDUL JABBAR AHMAD ALI SHARAHILI CONTRACTING EST. (AJASCO) | SAR | 998000 | APPROVED |  |  | 2024-01-01 | 0 | 12 | Mohammed, Faisal Ansari | -45280 | 12
105-96 | Modon Aseer S/S | 2153 | Modon Aseer S/S-Safety Requirement for site | RETURNED | No | 2024-01-10 | Akhtar, Farhan | 2024-06-03 | 2024-01-11 | 2024-06-03 |  | PO already Issued | 110000 | 5401 | 0 | STANDARD | Versatile Advanced Limited Company. | SAR | 59266.85 | APPROVED |  |  | 2024-05-05 | 50733.15 |  | Akhtar, Farhan | -45302 | 115
105-96 | Modon Aseer S/S | 2153 | Modon Aseer S/S-Safety Requirement for site | RETURNED | No | 2024-01-10 | Akhtar, Farhan | 2024-06-03 | 2024-01-11 | 2024-06-03 |  | PO already Issued | 5000 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45302 | -45302
105-96 | Modon Aseer S/S | 2528 | Modon Aseer S/S-120kV Surge arrester - Modon Asir SS | APPROVED | No | 2024-02-11 | Abas, Mohammed Fekry | 2024-02-11 | 2024-02-12 |  |  |  | 74508 | 4992 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 74508 | APPROVED |  |  | 2024-03-17 | 0 | 34 | Kumar, Mr. Ranjan | -45334 | 34
105-96 | Modon Aseer S/S | 2587 | Modon Aseer S/S-ESIA | APPROVED | No | 2024-02-18 | Abas, Mohammed Fekry | 2024-02-20 | 2024-02-21 |  |  |  | 18000 | 5105 | 0 | STANDARD | Abnia Environmental Consultants Est. | SAR | 18000 | APPROVED |  |  | 2024-02-28 | 0 | 7 | Mohammed, Faisal Ansari | -45343 | 7
105-96 | Modon Aseer S/S | 2589 | Modon Aseer S/S-Civil & Structure Works - Subcontracting | REJECTED | No | 2024-02-18 | Khan, Muhammad Safdar | 2024-02-19 | 2024-02-18 |  | 2024-02-20 |  | 13916947 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45340 | -45340
105-96 | Modon Aseer S/S | 2677 | Modon Aseer S/S-Civil Subcontractor | INCOMPLETE | No |  | Khalid, Saber Mohammed | 2024-02-25 |  |  |  |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-96 | Modon Aseer S/S | 2678 | Modon Aseer S/S-Civil Subcontractor | REJECTED | No | 2024-02-25 | Khalid, Saber Mohammed | 2024-07-21 | 2024-02-28 | 2024-06-30 | 2024-07-21 | It was returned as requested by the project manager, Engineer Saber, due to a change in Budget value | 11000000 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45350 | -45350
105-96 | Modon Aseer S/S | 2704 | Modon Aseer S/S-Excavation Work | APPROVED | No | 2024-02-27 | Abas, Mohammed Fekry | 2024-02-28 | 2024-02-28 |  |  |  | 48600 | 5263 | 0 | STANDARD | Aryaf Abha Company | SAR | 37800 | APPROVED |  |  | 2024-03-31 | 10800 | 32 | Mohammed, Faisal Ansari | -45350 | 32
105-96 | Modon Aseer S/S | 2996 | Modon Aseer S/S-Diesel for generator | APPROVED | No | 2024-04-04 | Abas, Mohammed Fekry | 2024-04-07 | 2024-04-07 |  |  |  | 36412.82 | 5313 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 36412.82 | APPROVED |  |  | 2024-05-08 | 0 | 31 | Badhman, Saeed | -45389 | 31
105-96 | Modon Aseer S/S | 2996 | Modon Aseer S/S-Diesel for generator | APPROVED | No | 2024-04-04 | Abas, Mohammed Fekry | 2024-04-07 | 2024-04-07 |  |  |  | 36412.82 | 5313 | 1 | STANDARD | Talaea Alahlam Trading Company | SAR | 8147.78 | REQUIRES REAPPROVAL |  |  |  | 28265.05 | 665 | Badhman, Saeed | -45389 | -45389
105-96 | Modon Aseer S/S | 3237 | Modon Aseer S/S-OHT Crane | REJECTED | No | 2024-05-01 | Issa, Amr Ali | 2024-05-12 | 2024-05-01 |  | 2024-05-12 |  | 180000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45413 | -45413
105-96 | Modon Aseer S/S | 3359 | Modon Aseer S/S-Battery & Chargers | APPROVED | No | 2024-05-09 | Abas, Mohammed Fekry | 2024-05-16 | 2024-05-17 |  |  |  | 689000 | 5756 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 464000 | APPROVED |  |  | 2024-07-15 | 225000 | 59 | Mohammed, Faisal Ansari | -45429 | 59
105-96 | Modon Aseer S/S | 3387 | Modon Aseer S/S-Crane | APPROVED | No | 2024-05-12 | Abas, Mohammed Fekry | 2024-05-13 | 2024-05-14 |  |  |  | 170000 | 5573 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 138500 | APPROVED |  |  | 2024-06-06 | 31500 | 23 | Mohammed, Faisal Ansari | -45426 | 23
105-96 | Modon Aseer S/S | 3665 | Modon Aseer S/S-Fire System | REJECTED | No | 2024-06-23 | Khalid, Saber Mohammed | 2024-07-25 | 2024-06-25 | 2024-07-18 | 2024-07-25 | PR value is less than the PO value. Please raise new PR with value SAR. 2,150,000/-. | 1900000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45468 | -45468
105-96 | Modon Aseer S/S | 3775 | Modon Aseer S/S-Grounding Material | REJECTED | No | 2024-07-07 | Khalid, Saber Mohammed | 2024-07-17 | 2024-07-11 | 2024-07-15 | 2024-07-17 | PR value is less than the PO value. | 50000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45484 | -45484
105-96 | Modon Aseer S/S | 3826 | Modon Aseer S/S-Security System | REJECTED | No | 2024-07-11 | Khalid, Saber Mohammed | 2024-07-11 |  |  | 2024-07-11 |  | 1900000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-96 | Modon Aseer S/S | 3827 | Modon Aseer S/S-Security System CCTV | REJECTED | No | 2024-07-11 | Khalid, Saber Mohammed | 2024-08-04 | 2024-07-16 | 2024-07-28 | 2024-08-04 | Please raise PR when the subject for security is concluded with SEC. | 700000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45489 | -45489
105-96 | Modon Aseer S/S | 3828 | Modon Aseer S/S-HVAC System | REJECTED | No | 2024-07-11 | Khalid, Saber Mohammed | 2024-12-30 | 2024-12-03 |  | 2024-12-30 |  | 1920000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45629 | -45629
105-96 | Modon Aseer S/S | 3829 | Modon Aseer S/S-MV Cables | REJECTED | No | 2024-07-11 | Khalid, Saber Mohammed | 2024-07-23 | 2024-07-16 | 2024-07-22 | 2024-07-23 | Please adjust QTY, Prices | 450000 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45489 | -45489
105-96 | Modon Aseer S/S | 3830 | Modon Aseer S/S-LV Cables | REJECTED | No | 2024-07-11 | Khalid, Saber Mohammed | 2024-08-14 | 2024-07-16 | 2024-08-14 | 2024-08-14 | Please raise correct items and with the shared list prices | 750000 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45489 | -45489
105-96 | Modon Aseer S/S | 3854 | Modon Aseer S/S-bare copper conductor and Y/G | APPROVED | No | 2024-07-11 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 508000 | 5781 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 507930 | APPROVED |  |  | 2024-07-25 | 70 | 9 | Mohammed, Faisal Ansari | -45489 | 9
105-96 | Modon Aseer S/S | 3854 | Modon Aseer S/S-bare copper conductor and Y/G | APPROVED | No | 2024-07-11 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 508000 | 5781 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 466633 | APPROVED |  |  | 2024-07-31 | 41367 | 15 | Mohammed, Faisal Ansari | -45489 | 15
105-96 | Modon Aseer S/S | 3898 | Modon Aseer S/S-OH Conductor ACSR | APPROVED | No | 2024-07-15 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 7950 | 5818 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 7500 | APPROVED |  |  | 2024-07-29 | 450 | 13 | Mohammed, Faisal Ansari | -45489 | 13
105-96 | Modon Aseer S/S | 3944 | Modon Aseer S/S-Earthing Material | APPROVED | No | 2024-07-17 | Abas, Mohammed Fekry | 2024-07-18 | 2024-07-18 |  |  |  | 53000 | 5845 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 51240 | APPROVED |  |  | 2024-07-23 | 1760 | 5 | Mohammed, Faisal Ansari | -45491 | 5
105-96 | Modon Aseer S/S | 3955 | Modon Aseer S/S-Medium Voltage Termination | APPROVED | No | 2024-07-18 | Abas, Mohammed Fekry | 2024-07-23 | 2024-07-23 |  |  |  | 80424 | 5847 | 1 | STANDARD | Nima Arabia Company Limited | SAR | 33166 | APPROVED |  |  | 2025-01-07 | 47258 | 168 | Mohammed, Faisal Ansari | -45496 | 168
105-96 | Modon Aseer S/S | 3955 | Modon Aseer S/S-Medium Voltage Termination | APPROVED | No | 2024-07-18 | Abas, Mohammed Fekry | 2024-07-23 | 2024-07-23 |  |  |  | 97096 | 5847 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 97056 | APPROVED |  |  | 2024-07-31 | 40 | 8 | Mohammed, Faisal Ansari | -45496 | 8
105-96 | Modon Aseer S/S | 3957 | Modon Aseer S/S-Medium Voltaget termination FAT test (following PR 3955) | APPROVED | No | 2024-07-18 | Abas, Mohammed Fekry | 2024-07-23 | 2024-07-24 |  |  |  | 10000 | 5847 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 8250 | APPROVED |  |  | 2024-07-31 | 1750 | 7 | Mohammed, Faisal Ansari | -45497 | 7
105-96 | Modon Aseer S/S | 3957 | Modon Aseer S/S-Medium Voltaget termination FAT test (following PR 3955) | APPROVED | No | 2024-07-18 | Abas, Mohammed Fekry | 2024-07-23 | 2024-07-24 |  |  |  | 10000 | 5847 | 1 | STANDARD | Nima Arabia Company Limited | SAR | 5500 | APPROVED |  |  | 2025-01-07 | 4500 | 167 | Mohammed, Faisal Ansari | -45497 | 167
105-96 | Modon Aseer S/S | 3973 | Modon Aseer S/S-Shielding Mast | REJECTED | No | 2024-07-21 | Khalid, Saber Mohammed | 2024-09-18 | 2024-07-23 | 2024-09-18 | 2024-09-18 | returned to be urgent update and resend back as per the issued PO BOQ lined items | 80000 | [5 empty] | 0 |  |  |  |  | 0 |  | Eliwa, Mahmoud | -45496 | -45496
105-96 | Modon Aseer S/S | 3997 | Modon Aseer S/S-MV Cables | APPROVED | No | 2024-07-24 | Abas, Mohammed Fekry | 2024-07-25 | 2024-07-25 |  |  |  | 753176.8 | 5899 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 700649.27 | APPROVED |  |  | 2024-10-09 | 52527.53 | 76 | Badhman, Saeed | -45498 | 76
105-96 | Modon Aseer S/S | 4016 | Modon Aseer S/S-Fire Fighting | APPROVED | No | 2024-07-25 | Abas, Mohammed Fekry | 2024-07-29 | 2024-07-29 |  |  |  | 2072000 | 5859 | 0 | STANDARD | Conexus Contracting Company | SAR | 2072000 | APPROVED |  |  | 2024-10-19 | 0 | 82 | Mohammed, Faisal Ansari | -45502 | 82
105-96 | Modon Aseer S/S | 4017 | Modon Aseer S/S-Fire Fighting - Control and LV cables | APPROVED | No | 2024-07-25 | Abas, Mohammed Fekry | 2024-07-29 | 2024-07-29 |  |  |  | 70000 | 5859 | 0 | STANDARD | Conexus Contracting Company | SAR | 67000 | APPROVED |  |  | 2024-10-19 | 3000 | 82 | Mohammed, Faisal Ansari | -45502 | 82
105-96 | Modon Aseer S/S | 4026 | Modon Aseer S/S-Civil Subcontractor | APPROVED | No | 2024-07-28 | Abas, Mohammed Fekry | 2024-07-30 | 2024-07-30 |  |  |  | 14399999 | 6101 | 0 | STANDARD | Al Rawy Al Arabia | SAR | 14399999 | APPROVED |  |  | 2024-09-12 | 0 | 44 | Tananeh, Khalid Jamal | -45503 | 44
105-96 | Modon Aseer S/S | 4028 | Modon Aseer S/S-Security service | APPROVED | No | 2024-07-28 | Abas, Mohammed Fekry | 2024-07-29 | 2024-07-29 |  |  |  | 500000 | 5923 | 0 | STANDARD | Rukn Al Kateibah Company for Security Guards. | SAR | 81000 | APPROVED |  |  | 2024-08-14 | 419000 | 16 | Abuhammad, Samir | -45502 | 16
105-96 | Modon Aseer S/S | 4036 | Modon Aseer S/S-Gantry Steel Support & Design | REJECTED | No | 2024-07-28 | Khalid, Saber Mohammed | 2024-10-10 | 2024-07-29 | 2024-09-05 | 2024-10-10 | no data recieved from pmt | 447000 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -45502 | -45502
105-96 | Modon Aseer S/S | 4077 | Modon Aseer S/S-Stationary & Sute miscellinious | APPROVED | No | 2024-08-01 | Abas, Mohammed Fekry | 2024-08-05 | 2024-08-05 |  |  |  | 21000 | 5935 | 0 | STANDARD | TALABAT AL MAKTAB CO.LTD | SAR | 18928.29 | APPROVED |  |  | 2024-08-25 | 2071.71 | 20 | Akhtar, Farhan | -45509 | 20
105-96 | Modon Aseer S/S | 4085 | Modon Aseer S/S-Security System | APPROVED | No | 2024-08-04 | Abas, Mohammed Fekry | 2024-08-05 | 2024-08-05 |  |  |  | 790000 | 5952 | 0 | STANDARD | Equipment & Technical Services Co.(ETECHS) | SAR | 748000 | APPROVED |  |  | 2024-08-28 | 42000 | 23 | Muhammad, Muhammad Atif | -45509 | 23
105-96 | Modon Aseer S/S | 4087 | Modon Aseer S/S-Security System - control Cables | REJECTED | No | 2024-08-04 | Khalid, Saber Mohammed | 2024-08-14 | 2024-08-05 | 2024-08-11 | 2024-08-14 | As discussed, we are returning this PR. | 60000 | [5 empty] | 0 |  |  |  |  | 0 |  | Muhammad, Muhammad Atif | -45509 | -45509
105-96 | Modon Aseer S/S | 4096 | Modon Aseer S/S-Indoor & Outdoor lighting and receptable | REJECTED | No | 2024-08-05 | Khalid, Saber Mohammed | 2024-10-07 | 2024-08-07 | 2024-09-09 | 2024-10-07 | rturned till recive the itemized lined PR , separe receptacle & lighting each in separate PR and send us the designer reply for sent offer from 3 weeks later | 380000 | [5 empty] | 0 |  |  |  |  | 0 |  | Eliwa, Mahmoud | -45511 | -45511
105-96 | Modon Aseer S/S | 4112 | Modon Aseer S/S-Civil Subcontractor (PR amount is 1SAR, the budget exception approved with 1 SAR less) | APPROVED | No | 2024-08-07 | Abas, Mohammed Fekry | 2024-08-12 | 2024-08-13 |  |  |  | 1 | 6101 | 0 | STANDARD | Al Rawy Al Arabia | SAR | 1 | APPROVED |  |  | 2024-09-12 | 0 | 30 | Tananeh, Khalid Jamal | -45517 | 30
105-96 | Modon Aseer S/S | 4119 | Modon Aseer S/S-Standalone CT | REJECTED | No | 2024-08-07 | Khan, Muhammad Safdar | 2024-08-07 | 2024-08-07 |  | 2024-08-08 |  | 160000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45511 | -45511
105-96 | Modon Aseer S/S | 4126 | Modon Aseer S/S-Standalone CT | APPROVED | No | 2024-08-11 | Abas, Mohammed Fekry | 2024-08-13 | 2024-08-13 |  |  |  | 240000 | 6090 | 0 | STANDARD | ELECTROTECNICA ARTECHE HERMANOS S.L. | EUR | 220170 | APPROVED |  |  | 2024-09-10 | 19830 | 28 | Alhadi, Khalid | -45517 | 28
105-96 | Modon Aseer S/S | 4340 | Modon Aseer S/S-Modon Asir - Cable ladder, trays & Supports | APPROVED | No | 2024-09-03 | Abas, Mohammed Fekry | 2024-09-09 | 2024-09-09 |  | 2024-09-03 |  | 235515.87 | 6147 | 0 | STANDARD | Power Solution Industries | SAR | 235515.87 | APPROVED |  |  | 2024-10-17 | 0 | 38 | Badhman, Saeed | -45544 | 38
105-96 | Modon Aseer S/S | 4341 | Modon Aseer S/S-Modon Asir - Cable ladder, trays & Supports | INCOMPLETE | No |  | Khalid, Saber Mohammed | 2024-09-03 |  |  |  |  | 235515.87 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-96 | Modon Aseer S/S | 4342 | Modon Aseer S/S-Modon Asir - Cable ladder, trays & Supports | INCOMPLETE | No |  | Khalid, Saber Mohammed | 2024-09-03 |  |  |  |  | 235515.87 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-96 | Modon Aseer S/S | 4359 | Modon Aseer S/S-Modon Asir - Cable tray, ladders and supports | REJECTED | No | 2024-09-03 | Khalid, Saber Mohammed | 2024-09-03 |  |  | 2024-09-03 |  | 370.44 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-96 | Modon Aseer S/S | 4367 | Modon Aseer S/S-Cable trays, ladders and supports | REJECTED | No | 2024-09-04 | Khalid, Saber Mohammed | 2024-09-04 |  |  | 2024-09-04 |  | 370.44 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-96 | Modon Aseer S/S | 4378 | Modon Aseer S/S-Modon Asir - Cable Ladder, tray & Supports | APPROVED | No | 2024-09-05 | Abas, Mohammed Fekry | 2024-09-09 | 2024-09-09 |  |  |  | 6844.45 | 6147 | 0 | STANDARD | Power Solution Industries | SAR | 6844.45 | APPROVED |  |  | 2024-10-17 | 0 | 38 | Badhman, Saeed | -45544 | 38
105-96 | Modon Aseer S/S | 4461 | Modon Aseer S/S-Laptop (Not PC)For SEC as part from mobilization | REJECTED | No | 2024-09-16 | Khalid, Saber Mohammed | 2024-10-23 | 2024-09-17 | 2024-10-22 | 2024-10-23 | Revise the amount | 3000 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45552 | -45552
105-96 | Modon Aseer S/S | 4475 | Modon Aseer S/S-Projector For MODON-Asir Site | REJECTED | No | 2024-09-18 | Khalid, Saber Mohammed | 2024-10-23 | 2024-09-18 | 2024-10-22 | 2024-10-23 | Revise the amount | 2000 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45553 | -45553
105-96 | Modon Aseer S/S | 4495 | Modon Aseer S/S-PR for Lightning Mast | APPROVED | No | 2024-09-22 | Abas, Mohammed Fekry | 2024-09-24 | 2024-09-24 |  |  |  | 74280 | 6145 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 74280 | APPROVED |  |  | 2024-09-30 | 0 | 6 | Eliwa, Mahmoud | -45559 | 6
105-96 | Modon Aseer S/S | 4648 | Modon Aseer S/S-Lighting | REJECTED | No | 2024-10-10 | Khalid, Saber Mohammed | 2024-11-06 | 2024-10-14 | 2024-11-06 | 2024-11-06 | PR to be itemized and also update the budget | 80000 | [5 empty] | 0 |  |  |  |  | 0 |  | Eliwa, Mahmoud | -45579 | -45579
105-96 | Modon Aseer S/S | 4649 | Modon Aseer S/S-Lighting | APPROVED | No | 2024-10-10 | Abas, Mohammed Fekry | 2024-10-13 | 2024-10-14 |  |  |  | 150000 | 6296 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 81697 | APPROVED |  |  | 2024-10-23 | 68303 | 9 | Eliwa, Mahmoud | -45579 | 9
105-96 | Modon Aseer S/S | 4654 | Modon Aseer S/S-Site store | APPROVED | No | 2024-10-10 | Abas, Mohammed Fekry | 2024-10-22 | 2024-10-22 |  |  |  | 80000 | 6526 | 0 | STANDARD | Construction Expertise Est. | SAR | 80000 | APPROVED |  |  | 2024-11-28 | 0 | 37 | Mohammed, Faisal Ansari | -45587 | 37
105-96 | Modon Aseer S/S | 4776 | Modon Aseer S/S-Projector, INK for printers , Laptop for the consultanat as part of mobilization | APPROVED | No | 2024-10-23 | Abas, Mohammed Fekry | 2024-10-27 | 2024-10-27 |  |  |  | 13500 | 6397 | 0 | STANDARD | Mohammad Abdul Rahman Mohd Al Zahid Information Technology Co | SAR | 10400 | APPROVED |  |  | 2024-11-04 | 3100 | 8 | Akhtar, Farhan | -45592 | 8
105-96 | Modon Aseer S/S | 4779 | Modon Aseer S/S-Over Head Clamps - PR | APPROVED | No | 2024-10-23 | Abas, Mohammed Fekry | 2024-11-27 | 2024-11-28 | 2024-11-26 |  | PR value is less than the PO value. Please revise or create a new PR to proceed further | 22804.2 | 6556 | 0 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 20800.01 | APPROVED |  |  | 2024-12-12 | 2004.19 | 14 | Mohammed, Faisal Ansari | -45624 | 14
105-96 | Modon Aseer S/S | 4782 | Modon Aseer S/S-Lighting Poles - PR | APPROVED | No | 2024-10-23 | Abas, Mohammed Fekry | 2024-10-27 | 2024-10-27 |  |  |  | 12400 | 6388 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 12000 | APPROVED |  |  | 2024-11-03 | 400 | 7 | Mohammed, Faisal Ansari | -45592 | 7
105-96 | Modon Aseer S/S | 4794 | Modon Aseer S/S-Metal Fuse Box | APPROVED | No | 2024-10-27 | Abas, Mohammed Fekry | 2024-10-28 | 2024-10-28 |  |  |  | 1000 | 6388 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 1000 | APPROVED |  |  | 2024-11-03 | 0 | 6 | Mohammed, Faisal Ansari | -45593 | 6
105-96 | Modon Aseer S/S | 4800 | Modon Aseer S/S-Camera for site & Mobilization | RETURNED | No | 2024-10-28 | Mohammed, Faisal Ansari | 2024-10-30 | 2024-10-30 | 2024-10-30 |  | The description is unclear and I have not received a BOQ for this. Please send the BOQ via email and then create a PR. | 15000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45595 | -45595
105-96 | Modon Aseer S/S | 4849 | Modon Aseer S/S-Power Sockets | APPROVED | No | 2024-11-06 | Abas, Mohammed Fekry | 2024-11-10 | 2024-11-11 |  |  |  | 95000 | 6305 | 0 | STANDARD | Power House Company | SAR | 84000 | APPROVED |  |  | 2025-02-12 | 11000 | 93 | Mohammed, Faisal Ansari | -45607 | 93
105-96 | Modon Aseer S/S | 4997 | Modon Aseer S/S-Asir Modon-2 - MV Termination PR | APPROVED | No | 2024-11-20 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-12 | 2024-12-05 |  | The PR value is less than the PO value. Kindly revise the PR to align with the latest offer. | 109896 | 6655 | 0 | STANDARD | CIVIL ELECT.PROJECTS CONTG.CO | EUR | 109880.01 | APPROVED |  |  | 2024-12-26 | 15.99 | 14 | Mohammed, Faisal Ansari | -45638 | 14
105-96 | Modon Aseer S/S | 4997 | Modon Aseer S/S-Asir Modon-2 - MV Termination PR | APPROVED | No | 2024-11-20 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-12 | 2024-12-05 |  | The PR value is less than the PO value. Kindly revise the PR to align with the latest offer. | 109896 | 6925 | 0 | STANDARD | Bright Wire Company | SAR | 60900 | APPROVED |  |  | 2025-02-27 | 48996 | 77 | Mohammed, Faisal Ansari | -45638 | 77
105-96 | Modon Aseer S/S | 5074 | Modon Aseer S/S-Asir Modon-2 - Gantry PR | REJECTED | No | 2024-11-27 | Khalid, Saber Mohammed | 2024-12-09 | 2024-12-03 | 2024-12-09 | 2024-12-09 | to update the budget and quantities to include the SA and ST. | 313750 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -45629 | -45629
105-96 | Modon Aseer S/S | 5209 | Modon Aseer S/S-Test | REJECTED | No | 2024-12-10 | Khalid, Saber Mohammed | 2024-12-10 |  |  | 2024-12-10 |  | 4000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-96 | Modon Aseer S/S | 5211 | Modon Aseer S/S-Test | REJECTED | No | 2024-12-10 | Khalid, Saber Mohammed | 2024-12-10 |  |  | 2024-12-10 |  | 1000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-96 | Modon Aseer S/S | 5248 | Modon Aseer S/S-Asir Modon - Gantry PR | APPROVED | No | 2024-12-19 | Abas, Mohammed Fekry | 2024-12-23 | 2024-12-25 |  |  |  | 392904 | 6571 | 0 | STANDARD | AL-ASHOURY FACTORY FOR CABLE SUPPORTS COMPANY(S) | SAR | 392904 | APPROVED |  |  | 2025-04-13 | 0 | 109 | Hegazy, Ayman | -45651 | 109
105-96 | Modon Aseer S/S | 5278 | Modon Aseer S/S-Modon Assir - LV & Control Cable -New PR | APPROVED | No | 2024-12-26 | Abas, Mohammed Fekry | 2024-12-31 | 2025-01-01 |  |  |  | 746332.52 | 6726 | 0 | STANDARD | ALFANAR CO | SAR | 746174.12 | APPROVED |  |  | 2025-01-14 | 158.4 | 13 | Mohammed, Faisal Ansari | -45658 | 13
105-96 | Modon Aseer S/S | 5301 | Modon Aseer S/S-Modon Aseer- HVAC system -New PR | APPROVED | No | 2024-12-30 | Abas, Mohammed Fekry | 2025-01-02 | 2025-01-02 |  |  |  | 1970000 | 6709 | 0 | STANDARD | Ramz Alataa Company for Trading | SAR | 1970000 | APPROVED |  |  | 2025-01-14 | 0 | 12 | Mohammed, Faisal Ansari | -45659 | 12
105-96 | Modon Aseer S/S | 5302 | Modon Aseer S/S-Modon Assir- Conduits,Fittings And Cables | APPROVED | No | 2024-12-30 | Abas, Mohammed Fekry | 2025-01-05 | 2025-01-06 | 2025-01-05 |  | PR value is less than the PO value. | 118700 | 6710 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 118000 | APPROVED |  |  | 2025-01-14 | 700 | 8 | Mohammed, Faisal Ansari | -45663 | 8
105-96 | Modon Aseer S/S | 5345 | Modon Aseer S/S-Modon Assir - Security Services - New PR | APPROVED | No | 2025-01-02 | Abas, Mohammed Fekry | 2025-01-05 | 2025-01-06 |  |  |  | 270000 | 5923 | 1 | STANDARD | Rukn Al Kateibah Company for Security Guards. | SAR | 270000 | APPROVED |  |  | 2025-01-14 | 0 | 8 | Abuhammad, Samir | -45663 | 8
105-96 | Modon Aseer S/S | 5372 | Modon Aseer S/S-Site Installation Tools | APPROVED | No | 2025-01-08 | Abas, Mohammed Fekry | 2025-01-12 | 2025-01-12 |  |  |  | 66000 | 6762 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 52000 | APPROVED |  |  | 2025-01-20 | 14000 | 8 | Akhtar, Farhan | -45669 | 8
105-96 | Modon Aseer S/S | 5797 | Modon Aseer S/S-Asir Modon-2 - Fiber Optic Patch Panels | RETURNED | No | 2025-02-05 | Mohammed, Faisal Ansari | 2025-08-18 | 2025-04-21 |  |  |  | 150000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45768 | -45768
105-96 | Modon Aseer S/S | 6153 | Modon Aseer S/S-Asir Modon-2 S/S - Additional Cable Trays,Ladders,Fittings and Accessories | APPROVED | No | 2025-03-11 | Abas, Mohammed Fekry | 2025-03-13 | 2025-03-16 |  |  |  | 85028.85 | 6970 | 0 | STANDARD | Power Solution Industries | SAR | 85028.85 | APPROVED |  |  | 2025-03-18 | 0 | 2 | Mohammed, Faisal Ansari | -45732 | 2
105-96 | Modon Aseer S/S | 6276 | Modon Aseer S/S-Rental Dilo Machine - Modon Assir | RETURNED | No | 2025-03-25 | Mohammed, Faisal Ansari | 2025-05-19 | 2025-03-27 | 2025-05-19 |  | More Info is needed or cancel the PR if not required as of now. | 90000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45743 | -45743
105-96 | Modon Aseer S/S | 6344 | Modon Aseer S/S-Asir Modon-2 S/S - Capacitor Bank Sealing FAT Test (Eram International) | RETURNED | No | 2025-04-15 |  |  | 2025-04-22 |  |  |  | 1400 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45769 | -45769
105-96 | Modon Aseer S/S | 6360 | Modon Aseer S/S-Asir Modon-2 - Fiber Optic Cable | RETURNED | No | 2025-04-17 | Mohammed, Faisal Ansari | 2025-05-19 | 2025-04-21 | 2025-05-19 |  | Kindly issue the PR when the value of the PO is finalized. | 200000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45768 | -45768
105-96 | Modon Aseer S/S | 6396 | Modon Aseer S/S-Asir Modon-2 - Testing & Commissioning PR | APPROVED | No | 2025-04-20 | Abas, Mohammed Fekry | 2025-04-22 | 2025-04-22 |  |  |  | 1785049 | 6893 | 0 | STANDARD | Al Fanar Technical Services | SAR | 1785049 | APPROVED |  |  | 2025-04-28 | 0 | 6 | Mohammed, Faisal Ansari | -45769 | 6
105-96 | Modon Aseer S/S | 6708 | Modon Aseer S/S-Diesel supply for Generator at site | APPROVED | No | 2025-05-25 | Abas, Mohammed Fekry | 2025-05-28 | 2025-05-29 |  |  | 6.1.6.1 | 152000 | 7388 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 148000 | APPROVED |  |  | 2025-06-25 | 4000 | 27 | Akhtar, Farhan | -45806 | 27
105-96 | Modon Aseer S/S | 6708 | Modon Aseer S/S-Diesel supply for Generator at site | APPROVED | No | 2025-05-25 | Abas, Mohammed Fekry | 2025-05-28 | 2025-05-29 |  |  | 6.1.6.1 | 152000 | 7388 | 1 | STANDARD | Talaea Alahlam Trading Company | SAR | 148000 | REQUIRES REAPPROVAL |  |  |  | 4000 | 248 | Akhtar, Farhan | -45806 | -45806
105-96 | Modon Aseer S/S | 6840 | Modon Aseer S/S-Asir Modon-2 - 1X150mm2 Bare Copper Conductor | REJECTED | No | 2025-06-19 | Khalid, Saber Mohammed | 2025-07-26 | 2025-06-25 | 2025-07-20 | 2025-07-26 | Change the quantity to 2,000 meters and adjust the unit price to match the PO value. | 83625 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45833 | -45833
105-96 | Modon Aseer S/S | 7118 | Modon Aseer S/S-Asir Modon-2 - Cable Cleats | APPROVED | No | 2025-07-16 | Abas, Mohammed Fekry | 2025-07-20 | 2025-07-20 |  |  |  | 100000 | 7559 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 36120 | APPROVED |  |  | 2025-08-04 | 63880 | 15 | Mohammed, Faisal Ansari | -45858 | 15
105-96 | Modon Aseer S/S | 7207 | Modon Aseer S/S-Asir Modon-2 - 1X150mm2 Bare Copper Conductor | APPROVED | No | 2025-07-26 | Abas, Mohammed Fekry | 2025-07-28 | 2025-07-29 |  |  |  | 111500 | 7540 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 111500 | APPROVED |  |  | 2025-08-06 | 0 | 8 | Mohammed, Faisal Ansari | -45867 | 8
105-96 | Modon Aseer S/S | 7258 | Modon Aseer S/S-Lugs, Glands And Wires | APPROVED | No | 2025-08-03 | Abas, Mohammed Fekry | 2025-08-07 | 2025-08-10 |  |  | task no.3.1.9.3 | 135000 | 7500 | 0 | STANDARD | Ahmed Essa Mohammed Al Muslim Est. | SAR | 134987 | APPROVED |  |  | 2025-08-19 | 13 | 9 | Hegazy, Ayman | -45879 | 9
105-96 | Modon Aseer S/S | 7320 | Modon Aseer S/S-Office supplies | APPROVED | No | 2025-08-10 | Abas, Mohammed Fekry | 2025-08-17 | 2025-08-18 |  |  | 6.1.4.4 | 20000 | 7674 | 0 | STANDARD | DANAH AL RAYEDA ESTABLISHMENT | SAR | 20000 | APPROVED |  |  | 2025-10-02 | 0 | 45 | Akhtar, Farhan | -45887 | 45
105-96 | Modon Aseer S/S | 7363 | Modon Aseer S/S-Walkie Talkies for Site | APPROVED | No | 2025-08-14 | Abas, Mohammed Fekry | 2025-08-17 | 2025-08-18 |  |  | 6.1.4.4 | 4000 | 7627 | 0 | STANDARD | Versatile Advanced Limited Company. | SAR | 3950 | APPROVED |  |  | 2025-08-28 | 50 | 10 | Akhtar, Farhan | -45887 | 10
105-96 | Modon Aseer S/S | 7369 | Modon Aseer S/S-Asir Modon-2 S/S- GEM Material (25 kG Bag) | APPROVED | No | 2025-08-18 | Abas, Mohammed Fekry | 2025-08-19 | 2025-08-19 |  |  | Budget item no. 4.2 | 50580 | 7643 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 41105.6 | APPROVED |  |  | 2025-10-05 | 9474.4 | 47 | Muaz, Alaa | -45888 | 47
105-96 | Modon Aseer S/S | 7422 | Modon Aseer S/S-Asir Modon-2 132/33kV - Earthing Conductor 150mm2 soft annealed copper conductor | REJECTED | No | 2025-08-21 | Ghith, Saad Gamal | 2025-08-24 | 2025-08-24 |  | 2025-08-25 |  | 111500 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45893 | -45893
105-96 | Modon Aseer S/S | 7448 | stationary | REJECTED | No | 2025-08-24 | Ghith, Saad Gamal | 2025-08-24 | 2025-08-24 |  | 2025-08-25 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45893 | -45893
105-96 | Modon Aseer S/S | 7510 | office supplies | APPROVED | No | 2025-08-26 | Abas, Mohammed Fekry | 2025-08-28 | 2025-08-28 |  |  |  | 0 | 7674 | 0 | STANDARD | DANAH AL RAYEDA ESTABLISHMENT | SAR | 10000 | APPROVED |  |  | 2025-10-02 | -10000 | 35 | Akhtar, Farhan | -45897 | 35
105-96 | Modon Aseer S/S | 7599 | Security Porta cabin | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | 0 | 0
105-96 | Modon Aseer S/S | 7640 | Fiber Optic Cables and Patch Panels | APPROVED | No | 2025-09-04 | Abas, Mohammed Fekry | 2025-09-09 | 2025-09-10 |  |  | Budget item no. 3.1.6.2, kindly approve | 0 | 7373 | 0 | STANDARD | RASHID SAEED AHMED AL GHAMDI COMM INFO TRAD EST | SAR | 272500 | APPROVED |  |  | 2025-09-29 | -272500 | 19 | Mohammed, Faisal Ansari | -45910 | 19
105-96 | Modon Aseer S/S | 7657 | Earthing Material | APPROVED | No | 2025-09-07 | Abas, Mohammed Fekry | 2025-09-18 | 2025-09-21 |  |  | Please Approve | 0 | 7732 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 41590 | APPROVED |  |  | 2025-10-13 | -41590 | 22 | Muaz, Alaa | -45921 | 22
105-96 | Modon Aseer S/S | 7669 | Rental for Dilo Machine | REJECTED | No | 2025-09-07 | Ghith, Saad Gamal | 2025-09-09 | 2025-09-09 |  | 2025-09-15 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45909 | -45909
105-96 | Modon Aseer S/S | 7718 | 1X150mm2 Earthing Conductor | APPROVED | No | 2025-09-11 | Abas, Mohammed Fekry | 2025-09-15 | 2025-09-15 |  |  | Kindly approve | 0 | 7540 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 111500 | APPROVED |  |  | 2025-10-09 | -111500 | 24 | Mohammed, Faisal Ansari | -45915 | 24
105-96 | Modon Aseer S/S | 7761 | Dilo Machine Rental | RETURNED | No | 2025-09-16 | Akhtar, Farhan | 2025-10-26 | 2025-09-23 | 2025-10-26 |  | No Responce from PMT | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45923 | -45923
105-96 | Modon Aseer S/S | 7904 | Variation order for gantry | APPROVED | No | 2025-10-06 | Abas, Mohammed Fekry | 2025-10-23 | 2025-10-25 |  |  | Task no. 4.5 | 0 | 6571 | 1 | STANDARD | AL-ASHOURY FACTORY FOR CABLE SUPPORTS COMPANY(S) | SAR | 105288 | APPROVED |  |  | 2025-11-25 | -105288 | 31 | Hegazy, Ayman | -45955 | 31
105-96 | Modon Aseer S/S | 8080 | Diesel Supply for Generator at Site | APPROVED | No | 2025-10-28 | Abas, Mohammed Fekry | 2026-01-25 | 2026-01-26 | 2026-01-18 |  | Resbmit the PR once POCR is approved | 0 | 7388 | 1 | STANDARD | Talaea Alahlam Trading Company | SAR | 148000 | REQUIRES REAPPROVAL |  |  |  | -148000 | 6 | Akhtar, Farhan | -46048 | -46048
105-96 | Modon Aseer S/S | 8080 | Diesel Supply for Generator at Site | APPROVED | No | 2025-10-28 | Abas, Mohammed Fekry | 2026-01-25 | 2026-01-26 | 2026-01-18 |  | Resbmit the PR once POCR is approved | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -46048 | -46048
105-96 | Modon Aseer S/S | 8185 | Waste management and water supply | APPROVED | No | 2025-11-11 | Abas, Mohammed Fekry | 2025-12-30 | 2026-01-01 | 2025-12-21 |  | No responce from PMT | 0 | 15030 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 35280 | APPROVED | 2026-01-19 | 2026-01-21 | 2026-01-26 | -35280 | 25 | Akhtar, Farhan | 20 | 25
105-96 | Modon Aseer S/S | 8285 | MV Cable Vertical Supports | APPROVED | No | 2025-11-19 | Abas, Mohammed Fekry | 2025-11-23 | 2025-11-24 |  |  |  | 0 | 8026 | 0 | STANDARD | Electrolink Co Ltd | SAR | 19500 | APPROVED |  |  | 2025-12-29 | -19500 | 35 | Mohammed, Faisal Ansari | -45985 | 35
105-96 | Modon Aseer S/S | 8465 | Spacer for ACSR spacing 200mm | RETURNED | No | 2025-12-10 | Mohammed, Faisal Ansari | 2025-12-21 | 2025-12-18 | 2025-12-21 |  | This item can be purchased thru Petty Cash. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46009 | -46009
105-96 | Modon Aseer S/S | 8517 | Fire Rated Material | RETURNED | No | 2025-12-14 | Mohammed, Faisal Ansari | 2025-12-21 | 2025-12-21 | 2025-12-21 |  | Kindly issue the PR once the BOQ is ready. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46012 | -46012
105-96 | Modon Aseer S/S | 8557 | Standalone CT BOX | APPROVED | No | 2025-12-18 | Abas, Mohammed Fekry | 2025-12-29 | 2026-01-01 |  |  | Kindly approve | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46023 | -46023
105-96 | Modon Aseer S/S | 8617 | Transportation and Off loading of Power Transformer | APPROVED | No | 2025-12-31 | Abas, Mohammed Fekry | 2026-01-06 | 2026-01-08 |  |  | Scope is transportation and offloading of two power transformer | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -46030 | -46030
105-96 | Modon Aseer S/S | 8798 | Gantry, SA & CT installation | IN PROCESS | No | 2026-01-27 | Ghith, Saad Gamal | 2026-01-27 | 2026-01-27 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46049 | -46049
105-97 | Diriyah Gate S/S # 8241 | 1705 | Diriyah Gate S/S # 8241-PR for capacitor bank | APPROVED | No | 2023-11-13 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 2090200 | 4795 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 2090200 | APPROVED |  |  | 2023-12-17 | 0 | 31 | Kumar, Mr. Ranjan | -45246 | 31
105-97 | Diriyah Gate S/S # 8241 | 1736 | Diriyah Gate S/S # 8241-PR FOR SITE HANDOVER & TOPOGRAPHIC SURVEY | REJECTED | No | 2023-11-14 | Nabi, Ashraf | 2023-11-14 |  |  | 2023-11-14 |  | 10250 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-97 | Diriyah Gate S/S # 8241 | 1834 | Diriyah Gate S/S # 8241-PR_POWER TR | APPROVED | No | 2023-11-28 | Abas, Mohammed Fekry | 2023-11-30 | 2023-12-04 |  |  |  | 28162500 | 5084 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 28162500 | APPROVED |  |  | 2024-02-21 | 0 | 79 | Alhadi, Khalid | -45264 | 79
105-97 | Diriyah Gate S/S # 8241 | 1839 | Diriyah Gate S/S # 8241-PR_13.8KV SWITCHGEAR | APPROVED | No | 2023-11-28 | Abas, Mohammed Fekry | 2023-11-30 | 2023-12-04 |  |  |  | 14560000 | 5700 | 0 | STANDARD | ALFANAR CO | SAR | 14560000 | APPROVED |  |  | 2024-06-26 | 0 | 205 | Kumar, Mr. Ranjan | -45264 | 205
105-97 | Diriyah Gate S/S # 8241 | 1843 | Diriyah Gate S/S # 8241-PR_SOIL INVESTIGATION | APPROVED | No | 2023-11-28 | Abas, Mohammed Fekry | 2023-11-30 | 2023-12-04 |  |  |  | 17910 | 4741 | 0 | STANDARD | International Agent Commercial Company(S) | SAR | 17910 | APPROVED |  |  | 2024-03-26 | 0 | 113 | Alhadi, Khalid | -45264 | 113
105-97 | Diriyah Gate S/S # 8241 | 1894 | Diriyah Gate S/S # 8241-PR_Battary & Charger | APPROVED | No | 2023-12-05 | Abas, Mohammed Fekry | 2023-12-06 | 2023-12-07 |  |  |  | 472500 | 4813 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 472500 | APPROVED |  |  | 2023-12-19 | 0 | 12 | Alhadi, Khalid | -45267 | 12
105-97 | Diriyah Gate S/S # 8241 | 1912 | Diriyah Gate S/S # 8241-PR_ESIA | APPROVED | No | 2023-12-06 | Abas, Mohammed Fekry | 2023-12-07 | 2023-12-10 |  |  |  | 18000 | 5091 | 0 | STANDARD | Aran Aljazeera Enviromental Consultant | SAR | 18000 | APPROVED |  |  | 2024-02-18 | 0 | 70 | Alhadi, Khalid | -45270 | 70
105-97 | Diriyah Gate S/S # 8241 | 2167 | Diriyah Gate S/S # 8241-Supply of IT Requirments | APPROVED | No | 2024-01-15 | Abas, Mohammed Fekry | 2024-01-16 | 2024-01-17 |  |  |  | 21295 | 5025 | 0 | STANDARD | Mohmmed Abdulrahman AlZahid IT CO. | SAR | 21295 | APPROVED |  |  | 2024-02-06 | 0 | 20 | Akhtar, Farhan | -45308 | 20
105-97 | Diriyah Gate S/S # 8241 | 2262 | Diriyah Gate S/S # 8241-OHTC_PR | APPROVED | No | 2024-01-23 | Abas, Mohammed Fekry | 2024-01-24 | 2024-01-25 |  |  |  | 138500 | 5022 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 138500 | APPROVED |  |  | 2024-02-12 | 0 | 18 | Alhadi, Khalid | -45316 | 18
105-97 | Diriyah Gate S/S # 8241 | 2277 | Diriyah Gate S/S # 8241-GIS_PR | APPROVED | No | 2024-01-25 | Abas, Mohammed Fekry | 2024-01-29 | 2024-01-29 |  |  |  | 26900000 | 5034 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 26900000 | APPROVED |  |  | 2024-02-05 | 0 | 7 | Kumar, Mr. Ranjan | -45320 | 7
105-97 | Diriyah Gate S/S # 8241 | 2890 | Diriyah Gate S/S # 8241-E&D | APPROVED | No | 2024-03-24 | Abas, Mohammed Fekry | 2024-03-28 | 2024-03-31 |  |  |  | 670000 | 5324 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 670000 | APPROVED |  |  | 2024-04-14 | 0 | 14 | Kumar, Mr. Ranjan | -45382 | 14
105-97 | Diriyah Gate S/S # 8241 | 2952 | Diriyah Gate S/S # 8241-bare copper_PR | APPROVED | No | 2024-03-31 | Abas, Mohammed Fekry | 2024-04-01 | 2024-04-02 |  |  |  | 159414.38 | 5342 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 159414.38 | APPROVED |  |  | 2024-04-23 | 0 | 21 | Alhadi, Khalid | -45384 | 21
105-97 | Diriyah Gate S/S # 8241 | 2952 | Diriyah Gate S/S # 8241-bare copper_PR | APPROVED | No | 2024-03-31 | Abas, Mohammed Fekry | 2024-04-01 | 2024-04-02 |  |  |  | 159414.38 | 5499 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 318828.75 | APPROVED |  |  | 2024-05-28 | -159414.38 | 56 | Alhadi, Khalid | -45384 | 56
105-97 | Diriyah Gate S/S # 8241 | 3052 | Diriyah Gate S/S # 8241-NGR | APPROVED | No | 2024-04-16 | Abas, Mohammed Fekry | 2024-04-17 | 2024-04-24 |  |  |  | 106125 | 5474 | 0 | STANDARD | National Switchgears | USD | 106125 | APPROVED |  |  | 2024-05-16 | 0 | 22 | Kumar, Mr. Ranjan | -45406 | 22
105-97 | Diriyah Gate S/S # 8241 | 4293 | Diriyah Gate S/S # 8241-PR- Protection, Control and SAS - Manual P.O.-8407-HV1444-0 | APPROVED | No | 2024-08-28 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 13161000 | 6261 | 0 | STANDARD | ALFANAR CO | SAR | 13161000 | APPROVED |  |  | 2024-10-06 | 0 | 14 | Kumar, Mr. Ranjan | -45557 | 14
105-97 | Diriyah Gate S/S # 8241 | 4300 | Diriyah Gate S/S # 8241-PR-Telecommunication System - Manual P.O.8403-HV1444-0 | APPROVED | No | 2024-08-29 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 2000000 | 6267 | 0 | STANDARD | ALFANAR CO | SAR | 2000000 | APPROVED |  |  | 2024-10-06 | 0 | 14 | Kumar, Mr. Ranjan | -45557 | 14
105-97 | Diriyah Gate S/S # 8241 | 4302 | Diriyah Gate S/S # 8241-PR-Supply of Ring Main Unit - Manual P.O.8495-HV1433-0 | APPROVED | No | 2024-08-29 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 139000 | 6232 | 0 | STANDARD | ALFANAR CO | SAR | 139000 | APPROVED |  |  | 2024-10-01 | 0 | 9 | Alhadi, Khalid | -45557 | 9
105-97 | Diriyah Gate S/S # 8241 | 4304 | Diriyah Gate S/S # 8241-PR-Cyber Security - Manual P.O. 8515-HV1444-0 | APPROVED | No | 2024-08-29 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 1590000 | 6297 | 0 | STANDARD | ALFANAR CO | SAR | 1590000 | APPROVED |  |  | 2024-10-07 | 0 | 15 | Alhadi, Khalid | -45557 | 15
105-97 | Diriyah Gate S/S # 8241 | 4305 | Diriyah Gate S/S # 8241-PR-750kVA Station Service Transformer-Manual P.O.8511-HV1444-0 | APPROVED | No | 2024-08-29 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 202000 | 6243 | 0 | STANDARD | ALFANAR CO | SAR | 202000 | APPROVED |  |  | 2024-10-01 | 0 | 9 | Alhadi, Khalid | -45557 | 9
105-97 | Diriyah Gate S/S # 8241 | 4307 | Diriyah Gate S/S # 8241-PR-AC / DC Distribution and Lighting Panels-Manual P.O.8554-HV1444-0 | APPROVED | No | 2024-08-29 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 787000 | 6248 | 0 | STANDARD | ALFANAR CO | SAR | 787000 | APPROVED |  |  | 2024-10-01 | 0 | 9 | Alhadi, Khalid | -45557 | 9
105-98 | Diriyah Gate S/S# 8243 | 1717 | Diriyah Gate S/S# 8243-PR for capacitor bank | APPROVED | No | 2023-11-14 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 2090200 | 4794 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 2090200 | APPROVED |  |  | 2023-12-17 | 0 | 31 | Kumar, Mr. Ranjan | -45246 | 31
105-98 | Diriyah Gate S/S# 8243 | 1827 | Diriyah Gate S/S# 8243-Power TR PR | REJECTED | No | 2023-11-28 | Nabi, Ashraf | 2023-11-28 |  |  | 2023-11-28 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-98 | Diriyah Gate S/S# 8243 | 1833 | Diriyah Gate S/S# 8243-PR_ POWER TR | APPROVED | No | 2023-11-28 | Abas, Mohammed Fekry | 2023-11-30 | 2023-12-04 |  |  |  | 28162500 | 5083 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 28162500 | APPROVED |  |  | 2024-02-21 | 0 | 79 | Alhadi, Khalid | -45264 | 79
105-98 | Diriyah Gate S/S# 8243 | 1838 | Diriyah Gate S/S# 8243-PR_13.8KV SWITCHGEAR | APPROVED | No | 2023-11-28 | Abas, Mohammed Fekry | 2023-11-30 | 2023-12-04 |  |  |  | 14560000 | 5701 | 0 | STANDARD | ALFANAR CO | SAR | 14560000 | APPROVED |  |  | 2024-06-26 | 0 | 205 | Kumar, Mr. Ranjan | -45264 | 205
105-98 | Diriyah Gate S/S# 8243 | 1842 | Diriyah Gate S/S# 8243-PR_SOIL INVESTIGATION | APPROVED | No | 2023-11-28 | Abas, Mohammed Fekry | 2023-11-30 | 2023-12-04 |  |  |  | 17910 | 4740 | 0 | STANDARD | International Agent Commercial Company(S) | SAR | 17910 | APPROVED |  |  | 2024-03-25 | 0 | 112 | Kumar, Mr. Ranjan | -45264 | 112
105-98 | Diriyah Gate S/S# 8243 | 1895 | Diriyah Gate S/S# 8243-PR_Battary & Charger | APPROVED | No | 2023-12-05 | Abas, Mohammed Fekry | 2023-12-06 | 2023-12-07 |  |  |  | 472500 | 4814 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 472500 | APPROVED |  |  | 2023-12-21 | 0 | 14 | Alhadi, Khalid | -45267 | 14
105-98 | Diriyah Gate S/S# 8243 | 1911 | Diriyah Gate S/S# 8243-PR_ESIA | APPROVED | No | 2023-12-06 | Abas, Mohammed Fekry | 2023-12-07 | 2023-12-10 |  |  |  | 18000 | 5092 | 0 | STANDARD | Aran Aljazeera Enviromental Consultant | SAR | 18000 | APPROVED |  |  | 2024-02-18 | 0 | 70 | Alhadi, Khalid | -45270 | 70
105-98 | Diriyah Gate S/S# 8243 | 2168 | Diriyah Gate S/S# 8243-Supply of IT Requirments | APPROVED | No | 2024-01-15 | Abas, Mohammed Fekry | 2024-01-16 | 2024-01-17 |  |  |  | 21295 | 5027 | 0 | STANDARD | Mohmmed Abdulrahman AlZahid IT CO. | SAR | 21295 | APPROVED |  |  | 2024-02-06 | 0 | 20 | Akhtar, Farhan | -45308 | 20
105-98 | Diriyah Gate S/S# 8243 | 2263 | Diriyah Gate S/S# 8243-OHTC_PR | APPROVED | No | 2024-01-23 | Abas, Mohammed Fekry | 2024-01-24 | 2024-01-25 |  |  |  | 138500 | 5021 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 138500 | APPROVED |  |  | 2024-02-07 | 0 | 13 | Alhadi, Khalid | -45316 | 13
105-98 | Diriyah Gate S/S# 8243 | 2275 | Diriyah Gate S/S# 8243-GIS_PR | APPROVED | No | 2024-01-25 | Abas, Mohammed Fekry | 2024-01-29 | 2024-01-29 |  |  |  | 28800000 | 5035 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 28800000 | APPROVED |  |  | 2024-02-05 | 0 | 7 | Kumar, Mr. Ranjan | -45320 | 7
105-98 | Diriyah Gate S/S# 8243 | 2889 | Diriyah Gate S/S# 8243-E&D | APPROVED | No | 2024-03-24 | Abas, Mohammed Fekry | 2024-03-28 | 2024-03-28 |  |  |  | 670000 | 5322 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 670000 | APPROVED |  |  | 2024-04-14 | 0 | 17 | Kumar, Mr. Ranjan | -45379 | 17
105-98 | Diriyah Gate S/S# 8243 | 2951 | Diriyah Gate S/S# 8243-bare copper_PR | APPROVED | No | 2024-03-31 | Abas, Mohammed Fekry | 2024-04-01 | 2024-04-02 |  |  |  | 159414.38 | 5341 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 159414.38 | APPROVED |  |  | 2024-04-18 | 0 | 16 | Alhadi, Khalid | -45384 | 16
105-98 | Diriyah Gate S/S# 8243 | 2951 | Diriyah Gate S/S# 8243-bare copper_PR | APPROVED | No | 2024-03-31 | Abas, Mohammed Fekry | 2024-04-01 | 2024-04-02 |  |  |  | 159414.38 | 5499 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 318828.75 | APPROVED |  |  | 2024-05-28 | -159414.38 | 56 | Alhadi, Khalid | -45384 | 56
105-98 | Diriyah Gate S/S# 8243 | 3051 | Diriyah Gate S/S# 8243-NGR | APPROVED | No | 2024-04-16 | Abas, Mohammed Fekry | 2024-04-18 | 2024-04-24 |  |  |  | 106125 | 5475 | 0 | STANDARD | National Switchgears | USD | 106125 | APPROVED |  |  | 2024-05-13 | 0 | 19 | Kumar, Mr. Ranjan | -45406 | 19
105-98 | Diriyah Gate S/S# 8243 | 4308 | Diriyah Gate S/S# 8243-PR-Protection,Control &SAS-Manual P.O.8408-HV1444-0 | APPROVED | No | 2024-08-29 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 13961000 | 6262 | 0 | STANDARD | ALFANAR CO | SAR | 13961000 | APPROVED |  |  | 2024-10-06 | 0 | 14 | Kumar, Mr. Ranjan | -45557 | 14
105-98 | Diriyah Gate S/S# 8243 | 4309 | Diriyah Gate S/S# 8243-PR-Telecommunication System-Manual P.O.8404-HV1444-0 | APPROVED | No | 2024-08-29 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 2000000 | 6268 | 0 | STANDARD | ALFANAR CO | SAR | 2000000 | APPROVED |  |  | 2024-10-06 | 0 | 14 | Kumar, Mr. Ranjan | -45557 | 14
105-98 | Diriyah Gate S/S# 8243 | 4310 | Diriyah Gate S/S# 8243-PR-Cyber Security-Manual P.O. 8517-HV1433-0 | APPROVED | No | 2024-08-29 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 1590000 | 6298 | 0 | STANDARD | ALFANAR CO | SAR | 1590000 | APPROVED |  |  | 2024-10-06 | 0 | 14 | Alhadi, Khalid | -45557 | 14
105-98 | Diriyah Gate S/S# 8243 | 4324 | Diriyah Gate S/S# 8243-PR-750kVA Station Service Transformer-Manual P.O.8513-HV1433-0 | APPROVED | No | 2024-08-29 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 202000 | 6244 | 0 | STANDARD | ALFANAR CO | SAR | 202000 | APPROVED |  |  | 2024-10-01 | 0 | 9 | Alhadi, Khalid | -45557 | 9
105-98 | Diriyah Gate S/S# 8243 | 4326 | Diriyah Gate S/S# 8243-PR-RingMain Unit ( RMU ) - Manual P.O. 8493-HV1433-0 | APPROVED | No | 2024-08-29 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 139000 | 6233 | 0 | STANDARD | ALFANAR CO | SAR | 139000 | APPROVED |  |  | 2024-10-01 | 0 | 9 | Alhadi, Khalid | -45557 | 9
105-98 | Diriyah Gate S/S# 8243 | 4327 | Diriyah Gate S/S# 8243-PR-AC,DC Distribution and Lighting Panels - Manual P.O.8557-HV1433-0 | APPROVED | No | 2024-08-29 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 787000 | 6249 | 0 | STANDARD | ALFANAR CO | SAR | 787000 | APPROVED |  |  | 2024-10-01 | 0 | 9 | Alhadi, Khalid | -45557 | 9
105-99 | Diriyah Gate S/S # 8171 | 1686 | Diriyah Gate S/S # 8171-PR for two generators | APPROVED | No | 2023-11-12 | Abas, Mohammed Fekry | 2023-11-14 | 2023-11-15 |  |  |  | 250000 | 4742 | 0 | STANDARD | Mohammed A. AlFaddaghi & Partners | SAR | 250000 | APPROVED |  |  | 2023-12-04 | 0 | 19 | Badhman, Saeed | -45245 | 19
105-99 | Diriyah Gate S/S # 8171 | 1686 | Diriyah Gate S/S # 8171-PR for two generators | APPROVED | No | 2023-11-12 | Abas, Mohammed Fekry | 2023-11-14 | 2023-11-15 |  |  |  | 250000 | 4742 | 1 | STANDARD | Mohammed A. AlFaddaghi & Partners | SAR | 236000 | APPROVED |  |  | 2024-10-30 | 14000 | 350 | Badhman, Saeed | -45245 | 350
105-99 | Diriyah Gate S/S # 8171 | 1688 | Diriyah Gate S/S # 8171-PR for Precast | RETURNED | No | 2023-11-12 | Kumar, Mr. Ranjan | 2023-11-23 | 2023-11-16 | 2023-11-23 |  | Please correct Price its mentioned SAR 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45246 | -45246
105-99 | Diriyah Gate S/S # 8171 | 1700 | Diriyah Gate S/S # 8171-PR for capacitor bank | APPROVED | No | 2023-11-13 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 2090200 | 4796 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 2090200 | APPROVED |  |  | 2023-12-17 | 0 | 31 | Kumar, Mr. Ranjan | -45246 | 31
105-99 | Diriyah Gate S/S # 8171 | 1755 | Diriyah Gate S/S # 8171-Power TR PR | APPROVED | No | 2023-11-15 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 26287500 | 5082 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 26287500 | APPROVED |  |  | 2024-02-25 | 0 | 101 | Alhadi, Khalid | -45246 | 101
105-99 | Diriyah Gate S/S # 8171 | 1755 | Diriyah Gate S/S # 8171-Power TR PR | APPROVED | No | 2023-11-15 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 26287500 | 5082 | 1 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 26000000 | APPROVED |  |  | 2024-06-26 | 287500 | 223 | Alhadi, Khalid | -45246 | 223
105-99 | Diriyah Gate S/S # 8171 | 1837 | Diriyah Gate S/S # 8171-PR_13.8KV SWITCHGEAR | APPROVED | No | 2023-11-28 | Abas, Mohammed Fekry | 2023-11-30 | 2023-12-04 |  |  |  | 12300000 | 5702 | 0 | STANDARD | ALFANAR CO | SAR | 12300000 | APPROVED |  |  | 2024-06-26 | 0 | 205 | Kumar, Mr. Ranjan | -45264 | 205
105-99 | Diriyah Gate S/S # 8171 | 1841 | Diriyah Gate S/S # 8171-PR_SOIL INVESTIGATION | APPROVED | No | 2023-11-28 | Abas, Mohammed Fekry | 2023-11-30 | 2023-12-04 |  |  |  | 17910 | 5238 | 0 | STANDARD | International Agent Commercial Company(S) | SAR | 17910 | APPROVED |  |  | 2024-03-20 | 0 | 107 | Kumar, Mr. Ranjan | -45264 | 107
105-99 | Diriyah Gate S/S # 8171 | 1892 | Diriyah Gate S/S # 8171-PR_Battary & Charger | APPROVED | No | 2023-12-05 | Abas, Mohammed Fekry | 2023-12-06 | 2023-12-07 |  |  |  | 472500 | 4811 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 472500 | APPROVED |  |  | 2023-12-19 | 0 | 12 | Alhadi, Khalid | -45267 | 12
105-99 | Diriyah Gate S/S # 8171 | 1910 | Diriyah Gate S/S # 8171-PR_ESIA | APPROVED | No | 2023-12-06 | Abas, Mohammed Fekry | 2023-12-07 | 2023-12-10 |  |  |  | 18000 | 5090 | 0 | STANDARD | Aran Aljazeera Enviromental Consultant | SAR | 18000 | APPROVED |  |  | 2024-02-18 | 0 | 70 | Alhadi, Khalid | -45270 | 70
105-99 | Diriyah Gate S/S # 8171 | 2096 | Diriyah Gate S/S # 8171-Overhead Crane | REJECTED | No | 2024-01-17 | Abas, Mohammed Fekry | 2024-01-22 | 2024-01-22 |  | 2024-01-22 |  | 138500 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45313 | -45313
105-99 | Diriyah Gate S/S # 8171 | 2166 | Diriyah Gate S/S # 8171-Supply of IT Requirments | APPROVED | No | 2024-01-15 | Abas, Mohammed Fekry | 2024-01-16 | 2024-01-17 |  |  |  | 21295 | 5024 | 0 | STANDARD | Mohmmed Abdulrahman AlZahid IT CO. | SAR | 21295 | APPROVED |  |  | 2024-02-06 | 0 | 20 | Akhtar, Farhan | -45308 | 20
105-99 | Diriyah Gate S/S # 8171 | 2261 | Diriyah Gate S/S # 8171-OHTC_PR | APPROVED | No | 2024-01-23 | Abas, Mohammed Fekry | 2024-01-24 | 2024-01-25 |  |  |  | 138500 | 5020 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 138500 | APPROVED |  |  | 2024-02-07 | 0 | 13 | Alhadi, Khalid | -45316 | 13
105-99 | Diriyah Gate S/S # 8171 | 2485 | Diriyah Gate S/S # 8171-Precast PR | APPROVED | No | 2024-02-07 | Abas, Mohammed Fekry | 2024-02-07 | 2024-02-10 |  |  |  | 6508607 | 5235 | 0 | STANDARD | Kifah Precast Company | SAR | 6508607 | APPROVED |  |  | 2024-05-26 | 0 | 106 | Alhadi, Khalid | -45332 | 106
105-99 | Diriyah Gate S/S # 8171 | 2696 | Diriyah Gate S/S # 8171-PR_GIS | APPROVED | No | 2024-02-26 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 26878750 | 5189 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 26878750 | APPROVED |  |  | 2024-03-14 | 0 | 7 | Kumar, Mr. Ranjan | -45358 | 7
105-99 | Diriyah Gate S/S # 8171 | 2722 | Diriyah Gate S/S # 8171-PR_Civil water proving activity | RETURNED | No | 2024-02-28 | Tananeh, Khalid Jamal | 2025-08-19 | 2024-03-04 | 2025-08-19 |  | It is not reqired | 1284604.71 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45355 | -45355
105-99 | Diriyah Gate S/S # 8171 | 2888 | Diriyah Gate S/S # 8171-E&D | APPROVED | No | 2024-03-24 | Abas, Mohammed Fekry | 2024-03-28 | 2024-03-31 |  |  |  | 695000 | 5321 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 695000 | APPROVED |  |  | 2024-04-14 | 0 | 14 | Kumar, Mr. Ranjan | -45382 | 14
105-99 | Diriyah Gate S/S # 8171 | 2949 | Diriyah Gate S/S # 8171-bare copper_PR | APPROVED | No | 2024-03-31 | Abas, Mohammed Fekry | 2024-04-01 | 2024-04-02 |  |  |  | 159414.38 | 5339 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 159414.38 | APPROVED |  |  | 2024-04-18 | 0 | 16 | Alhadi, Khalid | -45384 | 16
105-99 | Diriyah Gate S/S # 8171 | 2949 | Diriyah Gate S/S # 8171-bare copper_PR | APPROVED | No | 2024-03-31 | Abas, Mohammed Fekry | 2024-04-01 | 2024-04-02 |  |  |  | 159414.38 | 5500 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 318828.75 | APPROVED |  |  | 2024-05-28 | -159414.38 | 56 | Alhadi, Khalid | -45384 | 56
105-99 | Diriyah Gate S/S # 8171 | 2975 | Diriyah Gate S/S # 8171-Fire Alarm and Fire fighting system-3.2.2 | APPROVED | No | 2024-04-02 | Abas, Mohammed Fekry | 2024-04-04 | 2024-04-07 |  |  |  | 2900000 | 5624 | 0 | STANDARD | Equipment & Technical Services Co.(ETECHS) | SAR | 2765000 | APPROVED |  |  | 2024-06-30 | 135000 | 84 | Alhadi, Khalid | -45389 | 84
105-99 | Diriyah Gate S/S # 8171 | 3050 | Diriyah Gate S/S # 8171-NGR | APPROVED | No | 2024-04-16 | Abas, Mohammed Fekry | 2024-04-17 | 2024-04-24 |  |  |  | 106125 | 5476 | 0 | STANDARD | National Switchgears | USD | 106125 | APPROVED |  |  | 2024-05-13 | 0 | 19 | Kumar, Mr. Ranjan | -45406 | 19
105-99 | Diriyah Gate S/S # 8171 | 3318 | Diriyah Gate S/S # 8171-PR- MV Termination kit | APPROVED | No | 2024-05-07 | Abas, Mohammed Fekry | 2024-05-09 | 2024-05-12 |  |  |  | 218966 | 5539 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 218966 | APPROVED |  |  | 2024-05-26 | 0 | 14 | Alhadi, Khalid | -45424 | 14
105-99 | Diriyah Gate S/S # 8171 | 3372 | Diriyah Gate S/S # 8171-HV Cables PR | REJECTED | No | 2024-05-12 | Nabi, Ashraf | 2024-05-12 |  |  | 2024-05-12 |  | 183276 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-99 | Diriyah Gate S/S # 8171 | 3390 | Diriyah Gate S/S # 8171- 120 sqmm conductor | APPROVED | No | 2024-05-13 | Abas, Mohammed Fekry | 2024-05-19 | 2024-05-19 |  |  |  | 32800 | 5595 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 32400 | APPROVED |  |  | 2024-05-27 | 400 | 8 | Alhadi, Khalid | -45431 | 8
105-99 | Diriyah Gate S/S # 8171 | 3399 | Diriyah Gate S/S # 8171-Heritage and Archaeological Site Specialist | RETURNED | No | 2024-05-14 | Alhadi, Khalid | 2024-07-29 | 2024-07-09 |  |  |  | 25000 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45482 | -45482
105-99 | Diriyah Gate S/S # 8171 | 3527 | Diriyah Gate S/S # 8171-PR_Civil Main subcontractor | APPROVED | No | 2024-05-29 | Abas, Mohammed Fekry | 2024-06-03 | 2024-06-03 |  |  |  | 14569912 | 5674 | 0 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 14569912 | APPROVED |  |  | 2024-06-26 | 0 | 23 | Alhadi, Khalid | -45446 | 23
105-99 | Diriyah Gate S/S # 8171 | 3527 | Diriyah Gate S/S # 8171-PR_Civil Main subcontractor | APPROVED | No | 2024-05-29 | Abas, Mohammed Fekry | 2024-06-03 | 2024-06-03 |  |  |  | 14569912 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45446 | -45446
105-99 | Diriyah Gate S/S # 8171 | 3642 | Diriyah Gate S/S # 8171-PT - Supervision Of installation, testing & commission | APPROVED | No | 2024-06-11 | Abas, Mohammed Fekry | 2024-06-12 | 2024-06-12 |  |  |  | 287500 | 5082 | 1 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 287500 | APPROVED |  |  | 2024-06-26 | 0 | 14 | Alhadi, Khalid | -45455 | 14
105-99 | Diriyah Gate S/S # 8171 | 3684 | Diriyah Gate S/S # 8171-Mobilization PR | APPROVED | No | 2024-06-27 | Abas, Mohammed Fekry | 2024-07-02 | 2024-07-02 |  |  |  | 297000 | 5766 | 0 | STANDARD | Construction Expertise Est. | SAR | 296130 | APPROVED |  |  | 2024-07-17 | 870 | 15 | Alhadi, Khalid | -45475 | 15
105-99 | Diriyah Gate S/S # 8171 | 4088 | Diriyah Gate S/S # 8171-Temp generators for mobilization and site | RETURNED | No | 2024-08-04 | Badhman, Saeed | 2024-10-30 | 2024-08-13 | 2024-10-30 |  | no need for it anymore | 250000 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45517 | -45517
105-99 | Diriyah Gate S/S # 8171 | 4089 | Diriyah Gate S/S # 8171-Insulated Y/G Copper conductor | RETURNED | No | 2024-08-04 | Alhadi, Khalid | 2024-08-07 | 2024-08-05 | 2024-08-07 |  | Items lines are missing | 69902.5 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45509 | -45509
105-99 | Diriyah Gate S/S # 8171 | 4092 | Diriyah Gate S/S # 8171-Accessories_Insulated Y/G Copper conductor | RETURNED | No | 2024-08-04 | Alhadi, Khalid | 2024-08-07 | 2024-08-05 | 2024-08-07 |  | Items lines are missing | 82200 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45509 | -45509
105-99 | Diriyah Gate S/S # 8171 | 4375 | Diriyah Gate S/S # 8171-Grounding Material Accessories | REJECTED | No | 2024-09-04 | Issa, Amr Ali | 2024-09-05 | 2024-09-05 |  | 2024-09-05 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45540 | -45540
105-99 | Diriyah Gate S/S # 8171 | 4404 | Diriyah Gate S/S # 8171-13.8Kv SWG | RETURNED | No | 2024-09-10 | Kumar, Mr. Ranjan | 2024-09-30 | 2024-09-22 | 2024-09-30 |  | 8388-HV1444-0 MV Switchgear alfanar - Diriyah Gate 8171 PO value is SAR 12,300,000. PR value is SAR 134,000. Please issue the PR value as per PO value | 134000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45557 | -45557
105-99 | Diriyah Gate S/S # 8171 | 4407 | Diriyah Gate S/S # 8171-Telecommunication System-SS#8171 | APPROVED | No | 2024-09-11 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 2000000 | 6265 | 0 | STANDARD | ALFANAR CO | SAR | 2000000 | APPROVED |  |  | 2024-10-06 | 0 | 14 | Kumar, Mr. Ranjan | -45557 | 14
105-99 | Diriyah Gate S/S # 8171 | 4409 | Diriyah Gate S/S # 8171-Control-Protection-SAS SS#8171 | APPROVED | No | 2024-09-11 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 10632000 | 6263 | 0 | STANDARD | ALFANAR CO | SAR | 10632000 | APPROVED |  |  | 2024-10-06 | 0 | 14 | Kumar, Mr. Ranjan | -45557 | 14
105-99 | Diriyah Gate S/S # 8171 | 4411 | Diriyah Gate S/S # 8171-RMUs for SS#8171 | APPROVED | No | 2024-09-11 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 139000 | 6234 | 0 | STANDARD | ALFANAR CO | SAR | 139000 | APPROVED |  |  | 2024-10-06 | 0 | 14 | Alhadi, Khalid | -45557 | 14
105-99 | Diriyah Gate S/S # 8171 | 4414 | Diriyah Gate S/S # 8171-Aux Transformers for SS#8171 | APPROVED | No | 2024-09-11 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 202000 | 6245 | 0 | STANDARD | ALFANAR CO | SAR | 202000 | APPROVED |  |  | 2024-10-06 | 0 | 14 | Alhadi, Khalid | -45557 | 14
105-99 | Diriyah Gate S/S # 8171 | 4416 | Diriyah Gate S/S # 8171-Cyber Security for SS#8171 | APPROVED | No | 2024-09-11 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 1590000 | 6301 | 0 | STANDARD | ALFANAR CO | SAR | 1590000 | APPROVED |  |  | 2024-10-21 | 0 | 29 | Alhadi, Khalid | -45557 | 29
105-99 | Diriyah Gate S/S # 8171 | 4418 | Diriyah Gate S/S # 8171-AC/DC and lighting panel SS#8171 | APPROVED | No | 2024-09-11 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 787000 | 6259 | 0 | STANDARD | ALFANAR CO | SAR | 787000 | APPROVED |  |  | 2024-10-06 | 0 | 14 | Alhadi, Khalid | -45557 | 14
105-99 | Diriyah Gate S/S # 8171 | 4453 | Diriyah Gate S/S # 8171-TPI for precasting work | REJECTED | No | 2024-09-15 | Hassan, Ahmed Abdelzaher Abdelrahim | 2024-09-15 |  |  | 2025-01-15 |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-99 | Diriyah Gate S/S # 8171 | 4483 | Diriyah Gate S/S # 8171-TPI for Precast Work SS#8171_Replaced | APPROVED | No | 2024-09-19 | Abas, Mohammed Fekry | 2024-09-24 | 2024-09-24 |  |  |  | 95190 | 6353 | 0 | STANDARD | Al Muhandis Nizar Al Kurdi Al Milli Engineering Consultants | SAR | 95190 | APPROVED |  |  | 2024-11-03 | 0 | 40 | Tananeh, Khalid Jamal | -45559 | 40
105-99 | Diriyah Gate S/S # 8171 | 4586 | Diriyah Gate S/S # 8171-Fuel for diesel generator for 8171 SS | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-06 | 2024-10-07 |  |  |  | 60000 | 6338 | 0 | STANDARD | Al-Masar Al-Monasib Company for Logistics Services | SAR | 59997.6 | APPROVED |  |  | 2024-11-04 | 2.4 | 28 | Akhtar, Farhan | -45572 | 28
105-99 | Diriyah Gate S/S # 8171 | 4871 | Diriyah Gate S/S # 8171-LV & Control cables materials for 8171 SS | APPROVED | No | 2024-11-08 | Abas, Mohammed Fekry | 2024-11-13 | 2024-11-13 |  |  |  | 2033154.35 | 6276 | 1 | STANDARD | ALFANAR CO | SAR | 1529411.95 | REQUIRES REAPPROVAL |  |  |  | 503742.4 | 445 | Badhman, Saeed | -45609 | -45609
105-99 | Diriyah Gate S/S # 8171 | 4871 | Diriyah Gate S/S # 8171-LV & Control cables materials for 8171 SS | APPROVED | No | 2024-11-08 | Abas, Mohammed Fekry | 2024-11-13 | 2024-11-13 |  |  |  | 2419998.95 | 6276 | 0 | STANDARD | ALFANAR CO | SAR | 2419998.95 | APPROVED |  |  | 2024-11-21 | 0 | 8 | Badhman, Saeed | -45609 | 8
105-99 | Diriyah Gate S/S # 8171 | 4871 | Diriyah Gate S/S # 8171-LV & Control cables materials for 8171 SS | APPROVED | No | 2024-11-08 | Abas, Mohammed Fekry | 2024-11-13 | 2024-11-13 |  |  |  | 386844.6 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45609 | -45609
105-99 | Diriyah Gate S/S # 8171 | 4933 | Diriyah Gate S/S # 8171-Split dula core CT for 8171 SS | APPROVED | No | 2024-11-13 | Abas, Mohammed Fekry | 2024-11-17 | 2024-11-17 |  |  |  | 48000 | 6519 | 0 | STANDARD | ELEQ B.V. | EUR | 44331.19 | APPROVED |  |  | 2024-11-20 | 3668.81 | 3 | Alhadi, Khalid | -45613 | 3
105-99 | Diriyah Gate S/S # 8171 | 4935 | Diriyah Gate S/S # 8171-HVAC supplies materials for 8171 SS | APPROVED | No | 2024-11-13 | Abas, Mohammed Fekry | 2024-11-17 | 2024-11-17 |  |  |  | 2370000 | 6530 | 0 | STANDARD | Ramz Alataa Company for Trading | SAR | 2370000 | APPROVED |  |  | 2024-11-28 | 0 | 11 | Alhadi, Khalid | -45613 | 11
105-99 | Diriyah Gate S/S # 8171 | 4960 | Diriyah Gate S/S # 8171-Secuirty system supplies for 8171 SS | APPROVED | No | 2024-11-14 | Abas, Mohammed Fekry | 2024-11-20 | 2024-11-21 |  |  |  | 725000 | 6606 | 0 | STANDARD | Equipment & Technical Services Co.(ETECHS) | SAR | 700000 | APPROVED |  |  | 2024-12-15 | 25000 | 24 | Alhadi, Khalid | -45617 | 24
105-99 | Diriyah Gate S/S # 8171 | 5007 | Diriyah Gate S/S # 8171-Cables trays & supports for 8171 SS | APPROVED | No | 2024-11-20 | Hassan, Ahmed Abdelzaher Abdelrahim | 2024-11-27 | 2024-11-27 |  |  |  | 400000 | 6566 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 400000 | APPROVED |  |  | 2024-12-15 | 0 | 18 | Alqadhi, Abdulrahman Abdulghani | -45623 | 18
105-99 | Diriyah Gate S/S # 8171 | 5065 | Diriyah Gate S/S # 8171-Y/G cables materials for 8171SS | APPROVED | No | 2024-11-27 | Abas, Mohammed Fekry | 2024-12-02 | 2024-12-03 |  |  |  | 70676.5 | 6645 | 0 | STANDARD | ALFANAR CO | SAR | 63240.5 | APPROVED |  |  | 2024-12-24 | 7436 | 21 | Alhadi, Khalid | -45629 | 21
105-99 | Diriyah Gate S/S # 8171 | 5073 | Diriyah Gate S/S # 8171-Supply of Rigid Steel Conduits for 8171 SS | APPROVED | No | 2024-11-27 | Abas, Mohammed Fekry | 2024-12-02 | 2024-12-03 |  |  |  | 22850.79 | 6588 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 22850.79 | APPROVED |  |  | 2024-12-16 | 0 | 13 | Alqadhi, Abdulrahman Abdulghani | -45629 | 13
105-99 | Diriyah Gate S/S # 8171 | 5197 | Diriyah Gate S/S # 8171-installation of 132 KV outdoor & Indoor type cable sealing ends for 8171 SS | APPROVED | No | 2024-12-08 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-12 |  |  |  | 76000 | 6704 | 0 | STANDARD | BRUGG CABLES COMAPNY | SAR | 76000 | APPROVED |  |  | 2025-01-09 | 0 | 28 | Alhadi, Khalid | -45638 | 28
105-99 | Diriyah Gate S/S # 8171 | 5199 | Diriyah Gate S/S # 8171-Change order for Extra ACDB panel for 8171 SS | REJECTED | No | 2024-12-09 | Yasmin, Ahmed Elsayed Mohamed | 2024-12-10 | 2024-12-10 |  | 2024-12-15 |  | 150000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45636 | -45636
105-99 | Diriyah Gate S/S # 8171 | 5306 | Diriyah Gate S/S # 8171-Ground accessores materials for SS# 8171 | RETURNED | No | 2024-12-31 | Alhadi, Khalid | 2025-02-25 | 2025-01-06 | 2025-02-25 |  | Not required | 93710 | 6862 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 82841 | APPROVED |  |  | 2025-02-19 | 10869 |  | Alhadi, Khalid | -45663 | 44
105-99 | Diriyah Gate S/S # 8171 | 5378 | Diriyah Gate S/S # 8171-Fuel for diesel generator for 8171 SS | APPROVED | No | 2025-01-08 | Abas, Mohammed Fekry | 2025-01-12 | 2025-01-12 |  |  |  | 60000 | 6742 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 47241.54 | APPROVED |  |  | 2025-01-16 | 12758.46 | 4 | Akhtar, Farhan | -45669 | 4
105-99 | Diriyah Gate S/S # 8171 | 5444 | Diriyah Gate S/S # 8171-CONSTRUCTION OF NEW 132/13.8 KV DIRIYAH GATE SS 8171 | REJECTED | No | 2025-01-16 | Yasmin, Ahmed Elsayed Mohamed | 2025-01-19 | 2025-01-19 |  | 2025-01-19 |  | 81250 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45676 | -45676
105-99 | Diriyah Gate S/S # 8171 | 5458 | Diriyah Gate S/S # 8171-CONSTRUCTION OF NEW 132/13.8 KV DIRIYAH GATE SS 8171 | APPROVED | No | 2025-01-19 | Abas, Mohammed Fekry | 2025-01-23 | 2025-01-23 |  |  |  | 182075 | 6955 | 0 | STANDARD | Tawasul International Trad.Est. | SAR | 165171.15 | APPROVED |  |  | 2025-03-13 | 16903.85 | 49 | Alhadi, Khalid | -45680 | 49
105-99 | Diriyah Gate S/S # 8171 | 5473 | Diriyah Gate S/S # 8171-MV& HV cables for 8171SS | APPROVED | No | 2025-01-20 | Abas, Mohammed Fekry | 2025-01-23 | 2025-01-23 |  |  |  | 1882844 | 5503 | 4 | STANDARD | Riyadh Cables Group Company | SAR | 1882844 | APPROVED |  |  | 2025-02-27 | 0 | 35 | Alhadi, Khalid | -45680 | 35
105-99 | Diriyah Gate S/S # 8171 | 5473 | Diriyah Gate S/S # 8171-MV& HV cables for 8171SS | APPROVED | No | 2025-01-20 | Abas, Mohammed Fekry | 2025-01-23 | 2025-01-23 |  |  |  | 1882844 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45680 | -45680
105-99 | Diriyah Gate S/S # 8171 | 5521 | Diriyah Gate S/S # 8171-Grounding accessories - CONSTRUCTION OF NEW 132/13.8 KV DIRIYAH GATE SS 8171 | RETURNED | No | 2025-01-21 | Alhadi, Khalid | 2025-02-26 | 2025-01-23 | 2025-02-26 |  | Duplicated Lines | 8400 | 6862 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 8400 | APPROVED |  |  | 2025-02-19 | 0 |  | Alhadi, Khalid | -45680 | 27
105-99 | Diriyah Gate S/S # 8171 | 5709 | Diriyah Gate S/S # 8171-Lightning Masts and lighting poles for Diriyah Gate 8171 SS | APPROVED | No | 2025-01-28 | Abas, Mohammed Fekry | 2025-02-12 | 2025-02-13 |  |  |  | 91750 | 6984 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 86610 | APPROVED |  |  | 2025-03-13 | 5140 | 28 | Alhadi, Khalid | -45701 | 28
105-99 | Diriyah Gate S/S # 8171 | 5712 | Diriyah Gate S/S # 8171-Supply materials of 132 KV Out door & indoor type cable sealing Ends for 8171 SS | APPROVED | No | 2025-01-29 | Abas, Mohammed Fekry | 2025-02-05 | 2025-02-05 |  |  |  | 192525 | 6902 | 0 | STANDARD | BRUGG CABLES COMAPNY | CHF | 192525 | APPROVED |  |  | 2025-02-19 | 0 | 14 | Alhadi, Khalid | -45693 | 14
105-99 | Diriyah Gate S/S # 8171 | 5738 | Diriyah Gate S/S # 8171-HV and MV cable supports for Diriyah Gate 8171 | RETURNED | No | 2025-01-30 | Alhadi, Khalid | 2025-06-19 | 2025-02-13 | 2025-06-19 |  | As PM request due to budget issue | 102550 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45701 | -45701
105-99 | Diriyah Gate S/S # 8171 | 5755 | Diriyah Gate S/S # 8171-Lighting Fixtures for Diriyah Gate 8171 SS | APPROVED | No | 2025-02-26 | Abas, Mohammed Fekry | 2025-03-02 | 2025-03-03 |  |  |  | 107534 | 6963 | 0 | STANDARD | Integrated Lighting Co.,LED - Rayon | SAR | 86201 | APPROVED |  |  | 2025-04-15 | 21333 | 43 | Alhadi, Khalid | -45719 | 43
105-99 | Diriyah Gate S/S # 8171 | 5762 | Diriyah Gate S/S # 8171-MVand HV cable Cleats for Diriyah Gate SS 8171 | RETURNED | No | 2025-02-03 | Alhadi, Khalid | 2025-06-19 | 2025-02-13 | 2025-06-19 |  | As PM request due to budget issue | 75170 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45701 | -45701
105-99 | Diriyah Gate S/S # 8171 | 5782 | Diriyah Gate S/S # 8171-Overhead clamps and connections of ASCR for Diriyah Gate 8171 | APPROVED | No | 2025-02-04 | Abas, Mohammed Fekry | 2025-02-12 | 2025-02-13 |  |  |  | 13141 | 6990 | 0 | STANDARD | Arruti Subestaciones , S.A.U | SAR | 10149 | APPROVED |  |  | 2025-03-13 | 2992 | 28 | Alqadhi, Abdulrahman Abdulghani | -45701 | 28
105-99 | Diriyah Gate S/S # 8171 | 5786 | Diriyah Gate S/S # 8171-wires of Lighting sys of Diriyah Gate SS 8171 | REJECTED | No | 2025-02-04 | Hassan, Ahmed Abdelzaher Abdelrahim | 2025-02-04 |  |  | 2025-02-04 |  | 157439.8 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
105-99 | Diriyah Gate S/S # 8171 | 5789 | Diriyah Gate S/S # 8171-wires of Lighting sys for Diriyah Gate SS 8171 | REJECTED | No | 2025-02-05 | Hassan, Ahmed Abdelzaher Abdelrahim | 2025-02-05 |  |  | 2025-02-05 |  | 157439.8 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
105-99 | Diriyah Gate S/S # 8171 | 5791 | Diriyah Gate S/S # 8171-wires for lighting sys for Diriyah Gate ss 8171 | REJECTED | No | 2025-02-05 | Hassan, Ahmed Abdelzaher Abdelrahim | 2025-02-05 |  |  | 2025-02-05 |  | 157439.8 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
105-99 | Diriyah Gate S/S # 8171 | 5794 | Diriyah Gate S/S # 8171-LV Cable Glands for Diriyah Gate SS 8171 | RETURNED | No | 2025-02-05 | Alhadi, Khalid | 2025-03-10 | 2025-02-13 | 2025-03-10 |  | It will be secured from petty cash | 1617 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45701 | -45701
105-99 | Diriyah Gate S/S # 8171 | 5811 | Diriyah Gate S/S # 8171-wiring of lighting sys for Diriyah ss 8171 | REJECTED | No | 2025-02-06 | Hassan, Ahmed Abdelzaher Abdelrahim | 2025-02-06 |  |  | 2025-02-06 |  | 155588 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
105-99 | Diriyah Gate S/S # 8171 | 5859 | Diriyah Gate S/S # 8171-Applay and supplay for internal sealant work for precast for 8171 SS | APPROVED | No | 2025-02-12 | Abas, Mohammed Fekry | 2025-02-16 | 2025-02-18 |  |  |  | 105000 | 7043 | 0 | STANDARD | ATTON ANSHAIYA For General Contracting Establishment | SAR | 96000 | APPROVED |  |  | 2025-04-21 | 9000 | 62 | Tananeh, Khalid Jamal | -45706 | 62
105-99 | Diriyah Gate S/S # 8171 | 6003 | Diriyah Gate S/S # 8171-Testing and commissioning subcontractor for 8171SS | APPROVED | No | 2025-02-19 | Abas, Mohammed Fekry | 2025-02-20 | 2025-02-22 |  |  |  | 1808041 | 7040 | 0 | STANDARD |  | SAR | 1808041 | INCOMPLETE |  |  |  | 0 | 344 | Babic, Marian | -45710 | -45710
105-99 | Diriyah Gate S/S # 8171 | 6003 | Diriyah Gate S/S # 8171-Testing and commissioning subcontractor for 8171SS | APPROVED | No | 2025-02-19 | Abas, Mohammed Fekry | 2025-02-20 | 2025-02-22 |  |  |  | 1808041 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45710 | -45710
105-99 | Diriyah Gate S/S # 8171 | 6074 | Diriyah Gate S/S # 8171-Loading ,transportation and unloading for Power transformers for 8171 SS | APPROVED | No | 2025-02-26 | Abas, Mohammed Fekry | 2025-03-03 | 2025-03-05 |  |  |  | 300000 | 7129 | 0 | STANDARD | MOHAMMED HAMAD AL-AHMADE FOR TRADING AND CONSTRACTION | SAR | 151000 | APPROVED |  |  | 2025-06-15 | 149000 | 102 | Badhman, Saeed | -45721 | 102
105-99 | Diriyah Gate S/S # 8171 | 6116 | Diriyah Gate S/S # 8171-lighting fixtures (missed item )for Diriyah ss 8171 | APPROVED | No | 2025-03-05 | Abas, Mohammed Fekry | 2025-03-20 | 2025-03-20 |  |  |  | 1190 | 6963 | 0 | STANDARD | Integrated Lighting Co.,LED - Rayon | SAR | 950 | APPROVED |  |  | 2025-04-15 | 240 | 26 | Alhadi, Khalid | -45736 | 26
105-99 | Diriyah Gate S/S # 8171 | 6131 | Diriyah Gate S/S # 8171-Fuel for diesel generator | APPROVED | No | 2025-03-06 | Abas, Mohammed Fekry | 2025-03-19 | 2025-03-20 |  |  |  | 12758.46 | 6742 | 1 | STANDARD | Talaea Alahlam Trading Company | SAR | 12756.97 | APPROVED |  |  | 2025-04-14 | 1.49 | 25 | Akhtar, Farhan | -45736 | 25
105-99 | Diriyah Gate S/S # 8171 | 6388 | Diriyah Gate S/S # 8171-Fuel for diesel generator for 8171 SS | APPROVED | No | 2025-04-20 | Abas, Mohammed Fekry | 2025-04-21 | 2025-04-21 |  |  |  | 100000 | 7367 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 100000 | APPROVED |  |  | 2025-06-03 | 0 | 43 | Akhtar, Farhan | -45768 | 43
105-99 | Diriyah Gate S/S # 8171 | 6475 | Diriyah Gate S/S # 8171-Surge arrestor for 8171 | APPROVED | No | 2025-04-28 | Abas, Mohammed Fekry | 2025-04-30 | 2025-04-30 |  |  |  | 96600 | 7215 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 96599.79 | APPROVED |  |  | 2025-05-05 | 0.21 | 5 | Kumar, Mr. Ranjan | -45777 | 5
105-99 | Diriyah Gate S/S # 8171 | 6555 | Diriyah Gate S/S # 8171-Electrical installation subcontractor for 8171SS | APPROVED | No | 2025-05-07 | Abas, Mohammed Fekry | 2025-05-11 | 2025-05-11 |  |  |  | 3320000 | 7080 | 0 | STANDARD | City Crowns Energy | SAR | 3318000 | APPROVED |  |  | 2025-06-24 | 2000 | 44 | Alhadi, Khalid | -45788 | 44
105-99 | Diriyah Gate S/S # 8171 | 6566 | Diriyah Gate S/S # 8171-wires for lighting and Sockets | APPROVED | No | 2025-05-08 | Abas, Mohammed Fekry | 2025-05-15 | 2025-05-15 |  |  |  | 92472.3 | 6276 | 1 | STANDARD | ALFANAR CO | SAR | 98142.1 | REQUIRES REAPPROVAL |  |  |  | -5669.8 | 262 | Badhman, Saeed | -45792 | -45792
105-99 | Diriyah Gate S/S # 8171 | 6566 | Diriyah Gate S/S # 8171-wires for lighting and Sockets | APPROVED | No | 2025-05-08 | Abas, Mohammed Fekry | 2025-05-15 | 2025-05-15 |  |  |  | 60358 | 7222 | 0 | STANDARD | AL FANAR CABLES COMPANY | SAR | 60358 | APPROVED |  |  | 2025-09-28 | 0 | 136 | Badhman, Saeed | -45792 | 136
105-99 | Diriyah Gate S/S # 8171 | 6566 | Diriyah Gate S/S # 8171-wires for lighting and Sockets | APPROVED | No | 2025-05-08 | Abas, Mohammed Fekry | 2025-05-15 | 2025-05-15 |  |  |  | 92472.3 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45792 | -45792
105-99 | Diriyah Gate S/S # 8171 | 6594 | Diriyah Gate S/S # 8171-Accessories of lighting and sockets installation | REJECTED | No | 2025-05-12 | Hassan, Ahmed Abdelzaher Abdelrahim | 2025-05-12 |  |  | 2025-05-12 |  | 187369.35 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
105-99 | Diriyah Gate S/S # 8171 | 6595 | Diriyah Gate S/S # 8171-accessories of lighting sys installation | RETURNED | No | 2025-05-12 | Alhadi, Khalid | 2025-06-30 | 2025-05-18 | 2025-06-30 |  | Due to a budget issue in the unit price | 195125.35 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45795 | -45795
105-99 | Diriyah Gate S/S # 8171 | 6881 | Diriyah Gate S/S # 8171-MV and HV cable cleats | APPROVED | No | 2025-06-24 | Abas, Mohammed Fekry | 2025-06-30 | 2025-07-01 |  |  |  | 76764.75 | 7436 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 76764.75 | APPROVED |  |  | 2025-07-03 | 0 | 2 | Alhadi, Khalid | -45839 | 2
105-99 | Diriyah Gate S/S # 8171 | 6884 | Diriyah Gate S/S # 8171-HV and MV cables supports | APPROVED | No | 2025-06-24 | Abas, Mohammed Fekry | 2025-06-30 | 2025-07-01 |  |  |  | 32076.82 | 7438 | 0 | STANDARD | Power Solution Industries | SAR | 30576.82 | APPROVED |  |  | 2025-07-08 | 1500 | 7 | Alhadi, Khalid | -45839 | 7
105-99 | Diriyah Gate S/S # 8171 | 6935 | Diriyah Gate S/S # 8171-Accessories of lighting sys installation | REJECTED | No | 2025-07-01 | Hassan, Ahmed Abdelzaher Abdelrahim | 2025-07-01 |  |  | 2025-07-01 |  | 172874.61 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
105-99 | Diriyah Gate S/S # 8171 | 6962 | Diriyah Gate S/S # 8171-accessories of lighting sys installation | APPROVED | No | 2025-07-01 | Abas, Mohammed Fekry | 2025-07-03 | 2025-07-04 |  |  |  | 183243.01 | 7479 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 183243.01 | APPROVED |  |  | 2025-07-16 | 0 | 12 | Alhadi, Khalid | -45842 | 12
105-99 | Diriyah Gate S/S # 8171 | 7023 | Diriyah Gate S/S # 8171-Supply, Laying and Testing Fiber optic and communication cables for 8171 SS | APPROVED | No | 2025-07-09 | Abas, Mohammed Fekry | 2025-07-15 | 2025-07-16 |  |  |  | 287500 | 7363 | 0 | STANDARD | RASHID SAEED AHMED AL GHAMDI COMM INFO TRAD EST | SAR | 287500 | APPROVED |  |  | 2025-07-29 | 0 | 13 | Muaz, Alaa | -45854 | 13
105-99 | Diriyah Gate S/S # 8171 | 7163 | Diriyah Gate S/S # 8171-supply of Earthing Material | APPROVED | No | 2025-07-21 | Abas, Mohammed Fekry | 2025-07-22 | 2025-07-22 |  |  |  | 65814 | 6350 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 65814 | APPROVED |  |  | 2025-08-03 | 0 | 12 | Alhadi, Khalid | -45860 | 12
105-99 | Diriyah Gate S/S # 8171 | 7175 | Diriyah Gate S/S # 8171-supply of MV and HV cables | RETURNED | No | 2025-07-21 | Alhadi, Khalid | 2025-10-06 | 2025-10-03 | 2025-10-06 |  | PRs is duplicated | 492366.59 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45933 | -45933
105-99 | Diriyah Gate S/S # 8171 | 7579 | transportatiuon of power transformers | APPROVED | No | 2025-08-31 | Abas, Mohammed Fekry | 2025-09-01 | 2025-09-01 |  |  | pls approve | 0 | 7129 | 1 | STANDARD | MOHAMMED HAMAD AL-AHMADE FOR TRADING AND CONSTRACTION | SAR | 30000 | APPROVED |  |  | 2025-09-28 | -30000 | 27 | Badhman, Saeed | -45901 | 27
105-99 | Diriyah Gate S/S # 8171 | 7754 | Anchor bolts for cap banks | REJECTED | No | 2025-09-15 | Yasmin, Ahmed Elsayed Mohamed | 2025-09-16 | 2025-09-16 |  | 2025-09-21 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45916 | -45916
105-99 | Diriyah Gate S/S # 8171 | 7763 | supply of MV and HV cables | APPROVED | No | 2025-09-16 | Abas, Mohammed Fekry | 2025-09-21 | 2025-09-21 |  |  |  | 0 | 5503 | 5 | STANDARD | Riyadh Cables Group Company | SAR | 492366.59 | APPROVED |  |  | 2025-10-16 | -492366.59 | 25 | Alhadi, Khalid | -45921 | 25
105-99 | Diriyah Gate S/S # 8171 | 7772 | patch core panels | REJECTED | No | 2025-09-17 | Yasmin, Ahmed Elsayed Mohamed | 2025-09-21 | 2025-09-21 |  | 2025-09-21 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45921 | -45921
105-99 | Diriyah Gate S/S # 8171 | 7805 | Patch core panels for ss 8171 | RETURNED | No | 2025-09-21 | Alhadi, Khalid | 2025-11-13 | 2025-09-28 | 2025-11-13 |  | Please provide complete and final scope | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45928 | -45928
105-99 | Diriyah Gate S/S # 8171 | 8165 | Steel structure of CSE ss 8171 | APPROVED | No | 2025-11-10 | Abas, Mohammed Fekry | 2025-11-18 | 2025-11-19 |  |  | steel structure of CSE for ss 8171 | 0 | 7944 | 0 | STANDARD | Fursan Construction Industry Factory Industry Factory | SAR | 35400 | APPROVED |  |  | 2025-12-08 | -35400 | 19 | Hegazy, Ayman | -45980 | 19
105-99 | Diriyah Gate S/S # 8171 | 8293 | fiber optic patch core panels ss 8171 | REJECTED | No | 2025-11-20 | Yasmin, Ahmed Elsayed Mohamed | 2025-11-20 | 2025-11-20 |  | 2025-11-26 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45981 | -45981
105-99 | Diriyah Gate S/S # 8171 | 8355 | AC sup panel SDP - 3 | RETURNED | No | 2025-11-26 | Alhadi, Khalid | 2025-12-08 | 2025-12-02 | 2025-12-08 |  | No POCR | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45993 | -45993
105-99 | Diriyah Gate S/S # 8171 | 8360 | Supply of FO patch core panels | APPROVED | No | 2025-11-26 | Abas, Mohammed Fekry | 2025-12-02 | 2025-12-02 |  |  |  | 0 | 7363 | 1 | STANDARD | RASHID SAEED AHMED AL GHAMDI COMM INFO TRAD EST | SAR | 50000 | APPROVED | 2026-01-11 | 2026-01-13 | 2026-01-22 | -50000 | 51 | Alhadi, Khalid | 42 | 51
105-99 | Diriyah Gate S/S # 8171 | 8366 | link boxes and bonding cables | RETURNED | No | 2025-11-26 | Hegazy, Ayman | 2026-01-06 | 2025-12-02 | 2026-01-06 |  | returned based on PM request to hold the process | 0 | 15019 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 21800 | REJECTED |  |  |  | -21800 |  | Hegazy, Ayman | -45993 | -45993
105-99 | Diriyah Gate S/S # 8171 | 8366 | link boxes and bonding cables | RETURNED | No | 2025-11-26 | Hegazy, Ayman | 2026-01-06 | 2025-12-02 | 2026-01-06 |  | returned based on PM request to hold the process | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -45993 | -45993
105-99 | Diriyah Gate S/S # 8171 | 8375 | PDS cabinet and 42U rack panel | RETURNED | No | 2025-11-27 | Alhadi, Khalid | 2025-12-08 | 2025-12-02 | 2025-12-08 |  | No Details | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45993 | -45993
105-99 | Diriyah Gate S/S # 8171 | 8378 | 6 SWGR defected MV SWGR panels | RETURNED | No | 2025-11-27 | Alhadi, Khalid | 2025-12-08 | 2025-12-02 | 2025-12-08 |  | No PoCR | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45993 | -45993
105-99 | Diriyah Gate S/S # 8171 | 8477 | control & lv cables 8171 | APPROVED | No | 2025-12-08 | Abas, Mohammed Fekry | 2025-12-15 | 2025-12-17 |  |  |  | 0 | 6276 | 1 | STANDARD | ALFANAR CO | SAR | 608811.4 | REQUIRES REAPPROVAL |  |  |  | -608811.4 | 46 | Badhman, Saeed | -46008 | -46008
105-99 | Diriyah Gate S/S # 8171 | 8477 | control & lv cables 8171 | APPROVED | No | 2025-12-08 | Abas, Mohammed Fekry | 2025-12-15 | 2025-12-17 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -46008 | -46008
105-99 | Diriyah Gate S/S # 8171 | 8507 | Diesel Supply SS 8171 | APPROVED | No | 2025-12-11 | Abas, Mohammed Fekry | 2025-12-15 | 2025-12-17 |  |  | Diesel Supply SS 8171 | 0 | 7367 | 1 | STANDARD | Talaea Alahlam Trading Company | SAR | 65999.01 | APPROVED | 2025-12-18 | 2026-01-01 | 2026-01-05 | -65999.01 | 19 | Akhtar, Farhan | 15 | 19
105-99 | Diriyah Gate S/S # 8171 | 8535 | AC sub panel SDP-3 | APPROVED | No | 2025-12-16 | Abas, Mohammed Fekry | 2025-12-29 | 2026-01-01 |  |  | kindly approve as this returned by procurement team | 0 | 6259 | 1 | STANDARD | ALFANAR CO | SAR | 150000 | APPROVED | 2026-01-06 | 2026-01-13 | 2026-01-15 | -150000 | 14 | Alhadi, Khalid | 12 | 14
105-99 | Diriyah Gate S/S # 8171 | 8536 | PDS cabinet and 42U rack panel | APPROVED | No | 2025-12-16 | Abas, Mohammed Fekry | 2025-12-29 | 2026-01-01 |  |  | kindly approve as this returned by procurement team | 0 | 15054 | 0 | STANDARD |  | SAR | 0 | INCOMPLETE |  |  |  | 0 | 31 | Alhadi, Khalid | -46023 | -46023
105-99 | Diriyah Gate S/S # 8171 | 8536 | PDS cabinet and 42U rack panel | APPROVED | No | 2025-12-16 | Abas, Mohammed Fekry | 2025-12-29 | 2026-01-01 |  |  | kindly approve as this returned by procurement team | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46023 | -46023
105-99 | Diriyah Gate S/S # 8171 | 8604 | Fire Stop Material | APPROVED | No | 2025-12-29 | Abas, Mohammed Fekry | 2026-01-13 | 2026-01-13 |  |  | fire stop materials | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -46035 | -46035
105-99 | Diriyah Gate S/S # 8171 | 8688 | modification of steel panel support of control room ss 8171 | APPROVED | No | 2026-01-12 | Abas, Mohammed Fekry | 2026-01-22 | 2026-01-25 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46047 | -46047
105-99 | Diriyah Gate S/S # 8171 | 8782 | 240 YG cabel for ss 8171 | IN PROCESS | No | 2026-01-25 | Yasmin, Ahmed Elsayed Mohamed | 2026-01-25 | 2026-01-25 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46047 | -46047
105-99 | Diriyah Gate S/S # 8171 | 8788 | 150 bare CU conductor | IN PROCESS | No | 2026-01-25 | Yasmin, Ahmed Elsayed Mohamed | 2026-01-25 | 2026-01-25 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46047 | -46047
105-99 | Diriyah Gate S/S # 8171 | 8793 | Electrical Technicians | APPROVED | No | 2026-01-26 | Abas, Mohammed Fekry | 2026-01-26 | 2026-01-27 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46049 | -46049
105-100 | Diriyah Gate S/S # 8242 | 1680 | Diriyah Gate S/S # 8242-PR for precast | RETURNED | No | 2023-11-12 | Kumar, Mr. Ranjan | 2023-11-23 | 2023-11-16 | 2023-11-23 |  | Please correct unit Price its mentioned as SAR 1 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45246 | -45246
105-100 | Diriyah Gate S/S # 8242 | 1681 | Diriyah Gate S/S # 8242-PR for two Generators | APPROVED | No | 2023-11-12 | Abas, Mohammed Fekry | 2023-11-14 | 2023-11-15 |  |  |  | 250000 | 4738 | 0 | STANDARD | Mohammed A. AlFaddaghi & Partners | SAR | 250000 | APPROVED |  |  | 2023-12-04 | 0 | 19 | Badhman, Saeed | -45245 | 19
105-100 | Diriyah Gate S/S # 8242 | 1681 | Diriyah Gate S/S # 8242-PR for two Generators | APPROVED | No | 2023-11-12 | Abas, Mohammed Fekry | 2023-11-14 | 2023-11-15 |  |  |  | 250000 | 4738 | 1 | STANDARD | Mohammed A. AlFaddaghi & Partners | SAR | 241500 | APPROVED |  |  | 2024-04-15 | 8500 | 152 | Badhman, Saeed | -45245 | 152
105-100 | Diriyah Gate S/S # 8242 | 1699 | Diriyah Gate S/S # 8242-PR for Capacitor bank | APPROVED | No | 2023-11-13 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 2090200 | 4797 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 2090200 | APPROVED |  |  | 2023-12-20 | 0 | 34 | Kumar, Mr. Ranjan | -45246 | 34
105-100 | Diriyah Gate S/S # 8242 | 1731 | Diriyah Gate S/S # 8242- PR For GIS | APPROVED | No | 2023-11-27 | Abas, Mohammed Fekry | 2023-11-28 | 2023-11-28 |  |  |  | 23165000 | 4815 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 23165000 | APPROVED |  |  | 2023-12-17 | 0 | 19 | Kumar, Mr. Ranjan | -45258 | 19
105-100 | Diriyah Gate S/S # 8242 | 1836 | Diriyah Gate S/S # 8242-PR_13.8KV Switchgear | APPROVED | No | 2023-11-28 | Abas, Mohammed Fekry | 2023-11-30 | 2023-12-04 |  |  |  | 12550000 | 5703 | 0 | STANDARD | ALFANAR CO | SAR | 12550000 | APPROVED |  |  | 2024-07-09 | 0 | 218 | Kumar, Mr. Ranjan | -45264 | 218
105-100 | Diriyah Gate S/S # 8242 | 1840 | Diriyah Gate S/S # 8242-PR_SOIL INVESTIGATION | APPROVED | No | 2023-11-28 | Abas, Mohammed Fekry | 2023-11-30 | 2023-12-04 |  |  |  | 17910 | 5237 | 0 | STANDARD | International Agent Commercial Company(S) | SAR | 17910 | APPROVED |  |  | 2024-03-20 | 0 | 107 | Kumar, Mr. Ranjan | -45264 | 107
105-100 | Diriyah Gate S/S # 8242 | 1844 | Diriyah Gate S/S # 8242-Power TR PR | APPROVED | No | 2023-11-28 | Abas, Mohammed Fekry | 2023-11-30 | 2023-12-04 |  |  |  | 26287500 | 5085 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 26287500 | APPROVED |  |  | 2024-02-25 | 0 | 83 | Alhadi, Khalid | -45264 | 83
105-100 | Diriyah Gate S/S # 8242 | 1844 | Diriyah Gate S/S # 8242-Power TR PR | APPROVED | No | 2023-11-28 | Abas, Mohammed Fekry | 2023-11-30 | 2023-12-04 |  |  |  | 26287500 | 5085 | 1 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 26000000 | APPROVED |  |  | 2024-06-26 | 287500 | 205 | Alhadi, Khalid | -45264 | 205
105-100 | Diriyah Gate S/S # 8242 | 1891 | Diriyah Gate S/S # 8242-PR_Battary & Charger | APPROVED | No | 2023-12-05 | Abas, Mohammed Fekry | 2023-12-06 | 2023-12-07 |  |  |  | 472500 | 4810 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 472500 | APPROVED |  |  | 2023-12-19 | 0 | 12 | Alhadi, Khalid | -45267 | 12
105-100 | Diriyah Gate S/S # 8242 | 1908 | Diriyah Gate S/S # 8242-PR_ESIA | APPROVED | No | 2023-12-06 | Abas, Mohammed Fekry | 2023-12-07 | 2023-12-10 |  |  |  | 18000 | 5089 | 0 | STANDARD | Aran Aljazeera Enviromental Consultant | SAR | 18000 | APPROVED |  |  | 2024-02-18 | 0 | 70 | Alhadi, Khalid | -45270 | 70
105-100 | Diriyah Gate S/S # 8242 | 2123 | Diriyah Gate S/S # 8242-Moblization | APPROVED | No | 2024-01-09 | Abas, Mohammed Fekry | 2024-01-10 | 2024-01-10 |  |  |  | 396300 | 4983 | 0 | STANDARD | Construction Expertise Est. | SAR | 396300 | APPROVED |  |  | 2024-02-06 | 0 | 27 | Alhadi, Khalid | -45301 | 27
105-100 | Diriyah Gate S/S # 8242 | 2165 | Diriyah Gate S/S # 8242-Supply of IT Requirments | APPROVED | No | 2024-01-15 | Abas, Mohammed Fekry | 2024-01-16 | 2024-01-17 |  |  |  | 21295 | 5023 | 0 | STANDARD | Mohmmed Abdulrahman AlZahid IT CO. | SAR | 21295 | APPROVED |  |  | 2024-02-06 | 0 | 20 | Akhtar, Farhan | -45308 | 20
105-100 | Diriyah Gate S/S # 8242 | 2260 | Diriyah Gate S/S # 8242-OHTC_PR | APPROVED | No | 2024-01-23 | Abas, Mohammed Fekry | 2024-01-24 | 2024-01-25 |  |  |  | 138500 | 5019 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 138500 | APPROVED |  |  | 2024-02-06 | 0 | 12 | Alhadi, Khalid | -45316 | 12
105-100 | Diriyah Gate S/S # 8242 | 2484 | Diriyah Gate S/S # 8242-Precast PR | REJECTED | No | 2024-02-07 | Alnaeem, Rami Mayraghany alkaram | 2024-02-07 | 2024-02-07 |  | 2024-02-07 |  | 6508607 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45329 | -45329
105-100 | Diriyah Gate S/S # 8242 | 2488 | Diriyah Gate S/S # 8242-Precast PR | APPROVED | No | 2024-02-07 | Abas, Mohammed Fekry | 2024-02-11 | 2024-02-12 |  |  |  | 6705919 | 5234 | 0 | STANDARD | Kifah Precast Company | SAR | 6705919 | APPROVED |  |  | 2024-05-30 | 0 | 108 | Alhadi, Khalid | -45334 | 108
105-100 | Diriyah Gate S/S # 8242 | 2565 | Diriyah Gate S/S # 8242-Shunt reactor | APPROVED | No | 2024-02-15 | Abas, Mohammed Fekry | 2024-02-19 | 2024-02-21 |  |  |  | 7312500 | 5128 | 0 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 7312500 | APPROVED |  |  | 2024-03-14 | 0 | 22 | Alhadi, Khalid | -45343 | 22
105-100 | Diriyah Gate S/S # 8242 | 2715 | Diriyah Gate S/S # 8242-PR_ Civil water proving | APPROVED | No | 2024-02-28 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 1136563.89 | 5713 | 0 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 731669.32 | APPROVED |  |  | 2024-07-25 | 404894.57 | 140 | Tananeh, Khalid Jamal | -45358 | 140
105-100 | Diriyah Gate S/S # 8242 | 2887 | Diriyah Gate S/S # 8242-E&D | APPROVED | No | 2024-03-24 | Abas, Mohammed Fekry | 2024-03-28 | 2024-03-28 |  |  |  | 695000 | 5323 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 695000 | APPROVED |  |  | 2024-04-14 | 0 | 17 | Kumar, Mr. Ranjan | -45379 | 17
105-100 | Diriyah Gate S/S # 8242 | 2900 | Diriyah Gate S/S # 8242-Water and Sewage_PR | RETURNED | No | 2024-03-25 | Alhadi, Khalid | 2024-06-12 | 2024-03-31 | 2024-06-12 |  | No details about the required service | 27000 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45382 | -45382
105-100 | Diriyah Gate S/S # 8242 | 2901 | Diriyah Gate S/S # 8242-Electricity - Operation_Diesal PR | APPROVED | No | 2024-03-25 | Abas, Mohammed Fekry | 2024-03-28 | 2024-03-31 |  |  |  | 60000 | 5411 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 59500 | APPROVED |  |  | 2024-05-14 | 500 | 44 | Akhtar, Farhan | -45382 | 44
105-100 | Diriyah Gate S/S # 8242 | 2950 | Diriyah Gate S/S # 8242-bare copper_PR | APPROVED | No | 2024-03-31 | Abas, Mohammed Fekry | 2024-04-01 | 2024-04-02 |  |  |  | 159414.38 | 5340 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 159414.38 | APPROVED |  |  | 2024-04-18 | 0 | 16 | Alhadi, Khalid | -45384 | 16
105-100 | Diriyah Gate S/S # 8242 | 2950 | Diriyah Gate S/S # 8242-bare copper_PR | APPROVED | No | 2024-03-31 | Abas, Mohammed Fekry | 2024-04-01 | 2024-04-02 |  |  |  | 159414.38 | 5500 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 318828.75 | APPROVED |  |  | 2024-05-28 | -159414.38 | 56 | Alhadi, Khalid | -45384 | 56
105-100 | Diriyah Gate S/S # 8242 | 2979 | Diriyah Gate S/S # 8242-Fire Alarm and Fire fighting system-3.2.2 | APPROVED | No | 2024-04-02 | Abas, Mohammed Fekry | 2024-04-04 | 2024-04-04 |  |  |  | 2900000 | 5622 | 0 | STANDARD | Equipment & Technical Services Co.(ETECHS) | SAR | 2895000 | APPROVED |  |  | 2024-06-30 | 5000 | 87 | Alhadi, Khalid | -45386 | 87
105-100 | Diriyah Gate S/S # 8242 | 3049 | Diriyah Gate S/S # 8242-NGR | APPROVED | No | 2024-04-16 | Abas, Mohammed Fekry | 2024-04-20 | 2024-04-24 |  |  |  | 106125 | 5477 | 0 | STANDARD | National Switchgears | USD | 106125 | APPROVED |  |  | 2024-05-13 | 0 | 19 | Kumar, Mr. Ranjan | -45406 | 19
105-100 | Diriyah Gate S/S # 8242 | 3317 | Diriyah Gate S/S # 8242-PR- MV Termination kit | APPROVED | No | 2024-05-07 | Abas, Mohammed Fekry | 2024-05-09 | 2024-05-12 |  |  |  | 218966 | 5538 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 218966 | APPROVED |  |  | 2024-05-26 | 0 | 14 | Alhadi, Khalid | -45424 | 14
105-100 | Diriyah Gate S/S # 8242 | 3389 | Diriyah Gate S/S # 8242-120 sqmm | APPROVED | No | 2024-05-13 | Abas, Mohammed Fekry | 2024-05-17 | 2024-05-19 |  |  |  | 32800 | 5596 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 32400 | APPROVED |  |  | 2024-05-27 | 400 | 8 | Alhadi, Khalid | -45431 | 8
105-100 | Diriyah Gate S/S # 8242 | 3389 | Diriyah Gate S/S # 8242-120 sqmm | APPROVED | No | 2024-05-13 | Abas, Mohammed Fekry | 2024-05-17 | 2024-05-19 |  |  |  | 32800 | 5596 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 32800 | APPROVED |  |  | 2024-07-12 | 0 | 54 | Alhadi, Khalid | -45431 | 54
105-100 | Diriyah Gate S/S # 8242 | 3398 | Diriyah Gate S/S # 8242-Heritage and Archaeological Site Specialist | REJECTED | No | 2024-05-14 | Nabi, Ashraf | 2024-05-14 |  |  | 2024-05-14 |  | 5000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-100 | Diriyah Gate S/S # 8242 | 3528 | Diriyah Gate S/S # 8242-PR_Civil Main subcontractor | APPROVED | No | 2024-05-29 | Abas, Mohammed Fekry | 2024-05-31 | 2024-05-31 |  |  |  | 15172848 | 5676 | 0 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 15172848 | APPROVED |  |  | 2024-06-26 | 0 | 26 | Alhadi, Khalid | -45443 | 26
105-100 | Diriyah Gate S/S # 8242 | 3549 | Diriyah Gate S/S # 8242-Additional scope for CEC | APPROVED | No | 2024-06-02 | Abas, Mohammed Fekry | 2024-09-30 | 2024-10-01 |  |  |  | 137390 | 4983 | 1 | STANDARD | Construction Expertise Est. | SAR | 137390 | APPROVED |  |  | 2024-10-06 | 0 | 5 | Alhadi, Khalid | -45566 | 5
105-100 | Diriyah Gate S/S # 8242 | 3641 | Diriyah Gate S/S # 8242-PT - Supervision Of installation, testing & commission | APPROVED | No | 2024-06-11 | Abas, Mohammed Fekry | 2024-06-12 | 2024-06-13 |  |  |  | 287500 | 5085 | 1 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 287500 | APPROVED |  |  | 2024-06-26 | 0 | 13 | Alhadi, Khalid | -45456 | 13
105-100 | Diriyah Gate S/S # 8242 | 4090 | Diriyah Gate S/S # 8242-Insulated Y/G Copper conductor | RETURNED | No | 2024-08-04 | Alhadi, Khalid | 2024-08-07 | 2024-08-05 | 2024-08-07 |  | Items lines are missing | 69902.5 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45509 | -45509
105-100 | Diriyah Gate S/S # 8242 | 4093 | Diriyah Gate S/S # 8242-Accessories_Insulated Y/G Copper conductor | RETURNED | No | 2024-08-04 | Alhadi, Khalid | 2024-08-07 | 2024-08-05 | 2024-08-07 |  | Items lines are missing | 82200 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45509 | -45509
105-100 | Diriyah Gate S/S # 8242 | 4405 | Diriyah Gate S/S # 8242-13.8 Kv SWG | REJECTED | No | 2024-09-10 | Yasmin, Ahmed Elsayed Mohamed | 2024-09-19 | 2024-09-16 |  | 2024-09-19 |  | 136000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45551 | -45551
105-100 | Diriyah Gate S/S # 8242 | 4408 | Diriyah Gate S/S # 8242-Telecommunication System-SS#8242 | APPROVED | No | 2024-09-11 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 2000000 | 6266 | 0 | STANDARD | ALFANAR CO | SAR | 2000000 | APPROVED |  |  | 2024-10-06 | 0 | 14 | Kumar, Mr. Ranjan | -45557 | 14
105-100 | Diriyah Gate S/S # 8242 | 4410 | Diriyah Gate S/S # 8242-Control-Protection-SAS SS#8242 | APPROVED | No | 2024-09-11 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 10600000 | 6264 | 0 | STANDARD | ALFANAR CO | SAR | 10600000 | APPROVED |  |  | 2024-10-06 | 0 | 14 | Kumar, Mr. Ranjan | -45557 | 14
105-100 | Diriyah Gate S/S # 8242 | 4415 | Diriyah Gate S/S # 8242-Aux Transformers for SS#8242 | APPROVED | No | 2024-09-11 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 202000 | 6246 | 0 | STANDARD | ALFANAR CO | SAR | 202000 | APPROVED |  |  | 2024-10-06 | 0 | 14 | Alhadi, Khalid | -45557 | 14
105-100 | Diriyah Gate S/S # 8242 | 4417 | Diriyah Gate S/S # 8242-Cyber Security for SS#8242 | APPROVED | No | 2024-09-11 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 1580000 | 6299 | 0 | STANDARD | ALFANAR CO | SAR | 1580000 | APPROVED |  |  | 2024-10-21 | 0 | 29 | Alhadi, Khalid | -45557 | 29
105-100 | Diriyah Gate S/S # 8242 | 4419 | Diriyah Gate S/S # 8242-AC/DC and lighting panel SS#8242 | APPROVED | No | 2024-09-11 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 787000 | 6258 | 0 | STANDARD | ALFANAR CO | SAR | 787000 | APPROVED |  |  | 2024-10-06 | 0 | 14 | Alhadi, Khalid | -45557 | 14
105-100 | Diriyah Gate S/S # 8242 | 4452 | Diriyah Gate S/S # 8242-TPI for precasting work | REJECTED | No | 2024-09-15 | Hassan, Ahmed Abdelzaher Abdelrahim | 2024-09-15 |  |  | 2025-01-15 |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-100 | Diriyah Gate S/S # 8242 | 4482 | Diriyah Gate S/S # 8242-TPI for Precast Work SS#8242_Replaced | APPROVED | No | 2024-09-19 | Abas, Mohammed Fekry | 2024-09-24 | 2024-09-24 |  |  |  | 95190 | 6354 | 0 | STANDARD | Al Muhandis Nizar Al Kurdi Al Milli Engineering Consultants | SAR | 95190 | APPROVED |  |  | 2024-11-03 | 0 | 40 | Tananeh, Khalid Jamal | -45559 | 40
105-100 | Diriyah Gate S/S # 8242 | 4872 | Diriyah Gate S/S # 8242-LV & control cables materials for 8242 SS | APPROVED | No | 2024-11-09 | Abas, Mohammed Fekry | 2024-11-13 | 2024-11-13 |  |  |  | 2033154.35 | 6277 | 1 | STANDARD | ALFANAR CO | SAR | 2033154.35 | REQUIRES REAPPROVAL |  |  |  | 0 | 445 | Badhman, Saeed | -45609 | -45609
105-100 | Diriyah Gate S/S # 8242 | 4872 | Diriyah Gate S/S # 8242-LV & control cables materials for 8242 SS | APPROVED | No | 2024-11-09 | Abas, Mohammed Fekry | 2024-11-13 | 2024-11-13 |  |  |  | 2419998.95 | 6277 | 0 | STANDARD | ALFANAR CO | SAR | 2419998.95 | APPROVED |  |  | 2024-11-25 | 0 | 12 | Badhman, Saeed | -45609 | 12
105-100 | Diriyah Gate S/S # 8242 | 4872 | Diriyah Gate S/S # 8242-LV & control cables materials for 8242 SS | APPROVED | No | 2024-11-09 | Abas, Mohammed Fekry | 2024-11-13 | 2024-11-13 |  |  |  | 386844.6 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45609 | -45609
105-100 | Diriyah Gate S/S # 8242 | 4934 | Diriyah Gate S/S # 8242-Split dual core CT for 8242 SS | APPROVED | No | 2024-11-13 | Abas, Mohammed Fekry | 2024-11-17 | 2024-11-17 |  |  |  | 48000 | 6521 | 0 | STANDARD | ELEQ B.V. | EUR | 44331.19 | APPROVED |  |  | 2024-11-20 | 3668.81 | 3 | Alhadi, Khalid | -45613 | 3
105-100 | Diriyah Gate S/S # 8242 | 4936 | Diriyah Gate S/S # 8242-HVAC supplies materials for 8242 SS | APPROVED | No | 2024-11-13 | Abas, Mohammed Fekry | 2024-11-17 | 2024-11-17 |  |  |  | 2370000 | 6531 | 0 | STANDARD | Ramz Alataa Company for Trading | SAR | 2370000 | APPROVED |  |  | 2024-11-28 | 0 | 11 | Alhadi, Khalid | -45613 | 11
105-100 | Diriyah Gate S/S # 8242 | 5006 | Diriyah Gate S/S # 8242-Cables trays & supports for 8242 SS | REJECTED | No | 2024-11-20 | Yasmin, Ahmed Elsayed Mohamed | 2024-11-26 | 2024-11-25 |  | 2024-11-27 |  | 400000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45621 | -45621
105-100 | Diriyah Gate S/S # 8242 | 5057 | Diriyah Gate S/S # 8242-Cables trays & supports for 8242 SS | APPROVED | No | 2024-11-27 | Abas, Mohammed Fekry | 2024-12-02 | 2024-12-03 |  |  |  | 400000 | 6590 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 400000 | APPROVED |  |  | 2024-12-26 | 0 | 23 | Alqadhi, Abdulrahman Abdulghani | -45629 | 23
105-100 | Diriyah Gate S/S # 8242 | 5062 | Diriyah Gate S/S # 8242-Y/G cables materials for 8242 SS | APPROVED | No | 2024-11-27 | Abas, Mohammed Fekry | 2024-12-02 | 2024-12-03 |  |  |  | 70676.5 | 6644 | 0 | STANDARD | ALFANAR CO | SAR | 63240.5 | APPROVED |  |  | 2024-12-24 | 7436 | 21 | Alhadi, Khalid | -45629 | 21
105-100 | Diriyah Gate S/S # 8242 | 5072 | Diriyah Gate S/S # 8242-Supply of Rigid Steel Conduits for 8242 SS | APPROVED | No | 2024-11-27 | Abas, Mohammed Fekry | 2024-12-02 | 2024-12-03 |  |  |  | 22850.79 | 6587 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 22850.79 | APPROVED |  |  | 2024-12-16 | 0 | 13 | Alqadhi, Abdulrahman Abdulghani | -45629 | 13
105-100 | Diriyah Gate S/S # 8242 | 5198 | Diriyah Gate S/S # 8242-Change order for Extra ACDB panel for 8242 SS | REJECTED | No | 2024-12-09 | Yasmin, Ahmed Elsayed Mohamed | 2024-12-10 | 2024-12-10 |  | 2024-12-15 |  | 150000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45636 | -45636
105-100 | Diriyah Gate S/S # 8242 | 5201 | Diriyah Gate S/S # 8242-installation of 132 KV outdoor & Indoor type cable sealing ends for 8242 SS | APPROVED | No | 2024-12-09 | Abas, Mohammed Fekry | 2024-12-15 | 2024-12-15 |  |  |  | 76000 | 6701 | 0 | STANDARD | BRUGG CABLES COMAPNY | SAR | 76000 | APPROVED |  |  | 2025-01-27 | 0 | 43 | Alhadi, Khalid | -45641 | 43
105-100 | Diriyah Gate S/S # 8242 | 5305 | Diriyah Gate S/S # 8242-Ground accessores materials for SS# 8242 | RETURNED | No | 2024-12-30 | Alhadi, Khalid | 2025-02-17 | 2025-01-06 | 2025-02-17 |  | Budget is not sufficient | 93710 | 6863 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 81841 | APPROVED |  |  | 2025-02-19 | 11869 |  | Alhadi, Khalid | -45663 | 44
105-100 | Diriyah Gate S/S # 8242 | 5443 | Diriyah Gate S/S # 8242-CONSTRUCTION OF NEW 132/13.8 KV DIRIYAH GATE SS 8242 | APPROVED | No | 2025-01-16 | Abas, Mohammed Fekry | 2025-01-26 | 2025-01-27 |  |  |  | 81250 | 6986 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 76350 | APPROVED |  |  | 2025-03-13 | 4900 | 45 | Alhadi, Khalid | -45684 | 45
105-100 | Diriyah Gate S/S # 8242 | 5456 | Diriyah Gate S/S # 8242-CONSTRUCTION OF NEW 132/13.8 KV DIRIYAH GATE SS 8242 | APPROVED | No | 2025-01-19 | Abas, Mohammed Fekry | 2025-01-23 | 2025-01-23 |  |  |  | 176860 | 6969 | 0 | STANDARD | Tawasul International Trad.Est. | SAR | 160353 | APPROVED |  |  | 2025-03-13 | 16507 | 49 | Alhadi, Khalid | -45680 | 49
105-100 | Diriyah Gate S/S # 8242 | 5520 | Diriyah Gate S/S # 8242-Grounding accessories-CONSTRUCTION OF NEW 132/13.8 KV DIRIYAH GATE SS 8242 | RETURNED | No | 2025-01-21 | Alhadi, Khalid | 2025-02-26 | 2025-01-23 | 2025-02-26 |  | Duplicated Items | 8400 | 6863 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 8200 | APPROVED |  |  | 2025-02-19 | 200 |  | Alhadi, Khalid | -45680 | 27
105-100 | Diriyah Gate S/S # 8242 | 5587 | Diriyah Gate S/S # 8242-MV& HV cables for 8242 SS | APPROVED | No | 2025-01-25 | Abas, Mohammed Fekry | 2025-02-05 | 2025-02-05 |  |  |  | 1952768.8 | 5504 | 7 | STANDARD | Riyadh Cables Group Company | SAR | 1952768.8 | APPROVED |  |  | 2025-03-03 | 0 | 26 | Alhadi, Khalid | -45693 | 26
105-100 | Diriyah Gate S/S # 8242 | 5587 | Diriyah Gate S/S # 8242-MV& HV cables for 8242 SS | APPROVED | No | 2025-01-25 | Abas, Mohammed Fekry | 2025-02-05 | 2025-02-05 |  |  |  | 1952768.8 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45693 | -45693
105-100 | Diriyah Gate S/S # 8242 | 5737 | Diriyah Gate S/S # 8242-HV and MV Cable supports for Diriyah Gate SS 8242 | RETURNED | No | 2025-01-30 | Alhadi, Khalid | 2025-06-19 | 2025-02-05 | 2025-06-19 |  | As PM request, due to budget issue | 92950 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45693 | -45693
105-100 | Diriyah Gate S/S # 8242 | 5754 | Diriyah Gate S/S # 8242-Lighting Fixtures for Diriyah Gate 8242 | APPROVED | No | 2025-02-02 | Abas, Mohammed Fekry | 2025-02-05 | 2025-02-05 |  |  |  | 108472 | 6954 | 0 | STANDARD | Integrated Lighting Co.,LED - Rayon | SAR | 86938 | APPROVED |  |  | 2025-05-12 | 21534 | 96 | Alhadi, Khalid | -45693 | 96
105-100 | Diriyah Gate S/S # 8242 | 5763 | Diriyah Gate S/S # 8242-MV and HV Cable Cleats for Diriyah Gates SS 8242 | RETURNED | No | 2025-02-03 | Alhadi, Khalid | 2025-06-19 | 2025-02-13 | 2025-06-19 |  | As PM request, due to budget issue | 71810 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45701 | -45701
105-100 | Diriyah Gate S/S # 8242 | 5783 | Diriyah Gate S/S # 8242-Overhead Clamps and connections for ASCR of Diriyah Gate SS 8242 | APPROVED | No | 2025-02-04 | Abas, Mohammed Fekry | 2025-02-12 | 2025-02-13 |  |  |  | 13141 | 6991 | 0 | STANDARD | Arruti Subestaciones , S.A.U | SAR | 10149 | APPROVED |  |  | 2025-03-13 | 2992 | 28 | Alqadhi, Abdulrahman Abdulghani | -45701 | 28
105-100 | Diriyah Gate S/S # 8242 | 5796 | Diriyah Gate S/S # 8242-LV cable Glands for Diriyah Gate 8242 | RETURNED | No | 2025-02-05 | Alhadi, Khalid | 2025-03-10 | 2025-02-13 | 2025-03-10 |  | It will be secured from Petty Cash | 1617 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45701 | -45701
105-100 | Diriyah Gate S/S # 8242 | 5813 | Diriyah Gate S/S # 8242-Secuirty system supplies (CCTV)for 8242 SS | APPROVED | No | 2025-02-06 | Abas, Mohammed Fekry | 2025-02-12 | 2025-02-13 |  |  |  | 700000 | 6987 | 0 | STANDARD | Equipment & Technical Services Co.(ETECHS) | SAR | 700000 | APPROVED |  |  | 2025-03-11 | 0 | 26 | Alhadi, Khalid | -45701 | 26
105-100 | Diriyah Gate S/S # 8242 | 5855 | Diriyah Gate S/S # 8242-Ring Main Unit 13.8kV, 400A, SF7 materials for 8242 SS | APPROVED | No | 2025-02-12 | Abas, Mohammed Fekry | 2025-02-18 | 2025-02-18 |  |  |  | 139000 | 6988 | 0 | STANDARD | ALFANAR CO | SAR | 139000 | APPROVED |  |  | 2025-03-11 | 0 | 21 | Alhadi, Khalid | -45706 | 21
105-100 | Diriyah Gate S/S # 8242 | 5857 | Diriyah Gate S/S # 8242-Supply materials of 132 KV Out door & indoor type cable sealing Ends for 8242 SS | APPROVED | No | 2025-02-12 | Abas, Mohammed Fekry | 2025-02-18 | 2025-02-18 |  |  |  | 192525 | 6703 | 0 | STANDARD | BRUGG CABLES COMAPNY | CHF | 192525 | APPROVED |  |  | 2025-03-13 | 0 | 23 | Alhadi, Khalid | -45706 | 23
105-100 | Diriyah Gate S/S # 8242 | 5857 | Diriyah Gate S/S # 8242-Supply materials of 132 KV Out door & indoor type cable sealing Ends for 8242 SS | APPROVED | No | 2025-02-12 | Abas, Mohammed Fekry | 2025-02-18 | 2025-02-18 |  |  |  | 192525 | 6703 | 1 | STANDARD | BRUGG CABLES COMAPNY | CHF | 192525 | REQUIRES REAPPROVAL |  |  |  | 0 | 348 | Alhadi, Khalid | -45706 | -45706
105-100 | Diriyah Gate S/S # 8242 | 5860 | Diriyah Gate S/S # 8242-Applay and supplay for internal sealant work for precast for 8242 SS | APPROVED | No | 2025-02-12 | Abas, Mohammed Fekry | 2025-02-16 | 2025-02-18 |  |  |  | 105000 | 7044 | 0 | STANDARD | ATTON ANSHAIYA For General Contracting Establishment | SAR | 96000 | APPROVED |  |  | 2025-04-21 | 9000 | 62 | Tananeh, Khalid Jamal | -45706 | 62
105-100 | Diriyah Gate S/S # 8242 | 6002 | Diriyah Gate S/S # 8242-Testing and commissioning subcontractor for 8242 SS | RETURNED | No | 2025-02-19 | Alhadi, Khalid | 2026-01-13 | 2025-02-22 | 2026-01-13 |  | The PR value does not meet the PO value or the Alfanar agreement. | 1808041 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45710 | -45710
105-100 | Diriyah Gate S/S # 8242 | 6038 | Diriyah Gate S/S # 8242-Supplt 2 PC's of steel Container's 40 feet for site storage materials . | RETURNED | No | 2025-02-24 | Badhman, Saeed | 2025-08-17 | 2025-03-03 | 2025-08-17 |  | Not Needed | 23000 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45719 | -45719
105-100 | Diriyah Gate S/S # 8242 | 6073 | Diriyah Gate S/S # 8242-Loading ,transportation and unloading for Power transformers for 8242 SS | APPROVED | No | 2025-02-26 | Abas, Mohammed Fekry | 2025-03-03 | 2025-03-05 |  |  |  | 300000 | 7130 | 0 | STANDARD | MOHAMMED HAMAD AL-AHMADE FOR TRADING AND CONSTRACTION | SAR | 151000 | APPROVED |  |  | 2025-06-17 | 149000 | 104 | Badhman, Saeed | -45721 | 104
105-100 | Diriyah Gate S/S # 8242 | 6389 | Diriyah Gate S/S # 8242-Fuel for diesel generator for 8242 SS | APPROVED | No | 2025-04-20 | Abas, Mohammed Fekry | 2025-04-21 | 2025-04-21 |  |  |  | 100000 | 7368 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 100000 | APPROVED |  |  | 2025-06-03 | 0 | 43 | Akhtar, Farhan | -45768 | 43
105-100 | Diriyah Gate S/S # 8242 | 6477 | Diriyah Gate S/S # 8242-surge arrestor 8242 | APPROVED | No | 2025-04-29 | Abas, Mohammed Fekry | 2025-04-30 | 2025-04-30 |  |  |  | 96600 | 7217 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 96599.79 | APPROVED |  |  | 2025-05-05 | 0.21 | 5 | Kumar, Mr. Ranjan | -45777 | 5
105-100 | Diriyah Gate S/S # 8242 | 6478 | Diriyah Gate S/S # 8242-Lighting Fixtures (Missed item ) | APPROVED | No | 2025-04-29 | Abas, Mohammed Fekry | 2025-05-07 | 2025-05-08 |  |  |  | 1045 | 6954 | 0 | STANDARD | Integrated Lighting Co.,LED - Rayon | SAR | 1045 | APPROVED |  |  | 2025-05-12 | 0 | 4 | Alhadi, Khalid | -45785 | 4
105-100 | Diriyah Gate S/S # 8242 | 6598 | Diriyah Gate S/S # 8242-Shunt reactor Civil work for 8238,8239 SSs | APPROVED | No | 2025-05-13 | Abas, Mohammed Fekry | 2025-05-18 | 2025-05-18 |  |  |  | 1200000 | 7527 | 0 | STANDARD | POWER RING Construction Company | SAR | 1081514.82 | APPROVED |  |  | 2025-09-04 | 118485.18 | 109 | Hegazy, Ayman | -45795 | 109
105-100 | Diriyah Gate S/S # 8242 | 6604 | Diriyah Gate S/S # 8242-accessories of lighting system installation | REJECTED | No | 2025-05-13 | Hassan, Ahmed Abdelzaher Abdelrahim | 2025-05-13 |  |  | 2025-05-13 |  | 209525.35 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
105-100 | Diriyah Gate S/S # 8242 | 6605 | Diriyah Gate S/S # 8242-Accessories of lighting for installation | RETURNED | No | 2025-05-13 | Alhadi, Khalid | 2025-06-30 | 2025-05-18 | 2025-06-30 |  | Due to a budget issue in the unit price | 195125.35 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45795 | -45795
105-100 | Diriyah Gate S/S # 8242 | 6631 | Diriyah Gate S/S # 8242-wires for lighting and sockets | APPROVED | No | 2025-05-18 | Abas, Mohammed Fekry | 2025-05-20 | 2025-05-20 |  |  |  | 92472.3 | 6277 | 1 | STANDARD | ALFANAR CO | SAR | 98142.1 | REQUIRES REAPPROVAL |  |  |  | -5669.8 | 257 | Badhman, Saeed | -45797 | -45797
105-100 | Diriyah Gate S/S # 8242 | 6631 | Diriyah Gate S/S # 8242-wires for lighting and sockets | APPROVED | No | 2025-05-18 | Abas, Mohammed Fekry | 2025-05-20 | 2025-05-20 |  |  |  | 60358 | 7223 | 0 | STANDARD | ALFANAR CO | SAR | 60358 | APPROVED |  |  | 2025-09-28 | 0 | 131 | Badhman, Saeed | -45797 | 131
105-100 | Diriyah Gate S/S # 8242 | 6631 | Diriyah Gate S/S # 8242-wires for lighting and sockets | APPROVED | No | 2025-05-18 | Abas, Mohammed Fekry | 2025-05-20 | 2025-05-20 |  |  |  | 92472.3 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45797 | -45797
105-100 | Diriyah Gate S/S # 8242 | 6718 | Diriyah Gate S/S # 8242-Electrical installation subcontractor for 8242 SS | APPROVED | No | 2025-05-26 | Abas, Mohammed Fekry | 2025-06-03 | 2025-06-12 |  |  |  | 3132000 | 7133 | 0 | STANDARD | City Crowns Energy | SAR | 3132000 | APPROVED |  |  | 2025-06-24 | 0 | 12 | Alhadi, Khalid | -45820 | 12
105-100 | Diriyah Gate S/S # 8242 | 6882 | Diriyah Gate S/S # 8242-MV and HV cable cleats | APPROVED | No | 2025-06-24 | Abas, Mohammed Fekry | 2025-06-30 | 2025-07-01 |  |  |  | 73344.75 | 7437 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 73344.75 | APPROVED |  |  | 2025-07-03 | 0 | 2 | Alhadi, Khalid | -45839 | 2
105-100 | Diriyah Gate S/S # 8242 | 6883 | Diriyah Gate S/S # 8242-HV and MV cable supports | APPROVED | No | 2025-06-24 | Abas, Mohammed Fekry | 2025-06-30 | 2025-07-01 |  |  |  | 29495.86 | 7439 | 0 | STANDARD | Power Solution Industries | SAR | 27995.86 | APPROVED |  |  | 2025-07-03 | 1500 | 2 | Alhadi, Khalid | -45839 | 2
105-100 | Diriyah Gate S/S # 8242 | 6924 | Diriyah Gate S/S # 8242-48,000 BTU/HR /cold (4 Tons) Free standing Air conditioners | APPROVED | No | 2025-06-29 | Abas, Mohammed Fekry | 2025-07-03 | 2025-07-04 |  |  |  | 72000 | 7442 | 0 | STANDARD | Voltage Professionals contracting establishment | SAR | 72000 | APPROVED |  |  | 2025-07-14 | 0 | 10 | Alhadi, Khalid | -45842 | 10
105-100 | Diriyah Gate S/S # 8242 | 6957 | Diriyah Gate S/S # 8242-Accessories of lighting sys installation | APPROVED | No | 2025-07-01 | Abas, Mohammed Fekry | 2025-07-03 | 2025-07-04 |  |  |  | 183243.01 | 7445 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 183243.01 | APPROVED |  |  | 2025-07-16 | 0 | 12 | Alhadi, Khalid | -45842 | 12
105-100 | Diriyah Gate S/S # 8242 | 7162 | Diriyah Gate S/S # 8242-supply of earthing materials | APPROVED | No | 2025-07-21 | Abas, Mohammed Fekry | 2025-07-22 | 2025-07-22 |  |  |  | 61240 | 6334 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 61240 | APPROVED |  |  | 2025-08-13 | 0 | 22 | Alhadi, Khalid | -45860 | 22
105-100 | Diriyah Gate S/S # 8242 | 7490 | Cable cealing end for shunt reactors ss 8242 | APPROVED | No | 2025-08-25 | Abas, Mohammed Fekry | 2025-08-27 | 2025-08-28 |  |  | Cable cealing end for shunt reactors ss 8242 | 0 | 6703 | 1 | STANDARD | BRUGG CABLES COMAPNY | CHF | 210375 | REQUIRES REAPPROVAL |  |  |  | -210375 | 157 | Alhadi, Khalid | -45897 | -45897
105-100 | Diriyah Gate S/S # 8242 | 7490 | Cable cealing end for shunt reactors ss 8242 | APPROVED | No | 2025-08-25 | Abas, Mohammed Fekry | 2025-08-27 | 2025-08-28 |  |  | Cable cealing end for shunt reactors ss 8242 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45897 | -45897
105-100 | Diriyah Gate S/S # 8242 | 7491 | supply , laying and testing of fiber optic cables for ss 8242 | APPROVED | No | 2025-08-25 | Abas, Mohammed Fekry | 2025-08-27 | 2025-08-28 |  |  | supply , laying and testing of fiber optic cables for ss 8242 | 0 | 7364 | 0 | STANDARD | RASHID SAEED AHMED AL GHAMDI COMM INFO TRAD EST | SAR | 287500 | APPROVED |  |  | 2025-09-14 | -287500 | 17 | Muaz, Alaa | -45897 | 17
105-100 | Diriyah Gate S/S # 8242 | 7512 | HV and MV cables for 8242 | APPROVED | No | 2025-08-26 | Abas, Mohammed Fekry | 2025-08-27 | 2025-08-28 |  |  |  | 0 | 5504 | 8 | STANDARD | Riyadh Cables Group Company | SAR | 366312.49 | APPROVED |  |  | 2025-10-16 | -366312.49 | 49 | Alhadi, Khalid | -45897 | 49
105-100 | Diriyah Gate S/S # 8242 | 7753 | anchor bolts for CAP banks supports | REJECTED | No | 2025-09-15 | Yasmin, Ahmed Elsayed Mohamed | 2025-09-16 | 2025-09-16 |  | 2025-09-21 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45916 | -45916
105-100 | Diriyah Gate S/S # 8242 | 7774 | supply of patch core panels | REJECTED | No | 2025-09-17 | Yasmin, Ahmed Elsayed Mohamed | 2025-09-21 | 2025-09-21 |  | 2025-09-21 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45921 | -45921
105-100 | Diriyah Gate S/S # 8242 | 7804 | Patch core panels for ss 8242 | RETURNED | No | 2025-09-21 | Alhadi, Khalid | 2025-11-13 | 2025-09-28 | 2025-11-13 |  | Please provide complete and final scope | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45928 | -45928
105-100 | Diriyah Gate S/S # 8242 | 8164 | CSE steel structure ss 8242 | APPROVED | No | 2025-11-10 | Abas, Mohammed Fekry | 2025-11-18 | 2025-11-19 |  |  | Steel structure of CSE ss 8242 | 0 | 7943 | 0 | STANDARD | Fursan Construction Industry Factory Industry Factory | SAR | 42000 | APPROVED |  |  | 2025-12-08 | -42000 | 19 | Hegazy, Ayman | -45980 | 19
105-100 | Diriyah Gate S/S # 8242 | 8292 | Fiber Optic Patch core panels ss 8242 | REJECTED | No | 2025-11-20 | Yasmin, Ahmed Elsayed Mohamed | 2025-11-20 | 2025-11-20 |  | 2025-11-26 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45981 | -45981
105-100 | Diriyah Gate S/S # 8242 | 8354 | AC sub panel SDP-3 | RETURNED | No | 2025-11-26 | Alhadi, Khalid | 2025-12-08 | 2025-12-02 | 2025-12-08 |  | No POCR | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45993 | -45993
105-100 | Diriyah Gate S/S # 8242 | 8361 | Supply of FO patch core panels | APPROVED | No | 2025-11-26 | Abas, Mohammed Fekry | 2025-12-02 | 2025-12-02 |  |  |  | 0 | 7364 | 1 | STANDARD | RASHID SAEED AHMED AL GHAMDI COMM INFO TRAD EST | SAR | 50000 | APPROVED | 2026-01-11 | 2026-01-13 | 2026-01-22 | -50000 | 51 | Alhadi, Khalid | 42 | 51
105-100 | Diriyah Gate S/S # 8242 | 8362 | Link boxes and bonding cables | RETURNED | No | 2025-11-26 | Hegazy, Ayman | 2026-01-06 | 2025-12-02 | 2026-01-06 |  | returned based on PM request to hold the process | 0 | 15018 | 0 | STANDARD | ABDULLAH M. AL-SHAHRANI FACTORY | SAR | 42800 | REJECTED |  |  |  | -42800 |  | Hegazy, Ayman | -45993 | -45993
105-100 | Diriyah Gate S/S # 8242 | 8362 | Link boxes and bonding cables | RETURNED | No | 2025-11-26 | Hegazy, Ayman | 2026-01-06 | 2025-12-02 | 2026-01-06 |  | returned based on PM request to hold the process | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -45993 | -45993
105-100 | Diriyah Gate S/S # 8242 | 8377 | PDS cabinet and 42U rack panel | RETURNED | No | 2025-11-27 | Alhadi, Khalid | 2025-12-08 | 2025-12-02 | 2025-12-08 |  | No Details | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45993 | -45993
105-100 | Diriyah Gate S/S # 8242 | 8431 | supply of LV & control cables | INCOMPLETE | No | [6 empty] | No Details | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
105-100 | Diriyah Gate S/S # 8242 | 8476 | control & lv caables 8242 | APPROVED | No | 2025-12-08 | Abas, Mohammed Fekry | 2025-12-15 | 2025-12-17 |  |  |  | 0 | 6277 | 1 | STANDARD | ALFANAR CO | SAR | 3851.4 | REQUIRES REAPPROVAL |  |  |  | -3851.4 | 46 | Badhman, Saeed | -46008 | -46008
105-100 | Diriyah Gate S/S # 8242 | 8476 | control & lv caables 8242 | APPROVED | No | 2025-12-08 | Abas, Mohammed Fekry | 2025-12-15 | 2025-12-17 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -46008 | -46008
105-100 | Diriyah Gate S/S # 8242 | 8508 | Diesel Supply SS 8242 | APPROVED | No | 2025-12-11 | Abas, Mohammed Fekry | 2025-12-15 | 2025-12-17 |  |  | Diesel Supply SS 8242 | 0 | 7368 | 1 | STANDARD | Talaea Alahlam Trading Company | SAR | 65999.01 | APPROVED | 2025-12-18 | 2026-01-01 | 2026-01-05 | -65999.01 | 19 | Akhtar, Farhan | 15 | 19
105-100 | Diriyah Gate S/S # 8242 | 8534 | AC sup panel SDP - 3 | APPROVED | No | 2025-12-16 | Abas, Mohammed Fekry | 2025-12-29 | 2026-01-01 |  |  | kindly approve as this returned by procurement | 0 | 6258 | 1 | STANDARD | ALFANAR CO | SAR | 150000 | APPROVED | 2026-01-06 | 2026-01-13 | 2026-01-15 | -150000 | 14 | Alhadi, Khalid | 12 | 14
105-100 | Diriyah Gate S/S # 8242 | 8537 | PDS cabinet and 42U rack panel | APPROVED | No | 2025-12-16 | Abas, Mohammed Fekry | 2025-12-29 | 2026-01-01 |  |  | kindly approve as this returned by procurment team | 0 | 15065 | 0 | STANDARD |  | SAR | 0 | INCOMPLETE |  |  |  | 0 | 31 | Alhadi, Khalid | -46023 | -46023
105-100 | Diriyah Gate S/S # 8242 | 8537 | PDS cabinet and 42U rack panel | APPROVED | No | 2025-12-16 | Abas, Mohammed Fekry | 2025-12-29 | 2026-01-01 |  |  | kindly approve as this returned by procurment team | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46023 | -46023
105-100 | Diriyah Gate S/S # 8242 | 8603 | Fire Stop Material | APPROVED | No | 2025-12-29 | Abas, Mohammed Fekry | 2026-01-13 | 2026-01-13 |  |  | fire stop materials | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -46035 | -46035
105-100 | Diriyah Gate S/S # 8242 | 8686 | LOA holder for activities in ss 8238 | APPROVED | No | 2026-01-12 | Abas, Mohammed Fekry | 2026-01-22 | 2026-01-25 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46047 | -46047
105-100 | Diriyah Gate S/S # 8242 | 8689 | modification of steel panel support of control room ss 8242 | APPROVED | No | 2026-01-12 | Abas, Mohammed Fekry | 2026-01-22 | 2026-01-25 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46047 | -46047
105-100 | Diriyah Gate S/S # 8242 | 8780 | 240 mm2 Y/G cable for ss8242 | IN PROCESS | No | 2026-01-25 | Yasmin, Ahmed Elsayed Mohamed | 2026-01-25 | 2026-01-25 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46047 | -46047
105-100 | Diriyah Gate S/S # 8242 | 8787 | Bare Cu conducor | IN PROCESS | No | 2026-01-25 | Yasmin, Ahmed Elsayed Mohamed | 2026-01-25 | 2026-01-25 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46047 | -46047
105-100 | Diriyah Gate S/S # 8242 | 8792 | electrical technicians | APPROVED | No | 2026-01-26 | Abas, Mohammed Fekry | 2026-01-26 | 2026-01-27 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46049 | -46049
105-101 | HARAM-3 SS | 1449 | HARAM-3 SS-Building Permit from Madinah Munciplity | APPROVED | No | 2023-09-04 | Abas, Mohammed Fekry | 2023-09-04 | 2023-09-05 |  |  |  | 33000 | 4607 | 0 | STANDARD | Ahmed Mohammed Turkustany Engineering Consultant Office | SAR | 33000 | APPROVED |  |  | 2023-09-18 | 0 | 13 | Babic, Marian | -45174 | 13
105-101 | HARAM-3 SS | 1473 | HARAM-3 SS-110kV Gas insulated Switchgear | APPROVED | No | 2023-09-10 | Abas, Mohammed Fekry | 2023-09-10 | 2023-09-12 |  |  |  | 12220000 | 4652 | 0 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 11655300 | APPROVED |  |  | 2023-10-12 | 564700 | 30 | Babic, Marian | -45181 | 30
105-101 | HARAM-3 SS | 1474 | HARAM-3 SS-Design & Engineering Works | APPROVED | No | 2023-09-10 | Abas, Mohammed Fekry | 2023-09-10 | 2023-09-12 |  |  |  | 415000 | 4629 | 0 | STANDARD | Design Tech Engineering Consultants Company /Simplified | SAR | 415000 | APPROVED |  |  | 2023-10-08 | 0 | 26 | Babic, Marian | -45181 | 26
105-101 | HARAM-3 SS | 1475 | HARAM-3 SS-SAS,AMI, Control & Protection panels | APPROVED | No | 2023-09-10 | Abas, Mohammed Fekry | 2023-09-10 | 2023-09-12 |  |  |  | 9198000 | 4632 | 0 | STANDARD | ALFANAR CO | SAR | 8850000 | APPROVED |  |  | 2023-10-08 | 348000 | 26 | Babic, Marian | -45181 | 26
105-101 | HARAM-3 SS | 1479 | HARAM-3 SS-13.8kV SWGR | APPROVED | No | 2023-09-10 | Abas, Mohammed Fekry | 2023-09-12 | 2023-09-14 |  |  |  | 10220016 | 4631 | 0 | STANDARD | ALFANAR CO | SAR | 8750000 | APPROVED |  |  | 2023-10-08 | 1470016 | 24 | Babic, Marian | -45183 | 24
105-101 | HARAM-3 SS | 1481 | HARAM-3 SS-Soil Investigatoin works | APPROVED | No | 2023-09-10 | Abas, Mohammed Fekry | 2023-09-12 | 2023-09-14 |  |  |  | 26545 | 4630 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 26545 | APPROVED |  |  | 2023-10-03 | 0 | 19 | Babic, Marian | -45183 | 19
105-101 | HARAM-3 SS | 1481 | HARAM-3 SS-Soil Investigatoin works | APPROVED | No | 2023-09-10 | Abas, Mohammed Fekry | 2023-09-12 | 2023-09-14 |  |  |  | 26545 | 4630 | 1 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 22375 | APPROVED |  |  | 2023-10-15 | 4170 | 31 | Babic, Marian | -45183 | 31
105-101 | HARAM-3 SS | 1482 | HARAM-3 SS-OHTC 5T | APPROVED | No | 2023-09-10 | Abas, Mohammed Fekry | 2023-09-12 | 2023-09-14 |  |  |  | 350000 | 4657 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 138500 | APPROVED |  |  | 2023-10-17 | 211500 | 33 | Kumar, Mr. Ranjan | -45183 | 33
105-101 | HARAM-3 SS | 1483 | HARAM-3 SS-Neutral Grounding Resistor 13.8kV, 800A, 10 Ohms | APPROVED | No | 2023-09-10 | Abas, Mohammed Fekry | 2023-09-12 | 2023-09-14 |  |  |  | 225000 | 4690 | 0 | STANDARD | National Switchgears | USD | 114750 | APPROVED |  |  | 2023-11-06 | 110250 | 53 | Kumar, Mr. Ranjan | -45183 | 53
105-101 | HARAM-3 SS | 1486 | HARAM-3 SS-Environmental Study (EISA) | APPROVED | No | 2023-09-10 | Abas, Mohammed Fekry | 2023-09-14 | 2023-09-14 |  |  |  | 90000 | 4609 | 0 | STANDARD | Aran Aljazeera Enviromental Consultant | SAR | 37500 | APPROVED |  |  | 2023-09-20 | 52500 | 6 | Babic, Marian | -45183 | 6
105-101 | HARAM-3 SS | 1494 | HARAM-3 SS-Site Facility - Site Mobilization | RETURNED | No | 2023-09-13 | Babic, Marian | 2023-11-29 | 2023-09-14 | 2023-11-29 |  | Please revise as per received prices and final BOQ | 152000 | 4647 | 0 | STANDARD | Construction Expertise Est. | SAR | 152000 | APPROVED |  |  | 2023-10-17 | 0 |  | Babic, Marian | -45183 | 33
105-101 | HARAM-3 SS | 1500 | HARAM-3 SS-Cyber Security Class3 | APPROVED | No | 2023-09-13 | Abas, Mohammed Fekry | 2023-09-17 | 2023-09-17 |  |  |  | 1788500 | 4645 | 0 | STANDARD | ALFANAR CO | SAR | 1525000 | APPROVED |  |  | 2023-10-26 | 263500 | 39 | Babic, Marian | -45186 | 39
105-101 | HARAM-3 SS | 1511 | HARAM-3 SS-Site Facility & Mobilization | APPROVED | No | 2023-09-18 | Abas, Mohammed Fekry | 2023-09-20 | 2023-09-20 |  |  |  | 630127 | 4647 | 0 | STANDARD | Construction Expertise Est. | SAR | 565952 | APPROVED |  |  | 2023-10-17 | 64175 | 27 | Babic, Marian | -45189 | 27
105-101 | HARAM-3 SS | 1523 | HARAM-3 SS-Station Service TR 750kV | REJECTED | Yes | 2023-09-26 | Khan, Tasawar | 2023-09-26 |  |  | 2023-09-26 |  | 202000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-101 | HARAM-3 SS | 1525 | HARAM-3 SS-Service station transformer 750KVA | APPROVED | No | 2023-09-26 | Abas, Mohammed Fekry | 2023-09-28 | 2023-09-29 |  |  |  | 202000 | 4638 | 0 | STANDARD | ALFANAR CO | SAR | 202000 | APPROVED |  |  | 2023-10-11 | 0 | 12 | Babic, Marian | -45198 | 12
105-101 | HARAM-3 SS | 1534 | HARAM-3 SS-Earthing Materials | RETURNED | No | 2023-09-28 | Babic, Marian | 2024-05-13 | 2023-10-02 | 2024-05-13 |  | it is returned since it was removed from the PO | 155250 | 4650 | 3 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 145230 | APPROVED |  |  | 2024-05-05 | 10020 |  | Babic, Marian | -45201 | 216
105-101 | HARAM-3 SS | 1534 | HARAM-3 SS-Earthing Materials | RETURNED | No | 2023-09-28 | Babic, Marian | 2024-05-13 | 2023-10-02 | 2024-05-13 |  | it is returned since it was removed from the PO | 354750 | 4650 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 295857.6 | APPROVED |  |  | 2023-10-24 | 58892.4 |  | Babic, Marian | -45201 | 22
105-101 | HARAM-3 SS | 1534 | HARAM-3 SS-Earthing Materials | RETURNED | No | 2023-09-28 | Babic, Marian | 2024-05-13 | 2023-10-02 | 2024-05-13 |  | it is returned since it was removed from the PO | 354750 | 4650 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 288032.1 | APPROVED |  |  | 2023-10-26 | 66717.9 |  | Babic, Marian | -45201 | 24
105-101 | HARAM-3 SS | 1534 | HARAM-3 SS-Earthing Materials | RETURNED | No | 2023-09-28 | Babic, Marian | 2024-05-13 | 2023-10-02 | 2024-05-13 |  | it is returned since it was removed from the PO | 16485 | 4651 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 16460 | APPROVED |  |  | 2023-10-15 | 25 |  | Babic, Marian | -45201 | 13
105-101 | HARAM-3 SS | 1534 | HARAM-3 SS-Earthing Materials | RETURNED | No | 2023-09-28 | Babic, Marian | 2024-05-13 | 2023-10-02 | 2024-05-13 |  | it is returned since it was removed from the PO | 199500 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45201 | -45201
105-101 | HARAM-3 SS | 1536 | HARAM-3 SS-96kV Outdoor Surge Arrestor Station Class SH, as per table 1 of IEC60099-4 | APPROVED | No | 2023-10-01 | Abas, Mohammed Fekry | 2023-10-02 | 2023-10-02 |  |  |  | 225000 | 4683 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 57939.08 | APPROVED |  |  | 2023-11-05 | 167060.92 | 34 | Kumar, Mr. Ranjan | -45201 | 34
105-101 | HARAM-3 SS | 1544 | HARAM-3 SS-3rd party safety training | RETURNED | No | 2023-10-03 | Badhman, Saeed | 2024-05-14 | 2023-10-06 | 2024-05-14 |  | Blanket agreement for all safety items | 11000 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45205 | -45205
105-101 | HARAM-3 SS | 1565 | HARAM-3 SS-AC/DC & lighitng panels | APPROVED | No | 2023-10-09 | Abas, Mohammed Fekry | 2023-10-11 | 2023-10-11 |  |  |  | 798000 | 5079 | 0 | STANDARD | ALFANAR CO | SAR | 798000 | APPROVED |  |  | 2024-02-25 | 0 | 137 | Babic, Marian | -45210 | 137
105-101 | HARAM-3 SS | 1570 | HARAM-3 SS-Safety materials for site team | RETURNED | No | 2023-10-10 | Akhtar, Farhan | 2024-04-25 | 2023-10-11 | 2024-04-25 |  | Revise the PR amount | 27200 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45210 | -45210
105-101 | HARAM-3 SS | 1646 | HARAM-3 SS-Gensets for Site facility | APPROVED | No | 2023-10-31 | Abas, Mohammed Fekry | 2023-11-01 | 2023-11-01 |  |  |  | 250000 | 4677 | 0 | STANDARD | Mohammed A. AlFaddaghi & Partners | SAR | 250000 | APPROVED |  |  | 2023-11-13 | 0 | 12 | Badhman, Saeed | -45231 | 12
105-101 | HARAM-3 SS | 1976 | HARAM-3 SS-50/67MVA Power Tr - HARAM3 -SPTC | APPROVED | No | 2023-12-17 | Abas, Mohammed Fekry | 2023-12-17 | 2023-12-17 |  |  |  | 17751250 | 4643 | 2 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 17751250 | APPROVED |  |  | 2023-12-24 | 0 | 7 | Babic, Marian | -45277 | 7
105-101 | HARAM-3 SS | 1986 | HARAM-3 SS-Supply, installation, T&C of CCTV system | APPROVED | No | 2023-12-18 | Abas, Mohammed Fekry | 2023-12-18 | 2023-12-18 |  |  |  | 1200000 | 4989 | 0 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 748649 | APPROVED |  |  | 2024-01-25 | 451351 | 38 | Babic, Marian | -45278 | 38
105-101 | HARAM-3 SS | 2071 | HARAM-3 SS-Firefighting & Fire alarm system - HARAM3 | APPROVED | No | 2024-01-01 | Abas, Mohammed Fekry | 2024-01-02 | 2024-01-02 |  |  |  | 1805666 | 4944 | 0 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 1805666 | APPROVED |  |  | 2024-01-15 | 0 | 13 | Babic, Marian | -45293 | 13
105-101 | HARAM-3 SS | 2072 | HARAM-3 SS-Civil Works - HARAM3 | APPROVED | No | 2024-01-01 | Abas, Mohammed Fekry | 2024-01-02 | 2024-01-02 |  |  |  | 12201882 | 4945 | 0 | STANDARD | Future Achievement Limited Co | SAR | 12200000 | APPROVED |  |  | 2024-01-25 | 1882 | 23 | Babic, Marian | -45293 | 23
105-101 | HARAM-3 SS | 2087 | HARAM-3 SS-13.8kV MV Power Cables - HARAM3 SS project | APPROVED | No | 2024-01-04 | Abas, Mohammed Fekry | 2024-01-04 | 2024-01-07 |  |  |  | 1446305 | 4995 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 1446305 | APPROVED |  |  | 2024-01-25 | 0 | 18 | Badhman, Saeed | -45298 | 18
105-101 | HARAM-3 SS | 2087 | HARAM-3 SS-13.8kV MV Power Cables - HARAM3 SS project | APPROVED | No | 2024-01-04 | Abas, Mohammed Fekry | 2024-01-04 | 2024-01-07 |  |  |  | 1446305 | 4995 | 1 | STANDARD | Riyadh Cables Group Company | SAR | 1440932.5 | APPROVED |  |  | 2024-10-27 | 5372.5 | 294 | Badhman, Saeed | -45298 | 294
105-101 | HARAM-3 SS | 2150 | HARAM-3 SS-HVAC system - HARAM3 | APPROVED | No | 2024-01-10 | Abas, Mohammed Fekry | 2024-01-10 | 2024-01-11 |  |  |  | 2100000 | 5099 | 0 | STANDARD | Magna Contracting Co | SAR | 1925000 | APPROVED |  |  | 2024-02-27 | 175000 | 47 | Babic, Marian | -45302 | 47
105-101 | HARAM-3 SS | 2186 | HARAM-3 SS-125V DC system -Haram3 | APPROVED | No | 2024-01-16 | Abas, Mohammed Fekry | 2024-01-16 | 2024-01-17 |  |  |  | 649000 | 5011 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 505000 | APPROVED |  |  | 2024-01-31 | 144000 | 14 | Babic, Marian | -45308 | 14
105-101 | HARAM-3 SS | 2297 | HARAM-3 SS-Control, LV AC/DC cables - HARAM3 | RETURNED | No | 2024-01-28 | Badhman, Saeed | 2024-03-04 | 2024-01-29 | 2024-03-04 |  | As discussed | 768241.8 | 5161 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 762433.29 | APPROVED |  |  | 2024-05-26 | 5808.51 |  | Badhman, Saeed | -45320 | 118
105-101 | HARAM-3 SS | 2297 | HARAM-3 SS-Control, LV AC/DC cables - HARAM3 | RETURNED | No | 2024-01-28 | Badhman, Saeed | 2024-03-04 | 2024-01-29 | 2024-03-04 |  | As discussed | 150577 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45320 | -45320
105-101 | HARAM-3 SS | 2500 | HARAM-3 SS-Furniture for HARAM3 | RETURNED | No | 2024-02-07 | Babic, Marian | 2024-04-21 | 2024-02-10 | 2024-04-21 |  | not required | 50000 | 5127 | 0 | STANDARD | DANAH AL RAYEDA ESTABLISHMENT | SAR | 36000 | APPROVED |  |  | 2024-03-04 | 14000 |  | Babic, Marian | -45332 | 23
105-101 | HARAM-3 SS | 2500 | HARAM-3 SS-Furniture for HARAM3 | RETURNED | No | 2024-02-07 | Babic, Marian | 2024-04-21 | 2024-02-10 | 2024-04-21 |  | not required | 41400 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45332 | -45332
105-101 | HARAM-3 SS | 2573 | HARAM-3 SS-Cable Ladder & Tray for HARAM3 | APPROVED | No | 2024-02-15 | Abas, Mohammed Fekry | 2024-02-18 | 2024-02-18 |  |  |  | 313224 | 5247 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 313224 | APPROVED |  |  | 2024-04-03 | 0 | 45 | Badhman, Saeed | -45340 | 45
105-101 | HARAM-3 SS | 2682 | HARAM-3 SS-13.8kV MV Termination Kits - HARAM3 | APPROVED | No | 2024-02-25 | Abas, Mohammed Fekry | 2024-02-27 | 2024-02-28 |  |  |  | 150000 | 5229 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 118820.3 | APPROVED |  |  | 2024-03-25 | 31179.7 | 26 | Babic, Marian | -45350 | 26
105-101 | HARAM-3 SS | 2830 | HARAM-3 SS-IT assets for Site offices | APPROVED | No | 2024-03-16 | Abas, Mohammed Fekry | 2024-03-19 | 2024-03-19 |  |  |  | 17000 | 5435 | 0 | STANDARD | Mohmmed Abdulrahman AlZahid IT CO. | SAR | 21920 | APPROVED |  |  | 2024-05-07 | -4920 | 49 | Babic, Marian | -45370 | 49
105-101 | HARAM-3 SS | 2839 | HARAM-3 SS-Control, LV AC/DC cables - HARAM3 SS project | RETURNED | No | 2024-03-18 | Badhman, Saeed | 2024-05-16 | 2024-03-19 | 2024-05-16 |  | QTYs are not right | 95770 | 5161 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 95465.6 | APPROVED |  |  | 2024-05-26 | 304.4 |  | Badhman, Saeed | -45370 | 68
105-101 | HARAM-3 SS | 2839 | HARAM-3 SS-Control, LV AC/DC cables - HARAM3 SS project | RETURNED | No | 2024-03-18 | Badhman, Saeed | 2024-05-16 | 2024-03-19 | 2024-05-16 |  | QTYs are not right | 36000 | 5525 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 32056 | APPROVED |  |  | 2024-09-19 | 3944 |  | Badhman, Saeed | -45370 | 184
105-101 | HARAM-3 SS | 2839 | HARAM-3 SS-Control, LV AC/DC cables - HARAM3 SS project | RETURNED | No | 2024-03-18 | Badhman, Saeed | 2024-05-16 | 2024-03-19 | 2024-05-16 |  | QTYs are not right | 108000 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45370 | -45370
105-101 | HARAM-3 SS | 2840 | HARAM-3 SS-Transportation of Cable Ladder & Tray- HARAM3 | APPROVED | No | 2024-03-18 | Abas, Mohammed Fekry | 2024-03-19 | 2024-03-19 |  |  |  | 11769.16 | 5247 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 11769.16 | APPROVED |  |  | 2024-04-03 | 0 | 15 | Badhman, Saeed | -45370 | 15
105-101 | HARAM-3 SS | 2931 | HARAM-3 SS-Equipment earthing & grounding materials - HARAM3 | APPROVED | No | 2024-03-28 | Abas, Mohammed Fekry | 2024-03-31 | 2024-03-31 |  |  |  | 11550 | 5452 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 9421.69 | APPROVED |  |  | 2024-05-21 | 2128.31 | 51 | Babic, Marian | -45382 | 51
105-101 | HARAM-3 SS | 2931 | HARAM-3 SS-Equipment earthing & grounding materials - HARAM3 | APPROVED | No | 2024-03-28 | Abas, Mohammed Fekry | 2024-03-31 | 2024-03-31 |  |  |  | 171000 | 5498 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 206902.63 | APPROVED |  |  | 2024-06-24 | -35902.63 | 85 | Babic, Marian | -45382 | 85
105-101 | HARAM-3 SS | 2931 | HARAM-3 SS-Equipment earthing & grounding materials - HARAM3 | APPROVED | No | 2024-03-28 | Abas, Mohammed Fekry | 2024-03-31 | 2024-03-31 |  |  |  | 251000 | 5498 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 281813.22 | APPROVED |  |  | 2024-05-23 | -30813.22 | 53 | Babic, Marian | -45382 | 53
105-101 | HARAM-3 SS | 2932 | HARAM-3 SS-Lightning Mast - HARAM3 SS project | APPROVED | No | 2024-03-28 | Abas, Mohammed Fekry | 2024-03-31 | 2024-03-31 |  |  |  | 64000 | 5526 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 60000 | APPROVED |  |  | 2024-07-07 | 4000 | 98 | Babic, Marian | -45382 | 98
105-101 | HARAM-3 SS | 3292 | HARAM-3 SS-110kV Conductor & connectors @ HARAM3 | APPROVED | No | 2024-05-05 | Abas, Mohammed Fekry | 2024-05-06 | 2024-05-06 |  |  |  | 9000 | 5566 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 7284.01 | APPROVED |  |  | 2024-05-26 | 1715.99 | 20 | Babic, Marian | -45418 | 20
105-101 | HARAM-3 SS | 3292 | HARAM-3 SS-110kV Conductor & connectors @ HARAM3 | APPROVED | No | 2024-05-05 | Abas, Mohammed Fekry | 2024-05-06 | 2024-05-06 |  |  |  | 6750 | 5580 | 0 | STANDARD | Arruti Subestaciones , S.A.U | EUR | 5470.79 | APPROVED |  |  | 2024-05-27 | 1279.21 | 21 | Babic, Marian | -45418 | 21
105-101 | HARAM-3 SS | 3324 | HARAM-3 SS-PDS - HARAM3 SS project | APPROVED | No | 2024-05-07 | Abas, Mohammed Fekry | 2024-05-09 | 2024-05-12 |  |  |  | 275000 | 5835 | 0 | STANDARD | MIDDLE EAST FIBER CABLE MANUFACTURING CO. | SAR | 217500 | APPROVED |  |  | 2024-07-31 | 57500 | 80 | Babic, Marian | -45424 | 80
105-101 | HARAM-3 SS | 3439 | HARAM-3 SS-TPI for FAT of OHTC- HARAM3 SS project | APPROVED | No | 2024-05-19 | Abas, Mohammed Fekry | 2024-05-20 | 2024-05-20 |  |  |  | 2850 | 5585 | 0 | STANDARD | Bureau Veritas Branch Saudi Arabia | SAR | 2850 | APPROVED |  |  | 2024-05-27 | 0 | 7 | Kumar, Mr. Ranjan | -45432 | 7
105-101 | HARAM-3 SS | 3558 | HARAM-3 SS-Additional Cables - HARAM3 | RETURNED | No | 2024-06-02 | Badhman, Saeed | 2024-09-25 | 2024-06-04 | 2024-09-25 |  | PO issued (5525) | 63222 | 5525 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 46370 | APPROVED |  |  | 2024-09-19 | 16852 |  | Badhman, Saeed | -45447 | 107
105-101 | HARAM-3 SS | 3558 | HARAM-3 SS-Additional Cables - HARAM3 | RETURNED | No | 2024-06-02 | Badhman, Saeed | 2024-09-25 | 2024-06-04 | 2024-09-25 |  | PO issued (5525) | 42209 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45447 | -45447
105-101 | HARAM-3 SS | 3769 | HARAM-3 SS-PR for TPI of MV SWGR - HARAM3 | APPROVED | No | 2024-07-04 | Abas, Mohammed Fekry | 2024-07-07 | 2024-07-07 |  |  |  | 5400 | 5787 | 0 | STANDARD | VELOSI SAUDI ARABIA CO LTD | SAR | 5400 | APPROVED |  |  | 2024-07-12 | 0 | 5 | Babic, Marian | -45480 | 5
105-101 | HARAM-3 SS | 3947 | HARAM-3 SS-Earthing Conductor 1x150 sqmm - HARAM3 | APPROVED | No | 2024-07-17 | Abas, Mohammed Fekry | 2024-07-18 | 2024-07-18 |  |  |  | 36000 | 5851 | 0 | STANDARD | ARABIAN RELIANCE COMPANY(S) | SAR | 36000 | APPROVED |  |  | 2024-07-23 | 0 | 5 | Babic, Marian | -45491 | 5
105-101 | HARAM-3 SS | 4151 | HARAM-3 SS-Diesel for Generators - HARAM3 SS project | APPROVED | No | 2024-08-14 | Abas, Mohammed Fekry | 2024-08-15 | 2024-08-15 |  |  |  | 60000 | 6089 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 52173.91 | APPROVED |  |  | 2024-09-02 | 7826.09 | 18 | Akhtar, Farhan | -45519 | 18
105-101 | HARAM-3 SS | 4235 | HARAM-3 SS-Electrical Installation works - HARAM3 | APPROVED | No | 2024-08-21 | Abas, Mohammed Fekry | 2024-08-25 | 2024-08-25 |  |  |  | 2162372.44 | 6228 | 0 | STANDARD | MASEERAT AL NAMA CONT.EST. | SAR | 1994868 | APPROVED |  |  | 2024-10-14 | 167504.44 | 50 | Babic, Marian | -45529 | 50
105-101 | HARAM-3 SS | 4436 | HARAM-3 SS-Transportation of Power TR's- HARAM3 SS project | APPROVED | No | 2024-09-12 | Abas, Mohammed Fekry | 2024-09-16 | 2024-09-17 |  |  |  | 302000 | 6048 | 0 | STANDARD | Branch Of: OFSAT LIMITED CO | SAR | 302000 | APPROVED |  |  | 2024-10-06 | 0 | 19 | Badhman, Saeed | -45552 | 19
105-101 | HARAM-3 SS | 4613 | HARAM-3 SS-Lighting materials (Fixtures)- HARAM3 SS project | APPROVED | No | 2024-10-07 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-10 |  |  |  | 102420 | 5809 | 13 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 92178 | APPROVED |  |  | 2024-10-13 | 10242 | 3 | Babic, Marian | -45575 | 3
105-101 | HARAM-3 SS | 4613 | HARAM-3 SS-Lighting materials (Fixtures)- HARAM3 SS project | APPROVED | No | 2024-10-07 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-10 |  |  |  | 102420 | 5809 | 14 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 92178 | REJECTED |  |  |  | 10242 |  | Babic, Marian | -45575 | -45575
105-101 | HARAM-3 SS | 4616 | HARAM-3 SS-Telecom system - HARAM3 SS project (manul PO# 8325) | APPROVED | No | 2024-10-07 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-10 |  |  |  | 5350000 | 6330 | 0 | STANDARD | ALFANAR CO | SAR | 5350000 | APPROVED |  |  | 2024-10-14 | 0 | 4 | Babic, Marian | -45575 | 4
105-101 | HARAM-3 SS | 4836 | HARAM-3 SS-T&C works - HARAM3 SS project | APPROVED | No | 2024-11-05 | Abas, Mohammed Fekry | 2024-11-10 | 2024-11-11 |  |  |  | 1863301 | 6666 | 0 | STANDARD | Al Fanar Technical Services | SAR | 1863301 | APPROVED |  |  | 2025-02-13 | 0 | 94 | Mohammed, Faisal Ansari | -45607 | 94
105-101 | HARAM-3 SS | 4837 | HARAM-3 SS-Laptops for SEC Consultants - HARAM3 SS project | APPROVED | No | 2024-11-05 | Abas, Mohammed Fekry | 2024-11-10 | 2024-11-11 |  |  |  | 7000 | 6500 | 0 | STANDARD | Excellence Arabia Trading Company | SAR | 4758 | APPROVED |  |  | 2024-11-28 | 2242 | 17 | Akhtar, Farhan | -45607 | 17
105-101 | HARAM-3 SS | 4858 | HARAM-3 SS-Oil Filteration works of 3 Power TR's - HARAM3 SS project | APPROVED | No | 2024-11-07 | Abas, Mohammed Fekry | 2024-11-10 | 2024-11-11 |  |  |  | 55000 | 6642 | 0 | STANDARD | MASEERAT AL NAMA CONT.EST. | SAR | 51000 | APPROVED |  |  | 2025-01-09 | 4000 | 59 | Mohammed, Faisal Ansari | -45607 | 59
105-101 | HARAM-3 SS | 4918 | HARAM-3 SS-Security Contract at WH- HARAM3 SS project | APPROVED | No | 2024-11-13 | Abas, Mohammed Fekry | 2024-11-13 | 2024-11-13 |  |  |  | 80000 | 6498 | 0 | STANDARD | Rukn Al Kateibah Company for Security Guards. | SAR | 77400 | APPROVED |  |  | 2024-11-26 | 2600 | 13 | Abuhammad, Samir | -45609 | 13
105-101 | HARAM-3 SS | 5001 | HARAM-3 SS-FO cable as per SAS Schedule - HARAM3 SS project | APPROVED | No | 2024-11-20 | Khan, Tasawar | 2024-12-17 | 2024-11-27 |  |  |  | 280500 | 6665 | 0 | STANDARD | Arabian Power Trading Est. | SAR | 260000 | APPROVED |  |  | 2025-01-05 | 20500 | 19 | Muhammad, Muhammad Atif | -45623 | 39
105-101 | HARAM-3 SS | 5045 | HARAM-3 SS-Addditional Cable tray and ladder as per site modification - HARAM3 | APPROVED | No | 2024-11-24 | Khan, Tasawar | 2024-11-28 | 2024-11-27 |  |  |  | 23772 | 6570 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 23000 | APPROVED |  |  | 2024-12-05 | 772 | 7 | Babic, Marian | -45623 | 8
105-101 | HARAM-3 SS | 5048 | HARAM-3 SS-Stand AC's for T&C works- HARAM3 SS project | APPROVED | No | 2024-11-25 | Abas, Mohammed Fekry | 2024-12-04 | 2024-12-04 |  |  |  | 96000 | 6601 | 0 | STANDARD | Current Makers For Contracting EST | SAR | 252000 | APPROVED |  |  | 2024-12-19 | -156000 | 15 | Babic, Marian | -45630 | 15
105-101 | HARAM-3 SS | 5109 | HARAM-3 SS-Power Sockets & Recepticals - HARAM3 SS Project | APPROVED | No | 2024-12-02 | Abas, Mohammed Fekry | 2024-12-03 | 2024-12-03 |  |  |  | 124211 | 6585 | 0 | STANDARD | Tawasul International Trad.Est. | SAR | 119242.56 | APPROVED |  |  | 2024-12-24 | 4968.44 | 21 | Babic, Marian | -45629 | 21
105-101 | HARAM-3 SS | 5469 | HARAM-3 SS-Outdoor Lighting fixtures and Sensors - HARAM3 SS project | RETURNED | No | 2025-01-20 | Babic, Marian | 2025-10-26 | 2025-03-05 |  |  | We are utilizing the budget from Item#4.3 | 25549.5 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45721 | -45721
105-101 | HARAM-3 SS | 6028 | HARAM-3 SS-Lighting Poles - HARAM3 SS PROJECT | APPROVED | No | 2025-02-24 | Abas, Mohammed Fekry | 2025-02-27 | 2025-02-27 |  |  | We are utilizing the budget from item 4.3 (This PR was issued earlier but later after 40 days PR was rejected by procurment engr without any discussion with Project team) | 19500 | 6981 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 19500 | APPROVED |  |  | 2025-03-17 | 0 | 18 | Muaz, Alaa | -45715 | 18
105-101 | HARAM-3 SS | 6175 | HARAM-3 SS-Fire retardant Materials for MV Cables- HARAM3 SS project | APPROVED | No | 2025-03-12 | Abas, Mohammed Fekry | 2025-03-13 | 2025-03-17 |  |  | We are utilizing the budget from item#4.7 | 100000 | 7141 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 99200 | APPROVED |  |  | 2025-04-24 | 800 | 38 | Babic, Marian | -45733 | 38
105-101 | HARAM-3 SS | 6189 | HARAM-3 SS-Diesel for Site Generators - HARAM3 SS project | APPROVED | No | 2025-03-17 | Abas, Mohammed Fekry | 2025-03-19 | 2025-03-20 |  |  | We are utilizing the budget from Item# 6.1.4.2(Electricity Operation). It shall be noted that Prices has been increased for diesel due to which revised PO need to be issued on urgent basis. | 67825.2 | 7073 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 67825.2 | APPROVED |  |  | 2025-04-07 | 0 | 18 | Akhtar, Farhan | -45736 | 18
105-101 | HARAM-3 SS | 6189 | HARAM-3 SS-Diesel for Site Generators - HARAM3 SS project | APPROVED | No | 2025-03-17 | Abas, Mohammed Fekry | 2025-03-19 | 2025-03-20 |  |  | We are utilizing the budget from Item# 6.1.4.2(Electricity Operation). It shall be noted that Prices has been increased for diesel due to which revised PO need to be issued on urgent basis. | 67825.2 | 7073 | 1 | STANDARD | Talaea Alahlam Trading Company | SAR | 67825.2 | REQUIRES REAPPROVAL |  |  |  | 0 | 318 | Akhtar, Farhan | -45736 | -45736
105-101 | HARAM-3 SS | 6202 | HARAM-3 SS-Rental Manpower for T&C works - HARAM3 SS project | APPROVED | No | 2025-03-18 | Abas, Mohammed Fekry | 2025-03-24 | 2025-03-24 |  |  | We are utilizing the budget from Item# 6.1.2.3 for Rental manpower required for T&C works at HARAM3 SS proejct. | 134400 | 7048 | 0 | STANDARD | Jasem M.AlJasem Contracting Est. | SAR | 96000 | APPROVED |  |  | 2025-04-15 | 38400 | 22 | Babic, Marian | -45740 | 22
105-101 | HARAM-3 SS | 6206 | HARAM-3 SS-MV Cable cleats Haram 3 S/S | APPROVED | No | 2025-03-19 | Abas, Mohammed Fekry | 2025-04-12 | 2025-04-13 | 2025-04-07 |  | Item 1 insufficient price | 75075 | 7135 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 75075 | APPROVED |  |  | 2025-04-24 | 0 | 11 | Babic, Marian | -45760 | 11
105-101 | HARAM-3 SS | 6620 | HARAM-3 SS-Additional Copper pipes for Stand AC's | APPROVED | No | 2025-05-15 | Abas, Mohammed Fekry | 2025-05-19 | 2025-05-19 |  |  | we are utilizing the budget from item#6.1.4.7. PO for Stand AC's issued already this is additional whcih need to be added in the PO based on installation. | 3120 | 6601 | 1 | STANDARD | Current Makers For Contracting EST | SAR | 3120 | APPROVED |  |  | 2025-05-24 | 0 | 5 | Babic, Marian | -45796 | 5
105-101 | HARAM-3 SS | 6849 | HARAM-3 SS-Security services | RETURNED | No | 2025-06-22 | Abuhammad, Samir | 2025-08-17 | 2025-06-25 | 2025-08-17 |  | as no response from PMT for the duration and Qty. | 59340 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45833 | -45833
105-101 | HARAM-3 SS | 7823 | Two Damaged Panels -Haram3 | RETURNED | No | 2025-09-25 | Babic, Marian | 2025-10-26 | 2025-09-28 | 2025-10-26 |  | please resubmit after the budget issues are resolved | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45928 | -45928
105-101 | HARAM-3 SS | 8169 | Diesel for GENSET | RETURNED | No | 2025-11-10 | Akhtar, Farhan | 2026-01-18 | 2025-11-16 | 2026-01-18 |  | Resubmit this PR again once POCR is approved | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45977 | -45977
105-101 | HARAM-3 SS | 8171 | Damaged MV SWGR panels | APPROVED | No | 2025-11-11 | Abas, Mohammed Fekry | 2025-11-15 | 2025-11-16 |  |  | We are utilizing the budget from item #3.1.6.5 – (13.8 kV MV Switchgear 630A - 25kA/1sec. SPARE PARTS). | 0 | 4631 | 1 | STANDARD | ALFANAR CO | SAR | 120000 | APPROVED |  |  | 2025-11-20 | -120000 | 4 | Babic, Marian | -45977 | 4
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1447 | CONSTRUCTION OF TAIBA WEST SS-13.8 k.v MV Switchgear 630A -25kA/1sec. | APPROVED | No | 2023-09-03 | Abas, Mohammed Fekry | 2023-09-04 | 2023-09-05 |  |  |  | 10220000 | 4624 | 0 | STANDARD | ALFANAR CO | SAR | 8400000 | APPROVED |  |  | 2023-10-04 | 1820000 | 29 | Babic, Marian | -45174 | 29
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1448 | CONSTRUCTION OF TAIBA WEST SS-Building Permit from Muncipility | APPROVED | No | 2023-09-04 | Abas, Mohammed Fekry | 2023-09-04 | 2023-09-05 |  |  |  | 33000 | 4608 | 0 | STANDARD | Ahmed Mohammed Turkustany Engineering Consultant Office | SAR | 33000 | APPROVED |  |  | 2023-09-18 | 0 | 13 | Babic, Marian | -45174 | 13
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1458 | CONSTRUCTION OF TAIBA WEST SS-Soil Investigation & Soil testing | APPROVED | No | 2023-09-06 | Abas, Mohammed Fekry | 2023-09-07 | 2023-09-07 |  |  |  | 26545 | 4623 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 26545 | APPROVED |  |  | 2023-10-02 | 0 | 25 | Babic, Marian | -45176 | 25
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1458 | CONSTRUCTION OF TAIBA WEST SS-Soil Investigation & Soil testing | APPROVED | No | 2023-09-06 | Abas, Mohammed Fekry | 2023-09-07 | 2023-09-07 |  |  |  | 26545 | 4623 | 1 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 22375 | APPROVED |  |  | 2023-10-15 | 4170 | 38 | Babic, Marian | -45176 | 38
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1459 | CONSTRUCTION OF TAIBA WEST SS-Design & Engineering Works | APPROVED | No | 2023-09-06 | Abas, Mohammed Fekry | 2023-09-10 | 2023-09-12 |  |  |  | 415000 | 4625 | 0 | STANDARD | Design Tech Engineering Consultants Company /Simplified | SAR | 415000 | APPROVED |  |  | 2023-10-04 | 0 | 22 | Babic, Marian | -45181 | 22
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1465 | CONSTRUCTION OF TAIBA WEST SS-Overhead travelling Crane 5T | APPROVED | No | 2023-09-07 | Abas, Mohammed Fekry | 2023-09-10 | 2023-09-12 |  |  |  | 350000 | 4658 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 138500 | APPROVED |  |  | 2023-10-17 | 211500 | 35 | Kumar, Mr. Ranjan | -45181 | 35
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1466 | CONSTRUCTION OF TAIBA WEST SS-Grounding Conductor | APPROVED | No | 2023-09-07 | Abas, Mohammed Fekry | 2023-09-10 | 2023-09-12 |  |  |  | 225000 | 4689 | 0 | STANDARD | National Switchgears | USD | 114750 | APPROVED |  |  | 2023-11-06 | 110250 | 55 | Kumar, Mr. Ranjan | -45181 | 55
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1472 | CONSTRUCTION OF TAIBA WEST SS-110kV GAS INSULATED SWTICHGEAR | APPROVED | No | 2023-09-10 | Abas, Mohammed Fekry | 2023-09-10 | 2023-09-12 |  |  |  | 12220000 | 4626 | 0 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 11585775 | APPROVED |  |  | 2023-10-04 | 634225 | 22 | Babic, Marian | -45181 | 22
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1485 | CONSTRUCTION OF TAIBA WEST SS-environmental Study (EISA) | APPROVED | No | 2023-09-10 | Abas, Mohammed Fekry | 2023-09-12 | 2023-09-14 |  |  |  | 90000 | 4610 | 0 | STANDARD | Aran Aljazeera Enviromental Consultant | SAR | 37500 | APPROVED |  |  | 2023-09-20 | 52500 | 6 | Babic, Marian | -45183 | 6
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1499 | CONSTRUCTION OF TAIBA WEST SS-Cyber Security Class3 | APPROVED | No | 2023-09-13 | Abas, Mohammed Fekry | 2023-09-13 | 2023-09-14 |  |  |  | 1788500 | 4644 | 0 | STANDARD | ALFANAR CO | SAR | 1400000 | APPROVED |  |  | 2023-10-31 | 388500 | 47 | Babic, Marian | -45183 | 47
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1510 | CONSTRUCTION OF TAIBA WEST SS-Site Facility - Mobilization | APPROVED | No | 2023-09-18 | Abas, Mohammed Fekry | 2023-09-20 | 2023-09-20 |  |  |  | 630127 | 4710 | 0 | STANDARD | Construction Expertise Est. | SAR | 356200 | APPROVED |  |  | 2023-11-27 | 273927 | 68 | Babic, Marian | -45189 | 68
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1524 | CONSTRUCTION OF TAIBA WEST SS-Station Service Transformers 750KVA | APPROVED | No | 2023-09-26 | Abas, Mohammed Fekry | 2023-09-29 | 2023-09-29 |  |  |  | 202000 | 4637 | 0 | STANDARD | ALFANAR CO | SAR | 202000 | APPROVED |  |  | 2023-10-11 | 0 | 12 | Babic, Marian | -45198 | 12
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1533 | CONSTRUCTION OF TAIBA WEST SS-Earthing Materials | RETURNED | No | 2023-09-28 | Babic, Marian | 2024-05-13 | 2023-10-02 | 2024-05-13 |  | it is returned since it was removed from the PO | 155250 | 4648 | 2 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 145230 | APPROVED |  |  | 2024-04-28 | 10020 |  | Babic, Marian | -45201 | 209
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1533 | CONSTRUCTION OF TAIBA WEST SS-Earthing Materials | RETURNED | No | 2023-09-28 | Babic, Marian | 2024-05-13 | 2023-10-02 | 2024-05-13 |  | it is returned since it was removed from the PO | 354750 | 4648 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 295857.6 | APPROVED |  |  | 2023-10-24 | 58892.4 |  | Babic, Marian | -45201 | 22
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1533 | CONSTRUCTION OF TAIBA WEST SS-Earthing Materials | RETURNED | No | 2023-09-28 | Babic, Marian | 2024-05-13 | 2023-10-02 | 2024-05-13 |  | it is returned since it was removed from the PO | 354750 | 4648 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 288032.1 | APPROVED |  |  | 2023-10-26 | 66717.9 |  | Babic, Marian | -45201 | 24
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1533 | CONSTRUCTION OF TAIBA WEST SS-Earthing Materials | RETURNED | No | 2023-09-28 | Babic, Marian | 2024-05-13 | 2023-10-02 | 2024-05-13 |  | it is returned since it was removed from the PO | 14565 | 4649 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 14540 | APPROVED |  |  | 2023-10-15 | 25 |  | Babic, Marian | -45201 | 13
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1533 | CONSTRUCTION OF TAIBA WEST SS-Earthing Materials | RETURNED | No | 2023-09-28 | Babic, Marian | 2024-05-13 | 2023-10-02 | 2024-05-13 |  | it is returned since it was removed from the PO | 199500 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45201 | -45201
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1535 | CONSTRUCTION OF TAIBA WEST SS-96kV Surge Arrestor Station Class SH as per table 1 of IEC 60099-4 | APPROVED | No | 2023-10-01 | Abas, Mohammed Fekry | 2023-10-02 | 2023-10-02 |  |  |  | 225000 | 4685 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 57939.08 | APPROVED |  |  | 2023-11-05 | 167060.92 | 34 | Kumar, Mr. Ranjan | -45201 | 34
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1543 | CONSTRUCTION OF TAIBA WEST SS-Safety Training for site team | RETURNED | No | 2023-10-03 | Badhman, Saeed | 2024-05-14 | 2023-10-06 | 2024-05-14 |  | Blanket agreement for all safety items | 11000 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45205 | -45205
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1564 | CONSTRUCTION OF TAIBA WEST SS-AC/DC & lighitng panels | APPROVED | No | 2023-10-09 | Abas, Mohammed Fekry | 2023-10-11 | 2023-10-11 |  |  |  | 798000 | 5078 | 0 | STANDARD | ALFANAR CO | SAR | 798000 | APPROVED |  |  | 2024-02-25 | 0 | 137 | Babic, Marian | -45210 | 137
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1569 | CONSTRUCTION OF TAIBA WEST SS-Safety Materials | RETURNED | No | 2023-10-10 | Akhtar, Farhan | 2024-04-25 | 2023-10-11 | 2024-04-25 |  | Revise the PR amount | 27263 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45210 | -45210
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1645 | CONSTRUCTION OF TAIBA WEST SS-Generators for Site facility | APPROVED | No | 2023-10-31 | Abas, Mohammed Fekry | 2023-11-01 | 2023-11-01 |  |  |  | 250000 | 4676 | 0 | STANDARD | Mohammed A. AlFaddaghi & Partners | SAR | 250000 | APPROVED |  |  | 2023-11-14 | 0 | 13 | Badhman, Saeed | -45231 | 13
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1722 | CONSTRUCTION OF TAIBA WEST SS-JIB crane for TAIBA WEST | APPROVED | No | 2023-11-14 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 180000 | 4873 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 82000 | APPROVED |  |  | 2023-12-21 | 98000 | 35 | Kumar, Mr. Ranjan | -45246 | 35
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1887 | CONSTRUCTION OF TAIBA WEST SS-IT materials for safety @ Taiba west | APPROVED | No | 2023-12-04 | Abas, Mohammed Fekry | 2023-12-06 | 2023-12-07 |  |  |  | 21000 | 4820 | 0 | STANDARD | Mohammad Abdul Rahman Mohd Al Zahid Information Technology Co | SAR | 20495 | APPROVED |  |  | 2023-12-21 | 505 | 14 | Babic, Marian | -45267 | 14
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1922 | CONSTRUCTION OF TAIBA WEST SS-Furniture of site facilities - TAIBA WEST | APPROVED | No | 2023-12-11 | Abas, Mohammed Fekry | 2023-12-12 | 2023-12-12 |  |  |  | 50000 | 4833 | 0 | STANDARD | DANAH AL RAYEDA ESTABLISHMENT | SAR | 50000 | APPROVED |  |  | 2023-12-21 | 0 | 9 | Babic, Marian | -45272 | 9
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1975 | CONSTRUCTION OF TAIBA WEST SS-50/67MVA Power Transformer - TAIBA WEST -SPTC | APPROVED | No | 2023-12-17 | Abas, Mohammed Fekry | 2023-12-17 | 2023-12-17 |  |  |  | 17751250 | 4622 | 2 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 17751250 | APPROVED |  |  | 2023-12-24 | 0 | 7 | Babic, Marian | -45277 | 7
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1985 | CONSTRUCTION OF TAIBA WEST SS-supply, installation, T&C of CCTV | APPROVED | No | 2023-12-18 | Abas, Mohammed Fekry | 2023-12-18 | 2023-12-18 |  |  |  | 1200000 | 4988 | 0 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 786974 | APPROVED |  |  | 2024-01-25 | 413026 | 38 | Babic, Marian | -45278 | 38
105-102 | CONSTRUCTION OF TAIBA WEST SS | 1987 | CONSTRUCTION OF TAIBA WEST SS-AC's for Site offices - TAIBA WEST | APPROVED | No | 2023-12-18 | Abas, Mohammed Fekry | 2023-12-18 | 2023-12-18 |  |  |  | 21600 | 4886 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 19200 | APPROVED |  |  | 2023-12-31 | 2400 | 13 | Babic, Marian | -45278 | 13
105-102 | CONSTRUCTION OF TAIBA WEST SS | 2014 | CONSTRUCTION OF TAIBA WEST SS-Civil works | APPROVED | No | 2023-12-20 | Abas, Mohammed Fekry | 2023-12-24 | 2023-12-25 |  |  |  | 12000000 | 4940 | 0 | STANDARD | Alfotohat Alomranyeh for Contracting CO | SAR | 10674600 | APPROVED |  |  | 2024-01-21 | 1325400 | 27 | Babic, Marian | -45285 | 27
105-102 | CONSTRUCTION OF TAIBA WEST SS | 2070 | CONSTRUCTION OF TAIBA WEST SS-FA&FF system | APPROVED | No | 2024-01-01 | Abas, Mohammed Fekry | 2024-01-02 | 2024-01-02 |  |  |  | 1805666 | 4943 | 0 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 1805666 | APPROVED |  |  | 2024-01-15 | 0 | 13 | Babic, Marian | -45293 | 13
105-102 | CONSTRUCTION OF TAIBA WEST SS | 2075 | CONSTRUCTION OF TAIBA WEST SS-C&P, SAS, AMI - TAIBA WEST | APPROVED | No | 2024-01-01 | Abas, Mohammed Fekry | 2024-01-02 | 2024-01-02 |  |  |  | 9400000 | 4946 | 0 | STANDARD | ALFANAR CO | SAR | 9400000 | APPROVED |  |  | 2024-01-17 | 0 | 15 | Babic, Marian | -45293 | 15
105-102 | CONSTRUCTION OF TAIBA WEST SS | 2076 | CONSTRUCTION OF TAIBA WEST SS-Telecom system - Taiba West | APPROVED | No | 2024-01-01 | Abas, Mohammed Fekry | 2024-01-02 | 2024-01-02 |  |  |  | 5350000 | 4947 | 0 | STANDARD | ALFANAR CO | SAR | 5350000 | APPROVED |  |  | 2024-01-14 | 0 | 12 | Babic, Marian | -45293 | 12
105-102 | CONSTRUCTION OF TAIBA WEST SS | 2088 | CONSTRUCTION OF TAIBA WEST SS-13.8kV MV Cables - TAIBA WEST | APPROVED | No | 2024-01-04 | Abas, Mohammed Fekry | 2024-01-08 | 2024-01-09 |  |  |  | 1275267 | 4996 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 1275267 | APPROVED |  |  | 2024-01-29 | 0 | 20 | Badhman, Saeed | -45300 | 20
105-102 | CONSTRUCTION OF TAIBA WEST SS | 2088 | CONSTRUCTION OF TAIBA WEST SS-13.8kV MV Cables - TAIBA WEST | APPROVED | No | 2024-01-04 | Abas, Mohammed Fekry | 2024-01-08 | 2024-01-09 |  |  |  | 1275267 | 4996 | 1 | STANDARD | Riyadh Cables Group Company | SAR | 1270537.1 | APPROVED |  |  | 2024-10-27 | 4729.9 | 292 | Badhman, Saeed | -45300 | 292
105-102 | CONSTRUCTION OF TAIBA WEST SS | 2149 | CONSTRUCTION OF TAIBA WEST SS-HVAC System | APPROVED | No | 2024-01-10 | Abas, Mohammed Fekry | 2024-01-10 | 2024-01-11 |  |  |  | 2100000 | 5098 | 0 | STANDARD | Magna Contracting Co | SAR | 1925000 | APPROVED |  |  | 2024-02-28 | 175000 | 48 | Babic, Marian | -45302 | 48
105-102 | CONSTRUCTION OF TAIBA WEST SS | 2185 | CONSTRUCTION OF TAIBA WEST SS-125V DC SYSTEM - TAIBA WEST | APPROVED | No | 2024-01-16 | Abas, Mohammed Fekry | 2024-01-16 | 2024-01-17 |  |  |  | 649000 | 5010 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 505000 | APPROVED |  |  | 2024-01-31 | 144000 | 14 | Babic, Marian | -45308 | 14
105-102 | CONSTRUCTION OF TAIBA WEST SS | 2197 | CONSTRUCTION OF TAIBA WEST SS-Excavation works @ TAIBA WEST SS PROJECT | APPROVED | No | 2024-01-18 | Abas, Mohammed Fekry | 2024-01-21 | 2024-01-21 |  |  |  | 90850 | 5003 | 0 | STANDARD | Construction Expertise Est. | SAR | 114550 | APPROVED |  |  | 2024-01-29 | -23700 | 8 | Babic, Marian | -45312 | 8
105-102 | CONSTRUCTION OF TAIBA WEST SS | 2246 | CONSTRUCTION OF TAIBA WEST SS-Diesel for GENSET - TAIBA WEST | APPROVED | No | 2024-01-22 | Abas, Mohammed Fekry | 2024-01-22 | 2024-01-22 |  |  |  | 60000 | 5028 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 59999.63 | APPROVED |  |  | 2024-02-06 | 0.37 | 15 | Badhman, Saeed | -45313 | 15
105-102 | CONSTRUCTION OF TAIBA WEST SS | 2294 | CONSTRUCTION OF TAIBA WEST SS-Control, LV AC/DC cables - TAIBA WEST | APPROVED | No | 2024-01-26 | Abas, Mohammed Fekry | 2024-01-29 | 2024-01-29 |  |  |  | 1179439.8 | 5118 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 1175141.82 | APPROVED |  |  | 2024-03-17 | 4297.98 | 48 | Badhman, Saeed | -45320 | 48
105-102 | CONSTRUCTION OF TAIBA WEST SS | 2294 | CONSTRUCTION OF TAIBA WEST SS-Control, LV AC/DC cables - TAIBA WEST | APPROVED | No | 2024-01-26 | Abas, Mohammed Fekry | 2024-01-29 | 2024-01-29 |  |  |  | 130680 | 5524 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 102258.32 | APPROVED |  |  | 2024-05-23 | 28421.68 | 115 | Badhman, Saeed | -45320 | 115
105-102 | CONSTRUCTION OF TAIBA WEST SS | 2501 | CONSTRUCTION OF TAIBA WEST SS-SITE OFFICE FURNITURE FOR NESMA TEAM- TAIBA WEST | RETURNED | No | 2024-02-07 | Babic, Marian | 2024-03-26 | 2024-02-10 | 2024-03-26 |  | PO for this subject already issued, this PR is a balance which is not needed | 14000 | 5097 | 0 | STANDARD | Excellence Area Trading Est.(S) | SAR | 11010 | APPROVED |  |  | 2024-02-25 | 2990 |  | Babic, Marian | -45332 | 15
105-102 | CONSTRUCTION OF TAIBA WEST SS | 2501 | CONSTRUCTION OF TAIBA WEST SS-SITE OFFICE FURNITURE FOR NESMA TEAM- TAIBA WEST | RETURNED | No | 2024-02-07 | Babic, Marian | 2024-03-26 | 2024-02-10 | 2024-03-26 |  | PO for this subject already issued, this PR is a balance which is not needed | 2000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45332 | -45332
105-102 | CONSTRUCTION OF TAIBA WEST SS | 2572 | CONSTRUCTION OF TAIBA WEST SS-Cable Ladder & Trays - Taiba West SS proejct | RETURNED | No | 2024-02-15 | Badhman, Saeed | 2024-05-21 | 2024-02-18 | 2024-05-21 |  | PO already issued (5248) | 258090.6 | 5248 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 258090.6 | APPROVED |  |  | 2024-04-02 | 0 |  | Badhman, Saeed | -45340 | 44
105-102 | CONSTRUCTION OF TAIBA WEST SS | 2680 | CONSTRUCTION OF TAIBA WEST SS-13.8kV MV Termination Kits - TAIBA WEST | APPROVED | No | 2024-02-25 | Abas, Mohammed Fekry | 2024-02-27 | 2024-02-28 |  |  |  | 150000 | 5228 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 118820.3 | APPROVED |  |  | 2024-03-27 | 31179.7 | 28 | Babic, Marian | -45350 | 28
105-102 | CONSTRUCTION OF TAIBA WEST SS | 2841 | CONSTRUCTION OF TAIBA WEST SS-Cable ladder & tray Missing item & Transportation to site- Taiba WEST | APPROVED | No | 2024-03-18 | Abas, Mohammed Fekry | 2024-03-19 | 2024-03-19 |  |  |  | 75101.67 | 5248 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 75101.67 | APPROVED |  |  | 2024-04-02 | 0 | 14 | Badhman, Saeed | -45370 | 14
105-102 | CONSTRUCTION OF TAIBA WEST SS | 3092 | CONSTRUCTION OF TAIBA WEST SS-Grounding & earthing materials- TAIBA WEST | APPROVED | No | 2024-04-22 | Abas, Mohammed Fekry | 2024-04-22 | 2024-04-23 |  |  |  | 80000 | 5527 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 76000 | APPROVED |  |  | 2024-07-07 | 4000 | 75 | Babic, Marian | -45405 | 75
105-102 | CONSTRUCTION OF TAIBA WEST SS | 3291 | CONSTRUCTION OF TAIBA WEST SS-110kV Conductor & Connectors | APPROVED | No | 2024-05-05 | Abas, Mohammed Fekry | 2024-05-06 | 2024-05-06 |  |  |  | 9000 | 5549 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 9402.99 | APPROVED |  |  | 2024-05-26 | -402.99 | 20 | Babic, Marian | -45418 | 20
105-102 | CONSTRUCTION OF TAIBA WEST SS | 3291 | CONSTRUCTION OF TAIBA WEST SS-110kV Conductor & Connectors | APPROVED | No | 2024-05-05 | Abas, Mohammed Fekry | 2024-05-06 | 2024-05-06 |  |  |  | 6750 | 5579 | 0 | STANDARD | Arruti Subestaciones , S.A.U | EUR | 5470.79 | APPROVED |  |  | 2024-05-27 | 1279.21 | 21 | Babic, Marian | -45418 | 21
105-102 | CONSTRUCTION OF TAIBA WEST SS | 3325 | CONSTRUCTION OF TAIBA WEST SS-PDS- TAIBA WEST | APPROVED | No | 2024-05-07 | Abas, Mohammed Fekry | 2024-05-09 | 2024-05-12 |  |  |  | 275000 | 5836 | 0 | STANDARD | MIDDLE EAST FIBER CABLE MANUFACTURING CO. | SAR | 217500 | APPROVED |  |  | 2024-07-31 | 57500 | 80 | Babic, Marian | -45424 | 80
105-102 | CONSTRUCTION OF TAIBA WEST SS | 3442 | CONSTRUCTION OF TAIBA WEST SS-TPI FOR FAT OF OHTC-TAIBA WEST SS PROJECT | APPROVED | No | 2024-05-19 | Abas, Mohammed Fekry | 2024-05-20 | 2024-05-21 |  |  |  | 2850 | 5330 | 0 | STANDARD | Bureau Veritas Branch Saudi Arabia | SAR | 2850 | APPROVED |  |  | 2024-05-27 | 0 | 6 | Kumar, Mr. Ranjan | -45433 | 6
105-102 | CONSTRUCTION OF TAIBA WEST SS | 3469 | CONSTRUCTION OF TAIBA WEST SS-Grounding & Earthing Materials - TAIBA WEST | RETURNED | No | 2024-05-21 | Babic, Marian | 2024-05-27 | 2024-05-23 | 2024-05-27 |  | Already 500m was included in PO for Haram, covering both SS | 9530 | 5625 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 9050.44 | APPROVED |  |  | 2024-06-03 | 479.56 |  | Babic, Marian | -45435 | 11
105-102 | CONSTRUCTION OF TAIBA WEST SS | 3469 | CONSTRUCTION OF TAIBA WEST SS-Grounding & Earthing Materials - TAIBA WEST | RETURNED | No | 2024-05-21 | Babic, Marian | 2024-05-27 | 2024-05-23 | 2024-05-27 |  | Already 500m was included in PO for Haram, covering both SS | 163700 | 5626 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 157488.03 | APPROVED |  |  | 2024-07-15 | 6211.97 |  | Babic, Marian | -45435 | 53
105-102 | CONSTRUCTION OF TAIBA WEST SS | 3469 | CONSTRUCTION OF TAIBA WEST SS-Grounding & Earthing Materials - TAIBA WEST | RETURNED | No | 2024-05-21 | Babic, Marian | 2024-05-27 | 2024-05-23 | 2024-05-27 |  | Already 500m was included in PO for Haram, covering both SS | 232700 | 5626 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 224226.55 | APPROVED |  |  | 2024-06-06 | 8473.45 |  | Babic, Marian | -45435 | 14
105-102 | CONSTRUCTION OF TAIBA WEST SS | 3469 | CONSTRUCTION OF TAIBA WEST SS-Grounding & Earthing Materials - TAIBA WEST | RETURNED | No | 2024-05-21 | Babic, Marian | 2024-05-27 | 2024-05-23 | 2024-05-27 |  | Already 500m was included in PO for Haram, covering both SS | 82670 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45435 | -45435
105-102 | CONSTRUCTION OF TAIBA WEST SS | 3543 | CONSTRUCTION OF TAIBA WEST SS-Installation works - TAIBA WEST | APPROVED | No | 2024-06-01 | Abas, Mohammed Fekry | 2024-06-03 | 2024-06-03 |  |  |  | 2861885.72 | 6272 | 0 | STANDARD | MASEERAT AL NAMA CONT.EST. | SAR | 1994868 | APPROVED |  |  | 2024-10-17 | 867017.72 | 136 | Babic, Marian | -45446 | 136
105-102 | CONSTRUCTION OF TAIBA WEST SS | 4437 | CONSTRUCTION OF TAIBA WEST SS-Transporation of Power TR's - TAIBA WEST | APPROVED | No | 2024-09-12 | Abas, Mohammed Fekry | 2024-09-16 | 2024-09-17 |  |  |  | 302000 | 6049 | 0 | STANDARD | Branch Of: OFSAT LIMITED CO | SAR | 302000 | APPROVED |  |  | 2024-10-06 | 0 | 19 | Badhman, Saeed | -45552 | 19
105-102 | CONSTRUCTION OF TAIBA WEST SS | 4614 | CONSTRUCTION OF TAIBA WEST SS-Lighting materials (FIXTURES) | APPROVED | No | 2024-10-07 | Abas, Mohammed Fekry | 2024-10-08 | 2024-10-08 |  |  |  | 82890 | 5808 | 14 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 74601 | APPROVED |  |  | 2024-10-13 | 8289 | 5 | Babic, Marian | -45573 | 5
105-102 | CONSTRUCTION OF TAIBA WEST SS | 4614 | CONSTRUCTION OF TAIBA WEST SS-Lighting materials (FIXTURES) | APPROVED | No | 2024-10-07 | Abas, Mohammed Fekry | 2024-10-08 | 2024-10-08 |  |  |  | 82890 | 5808 | 15 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 74601 | REJECTED |  |  |  | 8289 |  | Babic, Marian | -45573 | -45573
105-102 | CONSTRUCTION OF TAIBA WEST SS | 4799 | CONSTRUCTION OF TAIBA WEST SS-T&C works of Complete SS - TAIBA WEST SS PROJECT | APPROVED | No | 2024-10-28 | Abas, Mohammed Fekry | 2024-10-29 | 2024-10-29 |  |  |  | 1863301 | 6406 | 0 | STANDARD | Al Fanar Technical Services | SAR | 1863301 | APPROVED |  |  | 2025-02-17 | 0 | 111 | Mohammed, Faisal Ansari | -45594 | 111
105-102 | CONSTRUCTION OF TAIBA WEST SS | 4840 | CONSTRUCTION OF TAIBA WEST SS-Diesel Supply - GENSET- TAIBA WEST | APPROVED | No | 2024-11-05 | Abas, Mohammed Fekry | 2024-11-06 | 2024-11-06 |  |  |  | 60000 | 6493 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 52173.91 | APPROVED |  |  | 2024-11-26 | 7826.09 | 20 | Akhtar, Farhan | -45602 | 20
105-102 | CONSTRUCTION OF TAIBA WEST SS | 4860 | CONSTRUCTION OF TAIBA WEST SS-Oil Filteration machine - TAIBA WEST | APPROVED | No | 2024-11-07 | Abas, Mohammed Fekry | 2024-11-10 | 2024-11-10 |  |  |  | 55000 | 6643 | 0 | STANDARD | MASEERAT AL NAMA CONT.EST. | SAR | 51000 | APPROVED |  |  | 2025-01-12 | 4000 | 63 | Mohammed, Faisal Ansari | -45606 | 63
105-102 | CONSTRUCTION OF TAIBA WEST SS | 5036 | CONSTRUCTION OF TAIBA WEST SS-Power TR foundation works - TAIBA WEST | APPROVED | No | 2024-11-24 | Khan, Tasawar | 2024-11-28 | 2024-11-27 |  |  |  | 1129000 | 6594 | 0 | STANDARD | Al Rawy Al Arabia | SAR | 1129000 | APPROVED |  |  | 2024-12-15 | 0 | 17 | Tananeh, Khalid Jamal | -45623 | 18
105-102 | CONSTRUCTION OF TAIBA WEST SS | 5044 | CONSTRUCTION OF TAIBA WEST SS-Additional cable trays as per site modification- TAIBA WEST | APPROVED | No | 2024-11-24 | Abas, Mohammed Fekry | 2024-11-28 | 2024-11-28 |  |  |  | 43021.5 | 6574 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 39906.4 | APPROVED |  |  | 2024-12-05 | 3115.1 | 7 | Babic, Marian | -45624 | 7
105-102 | CONSTRUCTION OF TAIBA WEST SS | 5046 | CONSTRUCTION OF TAIBA WEST SS-MV termination kits for - Taiba west | APPROVED | No | 2024-11-25 | Abas, Mohammed Fekry | 2024-11-26 | 2024-11-27 |  |  |  | 8668 | 5228 | 1 | STANDARD | Nima Arabia Company Limited | SAR | 8668 | APPROVED |  |  | 2024-12-31 | 0 | 34 | Babic, Marian | -45623 | 34
105-102 | CONSTRUCTION OF TAIBA WEST SS | 5111 | CONSTRUCTION OF TAIBA WEST SS-Power Sockets & Recepticals - TAIBA WEST SS PROJECT | APPROVED | No | 2024-12-02 | Abas, Mohammed Fekry | 2024-12-03 | 2024-12-03 |  |  |  | 149056 | 6592 | 0 | STANDARD | Tawasul International Trad.Est. | SAR | 143370.25 | APPROVED |  |  | 2024-12-19 | 5685.75 | 16 | Babic, Marian | -45629 | 16
105-102 | CONSTRUCTION OF TAIBA WEST SS | 5472 | CONSTRUCTION OF TAIBA WEST SS-Outdoor Lighting fixtures & sensors - TAIBA WEST SS project | RETURNED | No | 2025-01-20 | Babic, Marian | 2025-10-26 | 2025-02-19 | 2025-10-26 |  | please resubmit after providing all the necessary documents | 47430 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45707 | -45707
105-102 | CONSTRUCTION OF TAIBA WEST SS | 5721 | CONSTRUCTION OF TAIBA WEST SS-Cable Tray for HVAC & Accessories for Cable ladder - TAIBA WEST | RETURNED | No | 2025-01-29 | Badhman, Saeed | 2025-08-25 | 2025-02-02 | 2025-08-25 |  | not needed | 150900.89 | 5248 | 1 | STANDARD | Mid-East Cable Support Solutions | SAR | 143376.63 | APPROVED |  |  | 2025-10-21 | 7524.26 |  | Badhman, Saeed | -45690 | 261
105-102 | CONSTRUCTION OF TAIBA WEST SS | 5721 | CONSTRUCTION OF TAIBA WEST SS-Cable Tray for HVAC & Accessories for Cable ladder - TAIBA WEST | RETURNED | No | 2025-01-29 | Badhman, Saeed | 2025-08-25 | 2025-02-02 | 2025-08-25 |  | not needed | 15226.1 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45690 | -45690
105-102 | CONSTRUCTION OF TAIBA WEST SS | 5723 | CONSTRUCTION OF TAIBA WEST SS-PR for Open WH @ TAIBA WEST SS Project | APPROVED | No | 2025-01-29 | Abas, Mohammed Fekry | 2025-02-01 | 2025-02-02 |  |  |  | 80000 | 6858 | 0 | STANDARD | Rukn Al Kateibah Company for Security Guards. | SAR | 77400 | APPROVED |  |  | 2025-02-17 | 2600 | 15 | Abuhammad, Samir | -45690 | 15
105-102 | CONSTRUCTION OF TAIBA WEST SS | 6029 | CONSTRUCTION OF TAIBA WEST SS-Lighting Poles - TAIBA WEST | APPROVED | No | 2025-02-24 | Abas, Mohammed Fekry | 2025-04-12 | 2025-04-13 |  |  | We are utilizing the budget from item#4.3 | 3250 | 6982 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 3250 | APPROVED |  |  | 2025-04-17 | 0 | 4 | Muaz, Alaa | -45760 | 4
105-102 | CONSTRUCTION OF TAIBA WEST SS | 6315 | CONSTRUCTION OF TAIBA WEST SS-Transporation charges for Cable ladder & tray- TAIBA WEST | APPROVED | No | 2025-04-10 | Abas, Mohammed Fekry | 2025-04-13 | 2025-04-13 |  |  | we are utilizing the budget from item# 6.1.8.2.4 For transporation of materials. | 4000 | 5248 | 1 | STANDARD | Mid-East Cable Support Solutions | SAR | 4000 | APPROVED |  |  | 2025-10-21 | 0 | 191 | Badhman, Saeed | -45760 | 191
105-102 | CONSTRUCTION OF TAIBA WEST SS | 6323 | CONSTRUCTION OF TAIBA WEST SS-Fire raterdient paint for MV cables - TAIBA WEST | APPROVED | No | 2025-04-10 | Abas, Mohammed Fekry | 2025-04-13 | 2025-04-13 |  |  | we are utilizing the budget from Item# 3.1.9.2 | 105000 | 7142 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 99200 | APPROVED |  |  | 2025-04-24 | 5800 | 11 | Babic, Marian | -45760 | 11
105-102 | CONSTRUCTION OF TAIBA WEST SS | 6527 | CONSTRUCTION OF TAIBA WEST SS-Stand AC's for T&C works | APPROVED | No | 2025-05-06 | Abas, Mohammed Fekry | 2025-05-11 | 2025-05-11 |  |  | We are utililizing budget from item#6.1.7.2 | 88000 | 7271 | 0 | STANDARD | Voltage Professionals contracting establishment | SAR | 83300 | APPROVED |  |  | 2025-05-15 | 4700 | 4 | Babic, Marian | -45788 | 4
105-102 | CONSTRUCTION OF TAIBA WEST SS | 6589 | CONSTRUCTION OF TAIBA WEST SS-Ground Enhancment Materials- TAIBA WEST | APPROVED | No | 2025-05-12 | Abas, Mohammed Fekry | 2025-05-12 | 2025-05-14 |  |  | We are utilizing the budget from Item#4.2 | 48950 | 7302 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 34375 | APPROVED |  |  | 2025-06-01 | 14575 | 18 | Babic, Marian | -45791 | 18
105-102 | CONSTRUCTION OF TAIBA WEST SS | 6621 | CONSTRUCTION OF TAIBA WEST SS-Diesel for Generators - TAIBA WEST | APPROVED | No | 2025-05-15 | Abas, Mohammed Fekry | 2025-05-19 | 2025-05-19 |  |  | We are utilizing the budget from item#6.1.4.2 as there is no meter connection at site so using Diesel Generators. | 57826.22 | 7327 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 57826.22 | APPROVED |  |  | 2025-06-04 | 0 | 16 | Akhtar, Farhan | -45796 | 16
105-102 | CONSTRUCTION OF TAIBA WEST SS | 6622 | CONSTRUCTION OF TAIBA WEST SS-Cable Clamps & Cleats - TAIBA WEST | APPROVED | No | 2025-05-15 | Abas, Mohammed Fekry | 2025-05-19 | 2025-05-19 |  |  | We are utilizing the budget from Item3.1.9.2 | 75075 | 7285 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 75075 | APPROVED |  |  | 2025-05-24 | 0 | 5 | Babic, Marian | -45796 | 5
105-102 | CONSTRUCTION OF TAIBA WEST SS | 6797 | CONSTRUCTION OF TAIBA WEST SS-MV Cable Glands & LV Cable Lugs - TAIBA WEST SS project | RETURNED | No | 2025-06-15 | Babic, Marian | 2025-07-20 | 2025-06-17 | 2025-07-20 |  | please revise items and prices | 31890 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45825 | -45825
105-102 | CONSTRUCTION OF TAIBA WEST SS | 6936 | CONSTRUCTION OF TAIBA WEST SS-Rental Dilo Machine | APPROVED | No | 2025-06-30 | Abas, Mohammed Fekry | 2025-07-01 | 2025-07-01 |  |  |  | 16500 | 7471 | 0 | STANDARD | Energy Direction Company | SAR | 16500 | APPROVED |  |  | 2025-07-16 | 0 | 15 | Babic, Marian | -45839 | 15
105-102 | CONSTRUCTION OF TAIBA WEST SS | 6953 | CONSTRUCTION OF TAIBA WEST SS-Rental Dilo Machine - Mobilization charges | APPROVED | No | 2025-07-01 | Abas, Mohammed Fekry | 2025-07-03 | 2025-07-04 |  |  |  | 6500 | 7471 | 0 | STANDARD | Energy Direction Company | SAR | 6500 | APPROVED |  |  | 2025-07-16 | 0 | 12 | Babic, Marian | -45842 | 12
105-102 | CONSTRUCTION OF TAIBA WEST SS | 7192 | CONSTRUCTION OF TAIBA WEST SS-Cable Lugs & Glands - Ahmed Essa CO | APPROVED | No | 2025-07-23 | Abas, Mohammed Fekry | 2025-07-24 | 2025-07-24 |  |  |  | 65935 | 7551 | 0 | STANDARD | Ahmed Essa Mohammed Al Muslim Est. | SAR | 62000 | APPROVED |  |  | 2025-08-31 | 3935 | 38 | Babic, Marian | -45862 | 38
105-102 | CONSTRUCTION OF TAIBA WEST SS | 7256 | CONSTRUCTION OF TAIBA WEST SS-Rental Manpower @ TAIBA WEST SS PROJECT | APPROVED | No | 2025-08-03 | Abas, Mohammed Fekry | 2025-09-15 | 2025-09-16 |  |  | We are utilizing the budget from item# 6.1.2.3 | 137280 | 7593 | 0 | STANDARD | Jasem M.AlJasem Contracting Est. | SAR | 9000 | APPROVED |  |  | 2025-09-28 | 128280 | 12 | Babic, Marian | -45916 | 12
105-102 | CONSTRUCTION OF TAIBA WEST SS | 7787 | FO cables - TAIBA WEST | RETURNED | No | 2025-09-18 | Muaz, Alaa | 2025-10-20 | 2025-09-28 | 2025-10-20 |  | As there is an issue with exceed budget and it doesn't resolved till now. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -45928 | -45928
105-102 | CONSTRUCTION OF TAIBA WEST SS | 7790 | PO for construction of Open WH beside SS project | REJECTED | No | 2025-09-18 | Alwahabi, Faisal Saad | 2025-09-18 | 2025-09-18 |  | 2025-09-21 |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45918 | -45918
105-102 | CONSTRUCTION OF TAIBA WEST SS | 7791 | 2No.s Damage MV SWGR panels | REJECTED | No | 2025-09-18 | Yamama, Loai Mohamed | 2025-09-24 | 2025-09-21 |  | 2025-09-24 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45921 | -45921
105-102 | CONSTRUCTION OF TAIBA WEST SS | 7960 | Rental Manpower for T&C @ TAIBA WEST | REJECTED | No | 2025-10-15 | Yamama, Loai Mohamed | 2025-10-22 | 2025-10-16 |  | 2025-10-22 |  | 5 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45946 | -45946
105-102 | CONSTRUCTION OF TAIBA WEST SS | 8036 | Rental Manpower for T&C @ TAIBA WEST | RETURNED | No | 2025-10-23 | Babic, Marian | 2025-11-06 | 2025-10-27 | 2025-11-06 |  | the unit price cannot be modified because it is not 0 | 5 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45957 | -45957
105-102 | CONSTRUCTION OF TAIBA WEST SS | 8166 | Rental Manpower | APPROVED | No | 2025-11-10 | Abas, Mohammed Fekry | 2025-11-12 | 2025-11-13 |  |  | We are utilizing manpower to assist Alfanar during T&C works. This PR has been raised earlier and PO of Al Jasem was raised. now It is raised again for new vendor | 0 | 7948 | 0 | STANDARD | Subl Al Nada Company Ltd(S) | SAR | 0 | REJECTED |  |  |  | 0 |  | Alhadi, Khalid | -45974 | -45974
105-102 | CONSTRUCTION OF TAIBA WEST SS | 8166 | Rental Manpower | APPROVED | No | 2025-11-10 | Abas, Mohammed Fekry | 2025-11-12 | 2025-11-13 |  |  | We are utilizing manpower to assist Alfanar during T&C works. This PR has been raised earlier and PO of Al Jasem was raised. now It is raised again for new vendor | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45974 | -45974
105-102 | CONSTRUCTION OF TAIBA WEST SS | 8225 | Open store @Taiba west SS Project | APPROVED | No | 2025-11-16 | Abas, Mohammed Fekry | 2025-12-18 | 2025-12-18 |  |  | We are utilizing the budget under Civil item as store was constructed to materials storage. | 0 | 8036 | 0 | STANDARD | Construction Expertise Est. | SAR | 103415 | APPROVED | 2026-01-06 | 2026-01-13 | 2026-01-22 | -103415 | 35 | Babic, Marian | 26 | 35
105-102 | CONSTRUCTION OF TAIBA WEST SS | 8539 | FO cables and its associated works | APPROVED | No | 2025-12-17 | Abas, Mohammed Fekry | 2025-12-23 | 2025-12-24 |  |  | We are utiliizing budget from Control & FO cables budget. PO 7646 was issued to Smart tech but due to shortage of budget this PR was rejected and issued again after approval of latest CTC | 0 | 7646 | 0 | STANDARD | SMART TECH | SAR | 280000 | APPROVED | 2025-12-24 | 2026-01-01 | 2026-01-05 | -280000 | 12 | Babic, Marian | 8 | 12
105-102 | CONSTRUCTION OF TAIBA WEST SS | 8541 | Diesel for GENSET | RETURNED | No | 2025-12-17 | Akhtar, Farhan | 2025-12-30 | 2025-12-24 | 2025-12-30 |  | Please check the QTY 102 Liters.QTY shall be more to proceeed further | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -46015 | -46015
105-105 | Operation of Security Systems- | 2760 | Operation of Security Systems--DAHUA CCTV ( Dahua Dome Cameras – 10 pcs,Dahua Bullet Cameras – 10 pcs & VMS – License – 20 licenses) | APPROVED | No | 2024-03-04 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 41930 | 5241 | 0 | STANDARD | Zamil Group Trade & Service Co | SAR | 41930 | APPROVED |  |  | 2024-04-15 | 0 | 39 | Abuhammad, Samir | -45358 | 39
105-105 | Operation of Security Systems- | 2783 | Operation of Security Systems--Supply of SKIDATA Screws For arm barriers ( Spare Parts ) | APPROVED | No | 2024-03-05 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 22050 | 5281 | 0 | STANDARD | QUDRA COMMUNICATION AND INFORMATION TECHNOLOGY | SAR | 22050 | APPROVED |  |  | 2024-04-15 | 0 | 39 | Abuhammad, Samir | -45358 | 39
105-105 | Operation of Security Systems- | 2786 | Operation of Security Systems--Manlift rental - Extention for 33 Months of PO# 8126 (4546) | APPROVED | No | 2024-03-05 | Abas, Mohammed Fekry | 2024-03-10 | 2024-03-10 |  |  |  | 544500 | 6260 | 0 | STANDARD | Expertise Contracting Co. | SAR | 181500 | APPROVED |  |  | 2024-10-24 | 363000 | 228 | Abuhammad, Samir | -45361 | 228
105-105 | Operation of Security Systems- | 2789 | Operation of Security Systems--Manlift rental - Extention for 36 Months of PO# 4470 | APPROVED | No | 2024-03-05 | Abas, Mohammed Fekry | 2024-03-10 | 2024-03-10 |  |  |  | 432000 | 6260 | 0 | STANDARD | Expertise Contracting Co. | SAR | 156000 | APPROVED |  |  | 2024-10-24 | 276000 | 228 | Abuhammad, Samir | -45361 | 228
105-105 | Operation of Security Systems- | 2812 | Operation of Security Systems--Supply of Dell Servers Expansion (Task 2.12 - Services - Spareparts and 3rd party services requested by customer) | APPROVED | No | 2024-03-12 | Abas, Mohammed Fekry | 2024-03-13 | 2024-03-13 |  |  |  | 42486 | 5257 | 0 | STANDARD | SAUDI BUSINESS MACHINES | SAR | 42486 | APPROVED |  |  | 2024-04-16 | 0 | 34 | Abuhammad, Samir | -45364 | 34
105-105 | Operation of Security Systems- | 2913 | Operation of Security Systems--Supply with installation SFSP office | APPROVED | No | 2024-03-27 | Abas, Mohammed Fekry | 2024-04-01 | 2024-04-02 |  |  |  | 299520 | 5334 | 0 | STANDARD | NESMA UNITED CO. | SAR | 299520 | APPROVED |  |  | 2024-05-01 | 0 | 29 | Abuhammad, Samir | -45384 | 29
105-105 | Operation of Security Systems- | 2970 | Operation of Security Systems--Remote Support For Terma Radar for Neom O&M Project | APPROVED | No | 2024-04-01 | Abas, Mohammed Fekry | 2024-04-03 | 2024-04-04 |  |  |  | 13280 | 5338 | 0 | STANDARD | TERMA A/S | EUR | 13280 | APPROVED |  |  | 2024-05-12 | 0 | 38 | Abuhammad, Samir | -45386 | 38
105-105 | Operation of Security Systems- | 3053 | Operation of Security Systems--Supply of Tools - Task No:3.1 | APPROVED | No | 2024-04-17 | Abas, Mohammed Fekry | 2024-04-20 | 2024-04-23 |  |  |  | 47537 | 5437 | 0 | STANDARD | Bright Wire Company | SAR | 47499 | APPROVED |  |  | 2024-05-14 | 38 | 21 | Abuhammad, Samir | -45405 | 21
105-105 | Operation of Security Systems- | 3059 | Operation of Security Systems--Supply of Hard disk | APPROVED | No | 2024-04-18 | Abas, Mohammed Fekry | 2024-04-23 | 2024-04-23 |  |  |  | 123760 | 5443 | 0 | STANDARD | Digital Security Shield Co. | SAR | 123760 | APPROVED |  |  | 2024-05-30 | 0 | 37 | Abuhammad, Samir | -45405 | 37
105-105 | Operation of Security Systems- | 3238 | Operation of Security Systems--Supply of PC for Neom O&M project 105-105 | APPROVED | No | 2024-05-01 | Abas, Mohammed Fekry | 2024-05-02 | 2024-05-02 |  |  |  | 6086.08 | 5521 | 0 | STANDARD | Golden Technology trading Company. | SAR | 6080 | APPROVED |  |  | 2024-05-14 | 6.08 | 12 | Abuhammad, Samir | -45414 | 12
105-105 | Operation of Security Systems- | 3444 | Operation of Security Systems--CCTV Installation Gate 4 FR | APPROVED | No | 2024-05-20 | Abas, Mohammed Fekry | 2024-05-21 | 2024-05-22 |  |  |  | 61000 | 5630 | 0 | STANDARD | Tabsher Est for operation and maintenance. | SAR | 55820 | APPROVED |  |  | 2024-06-13 | 5180 | 22 | Abuhammad, Samir | -45434 | 22
105-105 | Operation of Security Systems- | 3485 | Operation of Security Systems--Backup solution for 100/200 TB | APPROVED | No | 2024-05-23 | Abas, Mohammed Fekry | 2024-05-23 | 2024-05-26 |  |  |  | 89211 | 5672 | 0 | STANDARD | Golden Technology trading Company. | SAR | 72660 | APPROVED |  |  | 2024-06-10 | 16551 | 15 | Abuhammad, Samir | -45438 | 15
105-105 | Operation of Security Systems- | 3486 | Operation of Security Systems--Supply of PC's | APPROVED | No | 2024-05-23 | Abas, Mohammed Fekry | 2024-05-23 | 2024-05-26 |  |  |  | 13725 | 5621 | 0 | STANDARD | Golden Technology trading Company. | SAR | 13715 | APPROVED |  |  | 2024-06-03 | 10 | 8 | Abuhammad, Samir | -45438 | 8
105-105 | Operation of Security Systems- | 3717 | Operation of Security Systems--Supply of 1 PC & 3 Monitors | APPROVED | No | 2024-07-01 | Abas, Mohammed Fekry | 2024-07-02 | 2024-07-03 |  |  |  | 3130 | 5776 | 0 | STANDARD | Golden Technology trading Company. | SAR | 3130 | APPROVED |  |  | 2024-07-16 | 0 | 13 | Abuhammad, Samir | -45476 | 13
105-105 | Operation of Security Systems- | 3758 | Operation of Security Systems--Supply of Fortinet Firewalls | APPROVED | No | 2024-07-02 | Abas, Mohammed Fekry | 2024-07-09 | 2024-07-09 |  |  |  | 41560.74 | 5842 | 0 | STANDARD | Exclusive Networks For Information Systems Technology | SAR | 41560.74 | APPROVED |  |  | 2024-08-07 | 0 | 29 | Abuhammad, Samir | -45482 | 29
105-105 | Operation of Security Systems- | 3760 | Operation of Security Systems--Remote Support For Terma Radar | APPROVED | No | 2024-07-03 | Abas, Mohammed Fekry | 2024-07-09 | 2024-07-09 |  |  |  | 6150 | 5807 | 0 | STANDARD | TERMA A/S | EUR | 6150 | APPROVED |  |  | 2024-07-23 | 0 | 14 | Abuhammad, Samir | -45482 | 14
105-105 | Operation of Security Systems- | 3818 | Operation of Security Systems--Supply of SFP-1000BaseT – Huawei | APPROVED | No | 2024-07-10 | Abas, Mohammed Fekry | 2024-07-15 | 2024-07-15 |  |  |  | 2965 | 5861 | 0 | STANDARD | Integrated Network Solutions Trading Est. | SAR | 2885 | APPROVED |  |  | 2024-08-05 | 80 | 21 | Abuhammad, Samir | -45488 | 21
105-105 | Operation of Security Systems- | 4029 | Operation of Security Systems--Supply of Lenovo ThinkPad T14 Gen 4 Intel Laptop | APPROVED | No | 2024-07-28 | Abas, Mohammed Fekry | 2024-07-29 | 2024-07-29 |  |  |  | 6890 | 5877 | 0 | STANDARD | Golden Technology trading Company. | SAR | 6890 | APPROVED |  |  | 2024-08-05 | 0 | 7 | Abuhammad, Samir | -45502 | 7
105-105 | Operation of Security Systems- | 4032 | Operation of Security Systems--OSHA Team Training | APPROVED | No | 2024-07-28 | Abas, Mohammed Fekry | 2024-07-29 | 2024-07-29 |  |  |  | 14000 | 5878 | 0 | STANDARD | Abad Networks for Training | SAR | 14000 | APPROVED |  |  | 2024-08-20 | 0 | 22 | Abuhammad, Samir | -45502 | 22
105-105 | Operation of Security Systems- | 4104 | Operation of Security Systems--Supply of Arm Barriers - FAAC | APPROVED | No | 2024-08-06 | Abas, Mohammed Fekry | 2024-08-06 | 2024-08-07 |  |  |  | 20104 | 6099 | 0 | STANDARD | Aflak Electronic Industries Co.Ltd. | SAR | 20104 | APPROVED |  |  | 2024-09-05 | 0 | 29 | Abuhammad, Samir | -45511 | 29
105-105 | Operation of Security Systems- | 4105 | Operation of Security Systems--Supplying and Installation of the Board of Sliding Gate4 in NC1 | RETURNED | No | 2024-08-06 | Abuhammad, Samir | 2024-09-08 | 2024-08-07 | 2024-09-08 |  | as per PM considered as cash site. | 5126.4 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45511 | -45511
105-105 | Operation of Security Systems- | 4210 | Operation of Security Systems--Supply of Face Recognition Access Controller Devices ¦ Spareparts and 3rd party services requested by customer | APPROVED | No | 2024-08-19 | Abas, Mohammed Fekry | 2024-08-25 | 2024-08-25 |  |  |  | 26180 | 6097 | 0 | STANDARD | Zamil Group Trade & Service Co | SAR | 26180 | APPROVED |  |  | 2024-09-03 | 0 | 9 | Abuhammad, Samir | -45529 | 9
105-105 | Operation of Security Systems- | 4303 | Operation of Security Systems--Supply of HP Mini PC | APPROVED | No | 2024-08-29 | Abas, Mohammed Fekry | 2024-09-01 | 2024-09-01 |  |  |  | 22800 | 6110 | 0 | STANDARD | Golden Technology trading Company. | SAR | 20400 | APPROVED |  |  | 2024-09-05 | 2400 | 4 | Abuhammad, Samir | -45536 | 4
105-105 | Operation of Security Systems- | 4393 | Operation of Security Systems--Supply and Installation of Portacabin- Spare parts & 3rd party services | APPROVED | No | 2024-09-09 | Abas, Mohammed Fekry | 2024-09-11 | 2024-09-11 |  |  |  | 24000 | 6183 | 0 | STANDARD | Abdulmohsen Al Tamimi Contracting Company (S) | SAR | 24000 | APPROVED |  |  | 2024-09-19 | 0 | 8 | Abuhammad, Samir | -45546 | 8
105-105 | Operation of Security Systems- | 4413 | Operation of Security Systems--Installation of ANPR Cameras in Main Gate - NC2 | APPROVED | No | 2024-09-11 | Abas, Mohammed Fekry | 2024-09-16 | 2024-09-17 |  |  |  | 20308 | 6215 | 0 | STANDARD | Tabsher Est for operation and maintenance. | SAR | 19915 | APPROVED |  |  | 2024-09-19 | 393 | 2 | Abuhammad, Samir | -45552 | 2
105-105 | Operation of Security Systems- | 4428 | Operation of Security Systems--Supply of Dahua Service - Silver Cards | APPROVED | No | 2024-09-12 | Abas, Mohammed Fekry | 2024-09-16 | 2024-09-17 |  |  |  | 3750 | 6216 | 0 | STANDARD | Zamil Group Trade & Service Co | SAR | 3750 | APPROVED |  |  | 2024-09-19 | 0 | 2 | Abuhammad, Samir | -45552 | 2
105-105 | Operation of Security Systems- | 4457 | Operation of Security Systems--Supply of Servers | APPROVED | No | 2024-09-15 | Abas, Mohammed Fekry | 2024-09-16 | 2024-09-17 |  |  |  | 151978.19 | 6214 | 0 | STANDARD | Branch Bots Inc | SAR | 146410 | APPROVED |  |  | 2024-10-01 | 5568.19 | 14 | Abuhammad, Samir | -45552 | 14
105-105 | Operation of Security Systems- | 4655 | Operation of Security Systems--Dismantling of Um Alhasani VHF system and reinstall it on the STC tower | APPROVED | No | 2024-10-10 | Abas, Mohammed Fekry | 2024-10-14 | 2024-10-15 |  |  |  | 12000 | 6355 | 0 | STANDARD | Irshad Albnaa Contracting Est. | SAR | 12000 | APPROVED |  |  | 2024-10-28 | 0 | 13 | Abuhammad, Samir | -45580 | 13
105-105 | Operation of Security Systems- | 4712 | Operation of Security Systems--Supply Of Dahua CCTV | APPROVED | No | 2024-10-17 | Abas, Mohammed Fekry | 2024-10-20 | 2024-10-20 |  |  |  | 231863 | 6374 | 0 | STANDARD | Zamil Group Trade & Service Co | SAR | 231863 | APPROVED |  |  | 2024-10-30 | 0 | 10 | Abuhammad, Samir | -45585 | 10
105-105 | Operation of Security Systems- | 4767 | Operation of Security Systems--Supply of Motor Control Board SKIDATA Arm Barrier | APPROVED | No | 2024-10-22 | Abas, Mohammed Fekry | 2024-10-27 | 2024-10-27 |  |  |  | 7500 | 6395 | 0 | STANDARD | QUDRA COMMUNICATION AND INFORMATION TECHNOLOGY | SAR | 7500 | APPROVED |  |  | 2024-11-03 | 0 | 7 | Abuhammad, Samir | -45592 | 7
105-105 | Operation of Security Systems- | 4783 | Operation of Security Systems--Supply of Fiber Optics Materials | APPROVED | No | 2024-10-23 | Abas, Mohammed Fekry | 2024-10-27 | 2024-10-27 |  |  |  | 10410 | 6393 | 0 | STANDARD | Bright Wire Company | SAR | 10410 | APPROVED |  |  | 2024-11-04 | 0 | 8 | Abuhammad, Samir | -45592 | 8
105-105 | Operation of Security Systems- | 4797 | Operation of Security Systems--Supply of Jira licences | APPROVED | No | 2024-10-27 | Abas, Mohammed Fekry | 2024-11-05 | 2024-11-05 |  |  |  | 45600 | 6438 | 0 | STANDARD | SPECTRUM FOR INFORMATION TECHNOLOGIES CO | SAR | 45600 | APPROVED |  |  | 2024-11-12 | 0 | 7 | Abuhammad, Samir | -45601 | 7
105-105 | Operation of Security Systems- | 4853 | Operation of Security Systems--FAAC - Pro Access Barrier + FAAC spare part | APPROVED | No | 2024-11-06 | Abas, Mohammed Fekry | 2024-11-11 | 2024-11-12 |  |  |  | 82501 | 6482 | 0 | STANDARD | Aflak Electronic Industries Co.Ltd. | SAR | 82501 | APPROVED |  |  | 2024-11-20 | 0 | 8 | Abuhammad, Samir | -45608 | 8
105-105 | Operation of Security Systems- | 4919 | Operation of Security Systems--Supply of LBA La Barriere Automatique | REJECTED | No | 2024-11-13 | Mraish, Fahed Mhd Yaser | 2024-11-25 | 2024-11-18 | 2024-11-20 | 2024-11-25 | Pls amendment the UOM & Price in order to convert the cost to EUR. | 2071897427.6 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45614 | -45614
105-105 | Operation of Security Systems- | 5049 | Operation of Security Systems--Supply of Aluminum Termination kit cable 3*500 MV Denson | APPROVED | No | 2024-11-25 | Abas, Mohammed Fekry | 2024-11-27 | 2024-11-28 |  |  |  | 4750 | 6572 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 4750 | APPROVED |  |  | 2024-12-04 | 0 | 6 | Abuhammad, Samir | -45624 | 6
105-105 | Operation of Security Systems- | 5051 | Operation of Security Systems--Supply of LBA La Barriere Automatique | APPROVED | No | 2024-11-25 | Abas, Mohammed Fekry | 2024-11-27 | 2024-11-28 |  |  |  | 45518.2 | 6535 | 0 | STANDARD | LBA International Trading DWC-LLC | EUR | 45518.2 | APPROVED |  |  | 2024-12-04 | 0 | 6 | Abuhammad, Samir | -45624 | 6
105-105 | Operation of Security Systems- | 5192 | Operation of Security Systems--Price differences for extra scope for P.O# 6395 PR No.4767 Based on customer Approval. (spareparts requested by customer) | APPROVED | No | 2024-12-08 | Abas, Mohammed Fekry | 2024-12-11 | 2024-12-12 |  |  |  | 2000 | 6395 | 1 | STANDARD | QUDRA COMMUNICATION AND INFORMATION TECHNOLOGY | SAR | 2000 | APPROVED |  |  | 2024-12-24 | 0 | 12 | Abuhammad, Samir | -45638 | 12
105-105 | Operation of Security Systems- | 5299 | Operation of Security Systems--Supply of Sound System and Microphone | APPROVED | No | 2024-12-30 | Abas, Mohammed Fekry | 2025-01-02 | 2025-01-02 |  |  |  | 20950 | 6732 | 0 | STANDARD | BAKHITA TINI AL DOSSARY for CONTRACTING Est. | SAR | 20950 | APPROVED |  |  | 2025-01-15 | 0 | 13 | Abuhammad, Samir | -45659 | 13
105-105 | Operation of Security Systems- | 5377 | Operation of Security Systems--RENEWAL SIP TRUNK & ADDITIONAL SIP- Mobily Service | REJECTED | No | 2025-01-08 | Mraish, Fahed Mhd Yaser | 2025-01-08 |  |  | 2025-01-09 | based on site team request | 12000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | 0 | 0
105-105 | Operation of Security Systems- | 5437 | Operation of Security Systems--PR For Rental of 200Kva Diesel Generator to Neom Public Safety | APPROVED | No | 2025-01-15 | Abas, Mohammed Fekry | 2025-01-20 | 2025-01-23 |  |  |  | 4999 | 6849 | 0 | STANDARD | NESMA UNITED INDUSTRIES CO. LTD. | SAR | 4999 | APPROVED |  |  | 2025-02-17 | 0 | 25 | Abuhammad, Samir | -45680 | 25
105-105 | Operation of Security Systems- | 6111 | Operation of Security Systems--PR For Testing of HV cable as per ENOWA requirements | APPROVED | No | 2025-03-04 | Abas, Mohammed Fekry | 2025-03-05 | 2025-03-05 |  |  | Testing of Hv Cable-Budget Item-2.12(Services - Spareparts and 3rd party services requested by customer) | 8000 | 7001 | 0 | STANDARD | Saudi Delta Company for Power Projects Ltd | SAR | 8000 | APPROVED |  |  | 2025-03-18 | 0 | 13 | Abuhammad, Samir | -45721 | 13
105-105 | Operation of Security Systems- | 6207 | Operation of Security Systems--PR For Confluence License- Supplier(InfoSysta) | APPROVED | No | 2025-03-19 | Abas, Mohammed Fekry | 2025-03-25 | 2025-03-25 |  |  | Confluence License-Budget Task#2.12-Services Spareparts | 64598 | 7075 | 0 | STANDARD | SPECTRUM FOR INFORMATION TECHNOLOGIES CO | SAR | 45850 | APPROVED |  |  | 2025-04-14 | 18748 | 20 | Abuhammad, Samir | -45741 | 20
105-105 | Operation of Security Systems- | 6457 | Operation of Security Systems--PR for Nc1 Gate 1 Fiber | APPROVED | No | 2025-04-27 | Abas, Mohammed Fekry | 2025-05-05 | 2025-05-06 |  |  | 2.12-Services - Spareparts and 3rd party services requested by customer-NTT-Projects Services-Services (Non-Classified) | 17350 | 7239 | 0 | STANDARD | BAKHITA TINI AL DOSSARY for CONTRACTING Est. | SAR | 17350 | APPROVED |  |  | 2025-07-22 | 0 | 77 | Abuhammad, Samir | -45783 | 77
105-105 | Operation of Security Systems- | 6458 | Operation of Security Systems--PR for NC2 Excavation & Cable Conduit Test, Breaker | APPROVED | No | 2025-04-27 | Abas, Mohammed Fekry | 2025-05-05 | 2025-05-06 |  |  | 2.12-Services - Spareparts and 3rd party services requested by customer-NTT-Projects Services-Services (Non-Classified) | 19100 | 7238 | 0 | STANDARD | BAKHITA TINI AL DOSSARY for CONTRACTING Est. | SAR | 19100 | APPROVED |  |  | 2025-07-22 | 0 | 77 | Abuhammad, Samir | -45783 | 77
105-105 | Operation of Security Systems- | 6752 | Operation of Security Systems--PR For Tablet, License and SIM cards -O&M Project | APPROVED | No | 2025-05-29 | Abas, Mohammed Fekry | 2025-06-01 | 2025-06-02 |  |  | Tablet, License and SIM cards-(Task#2.12-Spare Parts) | 316296 | 7397 | 0 | STANDARD | Atheeb Integrated Solutions Company | SAR | 316296 | APPROVED |  |  | 2025-06-19 | 0 | 17 | Abuhammad, Samir | -45810 | 17
105-106 | O&M - Dammam, Al Ahsa & Hafer | 7576 | CMMS Software New Dammam Project | APPROVED | No | 2025-08-31 | Abas, Mohammed Fekry | 2025-09-29 | 2025-10-02 |  |  | CMM Software Services ,Budget Task# 3.9.1 | 0 | 7666 | 0 | STANDARD | Zoho Technologies Company(S) | SAR | 27226.08 | APPROVED |  |  | 2025-10-19 | -27226.08 | 17 | Abuhammad, Samir | -45932 | 17
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1583 | S/S NM PSS-A & PSS-B IN NEOM-33kV Switchgear PSSA & PSSB SS | APPROVED | No | 2023-10-11 | Abas, Mohammed Fekry | 2023-10-11 | 2023-10-12 |  |  |  | 14400000 | 5681 | 0 | STANDARD | ALFANAR CO | SAR | 14390000 | APPROVED |  |  | 2024-06-13 | 10000 | 245 | Kumar, Mr. Ranjan | -45211 | 245
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1583 | S/S NM PSS-A & PSS-B IN NEOM-33kV Switchgear PSSA & PSSB SS | APPROVED | No | 2023-10-11 | Abas, Mohammed Fekry | 2023-10-11 | 2023-10-12 |  |  |  | 9800000 | 5682 | 0 | STANDARD | ALFANAR CO | SAR | 9800000 | APPROVED |  |  | 2024-06-13 | 0 | 245 | Kumar, Mr. Ranjan | -45211 | 245
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1584 | S/S NM PSS-A & PSS-B IN NEOM-Control & Protection Panels | APPROVED | No | 2023-10-11 | Abas, Mohammed Fekry | 2023-10-11 | 2023-10-12 |  |  |  | 10200000 | 5779 | 0 | STANDARD | ALFANAR CO | SAR | 9335000 | APPROVED |  |  | 2024-07-17 | 865000 | 279 | Kumar, Mr. Ranjan | -45211 | 279
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1584 | S/S NM PSS-A & PSS-B IN NEOM-Control & Protection Panels | APPROVED | No | 2023-10-11 | Abas, Mohammed Fekry | 2023-10-11 | 2023-10-12 |  |  |  | 7700000 | 5780 | 0 | STANDARD | ALFANAR CO | SAR | 7083000 | APPROVED |  |  | 2024-07-17 | 617000 | 279 | Kumar, Mr. Ranjan | -45211 | 279
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1585 | S/S NM PSS-A & PSS-B IN NEOM-Telecommincation Panels | RETURNED | No | 2023-10-11 | Kumar, Mr. Ranjan | 2024-12-15 | 2023-10-12 | 2024-12-15 |  | Please issue PR with correct budget line reference as comented by finance department | 2450000 | 5782 | 0 | STANDARD | ALFANAR CO | SAR | 2120000 | APPROVED |  |  | 2025-01-02 | 330000 |  | Kumar, Mr. Ranjan | -45211 | 448
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1598 | S/S NM PSS-A & PSS-B IN NEOM-Topographical Survey -PSSA & PSSB | APPROVED | No | 2023-10-15 | Abas, Mohammed Fekry | 2023-10-16 | 2023-10-17 |  |  |  | 17200 | 4678 | 0 | STANDARD | Surveying Experts for Trading Est.(S) | SAR | 17200 | APPROVED |  |  | 2023-10-26 | 0 | 9 | Babic, Marian | -45216 | 9
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1623 | S/S NM PSS-A & PSS-B IN NEOM-Mobily Relocation works at PSSB | APPROVED | No | 2023-10-24 | Abas, Mohammed Fekry | 2023-10-25 | 2023-10-25 |  |  |  | 67000 | 4701 | 0 | STANDARD | Etihad Etisalat Company | SAR | 66941.5 | APPROVED |  |  | 2023-11-07 | 58.5 | 13 | Babic, Marian | -45224 | 13
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1624 | S/S NM PSS-A & PSS-B IN NEOM-Generators for NEOM PSSA & PSSB | RETURNED | No | 2023-10-24 | Badhman, Saeed | 2024-03-13 | 2023-10-25 | 2024-03-13 |  | revise the budget to have it as an asset and resubmit the PR | 500000 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45224 | -45224
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1629 | S/S NM PSS-A & PSS-B IN NEOM-Surge Arresters-PSSB | APPROVED | No | 2023-10-25 | Abas, Mohammed Fekry | 2023-10-26 | 2023-10-26 |  |  |  | 48000 | 4687 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 44170.06 | APPROVED |  |  | 2023-11-05 | 3829.94 | 10 | Kumar, Mr. Ranjan | -45225 | 10
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1631 | S/S NM PSS-A & PSS-B IN NEOM-Surge Arresters-PSSA | APPROVED | No | 2023-10-25 | Abas, Mohammed Fekry | 2023-10-26 | 2023-10-26 |  |  |  | 108000 | 4686 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 93751.18 | APPROVED |  |  | 2023-11-05 | 14248.82 | 10 | Kumar, Mr. Ranjan | -45225 | 10
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1633 | S/S NM PSS-A & PSS-B IN NEOM-Capacitor Bank for PSSA | APPROVED | No | 2023-10-26 | Abas, Mohammed Fekry | 2023-10-31 | 2023-10-31 |  |  |  | 4763000 | 4692 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 4581300 | APPROVED |  |  | 2023-11-12 | 181700 | 12 | Kumar, Mr. Ranjan | -45230 | 12
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1634 | S/S NM PSS-A & PSS-B IN NEOM-Capacitor Bank for PSSB | APPROVED | No | 2023-10-26 | Abas, Mohammed Fekry | 2023-10-31 | 2023-10-31 |  |  |  | 2520000 | 4693 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 2520000 | APPROVED |  |  | 2023-11-12 | 0 | 12 | Kumar, Mr. Ranjan | -45230 | 12
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1635 | S/S NM PSS-A & PSS-B IN NEOM-Supervision of Installation Capacitor bank at PSSB | APPROVED | No | 2023-10-26 | Abas, Mohammed Fekry | 2023-10-31 | 2023-10-31 |  |  |  | 367500 | 4693 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 147500 | APPROVED |  |  | 2023-11-12 | 220000 | 12 | Kumar, Mr. Ranjan | -45230 | 12
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1636 | S/S NM PSS-A & PSS-B IN NEOM-Supervision of Installation, FAT,Training & Spares of Capacitor bank at PSSB | RETURNED | No | 2023-10-26 | Kumar, Mr. Ranjan | 2024-04-01 | 2023-10-31 | 2024-04-01 |  | Item description is not clear. | 400000 | 4692 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 292500 | APPROVED |  |  | 2023-11-12 | 107500 |  | Kumar, Mr. Ranjan | -45230 | 12
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1636 | S/S NM PSS-A & PSS-B IN NEOM-Supervision of Installation, FAT,Training & Spares of Capacitor bank at PSSB | RETURNED | No | 2023-10-26 | Kumar, Mr. Ranjan | 2024-04-01 | 2023-10-31 | 2024-04-01 |  | Item description is not clear. | 40800 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45230 | -45230
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1678 | S/S NM PSS-A & PSS-B IN NEOM-Site Office Mobilization | APPROVED | No | 2023-11-12 | Abas, Mohammed Fekry | 2023-11-12 | 2023-11-13 |  |  |  | 473500 | 4872 | 0 | STANDARD | ABDUL JABBAR AHMAD ALI SHARAHILI CONTRACTING EST. (AJASCO) | SAR | 473500 | APPROVED |  |  | 2024-01-15 | 0 | 63 | Kumar, Mr. Ranjan | -45243 | 63
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1679 | S/S NM PSS-A & PSS-B IN NEOM-Site Office Mobilization- PSSB | APPROVED | No | 2023-11-12 | Abas, Mohammed Fekry | 2023-11-12 | 2023-11-13 |  |  |  | 473500 | 4872 | 0 | STANDARD | ABDUL JABBAR AHMAD ALI SHARAHILI CONTRACTING EST. (AJASCO) | SAR | 473500 | APPROVED |  |  | 2024-01-15 | 0 | 63 | Kumar, Mr. Ranjan | -45243 | 63
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1824 | S/S NM PSS-A & PSS-B IN NEOM-Service Vehicle for PSSA & PSSB | RETURNED | No | 2023-11-27 | Kumar, Mr. Ranjan | 2024-03-25 | 2023-11-28 | 2024-03-25 |  | As confirmed by Facility over email No need for the PR, Vehicle is already procured | 300000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45258 | -45258
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1825 | S/S NM PSS-A & PSS-B IN NEOM-Service Vehicle for PSSB | RETURNED | No | 2023-11-27 | Kumar, Mr. Ranjan | 2024-03-25 | 2023-11-28 | 2024-03-25 |  | As confirmed by Facility over email No need for the PR, Vehicle is already procured | 300000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45258 | -45258
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1900 | S/S NM PSS-A & PSS-B IN NEOM-SST for PSSA | APPROVED | No | 2023-12-06 | Abas, Mohammed Fekry | 2023-12-11 | 2023-12-11 |  |  |  | 225000 | 4954 | 0 | STANDARD | ALFANAR CO | SAR | 225000 | APPROVED |  |  | 2024-01-21 | 0 | 41 | Babic, Marian | -45271 | 41
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1901 | S/S NM PSS-A & PSS-B IN NEOM-SST for PSSB | APPROVED | No | 2023-12-06 | Abas, Mohammed Fekry | 2023-12-11 | 2023-12-11 |  |  |  | 250000 | 4955 | 0 | STANDARD | ALFANAR CO | SAR | 250000 | APPROVED |  |  | 2024-01-30 | 0 | 50 | Babic, Marian | -45271 | 50
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1903 | S/S NM PSS-A & PSS-B IN NEOM-NGR for PSSB | RETURNED | No | 2023-12-06 | Kumar, Mr. Ranjan | 2024-04-28 | 2023-12-11 | 2024-04-28 |  | Project Suspended | 675000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45271 | -45271
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1991 | S/S NM PSS-A & PSS-B IN NEOM-GIS for PSSA | INCOMPLETE | No |  | Ahmed, Khaja Asrar | 2023-12-18 |  |  |  | Project Suspended | 23100000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1993 | S/S NM PSS-A & PSS-B IN NEOM-GIS for PSSA | APPROVED | No | 2023-12-18 | Abas, Mohammed Fekry | 2023-12-19 | 2023-12-19 |  |  |  | 25370400 | 4922 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 23100000 | APPROVED |  |  | 2024-01-01 | 2270400 | 13 | Kumar, Mr. Ranjan | -45279 | 13
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1994 | S/S NM PSS-A & PSS-B IN NEOM-GIS for PSSB | APPROVED | No | 2023-12-18 | Abas, Mohammed Fekry | 2023-12-19 | 2023-12-19 |  |  |  | 23640600 | 4923 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 21900000 | APPROVED |  |  | 2024-01-01 | 1740600 | 13 | Kumar, Mr. Ranjan | -45279 | 13
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1995 | S/S NM PSS-A & PSS-B IN NEOM-Power Transformer for PSSA | APPROVED | No | 2023-12-18 | Abas, Mohammed Fekry | 2023-12-19 | 2023-12-19 |  |  |  | 24335000.01 | 4921 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 24072500 | APPROVED |  |  | 2024-01-01 | 262500.02 | 13 | Kumar, Mr. Ranjan | -45279 | 13
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1996 | S/S NM PSS-A & PSS-B IN NEOM-Power Transformer for PSSB | APPROVED | No | 2023-12-18 | Abas, Mohammed Fekry | 2023-12-19 | 2023-12-19 |  |  |  | 15040000 | 4920 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 14515000 | APPROVED |  |  | 2024-01-01 | 525000 | 13 | Kumar, Mr. Ranjan | -45279 | 13
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1997 | S/S NM PSS-A & PSS-B IN NEOM-33kV Switch Gear for PSSA | RETURNED | No | 2023-12-18 | Kumar, Mr. Ranjan | 2025-03-03 | 2023-12-19 | 2025-03-03 | 2023-12-18 | Duplicate PR. PO already approved with another PR | 14400000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45279 | -45279
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 1998 | S/S NM PSS-A & PSS-B IN NEOM-33kV Switch Gear for PSSB | RETURNED | No | 2023-12-18 | Kumar, Mr. Ranjan | 2024-04-28 | 2023-12-19 | 2024-04-28 |  | Project Suspended | 9800000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45279 | -45279
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2001 | S/S NM PSS-A & PSS-B IN NEOM-PSSA - Protection, SAS & AMI | RETURNED | No | 2023-12-18 | Kumar, Mr. Ranjan | 2024-07-04 | 2023-12-19 | 2024-07-04 |  | Duplicate PR, Alreay PO created with PR 1584 | 10200000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45279 | -45279
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2002 | S/S NM PSS-A & PSS-B IN NEOM-PSSB - Protection, SAS & AMI | RETURNED | No | 2023-12-18 | Kumar, Mr. Ranjan | 2024-07-04 | 2023-12-19 | 2024-07-04 |  | Duplicate PR, Alreay PO created with PR 1584 | 7700000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45279 | -45279
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2005 | S/S NM PSS-A & PSS-B IN NEOM-PSSA - ENGINEERING & DESIGN | APPROVED | No | 2023-12-18 | Abas, Mohammed Fekry | 2023-12-19 | 2023-12-19 |  |  |  | 1000000 | 5597 | 0 | STANDARD | BAHRAWY Gulf CONSULTANCY GROUP | SAR | 600000 | APPROVED |  |  | 2024-06-02 | 400000 | 166 | Kumar, Mr. Ranjan | -45279 | 166
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2006 | S/S NM PSS-A & PSS-B IN NEOM-PSSB - ENGINEERING & DESIGN | APPROVED | No | 2023-12-18 | Abas, Mohammed Fekry | 2023-12-19 | 2023-12-19 |  |  |  | 1000000 | 5598 | 0 | STANDARD | BAHRAWY Gulf CONSULTANCY GROUP | SAR | 600000 | APPROVED |  |  | 2025-01-27 | 400000 | 405 | Kumar, Mr. Ranjan | -45279 | 405
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2034 | S/S NM PSS-A & PSS-B IN NEOM-Relocation of STC Utility Cables in PSSB | APPROVED | No | 2023-12-25 | Abas, Mohammed Fekry | 2023-12-25 | 2023-12-26 |  |  |  | 109684.5 | 4932 | 0 | STANDARD | Telecommunications Consultants India Ltd. | SAR | 95377.83 | APPROVED |  |  | 2024-02-06 | 14306.67 | 42 | Babic, Marian | -45286 | 42
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2057 | S/S NM PSS-A & PSS-B IN NEOM-Site Temp Office for PSSA | APPROVED | No | 2023-12-31 | Abas, Mohammed Fekry | 2024-01-02 | 2024-01-02 |  |  |  | 119323 | 4872 | 0 | STANDARD | ABDUL JABBAR AHMAD ALI SHARAHILI CONTRACTING EST. (AJASCO) | SAR | 119323 | APPROVED |  |  | 2024-01-15 | 0 | 13 | Kumar, Mr. Ranjan | -45293 | 13
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2058 | S/S NM PSS-A & PSS-B IN NEOM-Site Temp Offcie for PSSB | APPROVED | No | 2023-12-31 | Abas, Mohammed Fekry | 2024-01-02 | 2024-01-02 |  |  |  | 119323 | 4872 | 0 | STANDARD | ABDUL JABBAR AHMAD ALI SHARAHILI CONTRACTING EST. (AJASCO) | SAR | 119323 | APPROVED |  |  | 2024-01-15 | 0 | 13 | Kumar, Mr. Ranjan | -45293 | 13
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2064 | S/S NM PSS-A & PSS-B IN NEOM-Soil Investigation for PSSA | APPROVED | No | 2023-12-31 | Abas, Mohammed Fekry | 2024-01-02 | 2024-01-02 |  |  |  | 42330 | 5784 | 0 | STANDARD | International Agent Commercial Company(S) | SAR | 42330 | APPROVED |  |  | 2024-07-12 | 0 | 192 | Kumar, Mr. Ranjan | -45293 | 192
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2065 | S/S NM PSS-A & PSS-B IN NEOM-Topographic Survey for PSSA | RETURNED | No | 2023-12-31 | Kumar, Mr. Ranjan | 2024-04-28 | 2024-01-02 | 2024-04-28 |  | Duplicate PR, PO 4678 is already created | 8600 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45293 | -45293
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2066 | S/S NM PSS-A & PSS-B IN NEOM-Soil Investigation for PSSB | APPROVED | No | 2023-12-31 | Abas, Mohammed Fekry | 2024-01-02 | 2024-01-02 |  |  |  | 42330 | 5239 | 0 | STANDARD | International Agent Commercial Company(S) | SAR | 42330 | APPROVED |  |  | 2024-03-20 | 0 | 78 | Kumar, Mr. Ranjan | -45293 | 78
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2067 | S/S NM PSS-A & PSS-B IN NEOM-Topographic Survey for PSSB | RETURNED | No | 2023-12-31 | Kumar, Mr. Ranjan | 2024-04-28 | 2024-01-02 | 2024-04-28 |  | PO 4678 is already issued | 8600 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45293 | -45293
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2068 | S/S NM PSS-A & PSS-B IN NEOM-Cyber Security for PSSA | APPROVED | No | 2023-12-31 | Abas, Mohammed Fekry | 2024-01-02 | 2024-01-02 |  |  |  | 1425000 | 5571 | 0 | STANDARD | ALFANAR CO | SAR | 1425000 | APPROVED |  |  | 2024-06-02 | 0 | 152 | Kumar, Mr. Ranjan | -45293 | 152
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2069 | S/S NM PSS-A & PSS-B IN NEOM-Cyber Security for PSSB | RETURNED | No | 2023-12-31 | Kumar, Mr. Ranjan | 2024-04-28 | 2024-01-02 | 2024-04-28 |  | Duplicate PR, PO 4678 is already issued | 1425000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45293 | -45293
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2137 | S/S NM PSS-A & PSS-B IN NEOM-Security Services for PSSA | RETURNED | No | 2024-01-09 | Kumar, Mr. Ranjan | 2024-04-28 | 2024-01-11 | 2024-04-28 |  | Please confirm the requiremet from Quality & Safety department | 500000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45302 | -45302
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2138 | S/S NM PSS-A & PSS-B IN NEOM-Secuirty Services for PSSB | RETURNED | No | 2024-01-09 | Akhtar, Farhan | 2024-05-06 | 2024-01-11 | 2024-05-06 |  | Reassign Buyer | 500000 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45302 | -45302
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2140 | S/S NM PSS-A & PSS-B IN NEOM-Diesel for PSSB Site | APPROVED | No | 2024-01-09 | Abas, Mohammed Fekry | 2024-01-10 | 2024-01-11 |  |  |  | 266000 | 5033 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 266000 | APPROVED |  |  | 2024-02-19 | 0 | 39 | Akhtar, Farhan | -45302 | 39
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2151 | S/S NM PSS-A & PSS-B IN NEOM-MV Cables for PSSB | RETURNED | No | 2024-01-10 | Kumar, Mr. Ranjan | 2024-01-24 | 2024-01-11 | 2024-01-24 |  | PR item to be corrected from SIS to MV Cable | 4391170.46 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45302 | -45302
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2155 | S/S NM PSS-A & PSS-B IN NEOM-Safety Requirement for PSSB | REJECTED | No | 2024-01-11 | Issa, Amr Ali | 2024-05-26 | 2024-04-23 |  | 2024-05-26 |  | 115000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45405 | -45405
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2273 | S/S NM PSS-A & PSS-B IN NEOM-Earthing Grid Materials with Accessories for PSSB | RETURNED | No | 2024-01-24 | Badhman, Saeed | 2024-03-19 | 2024-01-29 | 2024-03-19 |  | Please isssue it on itimized basis | 700000 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45320 | -45320
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2291 | S/S NM PSS-A & PSS-B IN NEOM-Lighting for PSSB SS | RETURNED | No | 2024-01-25 | Kumar, Mr. Ranjan | 2024-05-20 | 2024-01-29 | 2024-05-20 |  | PSS B Project Suspended, As confirmed by PMT, this PR is returned. | 41000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45320 | -45320
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2585 | S/S NM PSS-A & PSS-B IN NEOM-Furniture for Temp Site Office PSSA | RETURNED | No | 2024-02-18 | Kumar, Mr. Ranjan | 2024-04-28 | 2024-02-19 | 2024-04-28 |  | Project Suspended | 50000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45341 | -45341
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2586 | S/S NM PSS-A & PSS-B IN NEOM-Furniture for Temp Site Office PSSB | RETURNED | No | 2024-02-18 | Kumar, Mr. Ranjan | 2024-04-28 | 2024-02-19 | 2024-04-28 |  | Project Suspended | 50000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45341 | -45341
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2831 | S/S NM PSS-A & PSS-B IN NEOM-Battery & Battery Charger | RETURNED | No | 2024-03-17 | Muhammad, Muhammad Atif | 2024-04-28 | 2024-03-19 | 2024-04-28 |  | Project Suspended. | 1268000 | [5 empty] | 0 |  |  |  |  | 0 |  | Muhammad, Muhammad Atif | -45370 | -45370
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2873 | S/S NM PSS-A & PSS-B IN NEOM-150 SQ.MM Stranded Annealed Soft Drawn Tinned Copper Conductor | RETURNED | No | 2024-03-21 | Badhman, Saeed | 2024-06-04 | 2024-03-31 | 2024-06-04 |  | Retrned since Project is suspended (Until further notice) | 124410 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45382 | -45382
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 2903 | S/S NM PSS-A & PSS-B IN NEOM-Outdoor lighting | RETURNED | No | 2024-03-26 | Kumar, Mr. Ranjan | 2024-05-20 | 2024-03-31 | 2024-05-20 |  | PSS B Project Suspended, As confirmed by PMT, this PR is returned. | 28600 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45382 | -45382
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 3089 | S/S NM PSS-A & PSS-B IN NEOM-Generators for Site Office Facility | RETURNED | No | 2024-04-21 | Akhtar, Farhan | 2024-08-28 | 2024-04-23 | 2024-08-28 |  | Please re issue the PR when the site location is finalalized. | 250000 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45405 | -45405
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 4120 | S/S NM PSS-A & PSS-B IN NEOM-Architectural Design Engineering for NM PSS-A SS | RETURNED | No | 2024-08-08 | Kumar, Mr. Ranjan | 2024-09-15 | 2024-08-13 | 2024-09-15 |  | Please issue the PR once requirement is firmed | 200000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45517 | -45517
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 4908 | S/S NM PSS-A & PSS-B IN NEOM-Soil Investigation for PSS-A SS | RETURNED | No | 2024-11-12 | Kumar, Mr. Ranjan | 2024-12-04 | 2024-11-13 | 2024-12-04 |  | PR value is less than PO value, PO issuanced manually, PMT is requested to submit new PR with value as per PO | 50000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45609 | -45609
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 5274 | S/S NM PSS-A & PSS-B IN NEOM-NGR for PSS-A | APPROVED | No | 2024-12-26 | Abas, Mohammed Fekry | 2025-01-01 | 2025-01-02 |  |  |  | 675000 | 6839 | 0 | STANDARD | METAL DEPLOYE RESISTOR | EUR | 322434 | APPROVED |  |  | 2025-02-25 | 352566 | 54 | Kumar, Mr. Ranjan | -45659 | 54
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 5442 | S/S NM PSS-A & PSS-B IN NEOM-Communication System for NM PSS-B SS | RETURNED | No | 2025-01-16 | Kumar, Mr. Ranjan | 2025-03-12 | 2025-01-23 | 2025-03-12 |  | Duplicate PR , PO 5782 is already approved for PSS B Telecom | 2120000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45680 | -45680
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 5684 | S/S NM PSS-A & PSS-B IN NEOM-PSS-A Complete Earth Works (Excavation, Cutting, Leveling, Backfilling) | APPROVED | No | 2025-01-27 | Abas, Mohammed Fekry | 2025-02-01 | 2025-02-02 |  |  |  | 7556970 | 7046 | 0 | STANDARD | Mashael Aseer Contracting Company. | SAR | 7556970 | APPROVED |  |  | 2025-04-16 | 0 | 73 | Tananeh, Khalid Jamal | -45690 | 73
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 7008 | S/S NM PSS-A & PSS-B IN NEOM-DGA for PSS-A SS(Along with Installation & Commissioning) | APPROVED | No | 2025-07-08 | Abas, Mohammed Fekry | 2025-07-10 | 2025-07-10 |  |  | Budget Line no 3.3 for PSS-A SS requesting for DGA | 795000 | 4921 | 1 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 795000 | APPROVED |  |  | 2025-12-14 | 0 | 157 | Kumar, Mr. Ranjan | -45848 | 157
105-107 | S/S NM PSS-A & PSS-B IN NEOM | 8490 | Supply of DGA for PT(PSS-B) | APPROVED | No | 2025-12-11 | Abas, Mohammed Fekry | 2025-12-14 | 2025-12-14 |  |  | DGA for Power Transformer | 0 | 4920 | 1 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 530000 | APPROVED |  |  | 2025-12-24 | -530000 | 10 | Mohammed, Faisal Ansari | -46005 | 10
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 1574 | OHTL 132kV PSSA & PSSB IN NEOM-Engineering & Design-OHTL | APPROVED | No | 2023-10-10 | Abas, Mohammed Fekry | 2023-10-11 | 2023-10-12 |  |  |  | 1050000 | 5285 | 0 | STANDARD | Bahrawy Consultancy Group B.C.G | SAR | 400000 | APPROVED |  |  | 2024-04-03 | 650000 | 174 | Babic, Marian | -45211 | 174
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 1574 | OHTL 132kV PSSA & PSSB IN NEOM-Engineering & Design-OHTL | APPROVED | No | 2023-10-10 | Abas, Mohammed Fekry | 2023-10-11 | 2023-10-12 |  |  |  | 1050000 | 5285 | 2 | STANDARD | Bahrawy Consultancy Group B.C.G | SAR | 400000 | APPROVED |  |  | 2024-11-14 | 650000 | 399 | Babic, Marian | -45211 | 399
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 1575 | OHTL 132kV PSSA & PSSB IN NEOM-OHTL - Supply of Towers - Lattice Towers | APPROVED | No | 2023-10-10 | Abas, Mohammed Fekry | 2023-10-11 | 2023-10-12 |  |  |  | 24692500 | 4668 | 0 | STANDARD | Hesham Helal Elsewedy & Partners for Construction Co., Ltd. | SAR | 24110500.39 | APPROVED |  |  | 2023-10-26 | 581999.61 | 14 | Babic, Marian | -45211 | 14
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 1626 | OHTL 132kV PSSA & PSSB IN NEOM-Generators for NEOM PSSA & PSSB OHTL | RETURNED | Yes | 2023-10-24 | Saeed, Mahmoud | 2024-03-17 | 2023-10-29 | 2024-03-13 |  | revise the budget to have it as an asset and resubmit the PR | 250000 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45228 | -45228
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 1632 | OHTL 132kV PSSA & PSSB IN NEOM-Surge Arresters-PSSA& B OHTL | APPROVED | No | 2023-10-25 | Abas, Mohammed Fekry | 2023-10-26 | 2023-10-26 |  |  |  | 80400 | 4688 | 1 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 27915.99 | APPROVED |  |  | 2024-07-03 | 52484.01 | 251 | Kumar, Mr. Ranjan | -45225 | 251
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 1632 | OHTL 132kV PSSA & PSSB IN NEOM-Surge Arresters-PSSA& B OHTL | APPROVED | No | 2023-10-25 | Abas, Mohammed Fekry | 2023-10-26 | 2023-10-26 |  |  |  | 120600 | 4688 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 120021.8 | APPROVED |  |  | 2023-11-06 | 578.2 | 11 | Kumar, Mr. Ranjan | -45225 | 11
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 1660 | OHTL 132kV PSSA & PSSB IN NEOM-DGPS & Total Stations for OHTL | APPROVED | No | 2023-11-05 | Abas, Mohammed Fekry | 2023-11-07 | 2023-11-09 |  |  |  | 140000 | 4748 | 0 | STANDARD | ZAN Modren Co. LTD | SAR | 135700 | APPROVED |  |  | 2023-12-06 | 4300 | 27 | Babic, Marian | -45239 | 27
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 1812 | OHTL 132kV PSSA & PSSB IN NEOM-Route Topographic Survey | APPROVED | No | 2023-11-23 | Abas, Mohammed Fekry | 2023-11-23 | 2023-11-26 |  |  |  | 325000 | 4769 | 0 | STANDARD | MARKS SURVEY OFFICE | SAR | 325000 | APPROVED |  |  | 2023-12-04 | 0 | 8 | Babic, Marian | -45256 | 8
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 1855 | OHTL 132kV PSSA & PSSB IN NEOM-Porcelain Long Rod Insulators - NEOM OHL | APPROVED | No | 2023-11-29 | Abas, Mohammed Fekry | 2023-11-30 | 2023-11-30 |  |  |  | 3857865 | 4782 | 0 | STANDARD | LAPP Insulators GmbH | EUR | 3857865 | APPROVED |  |  | 2023-12-11 | 0 | 11 | Babic, Marian | -45260 | 11
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 1856 | OHTL 132kV PSSA & PSSB IN NEOM-UGNMFOC - NEOM OHL | APPROVED | No | 2023-11-29 | Abas, Mohammed Fekry | 2023-11-30 | 2023-11-30 |  |  |  | 155221.64 | 4959 | 0 | STANDARD | MIDDLE EAST FIBER CABLE MANUFACTURING CO. | SAR | 132000 | APPROVED |  |  | 2024-01-25 | 23221.64 | 56 | Babic, Marian | -45260 | 56
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 1857 | OHTL 132kV PSSA & PSSB IN NEOM-Twin Spacer Dampers - NEOM OHL | APPROVED | No | 2023-11-29 | Abas, Mohammed Fekry | 2023-11-30 | 2023-11-30 |  |  |  | 1786940 | 4835 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 1672880 | APPROVED |  |  | 2023-12-27 | 114060 | 27 | Babic, Marian | -45260 | 27
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 1860 | OHTL 132kV PSSA & PSSB IN NEOM-OFMR & FSTP - NEOM OHTL | APPROVED | No | 2023-11-29 | Abas, Mohammed Fekry | 2023-11-30 | 2023-11-30 |  |  |  | 32500 | 4918 | 0 | STANDARD | AMWAJ TELECOMMUNICATION MFG. CO. | SAR | 23100 | APPROVED |  |  | 2023-12-31 | 9400 | 31 | Babic, Marian | -45260 | 31
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 1875 | OHTL 132kV PSSA & PSSB IN NEOM-OPGW & OPGW JOINT BOX - NEOM OHL | APPROVED | No | 2023-11-30 | Abas, Mohammed Fekry | 2023-12-04 | 2023-12-05 |  |  |  | 1441125 | 4787 | 0 | STANDARD | ZTT International Limited. | USD | 1441125 | APPROVED |  |  | 2023-12-11 | 0 | 6 | Babic, Marian | -45265 | 6
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 1879 | OHTL 132kV PSSA & PSSB IN NEOM-Power Cable Termination Kits - NEOM OHTL | APPROVED | No | 2023-12-03 | Abas, Mohammed Fekry | 2023-12-04 | 2023-12-05 |  |  |  | 497767.75 | 5258 | 0 | STANDARD | PFISTERER Switzerland AG | EUR | 247366.31 | APPROVED |  |  | 2024-07-15 | 250401.44 | 223 | Babic, Marian | -45265 | 223
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 1882 | OHTL 132kV PSSA & PSSB IN NEOM-Insulated Joints - NEOM OHTL | APPROVED | No | 2023-12-03 | Abas, Mohammed Fekry | 2023-12-06 | 2023-12-07 |  |  |  | 914590.56 | 5258 | 0 | STANDARD | PFISTERER Switzerland AG | EUR | 884950.18 | APPROVED |  |  | 2024-07-15 | 29640.38 | 221 | Babic, Marian | -45267 | 221
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 1899 | OHTL 132kV PSSA & PSSB IN NEOM-Hardware Fittings - NEOM OHTL | APPROVED | No | 2023-12-06 | Abas, Mohammed Fekry | 2023-12-11 | 2023-12-11 |  |  |  | 3874575 | 4834 | 0 | STANDARD | PFISTERER Switzerland AG | USD | 3525863.25 | APPROVED |  |  | 2024-01-21 | 348711.75 | 41 | Babic, Marian | -45271 | 41
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 1931 | OHTL 132kV PSSA & PSSB IN NEOM-Geo Physical & Geo technical Investigation | APPROVED | No | 2023-12-12 | Abas, Mohammed Fekry | 2023-12-12 | 2023-12-12 |  |  |  | 700000 | 5000 | 0 | STANDARD | International Agent Commercial Company(S) | SAR | 565310 | APPROVED |  |  | 2024-02-06 | 134690 | 56 | Babic, Marian | -45272 | 56
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 2019 | OHTL 132kV PSSA & PSSB IN NEOM-Link Box | APPROVED | No | 2023-12-20 | Abas, Mohammed Fekry | 2023-12-24 | 2023-12-25 |  |  |  | 275200 | 4958 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 270200 | APPROVED |  |  | 2024-01-25 | 5000 | 31 | Babic, Marian | -45285 | 31
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 2701 | OHTL 132kV PSSA & PSSB IN NEOM-Installation of Indoor & Outdoor Cable Terminations | APPROVED | No | 2024-02-27 | Abas, Mohammed Fekry | 2024-02-28 | 2024-02-28 |  |  |  | 288504 | 5258 | 0 | STANDARD | PFISTERER Switzerland AG | EUR | 114834.11 | APPROVED |  |  | 2024-07-15 | 173669.89 | 138 | Babic, Marian | -45350 | 138
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 2711 | OHTL 132kV PSSA & PSSB IN NEOM-Supply of SVL & SVL Connection | APPROVED | No | 2024-02-28 | Abas, Mohammed Fekry | 2024-02-28 | 2024-03-03 |  |  |  | 34248 | 5227 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 16700 | APPROVED |  |  | 2024-04-21 | 17548 | 49 | Babic, Marian | -45354 | 49
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 2711 | OHTL 132kV PSSA & PSSB IN NEOM-Supply of SVL & SVL Connection | APPROVED | No | 2024-02-28 | Abas, Mohammed Fekry | 2024-02-28 | 2024-03-03 |  |  |  | 34248 | 5227 | 1 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 8600 | APPROVED |  |  | 2024-07-29 | 25648 | 148 | Babic, Marian | -45354 | 148
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 2711 | OHTL 132kV PSSA & PSSB IN NEOM-Supply of SVL & SVL Connection | APPROVED | No | 2024-02-28 | Abas, Mohammed Fekry | 2024-02-28 | 2024-03-03 |  |  |  | 34248 | 5258 | 0 | STANDARD | PFISTERER Switzerland AG | EUR | 5357.88 | APPROVED |  |  | 2024-07-15 | 28890.12 | 134 | Babic, Marian | -45354 | 134
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 2962 | OHTL 132kV PSSA & PSSB IN NEOM-Access Road & Strcuture Pad#1 | RETURNED | Yes | 2024-04-01 | Saeed, Mahmoud | 2024-05-07 | 2024-04-04 | 2024-04-15 |  | due to change the cost. | 2370000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45386 | -45386
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 2964 | OHTL 132kV PSSA & PSSB IN NEOM-Access Road & Structure Pad#2 | RETURNED | Yes | 2024-04-01 | Saeed, Mahmoud | 2024-04-15 | 2024-04-04 | 2024-04-15 |  | due to change the cost. | 2370000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45386 | -45386
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 2965 | OHTL 132kV PSSA & PSSB IN NEOM-Access Road & Structure Pad#3 | RETURNED | Yes | 2024-04-01 | Saeed, Mahmoud | 2024-04-15 | 2024-04-04 | 2024-04-15 |  | due to change the cost. | 2520000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45386 | -45386
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 2966 | OHTL 132kV PSSA & PSSB IN NEOM-Access Road & Structure Pad in Hilly#1 | RETURNED | Yes | 2024-04-01 | Saeed, Mahmoud | 2024-05-07 | 2024-04-04 | 2024-04-15 |  | due to change the cost. | 1050000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45386 | -45386
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 2967 | OHTL 132kV PSSA & PSSB IN NEOM-Access Road & Structure Pad in Hilly#2 | RETURNED | Yes | 2024-04-01 | Saeed, Mahmoud | 2024-04-15 | 2024-04-04 | 2024-04-15 |  | due to change the cost. | 1050000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45386 | -45386
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 2968 | OHTL 132kV PSSA & PSSB IN NEOM-Access Road & Structure Pad in Hilly#3 | RETURNED | Yes | 2024-04-01 | Saeed, Mahmoud | 2024-04-15 | 2024-04-04 | 2024-04-15 |  | due to change the cost. | 1110000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45386 | -45386
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 3030 | OHTL 132kV PSSA & PSSB IN NEOM-Generators for Site Facility | APPROVED | No | 2024-04-15 | Abas, Mohammed Fekry | 2024-09-25 | 2024-09-26 |  |  |  | 270000 | 6308 | 0 | STANDARD | Mohammed A. AlFaddaghi & Partners | SAR | 262500 | APPROVED |  |  | 2024-10-16 | 7500 | 20 | Akhtar, Farhan | -45561 | 20
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 3076 | OHTL 132kV PSSA & PSSB IN NEOM-Surge Arrester for PSSA OHTL | REJECTED | No | 2024-04-21 | Saeed, Mahmoud | 2024-04-21 |  |  | 2024-04-21 |  | 86670 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 3330 | OHTL 132kV PSSA & PSSB IN NEOM-Construction of Access Road & Structure Pad#1 | REJECTED | Yes | 2024-05-07 | Saeed, Mahmoud | 2024-05-14 | 2024-05-13 | 2024-05-12 | 2024-05-13 | due to change the Qty | 144156240 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45425 | -45425
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 3333 | OHTL 132kV PSSA & PSSB IN NEOM-Construction of Access Road & Structure Pad#3 | APPROVED | No | 2024-05-07 | Abas, Mohammed Fekry | 2024-05-07 | 2024-05-12 |  |  |  | 308000 | 5532 | 0 | STANDARD | Mashael Aseer Contracting Company. | SAR | 308000 | APPROVED |  |  | 2024-08-01 | 0 | 81 | Abuhammad, Samir | -45424 | 81
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 3392 | OHTL 132kV PSSA & PSSB IN NEOM-Construction of Access Road & Structure Pad#1 | APPROVED | No | 2024-05-14 | Abas, Mohammed Fekry | 2024-05-14 | 2024-05-14 |  |  |  | 576240 | 5532 | 0 | STANDARD | Mashael Aseer Contracting Company. | SAR | 576240 | APPROVED |  |  | 2024-08-01 | 0 | 79 | Abuhammad, Samir | -45426 | 79
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 3471 | OHTL 132kV PSSA & PSSB IN NEOM-Construction of Access Road | REJECTED | Yes | 2025-05-07 | Ahmed, Khaja Asrar | 2025-05-07 |  |  | 2025-05-07 |  | 120000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4065 | OHTL 132kV PSSA & PSSB IN NEOM-Ready Mix Concrete for PSSA OHTL | APPROVED | No | 2024-07-31 | Abas, Mohammed Fekry | 2024-10-03 | 2024-10-04 | 2024-10-01 |  | as requested by phone from Project manager Khaja to modify budget as per PO approved value | 4065600 | 6310 | 0 | STANDARD | Establishment Mohamed Fayez Al-fayez for contracting | SAR | 4065600 | APPROVED |  |  | 2024-10-09 | 0 | 5 | Tananeh, Khalid Jamal | -45569 | 5
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4066 | OHTL 132kV PSSA & PSSB IN NEOM-Steel Rebars for PSSA OHTL | APPROVED | No | 2024-07-31 | Abas, Mohammed Fekry | 2024-08-01 | 2024-08-01 |  |  |  | 2000000 | 6300 | 0 | STANDARD | AL FAISAL STEEL PRODUCT CO. | SAR | 1347580 | APPROVED |  |  | 2024-10-08 | 652420 | 68 | Tananeh, Khalid Jamal | -45505 | 68
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4118 | OHTL 132kV PSSA & PSSB IN NEOM-RTV Coating for Insulator | REJECTED | No | 2024-08-07 | Yamama, Loai Mohamed | 2024-08-13 | 2024-08-08 |  | 2024-08-13 |  | 607750 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45512 | -45512
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4123 | OHTL 132kV PSSA & PSSB IN NEOM-Environmental Impact Study & Hydrological Study | APPROVED | No | 2024-08-08 | Abas, Mohammed Fekry | 2024-08-13 | 2024-08-13 |  |  |  | 300000 | 6159 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 115000 | APPROVED |  |  | 2024-09-24 | 185000 | 42 | Alhadi, Khalid | -45517 | 42
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4135 | OHTL 132kV PSSA & PSSB IN NEOM-Grounding Materials Lot#1 for PSSA & PSSB | APPROVED | No | 2024-08-11 | Abas, Mohammed Fekry | 2024-08-12 | 2024-08-13 |  |  |  | 141316 | 6195 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 134092.68 | APPROVED |  |  | 2024-09-26 | 7223.32 | 44 | Babic, Marian | -45517 | 44
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4260 | OHTL 132kV PSSA & PSSB IN NEOM-Site IT Facilities | APPROVED | No | 2024-08-25 | Abas, Mohammed Fekry | 2024-08-26 | 2024-08-27 |  |  |  | 11345 | 6146 | 0 | STANDARD | Mohammad Abdul Rahman Mohd Al Zahid Information Technology Co | SAR | 10050 | APPROVED |  |  | 2024-09-17 | 1295 | 21 | Abuhammad, Samir | -45531 | 21
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4276 | OHTL 132kV PSSA & PSSB IN NEOM-Partial Laydown Area Improvemnet in PSSB | APPROVED | No | 2024-08-26 | Abas, Mohammed Fekry | 2024-09-03 | 2024-09-04 |  |  |  | 300000 | 6171 | 0 | STANDARD | Sam OG Construction | SAR | 222552 | APPROVED |  |  | 2024-09-26 | 77448 | 22 | Kumar, Mr. Ranjan | -45539 | 22
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4296 | OHTL 132kV PSSA & PSSB IN NEOM-Access Road & Structure for Last 3.9km of PSSA#1 | APPROVED | No | 2024-08-28 | Abas, Mohammed Fekry | 2024-09-05 | 2024-09-05 |  |  |  | 406200 | 6161 | 0 | STANDARD | Sam OG Construction | SAR | 406200 | APPROVED |  |  | 2024-09-24 | 0 | 19 | Abuhammad, Samir | -45540 | 19
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4298 | OHTL 132kV PSSA & PSSB IN NEOM-Access Road & Structure Pad for the last 3.9km of PSSA#2 | RETURNED | Yes | 2024-08-28 | Ahmed, Khaja Asrar | 2025-05-07 | 2024-09-05 | 2024-12-02 |  | Verification the area. | 217400 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45540 | -45540
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4351 | OHTL 132kV PSSA & PSSB IN NEOM-Civil Works (Augering & Foundation) for PSSA OHTL | APPROVED | No | 2024-09-03 | Abas, Mohammed Fekry | 2024-09-05 | 2024-09-05 |  |  |  | 5000000 | 6312 | 0 | STANDARD | Sharifa Musleh Al-Rashidi Contracting Est | SAR | 1622000 | APPROVED |  |  | 2024-10-16 | 3378000 | 41 | Abuhammad, Samir | -45540 | 41
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4356 | OHTL 132kV PSSA & PSSB IN NEOM-Erection & Stringing Works for PSSA | APPROVED | No | 2024-09-03 | Abas, Mohammed Fekry | 2024-09-05 | 2024-09-05 |  |  |  | 2112800 | 6555 | 0 | STANDARD | Saudi Pakistani Advanced Construction Company | SAR | 1647400 | APPROVED |  |  | 2025-01-15 | 465400 | 132 | Babic, Marian | -45540 | 132
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4476 | OHTL 132kV PSSA & PSSB IN NEOM-Construction of Access Road & Structure Pad#1 for PSSB Normal Area | APPROVED | No | 2024-09-18 | Abas, Mohammed Fekry | 2024-09-18 | 2024-09-18 |  |  |  | 1182000 | 6252 | 0 | STANDARD | Ibrahim Hussein Ibrahim Sayyadi General Contracting Est. | SAR | 1182000 | APPROVED |  |  | 2024-10-08 | 0 | 20 | Abuhammad, Samir | -45553 | 20
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4477 | OHTL 132kV PSSA & PSSB IN NEOM-Construction of Access Road & Structure Pad#2 for PSSB Hillyl Area | APPROVED | No | 2024-09-18 | Abas, Mohammed Fekry | 2024-09-18 | 2024-09-18 |  |  |  | 652600 | 6252 | 0 | STANDARD | Ibrahim Hussein Ibrahim Sayyadi General Contracting Est. | SAR | 652600 | APPROVED |  |  | 2024-10-08 | 0 | 20 | Abuhammad, Samir | -45553 | 20
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4555 | OHTL 132kV PSSA & PSSB IN NEOM-Independant Testing Laboratory | REJECTED | No | 2024-09-30 | Yamama, Loai Mohamed | 2024-10-01 | 2024-09-30 |  | 2024-10-03 |  | 100000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45565 | -45565
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4558 | OHTL 132kV PSSA & PSSB IN NEOM-Security Guards | REJECTED | No | 2024-09-30 | Yamama, Loai Mohamed | 2024-10-01 | 2024-09-30 |  | 2024-10-03 |  | 208000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45565 | -45565
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4559 | OHTL 132kV PSSA & PSSB IN NEOM-Independant Testing Laboratory | REJECTED | No | 2024-09-30 | Yamama, Loai Mohamed | 2024-10-07 | 2024-09-30 |  | 2024-10-07 |  | 100000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45565 | -45565
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4610 | OHTL 132kV PSSA & PSSB IN NEOM-Independant Testing Laboratory for Concrete Testing | APPROVED | No | 2024-10-07 | Abas, Mohammed Fekry | 2024-10-08 | 2024-10-08 |  |  |  | 120000 | 6317 | 0 | STANDARD | RIYADH GEOTECHNIQUE&FOUNDATION | SAR | 120000 | APPROVED |  |  | 2024-10-14 | 0 | 6 | Babic, Marian | -45573 | 6
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4612 | OHTL 132kV PSSA & PSSB IN NEOM-Security Guards | APPROVED | No | 2024-10-07 | Abas, Mohammed Fekry | 2024-10-08 | 2024-10-08 |  |  |  | 208000 | 6316 | 0 | STANDARD | Rukn Al Kateibah Company for Security Guards. | SAR | 208000 | APPROVED |  |  | 2024-10-17 | 0 | 9 | Abuhammad, Samir | -45573 | 9
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4628 | OHTL 132kV PSSA & PSSB IN NEOM-Auguring | APPROVED | No | 2024-10-08 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-09 |  |  |  | 2606800 | 6324 | 0 | STANDARD | Jeddah foundation contracting Company | SAR | 2606800 | APPROVED |  |  | 2024-10-14 | 0 | 5 | Babic, Marian | -45574 | 5
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4628 | OHTL 132kV PSSA & PSSB IN NEOM-Auguring | APPROVED | No | 2024-10-08 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-09 |  |  |  | 2606800 | 6324 | 1 | STANDARD | Jeddah foundation contracting Company | SAR | 1380070 | APPROVED |  |  | 2025-09-22 | 1226730 | 348 | Babic, Marian | -45574 | 348
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4629 | OHTL 132kV PSSA & PSSB IN NEOM-Laydown Area Improvement | APPROVED | No | 2024-10-08 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-09 |  |  |  | 200100 | 6332 | 0 | STANDARD | Sam OG Construction | SAR | 200079 | APPROVED |  |  | 2024-10-29 | 21 | 20 | Kumar, Mr. Ranjan | -45574 | 20
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4631 | OHTL 132kV PSSA & PSSB IN NEOM-Steel Strucrure Lot#4 (Additional Cost to Accelerate FAT) | APPROVED | No | 2024-10-08 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-09 |  |  |  | 172500 | 4668 | 1 | STANDARD | Hesham Helal Elsewedy & Partners for Construction Co., Ltd. | SAR | 171334.5 | APPROVED |  |  | 2024-10-21 | 1165.5 | 12 | Babic, Marian | -45574 | 12
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4639 | OHTL 132kV PSSA & PSSB IN NEOM-Grounding Accessories | APPROVED | No | 2024-10-09 | Abas, Mohammed Fekry | 2024-10-21 | 2024-10-22 |  |  |  | 67035 | 6327 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 48516 | APPROVED |  |  | 2024-10-27 | 18519 | 5 | Babic, Marian | -45587 | 5
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4659 | OHTL 132kV PSSA & PSSB IN NEOM-Hydrological Study for PSSB | APPROVED | No | 2024-10-13 | Abas, Mohammed Fekry | 2024-10-13 | 2024-10-14 |  |  |  | 130000 | 6484 | 0 | STANDARD | Applus Arabia for Geotechnical And Environmental Works Co. Ltd | SAR | 70000 | APPROVED |  |  | 2024-11-20 | 60000 | 37 | Alhadi, Khalid | -45579 | 37
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4671 | OHTL 132kV PSSA & PSSB IN NEOM-Supply of Fuel (Diesel) to Project Site | APPROVED | No | 2024-10-14 | Abas, Mohammed Fekry | 2024-10-15 | 2024-10-15 |  |  |  | 282500 | 6361 | 0 | STANDARD | New Innovation Company LtD | SAR | 282500 | APPROVED |  |  | 2024-10-30 | 0 | 15 | Abuhammad, Samir | -45580 | 15
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4671 | OHTL 132kV PSSA & PSSB IN NEOM-Supply of Fuel (Diesel) to Project Site | APPROVED | No | 2024-10-14 | Abas, Mohammed Fekry | 2024-10-15 | 2024-10-15 |  |  |  | 282500 | 6361 | 1 | STANDARD | New Innovation Company LtD | SAR | 8251.26 | APPROVED |  |  | 2025-08-10 | 274248.74 | 299 | Abuhammad, Samir | -45580 | 299
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4672 | OHTL 132kV PSSA & PSSB IN NEOM-Relocation of Site Offices | APPROVED | No | 2024-10-14 | Abas, Mohammed Fekry | 2024-10-15 | 2024-10-15 |  |  |  | 387470 | 6347 | 0 | STANDARD | ABDUL JABBAR AHMAD ALI SHARAHILI CONTRACTING EST. (AJASCO) | SAR | 387470 | APPROVED |  |  | 2024-10-19 | 0 | 4 | Babic, Marian | -45580 | 4
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4745 | OHTL 132kV PSSA & PSSB IN NEOM-Auguring#2 | APPROVED | No | 2024-10-20 | Abas, Mohammed Fekry | 2024-11-27 | 2024-11-28 | 2024-11-26 |  | Due to change the rate. | 3991750 | 6407 | 0 | STANDARD | Anhar Alyhari Contracting Co | SAR | 2971600 | APPROVED |  |  | 2024-11-12 | 1020150 | -16 | Abuhammad, Samir | -45624 | -16
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4745 | OHTL 132kV PSSA & PSSB IN NEOM-Auguring#2 | APPROVED | No | 2024-10-20 | Abas, Mohammed Fekry | 2024-11-27 | 2024-11-28 | 2024-11-26 |  | Due to change the rate. | 3991750 | 6546 | 0 | STANDARD | Giant Foundation Contracting Co | SAR | 3991750 | APPROVED |  |  | 2024-12-15 | 0 | 17 | Abuhammad, Samir | -45624 | 17
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4749 | OHTL 132kV PSSA & PSSB IN NEOM-Constrcution of Access Road & Structure Pad (Normal Area) | APPROVED | No | 2024-10-20 | Abas, Mohammed Fekry | 2024-10-21 | 2024-10-21 |  |  |  | 1182000 | 6370 | 0 | STANDARD | Omran Al Modon Contracting Co | SAR | 1182000 | APPROVED |  |  | 2024-10-30 | 0 | 9 | Abuhammad, Samir | -45586 | 9
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4750 | OHTL 132kV PSSA & PSSB IN NEOM-Construction of Access Road & Structure Pad (Hilly Area) | APPROVED | No | 2024-10-20 | Abas, Mohammed Fekry | 2024-10-21 | 2024-10-21 |  |  |  | 652600 | 6370 | 0 | STANDARD | Omran Al Modon Contracting Co | SAR | 652600 | APPROVED |  |  | 2024-10-30 | 0 | 9 | Abuhammad, Samir | -45586 | 9
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4812 | OHTL 132kV PSSA & PSSB IN NEOM-Access Road & Structure Pad in Hilly Area | REJECTED | No | 2024-10-30 | Saeed, Mahmoud | 2024-11-03 | 2024-11-03 | 2024-11-03 | 2024-11-03 | resubmit with correct criteria. | 256022000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45599 | -45599
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4813 | OHTL 132kV PSSA & PSSB IN NEOM-Construction of Access Road & Structure Pad in Heavy Rock Area | APPROVED | No | 2024-10-30 | Abas, Mohammed Fekry | 2024-11-04 | 2024-11-05 | 2024-11-03 |  | resubmit with correct criteria. | 318000 | 6429 | 0 | STANDARD | Northern Al Manarat Contracting Est | SAR | 318000 | APPROVED |  |  | 2024-11-14 | 0 | 9 | Abuhammad, Samir | -45601 | 9
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4818 | OHTL 132kV PSSA & PSSB IN NEOM-Twin Spacer Damper | APPROVED | No | 2024-10-31 | Abas, Mohammed Fekry | 2024-11-03 | 2024-11-04 |  |  |  | 51920 | 4835 | 1 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 51920 | APPROVED |  |  | 2024-11-25 | 0 | 21 | Babic, Marian | -45600 | 21
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4823 | OHTL 132kV PSSA & PSSB IN NEOM-Uplift Test for Tower Foundations | RETURNED | No | 2024-11-03 | Babic, Marian | 2026-01-27 | 2024-11-05 | 2026-01-27 |  | new PR 8805 has been issued | 300000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45601 | -45601
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4829 | OHTL 132kV PSSA & PSSB IN NEOM-Access Road & Structure Pad in Hilly Area | APPROVED | No | 2024-11-03 | Abas, Mohammed Fekry | 2024-11-04 | 2024-11-05 |  |  |  | 118000 | 6429 | 0 | STANDARD | Northern Al Manarat Contracting Est | SAR | 118000 | APPROVED |  |  | 2024-11-14 | 0 | 9 | Abuhammad, Samir | -45601 | 9
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4831 | OHTL 132kV PSSA & PSSB IN NEOM-Site Office Furniiture | APPROVED | No | 2024-11-04 | Abas, Mohammed Fekry | 2024-11-06 | 2024-11-06 |  |  |  | 300000 | 6567 | 0 | STANDARD | Excellence Area Trading Est.(S) | SAR | 172581 | APPROVED |  |  | 2024-12-09 | 127419 | 33 | Babic, Marian | -45602 | 33
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4937 | OHTL 132kV PSSA & PSSB IN NEOM-Auguring#4 | APPROVED | No | 2024-11-13 | Abas, Mohammed Fekry | 2024-11-14 | 2024-11-14 |  |  |  | 5355500 | 6499 | 0 | STANDARD | RAMAT UNITEDINTERNATIONAL | SAR | 5209550 | APPROVED |  |  | 2024-11-21 | 145950 | 7 | Abuhammad, Samir | -45610 | 7
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4958 | OHTL 132kV PSSA & PSSB IN NEOM-Security Guards for Laydown Area | APPROVED | No | 2024-11-14 | Abas, Mohammed Fekry | 2024-11-17 | 2024-11-17 |  |  |  | 208000 | 6523 | 0 | STANDARD | Rukn Al Kateibah Company for Security Guards. | SAR | 208000 | APPROVED |  |  | 2024-11-27 | 0 | 10 | Abuhammad, Samir | -45613 | 10
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 4990 | OHTL 132kV PSSA & PSSB IN NEOM-Cutting & Backfilling | RETURNED | Yes | 2024-11-19 | Ahmed, Khaja Asrar | 2025-05-07 | 2024-11-24 | 2025-02-09 |  | CO Form rejected by PMO. | 3001845 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45620 | -45620
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5052 | OHTL 132kV PSSA & PSSB IN NEOM-Site Office IT facilities | APPROVED | No | 2024-11-26 | Abas, Mohammed Fekry | 2024-11-27 | 2024-11-28 |  |  |  | 50000 | 6569 | 0 | STANDARD | Mohmmed Abdulrahman AlZahid IT CO. | SAR | 44300 | APPROVED |  |  | 2024-12-05 | 5700 | 7 | Babic, Marian | -45624 | 7
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5107 | OHTL 132kV PSSA & PSSB IN NEOM-Auguring#5 | APPROVED | No | 2024-12-01 | Abas, Mohammed Fekry | 2024-12-02 | 2024-12-03 |  |  |  | 4040500 | 6584 | 0 | STANDARD | BRANCH OF SURJIN TECH CO., LTD. | SAR | 2020500 | APPROVED |  |  | 2025-01-05 | 2020000 | 33 | Abuhammad, Samir | -45629 | 33
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5158 | OHTL 132kV PSSA & PSSB IN NEOM-Relocation of Site Offices#2 | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-09 | 2024-12-10 |  |  |  | 159355 | 6596 | 0 | STANDARD | ABDUL JABBAR AHMAD ALI SHARAHILI CONTRACTING EST. (AJASCO) | SAR | 159355 | APPROVED |  |  | 2025-01-15 | 0 | 36 | Babic, Marian | -45636 | 36
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5159 | OHTL 132kV PSSA & PSSB IN NEOM-Steel Rebars | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-17 | 2024-12-18 | 2024-12-16 |  | to modify budget | 735000 | 6673 | 0 | STANDARD | AL FAISAL STEEL PRODUCT CO. | SAR | 724500 | APPROVED |  |  | 2025-01-05 | 10500 | 18 | Tananeh, Khalid Jamal | -45644 | 18
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5247 | OHTL 132kV PSSA & PSSB IN NEOM-Ambulance Service | RETURNED | Yes | 2024-12-19 | Saeed, Mahmoud | 2024-12-25 | 2024-12-25 | 2024-12-25 |  | PR value is less than PO value, Please submit updated PR urgentely | 80000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45651 | -45651
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5268 | OHTL 132kV PSSA & PSSB IN NEOM-Site Office Stationary & Pantry Items | APPROVED | No | 2024-12-24 | Abas, Mohammed Fekry | 2024-12-29 | 2024-12-30 |  |  |  | 65000 | 6722 | 0 | STANDARD | TALABAT AL MAKTAB CO.LTD | SAR | 31000 | APPROVED |  |  | 2025-01-13 | 34000 | 14 | Akhtar, Farhan | -45656 | 14
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5271 | OHTL 132kV PSSA & PSSB IN NEOM-Waste Collection and Disposal | RETURNED | No | 2024-12-25 | Akhtar, Farhan | 2025-02-13 | 2024-12-26 | 2025-02-13 |  | Please cancel this PR.New Pr has been issued PR#5820 | 12500 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45652 | -45652
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5328 | OHTL 132kV PSSA & PSSB IN NEOM-Security Guards for Patrolling | APPROVED | No | 2025-01-01 | Abas, Mohammed Fekry | 2025-01-06 | 2025-01-06 |  |  |  | 135000 | 6730 | 0 | STANDARD | Rukn Al Kateibah Company for Security Guards. | SAR | 135000 | APPROVED |  |  | 2025-01-14 | 0 | 8 | Abuhammad, Samir | -45663 | 8
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5438 | OHTL 132kV PSSA & PSSB IN NEOM-Cold Blasting | REJECTED | No | 2025-01-15 | Yamama, Loai Mohamed | 2025-02-03 | 2025-01-16 |  | 2025-02-03 |  | 600000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45673 | -45673
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5482 | OHTL 132kV PSSA & PSSB IN NEOM-AlAtawi Change Order#1 | APPROVED | No | 2025-01-20 | Abas, Mohammed Fekry | 2025-01-27 | 2025-01-30 |  |  |  | 78680.94 | 6847 | 1 | STANDARD | Mohammed R.Al Atawi Est, | SAR | 78680.94 | APPROVED |  |  | 2025-02-05 | 0 | 6 | Abuhammad, Samir | -45687 | 6
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5483 | OHTL 132kV PSSA & PSSB IN NEOM-AlAtawi Change Order#2 | APPROVED | No | 2025-01-20 | Abas, Mohammed Fekry | 2025-01-27 | 2025-01-30 |  |  |  | 433313.8 | 6847 | 1 | STANDARD | Mohammed R.Al Atawi Est, | SAR | 433313.8 | APPROVED |  |  | 2025-02-05 | 0 | 6 | Abuhammad, Samir | -45687 | 6
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5532 | OHTL 132kV PSSA & PSSB IN NEOM-ERECTION#1 | APPROVED | No | 2025-01-22 | Abas, Mohammed Fekry | 2025-02-20 | 2025-02-22 |  |  | Budget Line Item#3.2 | 2000000 | 6826 | 0 | STANDARD | Capital Works Limited Company | SAR | 2000000 | APPROVED |  |  | 2025-03-03 | 0 | 9 | Babic, Marian | -45710 | 9
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5532 | OHTL 132kV PSSA & PSSB IN NEOM-ERECTION#1 | APPROVED | No | 2025-01-22 | Abas, Mohammed Fekry | 2025-02-20 | 2025-02-22 |  |  | Budget Line Item#3.2 | 2000000 | 6826 | 1 | STANDARD | Capital Works Limited Company | SAR | 2000000 | IN PROCESS |  |  |  | 0 | 344 | Babic, Marian | -45710 | -45710
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5533 | OHTL 132kV PSSA & PSSB IN NEOM-Foundation Works#1 | APPROVED | No | 2025-01-22 | Abas, Mohammed Fekry | 2025-01-26 | 2025-01-27 |  |  |  | 2000000 | 6832 | 0 | STANDARD | Termez Al - Mataqdema ltd. | SAR | 1727400 | APPROVED |  |  | 2025-03-06 | 272600 | 38 | Abuhammad, Samir | -45684 | 38
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5534 | OHTL 132kV PSSA & PSSB IN NEOM-Foundation Works#2 | APPROVED | No | 2025-01-22 | Abas, Mohammed Fekry | 2025-01-26 | 2025-01-27 |  |  |  | 2000000 | 6831 | 0 | STANDARD | Base and Target Contracting company | SAR | 1932000 | APPROVED |  |  | 2025-02-05 | 68000 | 9 | Abuhammad, Samir | -45684 | 9
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5614 | OHTL 132kV PSSA & PSSB IN NEOM-Tower Erection#2 | APPROVED | No | 2025-01-26 | Abas, Mohammed Fekry | 2025-02-20 | 2025-02-22 |  |  | Budget Line Item#3.2 | 529650 | 6826 | 0 | STANDARD | Capital Works Limited Company | SAR | 78750 | APPROVED |  |  | 2025-03-03 | 450900 | 9 | Babic, Marian | -45710 | 9
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5614 | OHTL 132kV PSSA & PSSB IN NEOM-Tower Erection#2 | APPROVED | No | 2025-01-26 | Abas, Mohammed Fekry | 2025-02-20 | 2025-02-22 |  |  | Budget Line Item#3.2 | 529650 | 6826 | 1 | STANDARD | Capital Works Limited Company | SAR | 78750 | IN PROCESS |  |  |  | 450900 | 344 | Babic, Marian | -45710 | -45710
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5784 | OHTL 132kV PSSA & PSSB IN NEOM-Cold Blasting - AlSayyadi | APPROVED | No | 2025-02-04 | Abas, Mohammed Fekry | 2025-02-13 | 2025-02-13 |  |  |  | 288400 | 6904 | 0 | STANDARD | Ibrahim Hussein Ibrahim Sayyadi General Contracting Est. | SAR | 288400 | APPROVED |  |  | 2025-02-26 | 0 | 13 | Abuhammad, Samir | -45701 | 13
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5804 | OHTL 132kV PSSA & PSSB IN NEOM-Steel Rebars for PSSB | APPROVED | No | 2025-02-05 | Abas, Mohammed Fekry | 2025-02-12 | 2025-02-13 |  |  |  | 832000 | 6941 | 0 | STANDARD | AL FAISAL STEEL PRODUCT CO. | SAR | 772500 | APPROVED |  |  | 2025-03-13 | 59500 | 28 | Tananeh, Khalid Jamal | -45701 | 28
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5820 | OHTL 132kV PSSA & PSSB IN NEOM-Concrete Waste Disposal | APPROVED | No | 2025-02-09 | Abas, Mohammed Fekry | 2025-02-12 | 2025-02-13 |  |  |  | 150000 | 6992 | 0 | STANDARD | Khalid Al-Adham Mutaeb Al-Enazi & Co | SAR | 150000 | APPROVED |  |  | 2025-03-24 | 0 | 39 | Akhtar, Farhan | -45701 | 39
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5858 | OHTL 132kV PSSA & PSSB IN NEOM-Cold Blasting New PO | APPROVED | No | 2025-02-12 | Abas, Mohammed Fekry | 2025-02-18 | 2025-02-18 |  |  |  | 130000 | 6932 | 0 | STANDARD | Sam OG Construction | SAR | 130000 | APPROVED |  |  | 2025-02-27 | 0 | 9 | Abuhammad, Samir | -45706 | 9
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5919 | OHTL 132kV PSSA & PSSB IN NEOM-Mobile Toilets | RETURNED | No | 2025-02-17 | Akhtar, Farhan | 2025-02-26 | 2025-02-22 | 2025-02-26 |  | Pay by Petty Cash | 10200 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45710 | -45710
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5933 | OHTL 132kV PSSA & PSSB IN NEOM-RTV Coating (Manual PO - 8781) | APPROVED | No | 2025-02-17 | Abas, Mohammed Fekry | 2025-02-20 | 2025-02-22 |  |  | Budget Line Item#3.26 | 596700 | 6942 | 0 | STANDARD | Y.S.G Global Arabia Contracting Co. | SAR | 596700 | APPROVED |  |  | 2025-03-03 | 0 | 9 | Babic, Marian | -45710 | 9
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5934 | OHTL 132kV PSSA & PSSB IN NEOM-Garbage Box Removal | APPROVED | No | 2025-02-17 | Abas, Mohammed Fekry | 2025-02-20 | 2025-02-22 |  |  | Budget Line Item#3.16 | 15000 | 6992 | 0 | STANDARD | Khalid Al-Adham Mutaeb Al-Enazi & Co | SAR | 15000 | APPROVED |  |  | 2025-03-24 | 0 | 30 | Akhtar, Farhan | -45710 | 30
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 5971 | OHTL 132kV PSSA & PSSB IN NEOM-Outdoor Equipment Steel Support Structure | REJECTED | No | 2025-02-19 | Ghith, Saad Gamal | 2025-08-11 | 2025-08-02 |  | 2025-08-11 |  | 96000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45871 | -45871
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6020 | OHTL 132kV PSSA & PSSB IN NEOM-Earthing material | REJECTED | No | 2025-02-20 | Yamama, Loai Mohamed | 2025-09-01 | 2025-08-02 |  | 2025-09-01 |  | 166642.4 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45871 | -45871
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6027 | OHTL 132kV PSSA & PSSB IN NEOM-Concrete Waste Removal | APPROVED | No | 2025-02-24 | Abas, Mohammed Fekry | 2025-02-27 | 2025-02-27 |  |  | Budget Line Item#3.6 | 273000 | 6974 | 0 | STANDARD | Khalid Al-Adham Mutaeb Al-Enazi & Co | SAR | 267000 | APPROVED |  |  | 2025-05-15 | 6000 | 77 | Akhtar, Farhan | -45715 | 77
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6044 | OHTL 132kV PSSA & PSSB IN NEOM-Earthing Material for NEOM PROJECT | APPROVED | No | 2025-02-26 | Abas, Mohammed Fekry | 2025-03-03 | 2025-03-05 |  |  | Budget Line Item#2.32 | 73759.04 | 6327 | 1 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 73759.04 | APPROVED |  |  | 2025-03-17 | 0 | 12 | Babic, Marian | -45721 | 12
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6054 | OHTL 132kV PSSA & PSSB IN NEOM-Earthing Materials | APPROVED | No | 2025-02-25 | Abas, Mohammed Fekry | 2025-02-27 | 2025-02-27 |  |  | 2.31 and 2.32 | 166642.4 | 6195 | 1 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 165460.39 | APPROVED |  |  | 2025-03-06 | 1182.01 | 7 | Babic, Marian | -45715 | 7
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6061 | OHTL 132kV PSSA & PSSB IN NEOM-Outdoor Equipment Steel Support Structure | APPROVED | No | 2025-02-26 | Abas, Mohammed Fekry | 2025-03-03 | 2025-03-05 |  |  | 8.2 | 48000 | 7140 | 0 | STANDARD | Alnafie Metal Industries Company | SAR | 29800 | APPROVED |  |  | 2025-04-29 | 18200 | 55 | Babic, Marian | -45721 | 55
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6062 | OHTL 132kV PSSA & PSSB IN NEOM-Sewage Water Removal | APPROVED | No | 2025-02-26 | Abas, Mohammed Fekry | 2025-03-03 | 2025-03-05 |  |  | 3.16 | 15000 | 6992 | 0 | STANDARD | Khalid Al-Adham Mutaeb Al-Enazi & Co | SAR | 14600 | APPROVED |  |  | 2025-03-24 | 400 | 19 | Akhtar, Farhan | -45721 | 19
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6115 | OHTL 132kV PSSA & PSSB IN NEOM-Concrete for PSSB | RETURNED | No | 2025-03-05 | Abuhammad, Samir | 2025-04-10 | 2025-03-13 | 2025-04-10 |  | Manual PO | 6000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45729 | -45729
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6173 | OHTL 132kV PSSA & PSSB IN NEOM-Walkie Talkie | APPROVED | No | 2025-03-12 | Abas, Mohammed Fekry | 2025-03-13 | 2025-03-17 |  |  | 3.13 | 6000 | 7204 | 0 | STANDARD | Versatile Advanced Limited Company. | SAR | 5925 | APPROVED |  |  | 2025-05-05 | 75 | 49 | Akhtar, Farhan | -45733 | 49
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6281 | OHTL 132kV PSSA & PSSB IN NEOM-Testing & Commissioning | APPROVED | No | 2025-03-26 | Abas, Mohammed Fekry | 2025-03-28 | 2025-04-01 |  |  | Budget Line Item 3.7 | 600000 | 7185 | 0 | STANDARD | Ahmed Naif Mohammed Aldawish | SAR | 278200 | APPROVED |  |  | 2025-04-24 | 321800 | 23 | Babic, Marian | -45748 | 23
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6302 | OHTL 132kV PSSA & PSSB IN NEOM-Clamps & Connectors | APPROVED | No | 2025-04-07 | Abas, Mohammed Fekry | 2025-04-10 | 2025-04-10 |  |  | 2.16 | 30312 | 7137 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 30300 | APPROVED |  |  | 2025-04-29 | 12 | 19 | Babic, Marian | -45757 | 19
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6302 | OHTL 132kV PSSA & PSSB IN NEOM-Clamps & Connectors | APPROVED | No | 2025-04-07 | Abas, Mohammed Fekry | 2025-04-10 | 2025-04-10 |  |  | 2.16 | 30312 | 7859 | 0 | STANDARD | ENERGY POWER SERVICE TRADING EST. | SAR | 16449.84 | APPROVED |  |  | 2025-11-24 | 13862.16 | 228 | Babic, Marian | -45757 | 228
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6303 | OHTL 132kV PSSA & PSSB IN NEOM-Backfill required to hydrology impacted towers as per design | APPROVED | No | 2025-04-07 | Abas, Mohammed Fekry | 2025-04-14 | 2025-04-15 |  |  | 3.6 | 98000 | 7294 | 0 | STANDARD | Mashael Aseer Contracting Company. | SAR | 2156000 | APPROVED |  |  | 2025-11-10 | -2058000 | 209 | Babic, Marian | -45762 | 209
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6332 | OHTL 132kV PSSA & PSSB IN NEOM-Ambulance Service (Manual PO alraedy Issued) | APPROVED | No | 2025-04-14 | Abas, Mohammed Fekry | 2025-04-17 | 2025-04-21 |  |  | 3.11 | 123000 | 6688 | 0 | STANDARD | CAPITAL AMBULANCE FOR MEDICAL SERVICES | SAR | 123000 | APPROVED |  |  | 2025-05-08 | 0 | 17 | Kumar, Mr. Ranjan | -45768 | 17
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6419 | OHTL 132kV PSSA & PSSB IN NEOM-Supply of Concrete Barriers | APPROVED | No | 2025-04-22 | Abas, Mohammed Fekry | 2025-04-24 | 2025-04-24 |  |  | 3.13 | 12000 | 7159 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 12000 | APPROVED |  |  | 2025-04-29 | 0 | 5 | Babic, Marian | -45771 | 5
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6420 | OHTL 132kV PSSA & PSSB IN NEOM-Cold Balsting | APPROVED | No | 2025-04-22 | Abas, Mohammed Fekry | 2025-04-24 | 2025-04-24 |  |  | 3.4 | 390000 | 7197 | 0 | STANDARD | Sam OG Construction | SAR | 300000 | APPROVED |  |  | 2025-04-29 | 90000 | 5 | Abuhammad, Samir | -45771 | 5
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6438 | OHTL 132kV PSSA & PSSB IN NEOM-Tower Segregation for PSS-A and PSS-B | APPROVED | No | 2025-04-23 | Abas, Mohammed Fekry | 2025-04-24 | 2025-04-24 |  |  | 3.2 | 156000 | 7212 | 0 | STANDARD | Al Aziziah for General Contracting Company | SAR | 156000 | APPROVED |  |  | 2025-05-18 | 0 | 24 | Babic, Marian | -45771 | 24
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6488 | OHTL 132kV PSSA & PSSB IN NEOM-Workimg at Heigh Drill | APPROVED | No | 2025-05-01 | Abas, Mohammed Fekry | 2025-05-06 | 2025-05-06 |  |  | 3.25 | 7000 | 7242 | 0 | STANDARD | Versatile Advanced Limited Company. | SAR | 7000 | APPROVED |  |  | 2025-05-12 | 0 | 6 | Akhtar, Farhan | -45783 | 6
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6492 | OHTL 132kV PSSA & PSSB IN NEOM-Security Guards | REJECTED | No | 2025-05-01 | Ahmed, Khaja Asrar | 2025-05-11 | 2025-05-06 | 2025-05-07 | 2025-05-11 | Due to change the Qty to 3 | 156000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45783 | -45783
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6528 | OHTL 132kV PSSA & PSSB IN NEOM-Backfilling#1 | REJECTED | No | 2025-05-06 | Yamama, Loai Mohamed | 2025-08-11 | 2025-05-11 |  | 2025-08-11 |  | 297000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45788 | -45788
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6529 | OHTL 132kV PSSA & PSSB IN NEOM-Backfilling#2 | REJECTED | No | 2025-05-06 | Yamama, Loai Mohamed | 2025-08-11 | 2025-05-11 |  | 2025-08-11 |  | 310500 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45788 | -45788
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6584 | OHTL 132kV PSSA & PSSB IN NEOM-Security Guards | APPROVED | No | 2025-05-11 | Abas, Mohammed Fekry | 2025-05-13 | 2025-05-14 |  |  | 3.8 | 78000 | 7230 | 0 | STANDARD | Rukn Al Kateibah Company for Security Guards. | SAR | 78000 | APPROVED |  |  | 2025-05-18 | 0 | 4 | Abuhammad, Samir | -45791 | 4
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6634 | OHTL 132kV PSSA & PSSB IN NEOM-Portable Toilet | APPROVED | No | 2025-05-18 | Abas, Mohammed Fekry | 2025-05-19 | 2025-05-20 |  |  | 3.16 | 18500 | 7329 | 0 | STANDARD | Versatile Advanced Limited Company. | SAR | 12600 | APPROVED |  |  | 2025-05-28 | 5900 | 8 | Akhtar, Farhan | -45797 | 8
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6636 | OHTL 132kV PSSA & PSSB IN NEOM-Stringing Additional Crew and Machine | INCOMPLETE | No |  | Ahmed, Khaja Asrar | 2025-05-18 |  |  |  | 3.16 | 200000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | 0 | 0
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6637 | OHTL 132kV PSSA & PSSB IN NEOM-Stringing additional team with equipments and tools | RETURNED | No | 2025-05-18 | Babic, Marian | 2026-01-12 | 2025-05-20 | 2026-01-12 |  | PPO 7737 was issued manually due to over budget. Please update the PR | 200000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45797 | -45797
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6696 | OHTL 132kV PSSA & PSSB IN NEOM-rental scafollding | APPROVED | No | 2025-05-25 | Abas, Mohammed Fekry | 2025-05-26 | 2025-05-26 |  |  | 3.13 | 22882.13 | 7286 | 0 | STANDARD | Safe and Support Co | SAR | 29395 | APPROVED |  |  | 2025-06-22 | -6512.87 | 27 | Abuhammad, Samir | -45803 | 27
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6696 | OHTL 132kV PSSA & PSSB IN NEOM-rental scafollding | APPROVED | No | 2025-05-25 | Abas, Mohammed Fekry | 2025-05-26 | 2025-05-26 |  |  | 3.13 | 22882.13 | 7286 | 3 | STANDARD | Safe and Support Co | SAR | 29395 | REQUIRES REAPPROVAL |  |  |  | -6512.87 | 251 | Abuhammad, Samir | -45803 | -45803
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6699 | OHTL 132kV PSSA & PSSB IN NEOM-rental scfollding | APPROVED | No | 2025-05-25 | Abas, Mohammed Fekry | 2025-06-01 | 2025-06-02 |  |  | 3.13 | 6512.87 | 7286 | 0 | STANDARD | Safe and Support Co | SAR | 29395 | APPROVED |  |  | 2025-06-22 | -22882.13 | 20 | Abuhammad, Samir | -45810 | 20
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6699 | OHTL 132kV PSSA & PSSB IN NEOM-rental scfollding | APPROVED | No | 2025-05-25 | Abas, Mohammed Fekry | 2025-06-01 | 2025-06-02 |  |  | 3.13 | 6512.87 | 7286 | 3 | STANDARD | Safe and Support Co | SAR | 29395 | REQUIRES REAPPROVAL |  |  |  | -22882.13 | 244 | Abuhammad, Samir | -45810 | -45810
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6777 | OHTL 132kV PSSA & PSSB IN NEOM-Diesel as per updated PO | REJECTED | No | 2025-06-12 | Yamama, Loai Mohamed | 2025-06-23 | 2025-06-15 |  | 2025-06-23 |  | 274248.73 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45823 | -45823
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6801 | OHTL 132kV PSSA & PSSB IN NEOM-Stationary for PSSAB site | REJECTED | No | 2025-06-15 | Yamama, Loai Mohamed | 2025-06-19 | 2025-06-17 |  | 2025-06-19 |  | 83411 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45825 | -45825
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6835 | OHTL 132kV PSSA & PSSB IN NEOM-Testing & Commissioning | RETURNED | No | 2025-06-19 | Babic, Marian | 2025-12-04 | 2025-06-25 | 2025-12-04 |  | the amount is less than the agreed value with Alfanar | 321800 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45833 | -45833
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6847 | OHTL 132kV PSSA & PSSB IN NEOM-Stationary for Site office | REJECTED | No | 2025-06-23 | Ahmed, Khaja Asrar | 2025-06-23 |  |  | 2025-06-23 |  | 90000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | 0 | 0
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6848 | OHTL 132kV PSSA & PSSB IN NEOM-Stationary for site office | APPROVED | No | 2025-06-22 | Abas, Mohammed Fekry | 2025-06-23 | 2025-06-25 |  |  | 3.12 | 90000 | 7426 | 0 | STANDARD | TALABAT AL MAKTAB CO.LTD | SAR | 83411 | APPROVED |  |  | 2025-08-20 | 6589 | 56 | Akhtar, Farhan | -45833 | 56
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 6984 | OHTL 132kV PSSA & PSSB IN NEOM-3rd party training | APPROVED | No | 2025-07-06 | Abas, Mohammed Fekry | 2025-07-20 | 2025-07-20 | 2025-07-10 |  | revise the amount | 6000 | 7537 | 0 | STANDARD | Versatile Advanced Limited Company. | SAR | 4600 | APPROVED |  |  | 2025-08-03 | 1400 | 14 | Akhtar, Farhan | -45858 | 14
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 7009 | OHTL 132kV PSSA & PSSB IN NEOM-PR for diesel remaining qty | REJECTED | No | 2025-07-08 | Yamama, Loai Mohamed | 2025-07-10 | 2025-07-08 |  | 2025-07-10 |  | 274248.73 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45846 | -45846
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 7076 | OHTL 132kV PSSA & PSSB IN NEOM-Diesel remaining qty with updated price | APPROVED | No | 2025-07-13 | Abas, Mohammed Fekry | 2025-07-20 | 2025-07-20 |  |  | 3.13 | 274248.73 | 6361 | 1 | STANDARD | New Innovation Company LtD | SAR | 274248.73 | APPROVED |  |  | 2025-08-10 | 0 | 21 | Abuhammad, Samir | -45858 | 21
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 7205 | OHTL 132kV PSSA & PSSB IN NEOM-slope stability | APPROVED | No | 2025-07-31 | Abas, Mohammed Fekry | 2025-08-05 | 2025-08-06 |  |  | 2.2 | 59000 | 7489 | 0 | STANDARD | Saden Specialized Company for Geological Consulting | SAR | 59000 | APPROVED |  |  | 2025-08-31 | 0 | 25 | Babic, Marian | -45875 | 25
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 7206 | OHTL 132kV PSSA & PSSB IN NEOM-chain fence link | APPROVED | No | 2025-07-31 | Abas, Mohammed Fekry | 2025-08-05 | 2025-08-06 |  |  | 3.6 | 75210 | 7541 | 0 | STANDARD | Sam OG Construction | SAR | 75210 | APPROVED |  |  | 2025-08-31 | 0 | 25 | Babic, Marian | -45875 | 25
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 7316 | OHTL 132kV PSSA & PSSB IN NEOM-Scafollding Extension request for 2 more months | APPROVED | No | 2025-08-07 | Abas, Mohammed Fekry | 2025-08-10 | 2025-08-10 |  |  | 3.13 | 18995 | 7286 | 1 | STANDARD | Safe and Support Co | SAR | 18995 | APPROVED |  |  | 2025-08-20 | 0 | 10 | Abuhammad, Samir | -45879 | 10
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 7316 | OHTL 132kV PSSA & PSSB IN NEOM-Scafollding Extension request for 2 more months | APPROVED | No | 2025-08-07 | Abas, Mohammed Fekry | 2025-08-10 | 2025-08-10 |  |  | 3.13 | 18995 | 7286 | 3 | STANDARD | Safe and Support Co | SAR | 18995 | REQUIRES REAPPROVAL |  |  |  | 0 | 175 | Abuhammad, Samir | -45879 | -45879
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 7356 | OHTL 132kV PSSA & PSSB IN NEOM-security guard for 3 month with patrolling | APPROVED | No | 2025-08-13 | Abas, Mohammed Fekry | 2025-08-17 | 2025-08-18 |  |  | 3.8 | 78000 | 7626 | 0 | STANDARD | Rukn Al Kateibah Company for Security Guards. | SAR | 78000 | APPROVED |  |  | 2025-08-25 | 0 | 7 | Abuhammad, Samir | -45887 | 7
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 7393 | Auguring Additional machines pan est PO no 7512 | APPROVED | No | 2025-08-19 | Abas, Mohammed Fekry | 2025-09-04 | 2025-09-04 | 2025-09-02 |  | we cannot modify qty and unit price | 0 | 7512 | 0 | STANDARD | Umoum Alsharq Alraida | SAR | 2079700 | APPROVED |  |  | 2025-10-09 | -2079700 | 35 | Babic, Marian | -45904 | 35
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 7591 | excess fill and cut | RETURNED | No | 2025-08-31 | Abuhammad, Samir | 2025-09-07 | 2025-09-04 |  |  | 3.4 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45904 | -45904
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 7593 | Stone Pitching /RIP RAP | RETURNED | No | 2025-08-31 | Abuhammad, Samir | 2025-09-07 | 2025-09-04 | 2025-09-07 | 2025-09-01 | It will considered as Frame agreement , future can raise the PR as per actual Qty and SO.. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45904 | -45904
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 7596 | RFG sconcrete feild testing | APPROVED | No | 2025-08-31 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-04 |  |  | 3.25 | 0 | 6317 | 1 | STANDARD | RIYADH GEOTECHNIQUE&FOUNDATION | SAR | 160000 | APPROVED |  |  | 2025-11-02 | -160000 | 59 | Babic, Marian | -45904 | 59
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 7644 | Name/Danger Plates and tower grating platform | REJECTED | No | 2025-09-04 | Yamama, Loai Mohamed | 2025-09-04 | 2025-09-04 |  | 2025-09-04 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45904 | -45904
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 7647 | grounding mateiral for transition area gantry | RETURNED | No | 2025-09-09 | Hegazy, Ayman | 2025-11-16 | 2025-09-12 | 2025-11-16 |  | POCR NOT READY | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -45912 | -45912
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 7649 | ALFAYEZ CONCRETE REMAING AMOUNT | APPROVED | No | 2025-09-04 | Abas, Mohammed Fekry | 2025-11-27 | 2025-11-29 | 2025-10-20 | 2025-11-11 | return as per request the email from Anas dated Mon 10/20/2025 at 11:38 AM | 0 | 6310 | 1 | STANDARD | Establishment Mohamed Fayez Al-fayez for contracting | SAR | 4699350 | APPROVED |  |  | 2025-12-07 | -4699350 | 8 | Tananeh, Khalid Jamal | -45990 | 8
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 7806 | 6252 change order for cutting and backfilling AND access road ,st pad and bench cutting | APPROVED | No | 2025-09-21 | Abas, Mohammed Fekry | 2025-09-22 | 2025-09-23 |  |  | 3.4 | 5278110 | 6252 | 1 | STANDARD | Ibrahim Hussein Ibrahim Sayyadi General Contracting Est. | SAR | 5278110 | APPROVED |  |  | 2025-10-07 | 0 | 14 | Abuhammad, Samir | -45923 | 14
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 7811 | PO 5000 INAT Change order | APPROVED | No | 2025-09-22 | Abas, Mohammed Fekry | 2025-11-09 | 2025-11-09 |  |  | 2.2 | 57075 | 5000 | 1 | STANDARD | International Agent Commercial Company(S) | SAR | 57075 | APPROVED |  |  | 2025-11-18 | 0 | 9 | Babic, Marian | -45970 | 9
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 7814 | JFC -JEDDAH FOUNDATION NEW PO 1439 | APPROVED | No | 2025-09-24 | Abas, Mohammed Fekry | 2025-10-02 | 2025-10-03 |  |  | 3.6 | 892160 | 7486 | 0 | STANDARD | Jeddah foundation contracting Company | SAR | 892160 | APPROVED |  |  | 2025-10-08 | 0 | 5 | Babic, Marian | -45933 | 5
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 7876 | 2 additional security guard | RETURNED | No | 2025-10-01 | Abuhammad, Samir | 2025-10-27 | 2025-10-13 | 2025-10-27 |  | to change the vendor. | 37500 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45943 | -45943
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 7931 | SAM OG PR | REJECTED | No | 2025-10-08 | Yamama, Loai Mohamed | 2025-10-09 | 2025-10-09 |  | 2025-10-13 |  | 876782701749.27 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45939 | -45939
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 7933 | SAM OG cut and Fill PR | APPROVED | No | 2025-10-08 | Abas, Mohammed Fekry | 2025-10-19 | 2025-10-19 | 2025-10-19 |  | for modification | 5379017.49 | 6161 | 2 | STANDARD | Sam OG Construction | SAR | 4999017.49 | APPROVED |  |  | 2025-11-27 | 380000 | 39 | Abuhammad, Samir | -45949 | 39
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8081 | Surjin tech PR | APPROVED | No | 2025-10-28 | Abas, Mohammed Fekry | 2025-10-29 | 2025-10-30 |  |  | 3.6 | 663000 | 6584 | 1 | STANDARD | BRANCH OF SURJIN TECH CO., LTD. | SAR | 663000 | APPROVED |  |  | 2025-11-10 | 0 | 11 | Abuhammad, Samir | -45960 | 11
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8096 | Tower Idenetification and name plates | APPROVED | No | 2025-10-29 | Abas, Mohammed Fekry | 2025-12-04 | 2025-12-04 |  | 2025-11-04 | 2.4 | 0 | 7994 | 0 | STANDARD | REMOZ ARABIAN TRADING EST. | SAR | 76606.81 | APPROVED |  |  | 2025-12-15 | -76606.81 | 11 | Babic, Marian | -45995 | 11
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8097 | Tower Gratings | APPROVED | No | 2025-10-30 | Abas, Mohammed Fekry | 2025-12-04 | 2025-12-05 |  | 2025-11-04 | 2.4 | 0 | 8000 | 0 | STANDARD | Hesham Helal Elsewedy & Partners for Construction Co., Ltd. | SAR | 58500 | APPROVED |  |  | 2025-12-31 | -58500 | 26 | Babic, Marian | -45996 | 26
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8135 | JAWAD ALMODON ERECTION PO 6827 | APPROVED | No | 2025-11-05 | Abas, Mohammed Fekry | 2025-11-20 | 2025-11-23 |  |  | 3.2 tower erection | 0 | 6827 | 0 | STANDARD | Jawad Al Modan for contracting | SAR | 2000000 | APPROVED |  |  | 2025-12-01 | -2000000 | 8 | Babic, Marian | -45984 | 8
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8135 | JAWAD ALMODON ERECTION PO 6827 | APPROVED | No | 2025-11-05 | Abas, Mohammed Fekry | 2025-11-20 | 2025-11-23 |  |  | 3.2 tower erection | 0 | 6827 | 1 | STANDARD | Jawad Al Modan for contracting | SAR | 1083809.52 | APPROVED |  |  | 2025-12-08 | -1083809.52 | 15 | Babic, Marian | -45984 | 15
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8140 | Scafollding Rental | APPROVED | No | 2025-11-05 | Abas, Mohammed Fekry | 2025-11-06 | 2025-11-09 |  |  | 3.13 | 0 | 7286 | 2 | STANDARD | Safe and Support Co | SAR | 28492.5 | APPROVED |  |  | 2025-11-12 | -28492.5 | 3 | Abuhammad, Samir | -45970 | 3
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8140 | Scafollding Rental | APPROVED | No | 2025-11-05 | Abas, Mohammed Fekry | 2025-11-06 | 2025-11-09 |  |  | 3.13 | 0 | 7286 | 3 | STANDARD | Safe and Support Co | SAR | 28492.5 | REQUIRES REAPPROVAL |  |  |  | -28492.5 | 84 | Abuhammad, Samir | -45970 | -45970
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8372 | Modificaion of Access road on last 3 km | APPROVED | No | 2025-11-26 | Abas, Mohammed Fekry | 2025-12-03 | 2025-12-03 |  |  | 3.4 | 0 | 7894 | 0 | STANDARD | Mashael Aseer Contracting Company. | SAR | 246000 | APPROVED |  |  | 2025-12-24 | -246000 | 21 | Abuhammad, Samir | -45994 | 21
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8394 | Additional cost for Hilly towers -CWC PO 6826 amendment- | APPROVED | No | 2025-11-30 | Abas, Mohammed Fekry | 2025-12-14 | 2025-12-14 |  |  | 3.2 tower erection | 0 | 6826 | 1 | STANDARD | Capital Works Limited Company | SAR | 1269076.04 | IN PROCESS |  |  |  | -1269076.04 | 49 | Babic, Marian | -46005 | -46005
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8394 | Additional cost for Hilly towers -CWC PO 6826 amendment- | APPROVED | No | 2025-11-30 | Abas, Mohammed Fekry | 2025-12-14 | 2025-12-14 |  |  | 3.2 tower erection | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46005 | -46005
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8478 | Cut and Fill for 6370-1 | APPROVED | No | 2025-12-08 | Abas, Mohammed Fekry | 2025-12-09 | 2025-12-11 |  |  | 3.4 | 0 | 6370 | 1 | STANDARD | Omran Al Modon Contracting Co | SAR | 622370 | APPROVED |  |  | 2025-12-24 | -622370 | 13 | Abuhammad, Samir | -46002 | 13
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8562 | Modification of 3KM Access Road | RETURNED | No | 2025-12-21 | Abuhammad, Samir | 2025-12-31 | 2025-12-26 | 2025-12-31 |  | Due to budget modification. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46017 | -46017
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8724 | po 6688 CAPITAL AMBULANCE FOR MEDICAL SERVICES | RETURNED | No | 2026-01-18 | Kumar, Mr. Ranjan | 2026-01-28 | 2026-01-21 | 2026-01-28 |  | Please attached approved POCR | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46043 | -46043
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8725 | Rental scafollding | APPROVED | No | 2026-01-18 | Abas, Mohammed Fekry | 2026-01-19 | 2026-01-21 |  |  | 3.13 | 0 | 7286 | 3 | STANDARD | Safe and Support Co | SAR | 28492.5 | REQUIRES REAPPROVAL |  |  |  | -28492.5 | 11 | Abuhammad, Samir | -46043 | -46043
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8725 | Rental scafollding | APPROVED | No | 2026-01-18 | Abas, Mohammed Fekry | 2026-01-19 | 2026-01-21 |  |  | 3.13 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46043 | -46043
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8726 | omron modon cold blasting | RETURNED | No | 2026-01-18 | Abuhammad, Samir | 2026-01-21 | 2026-01-21 | 2026-01-21 |  | dut to budget modification. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46043 | -46043
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8740 | powerlinks foundation PR | APPROVED | No | 2026-01-20 | Abas, Mohammed Fekry | 2026-01-22 | 2026-01-25 |  |  | 3.6 | 0 | 15061 | 0 | STANDARD | Global Power Linx. Company | SAR | 495000 | IN PROCESS |  |  |  | -495000 | 7 | Abuhammad, Samir | -46047 | -46047
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8740 | powerlinks foundation PR | APPROVED | No | 2026-01-20 | Abas, Mohammed Fekry | 2026-01-22 | 2026-01-25 |  |  | 3.6 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46047 | -46047
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8805 | Uplift test -Re issuing PR 4823 with 0 value | APPROVED | No | 2026-01-27 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  | 3.25 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46050 | -46050
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8806 | RGF | APPROVED | No | 2026-01-27 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  | 3.25 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46050 | -46050
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8809 | 15014-0Ibrahim Hussein Ibrahim Sayyadi General Contracting Rectification of damaged Access Roads by Rain with backfilling | APPROVED | No | 2026-01-28 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  | 3.4 | 0 | 15014 | 0 | STANDARD |  | SAR | 0 | INCOMPLETE |  |  |  | 0 | 4 | Abuhammad, Samir | -46050 | -46050
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8809 | 15014-0Ibrahim Hussein Ibrahim Sayyadi General Contracting Rectification of damaged Access Roads by Rain with backfilling | APPROVED | No | 2026-01-28 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  | 3.4 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46050 | -46050
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8810 | PO 6730 PSSA line Patrolling security.-Security Guards | APPROVED | No | 2026-01-28 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  | 3.8 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46050 | -46050
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8811 | 7626-PSSB line Patrolling security in mountain area OHTL 132kV PSSB-A IN NEOM | APPROVED | No | 2026-01-28 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  | 3.8 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46050 | -46050
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8812 | 6316-Rukn Al Kateibah Company for Security Guards. | APPROVED | No | 2026-01-28 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  | 3.8 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46050 | -46050
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8813 | PO-6523 Rukn Al Kateibah Company for Security Guards. | APPROVED | No | 2026-01-28 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  | 3.8 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46050 | -46050
105-108 | OHTL 132kV PSSA & PSSB IN NEOM | 8814 | po 7230 OHTL 132kV PSSB IN NEOM-Security Guards. | APPROVED | No | 2026-01-28 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  | 3.8 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46050 | -46050
105-109 | Waly Alahad-3 SS in Makkah | 1740 | Waly Alahad-3 SS in Makkah-Design and Engineering of Waly Alahd -3 Substation | APPROVED | No | 2023-11-14 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 425000 | 5256 | 0 | STANDARD | Design Tech Engineering Consultants Company /Simplified | SAR | 425000 | APPROVED |  |  | 2024-03-26 | 0 | 131 | Mohammed, Faisal Ansari | -45246 | 131
105-109 | Waly Alahad-3 SS in Makkah | 1743 | Waly Alahad-3 SS in Makkah-Supply of 50/60 MVA, 110.13.8kV Power Transformer | REJECTED | No | 2023-11-14 | Ibrahim, Mr. Ahmed Abdulkadir | 2023-11-14 |  |  | 2023-11-14 |  | 53035249.98 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-109 | Waly Alahad-3 SS in Makkah | 1748 | Waly Alahad-3 SS in Makkah-Supply of 50/67 MVA, 110/13.8kV Power transformers (budget line #2.4) | APPROVED | No | 2023-11-15 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 17935250 | 5203 | 0 | STANDARD | SAUDI POWER TRANSFORMERS COMPANY | SAR | 17935250 | APPROVED |  |  | 2024-03-18 | 0 | 123 | Mohammed, Faisal Ansari | -45246 | 123
105-109 | Waly Alahad-3 SS in Makkah | 1759 | Waly Alahad-3 SS in Makkah-Station Service Transformers (Budget Line Item 2.14) | APPROVED | No | 2023-11-15 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 200000 | 4749 | 0 | STANDARD | ALFANAR CO | SAR | 200000 | APPROVED |  |  | 2023-12-03 | 0 | 17 | Mohammed, Faisal Ansari | -45246 | 17
105-109 | Waly Alahad-3 SS in Makkah | 1765 | Waly Alahad-3 SS in Makkah-Soil Investigation-Topographic survey (Budget Item Code 2.32) | APPROVED | No | 2023-11-15 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 40000 | 4736 | 0 | STANDARD | International Agent Commercial Company(S) | SAR | 17980 | APPROVED |  |  | 2023-12-03 | 22020 | 17 | Mohammed, Faisal Ansari | -45246 | 17
105-109 | Waly Alahad-3 SS in Makkah | 1766 | Waly Alahad-3 SS in Makkah-Construction Permit (Budget Item code 2.27) | APPROVED | No | 2023-11-15 | Abas, Mohammed Fekry | 2023-11-16 | 2023-11-16 |  |  |  | 42000 | 4733 | 0 | STANDARD | Quality Pioneers Professional Consulting Co. | SAR | 42000 | APPROVED |  |  | 2023-11-26 | 0 | 10 | Badhman, Saeed | -45246 | 10
105-109 | Waly Alahad-3 SS in Makkah | 1771 | Waly Alahad-3 SS in Makkah-Protection, SAS & AMI (Budget Item code 2.8) | APPROVED | No | 2023-11-16 | Abas, Mohammed Fekry | 2023-11-20 | 2023-11-20 |  |  |  | 10000000 | 4781 | 0 | STANDARD | ALFANAR CO | SAR | 10000000 | APPROVED |  |  | 2023-12-11 | 0 | 21 | Mohammed, Faisal Ansari | -45250 | 21
105-109 | Waly Alahad-3 SS in Makkah | 1779 | Waly Alahad-3 SS in Makkah-Communication System (Budget item code 2.9) | APPROVED | No | 2023-11-17 | Abas, Mohammed Fekry | 2023-11-22 | 2023-11-22 |  |  |  | 3500000 | 4801 | 0 | STANDARD | ALFANAR CO | SAR | 3500000 | APPROVED |  |  | 2023-12-19 | 0 | 27 | Mohammed, Faisal Ansari | -45252 | 27
105-109 | Waly Alahad-3 SS in Makkah | 1783 | Waly Alahad-3 SS in Makkah-Cyber Security (Budget item # 2.13) | APPROVED | No | 2023-11-18 | Abas, Mohammed Fekry | 2023-11-22 | 2023-11-22 |  |  |  | 1180000 | 4765 | 0 | STANDARD | ALFANAR CO | SAR | 1180000 | APPROVED |  |  | 2023-12-14 | 0 | 22 | Mohammed, Faisal Ansari | -45252 | 22
105-109 | Waly Alahad-3 SS in Makkah | 1791 | Waly Alahad-3 SS in Makkah-Neutral Grounding Resistor 13.8kV, 800A, 10 Ohms (Budget Item # 2.5) | APPROVED | No | 2023-11-20 | Abas, Mohammed Fekry | 2023-11-22 | 2023-11-22 |  |  |  | 114750 | 4909 | 0 | STANDARD | National Switchgears | USD | 114750 | APPROVED |  |  | 2024-01-01 | 0 | 40 | Kumar, Mr. Ranjan | -45252 | 40
105-109 | Waly Alahad-3 SS in Makkah | 1914 | Waly Alahad-3 SS in Makkah-13.8 k.v MV Switchgear 630A -25kA/1sec.(Oracle # 2.6) | APPROVED | No | 2023-12-07 | Abas, Mohammed Fekry | 2023-12-11 | 2023-12-11 |  |  |  | 7820000 | 4824 | 0 | STANDARD | ALFANAR CO | SAR | 7820000 | APPROVED |  |  | 2023-12-21 | 0 | 10 | Mohammed, Faisal Ansari | -45271 | 10
105-109 | Waly Alahad-3 SS in Makkah | 1956 | Waly Alahad-3 SS in Makkah-GIS 110k.v -2000A- 40 kA S.C DBB C.B (Budget Item code 2.2) | APPROVED | No | 2023-12-13 | Abas, Mohammed Fekry | 2023-12-15 | 2023-12-17 |  |  |  | 15000000 | 4823 | 0 | STANDARD | Hyosung Heavy Industries Corporation | USD | 14925000 | APPROVED |  |  | 2024-01-15 | 75000 | 29 | Mohammed, Faisal Ansari | -45277 | 29
105-109 | Waly Alahad-3 SS in Makkah | 2040 | Waly Alahad-3 SS in Makkah-Surge Arrester (Budget Item Code 2.19) | APPROVED | No | 2023-12-26 | Abas, Mohammed Fekry | 2023-12-28 | 2023-12-28 |  |  |  | 63000 | 5080 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 57078 | APPROVED |  |  | 2024-02-21 | 5922 | 55 | Mohammed, Faisal Ansari | -45288 | 55
105-109 | Waly Alahad-3 SS in Makkah | 2248 | Waly Alahad-3 SS in Makkah-Civil Work - Budget Line Item (2.27) | APPROVED | No | 2024-01-22 | Abas, Mohammed Fekry | 2024-01-24 | 2024-01-25 |  |  |  | 12458000 | 5119 | 0 | STANDARD | Future Achievement Limited Co | SAR | 12100000 | APPROVED |  |  | 2024-03-06 | 358000 | 41 | Mohammed, Faisal Ansari | -45316 | 41
105-109 | Waly Alahad-3 SS in Makkah | 2248 | Waly Alahad-3 SS in Makkah-Civil Work - Budget Line Item (2.27) | APPROVED | No | 2024-01-22 | Abas, Mohammed Fekry | 2024-01-24 | 2024-01-25 |  |  |  | 12458000 | 5119 | 1 | STANDARD | Future Achievement Limited Co | SAR | 11650001 | APPROVED |  |  | 2025-09-21 | 807999 | 605 | Mohammed, Faisal Ansari | -45316 | 605
105-109 | Waly Alahad-3 SS in Makkah | 2515 | Waly Alahad-3 SS in Makkah-Civil Work/ Moblilization | APPROVED | No | 2024-02-11 | Abas, Mohammed Fekry | 2024-02-11 | 2024-02-12 |  |  |  | 240000 | 5107 | 0 | STANDARD | Construction Expertise Est. | SAR | 85200 | APPROVED |  |  | 2024-03-03 | 154800 | 20 | Mohammed, Faisal Ansari | -45334 | 20
105-109 | Waly Alahad-3 SS in Makkah | 2584 | Waly Alahad-3 SS in Makkah-Overhead Traveling Crane- 5T | APPROVED | No | 2024-02-18 | Abas, Mohammed Fekry | 2024-02-19 | 2024-02-21 |  |  |  | 160000 | 5320 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 138500 | APPROVED |  |  | 2024-04-15 | 21500 | 54 | Mohammed, Faisal Ansari | -45343 | 54
105-109 | Waly Alahad-3 SS in Makkah | 2624 | Waly Alahad-3 SS in Makkah-Shelding System / Lightning Mast | APPROVED | No | 2024-02-19 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 140000 | 5576 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 52600 | APPROVED |  |  | 2024-05-27 | 87400 | 91 | Mohammed, Faisal Ansari | -45348 | 91
105-109 | Waly Alahad-3 SS in Makkah | 2630 | Waly Alahad-3 SS in Makkah-Site Mobilization // Offices | APPROVED | No | 2024-02-20 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 250000 | 5523 | 0 | STANDARD | Al Arab Modern Contracting Est | SAR | 181550 | APPROVED |  |  | 2024-06-26 | 68450 | 121 | Mohammed, Faisal Ansari | -45348 | 121
105-109 | Waly Alahad-3 SS in Makkah | 2648 | Waly Alahad-3 SS in Makkah-Fire Protection System | APPROVED | No | 2024-02-21 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 2400000 | 5421 | 0 | STANDARD | Advanced Elements Co. | SAR | 2100000 | APPROVED |  |  | 2024-05-30 | 300000 | 94 | Mohammed, Faisal Ansari | -45348 | 94
105-109 | Waly Alahad-3 SS in Makkah | 2685 | Waly Alahad-3 SS in Makkah-GEM Material Protection | APPROVED | No | 2024-02-26 | Abas, Mohammed Fekry | 2024-02-28 | 2024-03-03 |  |  |  | 100000 | 5151 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 63750 | APPROVED |  |  | 2024-03-11 | 36250 | 8 | Mohammed, Faisal Ansari | -45354 | 8
105-109 | Waly Alahad-3 SS in Makkah | 2739 | Waly Alahad-3 SS in Makkah-Battery and Battery Charger. | APPROVED | No | 2024-03-03 | Abas, Mohammed Fekry | 2024-03-03 | 2024-03-03 |  |  |  | 625000 | 5325 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 499500 | APPROVED |  |  | 2024-04-23 | 125500 | 51 | Mohammed, Faisal Ansari | -45354 | 51
105-109 | Waly Alahad-3 SS in Makkah | 2754 | Waly Alahad-3 SS in Makkah-AC, DC & Lighting Panels | REJECTED | No | 2024-03-04 | Yamama, Loai Mohamed | 2024-07-30 | 2024-05-27 | 2024-05-01 | 2024-07-30 | Please issue PR when SLDs are approved as it is taking longer than expected to issue the PO based on the unified SLD. | 850000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45439 | -45439
105-109 | Waly Alahad-3 SS in Makkah | 2755 | Waly Alahad-3 SS in Makkah-MV Cabels | APPROVED | No | 2024-03-04 | Abas, Mohammed Fekry | 2024-03-11 | 2024-03-13 |  |  |  | 959080 | 5430 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 956628.01 | APPROVED |  |  | 2024-05-23 | 2451.99 | 71 | Mohammed, Faisal Ansari | -45364 | 71
105-109 | Waly Alahad-3 SS in Makkah | 2799 | Waly Alahad-3 SS in Makkah-Permit / Demolishing Permit issuance (Budget Line Item 2.27) | APPROVED | No | 2024-03-06 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 6000 | 5170 | 0 | STANDARD | Quality Pioneers Professional Consulting Co. | SAR | 6000 | APPROVED |  |  | 2024-03-14 | 0 | 7 | Abuhammad, Samir | -45358 | 7
105-109 | Waly Alahad-3 SS in Makkah | 3061 | Waly Alahad-3 SS in Makkah-Grounding/ Earthing Materials | REJECTED | No | 2024-04-18 | Issa, Amr Ali | 2024-04-22 | 2024-04-22 |  | 2024-04-22 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45404 | -45404
105-109 | Waly Alahad-3 SS in Makkah | 3255 | Waly Alahad-3 SS in Makkah-MV Terimination KIts | APPROVED | No | 2024-05-02 | Abas, Mohammed Fekry | 2024-05-06 | 2024-05-06 |  |  |  | 123000 | 5505 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 112756 | APPROVED |  |  | 2024-05-23 | 10244 | 17 | Mohammed, Faisal Ansari | -45418 | 17
105-109 | Waly Alahad-3 SS in Makkah | 3259 | Waly Alahad-3 SS in Makkah-Grounding Conductor and Y/G Cables | APPROVED | No | 2024-05-02 | Issa, Amr Ali | 2024-05-12 | 2024-05-12 |  |  |  | 360000 | 5420 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 340632.88 | APPROVED |  |  | 2024-05-26 | 19367.12 | 14 | Mohammed, Faisal Ansari | -45424 | 14
105-109 | Waly Alahad-3 SS in Makkah | 3260 | Waly Alahad-3 SS in Makkah-Grounding Materials | APPROVED | No | 2024-05-02 | Abas, Mohammed Fekry | 2024-05-02 | 2024-05-05 |  |  |  | 80000 | 5417 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 72524 | APPROVED |  |  | 2024-05-19 | 7476 | 14 | Mohammed, Faisal Ansari | -45417 | 14
105-109 | Waly Alahad-3 SS in Makkah | 3316 | Waly Alahad-3 SS in Makkah-ACSR Conductor & Lugs, Fitting | APPROVED | No | 2024-05-07 | Abas, Mohammed Fekry | 2024-05-09 | 2024-05-12 |  |  |  | 20000 | 5761 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 4820.69 | APPROVED |  |  | 2024-07-09 | 15179.31 | 58 | Mohammed, Faisal Ansari | -45424 | 58
105-109 | Waly Alahad-3 SS in Makkah | 3367 | Waly Alahad-3 SS in Makkah-Electrical Installation subcontractor | APPROVED | No | 2024-05-11 | Abas, Mohammed Fekry | 2024-09-17 | 2024-09-17 |  |  |  | 2342150 | 6218 | 0 | STANDARD | Hussain Ali Hussain Contracting Company | SAR | 2342150 | APPROVED |  |  | 2024-10-01 | 0 | 14 | Alhadi, Khalid | -45552 | 14
105-109 | Waly Alahad-3 SS in Makkah | 3386 | Waly Alahad-3 SS in Makkah-Cable tray and ladders | RETURNED | No | 2024-05-12 | Badhman, Saeed | 2024-08-14 | 2024-05-14 | 2024-08-14 |  | submit it on item wise | 400000 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45426 | -45426
105-109 | Waly Alahad-3 SS in Makkah | 3487 | Waly Alahad-3 SS in Makkah-HVAC System | APPROVED | No | 2024-05-23 | Abas, Mohammed Fekry | 2024-05-25 | 2024-05-26 |  |  |  | 2100000 | 5777 | 0 | STANDARD | MARINE SERVICES CO LTD. | SAR | 1850000 | APPROVED |  |  | 2024-07-17 | 250000 | 52 | Mohammed, Faisal Ansari | -45438 | 52
105-109 | Waly Alahad-3 SS in Makkah | 3491 | Waly Alahad-3 SS in Makkah-AC, DC Distribution and Lighting Panels | APPROVED | No | 2024-05-26 | Malek, Warren | 2024-06-06 | 2024-06-06 | 2024-06-03 |  | PR value is less than the PO value. | 800000 | 5032 | 0 | STANDARD | ALFANAR CO | SAR | 800000 | APPROVED |  |  | 2024-07-25 | 0 | 49 | Mohammed, Faisal Ansari | -45449 | 49
105-109 | Waly Alahad-3 SS in Makkah | 3710 | Waly Alahad-3 SS in Makkah-PO value after the cooper booking.- Budget items - 2.28 | APPROVED | No | 2024-06-30 | Abas, Mohammed Fekry | 2024-07-08 | 2024-07-09 |  |  |  | 90000 | 5420 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 31282.62 | APPROVED |  |  | 2024-07-25 | 58717.38 | 16 | Mohammed, Faisal Ansari | -45482 | 16
105-109 | Waly Alahad-3 SS in Makkah | 3800 | Waly Alahad-3 SS in Makkah-MV cable CO from PO # 5430 | APPROVED | No | 2024-07-08 | Abas, Mohammed Fekry | 2024-08-07 | 2024-08-08 |  |  |  | 130000 | 5430 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 129854.79 | APPROVED |  |  | 2024-09-16 | 145.21 | 39 | Mohammed, Faisal Ansari | -45512 | 39
105-109 | Waly Alahad-3 SS in Makkah | 4063 | Waly Alahad-3 SS in Makkah-SECUIRTY SYSTEM CCTV | APPROVED | No | 2024-07-31 | Abas, Mohammed Fekry | 2024-08-04 | 2024-08-04 |  |  |  | 650000 | 6231 | 0 | STANDARD | ALFANAR CO | SAR | 650000 | APPROVED |  |  | 2024-10-08 | 0 | 65 | Muhammad, Muhammad Atif | -45508 | 65
105-109 | Waly Alahad-3 SS in Makkah | 4107 | Waly Alahad-3 SS in Makkah-Calmps and connectors | APPROVED | No | 2024-08-06 | Abas, Mohammed Fekry | 2024-08-14 | 2024-08-15 |  |  |  | 16009 | 6169 | 0 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 15327.69 | APPROVED |  |  | 2024-10-01 | 681.31 | 47 | Babic, Marian | -45519 | 47
105-109 | Waly Alahad-3 SS in Makkah | 4256 | Waly Alahad-3 SS in Makkah-Cable tray and Cable ladders | RETURNED | No | 2024-08-24 | Badhman, Saeed | 2024-10-13 | 2024-09-26 |  |  |  | 453748.6 | 5976 | 0 | STANDARD | Power Solution Industries | SAR | 453748.6 | APPROVED |  |  | 2024-10-31 | 0 |  | Badhman, Saeed | -45561 | 35
105-109 | Waly Alahad-3 SS in Makkah | 4256 | Waly Alahad-3 SS in Makkah-Cable tray and Cable ladders | RETURNED | No | 2024-08-24 | Badhman, Saeed | 2024-10-13 | 2024-09-26 |  |  |  | 221.76 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45561 | -45561
105-109 | Waly Alahad-3 SS in Makkah | 4297 | Waly Alahad-3 SS in Makkah-Security System Additiional budget (10,000) | APPROVED | No | 2024-08-28 | Abas, Mohammed Fekry | 2024-09-04 | 2024-09-04 |  |  |  | 10000 | 6231 | 0 | STANDARD | ALFANAR CO | SAR | 10000 | APPROVED |  |  | 2024-10-08 | 0 | 34 | Muhammad, Muhammad Atif | -45539 | 34
105-109 | Waly Alahad-3 SS in Makkah | 4301 | Waly Alahad-3 SS in Makkah-Power Transformer loading/unloading and Tranporation | APPROVED | No | 2024-08-29 | Abas, Mohammed Fekry | 2024-09-04 | 2024-09-04 |  |  |  | 184000 | 6250 | 0 | STANDARD | MOHAMMED HAMAD AL-AHMADE FOR TRADING AND CONSTRACTION | SAR | 184000 | APPROVED |  |  | 2024-10-14 | 0 | 40 | Badhman, Saeed | -45539 | 40
105-109 | Waly Alahad-3 SS in Makkah | 4328 | Waly Alahad-3 SS in Makkah-Supply Splicing and testing of fiber cables. | REJECTED | No | 2024-08-30 | Yamama, Loai Mohamed | 2024-11-13 | 2024-09-02 |  | 2024-11-14 |  | 300000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45537 | -45537
105-109 | Waly Alahad-3 SS in Makkah | 4401 | Waly Alahad-3 SS in Makkah-Additional PR for GIS Supplier Payment Issue.(PO # 4823 Already Issued) | REJECTED | No | 2024-09-09 | Yamama, Loai Mohamed | 2024-09-10 | 2024-09-10 |  | 2024-09-11 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45545 | -45545
105-109 | Waly Alahad-3 SS in Makkah | 4511 | Waly Alahad-3 SS in Makkah-Supply of LV & Control Cables | RETURNED | No | 2024-09-22 | Badhman, Saeed | 2025-11-16 | 2024-09-26 | 2025-11-16 |  | Not Needed, PO AND CO have been issued already | 34368 | 6106 | 3 | STANDARD | ALFANAR CO | SAR | 30247.96 | APPROVED |  |  | 2025-02-11 | 4120.04 |  | Mohammed, Faisal Ansari | -45561 | 138
105-109 | Waly Alahad-3 SS in Makkah | 4511 | Waly Alahad-3 SS in Makkah-Supply of LV & Control Cables | RETURNED | No | 2024-09-22 | Badhman, Saeed | 2025-11-16 | 2024-09-26 | 2025-11-16 |  | Not Needed, PO AND CO have been issued already | 1018193.43 | 6106 | 0 | STANDARD | ALFANAR CO | SAR | 1018193.43 | APPROVED |  |  | 2024-10-31 | 0 |  | Badhman, Saeed | -45561 | 35
105-109 | Waly Alahad-3 SS in Makkah | 4511 | Waly Alahad-3 SS in Makkah-Supply of LV & Control Cables | RETURNED | No | 2024-09-22 | Badhman, Saeed | 2025-11-16 | 2024-09-26 | 2025-11-16 |  | Not Needed, PO AND CO have been issued already | 136032.82 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45561 | -45561
105-109 | Waly Alahad-3 SS in Makkah | 4554 | Waly Alahad-3 SS in Makkah-GIS Optional Scope for Training | APPROVED | No | 2024-09-30 | Abas, Mohammed Fekry | 2024-10-04 | 2024-10-06 |  |  |  | 250000 | 4823 | 2 | STANDARD | Hyosung Heavy Industries Corporation | USD | 243750 | APPROVED |  |  | 2024-10-16 | 6250 | 10 | Babic, Marian | -45571 | 10
105-109 | Waly Alahad-3 SS in Makkah | 4683 | Waly Alahad-3 SS in Makkah-Cable tray and Cable ladders (Additional PR for adding one item) | APPROVED | No | 2024-10-15 | Abas, Mohammed Fekry | 2024-10-16 | 2024-10-16 |  |  |  | 221.76 | 5976 | 0 | STANDARD | Power Solution Industries | SAR | 221.76 | APPROVED |  |  | 2024-10-31 | 0 | 15 | Badhman, Saeed | -45581 | 15
105-109 | Waly Alahad-3 SS in Makkah | 4684 | Waly Alahad-3 SS in Makkah-Lghting Pole | REJECTED | No | 2024-10-15 | Yamama, Loai Mohamed | 2024-10-20 | 2024-10-15 |  | 2024-10-20 |  | 6400 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45580 | -45580
105-109 | Waly Alahad-3 SS in Makkah | 4743 | Waly Alahad-3 SS in Makkah-Lghting Pole (Additional) | APPROVED | No | 2024-10-20 | Abas, Mohammed Fekry | 2024-10-21 | 2024-10-22 |  |  |  | 7000 | 6217 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 7000 | APPROVED |  |  | 2024-10-28 | 0 | 6 | Eliwa, Mahmoud | -45587 | 6
105-109 | Waly Alahad-3 SS in Makkah | 4968 | Waly Alahad-3 SS in Makkah-Supply of Lighting Wire and Conduit | RETURNED | No | 2024-11-17 | Kumar, Mr. Ranjan | 2025-09-11 | 2024-11-20 | 2025-09-11 |  | PO 6382 issued, Transportation is included in the quited price hence, Transportation line is returned line Is Returned | 180892.69 | 6382 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 180369.97 | APPROVED |  |  | 2024-12-10 | 522.72 |  | Kumar, Mr. Ranjan | -45616 | 20
105-109 | Waly Alahad-3 SS in Makkah | 4968 | Waly Alahad-3 SS in Makkah-Supply of Lighting Wire and Conduit | RETURNED | No | 2024-11-17 | Kumar, Mr. Ranjan | 2025-09-11 | 2024-11-20 | 2025-09-11 |  | PO 6382 issued, Transportation is included in the quited price hence, Transportation line is returned line Is Returned | 20000 | [5 empty] | 0 |  |  |  |  | 0 |  | Eliwa, Mahmoud | -45616 | -45616
105-109 | Waly Alahad-3 SS in Makkah | 5050 | Waly Alahad-3 SS in Makkah-Supply of Lighting Wire and Conduit (Addition Item for PR #4968) | APPROVED | No | 2024-11-25 | Abas, Mohammed Fekry | 2024-12-01 | 2024-12-03 |  |  |  | 8447.6 | 6382 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 8183 | APPROVED |  |  | 2024-12-10 | 264.6 | 7 | Kumar, Mr. Ranjan | -45629 | 7
105-109 | Waly Alahad-3 SS in Makkah | 5221 | Waly Alahad-3 SS in Makkah-Testing and Commissioning Services | APPROVED | No | 2024-12-11 | Abas, Mohammed Fekry | 2024-12-16 | 2024-12-17 |  |  |  | 2130000 | 6597 | 0 | STANDARD | Al Fanar Technical Services | SAR | 2130000 | APPROVED |  |  | 2025-05-28 | 0 | 162 | Babic, Marian | -45643 | 162
105-109 | Waly Alahad-3 SS in Makkah | 5222 | Waly Alahad-3 SS in Makkah-Supply of MV Cable Clamps | APPROVED | No | 2024-12-12 | Abas, Mohammed Fekry | 2024-12-16 | 2024-12-18 |  |  |  | 56092 | 6646 | 0 | STANDARD | ABDULLAH M. AL-SHAHRANI FACTORY | SAR | 56092 | APPROVED |  |  | 2024-12-24 | 0 | 6 | Mohammed, Faisal Ansari | -45644 | 6
105-109 | Waly Alahad-3 SS in Makkah | 5229 | Waly Alahad-3 SS in Makkah-Supply & Installation of Freestanding Air Conditioners | APPROVED | No | 2024-12-15 | Abas, Mohammed Fekry | 2025-03-18 | 2025-03-18 |  |  |  | 81950 | 6565 | 0 | STANDARD | Roadwey Trading Company | SAR | 81950 | APPROVED |  |  | 2025-03-23 | 0 | 5 | Mohammed, Faisal Ansari | -45734 | 5
105-109 | Waly Alahad-3 SS in Makkah | 5229 | Waly Alahad-3 SS in Makkah-Supply & Installation of Freestanding Air Conditioners | APPROVED | No | 2024-12-15 | Abas, Mohammed Fekry | 2025-03-18 | 2025-03-18 |  |  |  | 81950 | 7422 | 0 | STANDARD | Voltage Professionals contracting establishment | SAR | 81910 | APPROVED |  |  | 2025-06-29 | 40 | 103 | Babic, Marian | -45734 | 103
105-109 | Waly Alahad-3 SS in Makkah | 5245 | Waly Alahad-3 SS in Makkah-Supply of RXBA For Fuse Monitoring Relay [Model: RK428004-AA] | APPROVED | No | 2024-12-19 | Abas, Mohammed Fekry | 2024-12-29 | 2024-12-30 |  |  |  | 15878 | 6659 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 15878 | APPROVED |  |  | 2025-01-09 | 0 | 10 | Mohammed, Faisal Ansari | -45656 | 10
105-109 | Waly Alahad-3 SS in Makkah | 5385 | Waly Alahad-3 SS in Makkah-P143 - Feeder Management Relay with autoreclose & synchronising | APPROVED | No | 2025-01-12 | Abas, Mohammed Fekry | 2025-01-20 | 2025-01-22 | 2025-01-16 |  | As discussed, please increase the PR value to SAR 38,600 to match the PO value. | 38600 | 6739 | 0 | STANDARD | Abdel Hadi Abdullah Al Qahtani & Sons Co (S) | SAR | 38535 | APPROVED |  |  | 2025-01-28 | 65 | 6 | Mohammed, Faisal Ansari | -45679 | 6
105-109 | Waly Alahad-3 SS in Makkah | 5417 | Waly Alahad-3 SS in Makkah-For Fectory Acceptance Test (FAT) | APPROVED | No | 2025-01-14 | Abas, Mohammed Fekry | 2025-01-21 | 2025-01-23 | 2025-01-20 |  | Please revise the prices | 2800 | 6848 | 0 | STANDARD | Atlas Support and Services | SAR | 2800 | APPROVED |  |  | 2025-02-10 | 0 | 18 | Akhtar, Farhan | -45680 | 18
105-109 | Waly Alahad-3 SS in Makkah | 5635 | Waly Alahad-3 SS in Makkah-Supply of Low Voltage Power & Control Cables (For Change Order) | APPROVED | No | 2025-01-27 | Abas, Mohammed Fekry | 2025-02-01 | 2025-02-02 |  |  |  | 230628.37 | 6106 | 3 | STANDARD | ALFANAR CO | SAR | 230628.37 | APPROVED |  |  | 2025-02-11 | 0 | 9 | Mohammed, Faisal Ansari | -45690 | 9
105-109 | Waly Alahad-3 SS in Makkah | 5705 | Waly Alahad-3 SS in Makkah-Supply of Indoor & Outdoor Lighting fixtures | APPROVED | No | 2025-01-28 | Abas, Mohammed Fekry | 2025-01-30 | 2025-01-31 |  |  |  | 99625 | 6795 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 99625 | APPROVED |  |  | 2025-02-10 | 0 | 10 | Muaz, Alaa | -45688 | 10
105-109 | Waly Alahad-3 SS in Makkah | 5757 | Waly Alahad-3 SS in Makkah-Indoor & Outdoor Receptacles | RETURNED | No | 2025-02-02 | Muaz, Alaa | 2025-02-06 | 2025-02-05 | 2025-02-06 |  | As the PR is in LOT and it should be itemized as DPO Annex | 160789.16 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -45693 | -45693
105-109 | Waly Alahad-3 SS in Makkah | 5865 | Waly Alahad-3 SS in Makkah-Supply of Printers | RETURNED | No | 2025-02-13 | Akhtar, Farhan | 2025-07-23 | 2025-03-13 |  |  |  | 20500 | 7023 | 0 | STANDARD | Mohammad Abdul Rahman Mohd Al Zahid Information Technology Co | SAR | 19500 | APPROVED |  |  | 2025-03-18 | 1000 |  | Akhtar, Farhan | -45729 | 5
105-109 | Waly Alahad-3 SS in Makkah | 5865 | Waly Alahad-3 SS in Makkah-Supply of Printers | RETURNED | No | 2025-02-13 | Akhtar, Farhan | 2025-07-23 | 2025-03-13 |  |  |  | 5775 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45729 | -45729
105-109 | Waly Alahad-3 SS in Makkah | 5954 | Waly Alahad-3 SS in Makkah-Supply of Indoor & Outdoor Receptacles | APPROVED | No | 2025-02-18 | Abas, Mohammed Fekry | 2025-02-22 | 2025-02-22 |  |  |  | 151866.04 | 6884 | 0 | STANDARD | Tawasul International Trad.Est. | SAR | 151866.04 | APPROVED |  |  | 2025-03-13 | 0 | 19 | Muaz, Alaa | -45710 | 19
105-109 | Waly Alahad-3 SS in Makkah | 6390 | Waly Alahad-3 SS in Makkah-Cable Tray and cable ladder additional material | APPROVED | No | 2025-04-20 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-20 |  |  |  | 26203.45 | 7112 | 0 | STANDARD | Power Solution Industries | SAR | 26203 | APPROVED |  |  | 2025-04-24 | 0.45 | 4 | Mohammed, Faisal Ansari | -45767 | 4
105-109 | Waly Alahad-3 SS in Makkah | 6451 | Waly Alahad-3 SS in Makkah-Supply of Surg Arrester | APPROVED | No | 2025-04-26 | Abas, Mohammed Fekry | 2025-04-28 | 2025-04-28 |  |  |  | 20000 | 7369 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 12831.35 | APPROVED |  |  | 2025-07-02 | 7168.65 | 65 | Mohammed, Faisal Ansari | -45775 | 65
105-109 | Waly Alahad-3 SS in Makkah | 6472 | Waly Alahad-3 SS in Makkah-Manufacturing, Fabrication, Supply and Installation of steel Decorative Fence and Gate Work | REJECTED | No | 2025-04-28 | UR Rehman, Habib | 2025-05-08 | 2025-05-01 |  | 2025-05-05 |  | 510350 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45778 | -45778
105-109 | Waly Alahad-3 SS in Makkah | 6611 | Waly Alahad-3 SS in Makkah-Supply, Installation, Splicing, and Testing of Fiber Optic Cables, Patch Cords, SAS & Serial Cables, and CAT6 Cables. | REJECTED | No | 2025-05-13 | UR Rehman, Habib | 2025-05-18 | 2025-05-14 | 2025-05-15 | 2025-05-15 | Please correct the Item Description and the UOM in the PR and resend it for approval. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45791 | -45791
105-109 | Waly Alahad-3 SS in Makkah | 6630 | Waly Alahad-3 SS in Makkah-Supply, Installation, Splicing, and Testing of Fiber Optic Cables, Patch Cords, SAS & Serial Cables, and CAT6 Cables. | APPROVED | No | 2025-05-18 | Abas, Mohammed Fekry | 2025-05-19 | 2025-05-20 |  |  | Budget Line Item 2.18 | 260000 | 7272 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 260000 | APPROVED |  |  | 2025-05-25 | 0 | 5 | Mohammed, Faisal Ansari | -45797 | 5
105-109 | Waly Alahad-3 SS in Makkah | 6676 | Waly Alahad-3 SS in Makkah-Testing Commissioning work ( Additional PR) | APPROVED | No | 2025-05-20 | Abas, Mohammed Fekry | 2025-05-21 | 2025-05-21 |  |  | Budget line item 3.8. | 10000 | 6597 | 0 | STANDARD | Al Fanar Technical Services | SAR | 9021 | APPROVED |  |  | 2025-05-28 | 979 | 7 | Babic, Marian | -45798 | 7
105-109 | Waly Alahad-3 SS in Makkah | 6766 | Waly Alahad-3 SS in Makkah-Supply of Firestop Material | APPROVED | No | 2025-06-03 | Abas, Mohammed Fekry | 2025-07-08 | 2025-07-08 | 2025-07-07 |  | The description appears to be incorrect. Please correct it. | 100000 | 7544 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 83400 | APPROVED |  |  | 2025-08-03 | 16600 | 26 | Hegazy, Ayman | -45846 | 26
105-109 | Waly Alahad-3 SS in Makkah | 7112 | Waly Alahad-3 SS in Makkah-Supply fabrication and modification of HDG steel panel | APPROVED | No | 2025-07-16 | Abas, Mohammed Fekry | 2025-07-20 | 2025-07-20 |  |  | Budget Line Item 2.27 | 36000 | 7552 | 0 | STANDARD | Zahi Maas General Contracting Est | SAR | 22000 | APPROVED |  |  | 2025-08-27 | 14000 | 38 | Mohammed, Faisal Ansari | -45858 | 38
105-109 | Waly Alahad-3 SS in Makkah | 7150 | Waly Alahad-3 SS in Makkah-TFR, DSM scope | APPROVED | No | 2025-07-20 | Abas, Mohammed Fekry | 2025-07-22 | 2025-07-22 |  |  |  | 218000 | 7547 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 218000 | APPROVED |  |  | 2025-08-02 | 0 | 11 | Babic, Marian | -45860 | 11
105-109 | Waly Alahad-3 SS in Makkah | 7273 | Waly Alahad-3 SS in Makkah-Manpower for Testing & Commissioning Activities | RETURNED | No | 2025-08-04 | Mohammed, Faisal Ansari | 2025-09-07 | 2025-08-10 | 2025-09-07 |  | Returning this PR after discussing with PE. | 575000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45879 | -45879
105-109 | Waly Alahad-3 SS in Makkah | 7377 | Steel Decorative Fence and Gates -Waly Al Ahad-3 Alfursan | APPROVED | No | 2025-08-24 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  |  | 0 | 6816 | 0 | STANDARD | Fursan Construction Industry Factory Industry Factory | SAR | 650095 | APPROVED |  |  | 2025-09-30 | -650095 | 36 | Hegazy, Ayman | -45894 | 36
105-109 | Waly Alahad-3 SS in Makkah | 7528 | SUBJECT: Design, Supply, Installation, Termination, Testing, and Commissioning of the Premises Distribution System (PDS) Cabling. | APPROVED | No | 2025-08-27 | Abas, Mohammed Fekry | 2025-08-27 | 2025-08-28 |  |  |  | 0 | 7644 | 0 | STANDARD | RASHID SAEED AHMED AL GHAMDI COMM INFO TRAD EST | SAR | 140000 | APPROVED |  |  | 2025-09-04 | -140000 | 7 | Mohammed, Faisal Ansari | -45897 | 7
105-109 | Waly Alahad-3 SS in Makkah | 7782 | Supply of cable Tray | APPROVED | No | 2025-09-17 | Abas, Mohammed Fekry | 2025-09-25 | 2025-09-28 |  |  |  | 0 | 7700 | 0 | STANDARD | Power Solution Industries | SAR | 107037 | APPROVED |  |  | 2025-10-21 | -107037 | 23 | Mohammed, Faisal Ansari | -45928 | 23
105-109 | Waly Alahad-3 SS in Makkah | 8102 | Supply of Rental Manpower | APPROVED | No | 2025-11-04 | Abas, Mohammed Fekry | 2025-11-06 | 2025-11-09 |  |  | For rental Manpower | 0 | 7828 | 0 | STANDARD | Modern Technical Fields Contracting Est | SAR | 226200 | APPROVED |  |  | 2025-12-17 | -226200 | 38 | Babic, Marian | -45970 | 38
105-109 | Waly Alahad-3 SS in Makkah | 8441 | Hazardous wastage collection | RETURNED | No | 2025-12-14 | Mohammed, Faisal Ansari | 2025-12-21 | 2025-12-18 | 2025-12-21 |  | BOQ shall be issued separately for Grounding & Lighting Materials. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46009 | -46009
105-109 | Waly Alahad-3 SS in Makkah | 8522 | Supply of Earthing,lighitng and small consumable Materials | RETURNED | No | 2025-12-14 | Mohammed, Faisal Ansari | 2025-12-21 | 2025-12-18 | 2025-12-21 |  | BOQ shall be issued separately for Earthing, Lighting & Consumable Materials. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46009 | -46009
105-111 | Rectification of TONOMUS fiber | 2352 | Rectification of TONOMUS fiber-PR for Rectification of Damaged fiber cables-PO-8383 | APPROVED | No | 2024-01-29 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 81880 | 5046 | 0 | STANDARD | Gawasem Construction Est | SAR | 81880 | APPROVED |  |  | 2024-02-21 | 0 | 17 | Abuhammad, Samir | -45326 | 17
105-112 | CONSTRUCTION OF MEDNO-3 SS | 2341 | CONSTRUCTION OF MEDNO-3 SS-Survey works for UGC portion - MEDNO | APPROVED | No | 2024-01-29 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 28318 | 5041 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 28318 | APPROVED |  |  | 2024-11-28 | 0 | 298 | Alhadi, Khalid | -45326 | 298
105-112 | CONSTRUCTION OF MEDNO-3 SS | 3293 | CONSTRUCTION OF MEDNO-3 SS-110kV GIS @ OUHD SS project | APPROVED | No | 2024-05-05 | Abas, Mohammed Fekry | 2024-05-06 | 2024-05-12 |  |  |  | 1425500 | 5081 | 0 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 1425500 | APPROVED |  |  | 2024-06-09 | 0 | 28 | Muhammad, Muhammad Atif | -45424 | 28
105-112 | CONSTRUCTION OF MEDNO-3 SS | 3489 | CONSTRUCTION OF MEDNO-3 SS-110kV GIS @ OUHD SS PROJECT | APPROVED | No | 2024-05-24 | Abas, Mohammed Fekry | 2024-05-30 | 2024-05-31 |  |  |  | 1162000 | 5081 | 0 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 1162000 | APPROVED |  |  | 2024-06-09 | 0 | 9 | Muhammad, Muhammad Atif | -45443 | 9
105-112 | CONSTRUCTION OF MEDNO-3 SS | 3880 | CONSTRUCTION OF MEDNO-3 SS-MEDNO: Protection, Control, & Metering PO | APPROVED | No | 2024-07-14 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 2300000 | 5970 | 0 | STANDARD | ALFANAR CO | SAR | 2300000 | APPROVED |  |  | 2024-12-26 | 0 | 163 | Muhammad, Muhammad Atif | -45489 | 163
105-112 | CONSTRUCTION OF MEDNO-3 SS | 3881 | CONSTRUCTION OF MEDNO-3 SS-MEDNO: Communication System PO | APPROVED | No | 2024-07-14 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 3400000 | 5843 | 0 | STANDARD | ALFANAR CO | SAR | 3400000 | APPROVED |  |  | 2024-07-31 | 0 | 15 | Muhammad, Muhammad Atif | -45489 | 15
105-112 | CONSTRUCTION OF MEDNO-3 SS | 3883 | CONSTRUCTION OF MEDNO-3 SS-MEDNO Project: Cyber Security PO | APPROVED | No | 2024-07-14 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 900000 | 6343 | 0 | STANDARD | ACET SOLUTIONS LLC | SAR | 399000 | APPROVED |  |  | 2024-11-07 | 501000 | 114 | Badhman, Saeed | -45489 | 114
105-112 | CONSTRUCTION OF MEDNO-3 SS | 3886 | CONSTRUCTION OF MEDNO-3 SS-MEDNO Project: SAS & SCADA Modification PO | APPROVED | No | 2024-07-14 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 1200000 | 6656 | 0 | STANDARD | Grid Solution Arabia LTD | SAR | 1086600 | APPROVED |  |  | 2025-02-10 | 113400 | 209 | Abdulqader, Ahmed Abdulhalim | -45489 | 209
105-112 | CONSTRUCTION OF MEDNO-3 SS | 4146 | CONSTRUCTION OF MEDNO-3 SS-IT for Site Office | APPROVED | No | 2024-08-12 | Malek, Warren | 2024-08-14 | 2024-08-14 |  |  |  | 23000 | 6050 | 0 | STANDARD | Mohmmed Abdulrahman AlZahid IT CO. | SAR | 19400 | APPROVED |  |  | 2024-09-02 | 3600 | 19 | Akhtar, Farhan | -45518 | 19
105-112 | CONSTRUCTION OF MEDNO-3 SS | 4279 | CONSTRUCTION OF MEDNO-3 SS-MEDNO Project: Service - Mesurements For Existing GIS Connection Adaptor | APPROVED | No | 2024-08-27 | Abas, Mohammed Fekry | 2024-08-29 | 2024-09-01 |  |  |  | 100000 | 6219 | 0 | STANDARD | Tayma Tech Co.,Ltd.(S) | SAR | 85000 | APPROVED |  |  | 2024-09-29 | 15000 | 28 | Alhadi, Khalid | -45536 | 28
105-112 | CONSTRUCTION OF MEDNO-3 SS | 4556 | CONSTRUCTION OF MEDNO-3 SS-MEDNO Project: Civil Works Service - Soil Investigation | APPROVED | No | 2024-09-30 | Abas, Mohammed Fekry | 2024-10-03 | 2024-10-04 |  |  |  | 100000 | 6322 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 30000 | APPROVED |  |  | 2024-10-17 | 70000 | 13 | Alhadi, Khalid | -45569 | 13
105-112 | CONSTRUCTION OF MEDNO-3 SS | 4557 | CONSTRUCTION OF MEDNO-3 SS-MEDNO Project: Civil Works Service - Radar Scanning | APPROVED | No | 2024-09-30 | Abas, Mohammed Fekry | 2024-10-03 | 2024-10-04 |  |  |  | 100000 | 6323 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 79500 | APPROVED |  |  | 2024-10-29 | 20500 | 25 | Alhadi, Khalid | -45569 | 25
105-112 | CONSTRUCTION OF MEDNO-3 SS | 4560 | CONSTRUCTION OF MEDNO-3 SS-MEDNO Project: Security Systems - FF & FA Modification Works | APPROVED | No | 2024-09-30 | Abas, Mohammed Fekry | 2024-10-03 | 2024-10-04 |  |  |  | 200000 | 6583 | 0 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 133244 | APPROVED |  |  | 2024-12-31 | 66756 | 88 | Alhadi, Khalid | -45569 | 88
105-112 | CONSTRUCTION OF MEDNO-3 SS | 4615 | CONSTRUCTION OF MEDNO-3 SS-MEDNO Project: Engineering & Design Service | APPROVED | No | 2024-10-07 | Abas, Mohammed Fekry | 2024-10-08 | 2024-10-08 |  |  |  | 690000 | 4950 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 690000 | APPROVED |  |  | 2024-10-14 | 0 | 6 | Muhammad, Muhammad Atif | -45573 | 6
105-112 | CONSTRUCTION OF MEDNO-3 SS | 4617 | CONSTRUCTION OF MEDNO-3 SS-MEDNO Project: UGFOC - NON METTALIC FIBER OPTIC CABLE | APPROVED | No | 2024-10-07 | Abas, Mohammed Fekry | 2024-10-08 | 2024-10-08 |  |  |  | 66000 | 6364 | 0 | STANDARD | AMWAJ TELECOMMUNICATION MFG. CO. | SAR | 60500 | APPROVED |  |  | 2024-10-29 | 5500 | 21 | Alhadi, Khalid | -45573 | 21
105-112 | CONSTRUCTION OF MEDNO-3 SS | 4717 | CONSTRUCTION OF MEDNO-3 SS-MEDNO Project: Link Box & SVL | APPROVED | No | 2024-10-17 | Abas, Mohammed Fekry | 2024-10-21 | 2024-10-22 |  |  |  | 96000 | 6363 | 2 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 60000 | APPROVED |  |  | 2025-10-05 | 36000 | 348 | Alhadi, Khalid | -45587 | 348
105-112 | CONSTRUCTION OF MEDNO-3 SS | 4717 | CONSTRUCTION OF MEDNO-3 SS-MEDNO Project: Link Box & SVL | APPROVED | No | 2024-10-17 | Abas, Mohammed Fekry | 2024-10-21 | 2024-10-22 |  |  |  | 126400 | 6363 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 126400 | APPROVED |  |  | 2024-10-30 | 0 | 8 | Alhadi, Khalid | -45587 | 8
105-112 | CONSTRUCTION OF MEDNO-3 SS | 4821 | CONSTRUCTION OF MEDNO-3 SS-MEDNO Project: MASTA SS Existing HV GIS Cable Compartment Modification | APPROVED | No | 2024-11-03 | Abas, Mohammed Fekry | 2024-11-07 | 2024-11-07 |  |  |  | 300000 | 7000 | 0 | STANDARD | Tayma Tech Co.,Ltd.(S) | SAR | 300000 | APPROVED |  |  | 2025-04-16 | 0 | 160 | Alhadi, Khalid | -45603 | 160
105-112 | CONSTRUCTION OF MEDNO-3 SS | 5120 | CONSTRUCTION OF MEDNO-3 SS-MEDNO Project: Testing & Comissioning Service | APPROVED | No | 2024-12-03 | Abas, Mohammed Fekry | 2024-12-04 | 2024-12-04 |  |  |  | 1400000 | 15017 | 0 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 1400000 | INCOMPLETE |  |  |  | 0 | 424 | Mohammed, Faisal Ansari | -45630 | -45630
105-112 | CONSTRUCTION OF MEDNO-3 SS | 5120 | CONSTRUCTION OF MEDNO-3 SS-MEDNO Project: Testing & Comissioning Service | APPROVED | No | 2024-12-03 | Abas, Mohammed Fekry | 2024-12-04 | 2024-12-04 |  |  |  | 1400000 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45630 | -45630
105-112 | CONSTRUCTION OF MEDNO-3 SS | 5410 | CONSTRUCTION OF MEDNO-3 SS-MEDNO Project: HV Cable Clamp | APPROVED | No | 2025-01-13 | Abas, Mohammed Fekry | 2025-01-18 | 2025-01-19 |  |  |  | 8400 | 6791 | 0 | STANDARD | ABDULLAH M. AL-SHAHRANI FACTORY | SAR | 8060 | APPROVED |  |  | 2025-02-06 | 340 | 18 | Alhadi, Khalid | -45676 | 18
105-112 | CONSTRUCTION OF MEDNO-3 SS | 5411 | CONSTRUCTION OF MEDNO-3 SS-MEDNO Project: Supply of FOMR & FSTP | APPROVED | No | 2025-01-13 | Abas, Mohammed Fekry | 2025-01-18 | 2025-01-19 |  |  |  | 54000 | 6792 | 0 | STANDARD | AMWAJ TELECOMMUNICATION MFG. CO. | SAR | 44700 | APPROVED |  |  | 2025-02-04 | 9300 | 16 | Alhadi, Khalid | -45676 | 16
105-112 | CONSTRUCTION OF MEDNO-3 SS | 5758 | CONSTRUCTION OF MEDNO-3 SS-the residual amount of FO Cable task no #2.38 | APPROVED | No | 2025-02-02 | Abas, Mohammed Fekry | 2025-02-03 | 2025-02-05 |  |  |  | 5500 | 6364 | 1 | STANDARD | AMWAJ TELECOMMUNICATION MFG. CO. | SAR | 5500 | APPROVED |  |  | 2025-03-13 | 0 | 36 | Alhadi, Khalid | -45693 | 36
105-112 | CONSTRUCTION OF MEDNO-3 SS | 6016 | CONSTRUCTION OF MEDNO-3 SS-HV Termination Kit & Joints ( 1200 , 630 ) # 2.39 2.40 | REJECTED | No | 2025-02-20 | Aboukhalifa, Mostafa Aly | 2025-07-31 |  |  | 2025-08-03 | the total quantity is modified based on submitted schematic drawings | 432036 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
105-112 | CONSTRUCTION OF MEDNO-3 SS | 6158 | CONSTRUCTION OF MEDNO-3 SS-GIS Degassing and gassing | APPROVED | No | 2025-03-11 | Abas, Mohammed Fekry | 2025-03-13 | 2025-03-17 |  |  | GIS Degassing and gassing for all remote ends | 293000 | 7000 | 0 | STANDARD | Tayma Tech Co.,Ltd.(S) | SAR | 293000 | APPROVED |  |  | 2025-04-16 | 0 | 30 | Alhadi, Khalid | -45733 | 30
105-112 | CONSTRUCTION OF MEDNO-3 SS | 6222 | CONSTRUCTION OF MEDNO-3 SS-scada / sas modification | APPROVED | No | 2025-03-20 | Abas, Mohammed Fekry | 2025-03-24 | 2025-03-25 |  |  |  | 300000 | 7055 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 285000 | APPROVED |  |  | 2025-07-03 | 15000 | 100 | Abdulqader, Ahmed Abdulhalim | -45741 | 100
105-112 | CONSTRUCTION OF MEDNO-3 SS | 6450 | CONSTRUCTION OF MEDNO-3 SS-Ring CT | APPROVED | No | 2025-04-24 | Abas, Mohammed Fekry | 2025-04-28 | 2025-04-28 |  |  | Please note that the PO was held till finalizing technical approval from SEC | 12000 | 7356 | 0 | STANDARD | S.T.E. STRUMENTI TRASFORMATORI ELETTRICI S.R.L. Company | EUR | 9072 | APPROVED |  |  | 2025-06-15 | 2928 | 48 | Alhadi, Khalid | -45775 | 48
105-112 | CONSTRUCTION OF MEDNO-3 SS | 6454 | CONSTRUCTION OF MEDNO-3 SS-installation works inside substations | REJECTED | No | 2025-04-26 | Aboukhalifa, Mostafa Aly | 2025-04-26 |  |  | 2025-04-26 | the BOQ is attached , the drawing link is attached | 1000000 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
105-112 | CONSTRUCTION OF MEDNO-3 SS | 6487 | CONSTRUCTION OF MEDNO-3 SS-Cable Termination & Joints | APPROVED | No | 2025-04-30 | Abas, Mohammed Fekry | 2025-05-01 | 2025-05-04 |  |  |  | 554700 | 6625 | 0 | STANDARD | PFISTERER Switzerland AG | EUR | 535860.23 | APPROVED |  |  | 2025-05-25 | 18839.77 | 21 | Alhadi, Khalid | -45781 | 21
105-112 | CONSTRUCTION OF MEDNO-3 SS | 6496 | CONSTRUCTION OF MEDNO-3 SS-Fault Recorder Renaming & Modifications for Taiba, Nasr & Isuni | REJECTED | No | 2025-05-01 | Aboukhalifa, Mostafa Aly | 2025-05-01 |  |  | 2025-05-01 | Kindly find the attached file for all supported data | 50000 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
105-112 | CONSTRUCTION OF MEDNO-3 SS | 6614 | CONSTRUCTION OF MEDNO-3 SS-Power Cable Supports & accessories | RETURNED | No | 2025-05-14 | Alhadi, Khalid | 2025-09-07 | 2025-05-19 | 2025-09-07 |  | The line was revised by a new line through change order. | 3305 | 7247 | 0 | STANDARD | Power Solution Industries | SAR | 3305 | APPROVED |  |  | 2025-05-22 | 0 |  | Alhadi, Khalid | -45796 | 3
105-112 | CONSTRUCTION OF MEDNO-3 SS | 6614 | CONSTRUCTION OF MEDNO-3 SS-Power Cable Supports & accessories | RETURNED | No | 2025-05-14 | Alhadi, Khalid | 2025-09-07 | 2025-05-19 | 2025-09-07 |  | The line was revised by a new line through change order. | 1440 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45796 | -45796
105-112 | CONSTRUCTION OF MEDNO-3 SS | 6616 | CONSTRUCTION OF MEDNO-3 SS-Earthing and grounding equipment | APPROVED | No | 2025-05-14 | Abas, Mohammed Fekry | 2025-05-19 | 2025-05-19 |  |  | The PR is issued based on the approved DPO | 29500 | 7279 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 29500 | APPROVED |  |  | 2025-05-22 | 0 | 3 | Alhadi, Khalid | -45796 | 3
105-112 | CONSTRUCTION OF MEDNO-3 SS | 6617 | CONSTRUCTION OF MEDNO-3 SS-Addendum to PR( 6616 ) material transportation | APPROVED | No | 2025-05-14 | Abas, Mohammed Fekry | 2025-05-19 | 2025-05-19 |  |  | Kindly note that this PR is addendum to PR no 6616 | 500 | 7279 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 500 | APPROVED |  |  | 2025-05-22 | 0 | 3 | Alhadi, Khalid | -45796 | 3
105-112 | CONSTRUCTION OF MEDNO-3 SS | 6618 | CONSTRUCTION OF MEDNO-3 SS-Civil Work Service order ( Almayal ) | APPROVED | No | 2025-05-14 | Abas, Mohammed Fekry | 2025-05-19 | 2025-05-20 |  |  | service order #'7143-HV-1459/1 item number 3&4 | 590500 | 7328 | 0 | STANDARD | Al Mayal Contracting Co Ltd. | SAR | 590500 | APPROVED |  |  | 2025-05-29 | 0 | 9 | Abuhammad, Samir | -45797 | 9
105-112 | CONSTRUCTION OF MEDNO-3 SS | 6619 | CONSTRUCTION OF MEDNO-3 SS-The Civil Subcontractor SOW based on Service order | APPROVED | No | 2025-05-14 | Abas, Mohammed Fekry | 2025-05-19 | 2025-05-20 |  |  | service order #'7143-HV-1459/1 item numbers 1,2,5,6&7 | 3904000 | 7328 | 0 | STANDARD | Al Mayal Contracting Co Ltd. | SAR | 3904000 | APPROVED |  |  | 2025-05-29 | 0 | 9 | Abuhammad, Samir | -45797 | 9
105-112 | CONSTRUCTION OF MEDNO-3 SS | 6702 | CONSTRUCTION OF MEDNO-3 SS-Ring CT Transportation | APPROVED | No | 2025-05-25 | Abas, Mohammed Fekry | 2025-06-01 | 2025-06-02 |  |  | kindly note that this PR is issued based on Procurement request | 4000 | 7356 | 0 | STANDARD | S.T.E. STRUMENTI TRASFORMATORI ELETTRICI S.R.L. Company | EUR | 3780 | APPROVED |  |  | 2025-06-15 | 220 | 13 | Alhadi, Khalid | -45810 | 13
105-112 | CONSTRUCTION OF MEDNO-3 SS | 6703 | CONSTRUCTION OF MEDNO-3 SS-Radar Scan for SEC Modified Power Cable route | APPROVED | No | 2025-05-25 | Abas, Mohammed Fekry | 2025-06-01 | 2025-06-02 |  |  |  | 30000 | 7424 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 10000 | APPROVED |  |  | 2025-07-01 | 20000 | 29 | Alhadi, Khalid | -45810 | 29
105-112 | CONSTRUCTION OF MEDNO-3 SS | 6866 | CONSTRUCTION OF MEDNO-3 SS-Additional quantity for the 1x300 LV cables | APPROVED | No | 2025-06-23 | Abas, Mohammed Fekry | 2025-06-24 | 2025-06-25 |  |  | kindly note that , these quantities are delivered to site and RMI's signed and we need to issue the payment to the supplier with the correct quantity. | 33578.6 | 5050 | 1 | STANDARD | Riyadh Cables Group Company | SAR | 33578.6 | APPROVED |  |  | 2025-07-29 | 0 | 34 | Alhadi, Khalid | -45833 | 34
105-112 | CONSTRUCTION OF MEDNO-3 SS | 6885 | CONSTRUCTION OF MEDNO-3 SS-LV & Control Cables | APPROVED | No | 2025-06-24 | Abas, Mohammed Fekry | 2025-06-29 | 2025-06-29 |  |  | this PR is raised based on Procurement request as they returned PR# 6181 | 124644.04 | 7444 | 0 | STANDARD | ALFANAR CO | SAR | 124644.04 | APPROVED |  |  | 2025-07-24 | 0 | 25 | Alhadi, Khalid | -45837 | 25
105-112 | CONSTRUCTION OF MEDNO-3 SS | 6885 | CONSTRUCTION OF MEDNO-3 SS-LV & Control Cables | APPROVED | No | 2025-06-24 | Abas, Mohammed Fekry | 2025-06-29 | 2025-06-29 |  |  | this PR is raised based on Procurement request as they returned PR# 6181 | 124644.04 | 7444 | 2 | STANDARD | ALFANAR CO | SAR | 98726.5 | REQUIRES REAPPROVAL |  |  |  | 25917.54 | 217 | Alhadi, Khalid | -45837 | -45837
105-112 | CONSTRUCTION OF MEDNO-3 SS | 6900 | CONSTRUCTION OF MEDNO-3 SS-Validation of optional scope of PO 6363 by suppling NLR | APPROVED | No | 2025-06-25 | Abas, Mohammed Fekry | 2025-06-29 | 2025-07-01 |  |  | kindly note that this PR os to Validate of optional scope of PO # 6363 by suppling 24 pcs NLR | 28800 | 6363 | 2 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 28800 | APPROVED |  |  | 2025-10-05 | 0 | 96 | Alhadi, Khalid | -45839 | 96
105-112 | CONSTRUCTION OF MEDNO-3 SS | 7057 | CONSTRUCTION OF MEDNO-3 SS-Cables quantities for PO 5050 | APPROVED | No | 2025-07-10 | Abas, Mohammed Fekry | 2025-07-15 | 2025-07-16 |  |  | kindly note that the supplier is holding our residual quantities for 1200 till finalizing his payment and the 630 & all 300 are fully delivered to the site & we need to finalize his payment | 14652469.86 | 5050 | 1 | STANDARD | Riyadh Cables Group Company | SAR | 14652469.86 | APPROVED |  |  | 2025-07-29 | 0 | 13 | Alhadi, Khalid | -45854 | 13
105-112 | CONSTRUCTION OF MEDNO-3 SS | 7225 | CONSTRUCTION OF MEDNO-3 SS-Pr to fianlize the PO of termination services with the subcontractor | APPROVED | No | 2025-07-27 | Abas, Mohammed Fekry | 2025-08-04 | 2025-08-04 |  |  | Kindly note that this PR to finalize DPO of termination services | 151600 | 7553 | 0 | STANDARD | Pfisterer Saudi Arabia LLC | SAR | 151600 | APPROVED | 2026-01-14 | 2026-01-19 | 2026-01-21 | 0 | 170 | Alhadi, Khalid | 168 | 170
105-112 | CONSTRUCTION OF MEDNO-3 SS | 7263 | CONSTRUCTION OF MEDNO-3 SS-Power Cable Supports as per design | APPROVED | No | 2025-08-03 | Abas, Mohammed Fekry | 2025-08-07 | 2025-08-10 |  |  |  | 10760 | 7247 | 2 | STANDARD | Power Solution Industries | SAR | 10760 | APPROVED |  |  | 2025-08-28 | 0 | 18 | Alhadi, Khalid | -45879 | 18
105-112 | CONSTRUCTION OF MEDNO-3 SS | 7296 | CONSTRUCTION OF MEDNO-3 SS-remaining quantity to riyadh cable for PO 5050 | APPROVED | No | 2025-08-06 | Abas, Mohammed Fekry | 2025-08-11 | 2025-08-11 |  |  | this amount to finalize the quantity as per the manufactured quantity to riyadh | 425826.12 | 5050 | 2 | STANDARD | Riyadh Cables Group Company | SAR | 425826.12 | APPROVED |  |  | 2025-08-31 | 0 | 20 | Alhadi, Khalid | -45880 | 20
105-112 | CONSTRUCTION OF MEDNO-3 SS | 7439 | Installation SOW | REJECTED | No | 2025-08-24 | Aboukhalifa, Mostafa Aly | 2025-08-24 |  |  | 2025-08-24 | the pr is resubmitted as per Eng.majed recommendations | 2500 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-112 | CONSTRUCTION OF MEDNO-3 SS | 7440 | installation SOW | RETURNED | No | 2025-08-24 | Alhadi, Khalid | 2025-10-12 | 2025-08-25 | 2025-10-12 |  | It will be executed in-house as per management instruction | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45894 | -45894
105-112 | CONSTRUCTION OF MEDNO-3 SS | 7453 | Nasr SS Scada Modification | APPROVED | No | 2025-08-24 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | the required data are available in this link :https://drive.google.com/drive/folders/1Y5pEDmzCeXAzU-dDFabrB8kkfEsJ-9kY?usp=sharing | 0 | 7915 | 0 | STANDARD | INNOVATIVE SYSTEMS COMPANY LTD. | SAR | 65000 | APPROVED |  |  | 2025-12-23 | -65000 | 120 | Alhadi, Khalid | -45894 | 120
105-112 | CONSTRUCTION OF MEDNO-3 SS | 7581 | Jointing & termination services | RETURNED | No | 2025-08-31 | Alhadi, Khalid | 2025-09-02 | 2025-09-01 | 2025-09-02 |  | Price can't change, Line type shall be "services by quantity" to enable price change. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45901 | -45901
105-112 | CONSTRUCTION OF MEDNO-3 SS | 7717 | Control Cables | APPROVED | No | 2025-09-10 | Abas, Mohammed Fekry | 2025-09-11 | 2025-09-12 |  |  |  | 0 | 7444 | 1 | STANDARD | ALFANAR CO | SAR | 22764.85 | APPROVED |  |  | 2025-10-15 | -22764.85 | 33 | Alhadi, Khalid | -45912 | 33
105-112 | CONSTRUCTION OF MEDNO-3 SS | 7717 | Control Cables | APPROVED | No | 2025-09-10 | Abas, Mohammed Fekry | 2025-09-11 | 2025-09-12 |  |  |  | 0 | 7444 | 2 | STANDARD | ALFANAR CO | SAR | 17637 | REQUIRES REAPPROVAL |  |  |  | -17637 | 142 | Alhadi, Khalid | -45912 | -45912
105-112 | CONSTRUCTION OF MEDNO-3 SS | 7739 | Panels Steel Support | APPROVED | No | 2025-09-15 | Abas, Mohammed Fekry | 2025-09-15 | 2025-09-16 |  |  | the required manufactured dwg are uploaded in the attached file link | 0 | 7837 | 0 | STANDARD | Fursan Construction Industry Factory Industry Factory | SAR | 30425 | APPROVED |  |  | 2025-11-02 | -30425 | 47 | Alhadi, Khalid | -45916 | 47
105-112 | CONSTRUCTION OF MEDNO-3 SS | 8005 | Internal Telecom Cables | APPROVED | No | 2025-10-27 | Abas, Mohammed Fekry | 2025-10-27 | 2025-10-27 |  |  | all required docs in https://drive.google.com/drive/folders/1UnDAOGXMS1B04WCYn9DvR78BaBxgaJre?usp=sharing | 0 | 8029 | 0 | STANDARD | NAIF AWADH LAVI AL-HUDHAYLI AL-BAQMI For Contracting. | SAR | 214112.8 | IN PROCESS | 2026-01-24 | 2026-01-28 |  | -85712.8 | 97 | Mohammed, Mohammed Adel Fahmy | 93 | -45957
105-112 | CONSTRUCTION OF MEDNO-3 SS | 8005 | Internal Telecom Cables | APPROVED | No | 2025-10-27 | Abas, Mohammed Fekry | 2025-10-27 | 2025-10-27 |  |  | all required docs in https://drive.google.com/drive/folders/1UnDAOGXMS1B04WCYn9DvR78BaBxgaJre?usp=sharing | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45957 | -45957
105-112 | CONSTRUCTION OF MEDNO-3 SS | 8006 | Rent of dilo machine for 1 month | RETURNED | No | 2025-10-20 | Alhadi, Khalid | 2025-11-03 | 2025-10-21 | 2025-11-03 |  | Secured Internally through Facility Dep. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45951 | -45951
105-112 | CONSTRUCTION OF MEDNO-3 SS | 8061 | Civil Scope | INCOMPLETE | No | [6 empty] | Secured Internally through Facility Dep. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
105-112 | CONSTRUCTION OF MEDNO-3 SS | 8449 | LV cables for AC-DC Modification | APPROVED | No | 2025-12-04 | Abas, Mohammed Fekry | 2025-12-07 | 2025-12-09 |  |  | this Pr is issued due to return of PR no 8076 | 0 | 7444 | 2 | STANDARD | ALFANAR CO | SAR | 32307.5 | REQUIRES REAPPROVAL |  |  |  | -32307.5 | 54 | Alhadi, Khalid | -46000 | -46000
105-112 | CONSTRUCTION OF MEDNO-3 SS | 8449 | LV cables for AC-DC Modification | APPROVED | No | 2025-12-04 | Abas, Mohammed Fekry | 2025-12-07 | 2025-12-09 |  |  | this Pr is issued due to return of PR no 8076 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46000 | -46000
105-112 | CONSTRUCTION OF MEDNO-3 SS | 8586 | GPS Device | APPROVED | No | 2025-12-25 | Abas, Mohammed Fekry | 2025-12-29 | 2026-01-01 |  |  | this pr to purshase a GPS device for medno project | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46023 | -46023
105-112 | CONSTRUCTION OF MEDNO-3 SS | 8587 | rental manpower for medno project | REJECTED | No | 2025-12-25 | Alfaiya, Majed | 2025-12-28 | 2025-12-28 |  | 2025-12-28 |  | 7 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46019 | -46019
105-112 | CONSTRUCTION OF MEDNO-3 SS | 8653 | Civil works UGC | APPROVED | No | 2026-01-06 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-13 |  |  | as per eng fekry instructions to issue the service order the total price shall be replace the qty | 0 | 7143 | 0 | BLANKET | Al Mayal Contracting Co Ltd. | SAR | 0 | APPROVED |  |  | 2025-04-24 | 0 | -264 | Abuhammad, Samir | -46035 | -264
105-112 | CONSTRUCTION OF MEDNO-3 SS | 8721 | Jointing SC | APPROVED | No | 2026-01-15 | Abas, Mohammed Fekry | 2026-01-19 | 2026-01-21 |  |  | this PR is replacement for approved PR no 7627 | 0 | 15034 | 0 | STANDARD | Al-Sharhan Company for Contracting | SAR | 255500 | INCOMPLETE |  |  |  | -255500 | 11 | Alhadi, Khalid | -46043 | -46043
105-112 | CONSTRUCTION OF MEDNO-3 SS | 8721 | Jointing SC | APPROVED | No | 2026-01-15 | Abas, Mohammed Fekry | 2026-01-19 | 2026-01-21 |  |  | this PR is replacement for approved PR no 7627 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46043 | -46043
105-112 | CONSTRUCTION OF MEDNO-3 SS | 8739 | Civil works UGC | APPROVED | No | 2026-01-20 | Abas, Mohammed Fekry | 2026-01-21 | 2026-01-25 |  |  | this pr to replace item no 1 in the approved PR 8653 | 0 | 7143 | 0 | BLANKET | Al Mayal Contracting Co Ltd. | SAR | 0 | APPROVED |  |  | 2025-04-24 | 0 | -276 | Abuhammad, Samir | -46047 | -276
105-112 | CONSTRUCTION OF MEDNO-3 SS | 8746 | service of termination of fiber optic | APPROVED | No | 2026-01-20 | Abas, Mohammed Fekry | 2026-01-22 | 2026-01-25 |  |  | this PR is for installation services of approved PR no 8005 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Mohammed Adel Fahmy | -46047 | -46047
105-113 | PS Systems for Sindalah - NEOM | 2099 | PS Systems for Sindalah - NEOM-Supply and PS of Firewall for Sindalah project-Dummy PO#8552-0 | APPROVED | No | 2024-01-07 | Abas, Mohammed Fekry | 2024-01-08 | 2024-01-09 |  |  |  | 2866547 | 4962 | 0 | STANDARD | REDINGTON SAUDI ARABIA DISTRIBUTION CO. | SAR | 2866547 | APPROVED |  |  | 2024-01-23 | 0 | 14 | Abuhammad, Samir | -45300 | 14
105-113 | PS Systems for Sindalah - NEOM | 2121 | PS Systems for Sindalah - NEOM-Middleware application & Integration srvices | APPROVED | No | 2024-01-08 | Abas, Mohammed Fekry | 2024-01-09 | 2024-01-09 |  |  |  | 3013500 | 4963 | 0 | STANDARD | Intelligent Business for Information Technology | SAR | 3000000 | APPROVED |  |  | 2024-01-28 | 13500 | 19 | Abuhammad, Samir | -45300 | 19
105-113 | PS Systems for Sindalah - NEOM | 2122 | PS Systems for Sindalah - NEOM-PCIM Solution - OODA | APPROVED | No | 2024-01-08 | Abas, Mohammed Fekry | 2024-01-09 | 2024-01-09 |  |  |  | 4122259.05 | 4964 | 0 | STANDARD | Zone of Multi Resources ZMR | SAR | 4122259.05 | APPROVED |  |  | 2024-01-29 | 0 | 20 | Abuhammad, Samir | -45300 | 20
105-113 | PS Systems for Sindalah - NEOM | 2122 | PS Systems for Sindalah - NEOM-PCIM Solution - OODA | APPROVED | No | 2024-01-08 | Abas, Mohammed Fekry | 2024-01-09 | 2024-01-09 |  |  |  | 4122259.05 | 5769 | 0 | STANDARD | Obvious Technologies. | USD | 4018387.5 | APPROVED |  |  | 2024-07-25 | 103871.55 | 198 | Abuhammad, Samir | -45300 | 198
105-113 | PS Systems for Sindalah - NEOM | 2131 | PS Systems for Sindalah - NEOM-CCTV Video Wall Supply and services | APPROVED | No | 2024-01-09 | Abas, Mohammed Fekry | 2024-01-11 | 2024-01-14 |  |  |  | 12818189.6 | 4991 | 0 | STANDARD | Zamil Group Trade & Service Co | SAR | 12818189.6 | APPROVED |  |  | 2024-01-29 | 0 | 15 | Abuhammad, Samir | -45305 | 15
105-113 | PS Systems for Sindalah - NEOM | 2171 | PS Systems for Sindalah - NEOM-Supply of F5 - Network Equipment and serices | APPROVED | No | 2024-01-15 | Abas, Mohammed Fekry | 2024-01-22 | 2024-01-22 |  |  |  | 574730.47 | 5007 | 0 | STANDARD | Starlink MDMC Arabian Trading Co | SAR | 574709 | APPROVED |  |  | 2024-03-03 | 21.47 | 41 | Abuhammad, Samir | -45313 | 41
105-113 | PS Systems for Sindalah - NEOM | 2183 | PS Systems for Sindalah - NEOM-Supply Radar and VHF ( Tianhe ) | APPROVED | No | 2024-01-16 | Abas, Mohammed Fekry | 2024-01-22 | 2024-01-22 |  |  |  | 2518900 | 5006 | 0 | STANDARD | ARABIAN DEVELOPMENT AND MARKETING CO.LTD. | SAR | 2518899 | APPROVED |  |  | 2024-02-25 | 1 | 34 | Abuhammad, Samir | -45313 | 34
105-113 | PS Systems for Sindalah - NEOM | 2220 | PS Systems for Sindalah - NEOM-Forescout - Network Security Supply and services | RETURNED | No | 2024-01-18 | Abuhammad, Samir | 2024-05-15 | 2024-01-22 | 2024-05-15 |  | As per PM request. | 364756 | 5005 | 0 | STANDARD | REDINGTON SAUDI ARABIA DISTRIBUTION CO. | SAR | 364756 | APPROVED |  |  | 2024-04-15 | 0 |  | Abuhammad, Samir | -45313 | 84
105-113 | PS Systems for Sindalah - NEOM | 2220 | PS Systems for Sindalah - NEOM-Forescout - Network Security Supply and services | RETURNED | No | 2024-01-18 | Abuhammad, Samir | 2024-05-15 | 2024-01-22 | 2024-05-15 |  | As per PM request. | 50000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45313 | -45313
105-113 | PS Systems for Sindalah - NEOM | 2563 | PS Systems for Sindalah - NEOM-Supply of Servers and computer supply and licenses (Dell) | APPROVED | No | 2024-02-14 | Abas, Mohammed Fekry | 2024-02-19 | 2024-02-21 |  |  |  | 821225.15 | 5124 | 0 | STANDARD | AKLANIAT TECHNOLOGIES LTD. | SAR | 821225.14 | APPROVED |  |  | 2024-04-17 | 0.01 | 56 | Abuhammad, Samir | -45343 | 56
105-113 | PS Systems for Sindalah - NEOM | 2588 | PS Systems for Sindalah - NEOM-Supply of Network Equipment & Network Services ( Huawei ) | APPROVED | No | 2024-02-18 | Abas, Mohammed Fekry | 2024-02-19 | 2024-02-21 |  |  |  | 1666145.45 | 5122 | 0 | STANDARD | REDINGTON SAUDI ARABIA DISTRIBUTION CO. | SAR | 1666145 | APPROVED |  |  | 2024-03-07 | 0.45 | 15 | Abuhammad, Samir | -45343 | 15
105-113 | PS Systems for Sindalah - NEOM | 2795 | PS Systems for Sindalah - NEOM-Additional CCTV | APPROVED | No | 2024-03-05 | Abas, Mohammed Fekry | 2024-03-07 | 2024-03-07 |  |  |  | 694402 | 5218 | 0 | STANDARD | Zamil Group Trade & Service Co | SAR | 694402 | APPROVED |  |  | 2024-05-01 | 0 | 55 | Abuhammad, Samir | -45358 | 55
105-113 | PS Systems for Sindalah - NEOM | 2798 | PS Systems for Sindalah - NEOM-CAD Solution Application Modules | APPROVED | No | 2024-03-06 | Abas, Mohammed Fekry | 2024-03-10 | 2024-03-10 |  |  |  | 718775 | 5220 | 0 | STANDARD | Atheeb Intergraph Saudi Company | SAR | 718775 | APPROVED |  |  | 2024-05-01 | 0 | 52 | Abuhammad, Samir | -45361 | 52
105-113 | PS Systems for Sindalah - NEOM | 3007 | PS Systems for Sindalah - NEOM-Mobile tower(Cow) For Radar Budget Line 1.11 Task No. 2.10 | APPROVED | No | 2024-04-07 | Abas, Mohammed Fekry | 2024-04-20 | 2024-04-23 |  |  |  | 468000 | 5432 | 0 | STANDARD | MADAF TRADING & CONTRACTING CO. LTD | SAR | 468000 | APPROVED |  |  | 2024-05-13 | 0 | 20 | Abuhammad, Samir | -45405 | 20
105-113 | PS Systems for Sindalah - NEOM | 3008 | PS Systems for Sindalah - NEOM-Solar System For Mobile tower(Cow) & Radar Budget Line 1.11 Task No. 2.10 | APPROVED | No | 2024-04-07 | Abas, Mohammed Fekry | 2024-04-20 | 2024-04-23 |  |  |  | 314735.5 | 5433 | 0 | STANDARD | Shabkat Al Mansurah Co.for Electric Contracting | SAR | 309335 | APPROVED |  |  | 2024-05-11 | 5400.5 | 18 | Abuhammad, Samir | -45405 | 18
105-113 | PS Systems for Sindalah - NEOM | 3009 | PS Systems for Sindalah - NEOM-Laptop Budget line 1.11, Task 2.10 | APPROVED | No | 2024-04-07 | Abas, Mohammed Fekry | 2024-04-20 | 2024-04-23 |  |  |  | 62499 | 5439 | 0 | STANDARD | Frontline Investment Company | SAR | 62499 | APPROVED |  |  | 2024-05-07 | 0 | 14 | Abuhammad, Samir | -45405 | 14
105-113 | PS Systems for Sindalah - NEOM | 3010 | PS Systems for Sindalah - NEOM-Firewall - Budget line 1.11 Task No. 2.10 | APPROVED | No | 2024-04-07 | Abas, Mohammed Fekry | 2024-04-21 | 2024-04-23 |  |  |  | 84747.68 | 5438 | 0 | STANDARD | REDINGTON SAUDI ARABIA DISTRIBUTION CO. | SAR | 84698 | APPROVED |  |  | 2024-05-21 | 49.68 | 28 | Abuhammad, Samir | -45405 | 28
105-113 | PS Systems for Sindalah - NEOM | 3031 | PS Systems for Sindalah - NEOM-Telecom Equipment Installation on COW - Task NO 1.36 | APPROVED | No | 2024-04-15 | Abas, Mohammed Fekry | 2024-04-21 | 2024-04-23 |  |  |  | 41000 | 5586 | 0 | STANDARD | MADAF TRADING & CONTRACTING CO. LTD | SAR | 41000 | APPROVED |  |  | 2024-06-10 | 0 | 48 | Abuhammad, Samir | -45405 | 48
105-113 | PS Systems for Sindalah - NEOM | 3294 | PS Systems for Sindalah - NEOM-Installation of Video Wall | REJECTED | No | 2024-05-05 | Issa, Amr Ali | 2024-05-08 | 2024-05-06 |  | 2024-05-08 |  | 85050 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45418 | -45418
105-113 | PS Systems for Sindalah - NEOM | 3354 | PS Systems for Sindalah - NEOM-Installation of Video Wall | APPROVED | No | 2024-05-09 | Abas, Mohammed Fekry | 2024-05-13 | 2024-05-14 |  |  |  | 85000 | 5631 | 0 | STANDARD | Advance International Company | SAR | 74000 | APPROVED |  |  | 2024-06-03 | 11000 | 20 | Abuhammad, Samir | -45426 | 20
105-113 | PS Systems for Sindalah - NEOM | 3533 | PS Systems for Sindalah - NEOM-Supply of Cisco Switches as per neom requirement, BL 1.11 | RETURNED | No | 2024-05-29 | Abuhammad, Samir | 2024-08-07 | 2024-06-03 | 2024-08-07 |  | As per PM request. | 81534.83 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45446 | -45446
105-113 | PS Systems for Sindalah - NEOM | 3534 | PS Systems for Sindalah - NEOM-Supply of Microsoft Licenses | APPROVED | No | 2024-05-29 | Abas, Mohammed Fekry | 2024-06-02 | 2024-06-03 |  |  |  | 678726 | 5694 | 0 | STANDARD | AL FALAK ELECTRONICS | SAR | 572769 | APPROVED |  |  | 2024-08-28 | 105957 | 86 | Abuhammad, Samir | -45446 | 86
105-113 | PS Systems for Sindalah - NEOM | 3536 | PS Systems for Sindalah - NEOM-Active equipment installtion in Sindalah DC. | APPROVED | No | 2024-05-29 | Abas, Mohammed Fekry | 2024-06-02 | 2024-06-03 |  |  |  | 200000 | 5696 | 0 | STANDARD | Advance International Company | SAR | 112820 | APPROVED |  |  | 2024-07-15 | 87180 | 42 | Abuhammad, Samir | -45446 | 42
105-113 | PS Systems for Sindalah - NEOM | 3551 | PS Systems for Sindalah - NEOM-Supply of Fingerprint Scanner & Documents reader | APPROVED | No | 2024-06-02 | Abas, Mohammed Fekry | 2024-06-03 | 2024-06-03 |  |  |  | 244980 | 5677 | 0 | STANDARD | Alyam Technical Trading Company | SAR | 244980 | APPROVED |  |  | 2024-06-11 | 0 | 8 | Abuhammad, Samir | -45446 | 8
105-113 | PS Systems for Sindalah - NEOM | 3552 | PS Systems for Sindalah - NEOM-Supply Of PC's | APPROVED | No | 2024-06-02 | Abas, Mohammed Fekry | 2024-06-05 | 2024-06-06 |  |  |  | 8220 | 5697 | 0 | STANDARD | Golden Technology trading Company. | SAR | 8220 | APPROVED |  |  | 2024-06-13 | 0 | 7 | Abuhammad, Samir | -45449 | 7
105-113 | PS Systems for Sindalah - NEOM | 3610 | PS Systems for Sindalah - NEOM-Outdoor Telecom cabinet, 21U with cooling 500W IP65 - Task 1.36 | APPROVED | No | 2024-06-06 | Abas, Mohammed Fekry | 2024-06-06 | 2024-06-07 |  |  |  | 25000 | 5698 | 0 | STANDARD | Integrated Network Solutions Trading Est. | SAR | 20770.65 | APPROVED |  |  | 2024-06-23 | 4229.35 | 16 | Abuhammad, Samir | -45450 | 16
105-113 | PS Systems for Sindalah - NEOM | 3670 | PS Systems for Sindalah - NEOM-Installation of Screening machine (X-Ray) Task No 1.36 | APPROVED | No | 2024-06-24 | Abas, Mohammed Fekry | 2024-07-03 | 2024-07-03 |  |  |  | 260000 | 5874 | 0 | STANDARD | High Point Technology Co, | SAR | 255000 | APPROVED |  |  | 2024-08-15 | 5000 | 43 | Abuhammad, Samir | -45476 | 43
105-113 | PS Systems for Sindalah - NEOM | 3770 | PS Systems for Sindalah - NEOM-Supply and installation of Fence for Radar | APPROVED | No | 2024-07-04 | Abas, Mohammed Fekry | 2024-07-10 | 2024-07-11 |  |  |  | 40000 | 5812 | 0 | STANDARD | Dorat Alshbk for Contracting | SAR | 39520 | APPROVED |  |  | 2024-08-05 | 480 | 25 | Abuhammad, Samir | -45484 | 25
105-113 | PS Systems for Sindalah - NEOM | 3770 | PS Systems for Sindalah - NEOM-Supply and installation of Fence for Radar | APPROVED | No | 2024-07-04 | Abas, Mohammed Fekry | 2024-07-10 | 2024-07-11 |  |  |  | 40000 | 5812 | 1 | STANDARD | Dorat Alshbk for Contracting | SAR | 37900 | APPROVED |  |  | 2024-10-08 | 2100 | 89 | Abuhammad, Samir | -45484 | 89
105-113 | PS Systems for Sindalah - NEOM | 3931 | PS Systems for Sindalah - NEOM-Cable accessories needed for installation- Supply of RJ45 SFP | APPROVED | No | 2024-07-16 | Abas, Mohammed Fekry | 2024-07-18 | 2024-07-21 |  |  |  | 25995.15 | 5865 | 0 | STANDARD | Integrated Network Solutions Trading Est. | SAR | 25965 | APPROVED |  |  | 2024-08-05 | 30.15 | 15 | Abuhammad, Samir | -45494 | 15
105-113 | PS Systems for Sindalah - NEOM | 4114 | PS Systems for Sindalah - NEOM-Supply of Huawei Routers and New Connectors | APPROVED | No | 2024-08-07 | Abas, Mohammed Fekry | 2024-08-14 | 2024-08-14 |  |  |  | 221201.72 | 5971 | 0 | STANDARD | REDINGTON SAUDI ARABIA DISTRIBUTION CO. | SAR | 221201.72 | APPROVED |  |  | 2024-08-22 | 0 | 8 | Abuhammad, Samir | -45518 | 8
105-113 | PS Systems for Sindalah - NEOM | 4117 | PS Systems for Sindalah - NEOM-Supply of 250 ACS FR pad | APPROVED | No | 2024-08-07 | Abas, Mohammed Fekry | 2024-08-08 | 2024-08-08 |  |  |  | 466378 | 5968 | 0 | STANDARD | Zamil Group Trade & Service Co | SAR | 466378 | APPROVED |  |  | 2024-08-22 | 0 | 14 | Abuhammad, Samir | -45512 | 14
105-113 | PS Systems for Sindalah - NEOM | 4225 | PS Systems for Sindalah - NEOM-Supply of PCIM BMS Connector | APPROVED | No | 2024-08-20 | Abas, Mohammed Fekry | 2024-08-22 | 2024-08-25 |  |  |  | 179100 | 6091 | 0 | STANDARD | Obvious Technologies. | USD | 179100 | APPROVED |  |  | 2024-09-05 | 0 | 11 | Abuhammad, Samir | -45529 | 11
105-113 | PS Systems for Sindalah - NEOM | 4451 | PS Systems for Sindalah - NEOM-Installtion of Neom Bay jetty - CCTV system | APPROVED | No | 2024-09-15 | Abas, Mohammed Fekry | 2024-09-24 | 2024-09-24 |  |  |  | 96425 | 6226 | 0 | STANDARD | Tabsher Est for operation and maintenance. | SAR | 77965 | APPROVED |  |  | 2024-09-26 | 18460 | 2 | Abuhammad, Samir | -45559 | 2
105-113 | PS Systems for Sindalah - NEOM | 4515 | PS Systems for Sindalah - NEOM-Supply of Outdoor Pole Mounted Clouser | APPROVED | No | 2024-09-24 | Abas, Mohammed Fekry | 2024-09-29 | 2024-09-29 |  |  |  | 10000 | 6269 | 0 | STANDARD | Integrated Network Solutions Trading Est. | SAR | 6750 | APPROVED |  |  | 2024-10-08 | 3250 | 9 | Abuhammad, Samir | -45564 | 9
105-113 | PS Systems for Sindalah - NEOM | 4761 | PS Systems for Sindalah - NEOM-Supply of 15 Biometric Tablets | RETURNED | No | 2024-10-21 | Abuhammad, Samir | 2024-12-02 | 2024-10-27 | 2024-12-02 |  | scope not confirmed by the client , once is ready submit again | 357163.3 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45592 | -45592
105-113 | PS Systems for Sindalah - NEOM | 4865 | PS Systems for Sindalah - NEOM-Required material to power up the system | APPROVED | No | 2024-11-07 | Abas, Mohammed Fekry | 2024-11-11 | 2024-11-12 |  |  |  | 18460 | 6486 | 0 | STANDARD | Tabsher Est for operation and maintenance. | SAR | 18460 | APPROVED |  |  | 2024-11-28 | 0 | 16 | Abuhammad, Samir | -45608 | 16
105-113 | PS Systems for Sindalah - NEOM | 5117 | PS Systems for Sindalah - NEOM-Galaxy tab S 2 PCs | REJECTED | No | 2024-12-03 | Mraish, Fahed Mhd Yaser | 2024-12-03 |  |  | 2024-12-04 | Please revised the amount as per the quote | 9086 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-113 | PS Systems for Sindalah - NEOM | 5126 | PS Systems for Sindalah - NEOM-Ras Gasabah Lounge - CCTV Solution | REJECTED | No | 2024-12-04 | Mraish, Fahed Mhd Yaser | 2024-12-04 |  |  | 2024-12-04 | Please revised the amount as per the discount | 744253 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-113 | PS Systems for Sindalah - NEOM | 5131 | PS Systems for Sindalah - NEOM-Ras Gasabah Lounge - CCTV Solution | APPROVED | No | 2024-12-04 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-12 |  |  |  | 632615.05 | 6672 | 0 | STANDARD | Zamil Group Trade & Service Co | SAR | 632615.05 | APPROVED |  |  | 2024-12-29 | 0 | 17 | Abuhammad, Samir | -45638 | 17
105-113 | PS Systems for Sindalah - NEOM | 5132 | PS Systems for Sindalah - NEOM-Galaxy tab S 2 PCs | APPROVED | No | 2024-12-04 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-12 |  |  |  | 7998 | 6669 | 0 | STANDARD | Excellence Arabia Trading Company | SAR | 6950 | APPROVED |  |  | 2025-01-09 | 1048 | 28 | Abuhammad, Samir | -45638 | 28
105-113 | PS Systems for Sindalah - NEOM | 5434 | PS Systems for Sindalah - NEOM-PR for Network Video Recorder & HDD-Neom Bay Jetty (Supplier-Dahua) | APPROVED | No | 2025-01-15 | Abas, Mohammed Fekry | 2025-01-22 | 2025-01-23 |  |  |  | 63752 | 6846 | 0 | STANDARD | Zamil Group Trade & Service Co | SAR | 63752 | APPROVED |  |  | 2025-02-06 | 0 | 14 | Abuhammad, Samir | -45680 | 14
105-113 | PS Systems for Sindalah - NEOM | 5435 | PS Systems for Sindalah - NEOM-PR for Supply of LAN Ports With 3 Yr Protection (Supplier-Fortinet) | APPROVED | No | 2025-01-15 | Abas, Mohammed Fekry | 2025-01-22 | 2025-01-23 |  |  |  | 404524.96 | 6845 | 0 | STANDARD | Exclusive Networks For Information Systems Technology | SAR | 394559 | APPROVED |  |  | 2025-02-10 | 9965.96 | 18 | Abuhammad, Samir | -45680 | 18
105-113 | PS Systems for Sindalah - NEOM | 5436 | PS Systems for Sindalah - NEOM-PR for Cloud Storage (Supplier-Reddington) | APPROVED | No | 2025-01-15 | Abas, Mohammed Fekry | 2025-01-22 | 2025-01-23 |  |  |  | 91123.52 | 6835 | 0 | STANDARD | Bayt Al Egada for Trading and Technology | SAR | 91123 | APPROVED |  |  | 2025-02-26 | 0.52 | 34 | Abuhammad, Samir | -45680 | 34
105-113 | PS Systems for Sindalah - NEOM | 6441 | PS Systems for Sindalah - NEOM-price differences for microsoft liceneses | APPROVED | No | 2025-04-23 | Abas, Mohammed Fekry | 2025-04-24 | 2025-04-24 |  |  | due to changes in Microsoft list price and delay on having the partneship with Microsoft | 75000 | 5694 | 1 | STANDARD | AL FALAK ELECTRONICS | SAR | 69789 | APPROVED |  |  | 2025-04-28 | 5211 | 4 | Abuhammad, Samir | -45771 | 4
[12 empty] | Note: we are using Nesma Injazat partnership | [14 empty] | 0 | 0
105-113 | PS Systems for Sindalah - NEOM | 6769 | PS Systems for Sindalah - NEOM-PR For Supply Of DC power supply 48 V 240 W Outdoor type | APPROVED | No | 2025-06-03 | Abas, Mohammed Fekry | 2025-06-19 | 2025-06-19 |  |  |  | 2430 | 7418 | 0 | STANDARD | Bright Wire Company | SAR | 2241 | APPROVED |  |  | 2025-06-29 | 189 | 10 | Abuhammad, Samir | -45827 | 10
105-113 | PS Systems for Sindalah - NEOM | 7900 | Portable radiation and Explosive tracer | APPROVED | No | 2025-10-06 | Abas, Mohammed Fekry | 2025-10-08 | 2025-10-08 |  |  | Portable radiation and Explosive tracer-Budget Task#2.9 | 0 | 7826 | 0 | STANDARD | Branch Bots Inc | SAR | 436160 | APPROVED |  |  | 2025-11-02 | -436160 | 25 | Abuhammad, Samir | -45938 | 25
105-113 | PS Systems for Sindalah - NEOM | 8274 | PR For DMR Two Way Radio | APPROVED | No | 2025-11-18 | Abas, Mohammed Fekry | 2025-11-25 | 2025-11-29 |  |  | PR For DMR Two Way Radio-Budget Task#1.36 | 0 | 7588 | 0 | STANDARD | Hytera Communications corporation limited | USD | 11700 | APPROVED |  |  | 2025-12-07 | -11700 | 8 | Abuhammad, Samir | -45990 | 8
105-114 | Sheraa 115/13.8kV SS | 1925 | Sheraa 115/13.8kV SS-Engineering & Design- Sheraa | APPROVED | No | 2023-12-11 | Abas, Mohammed Fekry | 2023-12-12 | 2023-12-12 |  |  |  | 581250 | 4896 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 570000 | APPROVED |  |  | 2024-01-08 | 11250 | 27 | Kumar, Mr. Ranjan | -45272 | 27
105-114 | Sheraa 115/13.8kV SS | 1968 | Sheraa 115/13.8kV SS-Control, Protection & SAS- Sheraa | APPROVED | No | 2023-12-14 | Abas, Mohammed Fekry | 2023-12-15 | 2023-12-17 |  |  |  | 8100000 | 4845 | 0 | STANDARD | ALFANAR CO | SAR | 8100000 | APPROVED |  |  | 2024-01-15 | 0 | 29 | Kumar, Mr. Ranjan | -45277 | 29
105-114 | Sheraa 115/13.8kV SS | 2089 | Sheraa 115/13.8kV SS-13.8KV MV SWGR | APPROVED | No | 2024-01-04 | Abas, Mohammed Fekry | 2024-01-04 | 2024-01-07 |  |  |  | 8210000 | 4862 | 0 | STANDARD | ALFANAR CO | SAR | 8210000 | APPROVED |  |  | 2024-01-21 | 0 | 14 | Alhadi, Khalid | -45298 | 14
105-114 | Sheraa 115/13.8kV SS | 2110 | Sheraa 115/13.8kV SS-Temporary Project Sign Board | APPROVED | No | 2024-01-08 | Abas, Mohammed Fekry | 2024-01-09 | 2024-01-09 |  |  |  | 20000 | 4978 | 0 | STANDARD | Construction Expertise Est. | SAR | 20000 | APPROVED |  |  | 2024-01-17 | 0 | 8 | Alhadi, Khalid | -45300 | 8
105-114 | Sheraa 115/13.8kV SS | 2257 | Sheraa 115/13.8kV SS-Fencing Work | APPROVED | No | 2024-01-23 | Abas, Mohammed Fekry | 2024-01-24 | 2024-01-25 |  |  |  | 92858.33 | 5134 | 0 | STANDARD | Construction Expertise Est. | SAR | 76285 | APPROVED |  |  | 2024-03-14 | 16573.33 | 49 | Alhadi, Khalid | -45316 | 49
105-114 | Sheraa 115/13.8kV SS | 2377 | Sheraa 115/13.8kV SS-Cyber Security | APPROVED | No | 2024-01-30 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 1100000 | 5057 | 0 | STANDARD | ALFANAR CO | SAR | 1100000 | APPROVED |  |  | 2024-02-18 | 0 | 14 | Babic, Marian | -45326 | 14
105-114 | Sheraa 115/13.8kV SS | 2523 | Sheraa 115/13.8kV SS-Geotechnical Investigation | APPROVED | No | 2024-02-11 | Abas, Mohammed Fekry | 2024-02-11 | 2024-02-12 |  |  |  | 16000 | 5704 | 0 | STANDARD | International Agent Commercial Company(S) | SAR | 16000 | APPROVED |  |  | 2024-06-24 | 0 | 133 | Alhadi, Khalid | -45334 | 133
105-114 | Sheraa 115/13.8kV SS | 2545 | Sheraa 115/13.8kV SS-Super Structure Precast including Fire Walls | APPROVED | No | 2024-02-13 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-19 |  |  |  | 2421479 | 5384 | 0 | STANDARD | Factory of Ideal Precast Concrete System Company | SAR | 1921165 | APPROVED |  |  | 2024-05-01 | 500314 | 72 | Tananeh, Khalid Jamal | -45341 | 72
105-114 | Sheraa 115/13.8kV SS | 2619 | Sheraa 115/13.8kV SS-Site Office facility | APPROVED | No | 2024-02-19 | Abas, Mohammed Fekry | 2024-02-20 | 2024-02-21 |  |  |  | 325197 | 5120 | 0 | STANDARD | Construction Expertise Est. | SAR | 192080 | APPROVED |  |  | 2024-03-24 | 133117 | 32 | Muhammad, Muhammad Atif | -45343 | 32
105-114 | Sheraa 115/13.8kV SS | 2908 | Sheraa 115/13.8kV SS-Topographic Survey of Project Area | APPROVED | No | 2024-03-26 | Abas, Mohammed Fekry | 2024-03-31 | 2024-03-31 |  |  |  | 5125 | 5715 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 5125 | APPROVED |  |  | 2024-06-24 | 0 | 85 | Alhadi, Khalid | -45382 | 85
105-114 | Sheraa 115/13.8kV SS | 2933 | Sheraa 115/13.8kV SS-AC/DB and DCDB & Lighting Panels | APPROVED | No | 2024-03-28 | Abas, Mohammed Fekry | 2024-03-31 | 2024-03-31 |  |  |  | 870000 | 5406 | 0 | STANDARD | ALFANAR CO | SAR | 870000 | APPROVED |  |  | 2024-05-05 | 0 | 35 | Mohammed, Faisal Ansari | -45382 | 35
105-114 | Sheraa 115/13.8kV SS | 3039 | Sheraa 115/13.8kV SS-Electric Overhead Travelling Crane (5 TON, 27.800 m Traviling dist., span 11.515 m) | APPROVED | No | 2024-04-16 | Abas, Mohammed Fekry | 2024-04-17 | 2024-04-24 |  |  |  | 130000 | 5462 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 126870 | APPROVED |  |  | 2024-05-16 | 3130 | 22 | Muhammad, Muhammad Atif | -45406 | 22
105-114 | Sheraa 115/13.8kV SS | 3158 | Sheraa 115/13.8kV SS-Supply & Install Doorswith Hardware | APPROVED | No | 2024-04-27 | Abas, Mohammed Fekry | 2024-05-02 | 2024-05-02 |  |  |  | 152037 | 6038 | 0 | STANDARD | AL MANASHY COMPANY | SAR | 102583 | APPROVED |  |  | 2024-10-19 | 49454 | 170 | Tananeh, Khalid Jamal | -45414 | 170
105-114 | Sheraa 115/13.8kV SS | 3211 | Sheraa 115/13.8kV SS-Supply & Install Metal Works | APPROVED | No | 2024-04-28 | Abas, Mohammed Fekry | 2024-05-02 | 2024-05-02 |  |  |  | 426160 | 5936 | 0 | STANDARD | Nesma Alfaris Contracting Est. | SAR | 388300 | APPROVED |  |  | 2024-10-14 | 37860 | 165 | Tananeh, Khalid Jamal | -45414 | 165
105-114 | Sheraa 115/13.8kV SS | 3303 | Sheraa 115/13.8kV SS-Site Office Facility-Electronic items | APPROVED | No | 2024-05-05 | Abas, Mohammed Fekry | 2024-05-07 | 2024-05-12 |  |  |  | 21550 | 5607 | 0 | STANDARD | Construction Expertise Est. | SAR | 21550 | APPROVED |  |  | 2024-06-03 | 0 | 22 | Muhammad, Muhammad Atif | -45424 | 22
105-114 | Sheraa 115/13.8kV SS | 3360 | Sheraa 115/13.8kV SS-Repair Site Fence | APPROVED | No | 2024-05-09 | Abas, Mohammed Fekry | 2024-05-12 | 2024-05-13 |  |  |  | 28800 | 5583 | 0 | STANDARD | Construction Expertise Est. | SAR | 27648 | APPROVED |  |  | 2024-05-27 | 1152 | 14 | Alhadi, Khalid | -45425 | 14
105-114 | Sheraa 115/13.8kV SS | 3407 | Sheraa 115/13.8kV SS-150sq.mm, Tinned copper conductor | APPROVED | No | 2024-05-15 | Abas, Mohammed Fekry | 2024-05-16 | 2024-05-17 |  |  |  | 38500 | 5353 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 38455.41 | APPROVED |  |  | 2024-05-21 | 44.59 | 4 | Muhammad, Muhammad Atif | -45429 | 4
105-114 | Sheraa 115/13.8kV SS | 3522 | Sheraa 115/13.8kV SS-Supply & Apply (Roof Waterproofing system & Underground Waterproofing Tanking system ) | APPROVED | No | 2024-05-28 | Sherif, Marwa | 2024-06-03 | 2024-06-03 |  |  |  | 392625 | 5678 | 0 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 347826.5 | APPROVED |  |  | 2024-06-13 | 44798.5 | 10 | Alhadi, Khalid | -45446 | 10
105-114 | Sheraa 115/13.8kV SS | 3523 | Sheraa 115/13.8kV SS-125 V DC System (Battery GEL Type & Chargers ) | APPROVED | No | 2024-05-28 | Sherif, Marwa | 2024-06-03 | 2024-06-03 |  |  |  | 550000 | 5738 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 457000 | APPROVED |  |  | 2024-07-10 | 93000 | 37 | Muhammad, Muhammad Atif | -45446 | 37
105-114 | Sheraa 115/13.8kV SS | 3619 | Sheraa 115/13.8kV SS-Grounding material accessories | APPROVED | No | 2024-06-08 | Abas, Mohammed Fekry | 2024-06-09 | 2024-06-09 |  |  |  | 72850 | 5556 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 72850 | APPROVED |  |  | 2024-07-07 | 0 | 28 | Muhammad, Muhammad Atif | -45452 | 28
105-114 | Sheraa 115/13.8kV SS | 3733 | Sheraa 115/13.8kV SS-Sewage Water removal services (10,000 Lt) | APPROVED | No | 2024-07-02 | Abas, Mohammed Fekry | 2024-07-05 | 2024-07-07 |  |  |  | 10000 | 5933 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 300 | APPROVED |  |  | 2024-08-18 | 9700 | 42 | Akhtar, Farhan | -45480 | 42
105-114 | Sheraa 115/13.8kV SS | 3734 | Sheraa 115/13.8kV SS-Supply & Delivery of Raw Water, 10 Cu. M Tanker | APPROVED | No | 2024-07-02 | Abas, Mohammed Fekry | 2024-07-24 | 2024-07-25 |  |  |  | 2000 | 5933 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 1800 | APPROVED |  |  | 2024-08-18 | 200 | 24 | Akhtar, Farhan | -45498 | 24
105-114 | Sheraa 115/13.8kV SS | 3737 | Sheraa 115/13.8kV SS-MV Power Cable (1Cx630mm2 & 1x3Cx300mm2) | APPROVED | No | 2024-07-02 | Abas, Mohammed Fekry | 2024-07-05 | 2024-07-07 |  |  |  | 1056472.72 | 6022 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 944356.49 | APPROVED |  |  | 2024-10-09 | 112116.24 | 94 | Badhman, Saeed | -45480 | 94
105-114 | Sheraa 115/13.8kV SS | 3777 | Sheraa 115/13.8kV SS-Garbage Waste Container, 12 Cu. M (1 year) | APPROVED | No | 2024-07-07 | Abas, Mohammed Fekry | 2024-07-09 | 2024-07-09 |  |  |  | 28800 | 5883 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 19200 | APPROVED |  |  | 2024-08-20 | 9600 | 42 | Akhtar, Farhan | -45482 | 42
105-114 | Sheraa 115/13.8kV SS | 3879 | Sheraa 115/13.8kV SS-LV Control Cables | APPROVED | No | 2024-07-14 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 716000 | 5824 | 0 | STANDARD | ALFANAR CO | SAR | 531752.8 | APPROVED |  |  | 2024-08-25 | 184247.2 | 40 | Muhammad, Muhammad Atif | -45489 | 40
105-114 | Sheraa 115/13.8kV SS | 3889 | Sheraa 115/13.8kV SS-Plate Load Test for Backfilling-Soil Third Party | APPROVED | No | 2024-07-14 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 7500 | 5942 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 7500 | APPROVED |  |  | 2024-10-08 | 0 | 84 | Tananeh, Khalid Jamal | -45489 | 84
105-114 | Sheraa 115/13.8kV SS | 3935 | Sheraa 115/13.8kV SS-MV Cable Termination Kit | APPROVED | No | 2024-07-16 | Issa, Amr Ali | 2024-07-21 | 2024-07-21 |  |  |  | 98837 | 5984 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 95871.89 | APPROVED |  |  | 2024-09-19 | 2965.11 | 60 | Badhman, Saeed | -45494 | 60
105-114 | Sheraa 115/13.8kV SS | 3960 | Sheraa 115/13.8kV SS-Testing & Commissioning | INCOMPLETE | No |  | Basharat, Ameen Ahmed | 2024-07-20 |  |  |  |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-114 | Sheraa 115/13.8kV SS | 3963 | Sheraa 115/13.8kV SS-Testing & Commissioning | INCOMPLETE | No |  | Basharat, Ameen Ahmed | 2024-07-21 |  |  |  |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-114 | Sheraa 115/13.8kV SS | 3964 | Sheraa 115/13.8kV SS-Testing & Commissioning | APPROVED | No | 2024-07-21 | Abas, Mohammed Fekry | 2024-07-23 | 2024-07-25 |  |  |  | 1854161 | 6445 | 0 | STANDARD | Al Fanar Technical Services | SAR | 1802080 | APPROVED |  |  | 2025-03-13 | 52081 | 231 | Alqadhi, Abdulrahman Abdulghani | -45498 | 231
105-114 | Sheraa 115/13.8kV SS | 4045 | Sheraa 115/13.8kV SS-Lightning System | APPROVED | No | 2024-07-29 | Abas, Mohammed Fekry | 2024-07-30 | 2024-07-30 |  |  |  | 59075 | 6033 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 59075 | APPROVED |  |  | 2024-10-06 | 0 | 68 | Badhman, Saeed | -45503 | 68
105-114 | Sheraa 115/13.8kV SS | 4069 | Sheraa 115/13.8kV SS-Supply & Delivery of Drinking Water | APPROVED | No | 2024-08-01 | Abas, Mohammed Fekry | 2024-08-02 | 2024-08-04 |  |  |  | 3500 | 5933 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 3000 | APPROVED |  |  | 2024-08-18 | 500 | 14 | Akhtar, Farhan | -45508 | 14
105-114 | Sheraa 115/13.8kV SS | 4081 | Sheraa 115/13.8kV SS-Soil Resistivity | IN PROCESS | No | 2024-08-01 | Ibrahim, Mahmoud Hassan Ali | 2024-08-04 | 2024-08-06 |  |  |  | 7360 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45510 | -45510
105-114 | Sheraa 115/13.8kV SS | 4193 | Sheraa 115/13.8kV SS-Hazardous and Non-Hazardous waste | APPROVED | No | 2024-08-19 | Abas, Mohammed Fekry | 2024-08-19 | 2024-08-19 |  |  |  | 5000 | 6123 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 3650 | APPROVED |  |  | 2024-09-19 | 1350 | 31 | Akhtar, Farhan | -45523 | 31
105-114 | Sheraa 115/13.8kV SS | 4196 | Sheraa 115/13.8kV SS-LV Power Cables | APPROVED | No | 2024-08-19 | Abas, Mohammed Fekry | 2024-08-19 | 2024-08-20 |  |  |  | 1611070 | 6079 | 0 | STANDARD | ALFANAR CO | SAR | 1110509.38 | APPROVED |  |  | 2024-09-26 | 500560.62 | 37 | Badhman, Saeed | -45524 | 37
105-114 | Sheraa 115/13.8kV SS | 4269 | Sheraa 115/13.8kV SS-Pest Control | APPROVED | No | 2024-08-26 | Abas, Mohammed Fekry | 2024-08-27 | 2024-09-01 |  |  |  | 1400 | 6222 | 0 | STANDARD | Trap Pest Control &Garden Maintenance Co. LTD | SAR | 1200 | APPROVED |  |  | 2024-09-30 | 200 | 29 | Akhtar, Farhan | -45536 | 29
105-114 | Sheraa 115/13.8kV SS | 4357 | Sheraa 115/13.8kV SS-Third Party lab Inspector for Precast Concrete Prodaction Test | APPROVED | No | 2024-09-03 | Abas, Mohammed Fekry | 2024-09-04 | 2024-09-04 |  |  |  | 84190 | 6137 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 84190 | APPROVED |  |  | 2024-10-07 | 0 | 33 | Tananeh, Khalid Jamal | -45539 | 33
105-114 | Sheraa 115/13.8kV SS | 4439 | Sheraa 115/13.8kV SS-Cable Tray | APPROVED | No | 2024-09-14 | Abas, Mohammed Fekry | 2024-09-16 | 2024-09-17 |  |  |  | 462701.68 | 6150 | 0 | STANDARD | Electrolink Co Ltd | SAR | 459950.01 | APPROVED |  |  | 2024-09-26 | 2751.67 | 9 | Muhammad, Muhammad Atif | -45552 | 9
105-114 | Sheraa 115/13.8kV SS | 4454 | Sheraa 115/13.8kV SS-Fire Alarm and Fire Protection System | APPROVED | No | 2024-09-15 | Abas, Mohammed Fekry | 2024-09-16 | 2024-09-17 |  |  |  | 2197362.42 | 6000 | 0 | STANDARD | Al Majal Group Four S for Security & Safety | SAR | 2197362.42 | APPROVED |  |  | 2024-09-26 | 0 | 9 | Muhammad, Muhammad Atif | -45552 | 9
105-114 | Sheraa 115/13.8kV SS | 4489 | Sheraa 115/13.8kV SS-Surveyor Tools:1.Total Station. 2.Levelling Machine | APPROVED | No | 2024-09-22 | Abas, Mohammed Fekry | 2024-09-22 | 2024-09-22 |  |  |  | 40000 | 6255 | 0 | STANDARD | Saudi International Trading & Marketing Ltd. (SITML) | SAR | 32500 | APPROVED |  |  | 2024-10-07 | 7500 | 15 | Babic, Marian | -45557 | 15
105-114 | Sheraa 115/13.8kV SS | 4578 | Sheraa 115/13.8kV SS-Station Service Transformer | APPROVED | No | 2024-10-02 | Abas, Mohammed Fekry | 2024-10-03 | 2024-10-04 |  |  |  | 164000 | 5907 | 0 | STANDARD | ALFANAR CO | SAR | 164000 | APPROVED |  |  | 2024-10-08 | 0 | 4 | Muhammad, Muhammad Atif | -45569 | 4
105-114 | Sheraa 115/13.8kV SS | 4581 | Sheraa 115/13.8kV SS-RTV Coating | APPROVED | No | 2024-10-14 | Abas, Mohammed Fekry | 2024-10-15 | 2024-10-15 |  |  |  | 250000 | 6366 | 0 | STANDARD | SAUDI CONDUIT COATING CO. (S3C) | SAR | 35268 | APPROVED |  |  | 2024-10-28 | 214732 | 13 | Muaz, Alaa | -45580 | 13
105-114 | Sheraa 115/13.8kV SS | 4597 | Sheraa 115/13.8kV SS-Electrical Installtion Subcontractor | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-06 | 2024-10-06 |  |  |  | 2992521 | 6537 | 0 | STANDARD | Construction Expertise Est. | SAR | 2230000 | APPROVED |  |  | 2024-12-29 | 762521 | 84 | Muhammad, Muhammad Atif | -45571 | 84
105-114 | Sheraa 115/13.8kV SS | 4635 | Sheraa 115/13.8kV SS-HVAC | APPROVED | No | 2024-10-09 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-10 |  |  |  | 2025000 | 6211 | 0 | STANDARD | Hamad Fahad Al Awad for Contracting Est | SAR | 2025000 | APPROVED |  |  | 2024-10-30 | 0 | 20 | Muhammad, Muhammad Atif | -45575 | 20
105-114 | Sheraa 115/13.8kV SS | 4679 | Sheraa 115/13.8kV SS-Telecom System | APPROVED | No | 2024-10-15 | Abas, Mohammed Fekry | 2024-10-16 | 2024-10-17 |  |  |  | 2574944 | 6237 | 0 | STANDARD | ALFANAR CO | SAR | 2574944 | APPROVED |  |  | 2025-03-18 | 0 | 152 | Kumar, Mr. Ranjan | -45582 | 152
105-114 | Sheraa 115/13.8kV SS | 4715 | Sheraa 115/13.8kV SS-Asphalt Works | APPROVED | No | 2024-10-17 | Abas, Mohammed Fekry | 2024-10-21 | 2024-10-21 |  |  |  | 150000 | 5637 | 1 | STANDARD | Future Achievement Limited Co | SAR | 150000 | APPROVED |  |  | 2025-04-07 | 0 | 168 | Tananeh, Khalid Jamal | -45586 | 168
105-114 | Sheraa 115/13.8kV SS | 4746 | Sheraa 115/13.8kV SS-Subcontractor for Civil Works | APPROVED | No | 2024-10-20 | Abas, Mohammed Fekry | 2024-10-21 | 2024-10-21 |  |  |  | 7280000 | 5637 | 0 | STANDARD | Future Achievement Limited Co | SAR | 7280000 | APPROVED |  |  | 2024-11-04 | 0 | 14 | Tananeh, Khalid Jamal | -45586 | 14
105-114 | Sheraa 115/13.8kV SS | 4763 | Sheraa 115/13.8kV SS-Grounding Cables | APPROVED | No | 2024-10-21 | Abas, Mohammed Fekry | 2024-10-22 | 2024-10-22 |  |  |  | 229400 | 6063 | 0 | STANDARD | ALFANAR CO | SAR | 226756.52 | APPROVED |  |  | 2024-10-30 | 2643.48 | 8 | Muhammad, Muhammad Atif | -45587 | 8
105-114 | Sheraa 115/13.8kV SS | 4965 | Sheraa 115/13.8kV SS-Lighting Fixtures | APPROVED | No | 2024-11-17 | Abas, Mohammed Fekry | 2024-11-19 | 2024-11-19 |  |  |  | 71998 | 6470 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 71998 | APPROVED |  |  | 2024-11-28 | 0 | 9 | Muhammad, Muhammad Atif | -45615 | 9
105-114 | Sheraa 115/13.8kV SS | 5096 | Sheraa 115/13.8kV SS-HCIS Consultant | APPROVED | No | 2024-11-30 | Abas, Mohammed Fekry | 2025-01-08 | 2025-01-08 |  |  |  | 33500 | 6509 | 0 | STANDARD | Khaled Drewesh Office for Consulting Security (KDOCS) | SAR | 33500 | APPROVED |  |  | 2025-01-15 | 0 | 7 | Muhammad, Muhammad Atif | -45665 | 7
105-114 | Sheraa 115/13.8kV SS | 5188 | Sheraa 115/13.8kV SS-Clamps & Connectors | APPROVED | No | 2024-12-08 | Abas, Mohammed Fekry | 2024-12-09 | 2024-12-12 |  |  |  | 4512 | 6414 | 0 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 4505.16 | APPROVED |  |  | 2025-01-02 | 6.84 | 21 | Mohammed, Faisal Ansari | -45638 | 21
105-114 | Sheraa 115/13.8kV SS | 5285 | Sheraa 115/13.8kV SS-Tinned Copper Conductor | APPROVED | No | 2024-12-29 | Abas, Mohammed Fekry | 2024-12-31 | 2025-01-01 |  |  |  | 171000 | 6753 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 158227.2 | APPROVED |  |  | 2025-03-03 | 12772.8 | 61 | Alhadi, Khalid | -45658 | 61
105-114 | Sheraa 115/13.8kV SS | 5316 | Sheraa 115/13.8kV SS-Control Cable for SAS Alarm (Blue Color) | APPROVED | No | 2025-01-01 | Abas, Mohammed Fekry | 2025-01-07 | 2025-01-07 |  |  |  | 55000 | 6781 | 0 | STANDARD | ALFANAR CO | SAR | 52600 | APPROVED |  |  | 2025-04-14 | 2400 | 97 | Muaz, Alaa | -45664 | 97
105-114 | Sheraa 115/13.8kV SS | 5352 | Sheraa 115/13.8kV SS-Lighting Conduits | APPROVED | No | 2025-01-05 | Abas, Mohammed Fekry | 2025-01-08 | 2025-01-12 |  |  |  | 342909.3 | 6690 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 342909.3 | APPROVED |  |  | 2025-01-22 | 0 | 10 | Muaz, Alaa | -45669 | 10
105-114 | Sheraa 115/13.8kV SS | 5507 | Sheraa 115/13.8kV SS-CTPU & CTPU Box | APPROVED | No | 2025-01-21 | Abas, Mohammed Fekry | 2025-01-26 | 2025-01-27 |  |  |  | 68000 | 6285 | 0 | STANDARD | Energy Tracks For Contracting | SAR | 68000 | APPROVED |  |  | 2025-03-04 | 0 | 36 | Kumar, Mr. Ranjan | -45684 | 36
105-114 | Sheraa 115/13.8kV SS | 5578 | Sheraa 115/13.8kV SS-Fibre Optic Cables | APPROVED | No | 2025-01-25 | Abas, Mohammed Fekry | 2025-01-27 | 2025-01-30 |  |  |  | 500000 | 6950 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 220000 | APPROVED |  |  | 2025-03-11 | 280000 | 40 | Abdulqader, Ahmed Abdulhalim | -45687 | 40
105-114 | Sheraa 115/13.8kV SS | 5584 | Sheraa 115/13.8kV SS-Remote Ends Modification | APPROVED | No | 2025-01-25 | Abas, Mohammed Fekry | 2025-01-27 | 2025-01-30 |  |  |  | 150000 | 7323 | 0 | STANDARD | TRINERGY TECHNOLOGIES SA | SAR | 65000 | APPROVED |  |  | 2025-05-24 | 85000 | 114 | Babic, Marian | -45687 | 114
105-114 | Sheraa 115/13.8kV SS | 5620 | Sheraa 115/13.8kV SS-Steel Parapet Works | APPROVED | No | 2025-01-26 | Abas, Mohammed Fekry | 2025-01-28 | 2025-01-30 |  |  |  | 36022 | 6820 | 0 | STANDARD | RAFCO Factory Company For Metal Industries | SAR | 36022 | APPROVED |  |  | 2025-03-03 | 0 | 32 | Hegazy, Ayman | -45687 | 32
105-114 | Sheraa 115/13.8kV SS | 5714 | Sheraa 115/13.8kV SS-Additional Cable Tray | APPROVED | No | 2025-01-29 | Abas, Mohammed Fekry | 2025-02-04 | 2025-02-05 |  |  |  | 48184 | 6878 | 0 | STANDARD | Essa Al Asmakh Trading Est. | SAR | 17272 | APPROVED |  |  | 2025-02-19 | 30912 | 14 | Abuhammad, Samir | -45693 | 14
105-114 | Sheraa 115/13.8kV SS | 5821 | Sheraa 115/13.8kV SS-Boxes and fittings for Sockets | APPROVED | No | 2025-02-09 | Abas, Mohammed Fekry | 2025-02-09 | 2025-02-11 |  |  |  | 49999 | 6899 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 12118 | APPROVED |  |  | 2025-02-19 | 37881 | 8 | Abuhammad, Samir | -45699 | 8
105-114 | Sheraa 115/13.8kV SS | 6080 | Sheraa 115/13.8kV SS-Earth works (Excavation, base course & General Backfill) | APPROVED | No | 2025-02-27 | Abas, Mohammed Fekry | 2025-03-03 | 2025-03-05 |  |  |  | 463030 | 5637 | 1 | STANDARD | Future Achievement Limited Co | SAR | 463030 | APPROVED |  |  | 2025-04-07 | 0 | 33 | Tananeh, Khalid Jamal | -45721 | 33
105-114 | Sheraa 115/13.8kV SS | 6098 | Sheraa 115/13.8kV SS-Drawings Printing A2 | APPROVED | No | 2025-03-03 | Abas, Mohammed Fekry | 2025-03-03 | 2025-03-05 |  |  | Drawing Printing - Line Item 2.33 | 31000 | 7060 | 0 | STANDARD | Print Magaies Al abdaa Printing | SAR | 30999 | APPROVED |  |  | 2025-04-07 | 1 | 33 | Abuhammad, Samir | -45721 | 33
105-114 | Sheraa 115/13.8kV SS | 6255 | Sheraa 115/13.8kV SS-Security System | APPROVED | No | 2025-03-24 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-20 |  |  | Security System - Line Item 2.7 | 736532.86 | 6639 | 0 | STANDARD | CEGELEC NETWORK AND SECURITY SYSTEMS | SAR | 736532.86 | APPROVED |  |  | 2025-05-22 | 0 | 32 | Abdulqader, Ahmed Abdulhalim | -45767 | 32
105-114 | Sheraa 115/13.8kV SS | 6375 | Sheraa 115/13.8kV SS-Retaining Walls, Ramp Wall, And Duct Bank Works Adding In Scope of work after Change in Drawings and diff. in Quantity | APPROVED | No | 2025-04-17 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-20 |  |  |  | 675000 | 5637 | 2 | STANDARD | Future Achievement Limited Co | SAR | 675000 | APPROVED |  |  | 2025-04-24 | 0 | 4 | Tananeh, Khalid Jamal | -45767 | 4
105-114 | Sheraa 115/13.8kV SS | 6476 | Sheraa 115/13.8kV SS-Design, Supply and Install Full Hardware and Door Frame (Change Order for PO# 6038) | APPROVED | No | 2025-04-28 | Abas, Mohammed Fekry | 2025-04-29 | 2025-04-30 |  |  |  | 22393 | 6038 | 1 | STANDARD | AL MANASHY COMPANY | SAR | 22393 | APPROVED |  |  | 2025-09-09 | 0 | 132 | Tananeh, Khalid Jamal | -45777 | 132
105-114 | Sheraa 115/13.8kV SS | 6504 | Sheraa 115/13.8kV SS-Air conditioner | APPROVED | No | 2025-05-04 | Abas, Mohammed Fekry | 2025-05-05 | 2025-05-05 |  |  | Air conditioner - 2.20 | 15400 | 7232 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 15400 | APPROVED |  |  | 2025-05-12 | 0 | 7 | Abuhammad, Samir | -45782 | 7
105-114 | Sheraa 115/13.8kV SS | 6520 | Sheraa 115/13.8kV SS-4P x 1.5mm2 | APPROVED | No | 2025-05-05 | Abas, Mohammed Fekry | 2025-05-06 | 2025-05-06 |  |  | 4P x 1.5mm2 Cable | 9000 | 7314 | 0 | STANDARD | Middle East Specialized Cables Mesc | SAR | 7500 | APPROVED |  |  | 2025-05-27 | 1500 | 21 | Abuhammad, Samir | -45783 | 21
105-114 | Sheraa 115/13.8kV SS | 6938 | Sheraa 115/13.8kV SS-Switches & Sockets | APPROVED | No | 2025-06-30 | Abas, Mohammed Fekry | 2025-07-03 | 2025-07-03 |  |  | Switches & Sockets - Line Item 2.23 | 99975 | 7175 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 99975 | APPROVED |  |  | 2025-08-10 | 0 | 38 | Muaz, Alaa | -45841 | 38
105-114 | Sheraa 115/13.8kV SS | 6967 | Sheraa 115/13.8kV SS-Site office equipment | APPROVED | No | 2025-07-02 | Abas, Mohammed Fekry | 2025-07-03 | 2025-07-03 |  |  | Site office equipment - Line Item 2.35 | 46736 | 7469 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 38456 | APPROVED |  |  | 2025-07-14 | 8280 | 11 | Abdulqader, Ahmed Abdulhalim | -45841 | 11
105-114 | Sheraa 115/13.8kV SS | 6991 | Sheraa 115/13.8kV SS-Testing Technicians | APPROVED | No | 2025-07-07 | Abas, Mohammed Fekry | 2025-07-09 | 2025-07-09 |  |  | Testing Techinicans (2.31) - M/s City Crown | 340000 | 7497 | 0 | STANDARD | City Crowns Energy | SAR | 339996 | APPROVED |  |  | 2025-07-24 | 4 | 15 | Babic, Marian | -45847 | 15
105-114 | Sheraa 115/13.8kV SS | 6991 | Sheraa 115/13.8kV SS-Testing Technicians | APPROVED | No | 2025-07-07 | Abas, Mohammed Fekry | 2025-07-09 | 2025-07-09 |  |  | Testing Techinicans (2.31) - M/s City Crown | 340000 | 7497 | 1 | STANDARD | City Crowns Energy | SAR | 339996 | IN PROCESS |  |  |  | 4 | 207 | Babic, Marian | -45847 | -45847
105-114 | Sheraa 115/13.8kV SS | 7107 | Sheraa 115/13.8kV SS-Fence relocation | APPROVED | No | 2025-07-15 | Abas, Mohammed Fekry | 2025-07-20 | 2025-07-20 |  |  | Fence relocation - 2.20 | 49270 | 7103 | 0 | STANDARD | Construction Expertise Est. | SAR | 36400 | APPROVED |  |  | 2025-08-10 | 12870 | 21 | Abdulqader, Ahmed Abdulhalim | -45858 | 21
105-114 | Sheraa 115/13.8kV SS | 7160 | Sheraa 115/13.8kV SS-Telecom DCDB | APPROVED | No | 2025-07-21 | Abas, Mohammed Fekry | 2025-07-23 | 2025-07-23 |  |  | telecom dcdb - 2.20 | 29700 | 7585 | 0 | STANDARD | HAWA ELECTRIC PANEL BOARD FAC | SAR | 29700 | APPROVED |  |  | 2025-08-06 | 0 | 14 | Abuhammad, Samir | -45861 | 14
105-114 | Sheraa 115/13.8kV SS | 7211 | Sheraa 115/13.8kV SS-Tower AC 5 Ton | APPROVED | No | 2025-07-26 | Abas, Mohammed Fekry | 2025-07-28 | 2025-07-28 |  |  | Tower AC - 2.20 | 36000 | 7565 | 0 | STANDARD | Versatile Advanced Limited Company. | SAR | 36000 | APPROVED |  |  | 2025-08-10 | 0 | 13 | Akhtar, Farhan | -45866 | 13
105-114 | Sheraa 115/13.8kV SS | 7254 | Sheraa 115/13.8kV SS-Additional LV Power Cables | RETURNED | No | 2025-08-03 | Mohammed, Mohammed Adel Fahmy | 2026-01-15 | 2025-08-06 | 2026-01-15 |  | Not Have POCR Until Now and PR incorrect qty. | 38000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Mohammed Adel Fahmy | -45875 | -45875
105-114 | Sheraa 115/13.8kV SS | 7268 | Sheraa 115/13.8kV SS-Grounding Accessories | APPROVED | No | 2025-08-03 | Abas, Mohammed Fekry | 2025-08-05 | 2025-08-06 |  |  | 2.21 - Earthing Accessories | 52560.5 | 7083 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 52560.5 | APPROVED |  |  | 2025-08-17 | 0 | 11 | Abdulqader, Ahmed Abdulhalim | -45875 | 11
105-114 | Sheraa 115/13.8kV SS | 7326 | Sheraa 115/13.8kV SS-POCR for ABSAR | APPROVED | No | 2025-08-11 | Abas, Mohammed Fekry | 2025-08-14 | 2025-08-18 |  |  | POCR for ABSAR | 27302.47 | 5678 | 1 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 27302.47 | APPROVED | 2026-01-21 | 2026-01-25 | 2026-01-28 | 0 | 163 | Alhadi, Khalid | 160 | 163
105-114 | Sheraa 115/13.8kV SS | 7466 | Clamps | APPROVED | No | 2025-08-25 | Abas, Mohammed Fekry | 2025-08-27 | 2025-08-28 |  |  | Cable Clamps for Sheraa - 2.19 | 0 | 7267 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 58425 | APPROVED |  |  | 2025-09-08 | -58425 | 11 | Hegazy, Ayman | -45897 | 11
105-114 | Sheraa 115/13.8kV SS | 7485 | Cable Supports | APPROVED | No | 2025-08-25 | Abas, Mohammed Fekry | 2025-08-27 | 2025-08-28 |  |  | Cable Support - Sheraa - 2.19 | 0 | 7379 | 0 | STANDARD | ISAM KABBANI &Partners | SAR | 67405 | APPROVED |  |  | 2025-09-08 | -67405 | 11 | Hegazy, Ayman | -45897 | 11
105-114 | Sheraa 115/13.8kV SS | 7566 | Lugs and Glands for Sheraa | APPROVED | No | 2025-08-28 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-03 |  |  | Revised PR for Lugs & Glands - Sheraa - 2.13 | 0 | 7609 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 21468.32 | APPROVED |  |  | 2025-09-10 | -21468.32 | 7 | Abdulqader, Ahmed Abdulhalim | -45903 | 7
105-114 | Sheraa 115/13.8kV SS | 7653 | Additional lighting wires - Sheraa | APPROVED | No | 2025-09-06 | Abas, Mohammed Fekry | 2025-09-08 | 2025-09-08 |  |  | PR for Additional Lighitng Wires- Sheraa | 0 | 7962 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 24579.54 | APPROVED | 2026-01-19 | 2026-01-25 | 2026-01-28 | -24579.54 | 142 | Mohammed, Mohammed Adel Fahmy | 139 | 142
105-114 | Sheraa 115/13.8kV SS | 7913 | Office furniture - Sheraa | APPROVED | No | 2025-10-07 | Abas, Mohammed Fekry | 2025-10-07 | 2025-10-08 |  |  | Office furniture - Sheraa - 2.33 | 0 | 7706 | 0 | STANDARD | ALISMAIL INDUSTRIAL CO.(S) | SAR | 17590 | APPROVED |  |  | 2025-10-14 | -17590 | 6 | Abdulqader, Ahmed Abdulhalim | -45938 | 6
105-114 | Sheraa 115/13.8kV SS | 7950 | Testing Technicians Sheraa (7000 manhours) | APPROVED | No | 2025-10-14 | Abas, Mohammed Fekry | 2025-11-17 | 2025-11-17 |  |  | Testin Technicians Sheraa (7000 manhours) - 2.31 | 1 | 7497 | 1 | STANDARD | City Crowns Energy | SAR | 203000 | IN PROCESS |  |  |  | -202999 | 76 | Babic, Marian | -45978 | -45978
105-114 | Sheraa 115/13.8kV SS | 7950 | Testing Technicians Sheraa (7000 manhours) | APPROVED | No | 2025-10-14 | Abas, Mohammed Fekry | 2025-11-17 | 2025-11-17 |  |  | Testin Technicians Sheraa (7000 manhours) - 2.31 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45978 | -45978
105-114 | Sheraa 115/13.8kV SS | 8242 | Decorative Fence | APPROVED | No | 2025-11-17 | Abas, Mohammed Fekry | 2025-11-18 | 2025-11-19 |  |  | Budget line 2.20 - Civil & Structural Works | 0 | 7895 | 0 | STANDARD | Fursan Construction Industry Factory Industry Factory | SAR | 463405 | APPROVED |  |  | 2025-12-14 | -463405 | 25 | Hegazy, Ayman | -45980 | 25
105-114 | Sheraa 115/13.8kV SS | 8246 | PDS System | APPROVED | No | 2025-11-18 | Abas, Mohammed Fekry | 2025-11-24 | 2025-11-24 |  |  | Budget line 2.5 - PDS System | 0 | 7771 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 140000 | APPROVED |  |  | 2025-12-25 | -140000 | 31 | Abdulqader, Ahmed Abdulhalim | -45985 | 31
105-114 | Sheraa 115/13.8kV SS | 8262 | Copper Tape 40x6 | APPROVED | No | 2025-11-18 | Abas, Mohammed Fekry | 2025-11-18 | 2025-11-19 |  |  | Budget line 2.21 - Grounding & Shielding system | 0 | 7665 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 21496 | APPROVED |  |  | 2025-11-24 | -21496 | 5 | Hegazy, Ayman | -45980 | 5
105-114 | Sheraa 115/13.8kV SS | 8448 | Swing Gate Motor | APPROVED | No | 2025-12-04 | Abas, Mohammed Fekry | 2025-12-07 | 2025-12-09 |  |  |  | 0 | 7987 | 0 | STANDARD | ALMOSALLAMY INDUSTRIAL COMPANY | SAR | 9330 | APPROVED |  |  | 2025-12-15 | -9330 | 6 | Abdelraouf, Islam ِAdel Hanafy | -46000 | 6
105-114 | Sheraa 115/13.8kV SS | 8506 | Motion Sensor - Lighting System - Sheraa | APPROVED | No | 2025-12-11 | Abas, Mohammed Fekry | 2025-12-15 | 2025-12-17 |  |  | Line Item 2.22 - Lighting System | 0 | 7347 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 68054 | APPROVED | 2025-12-23 | 2025-12-26 | 2026-01-21 | -68054 | 35 | Muaz, Alaa | 9 | 35
105-114 | Sheraa 115/13.8kV SS | 8568 | Transformer Oil Sampling - Sheraa | APPROVED | No | 2025-12-23 | Abas, Mohammed Fekry | 2025-12-24 | 2025-12-26 |  |  | Transformer Oil Sampling - 2.38 - Sheraa | 0 | 7916 | 0 | STANDARD | Saudi Arabian Engineering Company | SAR | 37300 | IN PROCESS |  |  |  | -37300 | 37 | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46017 | -46017
105-114 | Sheraa 115/13.8kV SS | 8568 | Transformer Oil Sampling - Sheraa | APPROVED | No | 2025-12-23 | Abas, Mohammed Fekry | 2025-12-24 | 2025-12-26 |  |  | Transformer Oil Sampling - 2.38 - Sheraa | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46017 | -46017
105-114 | Sheraa 115/13.8kV SS | 8594 | Metal Works (Change Order) - Sheraa | RETURNED | No | 2025-12-28 | Tananeh, Khalid Jamal | 2026-01-22 | 2026-01-01 | 2026-01-22 |  | return as per email from Arnie, in Thu 22/01/2026 10:36 AM | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -46023 | -46023
105-114 | Sheraa 115/13.8kV SS | 8648 | Metal Doors (Change Order) - Sheraa | RETURNED | No | 2026-01-05 | Tananeh, Khalid Jamal | 2026-01-22 | 2026-01-13 | 2026-01-22 |  | return as per email from Arnie, in Thu 22/01/2026 10:36 AM | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -46035 | -46035
105-115 | North Khobar Dist. 115/13.8kV | 1943 | North Khobar Dist. 115/13.8kV-Engineering & Design North Khobar | APPROVED | No | 2023-12-12 | Abas, Mohammed Fekry | 2023-12-13 | 2023-12-13 |  |  |  | 581250 | 4900 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 570000 | APPROVED |  |  | 2024-01-08 | 11250 | 26 | Kumar, Mr. Ranjan | -45273 | 26
105-115 | North Khobar Dist. 115/13.8kV | 1972 | North Khobar Dist. 115/13.8kV-13.8kV Switchgear-North Khobar | APPROVED | No | 2023-12-14 | Abas, Mohammed Fekry | 2023-12-15 | 2023-12-17 |  |  |  | 8210000 | 4866 | 0 | STANDARD | ALFANAR CO | SAR | 8210000 | APPROVED |  |  | 2024-01-25 | 0 | 39 | Alhadi, Khalid | -45277 | 39
105-115 | North Khobar Dist. 115/13.8kV | 2059 | North Khobar Dist. 115/13.8kV-C&P,SAS for NORTH KHOBAR DISTRICT SS | APPROVED | No | 2023-12-31 | Abas, Mohammed Fekry | 2024-01-02 | 2024-01-02 |  |  |  | 9729705 | 4849 | 0 | STANDARD | ALFANAR CO | SAR | 7800000 | APPROVED |  |  | 2024-04-15 | 1929705 | 104 | Kumar, Mr. Ranjan | -45293 | 104
105-115 | North Khobar Dist. 115/13.8kV | 2114 | North Khobar Dist. 115/13.8kV-Temporary Project Sign Board | APPROVED | No | 2024-01-08 | Abas, Mohammed Fekry | 2024-01-09 | 2024-01-09 |  |  |  | 20000 | 4972 | 0 | STANDARD | Construction Expertise Est. | SAR | 20000 | APPROVED |  |  | 2024-01-17 | 0 | 8 | Alhadi, Khalid | -45300 | 8
105-115 | North Khobar Dist. 115/13.8kV | 2258 | North Khobar Dist. 115/13.8kV-Fencing Work | APPROVED | No | 2024-01-23 | Abas, Mohammed Fekry | 2024-01-24 | 2024-01-25 |  |  |  | 92858.33 | 5136 | 0 | STANDARD | Construction Expertise Est. | SAR | 77813 | APPROVED |  |  | 2024-03-14 | 15045.33 | 49 | Alhadi, Khalid | -45316 | 49
105-115 | North Khobar Dist. 115/13.8kV | 2359 | North Khobar Dist. 115/13.8kV- UG Scanning | APPROVED | No | 2024-01-29 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 1900 | 5071 | 0 | STANDARD | Construction Expertise Est. | SAR | 1900 | APPROVED |  |  | 2024-02-15 | 0 | 11 | Alhadi, Khalid | -45326 | 11
105-115 | North Khobar Dist. 115/13.8kV | 2546 | North Khobar Dist. 115/13.8kV-Super Structure Precast including Fire Walls | APPROVED | No | 2024-02-13 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-19 |  |  |  | 2421479 | 5388 | 0 | STANDARD | Factory of Ideal Precast Concrete System Company | SAR | 1921165 | APPROVED |  |  | 2024-04-30 | 500314 | 71 | Tananeh, Khalid Jamal | -45341 | 71
105-115 | North Khobar Dist. 115/13.8kV | 2549 | North Khobar Dist. 115/13.8kV-Cyber Security | APPROVED | No | 2024-02-13 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-18 |  |  |  | 1180000 | 5103 | 0 | STANDARD | ALFANAR CO | SAR | 1000000 | APPROVED |  |  | 2024-02-28 | 180000 | 10 | Babic, Marian | -45340 | 10
105-115 | North Khobar Dist. 115/13.8kV | 2632 | North Khobar Dist. 115/13.8kV-Site Office facility | APPROVED | No | 2024-02-20 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 325197 | 5156 | 0 | STANDARD | Construction Expertise Est. | SAR | 192080 | APPROVED |  |  | 2024-03-27 | 133117 | 30 | Muhammad, Muhammad Atif | -45348 | 30
105-115 | North Khobar Dist. 115/13.8kV | 2718 | North Khobar Dist. 115/13.8kV-ACDB/DCDB & Lighting Panel | APPROVED | No | 2024-02-28 | Abas, Mohammed Fekry | 2024-02-28 | 2024-03-03 |  |  |  | 870000 | 5377 | 0 | STANDARD | ALFANAR CO | SAR | 870000 | APPROVED |  |  | 2024-04-30 | 0 | 58 | Mohammed, Faisal Ansari | -45354 | 58
105-115 | North Khobar Dist. 115/13.8kV | 2886 | North Khobar Dist. 115/13.8kV-Topographic Survey | APPROVED | No | 2024-03-24 | Abas, Mohammed Fekry | 2024-03-25 | 2024-03-25 |  |  |  | 5125 | 5370 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 5125 | APPROVED |  |  | 2024-04-18 | 0 | 24 | Alhadi, Khalid | -45376 | 24
105-115 | North Khobar Dist. 115/13.8kV | 3036 | North Khobar Dist. 115/13.8kV- OVERHEAD TRAVELING CRANE- Capacity 5 Ton & grider length 12m | APPROVED | No | 2024-04-16 | Abas, Mohammed Fekry | 2024-04-16 | 2024-04-16 |  |  |  | 129000 | 5465 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 126870 | APPROVED |  |  | 2024-05-16 | 2130 | 30 | Muhammad, Muhammad Atif | -45398 | 30
105-115 | North Khobar Dist. 115/13.8kV | 3183 | North Khobar Dist. 115/13.8kV-Water Proofing | APPROVED | No | 2024-04-28 | Abas, Mohammed Fekry | 2024-04-29 | 2024-04-29 |  |  |  | 392625 | 5657 | 0 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 347826.5 | APPROVED |  |  | 2024-06-13 | 44798.5 | 45 | Tananeh, Khalid Jamal | -45411 | 45
105-115 | North Khobar Dist. 115/13.8kV | 3186 | North Khobar Dist. 115/13.8kV-Hollow Metal Doors Works | APPROVED | No | 2024-04-28 | Abas, Mohammed Fekry | 2024-04-29 | 2024-04-29 |  |  |  | 152037 | 6039 | 0 | STANDARD | AL MANASHY COMPANY | SAR | 102583 | APPROVED |  |  | 2024-10-19 | 49454 | 173 | Tananeh, Khalid Jamal | -45411 | 173
105-115 | North Khobar Dist. 115/13.8kV | 3194 | North Khobar Dist. 115/13.8kV-Metal Works | APPROVED | No | 2024-04-28 | Abas, Mohammed Fekry | 2024-04-29 | 2024-04-29 |  |  |  | 426160 | 5937 | 0 | STANDARD | Nesma Alfaris Contracting Est. | SAR | 388300 | APPROVED |  |  | 2024-10-14 | 37860 | 168 | Tananeh, Khalid Jamal | -45411 | 168
105-115 | North Khobar Dist. 115/13.8kV | 3376 | North Khobar Dist. 115/13.8kV-150sq.mm, Tinned copper conductor | APPROVED | No | 2024-05-12 | Abas, Mohammed Fekry | 2024-05-13 | 2024-05-14 |  |  |  | 38500 | 5357 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 38455.41 | APPROVED |  |  | 2024-05-21 | 44.59 | 7 | Muhammad, Muhammad Atif | -45426 | 7
105-115 | North Khobar Dist. 115/13.8kV | 3457 | North Khobar Dist. 115/13.8kV-Site Office facility Electronic Item | APPROVED | No | 2024-05-21 | Abas, Mohammed Fekry | 2024-05-21 | 2024-05-22 |  |  |  | 18200 | 5611 | 0 | STANDARD | Construction Expertise Est. | SAR | 18200 | APPROVED |  |  | 2024-06-05 | 0 | 14 | Muhammad, Muhammad Atif | -45434 | 14
105-115 | North Khobar Dist. 115/13.8kV | 3502 | North Khobar Dist. 115/13.8kV-Battery and Charger | APPROVED | No | 2024-05-27 | Abas, Mohammed Fekry | 2024-05-28 | 2024-05-28 |  |  |  | 550000 | 5742 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 457000 | APPROVED |  |  | 2024-07-09 | 93000 | 42 | Muhammad, Muhammad Atif | -45440 | 42
105-115 | North Khobar Dist. 115/13.8kV | 3578 | North Khobar Dist. 115/13.8kV-Grounding Material Accessories | APPROVED | No | 2024-06-03 | Abas, Mohammed Fekry | 2024-06-03 | 2024-06-04 |  |  |  | 73475 | 5560 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 72850 | APPROVED |  |  | 2024-07-07 | 625 | 33 | Muhammad, Muhammad Atif | -45447 | 33
105-115 | North Khobar Dist. 115/13.8kV | 3723 | North Khobar Dist. 115/13.8kV-MV POWER CABLE ( 1C × 630mm2 & 1×3C×300mm2 ) | APPROVED | No | 2024-07-01 | Abas, Mohammed Fekry | 2024-07-04 | 2024-07-04 |  |  |  | 1069560 | 6026 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 956014.2 | APPROVED |  |  | 2024-10-09 | 113545.8 | 97 | Badhman, Saeed | -45477 | 97
105-115 | North Khobar Dist. 115/13.8kV | 3781 | North Khobar Dist. 115/13.8kV-Garbage Waste Container, 12 Cu. M (1-year) | APPROVED | No | 2024-07-07 | Abas, Mohammed Fekry | 2024-07-09 | 2024-07-09 |  |  |  | 28800 | 5884 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 19200 | APPROVED |  |  | 2024-08-20 | 9600 | 42 | Akhtar, Farhan | -45482 | 42
105-115 | North Khobar Dist. 115/13.8kV | 3835 | North Khobar Dist. 115/13.8kV-Testing for Plate load test-4Points | APPROVED | No | 2024-07-11 | Abas, Mohammed Fekry | 2024-07-21 | 2024-07-21 |  |  |  | 8400 | 5943 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 7540 | APPROVED |  |  | 2024-10-08 | 860 | 79 | Tananeh, Khalid Jamal | -45494 | 79
105-115 | North Khobar Dist. 115/13.8kV | 3876 | North Khobar Dist. 115/13.8kV-Control Cable | APPROVED | No | 2024-07-13 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 716000 | 5828 | 0 | STANDARD | ALFANAR CO | SAR | 531752.8 | APPROVED |  |  | 2024-08-28 | 184247.2 | 43 | Muhammad, Muhammad Atif | -45489 | 43
105-115 | North Khobar Dist. 115/13.8kV | 3900 | North Khobar Dist. 115/13.8kV-Testing & Commissioning | APPROVED | No | 2024-07-15 | Abas, Mohammed Fekry | 2024-07-17 | 2024-07-18 |  |  |  | 2042370 | 6449 | 0 | STANDARD | Al Fanar Technical Services | SAR | 1985000 | APPROVED |  |  | 2025-03-13 | 57370 | 238 | Alqadhi, Abdulrahman Abdulghani | -45491 | 238
105-115 | North Khobar Dist. 115/13.8kV | 3906 | North Khobar Dist. 115/13.8kV-RTV Coating | APPROVED | No | 2024-07-15 | Abas, Mohammed Fekry | 2024-07-17 | 2024-07-18 |  |  |  | 250000 | 6178 | 0 | STANDARD | SAUDI CONDUIT COATING CO. (S3C) | SAR | 35268 | APPROVED |  |  | 2024-10-13 | 214732 | 87 | Muaz, Alaa | -45491 | 87
105-115 | North Khobar Dist. 115/13.8kV | 3911 | North Khobar Dist. 115/13.8kV-MV TERMINATION KITS ( 1C × 630mm2 & 3C×300mm2 ) | APPROVED | No | 2024-07-16 | Abas, Mohammed Fekry | 2024-07-17 | 2024-07-18 |  |  |  | 98839 | 5988 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 95871.89 | APPROVED |  |  | 2024-09-19 | 2967.11 | 63 | Badhman, Saeed | -45491 | 63
105-115 | North Khobar Dist. 115/13.8kV | 4023 | North Khobar Dist. 115/13.8kV-LCLM | APPROVED | No | 2024-07-25 | Abas, Mohammed Fekry | 2024-07-29 | 2024-07-29 |  |  |  | 59075 | 5965 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 59075 | APPROVED |  |  | 2024-10-06 | 0 | 69 | Badhman, Saeed | -45502 | 69
105-115 | North Khobar Dist. 115/13.8kV | 4171 | North Khobar Dist. 115/13.8kV-LV AC / DC Cables and Lighitng Wires | APPROVED | No | 2024-08-17 | Abas, Mohammed Fekry | 2024-08-19 | 2024-08-19 |  |  |  | 1611070 | 6083 | 0 | STANDARD | ALFANAR CO | SAR | 1110509.38 | APPROVED |  |  | 2024-10-06 | 500560.62 | 48 | Badhman, Saeed | -45523 | 48
105-115 | North Khobar Dist. 115/13.8kV | 4181 | North Khobar Dist. 115/13.8kV-Hazardou and Non Hazardous Waste | APPROVED | No | 2024-08-18 | Abas, Mohammed Fekry | 2024-08-19 | 2024-08-19 |  |  |  | 5000 | 6113 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 3650 | APPROVED |  |  | 2024-09-16 | 1350 | 28 | Akhtar, Farhan | -45523 | 28
105-115 | North Khobar Dist. 115/13.8kV | 4205 | North Khobar Dist. 115/13.8kV-Supply and delivery of drinking Water 6 Cu. M Fiber Glass tank | APPROVED | No | 2024-08-19 | Abas, Mohammed Fekry | 2024-08-21 | 2024-08-22 |  |  |  | 3000 | 6093 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 3000 | APPROVED |  |  | 2024-09-02 | 0 | 11 | Akhtar, Farhan | -45526 | 11
105-115 | North Khobar Dist. 115/13.8kV | 4208 | North Khobar Dist. 115/13.8kV-Supply and delivery of Raw Water 10 Cu. M tanker | APPROVED | No | 2024-08-19 | Alharbi, Atef Saud | 2024-08-20 | 2024-08-21 |  |  |  | 1800 | 6093 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 1800 | APPROVED |  |  | 2024-09-02 | 0 | 12 | Akhtar, Farhan | -45525 | 12
105-115 | North Khobar Dist. 115/13.8kV | 4213 | North Khobar Dist. 115/13.8kV-Sewage water removal services 10,000 liters | APPROVED | No | 2024-08-19 | Abas, Mohammed Fekry | 2024-08-21 | 2024-08-22 |  |  |  | 300 | 6093 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 300 | APPROVED |  |  | 2024-09-02 | 0 | 11 | Akhtar, Farhan | -45526 | 11
105-115 | North Khobar Dist. 115/13.8kV | 4232 | North Khobar Dist. 115/13.8kV-Grounding cables, 0.6/1 KV, Y/G | APPROVED | No | 2024-08-21 | Abas, Mohammed Fekry | 2024-08-22 | 2024-08-22 |  |  |  | 244150 | 6067 | 0 | STANDARD | ALFANAR CO | SAR | 226756.52 | APPROVED |  |  | 2024-09-18 | 17393.48 | 27 | Muhammad, Muhammad Atif | -45526 | 27
105-115 | North Khobar Dist. 115/13.8kV | 4290 | North Khobar Dist. 115/13.8kV-Cable Tray and its accessories | APPROVED | No | 2024-08-28 | Abas, Mohammed Fekry | 2024-08-29 | 2024-09-01 |  |  |  | 460016.15 | 6151 | 0 | STANDARD | Electrolink Co Ltd | SAR | 459950.01 | APPROVED |  |  | 2024-09-26 | 66.14 | 25 | Muhammad, Muhammad Atif | -45536 | 25
105-115 | North Khobar Dist. 115/13.8kV | 4321 | North Khobar Dist. 115/13.8kV-Station Service Transformer-750KVA | APPROVED | No | 2024-08-29 | Abas, Mohammed Fekry | 2024-09-16 | 2024-09-17 |  |  |  | 164000 | 5911 | 0 | STANDARD | ALFANAR CO | SAR | 164000 | APPROVED |  |  | 2024-10-06 | 0 | 19 | Muhammad, Muhammad Atif | -45552 | 19
105-115 | North Khobar Dist. 115/13.8kV | 4361 | North Khobar Dist. 115/13.8kV-3rd Party lab Inspector For Precast Concrete Prodaction Test | APPROVED | No | 2024-09-04 | Abas, Mohammed Fekry | 2024-09-04 | 2024-09-05 |  |  |  | 84190 | 6138 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 84190 | APPROVED |  |  | 2024-10-07 | 0 | 32 | Tananeh, Khalid Jamal | -45540 | 32
105-115 | North Khobar Dist. 115/13.8kV | 4370 | North Khobar Dist. 115/13.8kV-Fire Protection System | APPROVED | No | 2024-09-04 | Abas, Mohammed Fekry | 2024-09-05 | 2024-09-05 |  |  |  | 2125389 | 6007 | 0 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 2125389 | APPROVED |  |  | 2024-09-18 | 0 | 13 | Muhammad, Muhammad Atif | -45540 | 13
105-115 | North Khobar Dist. 115/13.8kV | 4566 | North Khobar Dist. 115/13.8kV-Soil Investigation & Electrical Resistivity Soil test | APPROVED | No | 2024-10-01 | Abas, Mohammed Fekry | 2024-10-02 | 2024-10-02 |  |  |  | 10000 | 6335 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 6400 | APPROVED |  |  | 2024-10-20 | 3600 | 18 | Tananeh, Khalid Jamal | -45567 | 18
105-115 | North Khobar Dist. 115/13.8kV | 4590 | North Khobar Dist. 115/13.8kV-Electrical Installation Sub Contractor | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-06 | 2024-10-06 |  |  |  | 2992521 | 6369 | 0 | STANDARD | SMART LINES INDUSTRIAL & SERVCIES COMPANY | SAR | 2340000 | APPROVED |  |  | 2025-04-09 | 652521 | 185 | Abdulqader, Ahmed Abdulhalim | -45571 | 185
105-115 | North Khobar Dist. 115/13.8kV | 4676 | North Khobar Dist. 115/13.8kV-HVAC SYSTEM | APPROVED | No | 2024-10-15 | Abas, Mohammed Fekry | 2024-10-16 | 2024-10-17 |  |  |  | 2220000 | 6208 | 0 | STANDARD | MAINTENANCE OF AIRCONDITION AND REFRIGERATION COMPANY LTD.(MARCO) | SAR | 2050000 | APPROVED |  |  | 2024-10-30 | 170000 | 13 | Muhammad, Muhammad Atif | -45582 | 13
105-115 | North Khobar Dist. 115/13.8kV | 4765 | North Khobar Dist. 115/13.8kV-Soil Report | RETURNED | No | 2024-10-21 | Alhadi, Khalid | 2024-11-17 | 2024-10-22 | 2024-11-17 |  | No Feedback from PM and Engr. Amr | 15000 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45587 | -45587
105-115 | North Khobar Dist. 115/13.8kV | 4801 | North Khobar Dist. 115/13.8kV-PLATE BEARING TEST (PLATE LOAD) | REJECTED | No | 2024-10-28 | Ibrahim, Mahmoud Hassan Ali | 2024-11-06 | 2024-10-28 |  | 2024-11-07 |  | 8400 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45593 | -45593
105-115 | North Khobar Dist. 115/13.8kV | 4948 | North Khobar Dist. 115/13.8kV-Lighting Fixtures | APPROVED | No | 2024-11-14 | Abas, Mohammed Fekry | 2024-11-20 | 2024-11-20 |  |  |  | 71998 | 6474 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 71998 | APPROVED |  |  | 2024-11-28 | 0 | 8 | Muhammad, Muhammad Atif | -45616 | 8
105-115 | North Khobar Dist. 115/13.8kV | 5093 | North Khobar Dist. 115/13.8kV-HCIS-3 Consultancy for Security System | APPROVED | No | 2024-11-30 | Abas, Mohammed Fekry | 2024-12-25 | 2024-12-26 |  |  |  | 33500 | 6513 | 0 | STANDARD | Khaled Drewesh Office for Consulting Security (KDOCS) | SAR | 33500 | APPROVED |  |  | 2025-01-13 | 0 | 18 | Muhammad, Muhammad Atif | -45652 | 18
105-115 | North Khobar Dist. 115/13.8kV | 5105 | North Khobar Dist. 115/13.8kV-Fiber Optic Cables & Accessories, Installation and Testing Services-2.13 | APPROVED | No | 2024-12-01 | Abas, Mohammed Fekry | 2024-12-08 | 2024-12-09 |  |  |  | 220000 | 6619 | 0 | STANDARD | Arabian Power Trading Est. | SAR | 188000 | APPROVED |  |  | 2024-12-26 | 32000 | 17 | Muhammad, Muhammad Atif | -45635 | 17
105-115 | North Khobar Dist. 115/13.8kV | 5115 | North Khobar Dist. 115/13.8kV-Al. Connector for GIB Bushing | APPROVED | No | 2024-12-03 | Abas, Mohammed Fekry | 2024-12-08 | 2024-12-09 |  |  |  | 5675 | 6417 | 0 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 4617.79 | APPROVED |  |  | 2025-01-02 | 1057.21 | 24 | Mohammed, Faisal Ansari | -45635 | 24
105-115 | North Khobar Dist. 115/13.8kV | 5142 | North Khobar Dist. 115/13.8kV-Supply and delivery of drinking Water 6 Cu. M Fiber Glass tank | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-08 | 2024-12-09 |  |  |  | 5250 | 6685 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 4500 | APPROVED |  |  | 2025-01-02 | 750 | 24 | Akhtar, Farhan | -45635 | 24
105-115 | North Khobar Dist. 115/13.8kV | 5147 | North Khobar Dist. 115/13.8kV-Supply and delivery of Raw Water 10 Cu. M tanker | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-08 | 2024-12-09 |  |  |  | 2100 | 6685 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 1800 | APPROVED |  |  | 2025-01-02 | 300 | 24 | Akhtar, Farhan | -45635 | 24
105-115 | North Khobar Dist. 115/13.8kV | 5152 | North Khobar Dist. 115/13.8kV-Sewage water removal services 10,000 liters | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-08 | 2024-12-09 |  |  |  | 300 | 6685 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 300 | APPROVED |  |  | 2025-01-02 | 0 | 24 | Akhtar, Farhan | -45635 | 24
105-115 | North Khobar Dist. 115/13.8kV | 5160 | North Khobar Dist. 115/13.8kV-Civil Sub Contractor | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-08 | 2024-12-09 |  |  |  | 7200000 | 5664 | 0 | STANDARD | Intelligent System General Contracting Company | SAR | 7200000 | APPROVED |  |  | 2024-12-18 | 0 | 9 | Tananeh, Khalid Jamal | -45635 | 9
105-115 | North Khobar Dist. 115/13.8kV | 5359 | North Khobar Dist. 115/13.8kV-Supply of Conduits and Fittings | APPROVED | No | 2025-01-06 | Abas, Mohammed Fekry | 2025-01-08 | 2025-01-12 |  |  |  | 337272.4 | 6716 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 337271.55 | APPROVED |  |  | 2025-01-22 | 0.85 | 10 | Muaz, Alaa | -45669 | 10
105-115 | North Khobar Dist. 115/13.8kV | 5387 | North Khobar Dist. 115/13.8kV-150mm2 Tinned Copper Conductor | APPROVED | No | 2025-01-12 | Abas, Mohammed Fekry | 2025-01-14 | 2025-01-14 |  |  |  | 131100 | 6811 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 121307.52 | APPROVED |  |  | 2025-02-25 | 9792.48 | 42 | Alhadi, Khalid | -45671 | 42
105-115 | North Khobar Dist. 115/13.8kV | 5484 | North Khobar Dist. 115/13.8kV-CT Junction Box with 9 Single Phase CTPU - Including all accessories | APPROVED | No | 2025-01-20 | Abas, Mohammed Fekry | 2025-01-26 | 2025-01-26 |  |  |  | 68000 | 6289 | 0 | STANDARD | Energy Tracks For Contracting | SAR | 68000 | APPROVED |  |  | 2025-03-04 | 0 | 37 | Kumar, Mr. Ranjan | -45683 | 37
105-115 | North Khobar Dist. 115/13.8kV | 5543 | North Khobar Dist. 115/13.8kV-Remote End Modifications TFR & DSM | APPROVED | No | 2025-01-23 | Abas, Mohammed Fekry | 2025-01-26 | 2025-01-26 |  |  |  | 100000 | 7454 | 0 | STANDARD | TRINERGY TECHNOLOGIES SA | SAR | 61231 | APPROVED |  |  | 2025-07-06 | 38769 | 161 | Babic, Marian | -45683 | 161
105-115 | North Khobar Dist. 115/13.8kV | 5701 | North Khobar Dist. 115/13.8kV-Groudning System Accessories | RETURNED | No | 2025-01-28 | Abdulqader, Ahmed Abdulhalim | 2025-03-18 | 2025-01-30 | 2025-03-18 |  | PR amount is less than the received offers | 53260 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45687 | -45687
105-115 | North Khobar Dist. 115/13.8kV | 5799 | North Khobar Dist. 115/13.8kV-TEA BOY | APPROVED | No | 2025-02-05 | Abas, Mohammed Fekry | 2025-02-17 | 2025-02-18 |  |  |  | 12000 | 6946 | 0 | STANDARD | Nor Sail Contracting Est. | SAR | 12000 | APPROVED |  |  | 2025-04-24 | 0 | 65 | Abuhammad, Samir | -45706 | 65
105-115 | North Khobar Dist. 115/13.8kV | 6106 | North Khobar Dist. 115/13.8kV-Drawing Printing & Scanning | APPROVED | No | 2025-03-03 | Abas, Mohammed Fekry | 2025-03-05 | 2025-03-05 |  |  | Line Item: 2.33 - Drawing Printing & Scanning | 35000 | 7064 | 0 | STANDARD | Print Magaies Al abdaa Printing | SAR | 35000 | APPROVED |  |  | 2025-04-07 | 0 | 33 | Abuhammad, Samir | -45721 | 33
105-115 | North Khobar Dist. 115/13.8kV | 6208 | North Khobar Dist. 115/13.8kV-Asphalt Work | APPROVED | No | 2025-03-19 | Abas, Mohammed Fekry | 2025-03-19 | 2025-03-20 |  |  | line item2.20-Asphalt Work | 192174 | 5664 | 1 | STANDARD | Intelligent System General Contracting Company | SAR | 192173.65 | APPROVED |  |  | 2025-04-24 | 0.35 | 35 | Tananeh, Khalid Jamal | -45736 | 35
105-115 | North Khobar Dist. 115/13.8kV | 6209 | North Khobar Dist. 115/13.8kV-Excavation Work | APPROVED | No | 2025-03-19 | Abas, Mohammed Fekry | 2025-03-19 | 2025-03-20 |  |  | line item 2.20-Excavation Work | 71500 | 5664 | 1 | STANDARD | Intelligent System General Contracting Company | SAR | 71500 | APPROVED |  |  | 2025-04-24 | 0 | 35 | Tananeh, Khalid Jamal | -45736 | 35
105-115 | North Khobar Dist. 115/13.8kV | 6210 | North Khobar Dist. 115/13.8kV-Base Course work | APPROVED | No | 2025-03-19 | Abas, Mohammed Fekry | 2025-03-19 | 2025-03-20 |  |  | LINE ITEM 2.20-Base Course work | 182000 | 5664 | 1 | STANDARD | Intelligent System General Contracting Company | SAR | 182000 | APPROVED |  |  | 2025-04-24 | 0 | 35 | Tananeh, Khalid Jamal | -45736 | 35
105-115 | North Khobar Dist. 115/13.8kV | 6211 | North Khobar Dist. 115/13.8kV-General Backfilling work | APPROVED | No | 2025-03-19 | Abas, Mohammed Fekry | 2025-03-19 | 2025-03-20 |  |  | line item 2.20-General Backfilling work | 175000 | 5664 | 1 | STANDARD | Intelligent System General Contracting Company | SAR | 175000 | APPROVED |  |  | 2025-04-24 | 0 | 35 | Tananeh, Khalid Jamal | -45736 | 35
105-115 | North Khobar Dist. 115/13.8kV | 6366 | North Khobar Dist. 115/13.8kV-7X2.5 mm2 CU/XLPE/CTS/PVC | APPROVED | No | 2025-04-17 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-21 |  |  | line item 2.13-7X2.5 mm2 CU/XLPE/CTS/PVC | 52600 | 6785 | 0 | STANDARD | ALFANAR CO | SAR | 52600 | APPROVED |  |  | 2025-05-01 | 0 | 10 | Muaz, Alaa | -45768 | 10
|  |  | 0.6/1 KV – Blue Color | [8 empty] | 0.6/1 KV – Blue Color | [14 empty] | 0 | 0
105-115 | North Khobar Dist. 115/13.8kV | 6397 | North Khobar Dist. 115/13.8kV-Tower AC-5T0N | APPROVED | No | 2025-04-20 | Abas, Mohammed Fekry | 2025-04-21 | 2025-04-21 |  |  | line item 2.33-Tower AC-5T0N | 71760 | 7182 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 61600 | APPROVED |  |  | 2025-04-24 | 10160 | 3 | Abuhammad, Samir | -45768 | 3
105-115 | North Khobar Dist. 115/13.8kV | 6416 | North Khobar Dist. 115/13.8kV-Sealant work for External Wall | REJECTED | No | 2025-04-22 | Ibrahim, Mahmoud Hassan Ali | 2025-06-24 | 2025-04-22 |  | 2025-06-25 |  | 55000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45769 | -45769
105-115 | North Khobar Dist. 115/13.8kV | 6433 | North Khobar Dist. 115/13.8kV-Supply & Delivery of Raw Water,Drinking Water & Sweage Removal | APPROVED | No | 2025-04-23 | Abas, Mohammed Fekry | 2025-04-23 | 2025-04-24 |  |  | line item2.33-Supply & Delivery of Raw Water,Drinking Water & Sweage Removal | 6600 | 6685 | 1 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 6600 | APPROVED |  |  | 2025-07-14 | 0 | 81 | Akhtar, Farhan | -45771 | 81
105-115 | North Khobar Dist. 115/13.8kV | 6514 | North Khobar Dist. 115/13.8kV-4P x 1.5 Sqmm Cable | APPROVED | No | 2025-05-05 | Abas, Mohammed Fekry | 2025-05-06 | 2025-05-06 |  |  | Line Item: 2.13 - 4P x 1.5 Sqmm Cable | 9000 | 7318 | 0 | STANDARD | Middle East Specialized Cables Mesc | SAR | 7500 | APPROVED |  |  | 2025-05-27 | 1500 | 21 | Abuhammad, Samir | -45783 | 21
105-115 | North Khobar Dist. 115/13.8kV | 6692 | North Khobar Dist. 115/13.8kV-Grounding Accessories | APPROVED | No | 2025-05-22 | Abas, Mohammed Fekry | 2025-05-27 | 2025-05-27 |  |  | Line Item 2.21 - Grounding Accessories | 71134.7 | 7094 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 71134.7 | APPROVED |  |  | 2025-06-22 | 0 | 26 | Abdulqader, Ahmed Abdulhalim | -45804 | 26
105-115 | North Khobar Dist. 115/13.8kV | 6744 | North Khobar Dist. 115/13.8kV-125V DC DB for Communication System | APPROVED | No | 2025-05-28 | Abas, Mohammed Fekry | 2025-07-06 | 2025-07-07 |  |  | Line Item: 2.12 - 125V DC DB for Communication System | 35000 | 7524 | 0 | STANDARD | HAWA ELECTRIC PANEL BOARD FAC | SAR | 29700 | APPROVED |  |  | 2025-07-27 | 5300 | 20 | Abuhammad, Samir | -45845 | 20
105-115 | North Khobar Dist. 115/13.8kV | 6785 | North Khobar Dist. 115/13.8kV-Communication System | APPROVED | No | 2025-06-12 | Abas, Mohammed Fekry | 2025-06-15 | 2025-06-15 |  |  | line item 2.4-Communication System | 1762053 | 5853 | 0 | STANDARD | ALFANAR CO | SAR | 1762052.39 | APPROVED |  |  | 2025-06-24 | 0.61 | 9 | Kumar, Mr. Ranjan | -45823 | 9
105-115 | North Khobar Dist. 115/13.8kV | 6914 | North Khobar Dist. 115/13.8kV-Wiring devices( Switches, Socket and Push Buttons) | APPROVED | No | 2025-06-26 | Abas, Mohammed Fekry | 2025-06-30 | 2025-07-01 |  |  | line item 2.23-Wiring devices( Switches, Socket and Push Buttons) | 99975 | 7171 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 99975 | APPROVED |  |  | 2025-07-14 | 0 | 13 | Muaz, Alaa | -45839 | 13
105-115 | North Khobar Dist. 115/13.8kV | 6934 | North Khobar Dist. 115/13.8kV-Security Guard | APPROVED | No | 2025-06-30 | Abas, Mohammed Fekry | 2025-07-03 | 2025-07-03 |  |  | line item 2.30-Security Guard | 76500 | 7491 | 0 | STANDARD | Rukn Al Kateibah Company for Security Guards. | SAR | 38250 | APPROVED |  |  | 2025-07-20 | 38250 | 17 | Abuhammad, Samir | -45841 | 17
105-115 | North Khobar Dist. 115/13.8kV | 6976 | North Khobar Dist. 115/13.8kV-CCTV-Security System | APPROVED | No | 2025-07-03 | Abas, Mohammed Fekry | 2025-07-07 | 2025-07-07 |  |  | line item 2.7-CCTV | 781283 | 6633 | 0 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 781283 | APPROVED |  |  | 2025-07-24 | 0 | 17 | Abdulqader, Ahmed Abdulhalim | -45845 | 17
105-115 | North Khobar Dist. 115/13.8kV | 7017 | North Khobar Dist. 115/13.8kV-HV MV Cable Supports | APPROVED | No | 2025-07-08 | Abas, Mohammed Fekry | 2025-07-09 | 2025-07-09 |  |  | line item 2.19-HV/MV Cable supports | 127468 | 7301 | 0 | STANDARD | ISAM KABBANI &Partners | SAR | 127468 | APPROVED |  |  | 2025-09-29 | 0 | 82 | Hegazy, Ayman | -45847 | 82
105-115 | North Khobar Dist. 115/13.8kV | 7073 | North Khobar Dist. 115/13.8kV-MV Clamp/Cleats | INCOMPLETE | No |  | Mughal, Aurang | 2025-07-13 |  |  |  | line item 2.19-HV/MV Cable supports | 23750 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | 0 | 0
105-115 | North Khobar Dist. 115/13.8kV | 7082 | North Khobar Dist. 115/13.8kV-Supply with installation of AC units Stand Type 5 Ton | APPROVED | No | 2025-07-13 | Abas, Mohammed Fekry | 2025-07-14 | 2025-07-14 |  |  | line item 2.33-Supply with installation of AC units Stand Type 5 Ton | 30000 | 7518 | 0 | STANDARD | Versatile Advanced Limited Company. | SAR | 27000 | APPROVED |  |  | 2025-07-24 | 3000 | 10 | Akhtar, Farhan | -45852 | 10
105-115 | North Khobar Dist. 115/13.8kV | 7089 | North Khobar Dist. 115/13.8kV-PDS System | APPROVED | No | 2025-07-14 | Abas, Mohammed Fekry | 2025-07-22 | 2025-07-22 |  |  | line item 2.5-PDS System | 200000 | 7756 | 0 | STANDARD | RASHID SAEED AHMED AL GHAMDI COMM INFO TRAD EST | SAR | 140000 | APPROVED |  |  | 2025-10-30 | 60000 | 100 | Abdulqader, Ahmed Abdulhalim | -45860 | 100
105-115 | North Khobar Dist. 115/13.8kV | 7114 | North Khobar Dist. 115/13.8kV-MV CABLE CLAMPS /CLEATS | APPROVED | No | 2025-07-16 | Abas, Mohammed Fekry | 2025-07-20 | 2025-07-20 |  |  | line item 2.13-MV Cable Clamp | 56525 | 7255 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 56525 | APPROVED |  |  | 2025-08-10 | 0 | 21 | Hegazy, Ayman | -45858 | 21
105-115 | North Khobar Dist. 115/13.8kV | 7123 | North Khobar Dist. 115/13.8kV-Supply & Installation of H-Beam | REJECTED | No | 2025-07-17 | Ibrahim, Mahmoud Hassan Ali | 2025-12-21 | 2025-07-17 |  | 2025-12-21 |  | 66000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45855 | -45855
105-115 | North Khobar Dist. 115/13.8kV | 7195 | North Khobar Dist. 115/13.8kV-MV POWER CABLE -3C×300mm2 | APPROVED | No | 2025-07-23 | Abas, Mohammed Fekry | 2025-07-28 | 2025-07-28 |  |  | line item 2.13-MV POWER CABLE -3C×300mm2 | 112428 | 6026 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 112428 | APPROVED |  |  | 2025-08-12 | 0 | 15 | Abdulqader, Ahmed Abdulhalim | -45866 | 15
105-115 | North Khobar Dist. 115/13.8kV | 7276 | North Khobar Dist. 115/13.8kV-Fence Relocation work | APPROVED | No | 2025-08-04 | Abas, Mohammed Fekry | 2025-08-07 | 2025-08-10 |  |  | line item 2.20-Relocation of Fence with all Accessories | 31920 | 7104 | 0 | STANDARD | Construction Expertise Est. | SAR | 31920 | APPROVED |  |  | 2025-08-21 | 0 | 11 | Abdulqader, Ahmed Abdulhalim | -45879 | 11
105-115 | North Khobar Dist. 115/13.8kV | 7280 | North Khobar Dist. 115/13.8kV-Water Proofing work | APPROVED | No | 2025-08-04 | Abas, Mohammed Fekry | 2025-08-05 | 2025-08-06 |  |  | LINE ITEM 2.20-Water Proofing work | 27303 | 5657 | 1 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 27302.47 | APPROVED |  |  | 2025-09-17 | 0.53 | 42 | Tananeh, Khalid Jamal | -45875 | 42
105-115 | North Khobar Dist. 115/13.8kV | 7342 | North Khobar Dist. 115/13.8kV-Control Cables | REJECTED | No | 2025-08-12 | Khan, Muhammad Safdar | 2025-08-31 | 2025-08-12 |  | 2025-08-31 |  | 188000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45881 | -45881
105-115 | North Khobar Dist. 115/13.8kV | 7503 | DECORATIVE FENCE | APPROVED | No | 2025-08-26 | Abas, Mohammed Fekry | 2025-08-26 | 2025-08-26 |  |  | Line item 2.20-DECORATIVE FENCE | 0 | 7656 | 0 | STANDARD | Fursan Construction Industry Factory Industry Factory | SAR | 428370 | APPROVED |  |  | 2025-09-14 | -428370 | 19 | Hegazy, Ayman | -45895 | 19
105-115 | North Khobar Dist. 115/13.8kV | 7508 | Steel Parapet Works | APPROVED | No | 2025-08-26 | Abas, Mohammed Fekry | 2025-08-27 | 2025-08-28 |  |  | line item 2.20-Steel Parapet Works | 0 | 6819 | 0 | STANDARD | RAFCO Factory Company For Metal Industries | SAR | 36022 | APPROVED |  |  | 2025-09-07 | -36022 | 10 | Hegazy, Ayman | -45897 | 10
105-115 | North Khobar Dist. 115/13.8kV | 7552 | lugs and Glands | RETURNED | No | 2025-08-28 | Abdulqader, Ahmed Abdulhalim | 2025-10-12 | 2025-09-03 | 2025-10-12 |  | not required PO already uploaded in system | 0 | 7577 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 13947.12 | APPROVED |  |  | 2025-10-07 | -13947.12 |  | Abdulqader, Ahmed Abdulhalim | -45903 | 34
105-115 | North Khobar Dist. 115/13.8kV | 7552 | lugs and Glands | RETURNED | No | 2025-08-28 | Abdulqader, Ahmed Abdulhalim | 2025-10-12 | 2025-09-03 | 2025-10-12 |  | not required PO already uploaded in system | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45903 | -45903
105-115 | North Khobar Dist. 115/13.8kV | 7665 | Cable Lugs | APPROVED | No | 2025-09-07 | Abas, Mohammed Fekry | 2025-09-10 | 2025-09-13 |  |  | line item 2.13-Cable lugs | 0 | 7577 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 6483.36 | APPROVED |  |  | 2025-10-07 | -6483.36 | 24 | Abdulqader, Ahmed Abdulhalim | -45913 | 24
105-115 | North Khobar Dist. 115/13.8kV | 7751 | 250kVA Diesel Generator | RETURNED | No | 2025-09-15 | Badhman, Saeed | 2025-10-27 | 2025-09-16 | 2025-10-27 |  | PR isnt compleate | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45916 | -45916
105-115 | North Khobar Dist. 115/13.8kV | 7780 | Substation Office Furniture | APPROVED | No | 2025-09-17 | Abas, Mohammed Fekry | 2025-09-18 | 2025-09-19 |  |  | Line Item 2.33 - Substation Office Furniture. | 0 | 7712 | 0 | STANDARD | ALISMAIL INDUSTRIAL CO.(S) | SAR | 17590 | APPROVED |  |  | 2025-10-07 | -17590 | 18 | Abdulqader, Ahmed Abdulhalim | -45919 | 18
105-115 | North Khobar Dist. 115/13.8kV | 7939 | Lighting Control System/Motion Sensors | RETURNED | No | 2025-10-09 | Muaz, Alaa | 2025-10-20 | 2025-10-15 | 2025-10-20 |  | Not found in the PO annex | 0 | 7341 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 68054 | APPROVED |  |  | 2025-10-26 | -68054 |  | Muaz, Alaa | -45945 | 11
105-115 | North Khobar Dist. 115/13.8kV | 7939 | Lighting Control System/Motion Sensors | RETURNED | No | 2025-10-09 | Muaz, Alaa | 2025-10-20 | 2025-10-15 | 2025-10-20 |  | Not found in the PO annex | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -45945 | -45945
105-115 | North Khobar Dist. 115/13.8kV | 7971 | Technicians for Testing & Commissioning | APPROVED | No | 2025-10-16 | Abas, Mohammed Fekry | 2025-10-23 | 2025-10-25 |  |  | line item 2.31-Technicians needed for T&C stage = 12400 Mhrs. with 25Nos. of Technician | 0 | 7850 | 0 | STANDARD | Jasem M.AlJasem Contracting Est. | SAR | 248000 | APPROVED |  |  | 2025-11-16 | -248000 | 22 | Babic, Marian | -45955 | 22
105-115 | North Khobar Dist. 115/13.8kV | 8011 | Lighting Wires | APPROVED | No | 2025-10-20 | Abas, Mohammed Fekry | 2025-10-23 | 2025-10-25 |  |  | Line Item: 2.13 - Lighting Wires | 0 | 7964 | 0 | STANDARD |  | SAR | 0 | INCOMPLETE |  |  |  | 0 | 99 | Mohammed, Mohammed Adel Fahmy | -45955 | -45955
105-115 | North Khobar Dist. 115/13.8kV | 8011 | Lighting Wires | APPROVED | No | 2025-10-20 | Abas, Mohammed Fekry | 2025-10-23 | 2025-10-25 |  |  | Line Item: 2.13 - Lighting Wires | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -45955 | -45955
105-115 | North Khobar Dist. 115/13.8kV | 8041 | Swing Gate Motor | APPROVED | No | 2025-10-23 | Abas, Mohammed Fekry | 2025-10-27 | 2025-10-27 |  |  | Line item 2.20-Swing Gate Motor-Including All Accessories, Procurement, Installation, Testing & Commissioning. | 0 | 7925 | 0 | STANDARD | ALMOSALLAMY INDUSTRIAL COMPANY | SAR | 9330 | APPROVED |  |  | 2025-12-15 | -9330 | 49 | Abdelraouf, Islam ِAdel Hanafy | -45957 | 49
105-115 | North Khobar Dist. 115/13.8kV | 8042 | Lighting Motion Sensor | RETURNED | No | 2025-10-23 | Muaz, Alaa | 2025-11-03 | 2025-10-27 | 2025-11-03 |  | Raised by mistake based on discussion with Mr. Aruan | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -45957 | -45957
105-115 | North Khobar Dist. 115/13.8kV | 8070 | 250kVA Diesel Generator | APPROVED | No | 2025-10-28 | Abas, Mohammed Fekry | 2025-10-29 | 2025-10-30 |  |  | line item 2.33-250kVA Diesel Generator-2nos. for 1 months -North Khobar SS | 0 | 7883 | 0 | STANDARD | Energia Model General Contracting Company | SAR | 21000 | APPROVED |  |  | 2025-12-11 | -21000 | 42 | Badhman, Saeed | -45960 | 42
105-115 | North Khobar Dist. 115/13.8kV | 8590 | Metal Works (Change Order) | RETURNED | No | 2025-12-28 | Tananeh, Khalid Jamal | 2026-01-22 | 2026-01-01 | 2026-01-22 |  | return as per email from Arnie, in Thu 22/01/2026 10:36 AM | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -46023 | -46023
105-115 | North Khobar Dist. 115/13.8kV | 8643 | Metal Doors (Change Order) - North Khobar | APPROVED | No | 2026-01-05 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-13 |  |  | Budget line 2.20 - Civil Works | 0 | 6039 | 1 | STANDARD | AL MANASHY COMPANY | SAR | 10595.2 | APPROVED | 2026-01-21 | 2026-01-25 | 2026-01-28 | -10595.2 | 15 | Tananeh, Khalid Jamal | 12 | 15
105-115 | North Khobar Dist. 115/13.8kV | 8758 | Disposal of Hazardous Waste | APPROVED | No | 2026-01-21 | Abas, Mohammed Fekry | 2026-01-25 | 2026-01-26 |  |  | Line Item - 2.33: Disposal of Hazardous Waste | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -46048 | -46048
105-115 | North Khobar Dist. 115/13.8kV | 8783 | Substation Grounding Material | IN PROCESS | No | 2026-01-25 | Abas, Mohammed Fekry | 2026-01-29 | 2026-01-29 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46051 | -46051
105-115 | North Khobar Dist. 115/13.8kV | 8789 | Diesel For Generatro | IN PROCESS | No | 2026-01-25 | Abas, Mohammed Fekry | 2026-01-29 | 2026-01-29 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46051 | -46051
105-115 | North Khobar Dist. 115/13.8kV | 8796 | Supply & Delivery of Raw Water, Drinking Water & Sweage Removal | APPROVED | No | 2026-01-26 | Abas, Mohammed Fekry | 2026-01-29 | 2026-02-01 |  |  | Line Item - 2.33: Supply & Delivery of Raw Water, Drinking Water & Sweage Removal | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46054 | -46054
105-115 | North Khobar Dist. 115/13.8kV | 8797 | Supply of Cable Glands | IN PROCESS | No | 2026-01-26 | Abas, Mohammed Fekry | 2026-01-29 | 2026-01-29 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46051 | -46051
105-116 | North Thuqbah 115/13.8kv SS | 1942 | North Thuqbah 115/13.8kv SS-Engineering & Design North Thuqbah | APPROVED | No | 2023-12-12 | Abas, Mohammed Fekry | 2023-12-13 | 2023-12-13 |  |  |  | 581250 | 4895 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 570000 | APPROVED |  |  | 2024-01-08 | 11250 | 26 | Kumar, Mr. Ranjan | -45273 | 26
105-116 | North Thuqbah 115/13.8kv SS | 1950 | North Thuqbah 115/13.8kv SS-Control SAS protection panels- N.T | APPROVED | No | 2023-12-13 | Abas, Mohammed Fekry | 2023-12-13 | 2023-12-13 |  |  |  | 8775000 | 4857 | 0 | STANDARD | ALFANAR CO | SAR | 8775000 | APPROVED |  |  | 2024-01-15 | 0 | 33 | Kumar, Mr. Ranjan | -45273 | 33
105-116 | North Thuqbah 115/13.8kv SS | 1974 | North Thuqbah 115/13.8kv SS-13.8kV Switchgear | APPROVED | No | 2023-12-17 | Abas, Mohammed Fekry | 2023-12-17 | 2023-12-17 |  |  |  | 8210000 | 4861 | 0 | STANDARD | ALFANAR CO | SAR | 8210000 | APPROVED |  |  | 2024-01-18 | 0 | 32 | Alhadi, Khalid | -45277 | 32
105-116 | North Thuqbah 115/13.8kv SS | 2013 | North Thuqbah 115/13.8kv SS-Printer for Office use- Dammam Office | APPROVED | No | 2023-12-19 | Abas, Mohammed Fekry | 2023-12-19 | 2023-12-19 |  |  |  | 28200 | 4906 | 0 | STANDARD | Golden Technology trading Company. | SAR | 26000 | APPROVED |  |  | 2023-12-31 | 2200 | 12 | Abuhammad, Samir | -45279 | 12
105-116 | North Thuqbah 115/13.8kv SS | 2106 | North Thuqbah 115/13.8kv SS-Temporary Project Sign Board | APPROVED | No | 2024-01-08 | Abas, Mohammed Fekry | 2024-01-09 | 2024-01-09 |  |  |  | 20000 | 4973 | 0 | STANDARD | Construction Expertise Est. | SAR | 20000 | APPROVED |  |  | 2024-01-17 | 0 | 8 | Alhadi, Khalid | -45300 | 8
105-116 | North Thuqbah 115/13.8kv SS | 2256 | North Thuqbah 115/13.8kv SS-Fencing Work | APPROVED | No | 2024-01-23 | Abas, Mohammed Fekry | 2024-01-24 | 2024-01-25 |  |  |  | 92858.33 | 5137 | 0 | STANDARD | Construction Expertise Est. | SAR | 90802 | APPROVED |  |  | 2024-03-20 | 2056.33 | 55 | Alhadi, Khalid | -45316 | 55
105-116 | North Thuqbah 115/13.8kv SS | 2329 | North Thuqbah 115/13.8kv SS-Cyber Security | APPROVED | No | 2024-01-28 | Abas, Mohammed Fekry | 2024-01-29 | 2024-01-29 |  |  |  | 1000000 | 5056 | 0 | STANDARD | ALFANAR CO | SAR | 1000000 | APPROVED |  |  | 2024-02-18 | 0 | 20 | Babic, Marian | -45320 | 20
105-116 | North Thuqbah 115/13.8kv SS | 2356 | North Thuqbah 115/13.8kv SS- UG Scanning | APPROVED | No | 2024-01-29 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 1900 | 5069 | 0 | STANDARD | Construction Expertise Est. | SAR | 1900 | APPROVED |  |  | 2024-02-15 | 0 | 11 | Alhadi, Khalid | -45326 | 11
105-116 | North Thuqbah 115/13.8kv SS | 2499 | North Thuqbah 115/13.8kv SS-Temporary Fence, Gate Work & Security Cabin | APPROVED | No | 2024-02-07 | Abas, Mohammed Fekry | 2024-02-09 | 2024-02-10 |  |  |  | 8500 | 5137 | 0 | STANDARD | Construction Expertise Est. | SAR | 3299 | APPROVED |  |  | 2024-03-20 | 5201 | 39 | Alhadi, Khalid | -45332 | 39
105-116 | North Thuqbah 115/13.8kv SS | 2520 | North Thuqbah 115/13.8kv SS-Geotechnical Investigation | APPROVED | No | 2024-02-11 | Abas, Mohammed Fekry | 2024-02-11 | 2024-02-12 |  |  |  | 16000 | 5705 | 0 | STANDARD | International Agent Commercial Company(S) | SAR | 16000 | APPROVED |  |  | 2024-07-01 | 0 | 140 | Alhadi, Khalid | -45334 | 140
105-116 | North Thuqbah 115/13.8kv SS | 2533 | North Thuqbah 115/13.8kv SS-Super Structure Precast including Fire Walls | APPROVED | No | 2024-02-12 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-19 |  |  |  | 2421479 | 5383 | 0 | STANDARD | Factory of Ideal Precast Concrete System Company | SAR | 2095473 | APPROVED |  |  | 2024-05-01 | 326006 | 72 | Tananeh, Khalid Jamal | -45341 | 72
105-116 | North Thuqbah 115/13.8kv SS | 2618 | North Thuqbah 115/13.8kv SS-Site Office facility | APPROVED | No | 2024-02-19 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 325197 | 5159 | 0 | STANDARD | Construction Expertise Est. | SAR | 209900 | APPROVED |  |  | 2024-03-25 | 115297 | 28 | Muhammad, Muhammad Atif | -45348 | 28
105-116 | North Thuqbah 115/13.8kv SS | 2771 | North Thuqbah 115/13.8kv SS-Excavation of Normal Soil and Balidiyah (with) Disposal | APPROVED | No | 2024-03-05 | Abas, Mohammed Fekry | 2024-03-05 | 2024-03-07 |  |  |  | 54000 | 5264 | 0 | STANDARD | Morgan Construction for contracting | SAR | 54000 | APPROVED |  |  | 2024-04-15 | 0 | 39 | Alhadi, Khalid | -45358 | 39
105-116 | North Thuqbah 115/13.8kv SS | 2772 | North Thuqbah 115/13.8kv SS-General Backfilling | APPROVED | No | 2024-03-05 | Abas, Mohammed Fekry | 2024-03-05 | 2024-03-07 |  |  |  | 69520 | 5264 | 0 | STANDARD | Morgan Construction for contracting | SAR | 69520 | APPROVED |  |  | 2024-04-15 | 0 | 39 | Alhadi, Khalid | -45358 | 39
105-116 | North Thuqbah 115/13.8kv SS | 2773 | North Thuqbah 115/13.8kv SS-1000mm thick with Aggregate sub base class-"A(1A)" with CBR not less than 50 | APPROVED | No | 2024-03-05 | Abas, Mohammed Fekry | 2024-03-05 | 2024-03-07 |  |  |  | 27000 | 5264 | 0 | STANDARD | Morgan Construction for contracting | SAR | 27000 | APPROVED |  |  | 2024-04-15 | 0 | 39 | Alhadi, Khalid | -45358 | 39
105-116 | North Thuqbah 115/13.8kv SS | 2774 | North Thuqbah 115/13.8kv SS-600mm thick Aggregate base coarse (crashed stones) class-"A(1A) or A(1B)" with CBR not less than 100 | APPROVED | No | 2024-03-20 | Abas, Mohammed Fekry | 2024-03-21 | 2024-03-24 |  |  |  | 124200 | 5264 | 0 | STANDARD | Morgan Construction for contracting | SAR | 124200 | APPROVED |  |  | 2024-04-15 | 0 | 22 | Alhadi, Khalid | -45375 | 22
105-116 | North Thuqbah 115/13.8kv SS | 2775 | North Thuqbah 115/13.8kv SS-Shoring for 4 months duration | APPROVED | No | 2024-03-05 | Abas, Mohammed Fekry | 2024-03-05 | 2024-03-07 |  |  |  | 71300 | 5264 | 0 | STANDARD | Morgan Construction for contracting | SAR | 71300 | APPROVED |  |  | 2024-04-15 | 0 | 39 | Alhadi, Khalid | -45358 | 39
105-116 | North Thuqbah 115/13.8kv SS | 2775 | North Thuqbah 115/13.8kv SS-Shoring for 4 months duration | APPROVED | No | 2024-03-05 | Abas, Mohammed Fekry | 2024-03-05 | 2024-03-07 |  |  |  | 71300 | 5264 | 1 | STANDARD | Morgan Construction for contracting | SAR | 69000 | APPROVED |  |  | 2024-04-23 | 2300 | 47 | Alhadi, Khalid | -45358 | 47
105-116 | North Thuqbah 115/13.8kv SS | 2922 | North Thuqbah 115/13.8kv SS-Topography Survey for Project Area | APPROVED | No | 2024-03-28 | Abas, Mohammed Fekry | 2024-03-31 | 2024-03-31 |  |  |  | 5125 | 5716 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 5125 | APPROVED |  |  | 2024-07-01 | 0 | 92 | Alhadi, Khalid | -45382 | 92
105-116 | North Thuqbah 115/13.8kv SS | 2938 | North Thuqbah 115/13.8kv SS-AC/DC Panels with Sub DB's & LP's | APPROVED | No | 2024-03-28 | Abas, Mohammed Fekry | 2024-03-31 | 2024-03-31 |  |  |  | 870000 | 5402 | 0 | STANDARD | ALFANAR CO | SAR | 870000 | APPROVED |  |  | 2024-05-01 | 0 | 31 | Mohammed, Faisal Ansari | -45382 | 31
105-116 | North Thuqbah 115/13.8kv SS | 3045 | North Thuqbah 115/13.8kv SS-5T Over Head Travelling Crane with accessories. | APPROVED | No | 2024-04-16 | Abas, Mohammed Fekry | 2024-04-17 | 2024-04-24 |  |  |  | 130000 | 5461 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 126870 | APPROVED |  |  | 2024-05-16 | 3130 | 22 | Muhammad, Muhammad Atif | -45406 | 22
105-116 | North Thuqbah 115/13.8kv SS | 3256 | North Thuqbah 115/13.8kv SS-Supply & Apply of Roof Waterproofing System & Underground Waterproofing Tanking System | APPROVED | No | 2024-05-02 | Abas, Mohammed Fekry | 2024-05-02 | 2024-05-05 |  |  |  | 392625 | 5653 | 0 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 347826.5 | APPROVED |  |  | 2024-06-13 | 44798.5 | 39 | Tananeh, Khalid Jamal | -45417 | 39
105-116 | North Thuqbah 115/13.8kv SS | 3262 | North Thuqbah 115/13.8kv SS-Supply & Installation of Substation Doors | APPROVED | No | 2024-05-02 | Abas, Mohammed Fekry | 2024-05-05 | 2024-05-05 |  |  |  | 162672 | 6040 | 0 | STANDARD | AL MANASHY COMPANY | SAR | 106036.2 | APPROVED |  |  | 2024-10-21 | 56635.8 | 169 | Tananeh, Khalid Jamal | -45417 | 169
105-116 | North Thuqbah 115/13.8kv SS | 3266 | North Thuqbah 115/13.8kv SS-Supply & Install of Metal Works | APPROVED | No | 2024-05-02 | Abas, Mohammed Fekry | 2024-05-05 | 2024-05-05 |  |  |  | 426160 | 5948 | 0 | STANDARD | Al Sharek Al Daem Est for Contracting | SAR | 388300 | APPROVED |  |  | 2024-10-09 | 37860 | 157 | Tananeh, Khalid Jamal | -45417 | 157
105-116 | North Thuqbah 115/13.8kv SS | 3338 | North Thuqbah 115/13.8kv SS-Site Office Electroic Items | APPROVED | No | 2024-05-07 | Abas, Mohammed Fekry | 2024-05-08 | 2024-05-12 |  |  |  | 18200 | 5606 | 0 | STANDARD | Construction Expertise Est. | SAR | 18200 | APPROVED |  |  | 2024-06-05 | 0 | 24 | Muhammad, Muhammad Atif | -45424 | 24
105-116 | North Thuqbah 115/13.8kv SS | 3403 | North Thuqbah 115/13.8kv SS-150 Sq.mm Tinned Copper Conductor | APPROVED | No | 2024-05-15 | Abas, Mohammed Fekry | 2024-05-16 | 2024-05-17 |  |  |  | 38500 | 5574 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 38455.41 | APPROVED |  |  | 2024-05-26 | 44.59 | 9 | Muhammad, Muhammad Atif | -45429 | 9
105-116 | North Thuqbah 115/13.8kv SS | 3447 | North Thuqbah 115/13.8kv SS-Rental Generator with Diesel Tank | APPROVED | No | 2024-05-20 | Abas, Mohammed Fekry | 2024-05-21 | 2024-05-22 |  |  |  | 24000 | 5618 | 0 | STANDARD | SUDHIR EQUIPMENT RENTAL COMPANY | SAR | 19200 | APPROVED |  |  | 2024-06-03 | 4800 | 12 | Akhtar, Farhan | -45434 | 12
105-116 | North Thuqbah 115/13.8kv SS | 3510 | North Thuqbah 115/13.8kv SS-Battery & Chargers 125V, 2500AH GEL Type -2no/ 2no's | APPROVED | No | 2024-05-28 | Issa, Amr Ali | 2024-05-28 | 2024-05-29 |  |  |  | 550000 | 5737 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 457000 | APPROVED |  |  | 2024-07-10 | 93000 | 42 | Muhammad, Muhammad Atif | -45441 | 42
105-116 | North Thuqbah 115/13.8kv SS | 3602 | North Thuqbah 115/13.8kv SS-Grounding material and its accessories | APPROVED | No | 2024-06-05 | Abas, Mohammed Fekry | 2024-06-08 | 2024-06-09 |  |  |  | 72850 | 5555 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 72850 | APPROVED |  |  | 2024-07-07 | 0 | 28 | Muhammad, Muhammad Atif | -45452 | 28
105-116 | North Thuqbah 115/13.8kv SS | 3648 | North Thuqbah 115/13.8kv SS-Operation expense of Fuel for the Site Diesel Generators | APPROVED | No | 2024-06-12 | Abas, Mohammed Fekry | 2024-06-26 | 2024-06-26 |  |  |  | 42000 | 5768 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 17739.13 | APPROVED |  |  | 2024-07-12 | 24260.87 | 16 | Akhtar, Farhan | -45469 | 16
105-116 | North Thuqbah 115/13.8kv SS | 3743 | North Thuqbah 115/13.8kv SS-MV Cable ( 1C x 630 mm2 and 1x3Cx300mm2) | APPROVED | No | 2024-07-02 | Abas, Mohammed Fekry | 2024-07-05 | 2024-07-07 |  |  |  | 1260970 | 6020 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 1127267.9 | APPROVED |  |  | 2024-10-09 | 133702.1 | 94 | Badhman, Saeed | -45480 | 94
105-116 | North Thuqbah 115/13.8kv SS | 3786 | North Thuqbah 115/13.8kv SS-Garbage Waste Container, 12 Cu. M (1-year) | APPROVED | No | 2024-07-07 | Abas, Mohammed Fekry | 2024-07-09 | 2024-07-09 |  |  |  | 28800 | 5885 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 19200 | APPROVED |  |  | 2024-08-20 | 9600 | 42 | Akhtar, Farhan | -45482 | 42
105-116 | North Thuqbah 115/13.8kv SS | 3877 | North Thuqbah 115/13.8kv SS-Control Cables | APPROVED | No | 2024-07-13 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 716000 | 5823 | 0 | STANDARD | ALFANAR CO | SAR | 531752.8 | APPROVED |  |  | 2024-08-27 | 184247.2 | 42 | Muhammad, Muhammad Atif | -45489 | 42
105-116 | North Thuqbah 115/13.8kv SS | 3933 | North Thuqbah 115/13.8kv SS-MV Termination Kit | APPROVED | No | 2024-07-16 | Issa, Amr Ali | 2024-07-21 | 2024-07-21 |  |  |  | 98837 | 5983 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 95871.89 | APPROVED |  |  | 2024-09-19 | 2965.11 | 60 | Badhman, Saeed | -45494 | 60
105-116 | North Thuqbah 115/13.8kv SS | 3968 | North Thuqbah 115/13.8kv SS-Testing and Commissioning | APPROVED | No | 2024-07-21 | Abas, Mohammed Fekry | 2024-07-22 | 2024-07-23 |  |  |  | 1855063 | 6444 | 0 | STANDARD | Al Fanar Technical Services | SAR | 1855063 | APPROVED |  |  | 2025-03-13 | 0 | 233 | Alqadhi, Abdulrahman Abdulghani | -45496 | 233
105-116 | North Thuqbah 115/13.8kv SS | 3972 | North Thuqbah 115/13.8kv SS-RTV Coating | APPROVED | No | 2024-07-21 | Abas, Mohammed Fekry | 2024-07-29 | 2024-07-29 |  |  |  | 250000 | 6188 | 0 | STANDARD | SAUDI CONDUIT COATING CO. (S3C) | SAR | 35268 | APPROVED |  |  | 2024-10-13 | 214732 | 76 | Muaz, Alaa | -45502 | 76
105-116 | North Thuqbah 115/13.8kv SS | 4027 | North Thuqbah 115/13.8kv SS-Lightning Masts | APPROVED | No | 2024-07-28 | Abas, Mohammed Fekry | 2024-07-30 | 2024-07-30 |  |  |  | 59075 | 5962 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 59075 | APPROVED |  |  | 2024-10-07 | 0 | 69 | Badhman, Saeed | -45503 | 69
105-116 | North Thuqbah 115/13.8kv SS | 4054 | North Thuqbah 115/13.8kv SS-Cable Tray and its accessories | APPROVED | No | 2024-07-30 | Abas, Mohammed Fekry | 2024-08-01 | 2024-08-01 |  |  |  | 505784.96 | 5897 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 505784.96 | APPROVED |  |  | 2024-09-26 | 0 | 56 | Muhammad, Muhammad Atif | -45505 | 56
105-116 | North Thuqbah 115/13.8kv SS | 4172 | North Thuqbah 115/13.8kv SS-LV AC / DC Cables and Lighitng Wires | APPROVED | No | 2024-08-17 | Abas, Mohammed Fekry | 2024-08-21 | 2024-08-21 |  |  |  | 1611070 | 6078 | 0 | STANDARD | ALFANAR CO | SAR | 1110509.38 | APPROVED |  |  | 2024-09-26 | 500560.62 | 36 | Badhman, Saeed | -45525 | 36
105-116 | North Thuqbah 115/13.8kv SS | 4187 | North Thuqbah 115/13.8kv SS-Hazardas Waste Collection | APPROVED | No | 2024-08-18 | Abas, Mohammed Fekry | 2024-08-21 | 2024-08-21 |  |  |  | 5000 | 6119 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 3650 | APPROVED |  |  | 2024-09-19 | 1350 | 29 | Akhtar, Farhan | -45525 | 29
105-116 | North Thuqbah 115/13.8kv SS | 4237 | North Thuqbah 115/13.8kv SS-Grounding Conductor and Cables | APPROVED | No | 2024-08-21 | Abas, Mohammed Fekry | 2024-08-28 | 2024-09-01 |  |  |  | 244150 | 6062 | 0 | STANDARD | ALFANAR CO | SAR | 226756.52 | APPROVED |  |  | 2024-09-18 | 17393.48 | 17 | Muhammad, Muhammad Atif | -45536 | 17
105-116 | North Thuqbah 115/13.8kv SS | 4259 | North Thuqbah 115/13.8kv SS-Electrical Soil Resistivity MEasurement (Third Party Lab Testing) | APPROVED | No | 2024-08-24 | Abas, Mohammed Fekry | 2024-08-27 | 2024-09-01 |  |  |  | 7360 | 6139 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 6400 | APPROVED |  |  | 2024-10-10 | 960 | 39 | Tananeh, Khalid Jamal | -45536 | 39
105-116 | North Thuqbah 115/13.8kv SS | 4377 | North Thuqbah 115/13.8kv SS-Civil Sub Contractor | APPROVED | No | 2024-09-04 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 8300000 | 5645 | 0 | STANDARD | Liwa Al sharq Contracting Company | SAR | 8300000 | APPROVED |  |  | 2024-11-03 | 0 | 42 | Tananeh, Khalid Jamal | -45557 | 42
105-116 | North Thuqbah 115/13.8kv SS | 4386 | North Thuqbah 115/13.8kv SS-firefighting | APPROVED | No | 2024-09-06 | Abas, Mohammed Fekry | 2024-09-17 | 2024-09-17 |  |  |  | 2169000 | 6004 | 0 | STANDARD | Equipment & Technical Services Co.(ETECHS) | SAR | 2169000 | APPROVED |  |  | 2024-09-26 | 0 | 9 | Muhammad, Muhammad Atif | -45552 | 9
105-116 | North Thuqbah 115/13.8kv SS | 4577 | North Thuqbah 115/13.8kv SS-Station Service Transformer | APPROVED | No | 2024-10-02 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-09 |  |  |  | 164000 | 5906 | 0 | STANDARD | ALFANAR CO | SAR | 164000 | APPROVED |  |  | 2024-10-19 | 0 | 10 | Muhammad, Muhammad Atif | -45574 | 10
105-116 | North Thuqbah 115/13.8kv SS | 4596 | North Thuqbah 115/13.8kv SS-Electrical Installation - Contract | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-09 |  |  |  | 2992521 | 6432 | 0 | STANDARD | Future Vision Company | SAR | 2390000 | APPROVED |  |  | 2024-12-29 | 602521 | 81 | Muhammad, Muhammad Atif | -45574 | 81
105-116 | North Thuqbah 115/13.8kv SS | 4668 | North Thuqbah 115/13.8kv SS-HVAC System and Works | APPROVED | No | 2024-10-14 | Abas, Mohammed Fekry | 2024-10-16 | 2024-10-16 |  |  |  | 2050000 | 6203 | 0 | STANDARD | Ramz Alataa Company for Trading | SAR | 2050000 | APPROVED |  |  | 2024-10-31 | 0 | 15 | Muhammad, Muhammad Atif | -45581 | 15
105-116 | North Thuqbah 115/13.8kv SS | 4707 | North Thuqbah 115/13.8kv SS-Supply of Raw Water | APPROVED | No | 2024-10-17 | Abas, Mohammed Fekry | 2024-10-20 | 2024-10-20 |  |  |  | 5000 | 6373 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 8400 | APPROVED |  |  | 2024-11-03 | -3400 | 14 | Akhtar, Farhan | -45585 | 14
105-116 | North Thuqbah 115/13.8kv SS | 4708 | North Thuqbah 115/13.8kv SS-Site Waste Removal Services | APPROVED | No | 2024-10-17 | Abas, Mohammed Fekry | 2024-10-20 | 2024-10-20 |  |  |  | 5000 | 6373 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 8400 | APPROVED |  |  | 2024-11-03 | -3400 | 14 | Akhtar, Farhan | -45585 | 14
105-116 | North Thuqbah 115/13.8kv SS | 4720 | North Thuqbah 115/13.8kv SS-Telecommunication and Works | APPROVED | No | 2024-10-17 | Abas, Mohammed Fekry | 2024-12-05 | 2024-12-08 |  |  |  | 2249988.12 | 6240 | 0 | STANDARD | ALFANAR CO | SAR | 2249988.12 | APPROVED |  |  | 2025-04-13 | 0 | 126 | Kumar, Mr. Ranjan | -45634 | 126
105-116 | North Thuqbah 115/13.8kv SS | 4983 | North Thuqbah 115/13.8kv SS-Indoor and Outdoor Lighitng Fixtures | APPROVED | No | 2024-11-18 | Abas, Mohammed Fekry | 2024-11-28 | 2024-11-28 |  |  |  | 88037 | 6469 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 88037 | APPROVED |  |  | 2024-12-15 | 0 | 17 | Muhammad, Muhammad Atif | -45624 | 17
105-116 | North Thuqbah 115/13.8kv SS | 5088 | North Thuqbah 115/13.8kv SS-HCIS Consultant | APPROVED | No | 2024-11-30 | Abas, Mohammed Fekry | 2025-03-10 | 2025-03-12 |  |  | Line item 2.7 HCIS Consultant | 33500 | 6508 | 0 | STANDARD | Khaled Drewesh Office for Consulting Security (KDOCS) | SAR | 33500 | APPROVED |  |  | 2025-06-15 | 0 | 95 | Abdulqader, Ahmed Abdulhalim | -45728 | 95
105-116 | North Thuqbah 115/13.8kv SS | 5156 | North Thuqbah 115/13.8kv SS-Al-Conductor Clamps and Connector | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-12 |  |  |  | 4537 | 6413 | 0 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 4505.16 | APPROVED |  |  | 2024-12-25 | 31.84 | 13 | Mohammed, Faisal Ansari | -45638 | 13
105-116 | North Thuqbah 115/13.8kv SS | 5347 | North Thuqbah 115/13.8kv SS-Conduits and fittings | APPROVED | No | 2025-01-04 | Abas, Mohammed Fekry | 2025-01-07 | 2025-01-07 |  |  |  | 337272.4 | 6712 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 337271.55 | APPROVED |  |  | 2025-01-28 | 0.85 | 21 | Muaz, Alaa | -45664 | 21
105-116 | North Thuqbah 115/13.8kv SS | 5408 | North Thuqbah 115/13.8kv SS-150mm2 Tinned Copper Conductor | APPROVED | No | 2025-01-13 | Abas, Mohammed Fekry | 2025-01-14 | 2025-01-16 |  |  |  | 131100 | 6809 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 121307.52 | APPROVED |  |  | 2025-02-27 | 9792.48 | 42 | Alhadi, Khalid | -45673 | 42
105-116 | North Thuqbah 115/13.8kv SS | 5463 | North Thuqbah 115/13.8kv SS-CTPU and CTPU Box Including Accessories | APPROVED | No | 2025-01-19 | Abas, Mohammed Fekry | 2025-01-20 | 2025-01-23 |  |  |  | 68000 | 6284 | 0 | STANDARD | Energy Tracks For Contracting | SAR | 68000 | APPROVED |  |  | 2025-03-12 | 0 | 48 | Kumar, Mr. Ranjan | -45680 | 48
105-116 | North Thuqbah 115/13.8kv SS | 5528 | North Thuqbah 115/13.8kv SS-Design, Supply, Installation, Testing and commissioning of Securty System | APPROVED | No | 2025-01-22 | Abas, Mohammed Fekry | 2025-02-05 | 2025-02-05 |  |  |  | 788834 | 6627 | 0 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 788834 | APPROVED |  |  | 2025-02-20 | 0 | 15 | Abdulqader, Ahmed Abdulhalim | -45693 | 15
105-116 | North Thuqbah 115/13.8kv SS | 5560 | North Thuqbah 115/13.8kv SS-TFR,DSM,SOE and SAS/SCADA for Remote End Scope | APPROVED | No | 2025-01-23 | Abas, Mohammed Fekry | 2025-01-28 | 2025-01-30 |  |  |  | 100000 | 7455 | 0 | STANDARD | TRINERGY TECHNOLOGIES SA | SAR | 61231 | APPROVED |  |  | 2025-07-06 | 38769 | 157 | Babic, Marian | -45687 | 157
105-116 | North Thuqbah 115/13.8kv SS | 5564 | North Thuqbah 115/13.8kv SS-Fiber Optic Cables & Accessories,Installation and Testing Services | APPROVED | No | 2025-01-23 | Abas, Mohammed Fekry | 2025-01-28 | 2025-01-30 |  |  |  | 250000 | 7030 | 0 | STANDARD | RASHID SAEED AHMED AL GHAMDI COMM INFO TRAD EST | SAR | 210000 | APPROVED |  |  | 2025-04-17 | 40000 | 77 | Abdulqader, Ahmed Abdulhalim | -45687 | 77
105-116 | North Thuqbah 115/13.8kv SS | 5568 | North Thuqbah 115/13.8kv SS-Office Furniture | REJECTED | No | 2025-01-23 | Sherif, Marwa | 2025-03-09 | 2025-01-26 |  | 2025-03-09 |  | 50000 | [5 empty] | 0 |  |  |  |  | 0 |  | Muhammad, Muhammad Atif | -45683 | -45683
105-116 | North Thuqbah 115/13.8kv SS | 5694 | North Thuqbah 115/13.8kv SS-MV Cables Cleats and Supports | REJECTED | No | 2025-01-27 | Sherif, Marwa | 2025-03-09 | 2025-02-01 |  | 2025-03-09 |  | 100000 | [5 empty] | 0 |  |  |  |  | 0 |  | Muhammad, Muhammad Atif | -45689 | -45689
105-116 | North Thuqbah 115/13.8kv SS | 6072 | North Thuqbah 115/13.8kv SS-Steel Boundary Fence | RETURNED | No | 2025-02-26 | Abdulqader, Ahmed Abdulhalim | 2025-03-17 | 2025-03-10 | 2025-03-17 |  | PR is not matching the shared offer | 730000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45726 | -45726
105-116 | North Thuqbah 115/13.8kv SS | 6091 | North Thuqbah 115/13.8kv SS-Printing of Drawings in A2 size | APPROVED | No | 2025-03-01 | Abas, Mohammed Fekry | 2025-03-03 | 2025-03-05 |  |  | Line item 2.33 Printing of Drawings A2 Size | 31000 | 7057 | 0 | STANDARD | Print Magaies Al abdaa Printing | SAR | 30999 | APPROVED |  |  | 2025-04-07 | 1 | 33 | Abuhammad, Samir | -45721 | 33
105-116 | North Thuqbah 115/13.8kv SS | 6300 | North Thuqbah 115/13.8kv SS-Old Fence Relocation, installation of new fence (CEC works) | APPROVED | No | 2025-04-07 | Abas, Mohammed Fekry | 2025-04-08 | 2025-04-08 |  |  | Old Fence Relocation, installation of new fence (CEC works) | 65300 | 7102 | 0 | STANDARD | Construction Expertise Est. | SAR | 48040 | APPROVED |  |  | 2025-08-11 | 17260 | 125 | Abdulqader, Ahmed Abdulhalim | -45755 | 125
105-116 | North Thuqbah 115/13.8kv SS | 6336 | North Thuqbah 115/13.8kv SS-5 Ton Stand Alon AC for CSD TEsting ( 8 Numbers) | APPROVED | No | 2025-04-14 | Abas, Mohammed Fekry | 2025-04-16 | 2025-04-17 |  |  | 5 Ton Stand Alon AC for CSD TEsting ( 8 Numbers) | 71168 | 7162 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 61600 | APPROVED |  |  | 2025-04-24 | 9568 | 7 | Abuhammad, Samir | -45764 | 7
105-116 | North Thuqbah 115/13.8kv SS | 6379 | North Thuqbah 115/13.8kv SS-Control Cables for SAS | APPROVED | No | 2025-04-19 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-20 |  |  | Line item 2.13 control Cables for SAS | 52600 | 6780 | 0 | STANDARD | ALFANAR CO | SAR | 52600 | APPROVED |  |  | 2025-04-30 | 0 | 10 | Muaz, Alaa | -45767 | 10
105-116 | North Thuqbah 115/13.8kv SS | 6406 | North Thuqbah 115/13.8kv SS-Closing Openings with Gypsum Partitions – Substation Projects. | APPROVED | No | 2025-04-21 | Abas, Mohammed Fekry | 2025-04-22 | 2025-04-22 |  |  | Closing Openings with Gypsum Partitions – Substation Projects. | 6000 | 7201 | 0 | STANDARD | Tamim Company (PVT) LTD | SAR | 6000 | APPROVED |  |  | 2025-04-30 | 0 | 8 | Abuhammad, Samir | -45769 | 8
105-116 | North Thuqbah 115/13.8kv SS | 6443 | North Thuqbah 115/13.8kv SS-Rental Generator 250KVA for CSD Testing | APPROVED | No | 2025-04-23 | Abas, Mohammed Fekry | 2025-04-26 | 2025-04-28 |  |  | 250KVA Rental Generator for CSD Testing | 60000 | 7221 | 0 | STANDARD | Rawafd AlQwt Litaqt Est. | SAR | 37000 | APPROVED |  |  | 2025-05-07 | 23000 | 9 | Akhtar, Farhan | -45775 | 9
105-116 | North Thuqbah 115/13.8kv SS | 6452 | North Thuqbah 115/13.8kv SS-Supply of Raw Water | APPROVED | No | 2025-04-26 | Abas, Mohammed Fekry | 2025-04-28 | 2025-04-28 |  |  | Supply of Raw Water | 6000 | 6373 | 1 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 6000 | APPROVED |  |  | 2025-05-05 | 0 | 7 | Akhtar, Farhan | -45775 | 7
105-116 | North Thuqbah 115/13.8kv SS | 6517 | North Thuqbah 115/13.8kv SS-Instrumentation Cable ((4P X 1.5mm2) | APPROVED | No | 2025-05-05 | Abas, Mohammed Fekry | 2025-05-08 | 2025-05-08 |  |  | Instrumentation Cable ((4P X 1.5mm2)) | 9000 | 7313 | 0 | STANDARD | Middle East Specialized Cables Mesc | SAR | 7500 | APPROVED |  |  | 2025-05-29 | 1500 | 21 | Abuhammad, Samir | -45785 | 21
105-116 | North Thuqbah 115/13.8kv SS | 6600 | North Thuqbah 115/13.8kv SS-Third Party Lab Testing of Pre-Cast | APPROVED | No | 2025-05-13 | Abas, Mohammed Fekry | 2025-05-15 | 2025-05-15 |  |  | Third Party Lab Testing of Pre-Cast Material | 85000 | 7405 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 84190 | APPROVED |  |  | 2025-06-15 | 810 | 31 | Tananeh, Khalid Jamal | -45792 | 31
105-116 | North Thuqbah 115/13.8kv SS | 6653 | North Thuqbah 115/13.8kv SS-Transformer Oil DGA Analysis (Lab Testing) as per SEC-CSD requirment | APPROVED | No | 2025-05-19 | Abas, Mohammed Fekry | 2025-05-22 | 2025-05-27 |  |  | Transformer Oil DGA Analysis (Lab Testing) as per SEC-CSD requirment | 35000 | 7475 | 0 | STANDARD | Saudi Arabian Engineering Company | SAR | 35000 | APPROVED |  |  | 2025-07-21 | 0 | 55 | Abdulqader, Ahmed Abdulhalim | -45804 | 55
105-116 | North Thuqbah 115/13.8kv SS | 6707 | North Thuqbah 115/13.8kv SS-Diesel for Rental 250KVA Generator | APPROVED | No | 2025-05-25 | Abas, Mohammed Fekry | 2025-05-29 | 2025-05-29 |  |  | Diesel for Rental Generator | 44608.5 | 7395 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 44608.5 | APPROVED |  |  | 2025-06-15 | 0 | 17 | Akhtar, Farhan | -45806 | 17
105-116 | North Thuqbah 115/13.8kv SS | 6856 | North Thuqbah 115/13.8kv SS-Third Party Testing of IPC material | RETURNED | No | 2025-06-22 | Tananeh, Khalid Jamal | 2025-10-23 | 2025-08-25 | 2025-10-23 |  | return the PR. as per email sent to Talha Wed 10/22/2025 12:32 PM , and POCR was not approve | 75000 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45894 | -45894
105-116 | North Thuqbah 115/13.8kv SS | 6915 | North Thuqbah 115/13.8kv SS-Wiring Devices (Switches and Sockets) | APPROVED | No | 2025-06-28 | Abas, Mohammed Fekry | 2025-07-06 | 2025-07-07 |  |  | Line item 2.23 Wiring Devices | 96720 | 7172 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 96720 | APPROVED |  |  | 2025-07-18 | 0 | 11 | Muaz, Alaa | -45845 | 11
105-116 | North Thuqbah 115/13.8kv SS | 6969 | North Thuqbah 115/13.8kv SS-Manpower for Testing and Commissioning | APPROVED | No | 2025-07-02 | Abas, Mohammed Fekry | 2025-07-06 | 2025-07-07 |  |  | Line item 2.31 Manpower for Testing and Commissioning | 120000 | 7505 | 0 | STANDARD | Jasem M.AlJasem Contracting Est. | SAR | 120000 | APPROVED |  |  | 2025-08-02 | 0 | 26 | Babic, Marian | -45845 | 26
105-116 | North Thuqbah 115/13.8kv SS | 6999 | North Thuqbah 115/13.8kv SS-Transformer Oil Testing (As per CSD Requirement) | APPROVED | No | 2025-07-07 | Abas, Mohammed Fekry | 2025-07-12 | 2025-07-12 |  |  | Initially, I have created PR with the value of 35,000/-. Now OUR DPO value is 37,300. Therefore I am creating NewPR of 2300. | 2300 | 7475 | 0 | STANDARD | Saudi Arabian Engineering Company | SAR | 2300 | APPROVED |  |  | 2025-07-21 | 0 | 9 | Abdulqader, Ahmed Abdulhalim | -45850 | 9
105-116 | North Thuqbah 115/13.8kv SS | 7044 | North Thuqbah 115/13.8kv SS-MV and HV Supports | APPROVED | No | 2025-07-09 | Abas, Mohammed Fekry | 2025-07-13 | 2025-07-14 |  |  | MV & HV Cable Supports | 118598.25 | 7297 | 0 | STANDARD | ISAM KABBANI &Partners | SAR | 118598.25 | APPROVED |  |  | 2025-08-02 | 0 | 19 | Hegazy, Ayman | -45852 | 19
105-116 | North Thuqbah 115/13.8kv SS | 7101 | North Thuqbah 115/13.8kv SS- PDS System | REJECTED | No | 2025-07-15 | Khan, Muhammad Safdar | 2025-07-16 | 2025-07-16 |  | 2025-07-17 |  | 250000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45854 | -45854
105-116 | North Thuqbah 115/13.8kv SS | 7180 | North Thuqbah 115/13.8kv SS-Design, Supply, Installation, Testing and Commissioning of Lighting Control System | RETURNED | No | 2025-07-21 | Muaz, Alaa | 2025-09-09 | 2025-07-27 | 2025-09-09 |  | The budget is not sufficient | 60271 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -45865 | -45865
105-116 | North Thuqbah 115/13.8kv SS | 7222 | North Thuqbah 115/13.8kv SS-DC DB for Telecommunication | APPROVED | No | 2025-07-27 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | DC DB for Telecom | 50000 | 7654 | 0 | STANDARD | HAWA ELECTRIC PANEL BOARD FAC | SAR | 29700 | APPROVED |  |  | 2025-09-08 | 20300 | 14 | Abuhammad, Samir | -45894 | 14
105-116 | North Thuqbah 115/13.8kv SS | 7227 | North Thuqbah 115/13.8kv SS-1x400mm2 Extra LV Cables | RETURNED | No | 2025-07-27 | Mohammed, Mohammed Adel Fahmy | 2026-01-15 | 2025-08-03 | 2026-01-15 |  | Not Have POCR Until Now and PR incorrect qty. | 159570 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Mohammed Adel Fahmy | -45872 | -45872
105-116 | North Thuqbah 115/13.8kv SS | 7286 | North Thuqbah 115/13.8kv SS-Rental Bus-Driver | REJECTED | No | 2025-08-05 | Sherif, Marwa | 2025-08-19 | 2025-08-06 |  | 2025-08-27 |  | 52000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45875 | -45875
105-116 | North Thuqbah 115/13.8kv SS | 7287 | North Thuqbah 115/13.8kv SS-Extra Control Cables | RETURNED | No | 2025-08-05 | Mohammed, Mohammed Adel Fahmy | 2026-01-15 | 2025-08-10 | 2026-01-15 |  | Not Have POCR Until Now and PR incorrect qty. | 174000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Mohammed Adel Fahmy | -45879 | -45879
105-116 | North Thuqbah 115/13.8kv SS | 7307 | North Thuqbah 115/13.8kv SS-5 Number of 5 Ton AC's ( 3 Fixed and 2 Mobile) | RETURNED | No | 2025-08-06 |  |  | 2025-08-10 | 2026-01-11 |  | Not Required the AC's | 50000 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45879 | -45879
105-116 | North Thuqbah 115/13.8kv SS | 7409 | Asphalt, Backfilling and Steel boundary fence | REJECTED | No | 2025-08-21 | Sherif, Marwa | 2025-08-25 | 2025-08-21 |  | 2025-08-27 |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45890 | -45890
105-116 | North Thuqbah 115/13.8kv SS | 7420 | Hazardous Waste Collection | REJECTED | No | 2025-08-21 | Sherif, Marwa | 2025-08-25 | 2025-08-24 |  | 2025-08-27 |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45893 | -45893
105-116 | North Thuqbah 115/13.8kv SS | 7425 | Extra Grounding Accessories | APPROVED | No | 2025-08-23 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | Line item 2.21, Extra Grounding Accessories. PO already issued. PR was not issue due to less budget. Now CTC approved. | 0 | 7096 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 69784.7 | APPROVED |  |  | 2025-09-16 | -69784.7 | 22 | Abdulqader, Ahmed Abdulhalim | -45894 | 22
105-116 | North Thuqbah 115/13.8kv SS | 7432 | PDS System | APPROVED | No | 2025-08-23 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | Line Item 2.5 PDS | 0 | 7769 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 140000 | APPROVED |  |  | 2025-11-19 | -140000 | 86 | Hegazy, Ayman | -45894 | 86
105-116 | North Thuqbah 115/13.8kv SS | 7469 | MV Clamps | REJECTED | No | 2025-08-25 | Sherif, Marwa | 2025-08-25 | 2025-08-25 |  | 2025-08-27 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45894 | -45894
105-116 | North Thuqbah 115/13.8kv SS | 7524 | Asphalt, Backfilling and Steel boundary fence work | REJECTED | No | 2025-08-27 | Shahin, Hassan Magdy Hassan | 2025-08-27 |  |  | 2025-08-27 | Line item 2.20 PR for Backfilling, Steel Boundary Fence and Asphalt works | 3 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-116 | North Thuqbah 115/13.8kv SS | 7541 | Lugs and Glands | APPROVED | No | 2025-08-27 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-03 |  |  | Line item 2.13 Lugs and Glands | 0 | 7574 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 24541.6 | APPROVED |  |  | 2025-09-09 | -24541.6 | 6 | Abdulqader, Ahmed Abdulhalim | -45903 | 6
105-116 | North Thuqbah 115/13.8kv SS | 7668 | Rental T&C Coordinator | REJECTED | No | 2025-09-07 | Sherif, Marwa | 2025-09-08 | 2025-09-08 |  | 2025-09-08 |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45908 | -45908
105-116 | North Thuqbah 115/13.8kv SS | 7716 | Water Proofing Extra Scope | APPROVED | No | 2025-09-10 | Abas, Mohammed Fekry | 2025-09-16 | 2025-09-21 |  |  | Water Proofing for ABsar Scope of Work Change Order. Initially for NTQB SS PR was raised due to the CTC issue | 0 | 5653 | 1 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 37264.54 | APPROVED |  |  | 2025-10-15 | -37264.54 | 24 | Tananeh, Khalid Jamal | -45921 | 24
105-116 | North Thuqbah 115/13.8kv SS | 7728 | MV Clamps | APPROVED | No | 2025-09-14 | Abas, Mohammed Fekry | 2025-09-15 | 2025-09-16 |  |  | Line Item 2.13 MV Clamps. PO already issues. PO Number is 7660-HV1497-0 | 0 | 7660 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 56525 | APPROVED |  |  | 2025-09-29 | -56525 | 13 | Hegazy, Ayman | -45916 | 13
105-116 | North Thuqbah 115/13.8kv SS | 7798 | Office Furniture | APPROVED | No | 2025-09-20 | Abas, Mohammed Fekry | 2025-09-29 | 2025-10-02 |  |  | Line item 2.33 Office furniture | 0 | 7714 | 0 | STANDARD | ALISMAIL INDUSTRIAL CO.(S) | SAR | 17590 | APPROVED |  |  | 2025-10-14 | -17590 | 12 | Abdulqader, Ahmed Abdulhalim | -45932 | 12
105-116 | North Thuqbah 115/13.8kv SS | 7843 | Asphalting, Backfilling and Steel boundary fence | REJECTED | No | 2025-09-27 | Sherif, Marwa | 2025-09-30 | 2025-09-30 |  | 2025-10-05 |  | 3 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45930 | -45930
105-116 | North Thuqbah 115/13.8kv SS | 7987 | Steel fence, Asphalt and Backfilling | RETURNED | No | 2025-10-16 | Tananeh, Khalid Jamal | 2025-10-27 | 2025-10-21 | 2025-10-27 |  | Return as per email to Talha Salam in Mon 10/27/2025 4:04 PM, Once the POCR approved, we can proceed to raise the change order in the system. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45951 | -45951
105-116 | North Thuqbah 115/13.8kv SS | 8205 | Disposal of Waste Container (12CU.M3) | APPROVED | No | 2025-11-12 | Abas, Mohammed Fekry | 2025-11-16 | 2025-11-17 |  |  | Line item 2.33 Disposal of Waste Container | 0 | 5885 | 1 | STANDARD | Cebent for General Cont. Est. | SAR | 11200 | APPROVED |  |  | 2025-11-30 | -11200 | 13 | Akhtar, Farhan | -45978 | 13
105-116 | North Thuqbah 115/13.8kv SS | 8254 | Motors for NTQB Main Gate | APPROVED | No | 2025-11-18 | Abas, Mohammed Fekry | 2025-11-20 | 2025-11-23 |  |  | Line item 2.20 Motors for North Thouqba Main Gate | 0 | 7977 | 0 | STANDARD | ALMOSALLAMY INDUSTRIAL COMPANY | SAR | 9330 | APPROVED |  |  | 2025-12-14 | -9330 | 21 | Abdelraouf, Islam ِAdel Hanafy | -45984 | 21
105-116 | North Thuqbah 115/13.8kv SS | 8396 | Lighting Control System | APPROVED | No | 2025-11-30 | Abas, Mohammed Fekry | 2025-12-04 | 2025-12-04 |  |  | Line item 2.22 Lighting Control System | 0 | 7342 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 72407 | APPROVED | 2025-12-11 | 2025-12-14 | 2026-01-21 | -72407 | 48 | Muaz, Alaa | 10 | 48
105-116 | North Thuqbah 115/13.8kv SS | 8406 | Hazardous Waste Collection | RETURNED | No | 2025-12-01 | Akhtar, Farhan | 2025-12-07 | 2025-12-04 | 2025-12-07 |  | change the UOM and QTY | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45995 | -45995
105-116 | North Thuqbah 115/13.8kv SS | 8439 | Hazardous wastage collection | APPROVED | No | 2025-12-03 | Abas, Mohammed Fekry | 2025-12-04 | 2025-12-04 |  |  | Line item 2.33 Hazardous wastage collection | 0 | 7999 | 0 | STANDARD | Expertise Contracting Co. | SAR | 18300 | APPROVED |  |  | 2025-12-21 | -18300 | 17 | Akhtar, Farhan | -45995 | 17
105-116 | North Thuqbah 115/13.8kv SS | 8451 | Disel for site generator | APPROVED | No | 2025-12-04 | Abas, Mohammed Fekry | 2025-12-11 | 2025-12-14 |  |  | line item 2.33 disel for site generator | 0 | 7395 | 1 | STANDARD | Talaea Alahlam Trading Company | SAR | 89217 | APPROVED | 2025-12-18 | 2025-12-26 | 2026-01-15 | -89217 | 32 | Akhtar, Farhan | 12 | 32
105-116 | North Thuqbah 115/13.8kv SS | 8466 | Acs for site- 5 ton | RETURNED | No | 2025-12-07 | Abuhammad, Samir | 2025-12-29 | 2025-12-14 | 2025-12-29 |  | free of cost delivery. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46005 | -46005
105-116 | North Thuqbah 115/13.8kv SS | 8519 | 10 Rental Technicians for 10 Month | IN PROCESS | No | 2025-12-14 | Abdelhamid, Mohamed Ibrahim Mohamed | 2025-12-22 | 2025-12-15 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46006 | -46006
105-116 | North Thuqbah 115/13.8kv SS | 8585 | Rental 250KVA Generator | APPROVED | No | 2025-12-25 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-13 |  |  | 250KVA Rental Generator for North Thouqba SS | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -46035 | -46035
105-116 | North Thuqbah 115/13.8kv SS | 8650 | Metal Doors (Change Order) - North Thuqbah | APPROVED | No | 2026-01-05 | Abas, Mohammed Fekry | 2026-01-26 | 2026-01-27 |  |  | Budget line 2.20-Civil works | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46049 | -46049
105-116 | North Thuqbah 115/13.8kv SS | 8742 | Supply and Installation of Metal Works for N.Thuqbah SS | APPROVED | No | 2026-01-20 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46050 | -46050
105-117 | Ryadhiyah 115/13.8kv SS | 1941 | Ryadhiyah 115/13.8kv SS-Engineering & Design Ryadhiyah | APPROVED | No | 2023-12-12 | Abas, Mohammed Fekry | 2023-12-12 | 2023-12-13 |  |  |  | 581250 | 4893 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 570000 | APPROVED |  |  | 2024-01-08 | 11250 | 26 | Kumar, Mr. Ranjan | -45273 | 26
105-117 | Ryadhiyah 115/13.8kv SS | 1947 | Ryadhiyah 115/13.8kv SS-Site Fencing- Ryadhiyah | APPROVED | No | 2023-12-13 | Abas, Mohammed Fekry | 2023-12-13 | 2023-12-13 |  |  |  | 79350 | 5135 | 0 | STANDARD | Construction Expertise Est. | SAR | 18968.47 | APPROVED |  |  | 2024-03-14 | 60381.53 | 92 | Alhadi, Khalid | -45273 | 92
105-117 | Ryadhiyah 115/13.8kv SS | 1948 | Ryadhiyah 115/13.8kv SS-Control SAS protection panels- Ryaghiyah | APPROVED | No | 2023-12-13 | Abas, Mohammed Fekry | 2023-12-14 | 2023-12-17 |  |  |  | 9200000 | 4858 | 0 | STANDARD | ALFANAR CO | SAR | 9200000 | APPROVED |  |  | 2024-01-15 | 0 | 29 | Kumar, Mr. Ranjan | -45277 | 29
105-117 | Ryadhiyah 115/13.8kv SS | 1953 | Ryadhiyah 115/13.8kv SS-13.8kV Switchgear | APPROVED | No | 2023-12-13 | Abas, Mohammed Fekry | 2023-12-13 | 2023-12-13 |  |  |  | 8210000 | 4843 | 0 | STANDARD | ALFANAR CO | SAR | 8210000 | APPROVED |  |  | 2024-01-18 | 0 | 36 | Alhadi, Khalid | -45273 | 36
105-117 | Ryadhiyah 115/13.8kv SS | 2119 | Ryadhiyah 115/13.8kv SS-Temporary Project Sign Board | APPROVED | No | 2024-01-08 | Abas, Mohammed Fekry | 2024-01-09 | 2024-01-09 |  |  |  | 20000 | 4976 | 0 | STANDARD | Construction Expertise Est. | SAR | 20000 | APPROVED |  |  | 2024-01-17 | 0 | 8 | Alhadi, Khalid | -45300 | 8
105-117 | Ryadhiyah 115/13.8kv SS | 2255 | Ryadhiyah 115/13.8kv SS-Fencing Work | APPROVED | No | 2024-01-23 | Abas, Mohammed Fekry | 2024-01-24 | 2024-01-25 |  |  |  | 92858.33 | 5135 | 0 | STANDARD | Construction Expertise Est. | SAR | 78968.33 | APPROVED |  |  | 2024-03-14 | 13890 | 49 | Alhadi, Khalid | -45316 | 49
105-117 | Ryadhiyah 115/13.8kv SS | 2270 | Ryadhiyah 115/13.8kv SS-Cyber Security | APPROVED | No | 2024-01-24 | Abas, Mohammed Fekry | 2024-01-29 | 2024-01-29 |  |  |  | 1180000 | 5054 | 0 | STANDARD | ALFANAR CO | SAR | 1100000 | APPROVED |  |  | 2024-02-18 | 80000 | 20 | Babic, Marian | -45320 | 20
105-117 | Ryadhiyah 115/13.8kv SS | 2362 | Ryadhiyah 115/13.8kv SS-LINE ITEM 2.20 UG Scanning | APPROVED | No | 2024-01-29 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 1900 | 5073 | 0 | STANDARD | Construction Expertise Est. | SAR | 1900 | APPROVED |  |  | 2024-02-15 | 0 | 11 | Alhadi, Khalid | -45326 | 11
105-117 | Ryadhiyah 115/13.8kv SS | 2402 | Ryadhiyah 115/13.8kv SS-Site Office facility | APPROVED | No | 2024-02-04 | Abas, Mohammed Fekry | 2024-02-06 | 2024-02-06 |  |  |  | 245847 | 5424 | 0 | STANDARD | Construction Expertise Est. | SAR | 245847 | APPROVED |  |  | 2024-05-26 | 0 | 110 | Muhammad, Muhammad Atif | -45328 | 110
105-117 | Ryadhiyah 115/13.8kv SS | 2538 | Ryadhiyah 115/13.8kv SS-Super Structure Precast including Fire Walls | APPROVED | No | 2024-02-12 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-19 |  |  |  | 2421479 | 5381 | 0 | STANDARD | Factory of Ideal Precast Concrete System Company | SAR | 2095473 | APPROVED |  |  | 2024-04-30 | 326006 | 71 | Tananeh, Khalid Jamal | -45341 | 71
105-117 | Ryadhiyah 115/13.8kv SS | 2723 | Ryadhiyah 115/13.8kv SS-ACDB/DCDB & Lighting Panel | APPROVED | No | 2024-02-28 | Abas, Mohammed Fekry | 2024-03-03 | 2024-03-04 |  |  |  | 869999 | 5405 | 0 | STANDARD | ALFANAR CO | SAR | 869999 | APPROVED |  |  | 2024-05-01 | 0 | 58 | Mohammed, Faisal Ansari | -45355 | 58
105-117 | Ryadhiyah 115/13.8kv SS | 2806 | Ryadhiyah 115/13.8kv SS- OVERHEAD TRAVELING CRANE | APPROVED | No | 2024-03-09 | Abas, Mohammed Fekry | 2024-03-10 | 2024-03-10 |  |  |  | 130000 | 5459 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 126870 | APPROVED |  |  | 2024-05-16 | 3130 | 67 | Muhammad, Muhammad Atif | -45361 | 67
105-117 | Ryadhiyah 115/13.8kv SS | 2884 | Ryadhiyah 115/13.8kv SS-Topographic Survey | APPROVED | No | 2024-03-24 | Abas, Mohammed Fekry | 2024-03-25 | 2024-03-25 |  |  |  | 5125 | 5373 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 5125 | APPROVED |  |  | 2024-04-24 | 0 | 30 | Alhadi, Khalid | -45376 | 30
105-117 | Ryadhiyah 115/13.8kv SS | 3054 | Ryadhiyah 115/13.8kv SS-ACDB/DCDB & Lighting Panel | APPROVED | No | 2024-04-17 | Abas, Mohammed Fekry | 2024-04-21 | 2024-04-24 |  |  |  | 1 | 5405 | 0 | STANDARD | ALFANAR CO | SAR | 1 | APPROVED |  |  | 2024-05-01 | 0 | 7 | Mohammed, Faisal Ansari | -45406 | 7
105-117 | Ryadhiyah 115/13.8kv SS | 3067 | Ryadhiyah 115/13.8kv SS-Site Office facility | APPROVED | No | 2024-04-21 | Abas, Mohammed Fekry | 2024-04-21 | 2024-04-23 |  |  |  | 316703 | 5424 | 0 | STANDARD | Construction Expertise Est. | SAR | 316703 | APPROVED |  |  | 2024-05-26 | 0 | 33 | Muhammad, Muhammad Atif | -45405 | 33
105-117 | Ryadhiyah 115/13.8kv SS | 3181 | Ryadhiyah 115/13.8kv SS-Water Proofing | APPROVED | No | 2024-04-28 | Abas, Mohammed Fekry | 2024-04-29 | 2024-04-29 |  |  |  | 392625 | 5655 | 0 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 347826.5 | APPROVED |  |  | 2024-06-13 | 44798.5 | 45 | Tananeh, Khalid Jamal | -45411 | 45
105-117 | Ryadhiyah 115/13.8kv SS | 3187 | Ryadhiyah 115/13.8kv SS-Hollow Metal Doors Works | APPROVED | No | 2024-04-28 | Abas, Mohammed Fekry | 2024-04-29 | 2024-04-29 |  |  |  | 162672 | 6041 | 0 | STANDARD | AL MANASHY COMPANY | SAR | 106036.2 | APPROVED |  |  | 2024-10-21 | 56635.8 | 175 | Tananeh, Khalid Jamal | -45411 | 175
105-117 | Ryadhiyah 115/13.8kv SS | 3192 | Ryadhiyah 115/13.8kv SS-Metal Works | APPROVED | No | 2024-04-28 | Abas, Mohammed Fekry | 2024-04-29 | 2024-04-29 |  |  |  | 426160 | 5938 | 0 | STANDARD | Nesma Alfaris Contracting Est. | SAR | 388300 | APPROVED |  |  | 2024-10-14 | 37860 | 168 | Tananeh, Khalid Jamal | -45411 | 168
105-117 | Ryadhiyah 115/13.8kv SS | 3374 | Ryadhiyah 115/13.8kv SS-150sq.mm, Tinned copper conductor | APPROVED | No | 2024-05-12 | Abas, Mohammed Fekry | 2024-05-16 | 2024-05-17 |  |  |  | 38500 | 5350 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 38455.41 | APPROVED |  |  | 2024-05-21 | 44.59 | 4 | Muhammad, Muhammad Atif | -45429 | 4
105-117 | Ryadhiyah 115/13.8kv SS | 3453 | Ryadhiyah 115/13.8kv SS-Site Office facility Electronic Items | APPROVED | No | 2024-05-21 | Abas, Mohammed Fekry | 2024-05-21 | 2024-05-22 |  |  |  | 33800 | 5604 | 0 | STANDARD | Construction Expertise Est. | SAR | 33800 | APPROVED |  |  | 2024-06-03 | 0 | 12 | Muhammad, Muhammad Atif | -45434 | 12
105-117 | Ryadhiyah 115/13.8kv SS | 3504 | Ryadhiyah 115/13.8kv SS-Battery and Charger | APPROVED | No | 2024-05-27 | Abas, Mohammed Fekry | 2024-05-28 | 2024-05-28 |  |  |  | 550000 | 5735 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 457000 | APPROVED |  |  | 2024-07-09 | 93000 | 42 | Muhammad, Muhammad Atif | -45440 | 42
105-117 | Ryadhiyah 115/13.8kv SS | 3573 | Ryadhiyah 115/13.8kv SS-Grounding Material Accessories | APPROVED | No | 2024-06-03 | Abas, Mohammed Fekry | 2024-06-03 | 2024-06-04 |  |  |  | 73475 | 5553 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 72850 | APPROVED |  |  | 2024-07-02 | 625 | 28 | Muhammad, Muhammad Atif | -45447 | 28
105-117 | Ryadhiyah 115/13.8kv SS | 3722 | Ryadhiyah 115/13.8kv SS-MV POWER CABLE ( 1C × 630mm2 & 1×3C×300mm2 ) | APPROVED | No | 2024-07-01 | Abas, Mohammed Fekry | 2024-07-05 | 2024-07-07 |  |  |  | 1223740 | 5974 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 1093970.6 | APPROVED |  |  | 2024-10-14 | 129769.4 | 99 | Badhman, Saeed | -45480 | 99
105-117 | Ryadhiyah 115/13.8kv SS | 3783 | Ryadhiyah 115/13.8kv SS-Garbage Waste Container, 12 Cu. M (1-year) | APPROVED | No | 2024-07-07 | Abas, Mohammed Fekry | 2024-07-09 | 2024-07-09 |  |  |  | 28800 | 5890 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 19200 | APPROVED |  |  | 2024-08-20 | 9600 | 42 | Akhtar, Farhan | -45482 | 42
105-117 | Ryadhiyah 115/13.8kv SS | 3875 | Ryadhiyah 115/13.8kv SS-Control Cable | APPROVED | No | 2024-07-13 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 716000 | 5821 | 0 | STANDARD | ALFANAR CO | SAR | 531752.8 | APPROVED |  |  | 2024-08-28 | 184247.2 | 43 | Muhammad, Muhammad Atif | -45489 | 43
105-117 | Ryadhiyah 115/13.8kv SS | 3903 | Ryadhiyah 115/13.8kv SS-Testing & Commissioning | APPROVED | No | 2024-07-15 | Abas, Mohammed Fekry | 2024-07-17 | 2024-07-18 |  |  |  | 1908677 | 6442 | 0 | STANDARD | Al Fanar Technical Services | SAR | 1855063 | APPROVED |  |  | 2025-03-13 | 53614 | 238 | Alqadhi, Abdulrahman Abdulghani | -45491 | 238
105-117 | Ryadhiyah 115/13.8kv SS | 3904 | Ryadhiyah 115/13.8kv SS-RTV Coating | APPROVED | No | 2024-07-15 | Abas, Mohammed Fekry | 2024-07-17 | 2024-07-18 |  |  |  | 250000 | 6177 | 0 | STANDARD | SAUDI CONDUIT COATING CO. (S3C) | SAR | 35268 | APPROVED |  |  | 2024-10-13 | 214732 | 87 | Muaz, Alaa | -45491 | 87
105-117 | Ryadhiyah 115/13.8kv SS | 3909 | Ryadhiyah 115/13.8kv SS-MV TERMINATION KITS ( 1C × 630mm2 , 3C×300mm2 ) | APPROVED | No | 2024-07-16 | Abas, Mohammed Fekry | 2024-07-17 | 2024-07-18 |  |  |  | 98839 | 5981 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 95871.89 | APPROVED |  |  | 2024-09-19 | 2967.11 | 63 | Badhman, Saeed | -45491 | 63
105-117 | Ryadhiyah 115/13.8kv SS | 4021 | Ryadhiyah 115/13.8kv SS-LCLM | APPROVED | No | 2024-07-25 | Abas, Mohammed Fekry | 2024-07-29 | 2024-07-29 |  |  |  | 59075 | 5960 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 59075 | APPROVED |  |  | 2024-10-06 | 0 | 69 | Badhman, Saeed | -45502 | 69
105-117 | Ryadhiyah 115/13.8kv SS | 4049 | Ryadhiyah 115/13.8kv SS-Cable Trays & Ladders along with Accessories | APPROVED | No | 2024-07-29 | Abas, Mohammed Fekry | 2024-07-31 | 2024-07-31 |  |  |  | 552885 | 5896 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 505784.96 | APPROVED |  |  | 2024-09-18 | 47100.04 | 49 | Muhammad, Muhammad Atif | -45504 | 49
105-117 | Ryadhiyah 115/13.8kv SS | 4170 | Ryadhiyah 115/13.8kv SS-LV AC / DC Cables and Lighitng Wires | APPROVED | No | 2024-08-17 | Abas, Mohammed Fekry | 2024-08-19 | 2024-08-19 |  |  |  | 1611070 | 6076 | 0 | STANDARD | ALFANAR CO | SAR | 1110509.38 | APPROVED |  |  | 2024-09-26 | 500560.62 | 38 | Badhman, Saeed | -45523 | 38
105-117 | Ryadhiyah 115/13.8kv SS | 4185 | Ryadhiyah 115/13.8kv SS-Hazardou and Non Hazardous Waste | APPROVED | No | 2024-08-18 | Abas, Mohammed Fekry | 2024-08-19 | 2024-08-19 |  |  |  | 5000 | 6117 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 3650 | APPROVED |  |  | 2024-09-16 | 1350 | 28 | Akhtar, Farhan | -45523 | 28
105-117 | Ryadhiyah 115/13.8kv SS | 4203 | Ryadhiyah 115/13.8kv SS-Supply and delivery of drinking Water 6 Cu. M Fiber Glass tank | APPROVED | No | 2024-08-19 | Abas, Mohammed Fekry | 2024-08-21 | 2024-08-22 |  |  |  | 3000 | 6094 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 3000 | APPROVED |  |  | 2024-09-02 | 0 | 11 | Akhtar, Farhan | -45526 | 11
105-117 | Ryadhiyah 115/13.8kv SS | 4206 | Ryadhiyah 115/13.8kv SS-Supply and delivery of Raw Water 10 Cu. M tanker | APPROVED | No | 2024-08-19 | Abas, Mohammed Fekry | 2024-08-21 | 2024-08-22 |  |  |  | 1800 | 6094 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 1800 | APPROVED |  |  | 2024-09-02 | 0 | 11 | Akhtar, Farhan | -45526 | 11
105-117 | Ryadhiyah 115/13.8kv SS | 4211 | Ryadhiyah 115/13.8kv SS-Sewage water removal services 10,000 liters | APPROVED | No | 2024-08-19 | Abas, Mohammed Fekry | 2024-08-21 | 2024-08-22 |  |  |  | 300 | 6094 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 300 | APPROVED |  |  | 2024-09-02 | 0 | 11 | Akhtar, Farhan | -45526 | 11
105-117 | Ryadhiyah 115/13.8kv SS | 4226 | Ryadhiyah 115/13.8kv SS-Grounding Cables 0.6/1 KV Y/G | APPROVED | No | 2024-08-20 | Abas, Mohammed Fekry | 2024-08-22 | 2024-08-22 |  |  |  | 244150 | 6060 | 0 | STANDARD | ALFANAR CO | SAR | 226756.52 | APPROVED |  |  | 2024-09-18 | 17393.48 | 27 | Muhammad, Muhammad Atif | -45526 | 27
105-117 | Ryadhiyah 115/13.8kv SS | 4317 | Ryadhiyah 115/13.8kv SS-Electrical Resistivity Soil test | APPROVED | No | 2024-08-29 | Abas, Mohammed Fekry | 2024-09-02 | 2024-09-04 |  |  |  | 8000 | 6140 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 6400 | APPROVED |  |  | 2024-11-14 | 1600 | 71 | Tananeh, Khalid Jamal | -45539 | 71
105-117 | Ryadhiyah 115/13.8kv SS | 4368 | Ryadhiyah 115/13.8kv SS-Fire Protection System | APPROVED | No | 2024-09-04 | Abas, Mohammed Fekry | 2024-09-05 | 2024-09-05 |  |  |  | 2297310 | 5999 | 0 | STANDARD | Al Majal Group Four S for Security & Safety | SAR | 2274336.9 | APPROVED |  |  | 2024-09-18 | 22973.1 | 13 | Muhammad, Muhammad Atif | -45540 | 13
105-117 | Ryadhiyah 115/13.8kv SS | 4462 | Ryadhiyah 115/13.8kv SS-Station Service Transformer-750KVA | APPROVED | No | 2024-09-16 | Abas, Mohammed Fekry | 2024-09-17 | 2024-09-17 |  |  |  | 164000 | 5904 | 0 | STANDARD | ALFANAR CO | SAR | 164000 | APPROVED |  |  | 2024-10-06 | 0 | 19 | Muhammad, Muhammad Atif | -45552 | 19
105-117 | Ryadhiyah 115/13.8kv SS | 4587 | Ryadhiyah 115/13.8kv SS-Electrical Installation Sub Contractor | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-06 | 2024-10-06 |  |  |  | 2992521 | 6399 | 0 | STANDARD | Future Vision Company | SAR | 2390000 | APPROVED |  |  | 2024-12-29 | 602521 | 84 | Muhammad, Muhammad Atif | -45571 | 84
105-117 | Ryadhiyah 115/13.8kv SS | 4674 | Ryadhiyah 115/13.8kv SS-HVAC SYSTEM | APPROVED | No | 2024-10-15 | Abas, Mohammed Fekry | 2024-10-15 | 2024-10-15 |  |  |  | 2220000 | 6199 | 0 | STANDARD | Magna Contracting Co | SAR | 2050000 | APPROVED |  |  | 2024-11-05 | 170000 | 21 | Muhammad, Muhammad Atif | -45580 | 21
105-117 | Ryadhiyah 115/13.8kv SS | 4751 | Ryadhiyah 115/13.8kv SS-Asphalt work | RETURNED | No | 2024-10-20 | Tananeh, Khalid Jamal | 2025-04-21 | 2024-10-22 | 2025-04-21 |  | The PR has been resubmitted based on the email sent, with the value adjusted according to the approved PO. | 350000 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45587 | -45587
105-117 | Ryadhiyah 115/13.8kv SS | 4959 | Ryadhiyah 115/13.8kv SS-Lighting Fixtures | APPROVED | No | 2024-11-14 | Abas, Mohammed Fekry | 2024-11-17 | 2024-11-17 |  |  |  | 88037 | 6467 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 88037 | APPROVED |  |  | 2024-11-28 | 0 | 11 | Muhammad, Muhammad Atif | -45613 | 11
105-117 | Ryadhiyah 115/13.8kv SS | 5061 | Ryadhiyah 115/13.8kv SS-Civil Sub Contractor | APPROVED | No | 2024-11-27 | Abas, Mohammed Fekry | 2024-12-01 | 2024-12-01 |  |  |  | 7750000 | 5662 | 0 | STANDARD | Future Achievement Limited Co | SAR | 7750000 | APPROVED |  |  | 2024-12-23 | 0 | 22 | Alhadi, Khalid | -45627 | 22
105-117 | Ryadhiyah 115/13.8kv SS | 5095 | Ryadhiyah 115/13.8kv SS-HCIS-3 Consultancy for Security System | APPROVED | No | 2024-11-30 | Abas, Mohammed Fekry | 2025-01-08 | 2025-01-08 |  |  |  | 33500 | 6506 | 0 | STANDARD | Khaled Drewesh Office for Consulting Security (KDOCS) | SAR | 33500 | APPROVED |  |  | 2025-01-13 | 0 | 5 | Muhammad, Muhammad Atif | -45665 | 5
105-117 | Ryadhiyah 115/13.8kv SS | 5104 | Ryadhiyah 115/13.8kv SS-Fiber Optic Cables & Accessories, Installation and Testing Services | APPROVED | No | 2024-12-01 | Abas, Mohammed Fekry | 2024-12-02 | 2024-12-03 |  |  |  | 220000 | 6617 | 0 | STANDARD | Arabian Power Trading Est. | SAR | 188000 | APPROVED |  |  | 2024-12-24 | 32000 | 21 | Muhammad, Muhammad Atif | -45629 | 21
105-117 | Ryadhiyah 115/13.8kv SS | 5114 | Ryadhiyah 115/13.8kv SS-Al. Connector for GIB Bushing | APPROVED | No | 2024-12-03 | Abas, Mohammed Fekry | 2024-12-04 | 2024-12-04 |  |  |  | 5675 | 6411 | 0 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 4606.53 | APPROVED |  |  | 2024-12-25 | 1068.47 | 21 | Mohammed, Faisal Ansari | -45630 | 21
105-117 | Ryadhiyah 115/13.8kv SS | 5140 | Ryadhiyah 115/13.8kv SS-Supply and delivery of drinking Water 6 Cu. M Fiber Glass tank | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-11 | 2024-12-12 |  |  |  | 5250 | 6675 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 4500 | APPROVED |  |  | 2025-01-02 | 750 | 21 | Akhtar, Farhan | -45638 | 21
105-117 | Ryadhiyah 115/13.8kv SS | 5145 | Ryadhiyah 115/13.8kv SS-Supply and delivery of Raw Water 10 Cu. M tanker | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-15 | 2024-12-15 |  |  |  | 2100 | 6675 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 1800 | APPROVED |  |  | 2025-01-02 | 300 | 18 | Akhtar, Farhan | -45641 | 18
105-117 | Ryadhiyah 115/13.8kv SS | 5150 | Ryadhiyah 115/13.8kv SS-Sewage water removal services 10,000 liters | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-15 | 2024-12-15 |  |  |  | 300 | 6675 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 300 | APPROVED |  |  | 2025-01-02 | 0 | 18 | Akhtar, Farhan | -45641 | 18
105-117 | Ryadhiyah 115/13.8kv SS | 5282 | Ryadhiyah 115/13.8kv SS-150mm2 Tinned Copper Conductor | APPROVED | No | 2024-12-28 | Abas, Mohammed Fekry | 2024-12-31 | 2025-01-01 |  |  |  | 131100 | 6752 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 121307.52 | APPROVED |  |  | 2025-03-06 | 9792.48 | 64 | Alhadi, Khalid | -45658 | 64
105-117 | Ryadhiyah 115/13.8kv SS | 5358 | Ryadhiyah 115/13.8kv SS-Supply of Conduits and Fittings | APPROVED | No | 2025-01-05 | Abas, Mohammed Fekry | 2025-01-08 | 2025-01-12 |  |  |  | 337272.4 | 6717 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 337271.55 | APPROVED |  |  | 2025-01-22 | 0.85 | 10 | Muaz, Alaa | -45669 | 10
105-117 | Ryadhiyah 115/13.8kv SS | 5363 | Ryadhiyah 115/13.8kv SS-Supply, Installation, Testing & Comissioning of Security System as per HCIS Standards | APPROVED | No | 2025-01-06 | Abas, Mohammed Fekry | 2025-05-21 | 2025-05-27 |  |  |  | 855654.22 | 6638 | 0 | STANDARD | CEGELEC NETWORK AND SECURITY SYSTEMS | SAR | 855654.22 | APPROVED |  |  | 2025-07-07 | 0 | 41 | Abdulqader, Ahmed Abdulhalim | -45804 | 41
105-117 | Ryadhiyah 115/13.8kv SS | 5429 | Ryadhiyah 115/13.8kv SS-LCLM | APPROVED | No | 2025-01-14 | Abas, Mohammed Fekry | 2025-01-19 | 2025-01-19 |  |  |  | 30300 | 5960 | 1 | STANDARD | Al-Babtain Power & Telecom | SAR | 30075 | APPROVED |  |  | 2025-04-21 | 225 | 92 | Badhman, Saeed | -45676 | 92
105-117 | Ryadhiyah 115/13.8kv SS | 5459 | Ryadhiyah 115/13.8kv SS-CT Junction Box with 9 Single Phase CTPU including all Accessories | APPROVED | No | 2025-01-19 | Abas, Mohammed Fekry | 2025-01-19 | 2025-01-19 |  |  |  | 68000 | 6251 | 0 | STANDARD | Energy Tracks For Contracting | SAR | 68000 | APPROVED |  |  | 2025-03-04 | 0 | 44 | Kumar, Mr. Ranjan | -45676 | 44
105-117 | Ryadhiyah 115/13.8kv SS | 5539 | Ryadhiyah 115/13.8kv SS-Remote end modification for TFR , DSM | APPROVED | No | 2025-01-23 | Abas, Mohammed Fekry | 2025-01-26 | 2025-01-26 |  |  |  | 100000 | 7450 | 0 | STANDARD | TRINERGY TECHNOLOGIES SA | SAR | 61231 | APPROVED |  |  | 2025-07-06 | 38769 | 161 | Babic, Marian | -45683 | 161
105-117 | Ryadhiyah 115/13.8kv SS | 5623 | Ryadhiyah 115/13.8kv SS-3rd Party Lab Inspector for Precast Concrete Production Test | APPROVED | No | 2025-01-26 | Abas, Mohammed Fekry | 2025-01-30 | 2025-01-31 |  |  |  | 84190 | 7360 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 84190 | APPROVED |  |  | 2025-08-21 | 0 | 202 | Tananeh, Khalid Jamal | -45688 | 202
105-117 | Ryadhiyah 115/13.8kv SS | 6015 | Ryadhiyah 115/13.8kv SS-TEA BOY | RETURNED | No | 2025-02-20 | Abuhammad, Samir | 2025-12-22 | 2025-02-27 | 2025-12-22 |  | As no rental manpower | 13500 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45715 | -45715
105-117 | Ryadhiyah 115/13.8kv SS | 6104 | Ryadhiyah 115/13.8kv SS-Drawing Printing & Scanning | APPROVED | No | 2025-03-03 | Abas, Mohammed Fekry | 2025-03-05 | 2025-03-05 |  |  | Line Item: 2.33 - Drawing Printing & Scanning | 35000 | 7066 | 0 | STANDARD | Print Magaies Al abdaa Printing | SAR | 35000 | APPROVED |  |  | 2025-04-07 | 0 | 33 | Abuhammad, Samir | -45721 | 33
105-117 | Ryadhiyah 115/13.8kv SS | 6144 | Ryadhiyah 115/13.8kv SS-Cable Trays Acessories | APPROVED | No | 2025-03-10 | Abas, Mohammed Fekry | 2025-03-11 | 2025-03-12 |  |  | line item 2.19-Cable Trays Acessories | 44950 | 7152 | 0 | STANDARD | AL-AMAL ELECTRICAL SWITCHBOARDS | SAR | 14966.6 | APPROVED |  |  | 2025-04-24 | 29983.4 | 43 | Muaz, Alaa | -45728 | 43
105-117 | Ryadhiyah 115/13.8kv SS | 6190 | Ryadhiyah 115/13.8kv SS-Fence Relocation | APPROVED | No | 2025-03-17 | Abas, Mohammed Fekry | 2025-03-18 | 2025-03-20 |  |  | line item 2.20-Fence Relocation | 31340 | 7107 | 0 | STANDARD | Construction Expertise Est. | SAR | 23450 | APPROVED |  |  | 2025-08-10 | 7890 | 143 | Abdulqader, Ahmed Abdulhalim | -45736 | 143
105-117 | Ryadhiyah 115/13.8kv SS | 6232 | Ryadhiyah 115/13.8kv SS-Technicians for Testing & Commissioning | APPROVED | No | 2025-03-23 | Abas, Mohammed Fekry | 2025-03-23 | 2025-03-24 |  |  | line item 2.30-Technicians for Testing & Commissioning | 191000 | 7467 | 0 | STANDARD | SMART LINES INDUSTRIAL & SERVCIES COMPANY | SAR | 190998 | APPROVED |  |  | 2025-07-10 | 2 | 108 | Babic, Marian | -45740 | 108
105-117 | Ryadhiyah 115/13.8kv SS | 6232 | Ryadhiyah 115/13.8kv SS-Technicians for Testing & Commissioning | APPROVED | No | 2025-03-23 | Abas, Mohammed Fekry | 2025-03-23 | 2025-03-24 |  |  | line item 2.30-Technicians for Testing & Commissioning | 191000 | 7467 | 2 | STANDARD | SMART LINES INDUSTRIAL & SERVCIES COMPANY | SAR | 190998 | IN PROCESS |  |  |  | 2 | 314 | Babic, Marian | -45740 | -45740
105-117 | Ryadhiyah 115/13.8kv SS | 6312 | Ryadhiyah 115/13.8kv SS-Tower AC-5T0N | APPROVED | No | 2025-04-09 | Abas, Mohammed Fekry | 2025-04-10 | 2025-04-13 |  |  | line item 2.33-Tower AC-5T0N | 71760 | 7144 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 61600 | APPROVED |  |  | 2025-04-24 | 10160 | 11 | Abuhammad, Samir | -45760 | 11
105-117 | Ryadhiyah 115/13.8kv SS | 6363 | Ryadhiyah 115/13.8kv SS-7X2.5 mm2 CU/XLPE/CTS/PVC | APPROVED | No | 2025-04-17 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-21 |  |  | line item 2.13-7X2.5 mm2 CU/XLPE/CTS/PVC | 52600 | 6778 | 0 | STANDARD | ALFANAR CO | SAR | 52600 | APPROVED |  |  | 2025-04-30 | 0 | 9 | Muaz, Alaa | -45768 | 9
|  |  | 0.6/1 KV – Blue Color | [8 empty] | 0.6/1 KV – Blue Color | [14 empty] | 0 | 0
105-117 | Ryadhiyah 115/13.8kv SS | 6394 | Ryadhiyah 115/13.8kv SS-Closing of Opening - Switchgear Room to Control Room | APPROVED | No | 2025-04-20 | Abas, Mohammed Fekry | 2025-04-21 | 2025-04-21 |  |  | Line Item - 2.20: Closing of Opening - Switchgear Room to Control Room | 6000 | 7200 | 0 | STANDARD | Tamim Company (PVT) LTD | SAR | 6000 | APPROVED |  |  | 2025-04-30 | 0 | 9 | Abuhammad, Samir | -45768 | 9
105-117 | Ryadhiyah 115/13.8kv SS | 6413 | Ryadhiyah 115/13.8kv SS-Sealant work for External Wall | REJECTED | No | 2025-04-22 | Ibrahim, Mahmoud Hassan Ali | 2025-06-19 | 2025-04-22 |  | 2025-06-23 |  | 55000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45769 | -45769
105-117 | Ryadhiyah 115/13.8kv SS | 6435 | Ryadhiyah 115/13.8kv SS-Supply & Delivery of Raw Water,Drinking Water & Sweage Removal | APPROVED | No | 2025-04-23 | Abas, Mohammed Fekry | 2025-04-23 | 2025-04-24 |  |  | line item 2.33-Supply & Delivery of Raw Water,Drinking Water & Sweage Removal | 6600 | 6675 | 1 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 6600 | APPROVED |  |  | 2025-07-14 | 0 | 81 | Akhtar, Farhan | -45771 | 81
105-117 | Ryadhiyah 115/13.8kv SS | 6513 | Ryadhiyah 115/13.8kv SS-4P x 1.5Sqmm Cable | APPROVED | No | 2025-05-05 | Abas, Mohammed Fekry | 2025-05-06 | 2025-05-06 |  |  | Line Item: 2.13 - 4P x 1.5 Sqmm Cable | 9000 | 7311 | 0 | STANDARD | Middle East Specialized Cables Mesc | SAR | 7500 | APPROVED |  |  | 2025-05-27 | 1500 | 21 | Abuhammad, Samir | -45783 | 21
105-117 | Ryadhiyah 115/13.8kv SS | 6647 | Ryadhiyah 115/13.8kv SS-T&C Technicians (Rental) | APPROVED | No | 2025-05-19 | Abas, Mohammed Fekry | 2025-05-25 | 2025-05-26 |  |  | Line Item - 2.31: T&C Technicians (Rental) | 80000 | 7467 | 0 | STANDARD | SMART LINES INDUSTRIAL & SERVCIES COMPANY | SAR | 80000 | APPROVED |  |  | 2025-07-10 | 0 | 45 | Babic, Marian | -45803 | 45
105-117 | Ryadhiyah 115/13.8kv SS | 6647 | Ryadhiyah 115/13.8kv SS-T&C Technicians (Rental) | APPROVED | No | 2025-05-19 | Abas, Mohammed Fekry | 2025-05-25 | 2025-05-26 |  |  | Line Item - 2.31: T&C Technicians (Rental) | 80000 | 7467 | 2 | STANDARD | SMART LINES INDUSTRIAL & SERVCIES COMPANY | SAR | 80000 | IN PROCESS |  |  |  | 0 | 251 | Babic, Marian | -45803 | -45803
105-117 | Ryadhiyah 115/13.8kv SS | 6690 | Ryadhiyah 115/13.8kv SS-Grounding Accessories | APPROVED | No | 2025-05-22 | Abas, Mohammed Fekry | 2025-05-27 | 2025-05-27 |  |  | Line Item 2.21 - Grounding Accessories | 70594.7 | 7090 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 70594.7 | APPROVED |  |  | 2025-06-22 | 0 | 26 | Abdulqader, Ahmed Abdulhalim | -45804 | 26
105-117 | Ryadhiyah 115/13.8kv SS | 6740 | Ryadhiyah 115/13.8kv SS-125V DC DB for Communication System | APPROVED | No | 2025-05-28 | Abas, Mohammed Fekry | 2025-07-06 | 2025-07-07 |  |  | Line Item 2.12 - 125V DC DB for Communication System | 35000 | 7522 | 0 | STANDARD | HAWA ELECTRIC PANEL BOARD FAC | SAR | 29700 | APPROVED |  |  | 2025-07-27 | 5300 | 20 | Abuhammad, Samir | -45845 | 20
105-117 | Ryadhiyah 115/13.8kv SS | 6783 | Ryadhiyah 115/13.8kv SS-Communication System | APPROVED | No | 2025-06-12 | Abas, Mohammed Fekry | 2025-06-15 | 2025-06-15 |  |  | line item 2.4-Communication System | 1892635 | 5850 | 0 | STANDARD | ALFANAR CO | SAR | 1892634.08 | APPROVED |  |  | 2025-06-24 | 0.92 | 9 | Kumar, Mr. Ranjan | -45823 | 9
105-117 | Ryadhiyah 115/13.8kv SS | 6911 | Ryadhiyah 115/13.8kv SS-Wiring devices( Switches, Socket and Push Buttons) | APPROVED | No | 2025-06-26 | Abas, Mohammed Fekry | 2025-06-30 | 2025-07-01 |  |  | line item 2.23-Wiring devices( Switches, Socket and Push Buttons) | 96720 | 7184 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 96720 | APPROVED |  |  | 2025-07-14 | 0 | 13 | Muaz, Alaa | -45839 | 13
105-117 | Ryadhiyah 115/13.8kv SS | 6981 | Ryadhiyah 115/13.8kv SS-Container for Material-length-12meter/40ft | RETURNED | No | 2025-07-05 | Abdulqader, Ahmed Abdulhalim | 2025-10-06 | 2025-07-07 | 2025-10-06 |  | not required available in warhouse as per logistic team | 25000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45845 | -45845
105-117 | Ryadhiyah 115/13.8kv SS | 7015 | Ryadhiyah 115/13.8kv SS-HV MV Cable Supports | APPROVED | No | 2025-07-08 | Abas, Mohammed Fekry | 2025-07-09 | 2025-07-09 |  |  | LINE ITEM 2.19-HV MV Cable Supports | 120765 | 7295 | 0 | STANDARD | Power Solution Industries | SAR | 120765 | APPROVED |  |  | 2025-08-12 | 0 | 34 | Hegazy, Ayman | -45847 | 34
105-117 | Ryadhiyah 115/13.8kv SS | 7015 | Ryadhiyah 115/13.8kv SS-HV MV Cable Supports | APPROVED | No | 2025-07-08 | Abas, Mohammed Fekry | 2025-07-09 | 2025-07-09 |  |  | LINE ITEM 2.19-HV MV Cable Supports | 120765 | 7295 | 1 | STANDARD | Power Solution Industries | SAR | 120765 | REQUIRES REAPPROVAL |  |  |  | 0 | 207 | Hegazy, Ayman | -45847 | -45847
105-117 | Ryadhiyah 115/13.8kv SS | 7063 | Ryadhiyah 115/13.8kv SS-Supply for Diesal Genrator | APPROVED | No | 2025-07-10 | Abas, Mohammed Fekry | 2025-07-14 | 2025-07-14 |  |  | line item 2.33-Supply for Diesal Genrator | 50660 | 7503 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 50660 | APPROVED |  |  | 2025-07-22 | 0 | 8 | Akhtar, Farhan | -45852 | 8
105-117 | Ryadhiyah 115/13.8kv SS | 7079 | Ryadhiyah 115/13.8kv SS-Supply with installation of AC units Stand Type 5 Ton | APPROVED | No | 2025-07-13 | Abas, Mohammed Fekry | 2025-07-14 | 2025-07-14 |  |  | line item 2.33-Supply with installation of AC units Stand Type 5 Ton | 30000 | 7529 | 0 | STANDARD | Versatile Advanced Limited Company. | SAR | 27000 | APPROVED |  |  | 2025-07-27 | 3000 | 13 | Akhtar, Farhan | -45852 | 13
105-117 | Ryadhiyah 115/13.8kv SS | 7087 | Ryadhiyah 115/13.8kv SS-PDS System | APPROVED | No | 2025-07-14 | Abas, Mohammed Fekry | 2025-07-22 | 2025-07-22 |  |  | Line item 2.5-PDS System | 200000 | 7763 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 140000 | APPROVED |  |  | 2025-11-19 | 60000 | 120 | Hegazy, Ayman | -45860 | 120
105-117 | Ryadhiyah 115/13.8kv SS | 7113 | Ryadhiyah 115/13.8kv SS-MV CABLE CLEATS | APPROVED | No | 2025-07-16 | Abas, Mohammed Fekry | 2025-07-17 | 2025-07-20 |  |  | line item 2.13-MV Cable CLAMP/Cleats | 56525 | 7256 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 56525 | APPROVED |  |  | 2025-08-10 | 0 | 21 | Hegazy, Ayman | -45858 | 21
105-117 | Ryadhiyah 115/13.8kv SS | 7247 | Ryadhiyah 115/13.8kv SS-1Cx500 Sq. mm 0.6/1 KV, Cu / | RETURNED | No | 2025-07-30 | Mohammed, Mohammed Adel Fahmy | 2026-01-15 | 2025-08-04 | 2026-01-15 |  | Not Have POCR Until Now and PR incorrect qty. | 221400 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Mohammed Adel Fahmy | -45873 | -45873
|  |  | XLPE / PVC | [23 empty] | 0 | 0
105-117 | Ryadhiyah 115/13.8kv SS | 7277 | Ryadhiyah 115/13.8kv SS-Water Proofing work | APPROVED | No | 2025-08-04 | Abas, Mohammed Fekry | 2025-08-05 | 2025-08-06 |  |  | line item 2.20-Water Proofing work | 37265 | 5655 | 1 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 37264.54 | APPROVED |  |  | 2025-09-17 | 0.46 | 42 | Tananeh, Khalid Jamal | -45875 | 42
105-117 | Ryadhiyah 115/13.8kv SS | 7291 | Ryadhiyah 115/13.8kv SS-Control Cable 7* 2.5Sq.mm Blue Colour for SAS | RETURNED | No | 2025-08-05 | Mohammed, Mohammed Adel Fahmy | 2026-01-15 | 2025-08-07 | 2026-01-15 |  | Not Have POCR Until Now and PR incorrect qty. | 36000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Mohammed Adel Fahmy | -45876 | -45876
105-117 | Ryadhiyah 115/13.8kv SS | 7293 | Ryadhiyah 115/13.8kv SS-Control Cables | RETURNED | No | 2025-08-05 | Mohammed, Mohammed Adel Fahmy | 2026-01-15 | 2025-08-07 | 2026-01-15 |  | Not Have POCR Until Now and PR incorrect qty. | 128000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Mohammed Adel Fahmy | -45876 | -45876
105-117 | Ryadhiyah 115/13.8kv SS | 7504 | DECORATIVE FENCE | APPROVED | No | 2025-08-26 | Abas, Mohammed Fekry | 2025-08-26 | 2025-08-26 |  |  | Line item 2.20-DECORATIVE FENCE | 0 | 7657 | 0 | STANDARD | Fursan Construction Industry Factory Industry Factory | SAR | 649085 | APPROVED |  |  | 2025-09-14 | -649085 | 19 | Hegazy, Ayman | -45895 | 19
105-117 | Ryadhiyah 115/13.8kv SS | 7546 | Excavation and Back filling work | RETURNED | No | 2025-08-27 | Tananeh, Khalid Jamal | 2025-10-23 | 2025-09-03 | 2025-10-23 |  | return the PR., as per email , o Muhammad Afzal Wed 10/22/2025 12:12 PM and POCR was not approve | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45903 | -45903
105-117 | Ryadhiyah 115/13.8kv SS | 7549 | Lugs and Glands | APPROVED | No | 2025-08-27 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-03 |  |  | Line item 2.13 Lugs and Glands | 0 | 7575 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 21719.52 | APPROVED |  |  | 2025-09-10 | -21719.52 | 7 | Abdulqader, Ahmed Abdulhalim | -45903 | 7
105-117 | Ryadhiyah 115/13.8kv SS | 7683 | Testing Technician | APPROVED | No | 2025-09-08 | Abas, Mohammed Fekry | 2025-09-09 | 2025-09-10 |  |  | line item 2.31- Rental Testing Techician for 1 month | 0 | 7467 | 1 | STANDARD | SMART LINES INDUSTRIAL & SERVCIES COMPANY | SAR | 49998 | APPROVED |  |  | 2025-10-16 | -49998 | 36 | Babic, Marian | -45910 | 36
105-117 | Ryadhiyah 115/13.8kv SS | 7683 | Testing Technician | APPROVED | No | 2025-09-08 | Abas, Mohammed Fekry | 2025-09-09 | 2025-09-10 |  |  | line item 2.31- Rental Testing Techician for 1 month | 0 | 7467 | 2 | STANDARD | SMART LINES INDUSTRIAL & SERVCIES COMPANY | SAR | 49998 | IN PROCESS |  |  |  | -49998 | 144 | Babic, Marian | -45910 | -45910
105-117 | Ryadhiyah 115/13.8kv SS | 7707 | Cu Tape 25*3 | RETURNED | No | 2025-09-10 | Hegazy, Ayman | 2025-11-11 | 2025-09-21 | 2025-11-11 |  | To update the descreption and QTY. | 0 | 7693 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 600 | APPROVED |  |  | 2025-10-13 | -600 |  | Abdulqader, Ahmed Abdulhalim | -45921 | 22
105-117 | Ryadhiyah 115/13.8kv SS | 7707 | Cu Tape 25*3 | RETURNED | No | 2025-09-10 | Hegazy, Ayman | 2025-11-11 | 2025-09-21 | 2025-11-11 |  | To update the descreption and QTY. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -45921 | -45921
105-117 | Ryadhiyah 115/13.8kv SS | 7709 | Excavation, Base Course, and General Backfilling Work | REJECTED | No | 2025-09-10 | Ibrahim, Mahmoud Hassan Ali | 2025-09-24 | 2025-09-10 |  | 2025-09-24 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45910 | -45910
105-117 | Ryadhiyah 115/13.8kv SS | 7750 | 150kVA Diesel Generator | RETURNED | No | 2025-09-15 | Badhman, Saeed | 2025-10-27 | 2025-09-16 | 2025-10-27 |  | PR isnt compleate | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45916 | -45916
105-117 | Ryadhiyah 115/13.8kv SS | 7765 | Office Furniture | APPROVED | No | 2025-09-16 | Abas, Mohammed Fekry | 2025-09-18 | 2025-09-19 |  |  | line item 2.33-Office Furniture | 0 | 7709 | 0 | STANDARD | ALISMAIL INDUSTRIAL CO.(S) | SAR | 17590 | APPROVED |  |  | 2025-10-13 | -17590 | 24 | Abdulqader, Ahmed Abdulhalim | -45919 | 24
105-117 | Ryadhiyah 115/13.8kv SS | 7813 | Excavation work,Base work and Gen Back filling work | REJECTED | No | 2025-09-24 | Ibrahim, Mahmoud Hassan Ali | 2025-12-21 | 2025-09-24 |  | 2025-12-21 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45924 | -45924
105-117 | Ryadhiyah 115/13.8kv SS | 7844 | Tranportation Charges for PO # 7693 | REJECTED | No | 2025-09-28 | Ibrahim, Mahmoud Hassan Ali | 2025-11-18 | 2025-09-29 |  | 2025-11-18 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45929 | -45929
105-117 | Ryadhiyah 115/13.8kv SS | 7986 | Swing Gate Motor | APPROVED | No | 2025-10-16 | Abas, Mohammed Fekry | 2025-10-23 | 2025-10-25 |  |  | Line item 2.20-Swing Gate Motor-Including All Accesssories, Procurement, Installation, Testing & Commissioning. | 0 | 7926 | 0 | STANDARD | ALMOSALLAMY INDUSTRIAL COMPANY | SAR | 9330 | APPROVED |  |  | 2025-12-15 | -9330 | 51 | Abdelraouf, Islam ِAdel Hanafy | -45955 | 51
105-117 | Ryadhiyah 115/13.8kv SS | 8039 | Technicians for Testing & Commissioning | APPROVED | No | 2025-10-23 | Abas, Mohammed Fekry | 2025-12-21 | 2025-12-21 |  |  | line item 2.31-Technicians for Testing & Commissioning additional Man hour ( 6240Hr) required as approved. | 0 | 7467 | 2 | STANDARD | SMART LINES INDUSTRIAL & SERVCIES COMPANY | SAR | 162240 | IN PROCESS |  |  |  | -162240 | 42 | Babic, Marian | -46012 | -46012
105-117 | Ryadhiyah 115/13.8kv SS | 8039 | Technicians for Testing & Commissioning | APPROVED | No | 2025-10-23 | Abas, Mohammed Fekry | 2025-12-21 | 2025-12-21 |  |  | line item 2.31-Technicians for Testing & Commissioning additional Man hour ( 6240Hr) required as approved. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46012 | -46012
105-117 | Ryadhiyah 115/13.8kv SS | 8068 | 40MM*6MM Bare Copper Tapes | APPROVED | No | 2025-10-27 | Abas, Mohammed Fekry | 2025-10-29 | 2025-10-30 |  |  | line item 2.21-40MM*6MM Bare Copper Tapes-(Riyadhia SS) | 0 | 7693 | 1 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 52840 | APPROVED |  |  | 2025-11-20 | -52840 | 21 | Abdulqader, Ahmed Abdulhalim | -45960 | 21
105-117 | Ryadhiyah 115/13.8kv SS | 8071 | 150kVA Diesel Generator | APPROVED | No | 2025-10-28 | Abas, Mohammed Fekry | 2025-10-29 | 2025-10-30 |  |  | line item 2.33-150kVA Diesel Generator 1no. for 6 months- Riyadhia SS | 0 | 7884 | 0 | STANDARD | Energia Model General Contracting Company | SAR | 49400 | APPROVED |  |  | 2025-12-11 | -49400 | 42 | Badhman, Saeed | -45960 | 42
105-117 | Ryadhiyah 115/13.8kv SS | 8269 | Copper Tape 40x6 | REJECTED | No | 2025-11-18 | Mughal, Aurang | 2025-11-18 |  |  | 2025-11-18 | Budget line 2.21 - Grounding & Shielding system | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-117 | Ryadhiyah 115/13.8kv SS | 8463 | Acs for Site 5 ton | RETURNED | No | 2025-12-07 | Abuhammad, Samir | 2025-12-29 | 2025-12-09 | 2025-12-29 |  | Free of cost delivery. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46000 | -46000
105-117 | Ryadhiyah 115/13.8kv SS | 8473 | Lighting Motion Sensor | APPROVED | No | 2025-12-08 | Abas, Mohammed Fekry | 2025-12-15 | 2025-12-17 |  |  | line item 2.22-Lighting Motion Sensor-Ryadhia SS | 0 | 7345 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 72407 | APPROVED | 2025-12-23 | 2025-12-26 | 2026-01-08 | -72407 | 22 | Muaz, Alaa | 9 | 22
105-117 | Ryadhiyah 115/13.8kv SS | 8592 | Metal Works (Change Order) | APPROVED | No | 2025-12-28 | Abas, Mohammed Fekry | 2025-12-30 | 2026-01-01 |  |  | Budget line 2.20 - Civil Works | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46023 | -46023
105-117 | Ryadhiyah 115/13.8kv SS | 8645 | Metal Doors (Change Order) - Ryadiyah | APPROVED | No | 2026-01-05 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-13 |  |  | Budget line 2.20 - Civil works | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46035 | -46035
105-117 | Ryadhiyah 115/13.8kv SS | 8675 | Supply & Delivery of Raw Water, Drinking Water & Sweage Removal | APPROVED | No | 2026-01-26 | Abas, Mohammed Fekry | 2026-01-29 | 2026-02-01 |  |  | Line Item - 2.33: Supply & Delivery of Raw Water, Drinking Water & Sweage Removal | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46054 | -46054
105-117 | Ryadhiyah 115/13.8kv SS | 8759 | Disposal of Hazardous Waste | APPROVED | No | 2026-01-21 | Abas, Mohammed Fekry | 2026-01-25 | 2026-01-26 |  |  | Line Item - 2.33: Disposal of Hazardous Waste | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -46048 | -46048
105-117 | Ryadhiyah 115/13.8kv SS | 8786 | Substation Grounding Material | IN PROCESS | No | 2026-01-25 | Abas, Mohammed Fekry | 2026-01-29 | 2026-01-29 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46051 | -46051
105-117 | Ryadhiyah 115/13.8kv SS | 8827 | 150 mm.sq Tinned Copper Conductor | IN PROCESS | No | 2026-01-28 | Abas, Mohammed Fekry | 2026-01-29 | 2026-01-29 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46051 | -46051
105-118 | Bayoniyah (South Khobar) 115/1 | 1923 | Bayoniyah (South Khobar) 115/1-Engineering & Design- Bayoniyah | APPROVED | No | 2023-12-11 | Abas, Mohammed Fekry | 2023-12-12 | 2023-12-12 |  |  |  | 581250 | 4897 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 580000 | APPROVED |  |  | 2024-01-08 | 1250 | 27 | Kumar, Mr. Ranjan | -45272 | 27
105-118 | Bayoniyah (South Khobar) 115/1 | 1969 | Bayoniyah (South Khobar) 115/1-Control, Protection & SAS-bayoniyah | APPROVED | No | 2023-12-14 | Abas, Mohammed Fekry | 2023-12-15 | 2023-12-17 |  |  |  | 8000000 | 4846 | 0 | STANDARD | ALFANAR CO | SAR | 8000000 | APPROVED |  |  | 2024-01-18 | 0 | 32 | Kumar, Mr. Ranjan | -45277 | 32
105-118 | Bayoniyah (South Khobar) 115/1 | 2090 | Bayoniyah (South Khobar) 115/1-13.8KV MV SWITCHGEAR PANEL | APPROVED | No | 2024-01-10 | Abas, Mohammed Fekry | 2024-01-10 | 2024-01-11 |  |  |  | 8210000 | 4863 | 0 | STANDARD | ALFANAR CO | SAR | 8210000 | APPROVED |  |  | 2024-01-21 | 0 | 10 | Alhadi, Khalid | -45302 | 10
105-118 | Bayoniyah (South Khobar) 115/1 | 2090 | Bayoniyah (South Khobar) 115/1-13.8KV MV SWITCHGEAR PANEL | APPROVED | No | 2024-01-10 | Abas, Mohammed Fekry | 2024-01-10 | 2024-01-11 |  |  |  | 8210000 | 4863 | 1 | STANDARD | ALFANAR CO | SAR | 8210000 | REQUIRES REAPPROVAL |  |  |  | 0 | 752 | Alhadi, Khalid | -45302 | -45302
105-118 | Bayoniyah (South Khobar) 115/1 | 2111 | Bayoniyah (South Khobar) 115/1-Temporary Project Sign Board | APPROVED | No | 2024-01-08 | Abas, Mohammed Fekry | 2024-01-09 | 2024-01-09 |  |  |  | 20000 | 4967 | 0 | STANDARD | Construction Expertise Est. | SAR | 20000 | APPROVED |  |  | 2024-01-17 | 0 | 8 | Alhadi, Khalid | -45300 | 8
105-118 | Bayoniyah (South Khobar) 115/1 | 2358 | Bayoniyah (South Khobar) 115/1- UG Scanning | APPROVED | No | 2024-01-29 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 1900 | 5075 | 0 | STANDARD | Construction Expertise Est. | SAR | 1900 | APPROVED |  |  | 2024-02-15 | 0 | 11 | Alhadi, Khalid | -45326 | 11
105-118 | Bayoniyah (South Khobar) 115/1 | 2375 | Bayoniyah (South Khobar) 115/1-Cyber Security | APPROVED | No | 2024-01-30 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 1100000 | 5058 | 0 | STANDARD | ALFANAR CO | SAR | 1100000 | APPROVED |  |  | 2024-02-18 | 0 | 14 | Babic, Marian | -45326 | 14
105-118 | Bayoniyah (South Khobar) 115/1 | 2493 | Bayoniyah (South Khobar) 115/1-Security Cabin | APPROVED | No | 2024-02-07 | Abas, Mohammed Fekry | 2024-02-09 | 2024-02-10 |  |  |  | 9000 | 5311 | 0 | STANDARD | Construction Expertise Est. | SAR | 9000 | APPROVED |  |  | 2024-04-08 | 0 | 58 | Alhadi, Khalid | -45332 | 58
105-118 | Bayoniyah (South Khobar) 115/1 | 2521 | Bayoniyah (South Khobar) 115/1-Geotechnical Investigation | APPROVED | No | 2024-02-11 | Abas, Mohammed Fekry | 2024-02-11 | 2024-02-12 |  |  |  | 16000 | 5706 | 0 | STANDARD | International Agent Commercial Company(S) | SAR | 16000 | APPROVED |  |  | 2024-07-01 | 0 | 140 | Alhadi, Khalid | -45334 | 140
105-118 | Bayoniyah (South Khobar) 115/1 | 2543 | Bayoniyah (South Khobar) 115/1-Super Structure Precast including Fire Walls | APPROVED | No | 2024-02-13 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-19 |  |  |  | 2421479 | 5385 | 0 | STANDARD | Factory of Ideal Precast Concrete System Company | SAR | 2095473 | APPROVED |  |  | 2024-04-24 | 326006 | 65 | Tananeh, Khalid Jamal | -45341 | 65
105-118 | Bayoniyah (South Khobar) 115/1 | 2620 | Bayoniyah (South Khobar) 115/1-Site Office facility | APPROVED | No | 2024-02-19 | Abas, Mohammed Fekry | 2024-02-20 | 2024-02-21 |  |  |  | 319997 | 5121 | 0 | STANDARD | Construction Expertise Est. | SAR | 209900 | APPROVED |  |  | 2024-03-24 | 110097 | 32 | Muhammad, Muhammad Atif | -45343 | 32
105-118 | Bayoniyah (South Khobar) 115/1 | 2656 | Bayoniyah (South Khobar) 115/1-Excavation Works | APPROVED | No | 2024-02-21 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 55000 | 5262 | 0 | STANDARD | Morgan Construction for contracting | SAR | 49500 | APPROVED |  |  | 2024-04-15 | 5500 | 49 | Alhadi, Khalid | -45348 | 49
105-118 | Bayoniyah (South Khobar) 115/1 | 2674 | Bayoniyah (South Khobar) 115/1-Temporary Fence Works including Gates | APPROVED | No | 2024-02-25 | Issa, Amr Ali | 2024-04-02 | 2024-04-02 |  |  |  | 86600 | 5332 | 0 | STANDARD | ABDUL JABBAR AHMAD ALI SHARAHILI CONTRACTING EST. (AJASCO) | SAR | 84500 | APPROVED |  |  | 2024-04-16 | 2100 | 14 | Alhadi, Khalid | -45384 | 14
105-118 | Bayoniyah (South Khobar) 115/1 | 2763 | Bayoniyah (South Khobar) 115/1-General Backfilling | APPROVED | No | 2024-03-04 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 54000 | 5262 | 0 | STANDARD | Morgan Construction for contracting | SAR | 54000 | APPROVED |  |  | 2024-04-15 | 0 | 39 | Alhadi, Khalid | -45358 | 39
105-118 | Bayoniyah (South Khobar) 115/1 | 2764 | Bayoniyah (South Khobar) 115/1-Shoring for 4 months | APPROVED | No | 2024-03-04 | Abas, Mohammed Fekry | 2024-03-05 | 2024-03-07 |  |  |  | 124000 | 5262 | 0 | STANDARD | Morgan Construction for contracting | SAR | 124000 | APPROVED |  |  | 2024-04-15 | 0 | 39 | Alhadi, Khalid | -45358 | 39
105-118 | Bayoniyah (South Khobar) 115/1 | 2764 | Bayoniyah (South Khobar) 115/1-Shoring for 4 months | APPROVED | No | 2024-03-04 | Abas, Mohammed Fekry | 2024-03-05 | 2024-03-07 |  |  |  | 124000 | 5262 | 1 | STANDARD | Morgan Construction for contracting | SAR | 120000 | APPROVED |  |  | 2024-04-23 | 4000 | 47 | Alhadi, Khalid | -45358 | 47
105-118 | Bayoniyah (South Khobar) 115/1 | 2868 | Bayoniyah (South Khobar) 115/1-1000mm thick with Aggregate SUB BASE class-"A(1A)" with CBR not less than 50 | APPROVED | No | 2024-03-20 | Abas, Mohammed Fekry | 2024-03-21 | 2024-03-24 |  |  |  | 31500 | 5262 | 0 | STANDARD | Morgan Construction for contracting | SAR | 31500 | APPROVED |  |  | 2024-04-15 | 0 | 22 | Alhadi, Khalid | -45375 | 22
105-118 | Bayoniyah (South Khobar) 115/1 | 2869 | Bayoniyah (South Khobar) 115/1-600mm thick Aggregate BASE COARSE (crashed stones) class-"A(1A) or A(1B)" with CBR not less than 100 | APPROVED | No | 2024-03-20 | Abas, Mohammed Fekry | 2024-03-21 | 2024-03-24 |  |  |  | 81000 | 5262 | 0 | STANDARD | Morgan Construction for contracting | SAR | 81000 | APPROVED |  |  | 2024-04-15 | 0 | 22 | Alhadi, Khalid | -45375 | 22
105-118 | Bayoniyah (South Khobar) 115/1 | 2925 | Bayoniyah (South Khobar) 115/1-Topography Survey for Project Area | APPROVED | No | 2024-03-28 | Abas, Mohammed Fekry | 2024-03-31 | 2024-03-31 |  |  |  | 5125 | 5717 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 5125 | APPROVED |  |  | 2024-07-01 | 0 | 92 | Alhadi, Khalid | -45382 | 92
105-118 | Bayoniyah (South Khobar) 115/1 | 2941 | Bayoniyah (South Khobar) 115/1-AC/DC Panels with Sub DB's & LP's | APPROVED | No | 2024-03-28 | Abas, Mohammed Fekry | 2024-03-31 | 2024-03-31 |  |  |  | 870000 | 5365 | 0 | STANDARD | ALFANAR CO | SAR | 870000 | APPROVED |  |  | 2024-04-28 | 0 | 28 | Mohammed, Faisal Ansari | -45382 | 28
105-118 | Bayoniyah (South Khobar) 115/1 | 3048 | Bayoniyah (South Khobar) 115/1-5T Over Head Travelling Crane with Accessories | APPROVED | No | 2024-04-16 | Abas, Mohammed Fekry | 2024-04-28 | 2024-04-29 |  |  |  | 130000 | 5485 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 126870 | APPROVED |  |  | 2024-05-16 | 3130 | 17 | Muhammad, Muhammad Atif | -45411 | 17
105-118 | Bayoniyah (South Khobar) 115/1 | 3253 | Bayoniyah (South Khobar) 115/1-Supply & Apply of Roof Waterproofing System & Underground Waterproofing Tanking System | APPROVED | No | 2024-05-02 | Abas, Mohammed Fekry | 2024-05-02 | 2024-05-05 |  |  |  | 392625 | 5652 | 0 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 347826.5 | APPROVED |  |  | 2024-06-13 | 44798.5 | 39 | Tananeh, Khalid Jamal | -45417 | 39
105-118 | Bayoniyah (South Khobar) 115/1 | 3258 | Bayoniyah (South Khobar) 115/1-Supply and Installation of Substation Doors | APPROVED | No | 2024-05-02 | Abas, Mohammed Fekry | 2024-05-02 | 2024-05-05 |  |  |  | 162672 | 6042 | 0 | STANDARD | AL MANASHY COMPANY | SAR | 106036.2 | APPROVED |  |  | 2024-10-21 | 56635.8 | 169 | Tananeh, Khalid Jamal | -45417 | 169
105-118 | Bayoniyah (South Khobar) 115/1 | 3264 | Bayoniyah (South Khobar) 115/1-Supply & Install of Metal Works | APPROVED | No | 2024-05-02 | Abas, Mohammed Fekry | 2024-05-05 | 2024-05-05 |  |  |  | 426160 | 5949 | 0 | STANDARD | Al Sharek Al Daem Est for Contracting | SAR | 388300 | APPROVED |  |  | 2024-10-09 | 37860 | 157 | Tananeh, Khalid Jamal | -45417 | 157
105-118 | Bayoniyah (South Khobar) 115/1 | 3335 | Bayoniyah (South Khobar) 115/1-Site Office Electroic Items | APPROVED | No | 2024-05-07 | Abas, Mohammed Fekry | 2024-05-08 | 2024-05-12 |  |  |  | 33800 | 5608 | 0 | STANDARD | Construction Expertise Est. | SAR | 33800 | APPROVED |  |  | 2024-06-05 | 0 | 24 | Muhammad, Muhammad Atif | -45424 | 24
105-118 | Bayoniyah (South Khobar) 115/1 | 3406 | Bayoniyah (South Khobar) 115/1-150 Sq.mm Tinned Copper Conductor | APPROVED | No | 2024-05-15 | Abas, Mohammed Fekry | 2024-05-16 | 2024-05-17 |  |  |  | 38500 | 5354 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 38455.41 | APPROVED |  |  | 2024-05-26 | 44.59 | 9 | Muhammad, Muhammad Atif | -45429 | 9
105-118 | Bayoniyah (South Khobar) 115/1 | 3470 | Bayoniyah (South Khobar) 115/1-Rental Generator with Diesel Tank | APPROVED | No | 2024-05-22 | Abas, Mohammed Fekry | 2024-05-22 | 2024-05-23 |  |  |  | 24000 | 5617 | 0 | STANDARD | SUDHIR EQUIPMENT RENTAL COMPANY | SAR | 19200 | APPROVED |  |  | 2024-06-03 | 4800 | 11 | Akhtar, Farhan | -45435 | 11
105-118 | Bayoniyah (South Khobar) 115/1 | 3509 | Bayoniyah (South Khobar) 115/1-Battery & Chargers 125V, 2500AH GEL Type -2no/ 2no's | APPROVED | No | 2024-05-28 | Issa, Amr Ali | 2024-05-28 | 2024-05-29 |  |  |  | 550000 | 5739 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 457000 | APPROVED |  |  | 2024-07-10 | 93000 | 42 | Muhammad, Muhammad Atif | -45441 | 42
105-118 | Bayoniyah (South Khobar) 115/1 | 3599 | Bayoniyah (South Khobar) 115/1-Grounding Material and Its accessories | APPROVED | No | 2024-06-05 | Abas, Mohammed Fekry | 2024-06-08 | 2024-06-09 |  |  |  | 72850 | 5557 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 72850 | APPROVED |  |  | 2024-07-12 | 0 | 33 | Muhammad, Muhammad Atif | -45452 | 33
105-118 | Bayoniyah (South Khobar) 115/1 | 3744 | Bayoniyah (South Khobar) 115/1-MV Cable ( 1C x 630 mm2 and 1x3Cx300mm2) | APPROVED | No | 2024-07-02 | Abas, Mohammed Fekry | 2024-07-05 | 2024-07-07 |  |  |  | 1260970 | 6023 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 1127267.9 | APPROVED |  |  | 2024-10-09 | 133702.1 | 94 | Badhman, Saeed | -45480 | 94
105-118 | Bayoniyah (South Khobar) 115/1 | 3787 | Bayoniyah (South Khobar) 115/1-Garbage Waste Container, 12 Cu. M (1-year) | APPROVED | No | 2024-07-07 | Abas, Mohammed Fekry | 2024-07-09 | 2024-07-09 |  |  |  | 28800 | 5886 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 19200 | APPROVED |  |  | 2024-08-20 | 9600 | 42 | Akhtar, Farhan | -45482 | 42
105-118 | Bayoniyah (South Khobar) 115/1 | 3845 | Bayoniyah (South Khobar) 115/1-Control Cables | APPROVED | No | 2024-07-11 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 716000 | 5825 | 0 | STANDARD | ALFANAR CO | SAR | 531752.8 | APPROVED |  |  | 2024-08-27 | 184247.2 | 42 | Muhammad, Muhammad Atif | -45489 | 42
105-118 | Bayoniyah (South Khobar) 115/1 | 3934 | Bayoniyah (South Khobar) 115/1-MV Termination Kit | APPROVED | No | 2024-07-16 | Issa, Amr Ali | 2024-07-21 | 2024-07-21 |  |  |  | 98837 | 5985 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 95871.89 | APPROVED |  |  | 2024-09-19 | 2965.11 | 60 | Badhman, Saeed | -45494 | 60
105-118 | Bayoniyah (South Khobar) 115/1 | 3971 | Bayoniyah (South Khobar) 115/1-Testing and Commissioning | APPROVED | No | 2024-07-21 | Abas, Mohammed Fekry | 2024-07-22 | 2024-07-23 |  |  |  | 1855063 | 6446 | 0 | STANDARD | Al Fanar Technical Services | SAR | 1855063 | APPROVED | 2025-12-24 | 2025-12-29 | 2026-01-04 | 0 | 530 | Babic, Marian | 524 | 530
105-118 | Bayoniyah (South Khobar) 115/1 | 3976 | Bayoniyah (South Khobar) 115/1-RTV Coating | APPROVED | No | 2024-07-21 | Abas, Mohammed Fekry | 2024-07-29 | 2024-07-29 |  |  |  | 250000 | 6189 | 0 | STANDARD | SAUDI CONDUIT COATING CO. (S3C) | SAR | 35268 | APPROVED |  |  | 2024-10-13 | 214732 | 76 | Muaz, Alaa | -45502 | 76
105-118 | Bayoniyah (South Khobar) 115/1 | 4034 | Bayoniyah (South Khobar) 115/1-Lightning Mats | APPROVED | No | 2024-07-28 | Abas, Mohammed Fekry | 2024-07-30 | 2024-07-30 |  |  |  | 59075 | 5963 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 59075 | APPROVED |  |  | 2024-10-06 | 0 | 68 | Badhman, Saeed | -45503 | 68
105-118 | Bayoniyah (South Khobar) 115/1 | 4038 | Bayoniyah (South Khobar) 115/1-Eight number of 5G Routers for Sites | APPROVED | No | 2024-07-28 | Abas, Mohammed Fekry | 2024-08-01 | 2024-08-01 |  |  |  | 6900 | 5926 | 0 | STANDARD | Mohmmed Abdulrahman AlZahid IT CO. | SAR | 4800 | APPROVED |  |  | 2024-08-20 | 2100 | 19 | Akhtar, Farhan | -45505 | 19
105-118 | Bayoniyah (South Khobar) 115/1 | 4057 | Bayoniyah (South Khobar) 115/1-Cable Tray and its accessories | APPROVED | No | 2024-07-30 | Abas, Mohammed Fekry | 2024-08-01 | 2024-08-01 |  |  |  | 505784.96 | 5918 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 505784.96 | APPROVED |  |  | 2024-09-26 | 0 | 56 | Muhammad, Muhammad Atif | -45505 | 56
105-118 | Bayoniyah (South Khobar) 115/1 | 4175 | Bayoniyah (South Khobar) 115/1-LV AC /DC Cables and Lighting Wires | APPROVED | No | 2024-08-17 | Abas, Mohammed Fekry | 2024-08-21 | 2024-08-21 |  |  |  | 1611070 | 6080 | 0 | STANDARD | ALFANAR CO | SAR | 1110509.38 | APPROVED |  |  | 2024-09-26 | 500560.62 | 36 | Badhman, Saeed | -45525 | 36
105-118 | Bayoniyah (South Khobar) 115/1 | 4189 | Bayoniyah (South Khobar) 115/1-Hazardous Waste Collection | APPROVED | No | 2024-08-18 | Abas, Mohammed Fekry | 2024-08-21 | 2024-08-21 |  |  |  | 5000 | 6120 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 3650 | APPROVED |  |  | 2024-09-19 | 1350 | 29 | Akhtar, Farhan | -45525 | 29
105-118 | Bayoniyah (South Khobar) 115/1 | 4240 | Bayoniyah (South Khobar) 115/1-Grounding Conductor and Cables | APPROVED | No | 2024-08-21 | Abas, Mohammed Fekry | 2024-08-28 | 2024-09-01 |  |  |  | 244150 | 6064 | 0 | STANDARD | ALFANAR CO | SAR | 226756.52 | APPROVED |  |  | 2024-09-24 | 17393.48 | 23 | Muhammad, Muhammad Atif | -45536 | 23
105-118 | Bayoniyah (South Khobar) 115/1 | 4258 | Bayoniyah (South Khobar) 115/1-Electrical Soil Resistivity Measurement (Third Party Measurement) | APPROVED | No | 2024-08-24 | Abas, Mohammed Fekry | 2024-08-27 | 2024-09-01 |  |  |  | 7360 | 6141 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 6400 | APPROVED |  |  | 2024-10-13 | 960 | 42 | Tananeh, Khalid Jamal | -45536 | 42
105-118 | Bayoniyah (South Khobar) 115/1 | 4383 | Bayoniyah (South Khobar) 115/1-Civil Subcontractor | APPROVED | No | 2024-09-06 | Abas, Mohammed Fekry | 2024-09-16 | 2024-09-17 |  |  |  | 8250000 | 5644 | 0 | STANDARD | Liwa Al sharq Contracting Company | SAR | 8250000 | APPROVED |  |  | 2024-11-03 | 0 | 47 | Tananeh, Khalid Jamal | -45552 | 47
105-118 | Bayoniyah (South Khobar) 115/1 | 4383 | Bayoniyah (South Khobar) 115/1-Civil Subcontractor | APPROVED | No | 2024-09-06 | Abas, Mohammed Fekry | 2024-09-16 | 2024-09-17 |  |  |  | 8250000 | 5644 | 1 | STANDARD | Liwa Al sharq Contracting Company | SAR | 4987743.76 | APPROVED |  |  | 2025-12-23 | 3262256.24 | 462 | Tananeh, Khalid Jamal | -45552 | 462
105-118 | Bayoniyah (South Khobar) 115/1 | 4388 | Bayoniyah (South Khobar) 115/1-Firefighting System | APPROVED | No | 2024-09-06 | Abas, Mohammed Fekry | 2024-09-17 | 2024-09-17 |  |  |  | 2169000 | 6005 | 0 | STANDARD | Equipment & Technical Services Co.(ETECHS) | SAR | 2169000 | APPROVED |  |  | 2024-09-26 | 0 | 9 | Muhammad, Muhammad Atif | -45552 | 9
105-118 | Bayoniyah (South Khobar) 115/1 | 4575 | Bayoniyah (South Khobar) 115/1-Station Service Transformer | APPROVED | No | 2024-10-02 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-09 |  |  |  | 164000 | 5908 | 0 | STANDARD | ALFANAR CO | SAR | 164000 | APPROVED |  |  | 2024-10-19 | 0 | 10 | Muhammad, Muhammad Atif | -45574 | 10
105-118 | Bayoniyah (South Khobar) 115/1 | 4602 | Bayoniyah (South Khobar) 115/1-Electrical Installation - Contractor | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-09 |  |  |  | 2992521 | 6736 | 0 | STANDARD | Broadway Contracting Company | SAR | 2359500 | APPROVED |  |  | 2025-02-05 | 633021 | 119 | Abdulqader, Ahmed Abdulhalim | -45574 | 119
105-118 | Bayoniyah (South Khobar) 115/1 | 4669 | Bayoniyah (South Khobar) 115/1-HVAC System and Works | APPROVED | No | 2024-10-14 | Abas, Mohammed Fekry | 2024-10-16 | 2024-10-16 |  |  |  | 2050000 | 6202 | 0 | STANDARD | Magna Contracting Co | SAR | 2050000 | APPROVED |  |  | 2024-10-31 | 0 | 15 | Muhammad, Muhammad Atif | -45581 | 15
105-118 | Bayoniyah (South Khobar) 115/1 | 4709 | Bayoniyah (South Khobar) 115/1-Supply of Raw Water | APPROVED | No | 2024-10-17 | Abas, Mohammed Fekry | 2024-10-20 | 2024-10-21 |  |  |  | 5000 | 6377 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 7200 | APPROVED |  |  | 2024-11-12 | -2200 | 22 | Akhtar, Farhan | -45586 | 22
105-118 | Bayoniyah (South Khobar) 115/1 | 4710 | Bayoniyah (South Khobar) 115/1-Site Waster Removal Services | APPROVED | No | 2024-10-17 | Abas, Mohammed Fekry | 2024-10-20 | 2024-10-21 |  |  |  | 5000 | 6377 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 7200 | APPROVED |  |  | 2024-11-12 | -2200 | 22 | Akhtar, Farhan | -45586 | 22
105-118 | Bayoniyah (South Khobar) 115/1 | 4721 | Bayoniyah (South Khobar) 115/1-Telecommunication System and works | APPROVED | No | 2024-10-17 | Abas, Mohammed Fekry | 2024-12-05 | 2024-12-08 |  |  |  | 2245007.21 | 6241 | 0 | STANDARD | ALFANAR CO | SAR | 2245007.21 | APPROVED |  |  | 2025-03-18 | 0 | 100 | Kumar, Mr. Ranjan | -45634 | 100
105-118 | Bayoniyah (South Khobar) 115/1 | 4984 | Bayoniyah (South Khobar) 115/1-Indoor and Outdoor Lighting Fixtures | APPROVED | No | 2024-11-18 | Abas, Mohammed Fekry | 2024-11-28 | 2024-11-28 |  |  |  | 88037 | 6471 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 88037 | APPROVED |  |  | 2024-12-15 | 0 | 17 | Muhammad, Muhammad Atif | -45624 | 17
105-118 | Bayoniyah (South Khobar) 115/1 | 5089 | Bayoniyah (South Khobar) 115/1-HCIS Consultant | RETURNED | No | 2024-11-30 | Abdulqader, Ahmed Abdulhalim | 2025-03-02 | 2025-02-25 | 2025-03-02 |  | Insufficient Budget | 33500 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45713 | -45713
105-118 | Bayoniyah (South Khobar) 115/1 | 5163 | Bayoniyah (South Khobar) 115/1-Aluminum Conductor Clamps and Connector | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-12 |  |  |  | 4537 | 6415 | 0 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 4505.16 | APPROVED |  |  | 2025-01-02 | 31.84 | 21 | Mohammed, Faisal Ansari | -45638 | 21
105-118 | Bayoniyah (South Khobar) 115/1 | 5348 | Bayoniyah (South Khobar) 115/1-Conduit and fittings | APPROVED | No | 2025-01-04 | Abas, Mohammed Fekry | 2025-01-07 | 2025-01-07 |  |  |  | 337272.4 | 6711 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 337271.55 | APPROVED |  |  | 2025-01-28 | 0.85 | 21 | Muaz, Alaa | -45664 | 21
105-118 | Bayoniyah (South Khobar) 115/1 | 5407 | Bayoniyah (South Khobar) 115/1-Extra Tinned Copper Conductor 150mm2 | APPROVED | No | 2025-01-13 | Abas, Mohammed Fekry | 2025-01-14 | 2025-01-16 |  |  |  | 131100 | 6810 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 121307.52 | APPROVED |  |  | 2025-03-03 | 9792.48 | 46 | Alhadi, Khalid | -45673 | 46
105-118 | Bayoniyah (South Khobar) 115/1 | 5465 | Bayoniyah (South Khobar) 115/1-CTPU and CTPU Box Including Accessories | APPROVED | No | 2025-01-19 | Abas, Mohammed Fekry | 2025-01-20 | 2025-01-23 |  |  |  | 68000 | 6286 | 0 | STANDARD | Energy Tracks For Contracting | SAR | 68000 | APPROVED |  |  | 2025-03-09 | 0 | 45 | Kumar, Mr. Ranjan | -45680 | 45
105-118 | Bayoniyah (South Khobar) 115/1 | 5563 | Bayoniyah (South Khobar) 115/1-TFR-DSM-SOE-SAS, Protection Panel Testing for Remote End | APPROVED | No | 2025-01-23 | Abas, Mohammed Fekry | 2025-02-19 | 2025-02-19 |  |  |  | 200000 | 7457 | 0 | STANDARD | TRINERGY TECHNOLOGIES SA | SAR | 30615 | APPROVED |  |  | 2025-07-06 | 169385 | 137 | Babic, Marian | -45707 | 137
105-118 | Bayoniyah (South Khobar) 115/1 | 5567 | Bayoniyah (South Khobar) 115/1-Fiber Optic Cables & Accessories,Installation and Testing Services | APPROVED | No | 2025-01-23 | Abas, Mohammed Fekry | 2025-01-28 | 2025-01-30 |  |  |  | 250000 | 7029 | 0 | STANDARD | RASHID SAEED AHMED AL GHAMDI COMM INFO TRAD EST | SAR | 210000 | APPROVED |  |  | 2025-04-17 | 40000 | 77 | Abdulqader, Ahmed Abdulhalim | -45687 | 77
105-118 | Bayoniyah (South Khobar) 115/1 | 5570 | Bayoniyah (South Khobar) 115/1-Office furniture | REJECTED | No | 2025-01-23 | Sherif, Marwa | 2025-03-09 | 2025-01-26 |  | 2025-03-09 |  | 50000 | [5 empty] | 0 |  |  |  |  | 0 |  | Muhammad, Muhammad Atif | -45683 | -45683
105-118 | Bayoniyah (South Khobar) 115/1 | 5673 | Bayoniyah (South Khobar) 115/1-Motion Sensor for lighting | REJECTED | No | 2025-01-27 | Sherif, Marwa | 2025-03-09 | 2025-02-01 |  | 2025-03-09 |  | 100000 | [5 empty] | 0 |  |  |  |  | 0 |  | Muhammad, Muhammad Atif | -45689 | -45689
105-118 | Bayoniyah (South Khobar) 115/1 | 5695 | Bayoniyah (South Khobar) 115/1-MV Clamps and Cleats | APPROVED | No | 2025-01-27 | Abas, Mohammed Fekry | 2025-02-03 | 2025-02-05 |  |  |  | 100000 | 7003 | 0 | STANDARD | ABDULLAH M. AL-SHAHRANI FACTORY | SAR | 97327.5 | APPROVED |  |  | 2025-05-28 | 2672.5 | 112 | Hegazy, Ayman | -45693 | 112
105-118 | Bayoniyah (South Khobar) 115/1 | 5695 | Bayoniyah (South Khobar) 115/1-MV Clamps and Cleats | APPROVED | No | 2025-01-27 | Abas, Mohammed Fekry | 2025-02-03 | 2025-02-05 |  |  |  | 100000 | 7003 | 1 | STANDARD | ABDULLAH M. AL-SHAHRANI FACTORY | SAR | 97327.5 | REQUIRES REAPPROVAL |  |  |  | 2672.5 | 361 | Hegazy, Ayman | -45693 | -45693
105-118 | Bayoniyah (South Khobar) 115/1 | 6092 | Bayoniyah (South Khobar) 115/1-Printing of Drawings A2 Size | APPROVED | No | 2025-03-01 | Abas, Mohammed Fekry | 2025-03-03 | 2025-03-05 |  |  | Line 2.33 Printing of Drawings in A2 Size | 31000 | 7058 | 0 | STANDARD | Print Magaies Al abdaa Printing | SAR | 30999 | APPROVED |  |  | 2025-04-07 | 1 | 33 | Abuhammad, Samir | -45721 | 33
105-118 | Bayoniyah (South Khobar) 115/1 | 6123 | Bayoniyah (South Khobar) 115/1-Office Furniture | RETURNED | No | 2025-03-05 | Akhtar, Farhan | 2025-04-09 | 2025-03-10 | 2025-04-09 |  | Resubmit the PR once the BOQ is ready | 50000 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45726 | -45726
105-118 | Bayoniyah (South Khobar) 115/1 | 6135 | Bayoniyah (South Khobar) 115/1-steel parapet works | APPROVED | No | 2025-03-08 | Abas, Mohammed Fekry | 2025-03-10 | 2025-03-12 |  |  | steel parapet works | 39060 | 6818 | 0 | STANDARD | RAFCO Factory Company For Metal Industries | SAR | 39060 | APPROVED |  |  | 2025-08-03 | 0 | 144 | Hegazy, Ayman | -45728 | 144
105-118 | Bayoniyah (South Khobar) 115/1 | 6161 | Bayoniyah (South Khobar) 115/1-Old fence removal, New fence installation and relocation of Gates done by CEC | APPROVED | No | 2025-03-11 | Abas, Mohammed Fekry | 2025-03-13 | 2025-03-17 |  |  | Old fence removal, New fence installation and relocation of Gates done by CEC | 65300 | 7109 | 0 | STANDARD | Construction Expertise Est. | SAR | 48040 | APPROVED |  |  | 2025-08-11 | 17260 | 147 | Abdulqader, Ahmed Abdulhalim | -45733 | 147
105-118 | Bayoniyah (South Khobar) 115/1 | 6337 | Bayoniyah (South Khobar) 115/1-5 Ton Stand Alon AC for CSD TEsting ( 8 Numbers) | APPROVED | No | 2025-04-14 | Abas, Mohammed Fekry | 2025-04-16 | 2025-04-17 |  |  | 5 Ton Stand Alone AC for CSD TEsting ( 8 Numbers) | 71168 | 7161 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 61600 | APPROVED |  |  | 2025-04-24 | 9568 | 7 | Abuhammad, Samir | -45764 | 7
105-118 | Bayoniyah (South Khobar) 115/1 | 6370 | Bayoniyah (South Khobar) 115/1-Design, Supply, Installation, Testing and Commissioning of Security System | APPROVED | No | 2025-04-17 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-20 |  |  | Design, Supply, Installation, Testing and Commissing of Security System (Line item 2.7) | 870484.96 | 6637 | 0 | STANDARD | CEGELEC NETWORK AND SECURITY SYSTEMS | SAR | 870484.96 | APPROVED |  |  | 2025-04-24 | 0 | 4 | Abdulqader, Ahmed Abdulhalim | -45767 | 4
105-118 | Bayoniyah (South Khobar) 115/1 | 6384 | Bayoniyah (South Khobar) 115/1-Line item 2.13 control Cables for SAS | APPROVED | No | 2025-04-19 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-20 |  |  | Line item 2.13 control Cables for SAS | 52600 | 6782 | 0 | STANDARD | ALFANAR CO | SAR | 52600 | APPROVED |  |  | 2025-04-29 | 0 | 9 | Muaz, Alaa | -45767 | 9
105-118 | Bayoniyah (South Khobar) 115/1 | 6453 | Bayoniyah (South Khobar) 115/1-Supply of Raw Water | APPROVED | No | 2025-04-26 | Abas, Mohammed Fekry | 2025-04-28 | 2025-04-28 |  |  | Supply of Raw Water | 6000 | 6377 | 1 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 6000 | APPROVED |  |  | 2025-05-05 | 0 | 7 | Akhtar, Farhan | -45775 | 7
105-118 | Bayoniyah (South Khobar) 115/1 | 6519 | Bayoniyah (South Khobar) 115/1-Intrumentation Cable (4P X 1.5mm2) | APPROVED | No | 2025-05-05 | Abas, Mohammed Fekry | 2025-05-08 | 2025-05-08 |  |  | Instrumentation Cable (4P X 1.5mm2) | 9000 | 7315 | 0 | STANDARD | Middle East Specialized Cables Mesc | SAR | 7500 | APPROVED |  |  | 2025-05-27 | 1500 | 19 | Abuhammad, Samir | -45785 | 19
105-118 | Bayoniyah (South Khobar) 115/1 | 6599 | Bayoniyah (South Khobar) 115/1-Third Party Lab Tesitng | APPROVED | No | 2025-05-13 | Abas, Mohammed Fekry | 2025-05-15 | 2025-05-15 |  |  | Third Party Lab Testing of Pre-Cast Material | 85000 | 7359 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 84190 | APPROVED |  |  | 2025-06-15 | 810 | 31 | Tananeh, Khalid Jamal | -45792 | 31
105-118 | Bayoniyah (South Khobar) 115/1 | 6654 | Bayoniyah (South Khobar) 115/1-Transformer Oil DGA Analysis (Lab Testing) as per SEC-CSD requirment | APPROVED | No | 2025-05-19 | Abas, Mohammed Fekry | 2025-05-25 | 2025-05-26 |  |  | Transformer Oil DGA Analysis (Lab Testing) as per SEC-CSD requirment | 35000 | 7476 | 0 | STANDARD | Saudi Arabian Engineering Company | SAR | 35000 | APPROVED |  |  | 2025-07-21 | 0 | 56 | Abdulqader, Ahmed Abdulhalim | -45803 | 56
105-118 | Bayoniyah (South Khobar) 115/1 | 6758 | Bayoniyah (South Khobar) 115/1-Civil Works Inventory | RETURNED | No | 2025-06-01 | Tananeh, Khalid Jamal | 2025-09-03 | 2025-06-26 | 2025-09-03 |  | returned as requested by the PM | 28000 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45834 | -45834
105-118 | Bayoniyah (South Khobar) 115/1 | 6916 | Bayoniyah (South Khobar) 115/1-Wiring Devices | REJECTED | No | 2025-06-28 | Sherif, Marwa | 2025-07-14 | 2025-06-28 |  | 2025-07-15 |  | 96720 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45836 | -45836
105-118 | Bayoniyah (South Khobar) 115/1 | 6942 | Bayoniyah (South Khobar) 115/1-Fire Stopping Material | RETURNED | No | 2025-07-01 | Tananeh, Khalid Jamal | 2025-09-03 | 2025-07-07 | 2025-09-03 |  | returned as requested by the PM | 100000 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45845 | -45845
105-118 | Bayoniyah (South Khobar) 115/1 | 6947 | Bayoniyah (South Khobar) 115/1-Site Office Shifting | RETURNED | No | 2025-07-01 | Abdulqader, Ahmed Abdulhalim | 2025-08-10 | 2025-07-20 | 2025-08-10 |  | Material not required anymore | 50000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45858 | -45858
105-118 | Bayoniyah (South Khobar) 115/1 | 6949 | Bayoniyah (South Khobar) 115/1-Water Proofing Change Order | RETURNED | No | 2025-07-01 | Tananeh, Khalid Jamal | 2025-09-08 | 2025-08-25 | 2025-09-08 |  | This is a duplicate under PR 7284, and there is no approved POCR for it | 38000 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45894 | -45894
105-118 | Bayoniyah (South Khobar) 115/1 | 6955 | Bayoniyah (South Khobar) 115/1-Rental Generator (250KVA) for Transformer Dehydration | APPROVED | No | 2025-07-01 | Abas, Mohammed Fekry | 2025-07-06 | 2025-07-07 |  |  |  | 7000 | 7485 | 0 | STANDARD | Rawafd AlQwt Litaqt Est. | SAR | 7000 | APPROVED |  |  | 2025-07-18 | 0 | 11 | Akhtar, Farhan | -45845 | 11
105-118 | Bayoniyah (South Khobar) 115/1 | 6970 | Bayoniyah (South Khobar) 115/1-Manpower for Testing and Commissioning | APPROVED | No | 2025-07-02 | Abas, Mohammed Fekry | 2025-07-06 | 2025-07-07 |  |  | Line Item 2.31 Technicians for Testing and Commissioning | 120000 | 7506 | 0 | STANDARD | Jasem M.AlJasem Contracting Est. | SAR | 120000 | APPROVED |  |  | 2025-08-02 | 0 | 26 | Babic, Marian | -45845 | 26
105-118 | Bayoniyah (South Khobar) 115/1 | 7000 | Bayoniyah (South Khobar) 115/1-Transformer Oil Testing (As per CSD Requirement) | APPROVED | No | 2025-07-07 | Abas, Mohammed Fekry | 2025-07-12 | 2025-07-12 |  |  | Initally we created 6654 with the value of 35000/-. Now our PO requirement is increase. Therefore I have created new PR. | 2300 | 7476 | 0 | STANDARD | Saudi Arabian Engineering Company | SAR | 2300 | APPROVED |  |  | 2025-07-21 | 0 | 9 | Abdulqader, Ahmed Abdulhalim | -45850 | 9
105-118 | Bayoniyah (South Khobar) 115/1 | 7053 | Bayoniyah (South Khobar) 115/1-MV Cable Clamps | APPROVED | No | 2025-07-09 | Abas, Mohammed Fekry | 2025-07-13 | 2025-07-14 |  |  | Line item 2.13 MV Clamps | 56525 | 7538 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 56525 | APPROVED |  |  | 2025-08-05 | 0 | 22 | Hegazy, Ayman | -45852 | 22
105-118 | Bayoniyah (South Khobar) 115/1 | 7102 | Bayoniyah (South Khobar) 115/1-PDS System | REJECTED | No | 2025-07-15 | Sherif, Marwa | 2025-07-15 | 2025-07-15 |  | 2025-07-21 |  | 250000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45853 | -45853
105-118 | Bayoniyah (South Khobar) 115/1 | 7131 | Bayoniyah (South Khobar) 115/1-Wiring Devices | APPROVED | No | 2025-07-17 | Abas, Mohammed Fekry | 2025-07-22 | 2025-07-22 |  |  | Bayouniah SS Wiring Devices | 96720 | 7167 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 96720 | APPROVED |  |  | 2025-08-04 | 0 | 13 | Muaz, Alaa | -45860 | 13
105-118 | Bayoniyah (South Khobar) 115/1 | 7169 | Bayoniyah (South Khobar) 115/1-Diesel for Bayouniah Rental Generator | APPROVED | No | 2025-07-21 | Abas, Mohammed Fekry | 2025-07-26 | 2025-07-27 |  |  | PR for Bayouniah Rental Generator Diesel | 10000 | 7550 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 9999.39 | APPROVED |  |  | 2025-08-03 | 0.61 | 7 | Akhtar, Farhan | -45865 | 7
105-118 | Bayoniyah (South Khobar) 115/1 | 7181 | Bayoniyah (South Khobar) 115/1-Design,Supply, Installation, T&C of lighting Control System | RETURNED | No | 2025-07-21 | Muaz, Alaa | 2025-09-09 | 2025-07-27 | 2025-09-09 |  | The budget is not sufficient | 60271 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -45865 | -45865
105-118 | Bayoniyah (South Khobar) 115/1 | 7223 | Bayoniyah (South Khobar) 115/1-DC DB for Telecom | REJECTED | No | 2025-07-27 | Sherif, Marwa | 2025-08-06 | 2025-07-27 |  | 2025-08-09 |  | 50000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45865 | -45865
105-118 | Bayoniyah (South Khobar) 115/1 | 7229 | Bayoniyah (South Khobar) 115/1-1x500mm2 Extra LV Cables | RETURNED | No | 2025-07-28 | Mohammed, Mohammed Adel Fahmy | 2026-01-15 | 2025-08-03 | 2026-01-15 |  | Not Have POCR Until Now and PR incorrect qty. | 119700 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Mohammed Adel Fahmy | -45872 | -45872
105-118 | Bayoniyah (South Khobar) 115/1 | 7253 | Bayoniyah (South Khobar) 115/1-Extra THNN Wires | APPROVED | No | 2025-08-01 | Abas, Mohammed Fekry | 2025-08-03 | 2025-08-03 |  |  | Extra THNN Wires for Lighting Circuits | 59280 | 7853 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 65022.64 | IN PROCESS | 2026-01-19 | 2026-01-28 |  | -5742.64 | 182 | Mohammed, Mohammed Adel Fahmy | 178 | -45872
105-118 | Bayoniyah (South Khobar) 115/1 | 7253 | Bayoniyah (South Khobar) 115/1-Extra THNN Wires | APPROVED | No | 2025-08-01 | Abas, Mohammed Fekry | 2025-08-03 | 2025-08-03 |  |  | Extra THNN Wires for Lighting Circuits | 59280 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -45872 | -45872
105-118 | Bayoniyah (South Khobar) 115/1 | 7284 | Bayoniyah (South Khobar) 115/1-WaterProofing | APPROVED | No | 2025-08-04 | Abas, Mohammed Fekry | 2025-08-10 | 2025-08-10 |  |  | Line item 2.20 Water Proofing | 27305 | 5652 | 1 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 27302.47 | APPROVED |  |  | 2025-09-17 | 2.53 | 38 | Tananeh, Khalid Jamal | -45879 | 38
105-118 | Bayoniyah (South Khobar) 115/1 | 7308 | Bayoniyah (South Khobar) 115/1-6 No. of 5 Ton AC (4 Fixed and 2 Mobile) | RETURNED | No | 2025-08-06 |  |  | 2025-08-11 | 2026-01-11 |  | Not required the AC's | 58000 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45880 | -45880
105-118 | Bayoniyah (South Khobar) 115/1 | 7358 | Bayoniyah (South Khobar) 115/1-Supply of Raw Water | APPROVED | No | 2025-08-14 | Abas, Mohammed Fekry | 2025-08-17 | 2025-08-18 |  |  | Line item 2.33 Supply of Raw Water | 10500 | 6377 | 2 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 10500 | APPROVED |  |  | 2025-08-25 | 0 | 7 | Akhtar, Farhan | -45887 | 7
105-118 | Bayoniyah (South Khobar) 115/1 | 7421 | Hazardous Waste Collection | REJECTED | No | 2025-08-21 | Sherif, Marwa | 2025-08-25 | 2025-08-21 |  | 2025-08-27 |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45890 | -45890
105-118 | Bayoniyah (South Khobar) 115/1 | 7424 | Extra Grounding Accessories | APPROVED | No | 2025-08-22 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | Line item 2.21 Extra grounding accessories. PO already finalized (7092-HV1497-0) | 0 | 7092 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 69784.7 | APPROVED |  |  | 2025-09-16 | -69784.7 | 22 | Abdulqader, Ahmed Abdulhalim | -45894 | 22
105-118 | Bayoniyah (South Khobar) 115/1 | 7433 | PDS System | RETURNED | No | 2025-08-23 | Hegazy, Ayman | 2025-11-18 | 2025-08-25 | 2025-11-18 |  | No Available budjet | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -45894 | -45894
105-118 | Bayoniyah (South Khobar) 115/1 | 7543 | Lugs and Glands | APPROVED | No | 2025-08-27 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-03 |  |  | line item 2.13 Lugs and Glands | 0 | 7576 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 21560.54 | APPROVED |  |  | 2025-09-09 | -21560.54 | 6 | Abdulqader, Ahmed Abdulhalim | -45903 | 6
105-118 | Bayoniyah (South Khobar) 115/1 | 7583 | Bayouniah Switchgear Panel Repairing | APPROVED | No | 2025-08-31 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-03 |  |  | Bayouniah Damaged Switchgear Panel Repairing. | 0 | 4863 | 1 | STANDARD | ALFANAR CO | SAR | 0 | REQUIRES REAPPROVAL |  |  |  | 0 | 151 | Alhadi, Khalid | -45903 | -45903
105-118 | Bayoniyah (South Khobar) 115/1 | 7583 | Bayouniah Switchgear Panel Repairing | APPROVED | No | 2025-08-31 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-03 |  |  | Bayouniah Damaged Switchgear Panel Repairing. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45903 | -45903
105-118 | Bayoniyah (South Khobar) 115/1 | 7635 | DC DB for Telecom | APPROVED | No | 2025-09-03 | Abas, Mohammed Fekry | 2025-09-07 | 2025-09-08 |  |  | DCDB for Telecom | 0 | 7683 | 0 | STANDARD | HAWA ELECTRIC PANEL BOARD FAC | SAR | 29700 | APPROVED |  |  | 2025-09-17 | -29700 | 9 | Abuhammad, Samir | -45908 | 9
105-118 | Bayoniyah (South Khobar) 115/1 | 7747 | HV & MV Cable Supports | APPROVED | No | 2025-09-15 | Abas, Mohammed Fekry | 2025-09-16 | 2025-09-21 |  |  | PR for the MV and HV Cable Supports. PO already issue. PO number is 7296-HV1497-0 | 0 | 7296 | 0 | STANDARD | Power Solution Industries | SAR | 118662.35 | APPROVED |  |  | 2025-11-04 | -118662.35 | 44 | Hegazy, Ayman | -45921 | 44
105-118 | Bayoniyah (South Khobar) 115/1 | 7799 | Office furniture | APPROVED | No | 2025-09-20 | Abas, Mohammed Fekry | 2025-09-21 | 2025-09-21 |  |  | Line item 2.33 Office Furniture | 0 | 7710 | 0 | STANDARD | ALISMAIL INDUSTRIAL CO.(S) | SAR | 17590 | APPROVED |  |  | 2025-10-09 | -17590 | 18 | Abdulqader, Ahmed Abdulhalim | -45921 | 18
105-118 | Bayoniyah (South Khobar) 115/1 | 7877 | HV & MV Cable Supports | APPROVED | No | 2025-10-01 | Abas, Mohammed Fekry | 2025-10-05 | 2025-10-06 |  |  | PR for the HV&MV Cable Supports. PO # 7296-HV1497 already done | 0 | 7296 | 0 | STANDARD | Power Solution Industries | SAR | 377.25 | APPROVED |  |  | 2025-11-04 | -377.25 | 29 | Hegazy, Ayman | -45936 | 29
105-118 | Bayoniyah (South Khobar) 115/1 | 8188 | Disposal of Waste Container (12CU.M3) | APPROVED | No | 2025-11-12 | Abas, Mohammed Fekry | 2025-11-16 | 2025-11-17 |  |  | Line item 2.33 Disposal of Waste Container | 0 | 5886 | 1 | STANDARD | Cebent for General Cont. Est. | SAR | 11200 | APPROVED |  |  | 2025-11-30 | -11200 | 13 | Akhtar, Farhan | -45978 | 13
105-118 | Bayoniyah (South Khobar) 115/1 | 8259 | Motors for the Main Gate | APPROVED | No | 2025-11-18 | Abas, Mohammed Fekry | 2025-11-20 | 2025-11-23 |  |  | Line Item 2.20 Motors for Main Gate | 0 | 7979 | 0 | STANDARD | ALMOSALLAMY INDUSTRIAL COMPANY | SAR | 9330 | APPROVED |  |  | 2025-12-23 | -9330 | 30 | Abdelraouf, Islam ِAdel Hanafy | -45984 | 30
105-118 | Bayoniyah (South Khobar) 115/1 | 8313 | Civil and Arch. Works for Power Rings | APPROVED | No | 2025-11-21 | Abas, Mohammed Fekry | 2025-11-25 | 2025-11-29 |  |  | Line item 2.20 Civil and Arch. Works for Power Rings | 0 | 7989 | 0 | STANDARD | POWER RING Construction Company | SAR | 2147404.81 | APPROVED |  |  | 2025-12-17 | -2147404.81 | 18 | Tananeh, Khalid Jamal | -45990 | 18
105-118 | Bayoniyah (South Khobar) 115/1 | 8314 | Concrete Ready Mix | APPROVED | No | 2025-11-21 | Abas, Mohammed Fekry | 2025-11-27 | 2025-11-29 |  |  | Line item 2.20 Concrete Ready Mix | 0 | 7990 | 0 | STANDARD | Al Houssain & Al Afaliq Co. HACO | SAR | 536650 | APPROVED |  |  | 2025-12-14 | -536650 | 15 | Tananeh, Khalid Jamal | -45990 | 15
105-118 | Bayoniyah (South Khobar) 115/1 | 8315 | Fire Stop Material | APPROVED | No | 2025-11-21 | Abas, Mohammed Fekry | 2025-11-26 | 2025-11-29 |  |  | Line item 2.20 Fire Stop Material | 0 | 7985 | 0 | STANDARD | Construction Expertise Est. | SAR | 150000 | APPROVED |  |  | 2025-12-14 | -150000 | 15 | Tananeh, Khalid Jamal | -45990 | 15
105-118 | Bayoniyah (South Khobar) 115/1 | 8316 | Raised Floor | APPROVED | No | 2025-11-21 | Abas, Mohammed Fekry | 2025-11-26 | 2025-11-29 |  |  | Line Item 2.20 Raise Floor Works | 0 | 7984 | 0 | STANDARD | ISAM KABBANI &Partners | SAR | 18081 | APPROVED |  |  | 2025-12-11 | -18081 | 12 | Tananeh, Khalid Jamal | -45990 | 12
105-118 | Bayoniyah (South Khobar) 115/1 | 8317 | Steel Fence | RETURNED | No | 2025-11-21 | Hegazy, Ayman | 2025-12-23 | 2025-11-29 | 2025-12-23 |  | To update the PR to match the ack. PO (TO BE ITEMIZED) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -45990 | -45990
105-118 | Bayoniyah (South Khobar) 115/1 | 8318 | Steel Reinforcement Supply by Al-Faisal | APPROVED | No | 2025-11-21 | Abas, Mohammed Fekry | 2025-11-26 | 2025-11-29 |  |  | Line item 2.20 Steel Reinforcement Supply by Al-Faisal | 0 | 7983 | 0 | STANDARD | AL FAISAL STEEL PRODUCT CO. | SAR | 197250 | APPROVED |  |  | 2025-12-14 | -197250 | 15 | Tananeh, Khalid Jamal | -45990 | 15
105-118 | Bayoniyah (South Khobar) 115/1 | 8319 | Asphalt Works | APPROVED | No | 2025-11-21 | Abas, Mohammed Fekry | 2025-11-27 | 2025-11-29 |  |  | Line item 2.20 Asphalt Works | 0 | 7991 | 0 | STANDARD | The Giant Dam Contracting Est. | SAR | 278582.08 | APPROVED |  |  | 2025-12-14 | -278582.08 | 15 | Tananeh, Khalid Jamal | -45990 | 15
105-118 | Bayoniyah (South Khobar) 115/1 | 8405 | Hazardous Waste Collection | RETURNED | No | 2025-12-01 | Akhtar, Farhan | 2025-12-07 | 2025-12-04 | 2025-12-07 |  | change the UOM and qty | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45995 | -45995
105-118 | Bayoniyah (South Khobar) 115/1 | 8409 | Lighting Control System | APPROVED | No | 2025-12-01 | Abas, Mohammed Fekry | 2025-12-04 | 2025-12-04 |  |  | Line 2.22 Lighting Control System | 0 | 7336 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 72407 | APPROVED | 2025-12-11 | 2025-12-14 | 2026-01-08 | -72407 | 35 | Muaz, Alaa | 10 | 35
105-118 | Bayoniyah (South Khobar) 115/1 | 8442 | Hazard wastage collection | APPROVED | No | 2025-12-03 | Abas, Mohammed Fekry | 2025-12-11 | 2025-12-14 |  |  | line item 2.33 Hazard wastage collection | 0 | 8017 | 0 | STANDARD | Expertise Contracting Co. | SAR | 18300 | APPROVED |  |  | 2025-12-25 | -18300 | 11 | Akhtar, Farhan | -46005 | 11
105-118 | Bayoniyah (South Khobar) 115/1 | 8454 | 250KVA Generator | RETURNED | No | 2025-12-07 | Akhtar, Farhan | 2026-01-18 | 2025-12-17 | 2026-01-18 |  | Facility Dept Will provide the Generator from the Stock | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -46008 | -46008
105-118 | Bayoniyah (South Khobar) 115/1 | 8521 | Diesel for Rental Generator | APPROVED | No | 2025-12-14 | Abas, Mohammed Fekry | 2025-12-20 | 2025-12-21 |  |  | Line item 2.33, Diesel for the Rental Generator | 0 | 15036 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 78500 | APPROVED | 2026-01-15 | 2026-01-19 | 2026-01-29 | -78500 | 39 | Akhtar, Farhan | 29 | 39
105-118 | Bayoniyah (South Khobar) 115/1 | 8649 | Metal Doors (Change Order) - Bayoniah | APPROVED | No | 2026-01-05 | Abas, Mohammed Fekry | 2026-01-26 | 2026-01-27 |  |  | Budget line 2.20 - Civil works | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46049 | -46049
105-118 | Bayoniyah (South Khobar) 115/1 | 8668 | Manufacturing, Fabrication, Supply and Installation of Steel Decorative fence | APPROVED | No | 2026-01-08 | Abas, Mohammed Fekry | 2026-01-21 | 2026-01-25 |  |  | Line Item 2.20 Civil Work | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46047 | -46047
105-118 | Bayoniyah (South Khobar) 115/1 | 8743 | Supply and Installation of Metal Works for Bayouniah | APPROVED | No | 2026-01-20 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46050 | -46050
105-119 | Khobar Corniche 115/13.8kv SS | 1927 | Khobar Corniche 115/13.8kv SS-Engineering & Design- Khobar Corniche | APPROVED | No | 2023-12-11 | Abas, Mohammed Fekry | 2023-12-12 | 2023-12-12 |  |  |  | 581250 | 4898 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 581250 | APPROVED |  |  | 2024-03-17 | 0 | 96 | Kumar, Mr. Ranjan | -45272 | 96
105-119 | Khobar Corniche 115/13.8kv SS | 1973 | Khobar Corniche 115/13.8kv SS-Control, SAS Protection-Khobar corniche | APPROVED | No | 2023-12-17 | Abas, Mohammed Fekry | 2023-12-17 | 2023-12-17 |  |  |  | 8250000 | 4847 | 0 | STANDARD | ALFANAR CO | SAR | 8250000 | APPROVED |  |  | 2024-01-25 | 0 | 39 | Kumar, Mr. Ranjan | -45277 | 39
105-119 | Khobar Corniche 115/13.8kv SS | 2091 | Khobar Corniche 115/13.8kv SS-13.8KV MV SWITCHGEAR PANEL | APPROVED | No | 2024-01-10 | Abas, Mohammed Fekry | 2024-01-10 | 2024-01-11 |  |  |  | 8210000 | 4864 | 0 | STANDARD | ALFANAR CO | SAR | 8210000 | APPROVED |  |  | 2024-01-21 | 0 | 10 | Alhadi, Khalid | -45302 | 10
105-119 | Khobar Corniche 115/13.8kv SS | 2112 | Khobar Corniche 115/13.8kv SS-Temporary Project Sign Board | APPROVED | No | 2024-01-08 | Abas, Mohammed Fekry | 2024-01-09 | 2024-01-09 |  |  |  | 20000 | 4971 | 0 | STANDARD | Construction Expertise Est. | SAR | 20000 | APPROVED |  |  | 2024-01-17 | 0 | 8 | Alhadi, Khalid | -45300 | 8
105-119 | Khobar Corniche 115/13.8kv SS | 2343 | Khobar Corniche 115/13.8kv SS-DESIGN PR NO.2 ( PR1927) | APPROVED | No | 2024-01-29 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 48750 | 4898 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 48750 | APPROVED |  |  | 2024-03-17 | 0 | 42 | Kumar, Mr. Ranjan | -45326 | 42
105-119 | Khobar Corniche 115/13.8kv SS | 2357 | Khobar Corniche 115/13.8kv SS- UG Scanning | APPROVED | No | 2024-01-29 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 1900 | 5070 | 0 | STANDARD | Construction Expertise Est. | SAR | 1900 | APPROVED |  |  | 2024-02-15 | 0 | 11 | Alhadi, Khalid | -45326 | 11
105-119 | Khobar Corniche 115/13.8kv SS | 2376 | Khobar Corniche 115/13.8kv SS-Cyber Security | APPROVED | No | 2024-01-30 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 1100000 | 5059 | 0 | STANDARD | ALFANAR CO | SAR | 1100000 | APPROVED |  |  | 2024-02-18 | 0 | 14 | Babic, Marian | -45326 | 14
105-119 | Khobar Corniche 115/13.8kv SS | 2403 | Khobar Corniche 115/13.8kv SS-Site Office facility | APPROVED | No | 2024-02-04 | Abas, Mohammed Fekry | 2024-02-07 | 2024-02-10 |  |  |  | 319997 | 5425 | 0 | STANDARD | Construction Expertise Est. | SAR | 319997 | APPROVED |  |  | 2024-05-26 | 0 | 106 | Muhammad, Muhammad Atif | -45332 | 106
105-119 | Khobar Corniche 115/13.8kv SS | 2494 | Khobar Corniche 115/13.8kv SS-Temporary Fence & Gates | APPROVED | No | 2024-02-07 | Abas, Mohammed Fekry | 2024-02-09 | 2024-02-10 |  |  |  | 28850 | 5140 | 0 | STANDARD | Construction Expertise Est. | SAR | 28850 | APPROVED |  |  | 2024-03-14 | 0 | 33 | Alhadi, Khalid | -45332 | 33
105-119 | Khobar Corniche 115/13.8kv SS | 2535 | Khobar Corniche 115/13.8kv SS-Super Structure Precast including Fire Walls | APPROVED | No | 2024-02-12 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-19 |  |  |  | 2421479 | 5386 | 0 | STANDARD | Factory of Ideal Precast Concrete System Company | SAR | 2095473 | APPROVED |  |  | 2024-04-30 | 326006 | 71 | Tananeh, Khalid Jamal | -45341 | 71
105-119 | Khobar Corniche 115/13.8kv SS | 2719 | Khobar Corniche 115/13.8kv SS-ACDB/DCDB & Lighting Panel | APPROVED | No | 2024-02-28 | Issa, Amr Ali | 2024-03-03 | 2024-03-03 |  |  |  | 870000 | 5329 | 0 | STANDARD | ALFANAR CO | SAR | 870000 | APPROVED |  |  | 2024-04-28 | 0 | 56 | Mohammed, Faisal Ansari | -45354 | 56
105-119 | Khobar Corniche 115/13.8kv SS | 2885 | Khobar Corniche 115/13.8kv SS-Topographic Survey | APPROVED | No | 2024-03-24 | Abas, Mohammed Fekry | 2024-03-25 | 2024-03-25 |  |  |  | 5125 | 5367 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 5125 | APPROVED |  |  | 2024-04-18 | 0 | 24 | Alhadi, Khalid | -45376 | 24
105-119 | Khobar Corniche 115/13.8kv SS | 3035 | Khobar Corniche 115/13.8kv SS- OVERHEAD TRAVELING CRANE | APPROVED | No | 2024-04-16 | Abas, Mohammed Fekry | 2024-04-16 | 2024-04-16 |  |  |  | 129000 | 5463 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 126870 | APPROVED |  |  | 2024-05-16 | 2130 | 30 | Muhammad, Muhammad Atif | -45398 | 30
105-119 | Khobar Corniche 115/13.8kv SS | 3068 | Khobar Corniche 115/13.8kv SS-Site Office facility | APPROVED | No | 2024-04-21 | Abas, Mohammed Fekry | 2024-04-21 | 2024-04-23 |  |  |  | 242553 | 5425 | 0 | STANDARD | Construction Expertise Est. | SAR | 242553 | APPROVED |  |  | 2024-05-26 | 0 | 33 | Muhammad, Muhammad Atif | -45405 | 33
105-119 | Khobar Corniche 115/13.8kv SS | 3179 | Khobar Corniche 115/13.8kv SS-Water Proofing | APPROVED | No | 2024-04-28 | Abas, Mohammed Fekry | 2024-04-29 | 2024-04-29 |  |  |  | 392625 | 5656 | 0 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 347826.5 | APPROVED |  |  | 2024-06-13 | 44798.5 | 45 | Tananeh, Khalid Jamal | -45411 | 45
105-119 | Khobar Corniche 115/13.8kv SS | 3188 | Khobar Corniche 115/13.8kv SS-Hollow Metal Doors Works | APPROVED | No | 2024-04-28 | Abas, Mohammed Fekry | 2024-04-29 | 2024-04-29 |  |  |  | 162672 | 6043 | 0 | STANDARD | AL MANASHY COMPANY | SAR | 106036.2 | APPROVED |  |  | 2024-10-21 | 56635.8 | 175 | Tananeh, Khalid Jamal | -45411 | 175
105-119 | Khobar Corniche 115/13.8kv SS | 3193 | Khobar Corniche 115/13.8kv SS-Metal Works | APPROVED | No | 2024-04-28 | Abas, Mohammed Fekry | 2024-04-29 | 2024-04-29 |  |  |  | 426160 | 5939 | 0 | STANDARD | Nesma Alfaris Contracting Est. | SAR | 388300 | APPROVED |  |  | 2024-10-14 | 37860 | 168 | Tananeh, Khalid Jamal | -45411 | 168
105-119 | Khobar Corniche 115/13.8kv SS | 3375 | Khobar Corniche 115/13.8kv SS-150sq.mm, Tinned copper conductor | APPROVED | No | 2024-05-12 | Abas, Mohammed Fekry | 2024-05-16 | 2024-05-17 |  |  |  | 38500 | 5355 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 38455.41 | APPROVED |  |  | 2024-05-21 | 44.59 | 4 | Muhammad, Muhammad Atif | -45429 | 4
105-119 | Khobar Corniche 115/13.8kv SS | 3461 | Khobar Corniche 115/13.8kv SS-Site Office facility Electronic Item | APPROVED | No | 2024-05-21 | Abas, Mohammed Fekry | 2024-05-21 | 2024-05-22 |  |  |  | 33800 | 5609 | 0 | STANDARD | Construction Expertise Est. | SAR | 33800 | APPROVED |  |  | 2024-06-05 | 0 | 14 | Muhammad, Muhammad Atif | -45434 | 14
105-119 | Khobar Corniche 115/13.8kv SS | 3503 | Khobar Corniche 115/13.8kv SS-Battery and Charger | APPROVED | No | 2024-05-27 | Abas, Mohammed Fekry | 2024-05-28 | 2024-05-28 |  |  |  | 550000 | 5740 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 457000 | APPROVED |  |  | 2024-07-10 | 93000 | 43 | Muhammad, Muhammad Atif | -45440 | 43
105-119 | Khobar Corniche 115/13.8kv SS | 3577 | Khobar Corniche 115/13.8kv SS-Grounding Material Accessories | APPROVED | No | 2024-06-03 | Abas, Mohammed Fekry | 2024-06-03 | 2024-06-04 |  |  |  | 73475 | 5558 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 72850 | APPROVED |  |  | 2024-07-07 | 625 | 33 | Muhammad, Muhammad Atif | -45447 | 33
105-119 | Khobar Corniche 115/13.8kv SS | 3715 | Khobar Corniche 115/13.8kv SS-MV POWER CABLE ( 1C × 630mm2 & 1×3C×300mm2 | APPROVED | No | 2024-07-01 | Abas, Mohammed Fekry | 2024-07-02 | 2024-07-03 |  |  |  | 1223740 | 6024 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 1093970.6 | APPROVED |  |  | 2024-10-14 | 129769.4 | 103 | Badhman, Saeed | -45476 | 103
105-119 | Khobar Corniche 115/13.8kv SS | 3780 | Khobar Corniche 115/13.8kv SS-Garbage Waste Container, 12 Cu. M (1-year) | APPROVED | No | 2024-07-07 | Abas, Mohammed Fekry | 2024-07-09 | 2024-07-09 |  |  |  | 28800 | 5887 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 19200 | APPROVED |  |  | 2024-08-20 | 9600 | 42 | Akhtar, Farhan | -45482 | 42
105-119 | Khobar Corniche 115/13.8kv SS | 3833 | Khobar Corniche 115/13.8kv SS-Testing for Plate load test-4Points | APPROVED | No | 2024-07-11 | Abas, Mohammed Fekry | 2024-07-21 | 2024-07-21 |  |  |  | 8400 | 5944 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 7540 | APPROVED |  |  | 2024-10-13 | 860 | 84 | Tananeh, Khalid Jamal | -45494 | 84
105-119 | Khobar Corniche 115/13.8kv SS | 3846 | Khobar Corniche 115/13.8kv SS-Control Cable | APPROVED | No | 2024-07-11 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 716000 | 5826 | 0 | STANDARD | ALFANAR CO | SAR | 531752.8 | APPROVED |  |  | 2024-08-28 | 184247.2 | 43 | Muhammad, Muhammad Atif | -45489 | 43
105-119 | Khobar Corniche 115/13.8kv SS | 3901 | Khobar Corniche 115/13.8kv SS-Testing & Commissioning | APPROVED | No | 2024-07-15 | Abas, Mohammed Fekry | 2024-07-17 | 2024-07-18 |  |  |  | 1854163 | 6447 | 0 | STANDARD | Al Fanar Technical Services | SAR | 1802080 | APPROVED |  |  | 2025-03-13 | 52083 | 238 | Alqadhi, Abdulrahman Abdulghani | -45491 | 238
105-119 | Khobar Corniche 115/13.8kv SS | 3905 | Khobar Corniche 115/13.8kv SS-RTV Coating | APPROVED | No | 2024-07-15 | Abas, Mohammed Fekry | 2024-07-17 | 2024-07-18 |  |  |  | 250000 | 6179 | 0 | STANDARD | SAUDI CONDUIT COATING CO. (S3C) | SAR | 35268 | APPROVED |  |  | 2024-10-13 | 214732 | 87 | Muaz, Alaa | -45491 | 87
105-119 | Khobar Corniche 115/13.8kv SS | 3910 | Khobar Corniche 115/13.8kv SS-MV TERMINATION KITS ( 1C × 630mm2 & 3C×300mm2 ) | APPROVED | No | 2024-07-16 | Abas, Mohammed Fekry | 2024-07-17 | 2024-07-18 |  |  |  | 98839 | 5986 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 95871.89 | APPROVED |  |  | 2024-09-19 | 2967.11 | 63 | Badhman, Saeed | -45491 | 63
105-119 | Khobar Corniche 115/13.8kv SS | 4022 | Khobar Corniche 115/13.8kv SS-LCLM | APPROVED | No | 2024-07-25 | Abas, Mohammed Fekry | 2024-07-29 | 2024-07-29 |  |  |  | 59075 | 5964 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 59075 | APPROVED |  |  | 2024-10-06 | 0 | 69 | Badhman, Saeed | -45502 | 69
105-119 | Khobar Corniche 115/13.8kv SS | 4048 | Khobar Corniche 115/13.8kv SS-Cable tray and ladder along with Accessories | APPROVED | No | 2024-07-29 | Abas, Mohammed Fekry | 2024-07-31 | 2024-07-31 |  |  |  | 552885 | 5895 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 505784.96 | APPROVED |  |  | 2024-09-26 | 47100.04 | 57 | Muhammad, Muhammad Atif | -45504 | 57
105-119 | Khobar Corniche 115/13.8kv SS | 4168 | Khobar Corniche 115/13.8kv SS-LV AC / DC Cables and Lighitng Wires | APPROVED | No | 2024-08-17 | Abas, Mohammed Fekry | 2024-08-19 | 2024-08-19 |  |  |  | 1611070 | 6081 | 0 | STANDARD | ALFANAR CO | SAR | 1110509.38 | APPROVED |  |  | 2024-10-01 | 500560.62 | 43 | Badhman, Saeed | -45523 | 43
105-119 | Khobar Corniche 115/13.8kv SS | 4182 | Khobar Corniche 115/13.8kv SS-Hazardou and Non Hazardous Waste | APPROVED | No | 2024-08-18 | Abas, Mohammed Fekry | 2024-08-19 | 2024-08-19 |  |  |  | 5000 | 6114 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 3650 | APPROVED |  |  | 2024-09-16 | 1350 | 28 | Akhtar, Farhan | -45523 | 28
105-119 | Khobar Corniche 115/13.8kv SS | 4204 | Khobar Corniche 115/13.8kv SS-Supply and delivery of drinking Water 6 Cu. M Fiber Glass tank | APPROVED | No | 2024-08-19 | Alharbi, Atef Saud | 2024-08-20 | 2024-08-21 |  |  |  | 3000 | 6095 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 3000 | APPROVED |  |  | 2024-09-02 | 0 | 12 | Akhtar, Farhan | -45525 | 12
105-119 | Khobar Corniche 115/13.8kv SS | 4207 | Khobar Corniche 115/13.8kv SS-Supply and delivery of Raw Water 10 Cu. M tanker | APPROVED | No | 2024-08-19 | Alharbi, Atef Saud | 2024-08-20 | 2024-08-21 |  |  |  | 1800 | 6095 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 1800 | APPROVED |  |  | 2024-09-02 | 0 | 12 | Akhtar, Farhan | -45525 | 12
105-119 | Khobar Corniche 115/13.8kv SS | 4212 | Khobar Corniche 115/13.8kv SS-Sewage water removal services 10,000 liters | APPROVED | No | 2024-08-19 | Abas, Mohammed Fekry | 2024-08-21 | 2024-08-22 |  |  |  | 300 | 6095 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 300 | APPROVED |  |  | 2024-09-02 | 0 | 11 | Akhtar, Farhan | -45526 | 11
105-119 | Khobar Corniche 115/13.8kv SS | 4231 | Khobar Corniche 115/13.8kv SS-Grounding cables, 0.6/1 KV, Y/G | APPROVED | No | 2024-08-21 | Abas, Mohammed Fekry | 2024-08-22 | 2024-08-22 |  |  |  | 244150 | 6065 | 0 | STANDARD | ALFANAR CO | SAR | 226756.52 | APPROVED |  |  | 2024-09-18 | 17393.48 | 27 | Muhammad, Muhammad Atif | -45526 | 27
105-119 | Khobar Corniche 115/13.8kv SS | 4318 | Khobar Corniche 115/13.8kv SS-Electrical Resistivity Soil test | APPROVED | No | 2024-08-29 | Abas, Mohammed Fekry | 2024-09-01 | 2024-09-01 |  |  |  | 8000 | 6142 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 6400 | APPROVED |  |  | 2024-11-14 | 1600 | 74 | Tananeh, Khalid Jamal | -45536 | 74
105-119 | Khobar Corniche 115/13.8kv SS | 4320 | Khobar Corniche 115/13.8kv SS-Station Service Transformer-750KVA | APPROVED | No | 2024-08-29 | Abas, Mohammed Fekry | 2024-10-08 | 2024-10-09 |  |  |  | 164000 | 5909 | 0 | STANDARD | ALFANAR CO | SAR | 164000 | APPROVED |  |  | 2024-10-17 | 0 | 8 | Muhammad, Muhammad Atif | -45574 | 8
105-119 | Khobar Corniche 115/13.8kv SS | 4369 | Khobar Corniche 115/13.8kv SS-Fire Protection System | APPROVED | No | 2024-09-04 | Abas, Mohammed Fekry | 2024-09-05 | 2024-09-05 |  |  |  | 2247089 | 6006 | 0 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 2247089 | APPROVED |  |  | 2024-09-18 | 0 | 13 | Muhammad, Muhammad Atif | -45540 | 13
105-119 | Khobar Corniche 115/13.8kv SS | 4589 | Khobar Corniche 115/13.8kv SS-Electrical Installation Sub Contractor | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-06 | 2024-10-06 |  |  |  | 2992521 | 6436 | 0 | STANDARD | City Crowns Energy | SAR | 2475000 | APPROVED |  |  | 2024-12-26 | 517521 | 81 | Muhammad, Muhammad Atif | -45571 | 81
105-119 | Khobar Corniche 115/13.8kv SS | 4656 | Khobar Corniche 115/13.8kv SS-Security Guard | APPROVED | No | 2024-10-10 | Abas, Mohammed Fekry | 2024-10-13 | 2024-10-14 |  |  |  | 13500 | 6345 | 0 | STANDARD | Rukn Al Kateibah Company for Security Guards. | SAR | 12750 | APPROVED |  |  | 2024-10-16 | 750 | 2 | Abuhammad, Samir | -45579 | 2
105-119 | Khobar Corniche 115/13.8kv SS | 4675 | Khobar Corniche 115/13.8kv SS-HVAC SYSTEM | APPROVED | No | 2024-10-15 | Abas, Mohammed Fekry | 2024-10-15 | 2024-10-15 |  |  |  | 2220000 | 6200 | 0 | STANDARD | Magna Contracting Co | SAR | 2050000 | APPROVED |  |  | 2024-11-05 | 170000 | 21 | Muhammad, Muhammad Atif | -45580 | 21
105-119 | Khobar Corniche 115/13.8kv SS | 4978 | Khobar Corniche 115/13.8kv SS-Lighting Fixtures | APPROVED | No | 2024-11-18 | Abas, Mohammed Fekry | 2024-11-19 | 2024-11-19 |  |  |  | 88037 | 6472 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 88037 | APPROVED |  |  | 2024-11-26 | 0 | 7 | Muhammad, Muhammad Atif | -45615 | 7
105-119 | Khobar Corniche 115/13.8kv SS | 5017 | Khobar Corniche 115/13.8kv SS-Civil Sub Contractor | APPROVED | No | 2024-11-21 | Abas, Mohammed Fekry | 2024-11-24 | 2024-11-24 |  |  |  | 7700000 | 5663 | 0 | STANDARD | Intelligent System General Contracting Company | SAR | 7700000 | APPROVED |  |  | 2024-12-04 | 0 | 10 | Alhadi, Khalid | -45620 | 10
105-119 | Khobar Corniche 115/13.8kv SS | 5079 | Khobar Corniche 115/13.8kv SS-HCIS-3 Consultancy for Security System | APPROVED | No | 2024-11-28 | Abas, Mohammed Fekry | 2024-12-24 | 2024-12-24 |  |  |  | 33500 | 6511 | 0 | STANDARD | Khaled Drewesh Office for Consulting Security (KDOCS) | SAR | 33500 | APPROVED |  |  | 2025-01-13 | 0 | 20 | Muhammad, Muhammad Atif | -45650 | 20
105-119 | Khobar Corniche 115/13.8kv SS | 5092 | Khobar Corniche 115/13.8kv SS-Fiber Optic Cables & Accessories, Installation and Testing Services | APPROVED | No | 2024-11-30 | Abas, Mohammed Fekry | 2024-12-01 | 2024-12-03 |  |  |  | 220000 | 6618 | 0 | STANDARD | Arabian Power Trading Est. | SAR | 188000 | APPROVED |  |  | 2024-12-24 | 32000 | 21 | Muhammad, Muhammad Atif | -45629 | 21
105-119 | Khobar Corniche 115/13.8kv SS | 5113 | Khobar Corniche 115/13.8kv SS-OHTL (ACSR/AW), TYPE CONDOR | APPROVED | No | 2024-12-03 | Abas, Mohammed Fekry | 2024-12-04 | 2024-12-04 |  |  |  | 29760 | 6602 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 24000 | APPROVED |  |  | 2024-12-16 | 5760 | 12 | Mohammed, Faisal Ansari | -45630 | 12
|  |  | - 795 kcmil ASTM B549 | [23 empty] | 0 | 0
105-119 | Khobar Corniche 115/13.8kv SS | 5133 | Khobar Corniche 115/13.8kv SS-Al. Connector for GIB Bushing-2.13 | APPROVED | No | 2024-12-04 | Abas, Mohammed Fekry | 2024-12-04 | 2024-12-08 |  |  |  | 5675 | 6416 | 0 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 4617.79 | APPROVED |  |  | 2025-01-02 | 1057.21 | 25 | Mohammed, Faisal Ansari | -45634 | 25
105-119 | Khobar Corniche 115/13.8kv SS | 5141 | Khobar Corniche 115/13.8kv SS-Supply and delivery of drinking Water 6 Cu. M Fiber Glass tank | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-15 | 2024-12-15 |  |  |  | 5250 | 6684 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 4500 | APPROVED |  |  | 2025-03-09 | 750 | 84 | Akhtar, Farhan | -45641 | 84
105-119 | Khobar Corniche 115/13.8kv SS | 5146 | Khobar Corniche 115/13.8kv SS-Supply and delivery of Raw Water 10 Cu. M tanker | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-15 | 2024-12-15 |  |  |  | 2100 | 6684 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 1800 | APPROVED |  |  | 2025-03-09 | 300 | 84 | Akhtar, Farhan | -45641 | 84
105-119 | Khobar Corniche 115/13.8kv SS | 5151 | Khobar Corniche 115/13.8kv SS-Sewage water removal services 10,000 liters | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-15 | 2024-12-15 |  |  |  | 300 | 6684 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 300 | APPROVED |  |  | 2025-03-09 | 0 | 84 | Akhtar, Farhan | -45641 | 84
105-119 | Khobar Corniche 115/13.8kv SS | 5296 | Khobar Corniche 115/13.8kv SS-150mm2 Tinned Copper Conductor | APPROVED | No | 2024-12-30 | Abas, Mohammed Fekry | 2024-12-31 | 2025-01-01 |  |  |  | 133400 | 6754 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 121307.52 | APPROVED |  |  | 2025-02-27 | 12092.48 | 57 | Alhadi, Khalid | -45658 | 57
105-119 | Khobar Corniche 115/13.8kv SS | 5353 | Khobar Corniche 115/13.8kv SS-Supply of Conduits and Fittings | APPROVED | No | 2025-01-05 | Abas, Mohammed Fekry | 2025-01-08 | 2025-01-12 |  |  |  | 342909.3 | 6694 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 342909.3 | APPROVED |  |  | 2025-01-23 | 0 | 11 | Muaz, Alaa | -45669 | 11
105-119 | Khobar Corniche 115/13.8kv SS | 5428 | Khobar Corniche 115/13.8kv SS-LCLM | APPROVED | No | 2025-01-14 | Abas, Mohammed Fekry | 2025-01-16 | 2025-01-19 |  |  |  | 15700 | 5964 | 1 | STANDARD | Al-Babtain Power & Telecom | SAR | 15575 | APPROVED |  |  | 2025-08-26 | 125 | 219 | Badhman, Saeed | -45676 | 219
105-119 | Khobar Corniche 115/13.8kv SS | 5445 | Khobar Corniche 115/13.8kv SS-Supply and Install shinko Fence and 2*2 Security Cabin | RETURNED | No | 2025-01-16 | Tananeh, Khalid Jamal | 2025-09-22 | 2025-01-19 | 2025-09-22 |  | "As no response was received by the deadline of 21-09-2025 to the clarification request sent on Tue 16/09/2025 at 10:29 AM, the PR is being cancelled accordingly." | 68700 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45676 | -45676
105-119 | Khobar Corniche 115/13.8kv SS | 5460 | Khobar Corniche 115/13.8kv SS-CT Junction Box with 9 Single Phase CTPU including all accessories | APPROVED | No | 2025-01-19 | Abas, Mohammed Fekry | 2025-01-19 | 2025-01-19 |  |  |  | 85000 | 6287 | 0 | STANDARD | Energy Tracks For Contracting | SAR | 85000 | APPROVED |  |  | 2025-03-04 | 0 | 44 | Kumar, Mr. Ranjan | -45676 | 44
105-119 | Khobar Corniche 115/13.8kv SS | 5541 | Khobar Corniche 115/13.8kv SS-Remote end modification for TFR , DSM | APPROVED | No | 2025-01-23 | Abas, Mohammed Fekry | 2025-01-26 | 2025-01-26 |  |  |  | 100000 | 7452 | 0 | STANDARD | TRINERGY TECHNOLOGIES SA | SAR | 30615 | APPROVED |  |  | 2025-07-06 | 69385 | 161 | Babic, Marian | -45683 | 161
105-119 | Khobar Corniche 115/13.8kv SS | 5559 | Khobar Corniche 115/13.8kv SS-Security System Class-3 | APPROVED | No | 2025-01-23 | Abas, Mohammed Fekry | 2025-01-26 | 2025-01-26 |  |  |  | 795629 | 6632 | 0 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 795629 | APPROVED |  |  | 2025-03-05 | 0 | 38 | Abdulqader, Ahmed Abdulhalim | -45683 | 38
105-119 | Khobar Corniche 115/13.8kv SS | 5686 | Khobar Corniche 115/13.8kv SS-Cable Clamps & Cleats for HV & MV Cables | INCOMPLETE | No |  | Mughal, Aurang | 2025-01-27 |  |  |  |  | 100000 | [5 empty] | 0 |  |  |  |  | 0 |  | Muhammad, Muhammad Atif | 0 | 0
105-119 | Khobar Corniche 115/13.8kv SS | 6103 | Khobar Corniche 115/13.8kv SS-Drawing Printing & Scanning | APPROVED | No | 2025-03-03 | Abas, Mohammed Fekry | 2025-03-05 | 2025-03-05 |  |  | Line Item: 2.33 - Drawing Printing & Scanning | 35000 | 7065 | 0 | STANDARD | Print Magaies Al abdaa Printing | SAR | 35000 | APPROVED |  |  | 2025-04-07 | 0 | 33 | Abuhammad, Samir | -45721 | 33
105-119 | Khobar Corniche 115/13.8kv SS | 6143 | Khobar Corniche 115/13.8kv SS-Grounding Accessories | APPROVED | No | 2025-03-10 | Abas, Mohammed Fekry | 2025-03-11 | 2025-03-12 |  |  | line item 2.19-Tray Acessories | 44950 | 7154 | 0 | STANDARD | AL-AMAL ELECTRICAL SWITCHBOARDS | SAR | 14966.6 | APPROVED |  |  | 2025-04-24 | 29983.4 | 43 | Muaz, Alaa | -45728 | 43
105-119 | Khobar Corniche 115/13.8kv SS | 6191 | Khobar Corniche 115/13.8kv SS-Fence Relocation | APPROVED | No | 2025-03-17 | Abas, Mohammed Fekry | 2025-03-18 | 2025-03-20 |  |  | LINE ITEM 2.20-Fence Relocation | 55090 | 7108 | 0 | STANDARD | Construction Expertise Est. | SAR | 40050 | APPROVED |  |  | 2025-08-10 | 15040 | 143 | Abdulqader, Ahmed Abdulhalim | -45736 | 143
105-119 | Khobar Corniche 115/13.8kv SS | 6200 | Khobar Corniche 115/13.8kv SS-Technicians for Testing & Commissioning | APPROVED | No | 2025-03-18 | Abas, Mohammed Fekry | 2025-03-19 | 2025-03-20 |  |  | Line Item: 2.30 - Technicians for Testing & Commissioning | 190080 | 7209 | 0 | STANDARD | SMART LINES INDUSTRIAL & SERVCIES COMPANY | SAR | 190062 | APPROVED |  |  | 2025-05-08 | 18 | 49 | Babic, Marian | -45736 | 49
105-119 | Khobar Corniche 115/13.8kv SS | 6291 | Khobar Corniche 115/13.8kv SS-Supply & Delivery of Raw Water,Drinking Water & Sweage Removal | APPROVED | No | 2025-04-03 | Abas, Mohammed Fekry | 2025-04-06 | 2025-04-06 |  |  | line item 2.33-Supply & Delivery of Raw Water,Drinking Water & Sweage Removal | 6600 | 6684 | 1 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 6600 | APPROVED |  |  | 2025-04-14 | 0 | 8 | Akhtar, Farhan | -45753 | 8
105-119 | Khobar Corniche 115/13.8kv SS | 6310 | Khobar Corniche 115/13.8kv SS-Tower AC-5T0N | APPROVED | No | 2025-04-09 | Abas, Mohammed Fekry | 2025-04-10 | 2025-04-13 |  |  | line item 2.33-Tower AC-5T0N | 71760 | 7145 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 61600 | APPROVED |  |  | 2025-04-24 | 10160 | 11 | Abuhammad, Samir | -45760 | 11
105-119 | Khobar Corniche 115/13.8kv SS | 6362 | Khobar Corniche 115/13.8kv SS-7C X 2.5 Sq.mm 0.6/1 KV Grade , XLPE Insulated, PVC Jacketed, Copper Tape | APPROVED | No | 2025-04-17 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-20 |  |  | line item 2.13-7X2.5 mm2 CU/XLPE/CTS/PVC | 52600 | 6783 | 0 | STANDARD | ALFANAR CO | SAR | 52600 | APPROVED |  |  | 2025-04-30 | 0 | 10 | Muaz, Alaa | -45767 | 10
[12 empty] | 0.6/1 KV – Blue Color | [14 empty] | 0 | 0
105-119 | Khobar Corniche 115/13.8kv SS | 6393 | Khobar Corniche 115/13.8kv SS-Closing of Opening - Switchgear Room to Control Room | APPROVED | No | 2025-04-20 | Abas, Mohammed Fekry | 2025-04-21 | 2025-04-21 |  |  | Line Item - 2.20: Closing of Opening - Switchgear Room to Control Room | 6000 | 7199 | 0 | STANDARD | Tamim Company (PVT) LTD | SAR | 6000 | APPROVED |  |  | 2025-04-30 | 0 | 9 | Abuhammad, Samir | -45768 | 9
105-119 | Khobar Corniche 115/13.8kv SS | 6414 | Khobar Corniche 115/13.8kv SS-Sealant work for External Wall | REJECTED | No | 2025-04-22 | Ibrahim, Mahmoud Hassan Ali | 2025-06-19 | 2025-04-22 |  | 2025-06-23 |  | 55000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45769 | -45769
105-119 | Khobar Corniche 115/13.8kv SS | 6449 | Khobar Corniche 115/13.8kv SS-Technicians for Testing & Commissioning | APPROVED | No | 2025-04-24 | Abas, Mohammed Fekry | 2025-04-29 | 2025-04-29 |  |  | line item 2.30-Technicians for Testing & Commissioning | 80000 | 7209 | 0 | STANDARD | SMART LINES INDUSTRIAL & SERVCIES COMPANY | SAR | 80000 | APPROVED |  |  | 2025-05-08 | 0 | 9 | Babic, Marian | -45776 | 9
105-119 | Khobar Corniche 115/13.8kv SS | 6511 | Khobar Corniche 115/13.8kv SS-4P x 1.5 sqmm Cable | APPROVED | No | 2025-05-05 | Abas, Mohammed Fekry | 2025-05-06 | 2025-05-06 |  |  | Line Item: 2.13 - 4P x 1.5 sqmm Cable | 9000 | 7316 | 0 | STANDARD | Middle East Specialized Cables Mesc | SAR | 7500 | APPROVED |  |  | 2025-05-27 | 1500 | 21 | Abuhammad, Samir | -45783 | 21
105-119 | Khobar Corniche 115/13.8kv SS | 6543 | Khobar Corniche 115/13.8kv SS-Steel Decorative Fence | APPROVED | No | 2025-05-06 | Abas, Mohammed Fekry | 2025-05-08 | 2025-05-08 |  |  | Line Item: 2.20 - Steel Decorative Fence | 902000 | 6804 | 0 | STANDARD | Fursan Construction Industry Factory Industry Factory | SAR | 625000.2 | APPROVED |  |  | 2025-08-26 | 276999.8 | 110 | Hegazy, Ayman | -45785 | 110
105-119 | Khobar Corniche 115/13.8kv SS | 6686 | Khobar Corniche 115/13.8kv SS-HV & MV Cable Supports | APPROVED | No | 2025-05-22 | Abas, Mohammed Fekry | 2025-05-27 | 2025-05-27 |  |  | Line Item: 2.19 - HV & MV Cable Supports | 151624.4 | 7269 | 0 | STANDARD | ISAM KABBANI &Partners | SAR | 151624.4 | APPROVED |  |  | 2025-11-27 | 0 | 184 | Hegazy, Ayman | -45804 | 184
105-119 | Khobar Corniche 115/13.8kv SS | 6688 | Khobar Corniche 115/13.8kv SS-Grounding Accessories | APPROVED | No | 2025-05-22 | Abas, Mohammed Fekry | 2025-06-01 | 2025-06-02 |  |  | Line Item 2.21 - Grounding Accessories | 100732.7 | 7095 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 100732.7 | APPROVED |  |  | 2025-06-24 | 0 | 22 | Abdulqader, Ahmed Abdulhalim | -45810 | 22
105-119 | Khobar Corniche 115/13.8kv SS | 6739 | Khobar Corniche 115/13.8kv SS-125V DC DB for Communication System | APPROVED | No | 2025-05-28 | Abas, Mohammed Fekry | 2025-07-06 | 2025-07-07 |  |  | Line Item 2.12 - 125V DC DB for Communication System | 35000 | 7521 | 0 | STANDARD | HAWA ELECTRIC PANEL BOARD FAC | SAR | 29700 | APPROVED |  |  | 2025-07-27 | 5300 | 20 | Abuhammad, Samir | -45845 | 20
105-119 | Khobar Corniche 115/13.8kv SS | 6782 | Khobar Corniche 115/13.8kv SS-Communication System | APPROVED | No | 2025-06-12 | Abas, Mohammed Fekry | 2025-06-15 | 2025-06-15 |  |  | line item 2.4-Communication System | 2168370 | 6236 | 0 | STANDARD | ALFANAR CO | SAR | 2168369.78 | APPROVED |  |  | 2025-06-24 | 0.22 | 9 | Kumar, Mr. Ranjan | -45823 | 9
105-119 | Khobar Corniche 115/13.8kv SS | 6808 | Khobar Corniche 115/13.8kv SS-Al. Connector for GIB Bushing | APPROVED | No | 2025-06-16 | Abas, Mohammed Fekry | 2025-06-19 | 2025-06-19 |  |  | line item 2.13-Al. Connector for GIB Bushing | 10000 | 6416 | 1 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 8733 | APPROVED |  |  | 2025-06-30 | 1267 | 11 | Abdulqader, Ahmed Abdulhalim | -45827 | 11
105-119 | Khobar Corniche 115/13.8kv SS | 6909 | Khobar Corniche 115/13.8kv SS-Wiring devices( Switches, Socket and Push Buttons) | APPROVED | No | 2025-06-26 | Abas, Mohammed Fekry | 2025-06-30 | 2025-07-01 |  |  | line item 2.23-Wiring devices( Switches, Socket and Push Buttons) | 96720 | 7170 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 96720 | APPROVED |  |  | 2025-07-14 | 0 | 13 | Muaz, Alaa | -45839 | 13
105-119 | Khobar Corniche 115/13.8kv SS | 6979 | Khobar Corniche 115/13.8kv SS-Asphalt,Excavation and Back filling work | APPROVED | No | 2025-07-03 | Abas, Mohammed Fekry | 2025-07-07 | 2025-07-07 |  |  | line item 2.20-Asphalt,Excavation and Back filling work | 1135208 | 5663 | 1 | STANDARD | Intelligent System General Contracting Company | SAR | 1135208 | APPROVED |  |  | 2025-08-06 | 0 | 30 | Alhadi, Khalid | -45845 | 30
105-119 | Khobar Corniche 115/13.8kv SS | 6980 | Khobar Corniche 115/13.8kv SS-Container for Material | RETURNED | No | 2025-07-05 | Abdulqader, Ahmed Abdulhalim | 2025-10-06 | 2025-07-07 | 2025-10-06 |  | not required available in warhouse as per logistic team | 25000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45845 | -45845
105-119 | Khobar Corniche 115/13.8kv SS | 7003 | Khobar Corniche 115/13.8kv SS-Transformer oil DGA Analysis | APPROVED | No | 2025-07-07 | Abas, Mohammed Fekry | 2025-07-10 | 2025-07-10 |  |  | line item 2.33-Transformer oil DGA Analysis | 40000 | 7502 | 0 | STANDARD | Saudi Arabian Engineering Company | SAR | 37300 | APPROVED |  |  | 2025-07-22 | 2700 | 12 | Abdulqader, Ahmed Abdulhalim | -45848 | 12
105-119 | Khobar Corniche 115/13.8kv SS | 7048 | Khobar Corniche 115/13.8kv SS-MV CABLE CLAMP | APPROVED | No | 2025-07-09 | Abas, Mohammed Fekry | 2025-07-10 | 2025-07-10 |  |  | line item 2.13-MV Cable Clamps | 56525 | 7254 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 56525 | APPROVED |  |  | 2025-08-10 | 0 | 31 | Hegazy, Ayman | -45848 | 31
105-119 | Khobar Corniche 115/13.8kv SS | 7085 | Khobar Corniche 115/13.8kv SS-PDS System | APPROVED | No | 2025-07-14 | Abas, Mohammed Fekry | 2025-07-22 | 2025-07-22 |  |  | line item 2.5-PDS System | 200000 | 7767 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 140000 | APPROVED |  |  | 2025-11-18 | 60000 | 119 | Hegazy, Ayman | -45860 | 119
105-119 | Khobar Corniche 115/13.8kv SS | 7098 | Khobar Corniche 115/13.8kv SS-closure of openings in the GIS room | RETURNED | No | 2025-07-15 | Tananeh, Khalid Jamal | 2025-09-22 | 2025-07-20 | 2025-09-22 |  | "As no response was received by the deadline of 21-09-2025 to the clarification request sent on Tue 16/09/2025 at 10:29 AM, the PR is being cancelled accordingly." | 8400 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45858 | -45858
105-119 | Khobar Corniche 115/13.8kv SS | 7116 | Khobar Corniche 115/13.8kv SS-Supply, Installation of H-Beam | REJECTED | No | 2025-07-16 | Ibrahim, Mahmoud Hassan Ali | 2025-12-21 | 2025-07-17 |  | 2025-12-21 |  | 66000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45855 | -45855
105-119 | Khobar Corniche 115/13.8kv SS | 7228 | Khobar Corniche 115/13.8kv SS-Fire-Retardant Material Supply & Installation | RETURNED | No | 2025-07-27 | Tananeh, Khalid Jamal | 2025-09-22 | 2025-08-12 | 2025-09-22 |  | "As no response was received by the deadline of 21-09-2025 to the clarification request sent on Tue 16/09/2025 at 10:29 AM, the PR is being cancelled accordingly." | 7500 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45881 | -45881
105-119 | Khobar Corniche 115/13.8kv SS | 7278 | Khobar Corniche 115/13.8kv SS-Water Proofing work | APPROVED | No | 2025-08-04 | Abas, Mohammed Fekry | 2025-08-05 | 2025-08-06 |  |  | LINE ITEM 2.20-Water Proofing work | 37265 | 5656 | 1 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 37264.54 | APPROVED |  |  | 2025-09-17 | 0.46 | 42 | Tananeh, Khalid Jamal | -45875 | 42
105-119 | Khobar Corniche 115/13.8kv SS | 7355 | Khobar Corniche 115/13.8kv SS-Security Guard | APPROVED | No | 2025-08-13 | Abas, Mohammed Fekry | 2025-08-18 | 2025-08-18 |  |  | line item 2.30- 01 No. Security Guard-for 2 months | 8500 | 6345 | 1 | STANDARD | Rukn Al Kateibah Company for Security Guards. | SAR | 8500 | APPROVED |  |  | 2025-08-20 | 0 | 2 | Abuhammad, Samir | -45887 | 2
105-119 | Khobar Corniche 115/13.8kv SS | 7383 | 150Sq.Tinned copper Conductor | APPROVED | No | 2025-08-19 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | line item 2.21-150Sq.mm tinned copper conductor | 0 | 7689 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 41300 | APPROVED |  |  | 2025-10-14 | -41300 | 50 | Muaz, Alaa | -45894 | 50
105-119 | Khobar Corniche 115/13.8kv SS | 7501 | Technicians for Testing & Commissioning | APPROVED | No | 2025-08-26 | Abas, Mohammed Fekry | 2025-08-27 | 2025-08-28 |  |  | LINE ITEM 2.31-Technicians for Testing & Commissioning for 2 months | 0 | 7209 | 1 | STANDARD | SMART LINES INDUSTRIAL & SERVCIES COMPANY | SAR | 34476 | APPROVED |  |  | 2025-10-16 | -34476 | 49 | Babic, Marian | -45897 | 49
105-119 | Khobar Corniche 115/13.8kv SS | 7547 | Supply & installation of HDG Structural Staircases | RETURNED | No | 2025-08-27 | Tananeh, Khalid Jamal | 2025-10-23 | 2025-09-03 | 2025-10-23 |  | "Return this because it's duplicate work. Al Sharek Al Daim already works there and has an approved PO in the ERP system." | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45903 | -45903
105-119 | Khobar Corniche 115/13.8kv SS | 7752 | 400kVA Diesel Generator | RETURNED | No | 2025-09-15 | Badhman, Saeed | 2025-10-14 | 2025-09-16 | 2025-10-14 |  | all rquired information shall be provided in attachement. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45916 | -45916
105-119 | Khobar Corniche 115/13.8kv SS | 7762 | Office Furniture | APPROVED | No | 2025-09-16 | Abas, Mohammed Fekry | 2025-09-18 | 2025-09-19 |  |  | line item 2.33-Office Furniture | 0 | 7713 | 0 | STANDARD | ALISMAIL INDUSTRIAL CO.(S) | SAR | 17590 | APPROVED |  |  | 2025-10-07 | -17590 | 18 | Abdulqader, Ahmed Abdulhalim | -45919 | 18
105-119 | Khobar Corniche 115/13.8kv SS | 7983 | Swing Gate Motor | RETURNED | No | 2025-10-16 | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | 2025-10-30 | 2025-10-25 | 2025-10-30 |  | missing clear requirements | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -45955 | -45955
105-119 | Khobar Corniche 115/13.8kv SS | 8038 | Technicians for Testing & Commissioning | RETURNED | No | 2025-10-23 | Akhtar, Farhan | 2026-01-05 | 2025-12-21 | 2026-01-05 |  | NO detailed received | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -46012 | -46012
105-119 | Khobar Corniche 115/13.8kv SS | 8413 | Lighting Motion Sensor | APPROVED | No | 2025-12-08 | Abas, Mohammed Fekry | 2025-12-15 | 2025-12-17 |  |  | line item 2.22-Lighting Motion Sensor-Khobar Corniche SS | 0 | 7340 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 72407 | APPROVED | 2025-12-23 | 2025-12-26 | 2026-01-08 | -72407 | 22 | Muaz, Alaa | 9 | 22
105-119 | Khobar Corniche 115/13.8kv SS | 8563 | Metal door hard ware | APPROVED | No | 2025-12-22 | Abas, Mohammed Fekry | 2025-12-24 | 2025-12-24 |  |  | line item 2.20-Metal door hard ware POCR # 324-Khobar Corniche SS | 0 | 6043 | 1 | STANDARD | AL MANASHY COMPANY | SAR | 13904.2 | APPROVED | 2025-12-30 | 2026-01-08 | 2026-01-12 | -13904.2 | 19 | Tananeh, Khalid Jamal | 15 | 19
105-119 | Khobar Corniche 115/13.8kv SS | 8593 | Metal Works (Change Order) - Khobar Corniche | RETURNED | No | 2025-12-28 | Tananeh, Khalid Jamal | 2026-01-22 | 2026-01-01 | 2026-01-22 |  | return as per email from Arnie, in Thu 22/01/2026 10:36 AM | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -46023 | -46023
105-119 | Khobar Corniche 115/13.8kv SS | 8597 | Metal Doors (Change Order) - Khobar Corniche | APPROVED | No | 2025-12-28 | Abas, Mohammed Fekry | 2025-12-30 | 2026-01-01 |  |  | Budget line 2.20 - Civil Works | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -46023 | -46023
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 1926 | Hada-2 (Andalus) 115/13.8kv SS-Engineering & Design- hada-2 | APPROVED | No | 2023-12-11 | Abas, Mohammed Fekry | 2023-12-12 | 2023-12-12 |  |  |  | 581250 | 4894 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 570000 | APPROVED |  |  | 2024-01-15 | 11250 | 34 | Kumar, Mr. Ranjan | -45272 | 34
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 1949 | Hada-2 (Andalus) 115/13.8kv SS-Control SAS protection panels- Hada-2 | APPROVED | No | 2023-12-13 | Abas, Mohammed Fekry | 2023-12-13 | 2023-12-13 |  |  |  | 8350000 | 4856 | 0 | STANDARD | ALFANAR CO | SAR | 8350000 | APPROVED |  |  | 2024-01-15 | 0 | 33 | Kumar, Mr. Ranjan | -45273 | 33
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 1970 | Hada-2 (Andalus) 115/13.8kv SS-13.8kV Switchgear-Hada-2 | APPROVED | No | 2023-12-14 | Abas, Mohammed Fekry | 2023-12-15 | 2023-12-17 |  |  |  | 8120000 | 4860 | 0 | STANDARD | ALFANAR CO | SAR | 8120000 | APPROVED |  |  | 2024-03-13 | 0 | 87 | Alhadi, Khalid | -45277 | 87
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 2109 | Hada-2 (Andalus) 115/13.8kv SS-Temporary Project Sign Board | APPROVED | No | 2024-01-08 | Abas, Mohammed Fekry | 2024-01-09 | 2024-01-09 |  |  |  | 20000 | 4970 | 0 | STANDARD | Construction Expertise Est. | SAR | 20000 | APPROVED |  |  | 2024-01-17 | 0 | 8 | Alhadi, Khalid | -45300 | 8
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 2190 | Hada-2 (Andalus) 115/13.8kv SS-13.8KV SWITCHGEAR | APPROVED | No | 2024-01-17 | Abas, Mohammed Fekry | 2024-02-11 | 2024-02-12 |  |  |  | 90000 | 4860 | 0 | STANDARD | ALFANAR CO | SAR | 90000 | APPROVED |  |  | 2024-03-13 | 0 | 30 | Alhadi, Khalid | -45334 | 30
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 2235 | Hada-2 (Andalus) 115/13.8kv SS-Cyber Security | APPROVED | No | 2024-01-21 | Abas, Mohammed Fekry | 2024-01-22 | 2024-01-22 |  |  |  | 1180000 | 5055 | 0 | STANDARD | ALFANAR CO | SAR | 1100000 | APPROVED |  |  | 2024-02-18 | 80000 | 27 | Babic, Marian | -45313 | 27
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 2363 | Hada-2 (Andalus) 115/13.8kv SS-LINE ITEM 2.20 UG Scanning | APPROVED | No | 2024-01-29 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 1900 | 5074 | 0 | STANDARD | Construction Expertise Est. | SAR | 1900 | APPROVED |  |  | 2024-02-15 | 0 | 11 | Alhadi, Khalid | -45326 | 11
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 2490 | Hada-2 (Andalus) 115/13.8kv SS-Temporary Fencing Works & Security Cabin | APPROVED | No | 2024-02-07 | Abas, Mohammed Fekry | 2024-02-09 | 2024-02-10 |  |  |  | 113000 | 5142 | 0 | STANDARD | Construction Expertise Est. | SAR | 108789 | APPROVED |  |  | 2024-03-24 | 4211 | 43 | Alhadi, Khalid | -45332 | 43
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 2540 | Hada-2 (Andalus) 115/13.8kv SS-Super Structure Precast including Fire Walls | APPROVED | No | 2024-02-12 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-19 |  |  |  | 2421479 | 5382 | 0 | STANDARD | Factory of Ideal Precast Concrete System Company | SAR | 2095473 | APPROVED |  |  | 2024-04-24 | 326006 | 65 | Tananeh, Khalid Jamal | -45341 | 65
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 2923 | Hada-2 (Andalus) 115/13.8kv SS-Topography Survey for Project Area | APPROVED | No | 2024-03-28 | Abas, Mohammed Fekry | 2024-03-31 | 2024-03-31 |  |  |  | 5125 | 5718 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 5125 | APPROVED |  |  | 2024-06-26 | 0 | 87 | Alhadi, Khalid | -45382 | 87
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 2940 | Hada-2 (Andalus) 115/13.8kv SS-AC/DC Panels with Sub DB's & LP's | APPROVED | No | 2024-03-28 | Abas, Mohammed Fekry | 2024-03-31 | 2024-03-31 |  |  |  | 870000 | 5371 | 0 | STANDARD | ALFANAR CO | SAR | 870000 | APPROVED |  |  | 2024-05-07 | 0 | 37 | Mohammed, Faisal Ansari | -45382 | 37
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 3046 | Hada-2 (Andalus) 115/13.8kv SS-5T Over Head Travelling Cran with Accessories | APPROVED | No | 2024-04-16 | Abas, Mohammed Fekry | 2024-04-18 | 2024-04-24 |  |  |  | 130000 | 5460 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 126870 | APPROVED |  |  | 2024-05-16 | 3130 | 22 | Muhammad, Muhammad Atif | -45406 | 22
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 3254 | Hada-2 (Andalus) 115/13.8kv SS-Supply & Apply of Roof Waterproofing System & Underground Waterproofing Tanking System | APPROVED | No | 2024-05-02 | Abas, Mohammed Fekry | 2024-05-02 | 2024-05-02 |  |  |  | 392625 | 5654 | 0 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 347826.5 | APPROVED |  |  | 2024-06-16 | 44798.5 | 45 | Tananeh, Khalid Jamal | -45414 | 45
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 3261 | Hada-2 (Andalus) 115/13.8kv SS-Supply & Installation of Substation Doors | APPROVED | No | 2024-05-02 | Abas, Mohammed Fekry | 2024-05-06 | 2024-05-06 |  |  |  | 162672 | 6044 | 0 | STANDARD | AL MANASHY COMPANY | SAR | 106036.2 | APPROVED |  |  | 2024-10-21 | 56635.8 | 168 | Tananeh, Khalid Jamal | -45418 | 168
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 3265 | Hada-2 (Andalus) 115/13.8kv SS-Supply & Install of Metal Works | APPROVED | No | 2024-05-02 | Abas, Mohammed Fekry | 2024-05-06 | 2024-05-06 |  |  |  | 426160 | 5950 | 0 | STANDARD | Al Sharek Al Daem Est for Contracting | SAR | 388300 | APPROVED |  |  | 2024-10-09 | 37860 | 156 | Tananeh, Khalid Jamal | -45418 | 156
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 3337 | Hada-2 (Andalus) 115/13.8kv SS-Site Office Electroic Items | APPROVED | No | 2024-05-07 | Abas, Mohammed Fekry | 2024-05-09 | 2024-05-12 |  |  |  | 33800 | 5605 | 0 | STANDARD | Construction Expertise Est. | SAR | 21750 | APPROVED |  |  | 2024-06-05 | 12050 | 24 | Muhammad, Muhammad Atif | -45424 | 24
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 3404 | Hada-2 (Andalus) 115/13.8kv SS-150 Sq.mm Tinned Copper Conductor | APPROVED | No | 2024-05-15 | Abas, Mohammed Fekry | 2024-05-15 | 2024-05-15 |  |  |  | 38500 | 5351 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 38455.41 | APPROVED |  |  | 2024-05-26 | 44.59 | 11 | Muhammad, Muhammad Atif | -45427 | 11
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 3508 | Hada-2 (Andalus) 115/13.8kv SS-Battery & Chargers 125V, 2500AH GEL Type -2no/ 2no's | APPROVED | No | 2024-05-28 | Abas, Mohammed Fekry | 2024-05-28 | 2024-05-28 |  |  |  | 550000 | 5736 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 457000 | APPROVED |  |  | 2024-07-09 | 93000 | 42 | Muhammad, Muhammad Atif | -45440 | 42
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 3596 | Hada-2 (Andalus) 115/13.8kv SS-Grounding Material and Its accessories | APPROVED | No | 2024-06-05 | Abas, Mohammed Fekry | 2024-06-08 | 2024-06-09 |  |  |  | 72850 | 5554 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 72850 | APPROVED |  |  | 2024-07-07 | 0 | 28 | Muhammad, Muhammad Atif | -45452 | 28
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 3742 | Hada-2 (Andalus) 115/13.8kv SS-MV Cable ( 1C x 630 mm2 and 1x3Cx300mm2) | APPROVED | No | 2024-07-02 | Abas, Mohammed Fekry | 2024-07-05 | 2024-07-07 |  |  |  | 1260970 | 6019 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 1127267.9 | APPROVED |  |  | 2024-10-09 | 133702.1 | 94 | Badhman, Saeed | -45480 | 94
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 3785 | Hada-2 (Andalus) 115/13.8kv SS-Garbage Waste Container, 12 Cu. M (1-year) | APPROVED | No | 2024-07-07 | Abas, Mohammed Fekry | 2024-07-09 | 2024-07-09 |  |  |  | 28800 | 5889 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 19200 | APPROVED |  |  | 2024-08-20 | 9600 | 42 | Akhtar, Farhan | -45482 | 42
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 3844 | Hada-2 (Andalus) 115/13.8kv SS-Control Cables | APPROVED | No | 2024-07-11 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 716000 | 5822 | 0 | STANDARD | ALFANAR CO | SAR | 531752.8 | APPROVED |  |  | 2024-08-27 | 184247.2 | 42 | Muhammad, Muhammad Atif | -45489 | 42
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 3932 | Hada-2 (Andalus) 115/13.8kv SS-MV Termination Kit | APPROVED | No | 2024-07-16 | Abas, Mohammed Fekry | 2024-07-18 | 2024-07-18 |  |  |  | 98837 | 5982 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 95871.89 | APPROVED |  |  | 2024-09-19 | 2965.11 | 63 | Badhman, Saeed | -45491 | 63
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 3969 | Hada-2 (Andalus) 115/13.8kv SS-Testing and Commissioning | APPROVED | No | 2024-07-21 | Abas, Mohammed Fekry | 2024-07-22 | 2024-07-23 |  |  |  | 1855063 | 6443 | 0 | STANDARD | Al Fanar Technical Services | SAR | 1855063 | APPROVED |  |  | 2025-03-13 | 0 | 233 | Alqadhi, Abdulrahman Abdulghani | -45496 | 233
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 3974 | Hada-2 (Andalus) 115/13.8kv SS-RTV Coating | APPROVED | No | 2024-07-21 | Abas, Mohammed Fekry | 2024-07-29 | 2024-07-29 |  |  |  | 250000 | 6187 | 0 | STANDARD | SAUDI CONDUIT COATING CO. (S3C) | SAR | 35268 | APPROVED |  |  | 2024-10-13 | 214732 | 76 | Muaz, Alaa | -45502 | 76
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 4030 | Hada-2 (Andalus) 115/13.8kv SS-Lightning Mast | APPROVED | No | 2024-07-28 | Abas, Mohammed Fekry | 2024-07-30 | 2024-07-30 |  |  |  | 59075 | 5961 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 59075 | APPROVED |  |  | 2024-10-07 | 0 | 69 | Badhman, Saeed | -45503 | 69
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 4055 | Hada-2 (Andalus) 115/13.8kv SS-Cable Tray and its accessories | APPROVED | No | 2024-07-30 | Abas, Mohammed Fekry | 2024-08-01 | 2024-08-01 |  |  |  | 505784.96 | 5917 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 505784.96 | APPROVED |  |  | 2024-09-26 | 0 | 56 | Muhammad, Muhammad Atif | -45505 | 56
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 4139 | Hada-2 (Andalus) 115/13.8kv SS-Earth Work Excavation Remaining QTY | REJECTED | No | 2024-08-11 | Ayad, Ahmed Mostafa | 2024-08-11 |  |  | 2024-08-18 | HADA-2 Excavation is Hardrock with amount 31 M^3 | 631005.1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 4173 | Hada-2 (Andalus) 115/13.8kv SS-LV AC / DC Cables and Lighitng Wires | APPROVED | No | 2024-08-17 | Abas, Mohammed Fekry | 2024-08-21 | 2024-08-21 |  |  |  | 1611070 | 6077 | 0 | STANDARD | ALFANAR CO | SAR | 1110509.38 | APPROVED |  |  | 2024-09-26 | 500560.62 | 36 | Badhman, Saeed | -45525 | 36
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 4188 | Hada-2 (Andalus) 115/13.8kv SS-Hazardous Waste Collection | APPROVED | No | 2024-08-18 | Abas, Mohammed Fekry | 2024-08-21 | 2024-08-21 |  |  |  | 5000 | 6127 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 3650 | APPROVED |  |  | 2024-09-19 | 1350 | 29 | Akhtar, Farhan | -45525 | 29
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 4238 | Hada-2 (Andalus) 115/13.8kv SS-Grounding Conductor and Cables | APPROVED | No | 2024-08-21 | Abas, Mohammed Fekry | 2024-08-28 | 2024-09-01 |  |  |  | 244150 | 6061 | 0 | STANDARD | ALFANAR CO | SAR | 226756.52 | APPROVED |  |  | 2024-09-18 | 17393.48 | 17 | Muhammad, Muhammad Atif | -45536 | 17
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 4257 | Hada-2 (Andalus) 115/13.8kv SS-Electrical Soil Resistivity Testing | APPROVED | No | 2024-08-24 | Abas, Mohammed Fekry | 2024-08-27 | 2024-09-01 |  |  |  | 7360 | 6143 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 6400 | APPROVED |  |  | 2024-10-10 | 960 | 39 | Tananeh, Khalid Jamal | -45536 | 39
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 4384 | Hada-2 (Andalus) 115/13.8kv SS-Civil Subcontractor | APPROVED | No | 2024-09-06 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 7284700 | 5646 | 0 | STANDARD | Suliman Ahmad Khader General Contracting Est (SAK) | SAR | 7284700 | APPROVED |  |  | 2024-11-03 | 0 | 42 | Tananeh, Khalid Jamal | -45557 | 42
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 4387 | Hada-2 (Andalus) 115/13.8kv SS-FireFighting | APPROVED | No | 2024-09-06 | Abas, Mohammed Fekry | 2024-09-17 | 2024-09-17 |  |  |  | 2169000 | 6003 | 0 | STANDARD | Equipment & Technical Services Co.(ETECHS) | SAR | 2169000 | APPROVED |  |  | 2024-09-26 | 0 | 9 | Muhammad, Muhammad Atif | -45552 | 9
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 4526 | Hada-2 (Andalus) 115/13.8kv SS-HADA-02 Site Office Construction | APPROVED | No | 2024-09-28 | Abas, Mohammed Fekry | 2024-10-07 | 2024-10-07 |  |  |  | 562550 | 5429 | 0 | STANDARD | Construction Expertise Est. | SAR | 562550 | APPROVED |  |  | 2024-10-17 | 0 | 10 | Muhammad, Muhammad Atif | -45572 | 10
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 4576 | Hada-2 (Andalus) 115/13.8kv SS-Station Service Transformer | APPROVED | No | 2024-10-02 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-09 |  |  |  | 164000 | 5905 | 0 | STANDARD | ALFANAR CO | SAR | 164000 | APPROVED |  |  | 2024-10-19 | 0 | 10 | Muhammad, Muhammad Atif | -45574 | 10
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 4598 | Hada-2 (Andalus) 115/13.8kv SS-Electrical Installation - Contract | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-09 |  |  |  | 2992521 | 6357 | 0 | STANDARD | City Crowns Energy | SAR | 2269000 | APPROVED |  |  | 2024-12-29 | 723521 | 81 | Muhammad, Muhammad Atif | -45574 | 81
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 4667 | Hada-2 (Andalus) 115/13.8kv SS-HVAC System Works | APPROVED | No | 2024-10-14 | Abas, Mohammed Fekry | 2024-10-16 | 2024-10-16 |  |  |  | 2050000 | 6201 | 0 | STANDARD | Magna Contracting Co | SAR | 2050000 | APPROVED |  |  | 2024-10-31 | 0 | 15 | Muhammad, Muhammad Atif | -45581 | 15
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 4703 | Hada-2 (Andalus) 115/13.8kv SS-Supply of Raw Water | APPROVED | No | 2024-10-17 | Abas, Mohammed Fekry | 2024-10-20 | 2024-10-20 |  |  |  | 5000 | 6351 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 8400 | APPROVED |  |  | 2024-11-03 | -3400 | 14 | Akhtar, Farhan | -45585 | 14
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 4704 | Hada-2 (Andalus) 115/13.8kv SS-Site Waste Removal Services | APPROVED | No | 2024-10-17 | Abas, Mohammed Fekry | 2024-10-20 | 2024-10-21 |  |  |  | 5000 | 6351 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 8400 | APPROVED |  |  | 2024-11-03 | -3400 | 13 | Akhtar, Farhan | -45586 | 13
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 4718 | Hada-2 (Andalus) 115/13.8kv SS-Telecommunication System | APPROVED | No | 2024-10-17 | Abas, Mohammed Fekry | 2024-12-05 | 2024-12-08 |  |  |  | 2410478.76 | 6239 | 0 | STANDARD | ALFANAR CO | SAR | 2410478.76 | APPROVED |  |  | 2025-04-13 | 0 | 126 | Kumar, Mr. Ranjan | -45634 | 126
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 4982 | Hada-2 (Andalus) 115/13.8kv SS-Lighting Fixtures | APPROVED | No | 2024-11-18 | Abas, Mohammed Fekry | 2024-11-28 | 2024-11-28 |  |  |  | 88037 | 6468 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 88037 | APPROVED |  |  | 2024-12-15 | 0 | 17 | Muhammad, Muhammad Atif | -45624 | 17
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 5086 | Hada-2 (Andalus) 115/13.8kv SS-HCIS Consultant | APPROVED | No | 2024-11-30 | Abas, Mohammed Fekry | 2025-03-10 | 2025-03-12 |  |  | Line item 2.7 HCIS Consultant | 33500 | 6507 | 0 | STANDARD | Khaled Drewesh Office for Consulting Security (KDOCS) | SAR | 33500 | APPROVED |  |  | 2025-06-15 | 0 | 95 | Abdulqader, Ahmed Abdulhalim | -45728 | 95
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 5157 | Hada-2 (Andalus) 115/13.8kv SS-Alminum Conductor Clamps and Connector | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-12 |  |  |  | 4537 | 6412 | 0 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 4505.16 | APPROVED |  |  | 2024-12-25 | 31.84 | 13 | Mohammed, Faisal Ansari | -45638 | 13
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 5346 | Hada-2 (Andalus) 115/13.8kv SS-Conduits and Fittings | APPROVED | No | 2025-01-04 | Abas, Mohammed Fekry | 2025-01-07 | 2025-01-07 |  |  |  | 342909.3 | 6681 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 342909.3 | APPROVED |  |  | 2025-03-03 | 0 | 55 | Muaz, Alaa | -45664 | 55
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 5464 | Hada-2 (Andalus) 115/13.8kv SS-CTPU and CTPU Box including accessories | APPROVED | No | 2025-01-19 | Abas, Mohammed Fekry | 2025-01-20 | 2025-01-23 |  |  |  | 68000 | 6283 | 0 | STANDARD | Energy Tracks For Contracting | SAR | 68000 | APPROVED |  |  | 2025-03-09 | 0 | 45 | Kumar, Mr. Ranjan | -45680 | 45
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 5468 | Hada-2 (Andalus) 115/13.8kv SS-150mm2 Extra Tinned Copper Conductor | APPROVED | No | 2025-01-20 | Abas, Mohammed Fekry | 2025-01-22 | 2025-01-23 |  |  |  | 159600 | 6808 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 147678.72 | APPROVED |  |  | 2025-02-27 | 11921.28 | 35 | Alhadi, Khalid | -45680 | 35
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 5535 | Hada-2 (Andalus) 115/13.8kv SS-Third Party Inspector Lab Testing in Precast Factory | APPROVED | No | 2025-01-22 | Abas, Mohammed Fekry | 2025-02-24 | 2025-02-24 |  |  | Line item 2.20 Third Party Inspector Lab Testing in Precast Factory | 84130 | 7408 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 84130 | APPROVED |  |  | 2025-06-29 | 0 | 125 | Tananeh, Khalid Jamal | -45712 | 125
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 5561 | Hada-2 (Andalus) 115/13.8kv SS-TFR-DM-SOE-SAS for Remote End | APPROVED | No | 2025-01-23 | Abas, Mohammed Fekry | 2025-01-28 | 2025-01-30 |  |  |  | 100000 | 7456 | 0 | STANDARD | TRINERGY TECHNOLOGIES SA | SAR | 61231 | APPROVED |  |  | 2025-07-06 | 38769 | 157 | Babic, Marian | -45687 | 157
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 5565 | Hada-2 (Andalus) 115/13.8kv SS-Fiber Optic Cables & Accessories,Installation and Testing Services | APPROVED | No | 2025-01-23 | Abas, Mohammed Fekry | 2025-01-28 | 2025-01-30 |  |  |  | 250000 | 7031 | 0 | STANDARD | RASHID SAEED AHMED AL GHAMDI COMM INFO TRAD EST | SAR | 210000 | APPROVED |  |  | 2025-04-17 | 40000 | 77 | Abdulqader, Ahmed Abdulhalim | -45687 | 77
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 5595 | Hada-2 (Andalus) 115/13.8kv SS-Office Furniture | REJECTED | No | 2025-01-26 | Sherif, Marwa | 2025-03-09 | 2025-01-27 |  | 2025-03-09 |  | 50000 | [5 empty] | 0 |  |  |  |  | 0 |  | Muhammad, Muhammad Atif | -45684 | -45684
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 5625 | Hada-2 (Andalus) 115/13.8kv SS-Old Fence relocation and new fence installation CEC | RETURNED | No | 2025-01-26 | Abdulqader, Ahmed Abdulhalim | 2025-03-17 | 2025-02-27 | 2025-03-17 |  | PR is not matching the shared offer | 51870 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45715 | -45715
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 5693 | Hada-2 (Andalus) 115/13.8kv SS-MV Cables Cleats and Support | REJECTED | No | 2025-01-27 | Sherif, Marwa | 2025-03-09 | 2025-02-01 |  | 2025-03-09 |  | 100000 | [5 empty] | 0 |  |  |  |  | 0 |  | Muhammad, Muhammad Atif | -45689 | -45689
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 6022 | Hada-2 (Andalus) 115/13.8kv SS-Office Boy PR | REJECTED | No | 2025-02-23 | Sherif, Marwa | 2025-03-09 | 2025-02-25 |  | 2025-03-09 |  | 13500 | [5 empty] | 0 |  |  |  |  | 0 |  | Muhammad, Muhammad Atif | -45713 | -45713
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 6090 | Hada-2 (Andalus) 115/13.8kv SS-Printing of Drawings A2 Size | APPROVED | No | 2025-03-01 | Abas, Mohammed Fekry | 2025-03-03 | 2025-03-05 |  |  | Line item 2.33 Printing of Drawings on A2 size | 31000 | 7037 | 0 | STANDARD | Print Magaies Al abdaa Printing | SAR | 30999 | APPROVED |  |  | 2025-04-07 | 1 | 33 | Abuhammad, Samir | -45721 | 33
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 6295 | Hada-2 (Andalus) 115/13.8kv SS-Supply of RAW Water | APPROVED | No | 2025-04-06 | Abas, Mohammed Fekry | 2025-04-08 | 2025-04-08 |  |  | Line item 2.33 Supply of Raw Water | 6000 | 6351 | 1 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 6000 | APPROVED |  |  | 2025-04-17 | 0 | 9 | Akhtar, Farhan | -45755 | 9
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 6298 | Hada-2 (Andalus) 115/13.8kv SS-Old Fence relocation and new fence intallation CEC works | APPROVED | No | 2025-04-07 | Abas, Mohammed Fekry | 2025-04-08 | 2025-04-08 |  |  | Old Fence Relocation, installation of new fence (CEC works) | 51870 | 7101 | 0 | STANDARD | Construction Expertise Est. | SAR | 37580 | APPROVED |  |  | 2025-08-11 | 14290 | 125 | Abdulqader, Ahmed Abdulhalim | -45755 | 125
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 6335 | Hada-2 (Andalus) 115/13.8kv SS-AC For CSD Testing | APPROVED | No | 2025-04-14 | Abas, Mohammed Fekry | 2025-04-16 | 2025-04-17 |  |  | 5 Ton Stand Alon AC for CSD TEsting ( 8 Numbers) | 71168 | 7163 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 61600 | APPROVED |  |  | 2025-04-24 | 9568 | 7 | Abuhammad, Samir | -45764 | 7
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 6376 | Hada-2 (Andalus) 115/13.8kv SS-Design, Supply, Installation, Testing and Commissioning of Security System | APPROVED | No | 2025-04-17 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-20 |  |  | Design, Supply, Installation, Testing and Commissioning of Seciurity System | 874784.63 | 6634 | 0 | STANDARD | CEGELEC NETWORK AND SECURITY SYSTEMS | SAR | 874784.63 | APPROVED |  |  | 2025-04-24 | 0 | 4 | Abdulqader, Ahmed Abdulhalim | -45767 | 4
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 6383 | Hada-2 (Andalus) 115/13.8kv SS-control Cables for SAS | APPROVED | No | 2025-04-19 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-20 |  |  | Line item 2.13 control Cables for SAS | 52600 | 6779 | 0 | STANDARD | ALFANAR CO | SAR | 52600 | APPROVED |  |  | 2025-04-29 | 0 | 9 | Muaz, Alaa | -45767 | 9
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 6405 | Hada-2 (Andalus) 115/13.8kv SS-Closing Openings with Gypsum Partitions – Substation Projects. | APPROVED | No | 2025-04-21 | Abas, Mohammed Fekry | 2025-04-22 | 2025-04-22 |  |  | Closing Openings with Gypsum Partitions – Substation Projects. | 6000 | 7202 | 0 | STANDARD | Tamim Company (PVT) LTD | SAR | 6000 | APPROVED |  |  | 2025-04-30 | 0 | 8 | Abuhammad, Samir | -45769 | 8
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 6442 | Hada-2 (Andalus) 115/13.8kv SS-Rental Generator 250kVA for CSD Testing | APPROVED | No | 2025-04-23 | Abas, Mohammed Fekry | 2025-04-26 | 2025-04-28 |  |  | Rental Generator 250KVA for CSD Testing | 60000 | 7220 | 0 | STANDARD | Rawafd AlQwt Litaqt Est. | SAR | 37000 | APPROVED |  |  | 2025-05-07 | 23000 | 9 | Akhtar, Farhan | -45775 | 9
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 6516 | Hada-2 (Andalus) 115/13.8kv SS-Instrumentation (4P X 1.5mm2) | APPROVED | No | 2025-05-05 | Abas, Mohammed Fekry | 2025-05-08 | 2025-05-08 |  |  | Instrumentation Cable (4P X 1.5mm2) | 9000 | 7312 | 0 | STANDARD | Middle East Specialized Cables Mesc | SAR | 7500 | APPROVED |  |  | 2025-05-27 | 1500 | 19 | Abuhammad, Samir | -45785 | 19
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 6644 | Hada-2 (Andalus) 115/13.8kv SS-Diesel for 250KVA Rental Generator | APPROVED | No | 2025-05-19 | Abas, Mohammed Fekry | 2025-05-22 | 2025-05-27 |  |  | Diesel for 250KVA Rental Generator | 74347.5 | 7374 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 74347.5 | APPROVED |  |  | 2025-06-04 | 0 | 8 | Akhtar, Farhan | -45804 | 8
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 6652 | Hada-2 (Andalus) 115/13.8kv SS-Transformer Oil DGA Analysis (Lab Testing) as per SEC-CSD requirment | APPROVED | No | 2025-05-19 | Abas, Mohammed Fekry | 2025-05-22 | 2025-05-27 |  |  | Transformer Oil DGA Analysis (Lab Testing) as per SEC-CSD requirment | 35000 | 7477 | 0 | STANDARD | Saudi Arabian Engineering Company | SAR | 35000 | APPROVED |  |  | 2025-07-21 | 0 | 55 | Abdulqader, Ahmed Abdulhalim | -45804 | 55
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 6795 | Hada-2 (Andalus) 115/13.8kv SS-Third Party Lab Testing of IPC Pre-Cast Material | APPROVED | No | 2025-06-12 | Abas, Mohammed Fekry | 2025-06-16 | 2025-06-16 |  |  | PR for Third Party Lab Testing of IPC Mateiral. Initially we have create PR 5535. But PO value is more then previous PR. That's why this PR created. | 60 | 7408 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 60 | APPROVED |  |  | 2025-06-29 | 0 | 13 | Tananeh, Khalid Jamal | -45824 | 13
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 6968 | Hada-2 (Andalus) 115/13.8kv SS-Manpower for Testing and Commissioning | APPROVED | No | 2025-07-02 | Abas, Mohammed Fekry | 2025-07-06 | 2025-07-07 |  |  | Manpower for Testing and Commissioning | 120000 | 7504 | 0 | STANDARD | Jasem M.AlJasem Contracting Est. | SAR | 120000 | APPROVED |  |  | 2025-08-02 | 0 | 26 | Babic, Marian | -45845 | 26
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 6998 | Hada-2 (Andalus) 115/13.8kv SS-Transformer Oil Teting (As per CSD Requirement) | APPROVED | No | 2025-07-07 | Abas, Mohammed Fekry | 2025-07-12 | 2025-07-12 |  |  | Initially we have PR#6652 with the value of 35000/-. Now our PO value is increased from 35000. Therefore I am creating NEW PR with the value of 2300. | 2300 | 7477 | 0 | STANDARD | Saudi Arabian Engineering Company | SAR | 2300 | APPROVED |  |  | 2025-07-21 | 0 | 9 | Abdulqader, Ahmed Abdulhalim | -45850 | 9
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 7033 | Hada-2 (Andalus) 115/13.8kv SS-Onsite Backfilling FDT Testing | RETURNED | No | 2025-07-09 | Tananeh, Khalid Jamal | 2025-09-22 | 2025-07-14 | 2025-09-22 |  | "The PR are being returned in reference to the email sent on Tuesday, 09/09/2025 at 4:14 PM, as the works were carried out without prior approval from the Procurement Department and the payment shall be made from petty cash." | 27000 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45852 | -45852
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 7041 | Hada-2 (Andalus) 115/13.8kv SS-MV & HV Cable Supports | APPROVED | No | 2025-07-09 | Abas, Mohammed Fekry | 2025-07-13 | 2025-07-14 |  |  | Line 2.13 MV & HV Cable Supports | 121906.7 | 7464 | 0 | STANDARD | ISAM KABBANI &Partners | SAR | 121906.7 | APPROVED |  |  | 2025-08-02 | 0 | 19 | Hegazy, Ayman | -45852 | 19
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 7052 | Hada-2 (Andalus) 115/13.8kv SS-MV Cable Clamps | APPROVED | No | 2025-07-09 | Abas, Mohammed Fekry | 2025-07-13 | 2025-07-14 |  |  | Line item 2.13 MV Cable Clamps | 56525 | 7004 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 56525 | APPROVED |  |  | 2025-07-21 | 0 | 7 | Hegazy, Ayman | -45852 | 7
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 7075 | Hada-2 (Andalus) 115/13.8kv SS-Wiring Devices (switches and Sockets) | RETURNED | No | 2025-07-13 | Muaz, Alaa | 2025-07-30 | 2025-07-16 | 2025-07-30 |  | This line item will be returned as the line item added by mistake from the PMT. | 96720 | 7169 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 96720 | APPROVED |  |  | 2025-07-27 | 0 |  | Muaz, Alaa | -45854 | 11
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 7075 | Hada-2 (Andalus) 115/13.8kv SS-Wiring Devices (switches and Sockets) | RETURNED | No | 2025-07-13 | Muaz, Alaa | 2025-07-30 | 2025-07-16 | 2025-07-30 |  | This line item will be returned as the line item added by mistake from the PMT. | 260 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -45854 | -45854
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 7100 | Hada-2 (Andalus) 115/13.8kv SS-PDS System | REJECTED | No | 2025-07-15 | Khan, Muhammad Safdar | 2025-07-16 | 2025-07-16 |  | 2025-07-17 |  | 250000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45854 | -45854
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 7179 | Hada-2 (Andalus) 115/13.8kv SS-Design, Supply, Installation adn T&C of Lighting Control System | RETURNED | No | 2025-07-21 | Muaz, Alaa | 2025-09-09 | 2025-07-27 | 2025-09-09 |  | The budget is not sufficient | 60271 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -45865 | -45865
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 7221 | Hada-2 (Andalus) 115/13.8kv SS-DC Telecom DB | APPROVED | No | 2025-07-27 | Abas, Mohammed Fekry | 2025-08-03 | 2025-08-03 |  |  | DC DB Telecommunication | 50000 | 7607 | 0 | STANDARD | HAWA ELECTRIC PANEL BOARD FAC | SAR | 29700 | APPROVED |  |  | 2025-08-17 | 20300 | 14 | Abuhammad, Samir | -45872 | 14
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 7226 | Hada-2 (Andalus) 115/13.8kv SS-1x400mm2 LV AC Cable | RETURNED | No | 2025-07-27 | Mohammed, Mohammed Adel Fahmy | 2026-01-15 | 2025-08-03 | 2026-01-15 |  | Not Have POCR Until Now and PR incorrect qty. | 94500 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Mohammed Adel Fahmy | -45872 | -45872
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 7283 | Hada-2 (Andalus) 115/13.8kv SS-Water Proofing | APPROVED | No | 2025-08-04 | Abas, Mohammed Fekry | 2025-08-10 | 2025-08-10 |  |  | Line item 2.20 Water Proofing | 37265 | 5654 | 1 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 37264.54 | APPROVED |  |  | 2025-09-30 | 0.46 | 51 | Tananeh, Khalid Jamal | -45879 | 51
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 7285 | Hada-2 (Andalus) 115/13.8kv SS-HTV Rental Bus- Driver | REJECTED | No | 2025-08-05 | Sherif, Marwa | 2025-08-19 | 2025-08-06 |  | 2025-08-27 |  | 26000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45875 | -45875
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 7306 | Hada-2 (Andalus) 115/13.8kv SS-2 Number of 5 Ton Mobile AC's | RETURNED | No | 2025-08-06 |  |  | 2025-08-10 | 2026-01-11 |  | not required the AC | 21600 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45879 | -45879
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 7311 | Hada-2 (Andalus) 115/13.8kv SS-Control Cables for Bayouniah | RETURNED | No | 2025-08-06 | Mohammed, Mohammed Adel Fahmy | 2026-01-15 | 2025-08-18 | 2026-01-15 |  | not have POCR until now and PR not include correct Qty. | 62000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Mohammed Adel Fahmy | -45887 | -45887
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 7318 | Hada-2 (Andalus) 115/13.8kv SS-Extra Grounding Accessories | APPROVED | No | 2025-08-09 | Abas, Mohammed Fekry | 2025-08-17 | 2025-08-18 |  |  | We already have a PO 7093-HV1497 for Extra grounding accessories. PR was not created before before due to the Budget issue. Now CTC is approved. Therefore we have created PR of extra grounding accessories for this PO. | 69784.7 | 7093 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 69784.7 | APPROVED |  |  | 2025-08-28 | 0 | 10 | Abdulqader, Ahmed Abdulhalim | -45887 | 10
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 7419 | Hazardous Waste Collection | REJECTED | No | 2025-08-21 | Sherif, Marwa | 2025-08-25 | 2025-08-24 |  | 2025-08-27 |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45893 | -45893
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 7431 | PDS System | APPROVED | No | 2025-08-23 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | Line item 2.5 PDS System | 0 | 7757 | 0 | STANDARD | RASHID SAEED AHMED AL GHAMDI COMM INFO TRAD EST | SAR | 140000 | APPROVED |  |  | 2025-11-04 | -140000 | 71 | Abdulqader, Ahmed Abdulhalim | -45894 | 71
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 7537 | Lugs and Glands | APPROVED | No | 2025-08-27 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-03 |  |  | Line item 2.13 Lugs and Glands | 0 | 7578 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 24541.6 | APPROVED |  |  | 2025-09-16 | -24541.6 | 13 | Abdulqader, Ahmed Abdulhalim | -45903 | 13
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 7666 | Rental T&C Coordinators | REJECTED | No | 2025-09-07 | Sherif, Marwa | 2025-09-08 | 2025-09-08 |  | 2025-09-08 |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45908 | -45908
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 7785 | Office furniture | APPROVED | No | 2025-09-17 | Abas, Mohammed Fekry | 2025-09-29 | 2025-10-02 |  |  | Line Item 2.33 Office Furniture | 0 | 7711 | 0 | STANDARD | ALISMAIL INDUSTRIAL CO.(S) | SAR | 17590 | APPROVED |  |  | 2025-10-14 | -17590 | 12 | Abdulqader, Ahmed Abdulhalim | -45932 | 12
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 7976 | Motor for the Main Gate | APPROVED | No | 2025-10-16 | Abas, Mohammed Fekry | 2025-10-22 | 2025-10-23 |  |  | Motors for the Main Gate | 0 | 7927 | 0 | STANDARD | ALMOSALLAMY INDUSTRIAL COMPANY | SAR | 9330 | APPROVED |  |  | 2025-12-14 | -9330 | 52 | Abdelraouf, Islam ِAdel Hanafy | -45953 | 52
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 8045 | Asphalt and Steel Boundary Fence | APPROVED | No | 2025-10-23 | Abas, Mohammed Fekry | 2025-10-29 | 2025-10-29 |  |  | Line item 2.20 Asphalt and Steel Boundary Fence | 0 | 5646 | 1 | STANDARD | Suliman Ahmad Khader General Contracting Est (SAK) | SAR | 1380000 | APPROVED |  |  | 2025-11-10 | -1380000 | 12 | Tananeh, Khalid Jamal | -45959 | 12
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 8173 | Disposal of Waste Container (12CU.M3) | APPROVED | No | 2025-11-11 | Abas, Mohammed Fekry | 2025-11-12 | 2025-11-13 |  |  | Line Item 2.33 Disposal of Waste Container | 0 | 5889 | 1 | STANDARD | Cebent for General Cont. Est. | SAR | 11200 | APPROVED |  |  | 2025-11-30 | -11200 | 17 | Akhtar, Farhan | -45974 | 17
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 8226 | Supply of Raw Water | APPROVED | No | 2025-11-16 | Abas, Mohammed Fekry | 2025-11-20 | 2025-11-23 |  |  | Line item 2.33 Supply of Raw Water 10CU M Tanker | 0 | 6351 | 2 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 9000 | APPROVED |  |  | 2025-12-14 | -9000 | 21 | Akhtar, Farhan | -45984 | 21
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 8253 | Motors for Hada-2 SS Main Gate | REJECTED | No | 2025-11-18 | Abdel Naiem, Tarek Ali | 2025-11-18 | 2025-11-18 |  | 2025-11-18 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45979 | -45979
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 8391 | Lighting Control System | APPROVED | No | 2025-11-30 | Abas, Mohammed Fekry | 2025-12-04 | 2025-12-04 |  |  | Line item 2.22 Lighitng Control System | 0 | 7339 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 72407 | APPROVED | 2025-12-11 | 2025-12-14 | 2026-01-08 | -72407 | 35 | Muaz, Alaa | 10 | 35
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 8407 | Hazardous Waste Collection | REJECTED | No | 2025-12-01 | Shahin, Hassan Magdy Hassan | 2025-12-01 |  |  | 2025-12-01 | Line item 2.33 Hazardous Waste Collection | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 8438 | Hazardous Waste Collection | APPROVED | No | 2025-12-03 | Abas, Mohammed Fekry | 2025-12-04 | 2025-12-04 |  |  | Line item 2.33 Hazardous Waste Collection | 0 | 7998 | 0 | STANDARD | Expertise Contracting Co. | SAR | 18300 | APPROVED |  |  | 2025-12-21 | -18300 | 17 | Akhtar, Farhan | -45995 | 17
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 8461 | ACs for site- 5ton | REJECTED | No | 2025-12-07 | Shahin, Hassan Magdy Hassan | 2025-12-07 |  |  | 2025-12-07 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 8518 | Rental Technician for Testing Activity | APPROVED | No | 2025-12-14 | Abas, Mohammed Fekry | 2026-01-26 | 2026-01-27 |  |  | Line item 2.31, 10 Rental Technicians for 7 Months | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46049 | -46049
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 8651 | Metal Doors (Change Order) - Hada-2 | APPROVED | No | 2026-01-05 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-13 |  |  | budget line 2.20 - civil works | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46035 | -46035
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 8727 | Supply of Diesel for Generators | APPROVED | No | 2026-01-19 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46050 | -46050
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 8732 | Supply of Diesel Generators | APPROVED | No | 2026-01-19 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46050 | -46050
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 8738 | Supply and Installation of Metal Works | REJECTED | No | 2026-01-19 | Shahin, Hassan Magdy Hassan | 2026-01-19 |  |  | 2026-01-19 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-120 | Hada-2 (Andalus) 115/13.8kv SS | 8756 | Supply and Installation of Metal Works for HADA-2 | REJECTED | No | 2026-01-21 | Shahin, Hassan Magdy Hassan | 2026-01-21 |  |  | 2026-01-27 | Supply and Installation of Metal Works for HADA-2 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-121 | Al-Bahr 115/13.8kv Substation | 1930 | Al-Bahr 115/13.8kv Substation-Engineering & Design- Albahr | APPROVED | No | 2023-12-11 | Abas, Mohammed Fekry | 2023-12-12 | 2023-12-12 |  |  |  | 581250 | 4892 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 580000 | APPROVED |  |  | 2024-01-08 | 1250 | 27 | Kumar, Mr. Ranjan | -45272 | 27
105-121 | Al-Bahr 115/13.8kv Substation | 1937 | Al-Bahr 115/13.8kv Substation-Control, Protection & SAS Al-Bahr | APPROVED | No | 2023-12-12 | Abas, Mohammed Fekry | 2023-12-12 | 2023-12-12 |  |  |  | 9995000 | 4855 | 0 | STANDARD | ALFANAR CO | SAR | 9995000 | APPROVED |  |  | 2024-01-07 | 0 | 26 | Kumar, Mr. Ranjan | -45272 | 26
105-121 | Al-Bahr 115/13.8kv Substation | 1955 | Al-Bahr 115/13.8kv Substation-13.8kV switchgear | APPROVED | No | 2023-12-13 | Abas, Mohammed Fekry | 2023-12-13 | 2023-12-14 |  |  |  | 8950000 | 4842 | 0 | STANDARD | ALFANAR CO | SAR | 8950000 | APPROVED |  |  | 2024-01-25 | 0 | 42 | Alhadi, Khalid | -45274 | 42
105-121 | Al-Bahr 115/13.8kv Substation | 2108 | Al-Bahr 115/13.8kv Substation-Temporary Project Sign Board | APPROVED | No | 2024-01-08 | Abas, Mohammed Fekry | 2024-01-09 | 2024-01-09 |  |  |  | 20000 | 4966 | 0 | STANDARD | Construction Expertise Est. | SAR | 20000 | APPROVED |  |  | 2024-01-21 | 0 | 12 | Alhadi, Khalid | -45300 | 12
105-121 | Al-Bahr 115/13.8kv Substation | 2232 | Al-Bahr 115/13.8kv Substation-Cyber Security | APPROVED | No | 2024-01-21 | Abas, Mohammed Fekry | 2024-01-22 | 2024-01-22 |  |  |  | 1180000 | 5053 | 0 | STANDARD | ALFANAR CO | SAR | 1100000 | APPROVED |  |  | 2024-02-20 | 80000 | 29 | Babic, Marian | -45313 | 29
105-121 | Al-Bahr 115/13.8kv Substation | 2254 | Al-Bahr 115/13.8kv Substation-Fencing Work | APPROVED | No | 2024-01-23 | Abas, Mohammed Fekry | 2024-01-24 | 2024-01-25 |  |  |  | 92858.33 | 5138 | 0 | STANDARD | Construction Expertise Est. | SAR | 82669 | APPROVED |  |  | 2024-03-20 | 10189.33 | 55 | Alhadi, Khalid | -45316 | 55
105-121 | Al-Bahr 115/13.8kv Substation | 2542 | Al-Bahr 115/13.8kv Substation-Super Structure Precast including Fire Walls | APPROVED | No | 2024-02-12 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-19 |  |  |  | 2421479 | 5392 | 0 | STANDARD | Factory of Ideal Precast Concrete System Company | SAR | 1921165 | APPROVED |  |  | 2024-10-14 | 500314 | 238 | Tananeh, Khalid Jamal | -45341 | 238
105-121 | Al-Bahr 115/13.8kv Substation | 2616 | Al-Bahr 115/13.8kv Substation-Site Office facility | APPROVED | No | 2024-02-19 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 325197 | 5158 | 0 | STANDARD | Construction Expertise Est. | SAR | 209900 | APPROVED |  |  | 2024-03-25 | 115297 | 28 | Muhammad, Muhammad Atif | -45348 | 28
105-121 | Al-Bahr 115/13.8kv Substation | 2655 | Al-Bahr 115/13.8kv Substation-Excavation Works | APPROVED | No | 2024-02-21 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 50200 | 5261 | 0 | STANDARD | Morgan Construction for contracting | SAR | 45180 | APPROVED |  |  | 2024-04-06 | 5020 | 40 | Alhadi, Khalid | -45348 | 40
105-121 | Al-Bahr 115/13.8kv Substation | 2657 | Al-Bahr 115/13.8kv Substation-General Backfilling | APPROVED | No | 2024-02-23 | Abas, Mohammed Fekry | 2024-02-25 | 2024-02-26 |  |  |  | 49000 | 5261 | 0 | STANDARD | Morgan Construction for contracting | SAR | 49000 | APPROVED |  |  | 2024-04-06 | 0 | 40 | Alhadi, Khalid | -45348 | 40
105-121 | Al-Bahr 115/13.8kv Substation | 2658 | Al-Bahr 115/13.8kv Substation-1000mm thick Sub Base Class "A" with CBR not less than 50 | APPROVED | No | 2024-02-23 | Abas, Mohammed Fekry | 2024-02-25 | 2024-02-26 |  |  |  | 33750 | 5261 | 0 | STANDARD | Morgan Construction for contracting | SAR | 33750 | APPROVED |  |  | 2024-04-06 | 0 | 40 | Alhadi, Khalid | -45348 | 40
105-121 | Al-Bahr 115/13.8kv Substation | 2659 | Al-Bahr 115/13.8kv Substation-600mm thick Base Course Class "A" with CBR not less than 100 | APPROVED | No | 2024-02-23 | Abas, Mohammed Fekry | 2024-02-25 | 2024-02-26 |  |  |  | 29700 | 5261 | 0 | STANDARD | Morgan Construction for contracting | SAR | 29700 | APPROVED |  |  | 2024-04-06 | 0 | 40 | Alhadi, Khalid | -45348 | 40
105-121 | Al-Bahr 115/13.8kv Substation | 2924 | Al-Bahr 115/13.8kv Substation-Topography Survey for Project Area | APPROVED | No | 2024-03-28 | Abas, Mohammed Fekry | 2024-03-31 | 2024-03-31 |  |  |  | 5125 | 5719 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 5125 | APPROVED |  |  | 2024-07-01 | 0 | 92 | Alhadi, Khalid | -45382 | 92
105-121 | Al-Bahr 115/13.8kv Substation | 3033 | Al-Bahr 115/13.8kv Substation-Main AC/DC Panels with Sub DB's and Lighting Panels | APPROVED | No | 2024-04-15 | Abas, Mohammed Fekry | 2024-04-16 | 2024-04-16 |  |  |  | 870000 | 5409 | 0 | STANDARD | ALFANAR CO | SAR | 870000 | APPROVED |  |  | 2024-05-05 | 0 | 19 | Mohammed, Faisal Ansari | -45398 | 19
105-121 | Al-Bahr 115/13.8kv Substation | 3047 | Al-Bahr 115/13.8kv Substation-5T Over Head Travelling Crane with Accessories | APPROVED | No | 2024-04-16 | Abas, Mohammed Fekry | 2024-04-17 | 2024-04-24 |  |  |  | 130000 | 5458 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 126870 | APPROVED |  |  | 2024-05-16 | 3130 | 22 | Muhammad, Muhammad Atif | -45406 | 22
105-121 | Al-Bahr 115/13.8kv Substation | 3252 | Al-Bahr 115/13.8kv Substation-Supply & Apply of Roof Waterproofing System & Underground Waterproofing Tanking System | APPROVED | No | 2024-05-02 | Abas, Mohammed Fekry | 2024-05-02 | 2024-05-05 |  |  |  | 392625 | 5651 | 0 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 347826.5 | APPROVED |  |  | 2024-06-13 | 44798.5 | 39 | Tananeh, Khalid Jamal | -45417 | 39
105-121 | Al-Bahr 115/13.8kv Substation | 3257 | Al-Bahr 115/13.8kv Substation-Supply and Installation of Substation Doors | APPROVED | No | 2024-05-02 | Abas, Mohammed Fekry | 2024-05-02 | 2024-05-05 |  |  |  | 152037 | 6045 | 0 | STANDARD | AL MANASHY COMPANY | SAR | 102583 | APPROVED |  |  | 2024-10-21 | 49454 | 169 | Tananeh, Khalid Jamal | -45417 | 169
105-121 | Al-Bahr 115/13.8kv Substation | 3263 | Al-Bahr 115/13.8kv Substation-Supply & Install of Metal Works | APPROVED | No | 2024-05-02 | Abas, Mohammed Fekry | 2024-05-05 | 2024-05-05 |  |  |  | 426160 | 5951 | 0 | STANDARD | Al Sharek Al Daem Est for Contracting | SAR | 388300 | APPROVED |  |  | 2024-10-13 | 37860 | 161 | Tananeh, Khalid Jamal | -45417 | 161
105-121 | Al-Bahr 115/13.8kv Substation | 3332 | Al-Bahr 115/13.8kv Substation-Site Office Electronics Items | APPROVED | No | 2024-05-07 | Abas, Mohammed Fekry | 2024-05-08 | 2024-05-12 |  |  |  | 18200 | 5603 | 0 | STANDARD | Construction Expertise Est. | SAR | 18200 | APPROVED |  |  | 2024-06-05 | 0 | 24 | Muhammad, Muhammad Atif | -45424 | 24
105-121 | Al-Bahr 115/13.8kv Substation | 3405 | Al-Bahr 115/13.8kv Substation-150 Sq.mm Tinned Copper Conductor | APPROVED | No | 2024-05-15 | Abas, Mohammed Fekry | 2024-05-16 | 2024-05-17 |  |  |  | 38500 | 5349 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 38455.41 | APPROVED |  |  | 2024-05-26 | 44.59 | 9 | Muhammad, Muhammad Atif | -45429 | 9
105-121 | Al-Bahr 115/13.8kv Substation | 3501 | Al-Bahr 115/13.8kv Substation-Rental Generator with Diesel Tank | APPROVED | No | 2024-05-27 | Abas, Mohammed Fekry | 2024-05-28 | 2024-05-28 |  |  |  | 8000 | 5666 | 0 | STANDARD | SUDHIR EQUIPMENT RENTAL COMPANY | SAR | 7200 | APPROVED |  |  | 2024-06-13 | 800 | 16 | Akhtar, Farhan | -45440 | 16
105-121 | Al-Bahr 115/13.8kv Substation | 3513 | Al-Bahr 115/13.8kv Substation-Battery & Chargers 125V, 2500AH GEL Type -2no/ 2no's | APPROVED | No | 2024-05-28 | Issa, Amr Ali | 2024-05-28 | 2024-05-29 |  |  |  | 550000 | 5734 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 457000 | APPROVED |  |  | 2024-07-10 | 93000 | 42 | Muhammad, Muhammad Atif | -45441 | 42
105-121 | Al-Bahr 115/13.8kv Substation | 3542 | Al-Bahr 115/13.8kv Substation-Al-Bahr 115/13.8kv Substation-Desiel generator - Al bahr | APPROVED | No | 2024-05-30 | Sherif, Marwa | 2024-06-03 | 2024-06-03 |  |  |  | 275000 | 5727 | 0 | STANDARD | Mohammed A. AlFaddaghi & Partners | SAR | 268350 | APPROVED |  |  | 2024-07-21 | 6650 | 48 | Akhtar, Farhan | -45446 | 48
105-121 | Al-Bahr 115/13.8kv Substation | 3597 | Al-Bahr 115/13.8kv Substation-Grounding Material and its accessories | APPROVED | No | 2024-06-05 | Abas, Mohammed Fekry | 2024-06-08 | 2024-06-09 |  |  |  | 72850 | 5552 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 72850 | APPROVED |  |  | 2024-07-07 | 0 | 28 | Muhammad, Muhammad Atif | -45452 | 28
105-121 | Al-Bahr 115/13.8kv Substation | 3741 | Al-Bahr 115/13.8kv Substation-MV Cable ( 1C x 630 mm2 and 1x3Cx300mm2) | APPROVED | No | 2024-07-02 | Abas, Mohammed Fekry | 2024-07-11 | 2024-07-11 |  |  |  | 1069560 | 6018 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 956014.2 | APPROVED |  |  | 2024-10-09 | 113545.8 | 90 | Badhman, Saeed | -45484 | 90
105-121 | Al-Bahr 115/13.8kv Substation | 3755 | Al-Bahr 115/13.8kv Substation-Generator Fuel for Construction activities | APPROVED | No | 2024-07-02 | Abas, Mohammed Fekry | 2024-07-10 | 2024-07-11 |  |  |  | 115200 | 5810 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 115200 | APPROVED |  |  | 2024-07-31 | 0 | 20 | Akhtar, Farhan | -45484 | 20
105-121 | Al-Bahr 115/13.8kv Substation | 3840 | Al-Bahr 115/13.8kv Substation-Control Cables | APPROVED | No | 2024-07-11 | Abas, Mohammed Fekry | 2024-07-30 | 2024-07-30 |  |  |  | 716000 | 5834 | 0 | STANDARD | ALFANAR CO | SAR | 531752.8 | APPROVED |  |  | 2024-08-27 | 184247.2 | 28 | Muhammad, Muhammad Atif | -45503 | 28
105-121 | Al-Bahr 115/13.8kv Substation | 3929 | Al-Bahr 115/13.8kv Substation-MV Cable Termination Kit | APPROVED | No | 2024-07-16 | Issa, Amr Ali | 2024-07-21 | 2024-07-21 |  |  |  | 98837 | 5980 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 95871.89 | APPROVED |  |  | 2024-09-19 | 2965.11 | 60 | Badhman, Saeed | -45494 | 60
105-121 | Al-Bahr 115/13.8kv Substation | 3970 | Al-Bahr 115/13.8kv Substation-Testing and Commissioning | APPROVED | No | 2024-07-21 | Abas, Mohammed Fekry | 2024-07-22 | 2024-07-23 |  |  |  | 1973983 | 6441 | 0 | STANDARD | Al Fanar Technical Services | SAR | 1973983 | APPROVED |  |  | 2025-03-13 | 0 | 233 | Alqadhi, Abdulrahman Abdulghani | -45496 | 233
105-121 | Al-Bahr 115/13.8kv Substation | 3975 | Al-Bahr 115/13.8kv Substation-RTV Coating | APPROVED | No | 2024-07-21 | Abas, Mohammed Fekry | 2024-07-29 | 2024-07-29 |  |  |  | 250000 | 6186 | 0 | STANDARD | SAUDI CONDUIT COATING CO. (S3C) | SAR | 35268 | APPROVED |  |  | 2024-10-13 | 214732 | 76 | Muaz, Alaa | -45502 | 76
105-121 | Al-Bahr 115/13.8kv Substation | 4031 | Al-Bahr 115/13.8kv Substation-Lightning Masts | APPROVED | No | 2024-07-28 | Abas, Mohammed Fekry | 2024-07-30 | 2024-07-30 |  |  |  | 59075 | 5956 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 59075 | APPROVED |  |  | 2024-10-07 | 0 | 69 | Badhman, Saeed | -45503 | 69
105-121 | Al-Bahr 115/13.8kv Substation | 4042 | Al-Bahr 115/13.8kv Substation-Electrical Soil Resistivity | APPROVED | No | 2024-07-29 | Abas, Mohammed Fekry | 2024-07-30 | 2024-07-30 |  |  |  | 7360 | 5953 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 6400 | APPROVED |  |  | 2024-10-13 | 960 | 75 | Tananeh, Khalid Jamal | -45503 | 75
105-121 | Al-Bahr 115/13.8kv Substation | 4137 | Al-Bahr 115/13.8kv Substation-Earth Work Excavation Remaining QTY | RETURNED | No | 2024-08-11 | Tananeh, Khalid Jamal | 2025-09-22 | 2025-01-30 | 2025-09-22 |  | "As no response was received by the deadline of 21-09-2025 to the clarification request sent on Tue 16/09/2025 at 10:29 AM, the PR is being cancelled accordingly." | 271173.2 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45687 | -45687
105-121 | Al-Bahr 115/13.8kv Substation | 4174 | Al-Bahr 115/13.8kv Substation-LV ACDC Cables and Lighting wires | APPROVED | No | 2024-08-17 | Abas, Mohammed Fekry | 2024-08-21 | 2024-08-21 |  |  |  | 1611070 | 6075 | 0 | STANDARD | ALFANAR CO | SAR | 1110509.38 | APPROVED |  |  | 2024-09-26 | 500560.62 | 36 | Badhman, Saeed | -45525 | 36
105-121 | Al-Bahr 115/13.8kv Substation | 4186 | Al-Bahr 115/13.8kv Substation-hazardas and non hazardas Waste | APPROVED | No | 2024-08-18 | Abas, Mohammed Fekry | 2024-08-21 | 2024-08-21 |  |  |  | 6000 | 6118 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 3650 | APPROVED |  |  | 2024-09-19 | 2350 | 29 | Akhtar, Farhan | -45525 | 29
105-121 | Al-Bahr 115/13.8kv Substation | 4239 | Al-Bahr 115/13.8kv Substation-Grounding Conductor and Cables | APPROVED | No | 2024-08-21 | Abas, Mohammed Fekry | 2024-08-28 | 2024-09-01 |  |  |  | 244150 | 6059 | 0 | STANDARD | ALFANAR CO | SAR | 226756.52 | APPROVED |  |  | 2024-09-18 | 17393.48 | 17 | Muhammad, Muhammad Atif | -45536 | 17
105-121 | Al-Bahr 115/13.8kv Substation | 4284 | Al-Bahr 115/13.8kv Substation-Cable Tray and its accessories | APPROVED | No | 2024-08-27 | Abas, Mohammed Fekry | 2024-08-28 | 2024-09-01 |  |  |  | 460016.15 | 6149 | 0 | STANDARD | Electrolink Co Ltd | SAR | 459950.02 | APPROVED |  |  | 2024-09-26 | 66.13 | 25 | Muhammad, Muhammad Atif | -45536 | 25
105-121 | Al-Bahr 115/13.8kv Substation | 4385 | Al-Bahr 115/13.8kv Substation-Civil Sub-Contractor | APPROVED | No | 2024-09-06 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 7189800 | 5643 | 0 | STANDARD | Suliman Ahmad Khader General Contracting Est (SAK) | SAR | 7189800 | APPROVED |  |  | 2024-11-03 | 0 | 42 | Tananeh, Khalid Jamal | -45557 | 42
105-121 | Al-Bahr 115/13.8kv Substation | 4389 | Al-Bahr 115/13.8kv Substation-Firefighting System | APPROVED | No | 2024-09-06 | Abas, Mohammed Fekry | 2024-09-17 | 2024-09-17 |  |  |  | 2066000 | 6002 | 0 | STANDARD | Equipment & Technical Services Co.(ETECHS) | SAR | 2066000 | APPROVED |  |  | 2024-09-26 | 0 | 9 | Muhammad, Muhammad Atif | -45552 | 9
105-121 | Al-Bahr 115/13.8kv Substation | 4573 | Al-Bahr 115/13.8kv Substation-Station Service Transformer | APPROVED | No | 2024-10-02 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-09 |  |  |  | 164000 | 5903 | 0 | STANDARD | ALFANAR CO | SAR | 164000 | APPROVED |  |  | 2024-10-19 | 0 | 10 | Muhammad, Muhammad Atif | -45574 | 10
105-121 | Al-Bahr 115/13.8kv Substation | 4600 | Al-Bahr 115/13.8kv Substation-Electrical Installation - Contractor | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-09 |  |  |  | 2992521 | 6356 | 0 | STANDARD | City Crowns Energy | SAR | 2319000 | APPROVED |  |  | 2024-12-29 | 673521 | 81 | Muhammad, Muhammad Atif | -45574 | 81
105-121 | Al-Bahr 115/13.8kv Substation | 4682 | Al-Bahr 115/13.8kv Substation-HVAC System and Works | APPROVED | No | 2024-10-15 | Abas, Mohammed Fekry | 2024-10-16 | 2024-10-16 |  |  |  | 2220000 | 6210 | 0 | STANDARD | MAINTENANCE OF AIRCONDITION AND REFRIGERATION COMPANY LTD.(MARCO) | SAR | 2050000 | APPROVED |  |  | 2024-10-31 | 170000 | 15 | Muhammad, Muhammad Atif | -45581 | 15
105-121 | Al-Bahr 115/13.8kv Substation | 4705 | Al-Bahr 115/13.8kv Substation-Supply of Raw Water | APPROVED | No | 2024-10-17 | Abas, Mohammed Fekry | 2024-10-20 | 2024-10-21 |  |  |  | 3500 | 6376 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 6600 | APPROVED |  |  | 2024-11-12 | -3100 | 22 | Akhtar, Farhan | -45586 | 22
105-121 | Al-Bahr 115/13.8kv Substation | 4706 | Al-Bahr 115/13.8kv Substation-Site Waster Removal Services | APPROVED | No | 2024-10-17 | Abas, Mohammed Fekry | 2024-10-20 | 2024-10-20 |  |  |  | 3500 | 6376 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 6600 | APPROVED |  |  | 2024-11-12 | -3100 | 23 | Akhtar, Farhan | -45585 | 23
105-121 | Al-Bahr 115/13.8kv Substation | 4719 | Al-Bahr 115/13.8kv Substation-Telecommunication system | APPROVED | No | 2024-10-17 | Abas, Mohammed Fekry | 2024-12-05 | 2024-12-08 |  |  |  | 2509669.82 | 6238 | 0 | STANDARD | ALFANAR CO | SAR | 2509669.82 | APPROVED |  |  | 2025-04-10 | 0 | 123 | Kumar, Mr. Ranjan | -45634 | 123
105-121 | Al-Bahr 115/13.8kv Substation | 4724 | Al-Bahr 115/13.8kv Substation-Asphalt Works | RETURNED | No | 2024-10-19 | Tananeh, Khalid Jamal | 2025-08-21 | 2025-03-12 | 2025-08-21 |  | "The PR was returned at Mr. Talha's request to adjust its value, as the current amount is lower than the approved change order value." | 620000 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45728 | -45728
105-121 | Al-Bahr 115/13.8kv Substation | 4916 | Al-Bahr 115/13.8kv Substation-Garbage Waste Container, 12 Cu. M (1-year) | APPROVED | No | 2024-11-12 | Abas, Mohammed Fekry | 2024-11-17 | 2024-11-17 |  |  |  | 14000 | 6522 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 11200 | APPROVED |  |  | 2024-12-25 | 2800 | 38 | Akhtar, Farhan | -45613 | 38
105-121 | Al-Bahr 115/13.8kv Substation | 4961 | Al-Bahr 115/13.8kv Substation-Indoor and Outdoor Lighting Fixture | APPROVED | No | 2024-11-16 | Abas, Mohammed Fekry | 2024-11-20 | 2024-11-20 |  |  |  | 71998 | 6466 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 71998 | APPROVED |  |  | 2024-12-04 | 0 | 14 | Muhammad, Muhammad Atif | -45616 | 14
105-121 | Al-Bahr 115/13.8kv Substation | 5087 | Al-Bahr 115/13.8kv Substation-HCIS Consultant | APPROVED | No | 2024-11-30 | Abas, Mohammed Fekry | 2025-03-10 | 2025-03-12 |  |  | Line item 2.7 HCIS Consultant | 33500 | 6505 | 0 | STANDARD | Khaled Drewesh Office for Consulting Security (KDOCS) | SAR | 33500 | APPROVED |  |  | 2025-06-22 | 0 | 102 | Abdulqader, Ahmed Abdulhalim | -45728 | 102
105-121 | Al-Bahr 115/13.8kv Substation | 5122 | Al-Bahr 115/13.8kv Substation-Pre-Cast Third Party Lab Testing | APPROVED | No | 2024-12-03 | Abas, Mohammed Fekry | 2024-12-09 | 2024-12-12 |  |  |  | 84350 | 6744 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 84190 | APPROVED |  |  | 2025-02-04 | 160 | 54 | Tananeh, Khalid Jamal | -45638 | 54
105-121 | Al-Bahr 115/13.8kv Substation | 5155 | Al-Bahr 115/13.8kv Substation-AL Connector and Clamps | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-12 |  |  |  | 4616.1 | 6410 | 0 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 4606.53 | APPROVED |  |  | 2024-12-25 | 9.57 | 13 | Mohammed, Faisal Ansari | -45638 | 13
105-121 | Al-Bahr 115/13.8kv Substation | 5182 | Al-Bahr 115/13.8kv Substation-Tinned Copper Conductor 150mm2 Extra | APPROVED | No | 2024-12-07 | Abas, Mohammed Fekry | 2024-12-16 | 2024-12-19 |  |  |  | 121800 | 6751 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 110759.04 | APPROVED |  |  | 2025-02-25 | 11040.96 | 68 | Alhadi, Khalid | -45645 | 68
105-121 | Al-Bahr 115/13.8kv Substation | 5342 | Al-Bahr 115/13.8kv Substation-Conduits and fittings | APPROVED | No | 2025-01-02 | Abas, Mohammed Fekry | 2025-01-07 | 2025-01-07 |  |  |  | 342909.3 | 6695 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 342909.3 | APPROVED |  |  | 2025-02-11 | 0 | 35 | Muaz, Alaa | -45664 | 35
105-121 | Al-Bahr 115/13.8kv Substation | 5362 | Al-Bahr 115/13.8kv Substation-Design, supply, installation, testing and commissioning of Security system | APPROVED | No | 2025-01-06 | Abas, Mohammed Fekry | 2025-03-09 | 2025-03-10 |  |  | Line item 2.7 Design, supply, installation, testing and commissioning of Security system | 718209.19 | 6635 | 0 | STANDARD | CEGELEC NETWORK AND SECURITY SYSTEMS | SAR | 718209.19 | APPROVED |  |  | 2025-05-13 | 0 | 64 | Abdulqader, Ahmed Abdulhalim | -45726 | 64
105-121 | Al-Bahr 115/13.8kv Substation | 5462 | Al-Bahr 115/13.8kv Substation-CTPU and CTPU Box Including Accessories | APPROVED | No | 2025-01-19 | Abas, Mohammed Fekry | 2025-01-20 | 2025-01-23 |  |  |  | 68000 | 6281 | 0 | STANDARD | Energy Tracks For Contracting | SAR | 68000 | APPROVED |  |  | 2025-03-09 | 0 | 45 | Kumar, Mr. Ranjan | -45680 | 45
105-121 | Al-Bahr 115/13.8kv Substation | 5522 | Al-Bahr 115/13.8kv Substation-Purchasing of Total Station for ALBAHR SS | APPROVED | No | 2025-01-21 | Abas, Mohammed Fekry | 2025-01-29 | 2025-01-30 |  |  |  | 35000 | 7147 | 0 | STANDARD | ALBOKSOMATTI FOR SURVEYING COMPANY(S) | SAR | 35000 | APPROVED |  |  | 2025-04-29 | 0 | 89 | Abuhammad, Samir | -45687 | 89
105-121 | Al-Bahr 115/13.8kv Substation | 5562 | Al-Bahr 115/13.8kv Substation-TFR-DSM-SOE-SAS, Alfanar loose material delivery for switch gear , Alkhur and mohandaseen expansion for Remote End | RETURNED | No | 2025-01-23 | Babic, Marian | 2025-04-07 | 2025-01-30 | 2025-04-07 |  | As per confirmation from project team no DSM, TFR scope in this SS | 600000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45687 | -45687
105-121 | Al-Bahr 115/13.8kv Substation | 5566 | Al-Bahr 115/13.8kv Substation-Fiber Optic Cables & Accessories,Installation and Testing Services | APPROVED | No | 2025-01-23 | Abas, Mohammed Fekry | 2025-01-28 | 2025-01-30 |  |  |  | 250000 | 6949 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 220000 | APPROVED |  |  | 2025-03-13 | 30000 | 42 | Abdulqader, Ahmed Abdulhalim | -45687 | 42
105-121 | Al-Bahr 115/13.8kv Substation | 6130 | Al-Bahr 115/13.8kv Substation-Printing of Drawings on A2 size | APPROVED | No | 2025-03-06 | Abas, Mohammed Fekry | 2025-03-09 | 2025-03-10 |  |  | Printing of Drawings on A2 size | 31000 | 7068 | 0 | STANDARD | Print Magaies Al abdaa Printing | SAR | 30999.75 | APPROVED |  |  | 2025-04-07 | 0.25 | 28 | Abuhammad, Samir | -45726 | 28
105-121 | Al-Bahr 115/13.8kv Substation | 6134 | Al-Bahr 115/13.8kv Substation-steel parapet works | APPROVED | No | 2025-03-08 | Abas, Mohammed Fekry | 2025-03-10 | 2025-03-12 |  |  | steel parapet works Line item 2.20 | 36520 | 6817 | 0 | STANDARD | RAFCO Factory Company For Metal Industries | SAR | 36520 | APPROVED |  |  | 2025-08-11 | 0 | 152 | Hegazy, Ayman | -45728 | 152
105-121 | Al-Bahr 115/13.8kv Substation | 6185 | Al-Bahr 115/13.8kv Substation-Old fence removal, New fence installation and relocation of Gates done by CEC | APPROVED | No | 2025-03-15 | Abas, Mohammed Fekry | 2025-03-17 | 2025-03-17 |  |  | Old fence removal, New fence installation and relocation of Gates done by CEC | 54720 | 6961 | 0 | STANDARD | Construction Expertise Est. | SAR | 40090 | APPROVED |  |  | 2025-08-11 | 14630 | 147 | Abdulqader, Ahmed Abdulhalim | -45733 | 147
105-121 | Al-Bahr 115/13.8kv Substation | 6339 | Al-Bahr 115/13.8kv Substation-Supplt of RAW Water | APPROVED | No | 2025-04-15 | Abas, Mohammed Fekry | 2025-04-28 | 2025-04-28 |  |  | Supply of Raw Water at ALBAHR Site | 6000 | 6376 | 1 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 6000 | APPROVED |  |  | 2025-05-05 | 0 | 7 | Akhtar, Farhan | -45775 | 7
105-121 | Al-Bahr 115/13.8kv Substation | 6382 | Al-Bahr 115/13.8kv Substation-control Cables for SAS | APPROVED | No | 2025-04-19 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-20 |  |  | Line item 2.13 control Cables for SAS | 52600 | 6777 | 0 | STANDARD | ALFANAR CO | SAR | 52600 | APPROVED |  |  | 2025-04-29 | 0 | 9 | Muaz, Alaa | -45767 | 9
105-121 | Al-Bahr 115/13.8kv Substation | 6426 | Al-Bahr 115/13.8kv Substation-5 Ton AC for CSD Testing | APPROVED | No | 2025-04-23 | Abas, Mohammed Fekry | 2025-04-24 | 2025-04-24 |  |  | 5-Ton AC for CSD Testing | 79200 | 7190 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 69300 | APPROVED |  |  | 2025-04-29 | 9900 | 5 | Abuhammad, Samir | -45771 | 5
105-121 | Al-Bahr 115/13.8kv Substation | 6515 | Al-Bahr 115/13.8kv Substation-Instrumentation Cable (4P X 1.5mm2) | APPROVED | No | 2025-05-05 | Abas, Mohammed Fekry | 2025-05-08 | 2025-05-08 |  |  | Instrumentation Cable (4P X 1.5mm2) | 9000 | 7310 | 0 | STANDARD | Middle East Specialized Cables Mesc | SAR | 7500 | APPROVED |  |  | 2025-05-29 | 1500 | 21 | Abuhammad, Samir | -45785 | 21
105-121 | Al-Bahr 115/13.8kv Substation | 6577 | Al-Bahr 115/13.8kv Substation-Rental Generator | APPROVED | No | 2025-05-11 | Abas, Mohammed Fekry | 2025-05-12 | 2025-05-14 |  |  | Rental Generator | 13400 | 5666 | 1 | STANDARD | SUDHIR EQUIPMENT RENTAL COMPANY | SAR | 12000 | APPROVED |  |  | 2025-05-27 | 1400 | 13 | Akhtar, Farhan | -45791 | 13
105-121 | Al-Bahr 115/13.8kv Substation | 6651 | Al-Bahr 115/13.8kv Substation-Transformer Oil DGA Analysis (Lab Testing) as per SEC-CSD requirment | APPROVED | No | 2025-05-19 | Abas, Mohammed Fekry | 2025-05-25 | 2025-05-26 |  |  | Transformer Oil DGA Analysis (Lab Testing) as per SEC-CSD requirment | 35000 | 7478 | 0 | STANDARD | Saudi Arabian Engineering Company | SAR | 35000 | APPROVED |  |  | 2025-07-20 | 0 | 55 | Abdulqader, Ahmed Abdulhalim | -45803 | 55
105-121 | Al-Bahr 115/13.8kv Substation | 6701 | Al-Bahr 115/13.8kv Substation-Grounding Accessories | APPROVED | No | 2025-05-25 | Abas, Mohammed Fekry | 2025-05-29 | 2025-05-29 |  |  | Line item 2.21 Grounding Accessories | 45118.2 | 7077 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 45118.2 | APPROVED |  |  | 2025-06-22 | 0 | 24 | Abdulqader, Ahmed Abdulhalim | -45806 | 24
105-121 | Al-Bahr 115/13.8kv Substation | 6972 | Al-Bahr 115/13.8kv Substation-Manpower for Testing and Commissioning | APPROVED | No | 2025-07-02 | Abas, Mohammed Fekry | 2025-07-06 | 2025-07-07 |  |  | Line item 2.31 Manpower for Testing and Commissioning | 80000 | 7507 | 0 | STANDARD | Jasem M.AlJasem Contracting Est. | SAR | 80000 | APPROVED |  |  | 2025-07-27 | 0 | 20 | Babic, Marian | -45845 | 20
105-121 | Al-Bahr 115/13.8kv Substation | 6997 | Al-Bahr 115/13.8kv Substation-Transforemr Oil Tesitng (As per CSD Requirement) | APPROVED | No | 2025-07-07 | Abas, Mohammed Fekry | 2025-07-12 | 2025-07-12 |  |  | Initially, we have created PR (6651) with the value of 35,000. Now our DPO value is increased. Therefore I am creating new PR with the value of 2300. | 2300 | 7478 | 0 | STANDARD | Saudi Arabian Engineering Company | SAR | 2300 | APPROVED |  |  | 2025-07-20 | 0 | 8 | Abdulqader, Ahmed Abdulhalim | -45850 | 8
105-121 | Al-Bahr 115/13.8kv Substation | 7032 | Al-Bahr 115/13.8kv Substation-On Site FDT Testing By SAFCO | RETURNED | No | 2025-07-09 | Tananeh, Khalid Jamal | 2025-09-22 | 2025-07-14 | 2025-09-22 |  | "The PR are being returned in reference to the email sent on Tuesday, 09/09/2025 at 4:14 PM, as the works were carried out without prior approval from the Procurement Department and the payment shall be made from petty cash." | 27000 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45852 | -45852
105-121 | Al-Bahr 115/13.8kv Substation | 7035 | Al-Bahr 115/13.8kv Substation-MV & HV Cable Supports | APPROVED | No | 2025-07-09 | Abas, Mohammed Fekry | 2025-07-13 | 2025-07-14 |  |  | Line item 2.13 MV and HV Cable Supports | 118888.7 | 7298 | 0 | STANDARD | ISAM KABBANI &Partners | SAR | 118888.7 | APPROVED |  |  | 2025-08-02 | 0 | 19 | Hegazy, Ayman | -45852 | 19
105-121 | Al-Bahr 115/13.8kv Substation | 7051 | Al-Bahr 115/13.8kv Substation-MV Cable Clamps | APPROVED | No | 2025-07-09 | Abas, Mohammed Fekry | 2025-07-13 | 2025-07-14 |  |  | MV Cables Clamps Line item 2.13 | 56525 | 7265 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 56525 | APPROVED |  |  | 2025-07-27 | 0 | 13 | Hegazy, Ayman | -45852 | 13
105-121 | Al-Bahr 115/13.8kv Substation | 7099 | Al-Bahr 115/13.8kv Substation-PDS System | REJECTED | No | 2025-07-15 | Khan, Muhammad Safdar | 2025-07-16 | 2025-07-16 |  | 2025-07-17 |  | 250000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45854 | -45854
105-121 | Al-Bahr 115/13.8kv Substation | 7137 | Al-Bahr 115/13.8kv Substation-6 AC's 5 Ton (4 Fixed and 2 Mobile AC's) | REJECTED | No | 2025-07-17 | Issa, Amr Ali | 2025-07-30 | 2025-07-23 |  | 2025-07-30 |  | 42000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45861 | -45861
105-121 | Al-Bahr 115/13.8kv Substation | 7178 | Al-Bahr 115/13.8kv Substation-Design, Supply and Installation of Lighting Control System | RETURNED | No | 2025-07-21 | Muaz, Alaa | 2025-09-09 | 2025-07-27 | 2025-09-09 |  | The budget is not sufficient | 60271 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -45865 | -45865
105-121 | Al-Bahr 115/13.8kv Substation | 7220 | Al-Bahr 115/13.8kv Substation-DC DB for Telecom | APPROVED | No | 2025-07-27 | Abas, Mohammed Fekry | 2025-08-03 | 2025-08-03 |  |  | DC DB for Telecom | 50000 | 7606 | 0 | STANDARD | HAWA ELECTRIC PANEL BOARD FAC | SAR | 29700 | APPROVED |  |  | 2025-08-17 | 20300 | 14 | Abuhammad, Samir | -45872 | 14
105-121 | Al-Bahr 115/13.8kv Substation | 7224 | Al-Bahr 115/13.8kv Substation-1x500mm2 LV Cables | RETURNED | No | 2025-07-27 | Mohammed, Mohammed Adel Fahmy | 2026-01-15 | 2025-08-03 | 2026-01-15 |  | Not Have POCR Until Now and PR incorrect qty. | 78750 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Mohammed Adel Fahmy | -45872 | -45872
105-121 | Al-Bahr 115/13.8kv Substation | 7233 | Al-Bahr 115/13.8kv Substation-Extra THNN Wires | APPROVED | No | 2025-07-28 | Abas, Mohammed Fekry | 2025-08-03 | 2025-08-03 |  |  | Extra THNN Wires | 43390 | 7810 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 44046.76 | IN PROCESS | 2026-01-15 | 2026-01-19 |  | -656.76 | 182 | Mohammed, Mohammed Adel Fahmy | 169 | -45872
105-121 | Al-Bahr 115/13.8kv Substation | 7233 | Al-Bahr 115/13.8kv Substation-Extra THNN Wires | APPROVED | No | 2025-07-28 | Abas, Mohammed Fekry | 2025-08-03 | 2025-08-03 |  |  | Extra THNN Wires | 43390 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -45872 | -45872
105-121 | Al-Bahr 115/13.8kv Substation | 7260 | Al-Bahr 115/13.8kv Substation-Feul for Site Generator | APPROVED | No | 2025-08-03 | Abas, Mohammed Fekry | 2025-08-10 | 2025-08-10 |  |  | Line item 2.33 Diesel for ALBAHR Site Generator | 100000 | 7602 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 99999.86 | APPROVED |  |  | 2025-08-21 | 0.14 | 11 | Akhtar, Farhan | -45879 | 11
105-121 | Al-Bahr 115/13.8kv Substation | 7282 | Al-Bahr 115/13.8kv Substation-Water Proofing | APPROVED | No | 2025-08-04 | Abas, Mohammed Fekry | 2025-08-10 | 2025-08-10 |  |  | Line item 2.20 Water Proofing | 27305 | 5651 | 1 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 27302.47 | APPROVED |  |  | 2025-09-29 | 2.53 | 50 | Tananeh, Khalid Jamal | -45879 | 50
105-121 | Al-Bahr 115/13.8kv Substation | 7309 | Al-Bahr 115/13.8kv Substation-2 Number of 5 Ton AC's (Mobile) | RETURNED | No | 2025-08-06 |  |  | 2025-08-10 | 2026-01-11 |  | Not Required the AC's | 22000 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45879 | -45879
105-121 | Al-Bahr 115/13.8kv Substation | 7310 | Al-Bahr 115/13.8kv Substation-Control Cables For Bayouniah SS | RETURNED | No | 2025-08-06 | Mohammed, Mohammed Adel Fahmy | 2026-01-15 | 2025-08-18 | 2026-01-15 |  | Not Have POCR Until Now and PR incorrect qty. | 147000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Mohammed Adel Fahmy | -45887 | -45887
105-121 | Al-Bahr 115/13.8kv Substation | 7357 | Al-Bahr 115/13.8kv Substation-Supply of the Raw Water | APPROVED | No | 2025-08-14 | Abas, Mohammed Fekry | 2025-08-17 | 2025-08-18 |  |  | Line item 2.33 Supply of Raw Water. | 9000 | 6376 | 2 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 9000 | APPROVED |  |  | 2025-08-25 | 0 | 7 | Akhtar, Farhan | -45887 | 7
105-121 | Al-Bahr 115/13.8kv Substation | 7414 | Asphalt and Steel boundary fence | REJECTED | No | 2025-08-21 | Sherif, Marwa | 2025-08-25 | 2025-08-21 |  | 2025-08-27 |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45890 | -45890
105-121 | Al-Bahr 115/13.8kv Substation | 7418 | Hazardous Waste Collection | REJECTED | No | 2025-08-21 | Sherif, Marwa | 2025-08-25 | 2025-08-24 |  | 2025-08-27 |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45893 | -45893
105-121 | Al-Bahr 115/13.8kv Substation | 7427 | Wiring Devices | APPROVED | No | 2025-08-23 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | Line item 2.23 Wiring Devices. Previous PR was returned That'swhy created New PR | 0 | 7166 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 99975 | APPROVED |  |  | 2025-09-10 | -99975 | 16 | Muaz, Alaa | -45894 | 16
105-121 | Al-Bahr 115/13.8kv Substation | 7430 | PDS System | APPROVED | No | 2025-08-23 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | Line item 2.5 PDS for ALBAHR SS | 0 | 7766 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 140000 | APPROVED |  |  | 2025-11-18 | -140000 | 85 | Hegazy, Ayman | -45894 | 85
105-121 | Al-Bahr 115/13.8kv Substation | 7513 | Rental Technicaians | REJECTED | No | 2025-08-26 | Shahin, Hassan Magdy Hassan | 2025-08-26 |  |  | 2025-08-27 | Line item 2.31. Rental Technicians for Three Months | 3 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-121 | Al-Bahr 115/13.8kv Substation | 7526 | Asphalt and Steel Boundary Fence | REJECTED | No | 2025-08-27 | Shahin, Hassan Magdy Hassan | 2025-08-27 |  |  | 2025-08-27 | Line item 2.20 Asphalt Works and Steel boundary Fence | 2 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-121 | Al-Bahr 115/13.8kv Substation | 7535 | Lugs and Glands | APPROVED | No | 2025-08-27 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-03 |  |  | Line item 2.13 Lugs and Glands | 0 | 7579 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 19640.3 | APPROVED |  |  | 2025-09-16 | -19640.3 | 13 | Abdulqader, Ahmed Abdulhalim | -45903 | 13
105-121 | Al-Bahr 115/13.8kv Substation | 7575 | Asphalt and Steel Boundary Fence | REJECTED | No | 2025-08-31 | Sherif, Marwa | 2025-08-31 | 2025-08-31 |  | 2025-09-02 |  | 2 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45900 | -45900
105-121 | Al-Bahr 115/13.8kv Substation | 7609 | Hazardous Waste.Rental per Skip | REJECTED | No | 2025-09-01 | Sherif, Marwa | 2025-09-03 | 2025-09-03 |  | 2025-09-08 |  | 7 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45903 | -45903
105-121 | Al-Bahr 115/13.8kv Substation | 7628 | Steel Boundary Fence and Asphalt Works | REJECTED | No | 2025-09-03 | Sherif, Marwa | 2025-09-03 | 2025-09-03 |  | 2025-09-08 |  | 2 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45903 | -45903
105-121 | Al-Bahr 115/13.8kv Substation | 7715 | Rental Technician | APPROVED | No | 2025-09-10 | Abas, Mohammed Fekry | 2025-09-16 | 2025-09-18 |  |  | 10 Number of Rental Technician required for Three Months | 0 | 7507 | 1 | STANDARD | Jasem M.AlJasem Contracting Est. | SAR | 156000 | APPROVED |  |  | 2025-10-16 | -156000 | 28 | Babic, Marian | -45918 | 28
105-121 | Al-Bahr 115/13.8kv Substation | 7783 | Office Furniture | APPROVED | No | 2025-09-17 | Abas, Mohammed Fekry | 2025-09-29 | 2025-10-02 |  |  | Line item 2.33 Office Furniture. DPO already finalized for Dammam 16 SS | 0 | 7704 | 0 | STANDARD | ALISMAIL INDUSTRIAL CO.(S) | SAR | 14440 | APPROVED |  |  | 2025-10-14 | -14440 | 12 | Abdulqader, Ahmed Abdulhalim | -45932 | 12
105-121 | Al-Bahr 115/13.8kv Substation | 7901 | Office Furniture | APPROVED | No | 2025-10-05 | Abas, Mohammed Fekry | 2025-10-08 | 2025-10-08 |  |  | Line item 2.33 Office Furniture. PO already finalized. Previously one PR (7783) was created. One line item was missing. This PR is belong to the remaining Qty. | 0 | 7704 | 0 | STANDARD | ALISMAIL INDUSTRIAL CO.(S) | SAR | 3150 | APPROVED |  |  | 2025-10-14 | -3150 | 6 | Abdulqader, Ahmed Abdulhalim | -45938 | 6
105-121 | Al-Bahr 115/13.8kv Substation | 7934 | Lighting Control System | APPROVED | No | 2025-10-08 | Abas, Mohammed Fekry | 2025-10-13 | 2025-10-13 |  |  | Line item 2.22 Lighting Control System | 0 | 7335 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 68054 | APPROVED |  |  | 2025-10-21 | -68054 | 8 | Muaz, Alaa | -45943 | 8
105-121 | Al-Bahr 115/13.8kv Substation | 8019 | Diesel for the Site Generator | RETURNED | No | 2025-10-21 | Akhtar, Farhan | 2026-01-18 | 2025-10-27 | 2026-01-18 |  | Resubmit the PR once POCR is approved | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45957 | -45957
105-121 | Al-Bahr 115/13.8kv Substation | 8044 | Steel Fence and Asphalt | APPROVED | No | 2025-10-23 | Abas, Mohammed Fekry | 2025-10-27 | 2025-10-27 |  |  | Line item 2.20 Asphalt and Steel Boundary Fence | 0 | 5643 | 1 | STANDARD | Suliman Ahmad Khader General Contracting Est (SAK) | SAR | 1270000 | APPROVED |  |  | 2025-11-10 | -1270000 | 14 | Tananeh, Khalid Jamal | -45957 | 14
105-121 | Al-Bahr 115/13.8kv Substation | 8158 | Waste Management | REJECTED | No | 2025-11-09 | Sherif, Marwa | 2025-11-20 | 2025-11-10 |  | 2025-11-20 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -45971 | -45971
105-121 | Al-Bahr 115/13.8kv Substation | 8252 | Motor for ALBAHR SS Gate | APPROVED | No | 2025-11-18 | Abas, Mohammed Fekry | 2025-11-20 | 2025-11-23 |  |  | Line Item 2.20 Motors for ALBAHR SS Gate | 0 | 7980 | 0 | STANDARD | ALMOSALLAMY INDUSTRIAL COMPANY | SAR | 9330 | APPROVED |  |  | 2025-12-25 | -9330 | 32 | Abdelraouf, Islam ِAdel Hanafy | -45984 | 32
105-121 | Al-Bahr 115/13.8kv Substation | 8326 | Line item 2.33 Waste Management System | APPROVED | No | 2025-11-23 | Abas, Mohammed Fekry | 2025-11-27 | 2025-11-29 |  |  | Line item 2.33 Waste Management System | 0 | 6522 | 1 | STANDARD | Cebent for General Cont. Est. | SAR | 11200 | APPROVED |  |  | 2025-12-31 | -11200 | 32 | Akhtar, Farhan | -45990 | 32
105-121 | Al-Bahr 115/13.8kv Substation | 8460 | Standalone ACs 5 tons | REJECTED | No | 2025-12-07 | Shahin, Hassan Magdy Hassan | 2025-12-07 |  |  | 2025-12-07 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-121 | Al-Bahr 115/13.8kv Substation | 8515 | 12 Rental Technician for Testing | APPROVED | No | 2025-12-14 | Abas, Mohammed Fekry | 2026-01-26 | 2026-01-27 |  |  | Line item 2.31, 12 Rental Technician required for 3 Months to complete Testing Activity | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46049 | -46049
105-121 | Al-Bahr 115/13.8kv Substation | 8652 | Metal Doors (Change Order) - Al Bahr | APPROVED | No | 2026-01-05 | Abas, Mohammed Fekry | 2026-01-26 | 2026-01-27 |  |  | Budget line 2.20 - Civil works | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46049 | -46049
105-121 | Al-Bahr 115/13.8kv Substation | 8731 | Supply of Diesel Generators | APPROVED | No | 2026-01-19 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46050 | -46050
105-122 | Abu Maan 115/13.8kV Substation | 2044 | Abu Maan 115/13.8kV Substation-Abu Maan Engineering & Design | APPROVED | No | 2023-12-26 | Abas, Mohammed Fekry | 2023-12-28 | 2023-12-28 |  |  |  | 581250 | 4905 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 581250 | APPROVED |  |  | 2024-03-17 | 0 | 80 | Kumar, Mr. Ranjan | -45288 | 80
105-122 | Abu Maan 115/13.8kV Substation | 2053 | Abu Maan 115/13.8kV Substation-Abu Maan -13.8kV Switch Gear | APPROVED | No | 2023-12-28 | Abas, Mohammed Fekry | 2024-01-01 | 2024-01-01 |  |  |  | 8210000 | 4871 | 0 | STANDARD | ALFANAR CO | SAR | 8210000 | APPROVED |  |  | 2024-01-18 | 0 | 17 | Alhadi, Khalid | -45292 | 17
105-122 | Abu Maan 115/13.8kV Substation | 2063 | Abu Maan 115/13.8kV Substation-C&P,SAS for ABU MAAN SS | APPROVED | No | 2023-12-31 | Abas, Mohammed Fekry | 2024-01-02 | 2024-01-02 |  |  |  | 9090000 | 4854 | 0 | STANDARD | ALFANAR CO | SAR | 9090000 | APPROVED |  |  | 2024-01-21 | 0 | 19 | Kumar, Mr. Ranjan | -45293 | 19
105-122 | Abu Maan 115/13.8kV Substation | 2117 | Abu Maan 115/13.8kV Substation-Temporary Project Sign Board | APPROVED | No | 2024-01-08 | Abas, Mohammed Fekry | 2024-01-09 | 2024-01-09 |  |  |  | 20000 | 4965 | 0 | STANDARD | Construction Expertise Est. | SAR | 20000 | APPROVED |  |  | 2024-01-21 | 0 | 12 | Alhadi, Khalid | -45300 | 12
105-122 | Abu Maan 115/13.8kV Substation | 2237 | Abu Maan 115/13.8kV Substation-Cyber Security | APPROVED | No | 2024-01-21 | Abas, Mohammed Fekry | 2024-01-22 | 2024-01-22 |  |  |  | 1000000 | 5066 | 0 | STANDARD | ALFANAR CO | SAR | 1000000 | APPROVED |  |  | 2024-02-20 | 0 | 29 | Babic, Marian | -45313 | 29
105-122 | Abu Maan 115/13.8kV Substation | 2345 | Abu Maan 115/13.8kV Substation-Engineering & Design Services | APPROVED | No | 2024-01-29 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 48750 | 4905 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 48750 | APPROVED |  |  | 2024-03-17 | 0 | 42 | Kumar, Mr. Ranjan | -45326 | 42
105-122 | Abu Maan 115/13.8kV Substation | 2458 | Abu Maan 115/13.8kV Substation-Site Office Facility | APPROVED | No | 2024-02-06 | Abas, Mohammed Fekry | 2024-02-07 | 2024-02-10 |  |  |  | 175000 | 5157 | 0 | STANDARD | Construction Expertise Est. | SAR | 175000 | APPROVED |  |  | 2024-03-27 | 0 | 46 | Muhammad, Muhammad Atif | -45332 | 46
105-122 | Abu Maan 115/13.8kV Substation | 2462 | Abu Maan 115/13.8kV Substation-Main AC&DC Panel Boards with Sub Panels | APPROVED | No | 2024-02-06 | Abas, Mohammed Fekry | 2024-02-07 | 2024-02-10 |  |  |  | 450000 | 5352 | 0 | STANDARD | ALFANAR CO | SAR | 450000 | APPROVED |  |  | 2024-04-28 | 0 | 78 | Mohammed, Faisal Ansari | -45332 | 78
105-122 | Abu Maan 115/13.8kV Substation | 2519 | Abu Maan 115/13.8kV Substation-Geotechnical Investigation | APPROVED | No | 2024-02-11 | Abas, Mohammed Fekry | 2024-02-11 | 2024-02-12 |  |  |  | 16000 | 5245 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 10742 | APPROVED |  |  | 2024-03-20 | 5258 | 37 | Alhadi, Khalid | -45334 | 37
105-122 | Abu Maan 115/13.8kV Substation | 2532 | Abu Maan 115/13.8kV Substation-Super Structure Precast including Fire Walls | APPROVED | No | 2024-02-12 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-19 |  |  |  | 2421479 | 5394 | 0 | STANDARD | Factory of Ideal Precast Concrete System Company | SAR | 1921165 | APPROVED |  |  | 2024-05-07 | 500314 | 78 | Tananeh, Khalid Jamal | -45341 | 78
105-122 | Abu Maan 115/13.8kV Substation | 2628 | Abu Maan 115/13.8kV Substation-Excavation in Normal soil and Balidiyah Disposal | APPROVED | No | 2024-02-20 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 23400 | 5270 | 0 | STANDARD | Eastern Union Contracting Est | SAR | 23400 | APPROVED |  |  | 2024-04-15 | 0 | 49 | Alhadi, Khalid | -45348 | 49
105-122 | Abu Maan 115/13.8kV Substation | 2633 | Abu Maan 115/13.8kV Substation-Site Office facility | APPROVED | No | 2024-02-20 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 35778 | 5157 | 0 | STANDARD | Construction Expertise Est. | SAR | 34900 | APPROVED |  |  | 2024-03-27 | 878 | 30 | Muhammad, Muhammad Atif | -45348 | 30
105-122 | Abu Maan 115/13.8kV Substation | 2746 | Abu Maan 115/13.8kV Substation-Main AC/DC Panel Boards Including Sub DB's, Indoor and Outdoor Lighting Panels | APPROVED | No | 2024-03-04 | Abas, Mohammed Fekry | 2024-03-05 | 2024-03-07 |  |  |  | 420000 | 5352 | 0 | STANDARD | ALFANAR CO | SAR | 420000 | APPROVED |  |  | 2024-04-28 | 0 | 52 | Mohammed, Faisal Ansari | -45358 | 52
105-122 | Abu Maan 115/13.8kV Substation | 2757 | Abu Maan 115/13.8kV Substation-Single Grider Over Head Travelling Crane, Grider Length :11.515Mtr, 5Ton | APPROVED | No | 2024-03-04 | Abas, Mohammed Fekry | 2024-03-05 | 2024-03-07 |  |  |  | 130000 | 5470 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 126870 | APPROVED |  |  | 2024-05-16 | 3130 | 70 | Muhammad, Muhammad Atif | -45358 | 70
105-122 | Abu Maan 115/13.8kV Substation | 2858 | Abu Maan 115/13.8kV Substation-1000mm thick with Aggregate SUB BASEclass-"A(1A)" with CBR not less than 50 | APPROVED | No | 2024-03-20 | Abas, Mohammed Fekry | 2024-03-21 | 2024-03-24 |  |  |  | 49500 | 5270 | 0 | STANDARD | Eastern Union Contracting Est | SAR | 49500 | APPROVED |  |  | 2024-04-15 | 0 | 22 | Alhadi, Khalid | -45375 | 22
105-122 | Abu Maan 115/13.8kV Substation | 2859 | Abu Maan 115/13.8kV Substation-600mm thick Aggregate BASE COARSE (crashed stones) class-"A(1A) or A(1B)" with CBR not less than 100 | APPROVED | No | 2024-03-20 | Abas, Mohammed Fekry | 2024-03-21 | 2024-03-24 |  |  |  | 29700 | 5270 | 0 | STANDARD | Eastern Union Contracting Est | SAR | 29700 | APPROVED |  |  | 2024-04-15 | 0 | 22 | Alhadi, Khalid | -45375 | 22
105-122 | Abu Maan 115/13.8kV Substation | 2861 | Abu Maan 115/13.8kV Substation-General Backfilling | APPROVED | No | 2024-03-20 | Abas, Mohammed Fekry | 2024-03-21 | 2024-03-24 |  |  |  | 165000 | 5270 | 0 | STANDARD | Eastern Union Contracting Est | SAR | 165000 | APPROVED |  |  | 2024-04-15 | 0 | 22 | Alhadi, Khalid | -45375 | 22
105-122 | Abu Maan 115/13.8kV Substation | 2895 | Abu Maan 115/13.8kV Substation-Topographic Survey of Project Area | APPROVED | No | 2024-03-25 | Abas, Mohammed Fekry | 2024-03-27 | 2024-03-28 |  |  |  | 5125 | 5375 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 5125 | APPROVED |  |  | 2024-04-28 | 0 | 31 | Alhadi, Khalid | -45379 | 31
105-122 | Abu Maan 115/13.8kV Substation | 3131 | Abu Maan 115/13.8kV Substation-Supply & Apply of Roof Waterproofing System & Underground Waterproofing System | APPROVED | No | 2024-04-25 | Abas, Mohammed Fekry | 2024-04-25 | 2024-04-28 |  |  |  | 355000 | 5661 | 0 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 347826.5 | APPROVED |  |  | 2024-06-13 | 7173.5 | 46 | Tananeh, Khalid Jamal | -45410 | 46
105-122 | Abu Maan 115/13.8kV Substation | 3358 | Abu Maan 115/13.8kV Substation-Rentel Generator, 400kVA, 3Ph, 380V, 60Hz, for 3 Months | APPROVED | No | 2024-05-09 | Abas, Mohammed Fekry | 2024-05-12 | 2024-05-13 |  |  |  | 34998 | 5542 | 0 | STANDARD | Nour Communications Co. | SAR | 28500 | APPROVED |  |  | 2024-05-21 | 6498 | 8 | Akhtar, Farhan | -45425 | 8
105-122 | Abu Maan 115/13.8kV Substation | 3363 | Abu Maan 115/13.8kV Substation-Electronic Materials requirments for Site Office | APPROVED | No | 2024-05-09 | Abas, Mohammed Fekry | 2024-05-16 | 2024-05-17 |  |  |  | 33800 | 5615 | 0 | STANDARD | Construction Expertise Est. | SAR | 33800 | APPROVED |  |  | 2024-06-03 | 0 | 17 | Muhammad, Muhammad Atif | -45429 | 17
105-122 | Abu Maan 115/13.8kV Substation | 3380 | Abu Maan 115/13.8kV Substation-150Sq.mm Tinned Copper Conductor | APPROVED | No | 2024-05-12 | Abas, Mohammed Fekry | 2024-05-16 | 2024-05-17 |  |  |  | 38500 | 5362 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 38455.41 | APPROVED |  |  | 2024-05-27 | 44.59 | 10 | Muhammad, Muhammad Atif | -45429 | 10
105-122 | Abu Maan 115/13.8kV Substation | 3445 | Abu Maan 115/13.8kV Substation-Site Temporary Fence, Gate & Security Cabin | APPROVED | No | 2024-05-20 | Abas, Mohammed Fekry | 2024-05-22 | 2024-05-23 |  |  |  | 88200 | 5616 | 0 | STANDARD | Construction Expertise Est. | SAR | 85920 | APPROVED |  |  | 2024-06-03 | 2280 | 11 | Alhadi, Khalid | -45435 | 11
105-122 | Abu Maan 115/13.8kV Substation | 3518 | Abu Maan 115/13.8kV Substation-Batteries & Chargers | APPROVED | No | 2024-05-28 | Abas, Mohammed Fekry | 2024-05-29 | 2024-05-29 |  |  |  | 550000 | 5747 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 457000 | APPROVED |  |  | 2024-07-09 | 93000 | 41 | Muhammad, Muhammad Atif | -45441 | 41
105-122 | Abu Maan 115/13.8kV Substation | 3658 | Abu Maan 115/13.8kV Substation-Grounding Material and Accessories | APPROVED | No | 2024-06-13 | Issa, Amr Ali | 2024-07-02 | 2024-07-03 |  |  |  | 73475 | 5565 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 72850 | APPROVED |  |  | 2024-07-12 | 625 | 9 | Muhammad, Muhammad Atif | -45476 | 9
105-122 | Abu Maan 115/13.8kV Substation | 3697 | Abu Maan 115/13.8kV Substation-Supply of Non Potable Water for Site offices Use | APPROVED | No | 2024-06-30 | Abas, Mohammed Fekry | 2024-07-05 | 2024-07-07 |  |  |  | 18000 | 5839 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 16800 | APPROVED |  |  | 2024-08-01 | 1200 | 25 | Akhtar, Farhan | -45480 | 25
105-122 | Abu Maan 115/13.8kV Substation | 3699 | Abu Maan 115/13.8kV Substation-Testing for Plate Load Test - 4 Points | APPROVED | No | 2024-06-30 | Abas, Mohammed Fekry | 2024-07-05 | 2024-07-07 |  |  |  | 8400 | 5803 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 7540 | APPROVED |  |  | 2024-10-13 | 860 | 98 | Tananeh, Khalid Jamal | -45480 | 98
105-122 | Abu Maan 115/13.8kV Substation | 3702 | Abu Maan 115/13.8kV Substation-Supply of Diesel for Generator at Site | APPROVED | No | 2024-06-30 | Abas, Mohammed Fekry | 2024-07-05 | 2024-07-07 |  |  |  | 9000 | 5794 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 9000 | APPROVED |  |  | 2024-07-18 | 0 | 11 | Akhtar, Farhan | -45480 | 11
105-122 | Abu Maan 115/13.8kV Substation | 3726 | Abu Maan 115/13.8kV Substation-13.8kV MV Power Cable | APPROVED | No | 2024-07-01 | Abas, Mohammed Fekry | 2024-07-07 | 2024-07-08 |  |  |  | 1069560 | 6030 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 956014.2 | APPROVED |  |  | 2024-10-09 | 113545.8 | 93 | Badhman, Saeed | -45481 | 93
105-122 | Abu Maan 115/13.8kV Substation | 3790 | Abu Maan 115/13.8kV Substation-Garbage Waste Container, 12 Cu. M (1-year) | APPROVED | No | 2024-07-07 | Abas, Mohammed Fekry | 2024-07-09 | 2024-07-09 |  |  |  | 28800 | 5921 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 19200 | APPROVED |  |  | 2024-08-20 | 9600 | 42 | Akhtar, Farhan | -45482 | 42
105-122 | Abu Maan 115/13.8kV Substation | 3862 | Abu Maan 115/13.8kV Substation-Control Cables | APPROVED | No | 2024-07-12 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 716000 | 5833 | 0 | STANDARD | ALFANAR CO | SAR | 531752.8 | APPROVED |  |  | 2024-08-28 | 184247.2 | 43 | Muhammad, Muhammad Atif | -45489 | 43
105-122 | Abu Maan 115/13.8kV Substation | 3916 | Abu Maan 115/13.8kV Substation-RTV Coating for Transformer HV Busings and GIB HV Bushings | APPROVED | No | 2024-07-16 | Malek, Warren | 2024-07-25 | 2024-07-25 |  |  |  | 250000 | 6185 | 0 | STANDARD | SAUDI CONDUIT COATING CO. (S3C) | SAR | 35268 | APPROVED |  |  | 2024-10-13 | 214732 | 80 | Muaz, Alaa | -45498 | 80
105-122 | Abu Maan 115/13.8kV Substation | 3920 | Abu Maan 115/13.8kV Substation-Testing & Commissioning Works | APPROVED | No | 2024-07-16 | Malek, Warren | 2024-07-25 | 2024-07-25 |  |  |  | 2012387 | 6454 | 0 | STANDARD | Al Fanar Technical Services | SAR | 1955859 | APPROVED |  |  | 2025-02-25 | 56528 | 215 | Alqadhi, Abdulrahman Abdulghani | -45498 | 215
105-122 | Abu Maan 115/13.8kV Substation | 3924 | Abu Maan 115/13.8kV Substation-MV Termination Kits | APPROVED | No | 2024-07-16 | Malek, Warren | 2024-07-25 | 2024-07-25 |  |  |  | 98839 | 5993 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 95871.89 | APPROVED |  |  | 2024-09-19 | 2967.11 | 56 | Badhman, Saeed | -45498 | 56
105-122 | Abu Maan 115/13.8kV Substation | 4073 | Abu Maan 115/13.8kV Substation-Lighting Cum Lightning Mast | APPROVED | No | 2024-08-01 | Abas, Mohammed Fekry | 2024-08-03 | 2024-08-04 |  |  |  | 59075 | 6036 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 59075 | APPROVED |  |  | 2024-10-07 | 0 | 64 | Badhman, Saeed | -45508 | 64
105-122 | Abu Maan 115/13.8kV Substation | 4199 | Abu Maan 115/13.8kV Substation-Hazardous and Non Hazardous Waste Collection | APPROVED | No | 2024-08-19 | Issa, Amr Ali | 2024-08-25 | 2024-08-25 |  |  |  | 5000 | 6131 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 3650 | APPROVED |  |  | 2024-09-19 | 1350 | 25 | Akhtar, Farhan | -45529 | 25
105-122 | Abu Maan 115/13.8kV Substation | 4221 | Abu Maan 115/13.8kV Substation-LV AC/DC Cables and Lighting Wires | APPROVED | No | 2024-08-19 | Issa, Amr Ali | 2024-08-25 | 2024-08-25 |  |  |  | 1611070 | 6088 | 0 | STANDARD | ALFANAR CO | SAR | 1110509.38 | APPROVED |  |  | 2024-10-06 | 500560.62 | 42 | Badhman, Saeed | -45529 | 42
105-122 | Abu Maan 115/13.8kV Substation | 4241 | Abu Maan 115/13.8kV Substation-Grounding Conductor and Cables | APPROVED | No | 2024-08-21 | Abas, Mohammed Fekry | 2024-08-27 | 2024-09-01 |  |  |  | 244150 | 6072 | 0 | STANDARD | ALFANAR CO | SAR | 226756.52 | APPROVED |  |  | 2024-09-18 | 17393.48 | 17 | Muhammad, Muhammad Atif | -45536 | 17
105-122 | Abu Maan 115/13.8kV Substation | 4363 | Abu Maan 115/13.8kV Substation-Station Service Transformer 750kVA | APPROVED | No | 2024-09-04 | Abas, Mohammed Fekry | 2024-09-09 | 2024-09-09 |  |  |  | 164000 | 5916 | 0 | STANDARD | ALFANAR CO | SAR | 164000 | APPROVED |  |  | 2024-10-08 | 0 | 29 | Muhammad, Muhammad Atif | -45544 | 29
105-122 | Abu Maan 115/13.8kV Substation | 4443 | Abu Maan 115/13.8kV Substation-Fire Alarm & Fire Suppression System | APPROVED | No | 2024-09-14 | Abas, Mohammed Fekry | 2024-09-17 | 2024-09-17 |  |  |  | 2095567 | 5996 | 0 | STANDARD | Reda Trading & Development Co. for Machinery & Equipment Ltd(S) | SAR | 2095567 | APPROVED |  |  | 2024-09-26 | 0 | 9 | Muhammad, Muhammad Atif | -45552 | 9
105-122 | Abu Maan 115/13.8kV Substation | 4447 | Abu Maan 115/13.8kV Substation-Cable Ladder, Tray and Other Accesories | APPROVED | No | 2024-09-14 | Abas, Mohammed Fekry | 2024-09-17 | 2024-09-18 |  |  |  | 460016.15 | 6154 | 0 | STANDARD | Electrolink Co Ltd | SAR | 459950.59 | APPROVED |  |  | 2024-10-08 | 65.56 | 20 | Muhammad, Muhammad Atif | -45553 | 20
105-122 | Abu Maan 115/13.8kV Substation | 4594 | Abu Maan 115/13.8kV Substation-Electrical Installation - Contract | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-09 |  |  |  | 2992521 | 6372 | 0 | STANDARD | Hussain Ali Hussain Contracting Company | SAR | 2352585 | APPROVED |  |  | 2025-01-07 | 639936 | 90 | Muhammad, Muhammad Atif | -45574 | 90
105-122 | Abu Maan 115/13.8kV Substation | 4754 | Abu Maan 115/13.8kV Substation-Complete Substation HVAC System Works | APPROVED | No | 2024-10-21 | Abas, Mohammed Fekry | 2024-11-04 | 2024-11-04 |  |  |  | 2220000 | 6213 | 0 | STANDARD | Hamad Fahad Al Awad for Contracting Est | SAR | 2025000 | APPROVED |  |  | 2024-11-14 | 195000 | 10 | Muhammad, Muhammad Atif | -45600 | 10
105-122 | Abu Maan 115/13.8kV Substation | 4914 | Abu Maan 115/13.8kV Substation-Sewage Water Removal Services, 10000 Ltrs - 10 Trips | INCOMPLETE | No |  | Abdel Naiem, Tarek Ali | 2024-11-12 |  |  |  |  | 7000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-122 | Abu Maan 115/13.8kV Substation | 4924 | Abu Maan 115/13.8kV Substation-Sewage Water Removal Services, 10000 Ltrs - 10 Trips | APPROVED | No | 2024-11-13 | Abas, Mohammed Fekry | 2024-11-20 | 2024-11-20 |  |  |  | 3500 | 6541 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 3000 | APPROVED |  |  | 2024-12-01 | 500 | 11 | Akhtar, Farhan | -45616 | 11
105-122 | Abu Maan 115/13.8kV Substation | 4962 | Abu Maan 115/13.8kV Substation-2.22 Indoor & Outdoor Lighting Fixtures | APPROVED | No | 2024-11-16 | Abas, Mohammed Fekry | 2024-11-20 | 2024-11-20 |  |  |  | 71998 | 6478 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 71998 | APPROVED |  |  | 2024-11-28 | 0 | 8 | Muhammad, Muhammad Atif | -45616 | 8
105-122 | Abu Maan 115/13.8kV Substation | 5128 | Abu Maan 115/13.8kV Substation-150 Sq.mm Tinned Copper Conductor | APPROVED | No | 2024-12-04 | Abas, Mohammed Fekry | 2024-12-05 | 2024-12-08 |  |  |  | 79800 | 6760 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 73839.36 | APPROVED |  |  | 2025-02-24 | 5960.64 | 78 | Alhadi, Khalid | -45634 | 78
105-122 | Abu Maan 115/13.8kV Substation | 5195 | Abu Maan 115/13.8kV Substation-HV Clamps & Connectors / Terminal Hardwares | APPROVED | No | 2024-12-08 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-12 |  |  |  | 4616 | 6425 | 0 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 4505.16 | APPROVED |  |  | 2025-01-02 | 110.84 | 21 | Mohammed, Faisal Ansari | -45638 | 21
105-122 | Abu Maan 115/13.8kV Substation | 5249 | Abu Maan 115/13.8kV Substation-Complete scope of Civil and Architectural Works - Main Scope Only | APPROVED | No | 2024-12-22 | Abas, Mohammed Fekry | 2024-12-24 | 2024-12-25 |  |  |  | 10125645 | 5640 | 0 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 10125645 | APPROVED |  |  | 2025-01-02 | 0 | 8 | Tananeh, Khalid Jamal | -45651 | 8
105-122 | Abu Maan 115/13.8kV Substation | 5258 | Abu Maan 115/13.8kV Substation-Supply and Installation of Boundary Fence Works | APPROVED | No | 2024-12-23 | Abas, Mohammed Fekry | 2024-12-29 | 2024-12-30 |  |  |  | 492617 | 5640 | 1 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 492617 | APPROVED |  |  | 2025-11-18 | 0 | 323 | Hegazy, Ayman | -45656 | 323
105-122 | Abu Maan 115/13.8kV Substation | 5319 | Abu Maan 115/13.8kV Substation-7X2.5 Sq.mm, Control Cabels for SAS Alarm (with Blue Color wires) | APPROVED | No | 2025-01-01 | Abas, Mohammed Fekry | 2025-01-06 | 2025-01-06 |  |  |  | 55000 | 6790 | 0 | STANDARD | ALFANAR CO | SAR | 52600 | APPROVED |  |  | 2025-04-16 | 2400 | 100 | Muaz, Alaa | -45663 | 100
105-122 | Abu Maan 115/13.8kV Substation | 5334 | Abu Maan 115/13.8kV Substation-Supply of Conduits and Fittings | APPROVED | No | 2025-01-02 | Abas, Mohammed Fekry | 2025-01-06 | 2025-01-06 |  |  |  | 337272.4 | 6670 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 337271.55 | APPROVED |  |  | 2025-01-15 | 0.85 | 9 | Muaz, Alaa | -45663 | 9
105-122 | Abu Maan 115/13.8kV Substation | 5610 | Abu Maan 115/13.8kV Substation-FO Cables and Patch Cords | APPROVED | No | 2025-01-26 | Abas, Mohammed Fekry | 2025-01-28 | 2025-01-30 |  |  |  | 300000 | 6956 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 210000 | APPROVED |  |  | 2025-03-11 | 90000 | 40 | Abdulqader, Ahmed Abdulhalim | -45687 | 40
105-122 | Abu Maan 115/13.8kV Substation | 5644 | Abu Maan 115/13.8kV Substation-Remote End materials and Works | APPROVED | No | 2025-01-27 | Abas, Mohammed Fekry | 2025-02-02 | 2025-02-05 |  |  |  | 200000 | 7325 | 0 | STANDARD | TRINERGY TECHNOLOGIES SA | SAR | 85000 | APPROVED |  |  | 2025-05-24 | 115000 | 108 | Babic, Marian | -45693 | 108
105-122 | Abu Maan 115/13.8kV Substation | 5658 | Abu Maan 115/13.8kV Substation-Switches & Sockets, Power Receptacles | RETURNED | No | 2025-01-27 | Muaz, Alaa | 2025-07-30 | 2025-02-02 | 2025-07-30 |  | This PR was raised by mistake due to changes in the BOQ made by PMT | 35000 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -45690 | -45690
105-122 | Abu Maan 115/13.8kV Substation | 5793 | Abu Maan 115/13.8kV Substation-CTPU & CTPU BOX | APPROVED | No | 2025-02-05 | Abas, Mohammed Fekry | 2025-02-10 | 2025-02-11 |  |  |  | 68000 | 6294 | 0 | STANDARD | Energy Tracks For Contracting | SAR | 68000 | APPROVED |  |  | 2025-03-02 | 0 | 19 | Kumar, Mr. Ranjan | -45699 | 19
105-122 | Abu Maan 115/13.8kV Substation | 5928 | Abu Maan 115/13.8kV Substation-HCIS Consultancy for Security system | APPROVED | No | 2025-02-17 | Abas, Mohammed Fekry | 2025-02-19 | 2025-02-19 |  |  |  | 33500 | 6518 | 0 | STANDARD | Khaled Drewesh Office for Consulting Security (KDOCS) | SAR | 33500 | APPROVED |  |  | 2025-03-09 | 0 | 18 | Abdulqader, Ahmed Abdulhalim | -45707 | 18
105-122 | Abu Maan 115/13.8kV Substation | 6070 | Abu Maan 115/13.8kV Substation-Manufacturing, Fabrication, Supply and Installation of Steel Parapet Works | APPROVED | No | 2025-02-26 | Abas, Mohammed Fekry | 2025-05-25 | 2025-05-26 |  |  | Line Item #2.20, Manufacturing, Fabrication, Supply and Installation of Steel Parapet Works | 36520 | 6821 | 0 | STANDARD | RAFCO Factory Company For Metal Industries | SAR | 36520 | APPROVED |  |  | 2025-08-31 | 0 | 97 | Hegazy, Ayman | -45803 | 97
105-122 | Abu Maan 115/13.8kV Substation | 6093 | Abu Maan 115/13.8kV Substation-Raw Water Supply for site | REJECTED | No | 2025-03-02 | Abdel Naiem, Tarek Ali | 2025-03-02 |  |  | 2025-03-02 | dummy | 17500 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | 0 | 0
105-122 | Abu Maan 115/13.8kV Substation | 6094 | Abu Maan 115/13.8kV Substation-Raw Water Supply for site - 10000 Ltrs | APPROVED | No | 2025-03-02 | Abas, Mohammed Fekry | 2025-03-03 | 2025-03-05 |  |  | Line item 2.33, Raw Water Supply for site - 10000 Ltrs | 8750 | 5839 | 1 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 8750 | APPROVED |  |  | 2025-03-13 | 0 | 8 | Akhtar, Farhan | -45721 | 8
105-122 | Abu Maan 115/13.8kV Substation | 6096 | Abu Maan 115/13.8kV Substation-IFC Drawings, A2 Size, Printing, Scanning and Copying | APPROVED | No | 2025-03-03 | Abas, Mohammed Fekry | 2025-03-04 | 2025-03-05 |  |  | Line Item #2.33, IFC Drawings, A2 Size, Printing, Scanning and Copying | 31000 | 7069 | 0 | STANDARD | Print Magaies Al abdaa Printing | SAR | 30999 | APPROVED |  |  | 2025-04-07 | 1 | 33 | Abuhammad, Samir | -45721 | 33
105-122 | Abu Maan 115/13.8kV Substation | 6261 | Abu Maan 115/13.8kV Substation-Manpower supply - Testing Technicians, 6 Persons for 3 months | APPROVED | No | 2025-03-25 | Abas, Mohammed Fekry | 2025-03-27 | 2025-03-27 |  |  | Manpower supply - Testing Technicians, 6 Persons for 3 months | 131040 | 7496 | 0 | STANDARD | Jasem M.AlJasem Contracting Est. | SAR | 131040 | APPROVED |  |  | 2025-08-02 | 0 | 128 | Babic, Marian | -45743 | 128
105-122 | Abu Maan 115/13.8kV Substation | 6292 | Abu Maan 115/13.8kV Substation-Supply of CCVT/CVT for Remote End Juaymah PP SS - 6 Nos. | APPROVED | No | 2025-04-03 | Abas, Mohammed Fekry | 2025-04-15 | 2025-04-15 |  |  | Line Item #2.28, Supply of CCVT/CVT for Remote End Juaymah PP SS - 6 Nos. | 300000 | 7370 | 0 | STANDARD | KONCAR INSTRUMENT TRANSFORMERS | EUR | 282040 | APPROVED |  |  | 2025-08-02 | 17960 | 109 | Babic, Marian | -45762 | 109
105-122 | Abu Maan 115/13.8kV Substation | 6386 | Abu Maan 115/13.8kV Substation-Security System Complete | APPROVED | No | 2025-04-20 | Abas, Mohammed Fekry | 2025-04-21 | 2025-04-21 |  |  | Line Item #2.7. Security System Complete | 819673.89 | 6636 | 0 | STANDARD | CEGELEC NETWORK AND SECURITY SYSTEMS | SAR | 819673.89 | APPROVED |  |  | 2025-04-24 | 0 | 3 | Abdulqader, Ahmed Abdulhalim | -45768 | 3
105-122 | Abu Maan 115/13.8kV Substation | 6401 | Abu Maan 115/13.8kV Substation-Cable Lugs, 4 Hole, suitable for 500 Sq.mm | APPROVED | No | 2025-04-21 | Abas, Mohammed Fekry | 2025-04-21 | 2025-04-22 |  |  | Line item# 2.13, Cable Lugs, 4 Hole, suitable for 500 Sq.mm | 30420 | 7188 | 0 | STANDARD | Essa Al Asmakh Trading Est. | SAR | 30420 | APPROVED |  |  | 2025-04-27 | 0 | 5 | Abuhammad, Samir | -45769 | 5
105-122 | Abu Maan 115/13.8kV Substation | 6571 | Abu Maan 115/13.8kV Substation-4PX1.5mm2 Cu/XLPE/CT/PVC 0.6/1kV Gray Control Cables for ABUMAAN SS | APPROVED | No | 2025-05-10 | Abas, Mohammed Fekry | 2025-05-12 | 2025-05-14 |  |  | 2.13 - 4Px1.5mm2 Cu/XLPE/CT/PVC 0.6/1kV Gray Control Cables with Numbering for ABUMAAN SS | 9000 | 7305 | 0 | STANDARD | Middle East Specialized Cables Mesc | SAR | 7500 | APPROVED |  |  | 2025-05-27 | 1500 | 13 | Abuhammad, Samir | -45791 | 13
105-122 | Abu Maan 115/13.8kV Substation | 6585 | Abu Maan 115/13.8kV Substation-Asphalt Works for Abu Maan Substation | REJECTED | No | 2025-05-11 | Abdel Naiem, Tarek Ali | 2025-05-11 |  |  | 2025-05-11 | dummy | 126275 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | 0 | 0
105-122 | Abu Maan 115/13.8kV Substation | 6586 | Abu Maan 115/13.8kV Substation-Asphalt Works for Abu Maan Substation | APPROVED | No | 2025-05-11 | Abas, Mohammed Fekry | 2025-05-14 | 2025-05-14 |  |  | 2.20 - Asphalt Works | 126275 | 5640 | 1 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 126275 | APPROVED |  |  | 2025-11-18 | 0 | 188 | Hegazy, Ayman | -45791 | 188
105-122 | Abu Maan 115/13.8kV Substation | 6661 | Abu Maan 115/13.8kV Substation-Supply For Fire stop materials for ABUMAAN Substation | APPROVED | No | 2025-05-19 | Abas, Mohammed Fekry | 2025-05-25 | 2025-05-26 |  |  | 2.2 - Supply For Fire stop materials for ABUMAAN Substation | 83375 | 7331 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 72500 | APPROVED |  |  | 2025-08-31 | 10875 | 97 | Tananeh, Khalid Jamal | -45803 | 97
105-122 | Abu Maan 115/13.8kV Substation | 6730 | Abu Maan 115/13.8kV Substation-Metal Doors and Hardware (to activate the optional Scope from main PO #5640) | APPROVED | No | 2025-05-27 | Abas, Mohammed Fekry | 2025-05-28 | 2025-05-28 |  |  | Line item 2.2, Metaldoors and Hardwares | 106083 | 5640 | 1 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 106083 | APPROVED |  |  | 2025-11-18 | 0 | 174 | Hegazy, Ayman | -45805 | 174
105-122 | Abu Maan 115/13.8kV Substation | 6787 | Abu Maan 115/13.8kV Substation-Telecommunication System | APPROVED | No | 2025-06-12 | Abas, Mohammed Fekry | 2025-06-16 | 2025-06-16 |  |  | Line Item #2.4, Telecommunication System | 2399127.86 | 5858 | 0 | STANDARD | ALFANAR CO | SAR | 2399127.86 | APPROVED |  |  | 2025-06-24 | 0 | 8 | Kumar, Mr. Ranjan | -45824 | 8
105-122 | Abu Maan 115/13.8kV Substation | 6792 | Abu Maan 115/13.8kV Substation-FDT Testing for 270 Points and 30 visits | RETURNED | No | 2025-06-12 | Tananeh, Khalid Jamal | 2025-09-22 | 2025-06-16 | 2025-09-22 |  | "The PR are being returned in reference to the email sent on Tuesday, 09/09/2025 at 4:14 PM, as the works were carried out without prior approval from the Procurement Department and the payment shall be made from petty cash." | 10500 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45824 | -45824
105-122 | Abu Maan 115/13.8kV Substation | 6836 | Abu Maan 115/13.8kV Substation-Security Guards for Site (3 Persons for 3 Months) | APPROVED | No | 2025-06-19 | Abas, Mohammed Fekry | 2025-06-23 | 2025-06-25 |  |  | Line Item #2.3, Security Guards for Site (3 Persons for 3 Months) | 37500 | 7429 | 0 | STANDARD | Amnalawtan Security Company for civil security Guards | SAR | 37350 | APPROVED |  |  | 2025-07-14 | 150 | 19 | Abuhammad, Samir | -45833 | 19
105-122 | Abu Maan 115/13.8kV Substation | 6892 | Abu Maan 115/13.8kV Substation-Grounding Materials with Accessories (Manual PO #7078) | APPROVED | No | 2025-06-25 | Abas, Mohammed Fekry | 2025-06-30 | 2025-07-01 |  |  | Line Item 2.21, Grounding Material with Accessories | 52820.2 | 7078 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 52820.2 | APPROVED |  |  | 2025-07-14 | 0 | 13 | Abdulqader, Ahmed Abdulhalim | -45839 | 13
105-122 | Abu Maan 115/13.8kV Substation | 6893 | Abu Maan 115/13.8kV Substation-Groundign Materials and accessories | APPROVED | No | 2025-06-25 | Abas, Mohammed Fekry | 2025-06-30 | 2025-07-01 |  |  | Line Item 2.21, Groundign material adn accessories (DDP delivery only in this PR) | 750 | 7078 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 750 | APPROVED |  |  | 2025-07-14 | 0 | 13 | Abdulqader, Ahmed Abdulhalim | -45839 | 13
105-122 | Abu Maan 115/13.8kV Substation | 6894 | Abu Maan 115/13.8kV Substation-Safety Miscellaneous Materials (Breathing Apparatus-1No., Fire Blankets-3Nos, First Aid Box - 1No., Stretcher - 1No.) | RETURNED | No | 2025-06-25 | Akhtar, Farhan | 2025-10-12 | 2025-07-01 | 2025-10-12 |  | No responce from the PMT | 60000 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45839 | -45839
105-122 | Abu Maan 115/13.8kV Substation | 6920 | Abu Maan 115/13.8kV Substation-Switches & Sockets (Wiring Devices) | APPROVED | No | 2025-06-29 | Abas, Mohammed Fekry | 2025-07-01 | 2025-07-01 |  |  | Line Item #2.23, Switches & Sockets (Wiring Devices) | 99975 | 6697 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 99975 | APPROVED |  |  | 2025-07-14 | 0 | 13 | Muaz, Alaa | -45839 | 13
105-122 | Abu Maan 115/13.8kV Substation | 6978 | Abu Maan 115/13.8kV Substation-Raw Water Supply for Abu Maan site - 10000 Ltrs | APPROVED | No | 2025-07-03 | Abas, Mohammed Fekry | 2025-07-07 | 2025-07-07 |  |  | 2.33 Raw Water Supply for Abu Maan Site | 8750 | 7488 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 7500 | APPROVED |  |  | 2025-07-22 | 1250 | 15 | Akhtar, Farhan | -45845 | 15
105-122 | Abu Maan 115/13.8kV Substation | 7028 | Abu Maan 115/13.8kV Substation-Supply of Clamps/cleatsfor MV cables | APPROVED | No | 2025-07-09 | Abas, Mohammed Fekry | 2025-07-13 | 2025-07-14 |  |  | Line Item #2.13, Supply of Clamps/cleats for MV cables | 56525 | 7383 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 56525 | APPROVED |  |  | 2025-07-27 | 0 | 13 | Hegazy, Ayman | -45852 | 13
105-122 | Abu Maan 115/13.8kV Substation | 7034 | Abu Maan 115/13.8kV Substation-Supply of HV & MV Cable supports | APPROVED | No | 2025-07-09 | Abas, Mohammed Fekry | 2025-07-12 | 2025-07-12 |  |  | Line Item #2.19, Supply of HV & MV Cable supports | 15542 | 7376 | 0 | STANDARD | ISAM KABBANI &Partners | SAR | 15542 | APPROVED |  |  | 2025-07-27 | 0 | 15 | Hegazy, Ayman | -45850 | 15
105-122 | Abu Maan 115/13.8kV Substation | 7042 | Abu Maan 115/13.8kV Substation-Supply of Diesel for Generator at Site | APPROVED | No | 2025-07-09 | Abas, Mohammed Fekry | 2025-07-13 | 2025-07-14 |  |  | Line Item #2.33, Supply of Diesel for Generator at Site | 14890 | 7515 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 14889.57 | APPROVED |  |  | 2025-07-27 | 0.43 | 13 | Akhtar, Farhan | -45852 | 13
105-122 | Abu Maan 115/13.8kV Substation | 7067 | Abu Maan 115/13.8kV Substation-Laboratory Testing of Transformer Oils | APPROVED | No | 2025-07-13 | Abas, Mohammed Fekry | 2025-07-15 | 2025-07-16 |  |  | Line Item, 2.38, Laboratory Testing of Transformer Oils | 37300 | 7533 | 0 | STANDARD | Saudi Arabian Engineering Company | SAR | 37300 | APPROVED |  |  | 2025-08-04 | 0 | 19 | Abdulqader, Ahmed Abdulhalim | -45854 | 19
105-122 | Abu Maan 115/13.8kV Substation | 7119 | Abu Maan 115/13.8kV Substation-Complete PDS System | APPROVED | No | 2025-07-17 | Abas, Mohammed Fekry | 2025-07-21 | 2025-07-22 |  |  | 2.5, PDS System | 250000 | 7761 | 0 | STANDARD | RASHID SAEED AHMED AL GHAMDI COMM INFO TRAD EST | SAR | 140000 | APPROVED |  |  | 2025-11-04 | 110000 | 105 | Abdulqader, Ahmed Abdulhalim | -45860 | 105
105-122 | Abu Maan 115/13.8kV Substation | 7126 | Abu Maan 115/13.8kV Substation-Remote End - Visual Inspection of Existing GIS | APPROVED | No | 2025-07-17 | Abas, Mohammed Fekry | 2025-07-20 | 2025-07-20 |  |  | 2.27, Remote End - Visual Inspection of Existing GIS | 20000 | 7490 | 0 | STANDARD | HD Hyundai Electric Arabia Co., Ltd. | USD | 16965 | APPROVED |  |  | 2025-07-27 | 3035 | 7 | Abdulqader, Ahmed Abdulhalim | -45858 | 7
105-122 | Abu Maan 115/13.8kV Substation | 7152 | Abu Maan 115/13.8kV Substation-Lighting Control system Design, Supply, Installation, testing & commissioning and programming & as-built drawings | RETURNED | No | 2025-07-20 | Muaz, Alaa | 2025-09-09 | 2025-07-27 | 2025-09-09 |  | The budget is not sufficient | 60271 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -45865 | -45865
105-122 | Abu Maan 115/13.8kV Substation | 7519 | dummy | INCOMPLETE | No | [6 empty] | The budget is not sufficient | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | 0 | 0
105-122 | Abu Maan 115/13.8kV Substation | 7542 | Lugs & Glands | APPROVED | No | 2025-08-27 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-03 |  |  | 2.13, Cable Lugs & Cable Glands | 0 | 7618 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 3433.68 | APPROVED |  |  | 2025-09-16 | -3433.68 | 13 | Abdulqader, Ahmed Abdulhalim | -45903 | 13
105-122 | Abu Maan 115/13.8kV Substation | 7562 | Rubber Duct Seal/End Cap for Spare Cable Openings | RETURNED | No | 2025-08-28 | Tananeh, Khalid Jamal | 2025-09-22 | 2025-09-08 | 2025-09-22 |  | To be cancelled due to overlapping SOW with MULTI ACTIVITY SERVICES FOR TRADING Company. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45908 | -45908
105-122 | Abu Maan 115/13.8kV Substation | 7678 | Terminal Hardware for Power Transfomer Bushings and Surge Arrestors | RETURNED | No | 2025-09-08 | Abdulqader, Ahmed Abdulhalim | 2025-10-06 | 2025-09-21 | 2025-10-06 |  | Not required new PR#7860 issued for all sites | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45921 | -45921
105-122 | Abu Maan 115/13.8kV Substation | 7688 | Rental Technicians - 10 Nos. | APPROVED | No | 2025-09-09 | Abas, Mohammed Fekry | 2025-09-16 | 2025-09-21 |  |  | Line Item 2.31, Rental Technicians - 10 Nos. | 0 | 7496 | 1 | STANDARD | Jasem M.AlJasem Contracting Est. | SAR | 20800 | APPROVED |  |  | 2025-11-06 | -20800 | 46 | Babic, Marian | -45921 | 46
105-122 | Abu Maan 115/13.8kV Substation | 7743 | DCDB - 2Nos. for Telecom Room_Abu Maan | APPROVED | No | 2025-09-15 | Abas, Mohammed Fekry | 2025-12-01 | 2025-12-02 | 2025-09-25 |  | As per PM request | 0 | 7737 | 0 | STANDARD | Factory Meaden Al-Khalij for Manufacturing (GTE). | SAR | 25300 | APPROVED |  |  | 2025-12-14 | -25300 | 12 | Abuhammad, Samir | -45993 | 12
105-122 | Abu Maan 115/13.8kV Substation | 7764 | Miscellaneous Materials - Office Supply Materials to SS | APPROVED | No | 2025-09-16 | Abas, Mohammed Fekry | 2025-09-21 | 2025-09-21 |  |  | Line Item #2.33, Miscellaneous Materials - Office Supply Materials to SS | 0 | 7705 | 0 | STANDARD | ALISMAIL INDUSTRIAL CO.(S) | SAR | 17590 | APPROVED |  |  | 2025-10-09 | -17590 | 18 | Abdulqader, Ahmed Abdulhalim | -45921 | 18
105-122 | Abu Maan 115/13.8kV Substation | 7852 | Metal Works (Optional Scope Activiation in PO #5640) | APPROVED | No | 2025-09-29 | Abas, Mohammed Fekry | 2025-09-29 | 2025-10-02 |  |  | Line Item #2.20, Metal Works (Optional Scope Activation in PO #5640) | 0 | 5640 | 1 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 342295 | APPROVED |  |  | 2025-11-18 | -342295 | 47 | Hegazy, Ayman | -45932 | 47
105-122 | Abu Maan 115/13.8kV Substation | 7859 | Security Guards for Abu Maan SS (3 persons for 4 months) | APPROVED | No | 2025-09-30 | Abas, Mohammed Fekry | 2025-10-07 | 2025-10-08 |  |  | Line Item #2.30, Security Guards for Abu Maan SS (3 persons for 4 months) | 0 | 7797 | 0 | STANDARD | Al-Nufuth Al-Mutamayiza For Security Company | SAR | 51000 | APPROVED |  |  | 2025-10-27 | -51000 | 19 | Abuhammad, Samir | -45938 | 19
105-122 | Abu Maan 115/13.8kV Substation | 7988 | Motion System (Lighting control system)_Abu Maan SS | APPROVED | No | 2025-10-16 | Abas, Mohammed Fekry | 2025-10-21 | 2025-10-21 |  |  | Line 2.22, Motion Sensor (Lighting control system)_Abu Maan SS | 0 | 7273 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 68054 | APPROVED |  |  | 2025-10-29 | -68054 | 8 | Muaz, Alaa | -45951 | 8
105-122 | Abu Maan 115/13.8kV Substation | 8003 | General Fill Works at Abu Maan S/S | APPROVED | No | 2025-10-20 | Abas, Mohammed Fekry | 2025-10-21 | 2025-10-21 |  |  | 2.20 - General Fill Works at Abu Maan S/S | 0 | 7949 | 0 | STANDARD |  | SAR | 76912 | INCOMPLETE |  |  |  | -76912 | 103 | Alhadi, Khalid | -45951 | -45951
105-122 | Abu Maan 115/13.8kV Substation | 8003 | General Fill Works at Abu Maan S/S | APPROVED | No | 2025-10-20 | Abas, Mohammed Fekry | 2025-10-21 | 2025-10-21 |  |  | 2.20 - General Fill Works at Abu Maan S/S | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45951 | -45951
105-122 | Abu Maan 115/13.8kV Substation | 8007 | Swing Gate Motor-Including All Accesssories, Procurement, Installation, Testing | APPROVED | No | 2025-10-20 | Abas, Mohammed Fekry | 2025-12-11 | 2025-12-14 | 2025-10-30 |  | missing clear requirements | 0 | 7972 | 0 | STANDARD | ALMOSALLAMY INDUSTRIAL COMPANY | SAR | 9330 | APPROVED |  |  | 2025-12-25 | -9330 | 11 | Abdelraouf, Islam ِAdel Hanafy | -46005 | 11
105-122 | Abu Maan 115/13.8kV Substation | 8095 | Civil works and Steel Support structure at Juaymah PP 115kV S/S (Remote End of Abu Maan S/S) | APPROVED | No | 2025-10-29 | Abas, Mohammed Fekry | 2025-11-09 | 2025-12-24 |  |  | missing clear requirements | 0 | 8038 | 0 | STANDARD | POWER RING Construction Company | SAR | 249589.92 | APPROVED | 2025-12-25 | 2025-12-31 | 2026-01-05 | -249589.92 | 57 | Hegazy, Ayman | 7 | 12
105-122 | Abu Maan 115/13.8kV Substation | 8483 | Supply & Delivery of Raw Water for Abu Maan Substation Site | APPROVED | No | 2025-12-09 | Abas, Mohammed Fekry | 2025-12-11 | 2025-12-14 |  |  | 2.33 Supply and Delivery of Raw Water for Abu Maan S/S Site, 10000 Ltrs/ Trip | 0 | 8016 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 6000 | APPROVED |  |  | 2025-12-23 | -6000 | 9 | Akhtar, Farhan | -46005 | 9
105-122 | Abu Maan 115/13.8kV Substation | 8526 | TPI for CVT FAT 1 Day at Koncar, Croatia_Abu Maan SS | RETURNED | No | 2025-12-16 | Akhtar, Farhan | 2025-12-30 | 2025-12-21 | 2025-12-30 |  | TPI Booking has been confirmed from intertek as per Mr.Sundar | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -46012 | -46012
105-122 | Abu Maan 115/13.8kV Substation | 8561 | Security Guards for Abu Maan Site (3 Persons for 2 Months) | APPROVED | No | 2025-12-21 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-13 |  |  | 2.30- Security Guards at Abu Maan Site (3 Person for 2 months) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46035 | -46035
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 1944 | Wadi Al-Dhahran 115/13.8kv Sub-Engineering & Design wadi AlDhahran | APPROVED | No | 2023-12-12 | Abas, Mohammed Fekry | 2023-12-13 | 2023-12-13 |  |  |  | 581250 | 4901 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 570000 | APPROVED |  |  | 2024-01-08 | 11250 | 26 | Kumar, Mr. Ranjan | -45273 | 26
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 2049 | Wadi Al-Dhahran 115/13.8kv Sub-Wadi Al-Dhahran -13.8kV Switch Gear | APPROVED | No | 2023-12-28 | Abas, Mohammed Fekry | 2024-01-01 | 2024-01-01 |  |  |  | 8210000 | 4867 | 0 | STANDARD | ALFANAR CO | SAR | 8210000 | APPROVED |  |  | 2024-01-18 | 0 | 17 | Alhadi, Khalid | -45292 | 17
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 2060 | Wadi Al-Dhahran 115/13.8kv Sub-C&P,SAS for WADI ALDHAHRAN SS | APPROVED | No | 2023-12-31 | Abas, Mohammed Fekry | 2024-01-02 | 2024-01-02 |  |  |  | 10100000 | 4850 | 0 | STANDARD | ALFANAR CO | SAR | 10100000 | APPROVED |  |  | 2024-01-21 | 0 | 19 | Kumar, Mr. Ranjan | -45293 | 19
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 2097 | Wadi Al-Dhahran 115/13.8kv Sub-Temporary Project Sign Board | APPROVED | No | 2024-01-07 | Abas, Mohammed Fekry | 2024-01-08 | 2024-01-09 |  |  |  | 20000 | 4980 | 0 | STANDARD | Construction Expertise Est. | SAR | 20000 | APPROVED |  |  | 2024-01-17 | 0 | 8 | Alhadi, Khalid | -45300 | 8
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 2200 | Wadi Al-Dhahran 115/13.8kv Sub- OVERHEAD TRAVELING CRANE | APPROVED | No | 2024-01-18 | Abas, Mohammed Fekry | 2024-01-22 | 2024-01-23 |  |  |  | 150000 | 5466 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 126870 | APPROVED |  |  | 2024-05-16 | 23130 | 114 | Muhammad, Muhammad Atif | -45314 | 114
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 2360 | Wadi Al-Dhahran 115/13.8kv Sub- UG Scanning | APPROVED | No | 2024-01-29 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 1900 | 5072 | 0 | STANDARD | Construction Expertise Est. | SAR | 1900 | APPROVED |  |  | 2024-02-15 | 0 | 11 | Alhadi, Khalid | -45326 | 11
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 2400 | Wadi Al-Dhahran 115/13.8kv Sub-Site Office facility | APPROVED | No | 2024-02-04 | Abas, Mohammed Fekry | 2024-02-11 | 2024-02-12 |  |  |  | 325197 | 5427 | 0 | STANDARD | Construction Expertise Est. | SAR | 325197 | APPROVED |  |  | 2024-05-26 | 0 | 104 | Muhammad, Muhammad Atif | -45334 | 104
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 2410 | Wadi Al-Dhahran 115/13.8kv Sub-Battery and Charger | APPROVED | No | 2024-02-05 | Abas, Mohammed Fekry | 2024-02-07 | 2024-02-10 |  |  |  | 550000 | 5743 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 457000 | APPROVED |  |  | 2024-07-10 | 93000 | 151 | Muhammad, Muhammad Atif | -45332 | 151
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 2524 | Wadi Al-Dhahran 115/13.8kv Sub-Geotechnical Investigation | APPROVED | No | 2024-02-11 | Abas, Mohammed Fekry | 2024-02-11 | 2024-02-12 |  |  |  | 16000 | 5707 | 0 | STANDARD | International Agent Commercial Company(S) | SAR | 16000 | APPROVED |  |  | 2024-06-24 | 0 | 133 | Alhadi, Khalid | -45334 | 133
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 2534 | Wadi Al-Dhahran 115/13.8kv Sub-Super Structure Precast including Fire Walls | APPROVED | No | 2024-02-12 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-19 |  |  |  | 2421479 | 5389 | 0 | STANDARD | Factory of Ideal Precast Concrete System Company | SAR | 1921165 | APPROVED |  |  | 2024-04-30 | 500314 | 71 | Tananeh, Khalid Jamal | -45341 | 71
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 2579 | Wadi Al-Dhahran 115/13.8kv Sub-Cyber Security System | APPROVED | No | 2024-02-17 | Abas, Mohammed Fekry | 2024-02-19 | 2024-02-21 |  |  |  | 1100000 | 5062 | 0 | STANDARD | ALFANAR CO | SAR | 1100000 | APPROVED |  |  | 2024-03-27 | 0 | 35 | Babic, Marian | -45343 | 35
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 2716 | Wadi Al-Dhahran 115/13.8kv Sub-ACDB/DCDB & Lighting Panel | APPROVED | No | 2024-02-28 | Abas, Mohammed Fekry | 2024-02-28 | 2024-03-03 |  |  |  | 870000 | 5408 | 0 | STANDARD | ALFANAR CO | SAR | 870000 | APPROVED |  |  | 2024-04-30 | 0 | 58 | Mohammed, Faisal Ansari | -45354 | 58
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 2882 | Wadi Al-Dhahran 115/13.8kv Sub-Topographic Survey of Project Area | APPROVED | No | 2024-03-24 | Abas, Mohammed Fekry | 2024-03-25 | 2024-03-25 |  |  |  | 5125 | 5372 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 5125 | APPROVED |  |  | 2024-04-24 | 0 | 30 | Alhadi, Khalid | -45376 | 30
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 2985 | Wadi Al-Dhahran 115/13.8kv Sub-Shinko Fence, Chain-link Fence and Temporary Gate 6m & 8m | APPROVED | No | 2024-04-03 | Abas, Mohammed Fekry | 2024-04-04 | 2024-04-07 |  |  |  | 156390 | 5453 | 0 | STANDARD | Construction Expertise Est. | SAR | 156390 | APPROVED |  |  | 2024-05-11 | 0 | 34 | Alhadi, Khalid | -45389 | 34
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 3069 | Wadi Al-Dhahran 115/13.8kv Sub-Site Office facility | APPROVED | No | 2024-04-21 | Abas, Mohammed Fekry | 2024-04-21 | 2024-04-23 |  |  |  | 711103 | 5427 | 0 | STANDARD | Construction Expertise Est. | SAR | 711103 | APPROVED |  |  | 2024-05-26 | 0 | 33 | Muhammad, Muhammad Atif | -45405 | 33
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 3124 | Wadi Al-Dhahran 115/13.8kv Sub-Shinko Fence, Chain-link Fence and Temporary Gate 6m & 8m | APPROVED | No | 2024-04-24 | Abas, Mohammed Fekry | 2024-04-24 | 2024-04-25 |  |  |  | 23070 | 5453 | 0 | STANDARD | Construction Expertise Est. | SAR | 23070 | APPROVED |  |  | 2024-05-11 | 0 | 16 | Alhadi, Khalid | -45407 | 16
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 3178 | Wadi Al-Dhahran 115/13.8kv Sub-Water Proofing | APPROVED | No | 2024-04-28 | Abas, Mohammed Fekry | 2024-04-29 | 2024-04-29 |  |  |  | 392625 | 5658 | 0 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 347826.5 | APPROVED |  |  | 2024-06-13 | 44798.5 | 45 | Tananeh, Khalid Jamal | -45411 | 45
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 3185 | Wadi Al-Dhahran 115/13.8kv Sub-Hollow Metal Doors Works | APPROVED | No | 2024-04-28 | Abas, Mohammed Fekry | 2024-04-29 | 2024-04-29 |  |  |  | 152037 | 6046 | 0 | STANDARD | AL MANASHY COMPANY | SAR | 102583 | APPROVED |  |  | 2024-10-21 | 49454 | 175 | Tananeh, Khalid Jamal | -45411 | 175
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 3195 | Wadi Al-Dhahran 115/13.8kv Sub-Metal Works | APPROVED | No | 2024-04-28 | Abas, Mohammed Fekry | 2024-04-29 | 2024-04-29 |  |  |  | 426160 | 5940 | 0 | STANDARD | Nesma Alfaris Contracting Est. | SAR | 388300 | APPROVED |  |  | 2024-10-14 | 37860 | 168 | Tananeh, Khalid Jamal | -45411 | 168
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 3377 | Wadi Al-Dhahran 115/13.8kv Sub-150sq.mm, Tinned copper conductor | APPROVED | No | 2024-05-12 | Abas, Mohammed Fekry | 2024-05-16 | 2024-05-17 |  |  |  | 38500 | 5358 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 38455.41 | APPROVED |  |  | 2024-05-21 | 44.59 | 4 | Muhammad, Muhammad Atif | -45429 | 4
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 3459 | Wadi Al-Dhahran 115/13.8kv Sub-Site Office facility Electronic Item | APPROVED | No | 2024-05-21 | Abas, Mohammed Fekry | 2024-05-21 | 2024-05-22 |  |  |  | 33800 | 5612 | 0 | STANDARD | Construction Expertise Est. | SAR | 33800 | APPROVED |  |  | 2024-06-05 | 0 | 14 | Muhammad, Muhammad Atif | -45434 | 14
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 3575 | Wadi Al-Dhahran 115/13.8kv Sub-Grounding Material Accessories | RETURNED | No | 2024-06-03 | Muhammad, Muhammad Atif | 2024-09-02 | 2024-06-04 | 2024-09-02 |  | PO already issued. Duplicated item with unit price "0". | 73475 | 5561 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 72850 | APPROVED |  |  | 2024-07-07 | 625 |  | Muhammad, Muhammad Atif | -45447 | 33
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 3575 | Wadi Al-Dhahran 115/13.8kv Sub-Grounding Material Accessories | RETURNED | No | 2024-06-03 | Muhammad, Muhammad Atif | 2024-09-02 | 2024-06-04 | 2024-09-02 |  | PO already issued. Duplicated item with unit price "0". | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Muhammad, Muhammad Atif | -45447 | -45447
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 3652 | Wadi Al-Dhahran 115/13.8kv Sub-300KVA & 125kVA Generator, 3Ph, 400V, 60Hz | APPROVED | No | 2024-06-12 | Abas, Mohammed Fekry | 2024-06-26 | 2024-06-26 |  |  |  | 270000 | 5752 | 0 | STANDARD | Mohammed A. AlFaddaghi & Partners | SAR | 268350 | APPROVED |  |  | 2024-07-17 | 1650 | 21 | Akhtar, Farhan | -45469 | 21
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 3718 | Wadi Al-Dhahran 115/13.8kv Sub-MV POWER CABLE ( 1C × 630mm2 & 1×3C×300mm2 ) | APPROVED | No | 2024-07-01 | Abas, Mohammed Fekry | 2024-07-02 | 2024-07-03 |  |  |  | 1069560 | 6027 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 956014.2 | APPROVED |  |  | 2024-10-14 | 113545.8 | 103 | Badhman, Saeed | -45476 | 103
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 3762 | Wadi Al-Dhahran 115/13.8kv Sub-diesel for generators | APPROVED | No | 2024-07-04 | Abas, Mohammed Fekry | 2024-07-07 | 2024-07-08 |  |  |  | 75000 | 5863 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 67826.09 | APPROVED |  |  | 2024-08-05 | 7173.91 | 28 | Akhtar, Farhan | -45481 | 28
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 3782 | Wadi Al-Dhahran 115/13.8kv Sub-Garbage Waste Container, 12 Cu. M (1-year) | APPROVED | No | 2024-07-07 | Abas, Mohammed Fekry | 2024-07-09 | 2024-07-09 |  |  |  | 28800 | 5888 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 19200 | APPROVED |  |  | 2024-08-20 | 9600 | 42 | Akhtar, Farhan | -45482 | 42
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 3848 | Wadi Al-Dhahran 115/13.8kv Sub-Control Cable | APPROVED | No | 2024-07-11 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 716000 | 5829 | 0 | STANDARD | ALFANAR CO | SAR | 531752.8 | APPROVED |  |  | 2024-08-28 | 184247.2 | 43 | Muhammad, Muhammad Atif | -45489 | 43
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 3902 | Wadi Al-Dhahran 115/13.8kv Sub-Testing & Commissioning | APPROVED | No | 2024-07-15 | Abas, Mohammed Fekry | 2024-07-17 | 2024-07-18 |  |  |  | 1990449 | 6450 | 0 | STANDARD | Al Fanar Technical Services | SAR | 1934537 | APPROVED |  |  | 2025-03-13 | 55912 | 238 | Alqadhi, Abdulrahman Abdulghani | -45491 | 238
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 3907 | Wadi Al-Dhahran 115/13.8kv Sub-RTV Coating | APPROVED | No | 2024-07-15 | Abas, Mohammed Fekry | 2024-07-17 | 2024-07-18 |  |  |  | 250000 | 6172 | 0 | STANDARD | SAUDI CONDUIT COATING CO. (S3C) | SAR | 35268 | APPROVED |  |  | 2024-10-13 | 214732 | 87 | Muaz, Alaa | -45491 | 87
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 3912 | Wadi Al-Dhahran 115/13.8kv Sub-MV TERMINATION KITS ( 1C × 630mm2 & 3C×300mm2 ) | APPROVED | No | 2024-07-16 | Abas, Mohammed Fekry | 2024-07-17 | 2024-07-18 |  |  |  | 98839 | 5989 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 95871.89 | APPROVED |  |  | 2024-09-19 | 2967.11 | 63 | Badhman, Saeed | -45491 | 63
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 4024 | Wadi Al-Dhahran 115/13.8kv Sub-LCLM | APPROVED | No | 2024-07-25 | Abas, Mohammed Fekry | 2024-07-29 | 2024-07-29 |  |  |  | 59075 | 5966 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 59075 | APPROVED |  |  | 2024-10-06 | 0 | 69 | Badhman, Saeed | -45502 | 69
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 4041 | Wadi Al-Dhahran 115/13.8kv Sub-Electrical Resistivity Soil test | APPROVED | No | 2024-07-28 | Abas, Mohammed Fekry | 2024-07-29 | 2024-07-29 |  |  |  | 7400 | 5954 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 6400 | APPROVED |  |  | 2024-10-13 | 1000 | 76 | Tananeh, Khalid Jamal | -45502 | 76
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 4167 | Wadi Al-Dhahran 115/13.8kv Sub-LV AC/DC Cables and Lighting Wires | APPROVED | No | 2024-08-17 | Abas, Mohammed Fekry | 2024-08-19 | 2024-08-19 |  |  |  | 1611070 | 6084 | 0 | STANDARD | ALFANAR CO | SAR | 1110509.38 | APPROVED |  |  | 2024-10-01 | 500560.62 | 43 | Badhman, Saeed | -45523 | 43
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 4178 | Wadi Al-Dhahran 115/13.8kv Sub-Sewage Water Removal Services 10,000 Liters | APPROVED | No | 2024-08-18 | Abas, Mohammed Fekry | 2024-08-21 | 2024-08-22 |  |  |  | 300 | 6092 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 300 | APPROVED |  |  | 2024-09-02 | 0 | 11 | Akhtar, Farhan | -45526 | 11
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 4179 | Wadi Al-Dhahran 115/13.8kv Sub-Supply and Delivery of Raw Water 10 Cu.M Tanker | APPROVED | No | 2024-08-18 | Abas, Mohammed Fekry | 2024-08-19 | 2024-08-19 |  |  |  | 1800 | 6092 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 1800 | APPROVED |  |  | 2024-09-02 | 0 | 14 | Akhtar, Farhan | -45523 | 14
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 4180 | Wadi Al-Dhahran 115/13.8kv Sub-Supply and Delivery of drinking water 6 Cu. M fiber glass Tank | APPROVED | No | 2024-08-18 | Abas, Mohammed Fekry | 2024-08-19 | 2024-08-19 |  |  |  | 3000 | 6092 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 3000 | APPROVED |  |  | 2024-09-02 | 0 | 14 | Akhtar, Farhan | -45523 | 14
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 4184 | Wadi Al-Dhahran 115/13.8kv Sub-Hazardou and Non Hazardous Waste | APPROVED | No | 2024-08-18 | Abas, Mohammed Fekry | 2024-08-19 | 2024-08-19 |  |  |  | 5000 | 6116 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 3650 | APPROVED |  |  | 2024-09-16 | 1350 | 28 | Akhtar, Farhan | -45523 | 28
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 4233 | Wadi Al-Dhahran 115/13.8kv Sub-Grounding cables, 0.6/1 KV, Y/G | APPROVED | No | 2024-08-21 | Abas, Mohammed Fekry | 2024-08-22 | 2024-08-22 |  |  |  | 244150 | 6068 | 0 | STANDARD | ALFANAR CO | SAR | 226756.52 | APPROVED |  |  | 2024-09-18 | 17393.48 | 27 | Muhammad, Muhammad Atif | -45526 | 27
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 4289 | Wadi Al-Dhahran 115/13.8kv Sub-Cable tray and its accessories | APPROVED | No | 2024-08-28 | Abas, Mohammed Fekry | 2024-08-29 | 2024-09-01 |  |  |  | 460016.15 | 6152 | 0 | STANDARD | Electrolink Co Ltd | SAR | 459950.01 | APPROVED |  |  | 2024-09-26 | 66.14 | 25 | Muhammad, Muhammad Atif | -45536 | 25
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 4319 | Wadi Al-Dhahran 115/13.8kv Sub-Station Service Transformer-750KVA | APPROVED | No | 2024-08-29 | Abas, Mohammed Fekry | 2024-09-22 | 2024-09-22 |  |  |  | 164000 | 5912 | 0 | STANDARD | ALFANAR CO | SAR | 164000 | APPROVED |  |  | 2024-10-06 | 0 | 14 | Muhammad, Muhammad Atif | -45557 | 14
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 4371 | Wadi Al-Dhahran 115/13.8kv Sub-Fire Protection System | APPROVED | No | 2024-09-04 | Abas, Mohammed Fekry | 2024-09-05 | 2024-09-05 |  |  |  | 2131061 | 6008 | 0 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 2131061 | APPROVED |  |  | 2024-09-18 | 0 | 13 | Muhammad, Muhammad Atif | -45540 | 13
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 4433 | Wadi Al-Dhahran 115/13.8kv Sub-Civil Sub Contractor and Metal work | APPROVED | No | 2024-09-12 | Abas, Mohammed Fekry | 2024-09-16 | 2024-09-17 |  |  |  | 8708000 | 5665 | 0 | STANDARD | Al Rawy Al Arabia | SAR | 8244000 | APPROVED |  |  | 2024-11-13 | 464000 | 57 | Tananeh, Khalid Jamal | -45552 | 57
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 4433 | Wadi Al-Dhahran 115/13.8kv Sub-Civil Sub Contractor and Metal work | APPROVED | No | 2024-09-12 | Abas, Mohammed Fekry | 2024-09-16 | 2024-09-17 |  |  |  | 8708000 | 5665 | 1 | STANDARD | Al Rawy Al Arabia | SAR | 8244000 | IN PROCESS |  |  |  | 464000 | 502 | Tananeh, Khalid Jamal | -45552 | -45552
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 4588 | Wadi Al-Dhahran 115/13.8kv Sub-Electrical Installation Sub Contractor | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-06 | 2024-10-06 |  |  |  | 2992521 | 6368 | 0 | STANDARD | SMART LINES INDUSTRIAL & SERVCIES COMPANY | SAR | 2490000 | APPROVED |  |  | 2024-12-29 | 502521 | 84 | Muhammad, Muhammad Atif | -45571 | 84
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 4677 | Wadi Al-Dhahran 115/13.8kv Sub-HVAC SYSTEM | APPROVED | No | 2024-10-15 | Abas, Mohammed Fekry | 2024-10-15 | 2024-10-15 |  |  |  | 2220000 | 6209 | 0 | STANDARD | MAINTENANCE OF AIRCONDITION AND REFRIGERATION COMPANY LTD.(MARCO) | SAR | 2050000 | APPROVED |  |  | 2024-11-05 | 170000 | 21 | Muhammad, Muhammad Atif | -45580 | 21
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 4883 | Wadi Al-Dhahran 115/13.8kv Sub-3rd Party lab Inspector For Precast Concrete Prodaction Test | APPROVED | No | 2024-11-10 | Abas, Mohammed Fekry | 2024-11-12 | 2024-11-12 |  |  |  | 84200 | 6548 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 84190 | APPROVED |  |  | 2024-12-18 | 10 | 36 | Tananeh, Khalid Jamal | -45608 | 36
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 4947 | Wadi Al-Dhahran 115/13.8kv Sub-Lighting Fixtures | APPROVED | No | 2024-11-14 | Abas, Mohammed Fekry | 2024-11-14 | 2024-11-17 |  |  |  | 71998 | 6475 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 71998 | APPROVED |  |  | 2024-11-20 | 0 | 3 | Muhammad, Muhammad Atif | -45613 | 3
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 5078 | Wadi Al-Dhahran 115/13.8kv Sub-HCIS-3 Consultancy for Security System | APPROVED | No | 2024-11-28 | Abas, Mohammed Fekry | 2025-01-08 | 2025-01-08 |  |  |  | 34000 | 6514 | 0 | STANDARD | Khaled Drewesh Office for Consulting Security (KDOCS) | SAR | 33500 | APPROVED |  |  | 2025-01-13 | 500 | 5 | Muhammad, Muhammad Atif | -45665 | 5
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 5090 | Wadi Al-Dhahran 115/13.8kv Sub-Fiber Optic Cables & Accessories,Installation and Testing Services | APPROVED | No | 2024-11-30 | Abas, Mohammed Fekry | 2024-12-01 | 2024-12-03 |  |  |  | 220000 | 6620 | 0 | STANDARD | Arabian Power Trading Est. | SAR | 188000 | APPROVED |  |  | 2024-12-24 | 32000 | 21 | Muhammad, Muhammad Atif | -45629 | 21
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 5134 | Wadi Al-Dhahran 115/13.8kv Sub-Al. Connector for GIB Bushing | APPROVED | No | 2024-12-04 | Abas, Mohammed Fekry | 2024-12-04 | 2024-12-08 |  |  |  | 5675 | 6421 | 0 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 4617.79 | APPROVED |  |  | 2025-01-02 | 1057.21 | 25 | Mohammed, Faisal Ansari | -45634 | 25
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 5143 | Wadi Al-Dhahran 115/13.8kv Sub-Supply and delivery of drinking Water 6 Cu. M Fiber Glass tank | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-15 | 2024-12-15 |  |  |  | 5250 | 6686 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 4500 | APPROVED |  |  | 2025-01-02 | 750 | 18 | Akhtar, Farhan | -45641 | 18
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 5148 | Wadi Al-Dhahran 115/13.8kv Sub-Supply and delivery of Raw Water 10 Cu. M tanker | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-15 | 2024-12-15 |  |  |  | 2100 | 6686 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 1800 | APPROVED |  |  | 2025-01-02 | 300 | 18 | Akhtar, Farhan | -45641 | 18
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 5153 | Wadi Al-Dhahran 115/13.8kv Sub-Sewage water removal services 10,000 liters | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-15 | 2024-12-15 |  |  |  | 300 | 6686 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 300 | APPROVED |  |  | 2025-01-02 | 0 | 18 | Akhtar, Farhan | -45641 | 18
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 5281 | Wadi Al-Dhahran 115/13.8kv Sub-150mm2 Tinned Copper Conductor Extra | APPROVED | No | 2024-12-28 | Abas, Mohammed Fekry | 2024-12-31 | 2025-01-01 |  |  |  | 133400 | 6756 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 121307.52 | APPROVED |  |  | 2025-03-05 | 12092.48 | 63 | Alhadi, Khalid | -45658 | 63
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 5304 | Wadi Al-Dhahran 115/13.8kv Sub-3rd Party Lab Inspector for PreCast Concrete Production Test | APPROVED | No | 2024-12-30 | Abas, Mohammed Fekry | 2025-01-08 | 2025-01-12 |  |  |  | 84190 | 6748 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 84190 | APPROVED |  |  | 2025-02-04 | 0 | 23 | Tananeh, Khalid Jamal | -45669 | 23
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 5355 | Wadi Al-Dhahran 115/13.8kv Sub-Supply of Conduits and Fittings | APPROVED | No | 2025-01-05 | Abas, Mohammed Fekry | 2025-01-08 | 2025-01-12 |  |  |  | 342909.3 | 6693 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 342909.3 | APPROVED |  |  | 2025-01-22 | 0 | 10 | Muaz, Alaa | -45669 | 10
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 5480 | Wadi Al-Dhahran 115/13.8kv Sub-CT Junction Box wiht 9 Single Phase CTPU - including all accessories | APPROVED | No | 2025-01-20 | Abas, Mohammed Fekry | 2025-01-26 | 2025-01-26 |  |  |  | 85000 | 6290 | 0 | STANDARD | Energy Tracks For Contracting | SAR | 85000 | APPROVED |  |  | 2025-03-04 | 0 | 37 | Kumar, Mr. Ranjan | -45683 | 37
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 5540 | Wadi Al-Dhahran 115/13.8kv Sub-Remote end modification for TFR , DSM | APPROVED | No | 2025-01-23 | Abas, Mohammed Fekry | 2025-01-26 | 2025-01-26 |  |  |  | 100000 | 7451 | 0 | STANDARD | TRINERGY TECHNOLOGIES SA | SAR | 61231 | APPROVED |  |  | 2025-07-06 | 38769 | 161 | Babic, Marian | -45683 | 161
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 5557 | Wadi Al-Dhahran 115/13.8kv Sub-Security System Class-3 | APPROVED | No | 2025-01-23 | Abas, Mohammed Fekry | 2025-02-25 | 2025-02-25 |  |  | line item 2.7-Security System Class-3 | 786946 | 6630 | 0 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 786946 | APPROVED |  |  | 2025-03-05 | 0 | 8 | Abdulqader, Ahmed Abdulhalim | -45713 | 8
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 6102 | Wadi Al-Dhahran 115/13.8kv Sub-Drawing Printing & Scanning | APPROVED | No | 2025-03-03 | Abas, Mohammed Fekry | 2025-03-06 | 2025-03-10 |  |  | Line Item: 2.33 - Drawing Printing & Scanning | 13000 | 7063 | 0 | STANDARD | Print Magaies Al abdaa Printing | SAR | 12998.9 | APPROVED |  |  | 2025-04-07 | 1.1 | 28 | Abuhammad, Samir | -45726 | 28
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 6274 | Wadi Al-Dhahran 115/13.8kv Sub-Concerete duct bank,Excavation work and foam Concrete | RETURNED | No | 2025-03-25 | Tananeh, Khalid Jamal | 2025-09-22 | 2025-03-27 | 2025-09-22 |  | "As no response was received by the deadline of 21-09-2025 to the clarification request sent on Tue 16/09/2025 at 10:29 AM, the PR is being cancelled accordingly." | 276939 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45743 | -45743
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 6275 | Wadi Al-Dhahran 115/13.8kv Sub-Technicians for Testing & Commissioning | APPROVED | No | 2025-03-25 | Abas, Mohammed Fekry | 2025-03-26 | 2025-03-27 |  |  | line item 2.30-Technicians for Testing & Commissioning-2.30 | 191000 | 7468 | 0 | STANDARD | City Crowns Energy | SAR | 190994 | APPROVED |  |  | 2025-07-10 | 6 | 105 | Babic, Marian | -45743 | 105
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 6365 | Wadi Al-Dhahran 115/13.8kv Sub-7X2.5 mm2 CU/XLPE/CTS/PVC | APPROVED | No | 2025-04-17 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-21 |  |  | line item 2.13-7X2.5 mm2 CU/XLPE/CTS/PVC | 52600 | 6786 | 0 | STANDARD | ALFANAR CO | SAR | 52600 | APPROVED |  |  | 2025-05-01 | 0 | 10 | Muaz, Alaa | -45768 | 10
|  |  | 0.6/1 KV – Blue Color | [8 empty] | 0.6/1 KV – Blue Color | [14 empty] | 0 | 0
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 6412 | Wadi Al-Dhahran 115/13.8kv Sub-Sealant work for External Wall | REJECTED | No | 2025-04-22 | Ibrahim, Mahmoud Hassan Ali | 2025-06-24 | 2025-04-22 |  | 2025-06-25 |  | 55000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45769 | -45769
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 6510 | Wadi Al-Dhahran 115/13.8kv Sub-4Px1.5sqmm Cable | APPROVED | No | 2025-05-05 | Abas, Mohammed Fekry | 2025-05-06 | 2025-05-06 |  |  | Line Item: 2.13 - 4P x 1.5 sqmm Cable | 9000 | 7319 | 0 | STANDARD | Middle East Specialized Cables Mesc | SAR | 7500 | APPROVED |  |  | 2025-05-27 | 1500 | 21 | Abuhammad, Samir | -45783 | 21
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 6550 | Wadi Al-Dhahran 115/13.8kv Sub-Steel Decorative Fence | APPROVED | No | 2025-05-07 | Abas, Mohammed Fekry | 2025-05-18 | 2025-05-18 |  |  | Line Item: 2.20 - Steel Decorative Fence | 999000 | 5665 | 1 | STANDARD | Al Rawy Al Arabia | SAR | 520000 | IN PROCESS |  |  |  | 479000 | 259 | Tananeh, Khalid Jamal | -45795 | -45795
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 6550 | Wadi Al-Dhahran 115/13.8kv Sub-Steel Decorative Fence | APPROVED | No | 2025-05-07 | Abas, Mohammed Fekry | 2025-05-18 | 2025-05-18 |  |  | Line Item: 2.20 - Steel Decorative Fence | 999000 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -45795 | -45795
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 6687 | Wadi Al-Dhahran 115/13.8kv Sub-Grounding Accessories | APPROVED | No | 2025-05-22 | Abas, Mohammed Fekry | 2025-05-27 | 2025-05-27 |  |  | Line Item 2.21 - Grounding Accessories | 71764.7 | 7099 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 71764.7 | APPROVED |  |  | 2025-06-22 | 0 | 26 | Abdulqader, Ahmed Abdulhalim | -45804 | 26
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 6738 | Wadi Al-Dhahran 115/13.8kv Sub-125V DC DB for Communication System | APPROVED | No | 2025-05-28 | Abas, Mohammed Fekry | 2025-07-06 | 2025-07-07 |  |  | line item 2.12-125V DC DB for Communication System | 35000 | 7520 | 0 | STANDARD | HAWA ELECTRIC PANEL BOARD FAC | SAR | 29700 | APPROVED |  |  | 2025-07-27 | 5300 | 20 | Abuhammad, Samir | -45845 | 20
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 6778 | Wadi Al-Dhahran 115/13.8kv Sub-Telecom System | APPROVED | No | 2025-06-12 | Abas, Mohammed Fekry | 2025-06-15 | 2025-06-15 |  |  | LINE ITEM 2.4-Communication System | 2061298 | 5854 | 0 | STANDARD | ALFANAR CO | SAR | 2061297.41 | APPROVED |  |  | 2025-06-24 | 0.59 | 9 | Kumar, Mr. Ranjan | -45823 | 9
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 6796 | Wadi Al-Dhahran 115/13.8kv Sub-Supply of diesel for Generators | APPROVED | No | 2025-06-12 | Abas, Mohammed Fekry | 2025-06-16 | 2025-06-17 |  |  | line item 2.33-Supply of diesel for Generators | 49170 | 7416 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 49170 | APPROVED |  |  | 2025-06-23 | 0 | 6 | Akhtar, Farhan | -45825 | 6
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 6912 | Wadi Al-Dhahran 115/13.8kv Sub-Wiring devices( Switches, Socket and Push Buttons) | APPROVED | No | 2025-06-26 | Abas, Mohammed Fekry | 2025-06-30 | 2025-07-01 |  |  | line item 2.23-Wiring devices( Switches, Socket and Push Buttons) | 99975 | 7183 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 99975 | APPROVED |  |  | 2025-07-14 | 0 | 13 | Muaz, Alaa | -45839 | 13
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 6919 | Wadi Al-Dhahran 115/13.8kv Sub-Supply & Installation of HDG Steel Staircase | RETURNED | No | 2025-06-28 | Tananeh, Khalid Jamal | 2025-09-22 | 2025-07-01 | 2025-09-22 |  | "As no response was received by the deadline of 21-09-2025 to the clarification request sent on Tue 16/09/2025 at 10:29 AM, the PR is being cancelled accordingly." | 32000 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45839 | -45839
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7014 | Wadi Al-Dhahran 115/13.8kv Sub-HV MV Cable Supports | APPROVED | No | 2025-07-08 | Abas, Mohammed Fekry | 2025-07-09 | 2025-07-09 |  |  | line item 2.19-HV/MV Cable Supports | 132067.4 | 7300 | 0 | STANDARD | ISAM KABBANI &Partners | SAR | 132067.4 | APPROVED |  |  | 2025-09-29 | 0 | 82 | Hegazy, Ayman | -45847 | 82
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7050 | Wadi Al-Dhahran 115/13.8kv Sub-MV Cable Clamps | APPROVED | No | 2025-07-09 | Abas, Mohammed Fekry | 2025-07-10 | 2025-07-10 |  |  | LINE ITEM 2.13-MV Cable Clamps | 56525 | 7257 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 56525 | APPROVED |  |  | 2025-08-10 | 0 | 31 | Hegazy, Ayman | -45848 | 31
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7061 | Wadi Al-Dhahran 115/13.8kv Sub-3rd Party Laboratory Testing | RETURNED | No | 2025-07-10 | Tananeh, Khalid Jamal | 2025-09-22 | 2025-07-14 | 2025-09-22 |  | "As per the email dated Tue 9/9/2025 4:14 PM, the PR is returned since the works were done without procurement approval, and payment should be made from the project's petty cash." | 25000 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45852 | -45852
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7064 | Wadi Al-Dhahran 115/13.8kv Sub-Supply for Diesal Genrator | APPROVED | No | 2025-07-10 | Abas, Mohammed Fekry | 2025-07-14 | 2025-07-14 |  |  | line 2.33-Supply for Diesal Genrator | 74500 | 7416 | 1 | STANDARD | Talaea Alahlam Trading Company | SAR | 74500 | APPROVED |  |  | 2025-07-24 | 0 | 10 | Akhtar, Farhan | -45852 | 10
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7078 | Wadi Al-Dhahran 115/13.8kv Sub-Supply with installation of AC units Stand Type 5 Ton | APPROVED | No | 2025-07-13 | Abas, Mohammed Fekry | 2025-07-14 | 2025-07-14 |  |  | line item 2.33-Supply with installation of AC units Stand Type 5 Ton | 30000 | 7530 | 0 | STANDARD | Versatile Advanced Limited Company. | SAR | 27000 | APPROVED |  |  | 2025-07-27 | 3000 | 13 | Akhtar, Farhan | -45852 | 13
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7086 | Wadi Al-Dhahran 115/13.8kv Sub-PDS System | APPROVED | No | 2025-07-14 | Abas, Mohammed Fekry | 2025-07-20 | 2025-07-20 |  |  | line item 2.6-PDS SYSTEM | 200000 | 7759 | 0 | STANDARD | RASHID SAEED AHMED AL GHAMDI COMM INFO TRAD EST | SAR | 140000 | APPROVED |  |  | 2025-11-04 | 60000 | 107 | Abdulqader, Ahmed Abdulhalim | -45858 | 107
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7117 | Wadi Al-Dhahran 115/13.8kv Sub-Supply & Installation of H-Beam | REJECTED | No | 2025-07-16 | Ibrahim, Mahmoud Hassan Ali | 2025-10-04 | 2025-07-17 |  | 2025-10-07 |  | 78000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45855 | -45855
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7124 | Wadi Al-Dhahran 115/13.8kv Sub-Drawing Printing & Scanning | APPROVED | No | 2025-07-17 | Abas, Mohammed Fekry | 2025-07-17 | 2025-07-20 |  |  | LINE ITEM-2.33-Drawing Printing & Scanning | 30000 | 7601 | 0 | STANDARD | Print Magaies Al abdaa Printing | SAR | 29985 | APPROVED |  |  | 2025-08-28 | 15 | 39 | Abuhammad, Samir | -45858 | 39
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7279 | Wadi Al-Dhahran 115/13.8kv Sub-Water Proofing work | APPROVED | No | 2025-08-04 | Abas, Mohammed Fekry | 2025-08-05 | 2025-08-06 |  |  | LINE ITEM 2.20-Water Proofing work | 27303 | 5658 | 1 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 27302.47 | APPROVED |  |  | 2025-09-17 | 0.53 | 42 | Tananeh, Khalid Jamal | -45875 | 42
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7303 | Wadi Al-Dhahran 115/13.8kv Sub-Technicians for Testing & Commissioning | APPROVED | No | 2025-08-06 | Abas, Mohammed Fekry | 2025-08-07 | 2025-08-10 |  |  | line item 2.31-Technicians for Testing & Commissioning | 200000 | 7468 | 1 | STANDARD | City Crowns Energy | SAR | 199984 | APPROVED |  |  | 2025-10-16 | 16 | 67 | Babic, Marian | -45879 | 67
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7338 | Wadi Al-Dhahran 115/13.8kv Sub-Control Cables | REJECTED | No | 2025-08-12 | Khan, Muhammad Safdar | 2025-08-31 | 2025-08-12 |  | 2025-08-31 |  | 188000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45881 | -45881
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7507 | Steel Parapet Works | APPROVED | No | 2025-08-26 | Abas, Mohammed Fekry | 2025-08-27 | 2025-08-28 |  |  | Line item 2.20-Steel Parapet Works | 0 | 6825 | 0 | STANDARD | RAFCO Factory Company For Metal Industries | SAR | 36520 | APPROVED |  |  | 2025-09-07 | -36520 | 10 | Hegazy, Ayman | -45897 | 10
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7538 | Lugs and Glands | RETURNED | No | 2025-08-27 | Abdulqader, Ahmed Abdulhalim | 2025-10-02 | 2025-09-03 | 2025-10-02 |  | Not required PO approved in system | 0 | 7580 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 17862.24 | APPROVED |  |  | 2025-09-15 | -17862.24 |  | Abdulqader, Ahmed Abdulhalim | -45903 | 12
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7538 | Lugs and Glands | RETURNED | No | 2025-08-27 | Abdulqader, Ahmed Abdulhalim | 2025-10-02 | 2025-09-03 | 2025-10-02 |  | Not required PO approved in system | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45903 | -45903
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7544 | Rental Saftey Officer | RETURNED | No | 2025-08-27 | Alhadi, Khalid | 2025-10-05 | 2025-09-10 | 2025-10-05 |  | No feedback from project manager and approved CV's from Safety manager | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45910 | -45910
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7554 | DIESEL | APPROVED | No | 2025-08-28 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-03 |  |  | line item 2.33 for diesel genrator | 0 | 7719 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 44700 | APPROVED |  |  | 2025-10-02 | -44700 | 29 | Abdulqader, Ahmed Abdulhalim | -45903 | 29
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7602 | Rental Testing Technician | RETURNED | No | 2025-09-01 | Babic, Marian | 2025-10-06 | 2025-09-08 | 2025-10-06 |  | Returned because previous CO pending for approval for 3 weeks | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45908 | -45908
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7652 | Lugs and glands | APPROVED | No | 2025-09-04 | Abas, Mohammed Fekry | 2025-09-08 | 2025-09-08 |  |  | line item 2.13-Lugs and glands | 0 | 7580 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 6483.36 | APPROVED |  |  | 2025-09-15 | -6483.36 | 7 | Abdulqader, Ahmed Abdulhalim | -45908 | 7
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7679 | Asphalt, Excavation and Back filling work | APPROVED | No | 2025-09-08 | Abas, Mohammed Fekry | 2025-09-09 | 2025-09-10 |  |  | line item 2.20-Asphalt, excavation and back filling work | 0 | 5665 | 1 | STANDARD | Al Rawy Al Arabia | SAR | 512246 | IN PROCESS |  |  |  | -512246 | 144 | Tananeh, Khalid Jamal | -45910 | -45910
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7679 | Asphalt, Excavation and Back filling work | APPROVED | No | 2025-09-08 | Abas, Mohammed Fekry | 2025-09-09 | 2025-09-10 |  |  | line item 2.20-Asphalt, excavation and back filling work | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -45910 | -45910
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7733 | 150Sq.mmTinned Copper Conductor | APPROVED | No | 2025-09-14 | Abas, Mohammed Fekry | 2025-09-22 | 2025-09-23 |  |  | LINE ITEM 2.21-150 Sq.mm Tinned Copper Condutor | 0 | 7687 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 70800 | APPROVED |  |  | 2025-10-05 | -70800 | 12 | Muaz, Alaa | -45923 | 12
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7777 | Substation Office Furniture | APPROVED | No | 2025-09-17 | Abas, Mohammed Fekry | 2025-09-18 | 2025-09-19 |  |  | Line Item 2.33 - Substation Office Furniture | 0 | 7717 | 0 | STANDARD | ALISMAIL INDUSTRIAL CO.(S) | SAR | 17590 | APPROVED |  |  | 2025-10-07 | -17590 | 18 | Abdulqader, Ahmed Abdulhalim | -45919 | 18
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7935 | Lighting Control System/Motion Sensor | APPROVED | No | 2025-10-09 | Abas, Mohammed Fekry | 2025-10-15 | 2025-10-15 |  |  | line item 2.22-Lighting Control System/Motion Sensor | 0 | 7349 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 68054 | APPROVED |  |  | 2025-10-26 | -68054 | 11 | Muaz, Alaa | -45945 | 11
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 7985 | Swing Gate Motor | RETURNED | No | 2025-10-16 | Abdelraouf, Islam ِAdel Hanafy | 2026-01-18 | 2025-10-25 | 2026-01-18 |  | CASH BY SITE | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelraouf, Islam ِAdel Hanafy | -45955 | -45955
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 8033 | Lighitng Wires | APPROVED | No | 2025-10-22 | Abas, Mohammed Fekry | 2025-10-23 | 2025-10-25 |  |  | Line Item: 2.13 - Lighting Wires | 0 | 7965 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 73107.22 | APPROVED | 2026-01-19 | 2026-01-21 | 2026-01-22 | -73107.22 | 89 | Mohammed, Mohammed Adel Fahmy | 88 | 89
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 8216 | Hazardou and Non Hazardous Waste | RETURNED | No | 2025-11-13 | Akhtar, Farhan | 2025-12-08 | 2025-11-17 | 2025-12-08 |  | Kindly submi the budegted PR | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45978 | -45978
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 8342 | Fire Sealan/Rated Material | APPROVED | No | 2025-11-25 | Abas, Mohammed Fekry | 2025-12-01 | 2025-12-02 |  |  | line item 2.20-Fire Sealan/Rated Material-WADI AL DAHRAN SS | 0 | 8003 | 0 | STANDARD | Establishment MASADAR ETQAN AL-TAQI For Trading | SAR | 50715 | APPROVED | 2025-12-30 | 2026-01-01 | 2026-01-06 | -50715 | 35 | Tananeh, Khalid Jamal | 30 | 35
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 8395 | Transformer oil DGA ATransformer oil DGA Analysisnalysis | REJECTED | No | 2025-11-30 | Ibrahim, Mahmoud Hassan Ali | 2025-12-16 | 2025-12-11 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46002 | -46002
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 8464 | ACs for site 5 ton | RETURNED | No | 2025-12-07 | Abuhammad, Samir | 2025-12-16 | 2025-12-09 | 2025-12-16 |  | due to budget modification. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46000 | -46000
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 8491 | Checker plates- wadial daharan | REJECTED | No | 2025-12-10 | Mughal, Aurang | 2025-12-10 |  |  | 2025-12-10 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 8492 | civil works | REJECTED | No | 2025-12-10 | Mughal, Aurang | 2025-12-10 |  |  | 2025-12-10 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 8512 | Transformer oil DGA Analysis | APPROVED | No | 2025-12-14 | Abas, Mohammed Fekry | 2025-12-17 | 2025-12-18 |  |  | Line item 2.38-Transformer oil DGA Analysis-WADI AL DAHRAN | 0 | 8044 | 0 | STANDARD | Saudi Arabian Engineering Company | SAR | 37300 | APPROVED |  |  | 2025-12-29 | -37300 | 11 | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46009 | 11
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 8591 | Metal Works (Change Order) | APPROVED | No | 2025-12-28 | Abas, Mohammed Fekry | 2025-12-30 | 2026-01-01 |  |  | Budget line 2.20 - Civil Works | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46023 | -46023
105-123 | Wadi Al-Dhahran 115/13.8kv Sub | 8644 | Metal Doors (Change Order) - Wadi Dhahran | APPROVED | No | 2026-01-05 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-13 |  |  | Budget line 2.20 - Civil works | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46035 | -46035
105-124 | Qalah 115/13.8kv Substation | 1924 | Qalah 115/13.8kv Substation-Engineering & Design- Qalah | APPROVED | No | 2023-12-11 | Abas, Mohammed Fekry | 2023-12-12 | 2023-12-12 |  |  |  | 581250 | 4904 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 581250 | APPROVED |  |  | 2024-03-17 | 0 | 96 | Kumar, Mr. Ranjan | -45272 | 96
105-124 | Qalah 115/13.8kv Substation | 1971 | Qalah 115/13.8kv Substation-13.8kV Switchgear-Qalah | APPROVED | No | 2023-12-14 | Abas, Mohammed Fekry | 2023-12-15 | 2023-12-17 |  |  |  | 8210000 | 4870 | 0 | STANDARD | ALFANAR CO | SAR | 8210000 | APPROVED |  |  | 2024-01-18 | 0 | 32 | Alhadi, Khalid | -45277 | 32
105-124 | Qalah 115/13.8kv Substation | 2116 | Qalah 115/13.8kv Substation-Temporary Project Sign Board | APPROVED | No | 2024-01-08 | Abas, Mohammed Fekry | 2024-01-09 | 2024-01-09 |  |  |  | 20000 | 4974 | 0 | STANDARD | Construction Expertise Est. | SAR | 20000 | APPROVED |  |  | 2024-01-17 | 0 | 8 | Alhadi, Khalid | -45300 | 8
105-124 | Qalah 115/13.8kv Substation | 2238 | Qalah 115/13.8kv Substation-Cyber Security | APPROVED | No | 2024-01-21 | Abas, Mohammed Fekry | 2024-01-22 | 2024-01-22 |  |  |  | 1100000 | 5065 | 0 | STANDARD | ALFANAR CO | SAR | 1100000 | APPROVED |  |  | 2024-02-19 | 0 | 28 | Babic, Marian | -45313 | 28
105-124 | Qalah 115/13.8kv Substation | 2344 | Qalah 115/13.8kv Substation-Engineering & Design Services | APPROVED | No | 2024-01-29 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 18750 | 4904 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 18750 | APPROVED |  |  | 2024-03-17 | 0 | 42 | Kumar, Mr. Ranjan | -45326 | 42
105-124 | Qalah 115/13.8kv Substation | 2459 | Qalah 115/13.8kv Substation-Site Office Facility | APPROVED | No | 2024-02-06 | Abas, Mohammed Fekry | 2024-02-07 | 2024-02-10 |  |  |  | 175000 | 5115 | 0 | STANDARD | Construction Expertise Est. | SAR | 175000 | APPROVED |  |  | 2024-04-02 | 0 | 52 | Muhammad, Muhammad Atif | -45332 | 52
105-124 | Qalah 115/13.8kv Substation | 2463 | Qalah 115/13.8kv Substation-Main AC&DC Panel Boards with Sub Panels | APPROVED | No | 2024-02-06 | Abas, Mohammed Fekry | 2024-02-07 | 2024-02-10 |  |  |  | 450000 | 5403 | 0 | STANDARD | ALFANAR CO | SAR | 450000 | APPROVED |  |  | 2024-05-01 | 0 | 81 | Mohammed, Faisal Ansari | -45332 | 81
105-124 | Qalah 115/13.8kv Substation | 2489 | Qalah 115/13.8kv Substation-Temporary Fencing Works & Security Cabin | APPROVED | No | 2024-02-07 | Abas, Mohammed Fekry | 2024-02-09 | 2024-02-10 |  |  |  | 76000 | 5141 | 0 | STANDARD | Construction Expertise Est. | SAR | 73080 | APPROVED |  |  | 2024-03-14 | 2920 | 33 | Alhadi, Khalid | -45332 | 33
105-124 | Qalah 115/13.8kv Substation | 2526 | Qalah 115/13.8kv Substation-Geotechnical Investigation | APPROVED | No | 2024-02-11 | Abas, Mohammed Fekry | 2024-02-11 | 2024-02-12 |  |  |  | 16000 | 5246 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 10742 | APPROVED |  |  | 2024-03-20 | 5258 | 37 | Alhadi, Khalid | -45334 | 37
105-124 | Qalah 115/13.8kv Substation | 2626 | Qalah 115/13.8kv Substation-Normal Soil Excavation and Shifting to Baladiah Diaposal | APPROVED | No | 2024-02-20 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 72000 | 5266 | 0 | STANDARD | Eastern Union Contracting Est | SAR | 72000 | APPROVED |  |  | 2024-04-15 | 0 | 49 | Alhadi, Khalid | -45348 | 49
105-124 | Qalah 115/13.8kv Substation | 2626 | Qalah 115/13.8kv Substation-Normal Soil Excavation and Shifting to Baladiah Diaposal | APPROVED | No | 2024-02-20 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 72000 | 5266 | 1 | STANDARD | Eastern Union Contracting Est | SAR | 72000 | REQUIRES REAPPROVAL |  |  |  | 0 | 706 | Alhadi, Khalid | -45348 | -45348
105-124 | Qalah 115/13.8kv Substation | 2743 | Qalah 115/13.8kv Substation-Main AC/DC Panel Boards Including Sub DB's, Indoor and Outdoor Lighting Panels | APPROVED | No | 2024-03-04 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 420000 | 5403 | 0 | STANDARD | ALFANAR CO | SAR | 420000 | APPROVED |  |  | 2024-05-01 | 0 | 55 | Mohammed, Faisal Ansari | -45358 | 55
105-124 | Qalah 115/13.8kv Substation | 2765 | Qalah 115/13.8kv Substation-Shoring for 4 Months Duration | APPROVED | No | 2024-03-04 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 124000 | 5266 | 0 | STANDARD | Eastern Union Contracting Est | SAR | 124000 | APPROVED |  |  | 2024-04-15 | 0 | 39 | Alhadi, Khalid | -45358 | 39
105-124 | Qalah 115/13.8kv Substation | 2765 | Qalah 115/13.8kv Substation-Shoring for 4 Months Duration | APPROVED | No | 2024-03-04 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 124000 | 5266 | 1 | STANDARD | Eastern Union Contracting Est | SAR | 124000 | REQUIRES REAPPROVAL |  |  |  | 0 | 696 | Alhadi, Khalid | -45358 | -45358
105-124 | Qalah 115/13.8kv Substation | 2852 | Qalah 115/13.8kv Substation-1000mm thick with Aggregate SUB BASE class-"A(1A)" with CBR not less than 50 | APPROVED | No | 2024-03-20 | Abas, Mohammed Fekry | 2024-03-23 | 2024-03-24 |  |  |  | 49500 | 5266 | 0 | STANDARD | Eastern Union Contracting Est | SAR | 49500 | APPROVED |  |  | 2024-04-15 | 0 | 22 | Alhadi, Khalid | -45375 | 22
105-124 | Qalah 115/13.8kv Substation | 2852 | Qalah 115/13.8kv Substation-1000mm thick with Aggregate SUB BASE class-"A(1A)" with CBR not less than 50 | APPROVED | No | 2024-03-20 | Abas, Mohammed Fekry | 2024-03-23 | 2024-03-24 |  |  |  | 49500 | 5266 | 1 | STANDARD | Eastern Union Contracting Est | SAR | 49500 | REQUIRES REAPPROVAL |  |  |  | 0 | 679 | Alhadi, Khalid | -45375 | -45375
105-124 | Qalah 115/13.8kv Substation | 2853 | Qalah 115/13.8kv Substation-600mm thick Aggregate BASE COARSE (crashed stones) class-"A(1A) or A(1B)" with CBR not less than 100 | APPROVED | No | 2024-03-20 | Abas, Mohammed Fekry | 2024-03-23 | 2024-03-24 |  |  |  | 29700 | 5266 | 0 | STANDARD | Eastern Union Contracting Est | SAR | 29700 | APPROVED |  |  | 2024-04-15 | 0 | 22 | Alhadi, Khalid | -45375 | 22
105-124 | Qalah 115/13.8kv Substation | 2853 | Qalah 115/13.8kv Substation-600mm thick Aggregate BASE COARSE (crashed stones) class-"A(1A) or A(1B)" with CBR not less than 100 | APPROVED | No | 2024-03-20 | Abas, Mohammed Fekry | 2024-03-23 | 2024-03-24 |  |  |  | 29700 | 5266 | 1 | STANDARD | Eastern Union Contracting Est | SAR | 29700 | REQUIRES REAPPROVAL |  |  |  | 0 | 679 | Alhadi, Khalid | -45375 | -45375
105-124 | Qalah 115/13.8kv Substation | 2860 | Qalah 115/13.8kv Substation-General Backfilling | APPROVED | No | 2024-03-20 | Abas, Mohammed Fekry | 2024-03-23 | 2024-03-24 |  |  |  | 92000 | 5266 | 0 | STANDARD | Eastern Union Contracting Est | SAR | 92000 | APPROVED |  |  | 2024-04-15 | 0 | 22 | Alhadi, Khalid | -45375 | 22
105-124 | Qalah 115/13.8kv Substation | 2860 | Qalah 115/13.8kv Substation-General Backfilling | APPROVED | No | 2024-03-20 | Abas, Mohammed Fekry | 2024-03-23 | 2024-03-24 |  |  |  | 92000 | 5266 | 1 | STANDARD | Eastern Union Contracting Est | SAR | 92000 | REQUIRES REAPPROVAL |  |  |  | 0 | 679 | Alhadi, Khalid | -45375 | -45375
105-124 | Qalah 115/13.8kv Substation | 2864 | Qalah 115/13.8kv Substation-Site Office (Additional PR) | APPROVED | No | 2024-03-20 | Abas, Mohammed Fekry | 2024-03-23 | 2024-03-24 |  |  |  | 17080 | 5115 | 0 | STANDARD | Construction Expertise Est. | SAR | 17080 | APPROVED |  |  | 2024-04-02 | 0 | 9 | Muhammad, Muhammad Atif | -45375 | 9
105-124 | Qalah 115/13.8kv Substation | 2897 | Qalah 115/13.8kv Substation-Topographic Survey of Project Area | APPROVED | No | 2024-03-25 | Abas, Mohammed Fekry | 2024-03-28 | 2024-03-28 |  |  |  | 5125 | 5378 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 5125 | APPROVED |  |  | 2024-04-24 | 0 | 27 | Alhadi, Khalid | -45379 | 27
105-124 | Qalah 115/13.8kv Substation | 2997 | Qalah 115/13.8kv Substation-Control, Protection, SAS, AMI & RM Panels | APPROVED | No | 2024-04-04 | Abas, Mohammed Fekry | 2024-04-07 | 2024-04-07 |  |  |  | 10000000 | 4853 | 0 | STANDARD | ALFANAR CO | SAR | 10000000 | APPROVED |  |  | 2024-05-01 | 0 | 24 | Kumar, Mr. Ranjan | -45389 | 24
105-124 | Qalah 115/13.8kv Substation | 3041 | Qalah 115/13.8kv Substation-5 Ton Over Head Travelling Crane with all required Accessories | APPROVED | No | 2024-04-16 | Abas, Mohammed Fekry | 2024-04-18 | 2024-04-24 |  |  |  | 130000 | 5469 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 126870 | APPROVED |  |  | 2024-05-16 | 3130 | 22 | Muhammad, Muhammad Atif | -45406 | 22
105-124 | Qalah 115/13.8kv Substation | 3132 | Qalah 115/13.8kv Substation-Supply & Apply of Roof Waterproofing System & Underground Waterproofing System | APPROVED | No | 2024-04-25 | Abas, Mohammed Fekry | 2024-04-25 | 2024-04-28 |  |  |  | 355000 | 5660 | 0 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 347826.5 | APPROVED |  |  | 2024-06-16 | 7173.5 | 49 | Tananeh, Khalid Jamal | -45410 | 49
105-124 | Qalah 115/13.8kv Substation | 3361 | Qalah 115/13.8kv Substation-Electronic Materials requirments for Site Office | APPROVED | No | 2024-05-09 | Abas, Mohammed Fekry | 2024-05-15 | 2024-05-15 |  |  |  | 33800 | 5614 | 0 | STANDARD | Construction Expertise Est. | SAR | 33800 | APPROVED |  |  | 2024-06-03 | 0 | 19 | Muhammad, Muhammad Atif | -45427 | 19
105-124 | Qalah 115/13.8kv Substation | 3379 | Qalah 115/13.8kv Substation-150Sq.mm Tinned Copper Conductor | APPROVED | No | 2024-05-12 | Abas, Mohammed Fekry | 2024-05-15 | 2024-05-15 |  |  |  | 38500 | 5361 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 38455.41 | APPROVED |  |  | 2024-05-27 | 44.59 | 12 | Muhammad, Muhammad Atif | -45427 | 12
105-124 | Qalah 115/13.8kv Substation | 3516 | Qalah 115/13.8kv Substation-Batteries & Chargers | APPROVED | No | 2024-05-28 | Abas, Mohammed Fekry | 2024-05-29 | 2024-05-30 |  |  |  | 550000 | 5746 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 457000 | APPROVED |  |  | 2024-07-09 | 93000 | 40 | Muhammad, Muhammad Atif | -45442 | 40
105-124 | Qalah 115/13.8kv Substation | 3660 | Qalah 115/13.8kv Substation-Grounding Material and Accessories | APPROVED | No | 2024-06-13 | Abas, Mohammed Fekry | 2024-06-28 | 2024-06-30 |  |  |  | 73475 | 5564 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 72850 | APPROVED |  |  | 2024-07-12 | 625 | 12 | Muhammad, Muhammad Atif | -45473 | 12
105-124 | Qalah 115/13.8kv Substation | 3701 | Qalah 115/13.8kv Substation-Supply of Non Potabl Water for Site office Use | APPROVED | No | 2024-06-30 | Abas, Mohammed Fekry | 2024-07-05 | 2024-07-07 |  |  |  | 18000 | 5838 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 16800 | APPROVED |  |  | 2024-08-01 | 1200 | 25 | Akhtar, Farhan | -45480 | 25
105-124 | Qalah 115/13.8kv Substation | 3704 | Qalah 115/13.8kv Substation-Supply of Diesel for Generator at Site | APPROVED | No | 2024-06-30 | Abas, Mohammed Fekry | 2024-07-05 | 2024-07-07 |  |  |  | 9000 | 5793 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 9000 | APPROVED |  |  | 2024-07-18 | 0 | 11 | Akhtar, Farhan | -45480 | 11
105-124 | Qalah 115/13.8kv Substation | 3788 | Qalah 115/13.8kv Substation-Garbage Waste Container, 12 Cu. M (1-year) | APPROVED | No | 2024-07-07 | Abas, Mohammed Fekry | 2024-07-09 | 2024-07-09 |  |  |  | 28800 | 5958 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 19200 | APPROVED |  |  | 2024-08-20 | 9600 | 42 | Akhtar, Farhan | -45482 | 42
105-124 | Qalah 115/13.8kv Substation | 3866 | Qalah 115/13.8kv Substation-Control Cables | APPROVED | No | 2024-07-12 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 716000 | 5832 | 0 | STANDARD | ALFANAR CO | SAR | 531752.8 | APPROVED |  |  | 2024-08-28 | 184247.2 | 43 | Muhammad, Muhammad Atif | -45489 | 43
105-124 | Qalah 115/13.8kv Substation | 3914 | Qalah 115/13.8kv Substation-RTV Coating for Transformer HV Busings and GIB HV Bushings | APPROVED | No | 2024-07-16 | Abas, Mohammed Fekry | 2024-07-24 | 2024-07-25 |  |  |  | 250000 | 6181 | 0 | STANDARD | SAUDI CONDUIT COATING CO. (S3C) | SAR | 35268 | APPROVED |  |  | 2024-10-13 | 214732 | 80 | Muaz, Alaa | -45498 | 80
105-124 | Qalah 115/13.8kv Substation | 3914 | Qalah 115/13.8kv Substation-RTV Coating for Transformer HV Busings and GIB HV Bushings | APPROVED | No | 2024-07-16 | Abas, Mohammed Fekry | 2024-07-24 | 2024-07-25 |  |  |  | 250000 | 6181 | 1 | STANDARD | SAUDI CONDUIT COATING CO. (S3C) | SAR | 35268 | REQUIRES REAPPROVAL |  |  |  | 214732 | 556 | Muaz, Alaa | -45498 | -45498
105-124 | Qalah 115/13.8kv Substation | 3918 | Qalah 115/13.8kv Substation-Testing & Commissioning Works | APPROVED | No | 2024-07-16 | Abas, Mohammed Fekry | 2024-07-24 | 2024-07-25 |  |  |  | 2187379 | 6453 | 0 | STANDARD | Al Fanar Technical Services | SAR | 2125936 | APPROVED |  |  | 2025-02-25 | 61443 | 215 | Alqadhi, Abdulrahman Abdulghani | -45498 | 215
105-124 | Qalah 115/13.8kv Substation | 3922 | Qalah 115/13.8kv Substation-MV Termination Kits | APPROVED | No | 2024-07-16 | Abas, Mohammed Fekry | 2024-07-24 | 2024-07-25 |  |  |  | 98839 | 5992 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 95871.89 | APPROVED |  |  | 2024-09-19 | 2967.11 | 56 | Badhman, Saeed | -45498 | 56
105-124 | Qalah 115/13.8kv Substation | 3992 | Qalah 115/13.8kv Substation-13.8kV MV Power Cable | APPROVED | No | 2024-07-23 | Abas, Mohammed Fekry | 2024-07-24 | 2024-07-25 |  |  |  | 957460 | 6029 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 856195.4 | APPROVED |  |  | 2024-10-09 | 101264.6 | 76 | Badhman, Saeed | -45498 | 76
105-124 | Qalah 115/13.8kv Substation | 4197 | Qalah 115/13.8kv Substation-Hazardous and Non Hazardous Waste Collection | APPROVED | No | 2024-08-19 | Abas, Mohammed Fekry | 2024-08-25 | 2024-08-25 |  |  |  | 5000 | 6124 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 3650 | APPROVED |  |  | 2024-09-17 | 1350 | 23 | Akhtar, Farhan | -45529 | 23
105-124 | Qalah 115/13.8kv Substation | 4229 | Qalah 115/13.8kv Substation-LV Power Cable | APPROVED | No | 2024-08-21 | Abas, Mohammed Fekry | 2024-09-02 | 2024-09-04 |  |  |  | 1611070 | 6087 | 0 | STANDARD | ALFANAR CO | SAR | 1110509.38 | APPROVED |  |  | 2024-10-06 | 500560.62 | 32 | Badhman, Saeed | -45539 | 32
105-124 | Qalah 115/13.8kv Substation | 4236 | Qalah 115/13.8kv Substation-LCLM | APPROVED | No | 2024-08-21 | Abas, Mohammed Fekry | 2024-08-25 | 2024-08-25 |  |  |  | 59075 | 6196 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 59075 | APPROVED |  |  | 2024-10-07 | 0 | 43 | Badhman, Saeed | -45529 | 43
105-124 | Qalah 115/13.8kv Substation | 4251 | Qalah 115/13.8kv Substation-Gounding Cables | APPROVED | No | 2024-08-24 | Abas, Mohammed Fekry | 2024-08-27 | 2024-09-01 |  |  |  | 244150 | 6071 | 0 | STANDARD | ALFANAR CO | SAR | 226756.52 | APPROVED |  |  | 2024-09-24 | 17393.48 | 23 | Muhammad, Muhammad Atif | -45536 | 23
105-124 | Qalah 115/13.8kv Substation | 4366 | Qalah 115/13.8kv Substation-Station Service Transformer 750kVA | APPROVED | No | 2024-09-04 | Abas, Mohammed Fekry | 2024-09-09 | 2024-09-09 |  |  |  | 164000 | 5915 | 0 | STANDARD | ALFANAR CO | SAR | 164000 | APPROVED |  |  | 2024-10-08 | 0 | 29 | Muhammad, Muhammad Atif | -45544 | 29
105-124 | Qalah 115/13.8kv Substation | 4446 | Qalah 115/13.8kv Substation-Fire Alarm & Fire Suppression System | APPROVED | No | 2024-09-14 | Abas, Mohammed Fekry | 2024-09-17 | 2024-09-17 |  |  |  | 2176197 | 5995 | 0 | STANDARD | Reda Trading & Development Co. for Machinery & Equipment Ltd(S) | SAR | 2176197 | APPROVED |  |  | 2024-09-24 | 0 | 7 | Muhammad, Muhammad Atif | -45552 | 7
105-124 | Qalah 115/13.8kv Substation | 4592 | Qalah 115/13.8kv Substation-Electrical Installation - Contract | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-09 |  |  |  | 2992521 | 6553 | 0 | STANDARD | Hussain Ali Hussain Contracting Company | SAR | 2514745 | APPROVED |  |  | 2025-01-14 | 477776 | 97 | Muhammad, Muhammad Atif | -45574 | 97
105-124 | Qalah 115/13.8kv Substation | 4847 | Qalah 115/13.8kv Substation-Civil & Structural Works(Main+Optional Scopes)- Qalah | APPROVED | No | 2024-11-06 | Abas, Mohammed Fekry | 2025-01-04 | 2025-01-05 |  |  |  | 12250000 | 6735 | 0 | STANDARD | Future Achievement Limited Co | SAR | 12250000 | APPROVED |  |  | 2025-01-14 | 0 | 9 | Tananeh, Khalid Jamal | -45662 | 9
105-124 | Qalah 115/13.8kv Substation | 4847 | Qalah 115/13.8kv Substation-Civil & Structural Works(Main+Optional Scopes)- Qalah | APPROVED | No | 2024-11-06 | Abas, Mohammed Fekry | 2025-01-04 | 2025-01-05 |  |  |  | 12250000 | 6735 | 1 | STANDARD | Future Achievement Limited Co | SAR | 9300000 | APPROVED |  |  | 2025-10-01 | 2950000 | 269 | Tananeh, Khalid Jamal | -45662 | 269
105-124 | Qalah 115/13.8kv Substation | 4855 | Qalah 115/13.8kv Substation-2.2 Soil Improvement/Controlled Modules Column (CMC) Works | APPROVED | No | 2024-11-07 | Abas, Mohammed Fekry | 2024-11-12 | 2024-11-12 |  |  |  | 2500000 | 6543 | 0 | STANDARD | FREYSSINET MENARD SAUDI ARABIA LTD | SAR | 2500000 | APPROVED |  |  | 2024-11-28 | 0 | 16 | Tananeh, Khalid Jamal | -45608 | 16
105-124 | Qalah 115/13.8kv Substation | 4929 | Qalah 115/13.8kv Substation-Sewage Water Removal Services, 10000 Ltrs - 10 Trips | APPROVED | No | 2024-11-13 | Abas, Mohammed Fekry | 2024-11-17 | 2024-11-17 |  |  |  | 3500 | 6524 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 3000 | APPROVED |  |  | 2024-11-28 | 500 | 11 | Akhtar, Farhan | -45613 | 11
105-124 | Qalah 115/13.8kv Substation | 5080 | Qalah 115/13.8kv Substation-HCIS Consultancy for Security System | APPROVED | No | 2024-11-28 | Abas, Mohammed Fekry | 2025-01-15 | 2025-01-16 |  |  |  | 33500 | 6517 | 0 | STANDARD | Khaled Drewesh Office for Consulting Security (KDOCS) | SAR | 33500 | APPROVED |  |  | 2025-03-09 | 0 | 52 | Abdulqader, Ahmed Abdulhalim | -45673 | 52
105-124 | Qalah 115/13.8kv Substation | 5190 | Qalah 115/13.8kv Substation-HV Clamps & Connectors / Terminal Hardwares | APPROVED | No | 2024-12-08 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-12 |  |  |  | 4616 | 6424 | 0 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 4505.16 | APPROVED |  |  | 2025-01-02 | 110.84 | 21 | Mohammed, Faisal Ansari | -45638 | 21
105-124 | Qalah 115/13.8kv Substation | 5284 | Qalah 115/13.8kv Substation-150Sq.mm Tinned Copper Conductor | APPROVED | No | 2024-12-29 | Abas, Mohammed Fekry | 2024-12-29 | 2024-12-30 |  |  |  | 79800 | 6759 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 73839.36 | APPROVED |  |  | 2025-02-24 | 5960.64 | 56 | Alhadi, Khalid | -45656 | 56
105-124 | Qalah 115/13.8kv Substation | 5322 | Qalah 115/13.8kv Substation-7X2.5 Sq.mm, Control Cabels for SAS Alarm (with Blue Color wires) | APPROVED | No | 2025-01-01 | Abas, Mohammed Fekry | 2025-01-06 | 2025-01-06 |  |  |  | 55000 | 6789 | 0 | STANDARD | ALFANAR CO | SAR | 52600 | APPROVED |  |  | 2025-04-16 | 2400 | 100 | Muaz, Alaa | -45663 | 100
105-124 | Qalah 115/13.8kv Substation | 5531 | Qalah 115/13.8kv Substation-HVAC System works complete | APPROVED | No | 2025-01-22 | Abas, Mohammed Fekry | 2025-01-28 | 2025-01-30 |  |  |  | 2220000 | 6840 | 0 | STANDARD | Hamad Fahad Al Awad for Contracting Est | SAR | 2200000 | APPROVED |  |  | 2025-02-17 | 20000 | 18 | Abdulqader, Ahmed Abdulhalim | -45687 | 18
105-124 | Qalah 115/13.8kv Substation | 5613 | Qalah 115/13.8kv Substation-FO Cables and Patch Cords | APPROVED | No | 2025-01-26 | Abas, Mohammed Fekry | 2025-01-28 | 2025-01-30 |  |  |  | 300000 | 6966 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 210000 | APPROVED |  |  | 2025-03-11 | 90000 | 40 | Abdulqader, Ahmed Abdulhalim | -45687 | 40
105-124 | Qalah 115/13.8kv Substation | 5657 | Qalah 115/13.8kv Substation-Switches & Sockets, Power Receptacles | RETURNED | No | 2025-01-27 | Muaz, Alaa | 2025-07-30 | 2025-02-02 | 2025-07-30 |  | This PR was raised by mistake due to changes in the BOQ made by PMT | 35000 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -45690 | -45690
105-124 | Qalah 115/13.8kv Substation | 5726 | Qalah 115/13.8kv Substation-CTPU & CTPU BOX | APPROVED | No | 2025-01-29 | Abas, Mohammed Fekry | 2025-02-02 | 2025-02-05 |  |  |  | 102000 | 6293 | 0 | STANDARD | Energy Tracks For Contracting | SAR | 102000 | APPROVED |  |  | 2025-03-05 | 0 | 28 | Kumar, Mr. Ranjan | -45693 | 28
105-124 | Qalah 115/13.8kv Substation | 5924 | Qalah 115/13.8kv Substation-Security System Complete as per HCIS Standard and Requirment | APPROVED | No | 2025-02-17 | Abas, Mohammed Fekry | 2025-02-19 | 2025-02-19 |  |  |  | 775618 | 6628 | 0 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 775618 | APPROVED |  |  | 2025-03-05 | 0 | 14 | Abdulqader, Ahmed Abdulhalim | -45707 | 14
105-124 | Qalah 115/13.8kv Substation | 6574 | Qalah 115/13.8kv Substation-4P x 1.5mm2 Cu/XLPE/CT/PVC 0.6/1kV Gray Control Cables with Numbering for QALAH SS | APPROVED | No | 2025-05-10 | Abas, Mohammed Fekry | 2025-05-12 | 2025-05-14 |  |  | 2.13- 4P x 1.5mm2 Cu/XLPE/CT/PVC 0.6/1kV Gray Control Cables with Numbering for QALAH SS | 9000 | 7322 | 0 | STANDARD | Middle East Specialized Cables Mesc | SAR | 7500 | APPROVED |  |  | 2025-05-27 | 1500 | 13 | Abuhammad, Samir | -45791 | 13
105-124 | Qalah 115/13.8kv Substation | 6788 | Qalah 115/13.8kv Substation-Telecommunication System | APPROVED | No | 2025-06-12 | Abas, Mohammed Fekry | 2025-06-16 | 2025-06-16 |  |  | Line Item #2.4, Telecommunication System | 2021918.06 | 5857 | 0 | STANDARD | ALFANAR CO | SAR | 2021918.06 | APPROVED |  |  | 2025-06-24 | 0 | 8 | Kumar, Mr. Ranjan | -45824 | 8
105-124 | Qalah 115/13.8kv Substation | 7004 | Qalah 115/13.8kv Substation-Lighting Fixtures | APPROVED | No | 2025-07-08 | Abas, Mohammed Fekry | 2025-07-12 | 2025-07-12 |  |  | Line Item 2.22, Lighting Fixtures | 76766 | 7516 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 76766 | APPROVED |  |  | 2025-08-03 | 0 | 22 | Abdulqader, Ahmed Abdulhalim | -45850 | 22
105-124 | Qalah 115/13.8kv Substation | 7031 | Qalah 115/13.8kv Substation-Supply of Clamps/cleats for MV cables | APPROVED | No | 2025-07-09 | Abas, Mohammed Fekry | 2025-07-13 | 2025-07-14 |  |  | Line Item #2.13, Supply of Clamps/cleats for MV cables | 56525 | 7393 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 56525 | APPROVED |  |  | 2025-07-27 | 0 | 13 | Hegazy, Ayman | -45852 | 13
105-124 | Qalah 115/13.8kv Substation | 7039 | Qalah 115/13.8kv Substation-Supply of HV & MV Cable Supports | APPROVED | No | 2025-07-09 | Abas, Mohammed Fekry | 2025-07-13 | 2025-07-14 |  |  | Line Item #2.19, Supply of HV & MV Cable Supports | 112970 | 7381 | 0 | STANDARD | Power Solution Industries | SAR | 112970 | APPROVED |  |  | 2025-08-02 | 0 | 19 | Hegazy, Ayman | -45852 | 19
105-124 | Qalah 115/13.8kv Substation | 7091 | Qalah 115/13.8kv Substation-Transformer Laboratory oil testing | APPROVED | No | 2025-07-15 | Abas, Mohammed Fekry | 2025-07-23 | 2025-07-23 |  |  | 2.38, Transformer Oil Laboratory Testing | 37300 | 7569 | 0 | STANDARD | Saudi Arabian Engineering Company | SAR | 37300 | APPROVED |  |  | 2025-08-11 | 0 | 19 | Abdulqader, Ahmed Abdulhalim | -45861 | 19
105-124 | Qalah 115/13.8kv Substation | 7122 | Qalah 115/13.8kv Substation-Complete PDS System | APPROVED | No | 2025-07-17 | Abas, Mohammed Fekry | 2025-08-03 | 2025-08-03 |  |  | 2.5, PDS System | 250000 | 7755 | 0 | STANDARD | RASHID SAEED AHMED AL GHAMDI COMM INFO TRAD EST | SAR | 140000 | APPROVED |  |  | 2025-11-04 | 110000 | 93 | Abdulqader, Ahmed Abdulhalim | -45872 | 93
105-124 | Qalah 115/13.8kv Substation | 7348 | Qalah 115/13.8kv Substation-Metal Works for Qalah Substation | APPROVED | No | 2025-08-13 | Abas, Mohammed Fekry | 2025-08-21 | 2025-08-21 |  |  | 2.2 - Metal Works for Qalah Substation | 850000 | 7526 | 0 | STANDARD | Fursan Construction Industry Factory Industry Factory | SAR | 529457.5 | APPROVED |  |  | 2025-09-14 | 320542.5 | 24 | Hegazy, Ayman | -45890 | 24
105-124 | Qalah 115/13.8kv Substation | 7399 | Qalah 115/13.8kv Substation-Security Guard for Qalah substation Site | RETURNED | No | 2025-08-20 | Abuhammad, Samir | 2025-09-28 | 2025-08-28 | 2025-09-28 |  | to corect the task No. | 76500 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45897 | -45897
105-124 | Qalah 115/13.8kv Substation | 7461 | Qalah 115/13.8kv Substation-Manufacturing, Fabrication, Supply and Installation of Steel Parapet Works for Qalah S/S | REJECTED | No | 2025-08-25 | Abdel Naiem, Tarek Ali | 2025-08-25 |  |  | 2025-08-25 | 2.2 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | 0 | 0
105-124 | Qalah 115/13.8kv Substation | 7465 | Qalah 115/13.8kv Substation-Security Guards for Qalah Site (3 Persons for 1 Year) | APPROVED | No | 2025-08-25 | Abas, Mohammed Fekry | 2025-08-28 | 2025-08-28 |  |  | 2.30 - Security Guards for Qalah Site (3 Persons for 1 Year) | 153000 | 7655 | 0 | STANDARD | Rukn Al Kateibah Company for Security Guards. | SAR | 153000 | APPROVED |  |  | 2025-09-14 | 0 | 17 | Abuhammad, Samir | -45897 | 17
105-124 | Qalah 115/13.8kv Substation | 7556 | Cable Lugs and glands | RETURNED | No | 2025-08-28 | Abdulqader, Ahmed Abdulhalim | 2025-10-02 | 2025-09-03 | 2025-10-02 |  | Not required PO approved in system | 0 | 7619 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 7418.6 | APPROVED |  |  | 2025-09-29 | -7418.6 |  | Abdulqader, Ahmed Abdulhalim | -45903 | 26
105-124 | Qalah 115/13.8kv Substation | 7556 | Cable Lugs and glands | RETURNED | No | 2025-08-28 | Abdulqader, Ahmed Abdulhalim | 2025-10-02 | 2025-09-03 | 2025-10-02 |  | Not required PO approved in system | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45903 | -45903
105-124 | Qalah 115/13.8kv Substation | 7559 | Metal doors & Accessories | REJECTED | No | 2025-08-28 | Sherif, Marwa | 2025-08-28 | 2025-08-28 |  | 2025-09-02 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45897 | -45897
105-124 | Qalah 115/13.8kv Substation | 7571 | Concrete Coring Machine | REJECTED | No | 2025-08-31 | Sherif, Marwa | 2025-08-31 | 2025-08-31 |  | 2025-09-08 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45900 | -45900
105-124 | Qalah 115/13.8kv Substation | 7676 | Relocating of Fence with all Accessories | APPROVED | No | 2025-09-08 | Abas, Mohammed Fekry | 2025-09-16 | 2025-09-21 |  |  | Line Item #2.20, Relocating of Fence with all Accessories | 0 | 7106 | 0 | STANDARD | Construction Expertise Est. | SAR | 30030 | APPROVED |  |  | 2025-10-05 | -30030 | 14 | Abdulqader, Ahmed Abdulhalim | -45921 | 14
105-124 | Qalah 115/13.8kv Substation | 7692 | 3rd Party Lab Inspector for Precast Concrete Production Test | APPROVED | No | 2025-09-09 | Abas, Mohammed Fekry | 2025-09-16 | 2025-09-21 |  |  | Line Item #2.20, 3rd Party Lab Inspector for Precast Concrete Production Test | 0 | 7357 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 84190 | APPROVED |  |  | 2025-10-06 | -84190 | 15 | Tananeh, Khalid Jamal | -45921 | 15
105-124 | Qalah 115/13.8kv Substation | 7746 | DCDB - 2Nos. for Telecom Room_Qalah SS | APPROVED | No | 2025-09-15 | Abas, Mohammed Fekry | 2025-12-01 | 2025-12-02 | 2025-10-06 |  | For modification | 0 | 7975 | 0 | STANDARD | Factory Meaden Al-Khalij for Manufacturing (GTE). | SAR | 25300 | APPROVED |  |  | 2025-12-14 | -25300 | 12 | Abuhammad, Samir | -45993 | 12
105-124 | Qalah 115/13.8kv Substation | 7758 | Lugs and Glands, Rev.02 | APPROVED | No | 2025-09-15 | Abas, Mohammed Fekry | 2025-09-16 | 2025-09-21 |  |  | Line item, 2.13, Lugs and Glands, Rev.02 | 0 | 7619 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 13925.64 | APPROVED |  |  | 2025-09-29 | -13925.64 | 8 | Abdulqader, Ahmed Abdulhalim | -45921 | 8
105-124 | Qalah 115/13.8kv Substation | 7788 | Miscellaneous Requirements (Office Furniture, Filing Cabinet, Steel Table, Etc,.) | APPROVED | No | 2025-09-18 | Abas, Mohammed Fekry | 2025-09-21 | 2025-09-21 |  |  | Line Item #2.33, Miscellaneous Requirements (Office Furniture, Filing Cabinet, Steel Table, Etc,.) | 0 | 7715 | 0 | STANDARD | ALISMAIL INDUSTRIAL CO.(S) | SAR | 17590 | APPROVED |  |  | 2025-10-09 | -17590 | 18 | Abdulqader, Ahmed Abdulhalim | -45921 | 18
105-124 | Qalah 115/13.8kv Substation | 7818 | Supply and Installation of Metal Doors and related accessories | APPROVED | No | 2025-09-24 | Abas, Mohammed Fekry | 2025-10-05 | 2025-10-06 |  |  | Line Item #2.20, Supply and installation of Hollow Metal Doors and Accessories | 0 | 7806 | 0 | STANDARD | AL MANASHY COMPANY | SAR | 132150 | APPROVED |  |  | 2025-10-27 | -132150 | 21 | Abdelraouf, Islam ِAdel Hanafy | -45936 | 21
105-124 | Qalah 115/13.8kv Substation | 7851 | Security Guards for Qalah Site (3 Persons for 6 Months) | APPROVED | No | 2025-09-29 | Abas, Mohammed Fekry | 2025-09-29 | 2025-10-02 |  |  | Line Item #2.30, Security Guards for Qalah Site (3 Persons for 6 Months) | 0 | 7653 | 0 | STANDARD | Saad Al-Gazereh For Security Services Company | SAR | 76500 | APPROVED |  |  | 2025-10-14 | -76500 | 12 | Abuhammad, Samir | -45932 | 12
105-124 | Qalah 115/13.8kv Substation | 7860 | Supply of Clamp & Connectors | APPROVED | No | 2025-09-30 | Abas, Mohammed Fekry | 2025-10-05 | 2025-10-06 |  |  | Line Item #2.13, Supply of Clamp & Connectors | 0 | 7744 | 0 | STANDARD | ENERGY POWER SERVICE TRADING EST. | SAR | 75000 | APPROVED |  |  | 2025-10-14 | -75000 | 8 | Abdulqader, Ahmed Abdulhalim | -45936 | 8
105-124 | Qalah 115/13.8kv Substation | 7919 | Precast supply & Installation, Qalah SS | APPROVED | No | 2025-10-07 | Abas, Mohammed Fekry | 2025-10-08 | 2025-10-08 |  |  | Line Item 2.20, Precast Supply & Installation, Qalah SS. Please note that the old PR #6804, was approved on 22-June-2025 and retruned by Procurement. Hence cancelled the old PR and rasing this new PR for the same subject | 0 | 5393 | 0 | STANDARD | Factory of Ideal Precast Concrete System Company | SAR | 1921165 | APPROVED |  |  | 2025-11-02 | -1921165 | 25 | Tananeh, Khalid Jamal | -45938 | 25
105-124 | Qalah 115/13.8kv Substation | 7920 | Supply, Installation & Testing of 2T JIB Crane, Qalah SS | REJECTED | No | 2025-10-07 | Abdel Naiem, Tarek Ali | 2025-10-07 |  |  | 2025-10-07 | Line 2.17, Supply, Installation & Testing of 2T JIB Crane, Qalah SS (Manual PO attached) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | 0 | 0
105-124 | Qalah 115/13.8kv Substation | 8010 | Swing Gate Motor-Including All Accesssories, Procurement, Installation, testig and commissioning_Qalah SS | APPROVED | No | 2025-10-20 | Abas, Mohammed Fekry | 2025-12-11 | 2025-12-14 | 2025-10-30 |  | missing clear requirements | 0 | 7969 | 0 | STANDARD | ALMOSALLAMY INDUSTRIAL COMPANY | SAR | 9330 | APPROVED |  |  | 2025-12-25 | -9330 | 11 | Abdelraouf, Islam ِAdel Hanafy | -46005 | 11
105-124 | Qalah 115/13.8kv Substation | 8049 | Supply and installaiton of Steel Decoative Fence, Chain link Fence and gate works_Qalah SS | RETURNED | No | 2025-10-26 | Hegazy, Ayman | 2025-11-10 | 2025-10-30 | 2025-11-10 |  | The item descriptions are different from the ACK. PO. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -45960 | -45960
105-124 | Qalah 115/13.8kv Substation | 8155 | Supply & Supply of RoofWaterproofing System &Underground WaterproofingSystem_Qalah SS | RETURNED | No | 2025-11-09 | Tananeh, Khalid Jamal | 2025-11-23 | 2025-11-13 | 2025-11-23 |  | The unit price is 1 SAR, and the total amount shall be 27,302.47 SAR as per the approved POCR and CO value. | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45974 | -45974
105-124 | Qalah 115/13.8kv Substation | 8163 | Supply of Grounding Materials with Accessories_Qalah SS | REJECTED | No | 2025-11-10 | Sherif, Marwa | 2025-11-26 | 2025-11-26 | 2025-11-19 |  | item repeated | 0 | 7097 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 69784.7 | APPROVED |  |  | 2025-12-21 | -69784.7 |  | Abdulqader, Ahmed Abdulhalim | -45987 | 25
105-124 | Qalah 115/13.8kv Substation | 8222 | Hazardous and Non Hazardous Waste Removal_Qalah SS | APPROVED | No | 2025-11-13 | Abas, Mohammed Fekry | 2026-01-21 | 2026-01-22 |  |  | 2.33 - Hazardous and Non Hazardous Waste Removal_Qalah SS | 1 | 15051 | 0 | STANDARD | Expertise Contracting Co. | SAR | 18300 | IN PROCESS | 2026-01-27 | 2026-01-28 |  | -18299 | 10 | Akhtar, Farhan | 6 | -46044
105-124 | Qalah 115/13.8kv Substation | 8222 | Hazardous and Non Hazardous Waste Removal_Qalah SS | APPROVED | No | 2025-11-13 | Abas, Mohammed Fekry | 2026-01-21 | 2026-01-22 |  |  | 2.33 - Hazardous and Non Hazardous Waste Removal_Qalah SS | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -46044 | -46044
105-124 | Qalah 115/13.8kv Substation | 8236 | Decorative steel Fence, Gate along with all Accessories_Qalah SS | APPROVED | No | 2025-11-17 | Abas, Mohammed Fekry | 2025-11-26 | 2025-11-29 |  |  | Line Item 2.20, Decorative Steel Fence, Gate along with all Accessories_Qalah SS | 0 | 6800 | 0 | STANDARD | Fursan Construction Industry Factory Industry Factory | SAR | 390935 | APPROVED |  |  | 2025-12-25 | -390935 | 26 | Hegazy, Ayman | -45990 | 26
105-124 | Qalah 115/13.8kv Substation | 8334 | Supply of Grounding Materials with Accessories_Qalah SS | RETURNED | No | 2025-11-24 | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | 2025-12-25 | 2025-12-02 | 2025-12-25 |  | PR items are already issued in PO 7097 with another PR | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -45993 | -45993
105-124 | Qalah 115/13.8kv Substation | 8384 | 2 TON JIB Crane_Qalah SS | APPROVED | No | 2025-11-27 | Abas, Mohammed Fekry | 2025-12-20 | 2025-12-21 |  |  | Line 2.17, 2 TON JIB Crane_Qalah SS | 0 | 7351 | 0 | STANDARD | SAUDI CRANES & STEEL WORKS FACTORY LTD | SAR | 117000 | APPROVED | 2025-12-24 | 2025-12-31 | 2026-01-05 | -117000 | 15 | Abdulqader, Ahmed Abdulhalim | 10 | 15
105-124 | Qalah 115/13.8kv Substation | 8559 | Supply of Cable Tray, Ladders and accessories for Qalah Substation | RETURNED | No | 2025-12-18 | Mohammed, Mohammed Adel Fahmy | 2026-01-15 | 2026-01-01 | 2026-01-15 | 2025-12-19 | Not Have POCR Until Now and PR incorrect qty. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Mohammed Adel Fahmy | -46023 | -46023
105-124 | Qalah 115/13.8kv Substation | 8576 | Lighting Control System (Motion Sensor)_Qalah SS | APPROVED | No | 2025-12-23 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-13 |  |  | Line Item 2.22, Lighting Control System (Motion Sensor)_Qalah SS | 0 | 7754 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 72407 | INCOMPLETE |  |  |  | -72407 | 19 | Mohammed, Mohammed Adel Fahmy | -46035 | -46035
105-124 | Qalah 115/13.8kv Substation | 8576 | Lighting Control System (Motion Sensor)_Qalah SS | APPROVED | No | 2025-12-23 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-13 |  |  | Line Item 2.22, Lighting Control System (Motion Sensor)_Qalah SS | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Mohammed Adel Fahmy | -46035 | -46035
105-124 | Qalah 115/13.8kv Substation | 8683 | Supply of lighting wires for Qalah Substation | APPROVED | No | 2026-01-11 | Abas, Mohammed Fekry | 2026-01-21 | 2026-01-25 |  |  | 2.13 - Supply of lighting wires for Qalah S/S | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46047 | -46047
105-124 | Qalah 115/13.8kv Substation | 8685 | Supply of wiring devices for Qalah Substation | APPROVED | No | 2026-01-12 | Abas, Mohammed Fekry | 2026-01-21 | 2026-01-25 |  |  | 2.23 - Supply of Wiring Devices for Qalah Substation | 0 | 7887 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 72050 | IN PROCESS | 2026-01-28 | 2026-01-29 |  | -72050 | 7 | Hegazy, Ayman | 4 | -46047
105-124 | Qalah 115/13.8kv Substation | 8685 | Supply of wiring devices for Qalah Substation | APPROVED | No | 2026-01-12 | Abas, Mohammed Fekry | 2026-01-21 | 2026-01-25 |  |  | 2.23 - Supply of Wiring Devices for Qalah Substation | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46047 | -46047
105-124 | Qalah 115/13.8kv Substation | 8808 | Supply of Nonmagnetic Cable clamps for 3x300mm2 MV Cables for Qalah S/S | REJECTED | No | 2026-01-28 | Abdel Naiem, Tarek Ali | 2026-01-28 |  |  | 2026-01-28 | 2.13 - Supply of Nonmagnetic Cable clamps for 3x300mm2 MV Cables for Qalah S/S | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-125 | Uruba 115/13.8kv Substation | 1945 | Uruba 115/13.8kv Substation-Engineering & Design Urba | APPROVED | No | 2023-12-12 | Abas, Mohammed Fekry | 2023-12-13 | 2023-12-13 |  |  |  | 581250 | 4902 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 570000 | APPROVED |  |  | 2024-01-08 | 11250 | 26 | Kumar, Mr. Ranjan | -45273 | 26
105-125 | Uruba 115/13.8kv Substation | 2052 | Uruba 115/13.8kv Substation-Uruba-13.8kV Switch Gear | APPROVED | No | 2023-12-28 | Abas, Mohammed Fekry | 2024-01-01 | 2024-01-01 |  |  |  | 8210000 | 4868 | 0 | STANDARD | ALFANAR CO | SAR | 8210000 | APPROVED |  |  | 2024-01-18 | 0 | 17 | Alhadi, Khalid | -45292 | 17
105-125 | Uruba 115/13.8kv Substation | 2061 | Uruba 115/13.8kv Substation-C&P,SAS for URUBA SS | APPROVED | No | 2023-12-31 | Abas, Mohammed Fekry | 2024-01-02 | 2024-01-02 |  |  |  | 7250000 | 4851 | 0 | STANDARD | ALFANAR CO | SAR | 7250000 | APPROVED |  |  | 2024-01-21 | 0 | 19 | Kumar, Mr. Ranjan | -45293 | 19
105-125 | Uruba 115/13.8kv Substation | 2115 | Uruba 115/13.8kv Substation-Temporary Project Sign Board | APPROVED | No | 2024-01-08 | Abas, Mohammed Fekry | 2024-01-09 | 2024-01-09 |  |  |  | 20000 | 4979 | 0 | STANDARD | Construction Expertise Est. | SAR | 20000 | APPROVED |  |  | 2024-01-17 | 0 | 8 | Alhadi, Khalid | -45300 | 8
105-125 | Uruba 115/13.8kv Substation | 2240 | Uruba 115/13.8kv Substation-Cyber Security | APPROVED | No | 2024-01-21 | Abas, Mohammed Fekry | 2024-01-22 | 2024-01-22 |  |  |  | 1000000 | 5063 | 0 | STANDARD | ALFANAR CO | SAR | 1000000 | APPROVED |  |  | 2024-02-18 | 0 | 27 | Babic, Marian | -45313 | 27
105-125 | Uruba 115/13.8kv Substation | 2461 | Uruba 115/13.8kv Substation-Site Office Facility | APPROVED | No | 2024-02-06 | Abas, Mohammed Fekry | 2024-02-07 | 2024-02-10 |  |  |  | 175000 | 5113 | 0 | STANDARD | Construction Expertise Est. | SAR | 175000 | APPROVED |  |  | 2024-04-02 | 0 | 52 | Muhammad, Muhammad Atif | -45332 | 52
105-125 | Uruba 115/13.8kv Substation | 2464 | Uruba 115/13.8kv Substation-Main AC&DC Panel Boards with Sub Panels | APPROVED | No | 2024-02-06 | Abas, Mohammed Fekry | 2024-02-07 | 2024-02-10 |  |  |  | 450000 | 5407 | 0 | STANDARD | ALFANAR CO | SAR | 450000 | APPROVED |  |  | 2024-04-30 | 0 | 80 | Mohammed, Faisal Ansari | -45332 | 80
105-125 | Uruba 115/13.8kv Substation | 2525 | Uruba 115/13.8kv Substation-Geotechnical Investigation | APPROVED | No | 2024-02-11 | Abas, Mohammed Fekry | 2024-02-11 | 2024-02-12 |  |  |  | 16000 | 5708 | 0 | STANDARD | International Agent Commercial Company(S) | SAR | 16000 | APPROVED |  |  | 2024-06-26 | 0 | 135 | Alhadi, Khalid | -45334 | 135
105-125 | Uruba 115/13.8kv Substation | 2541 | Uruba 115/13.8kv Substation-Super Structure Precast including Fire Walls | APPROVED | No | 2024-02-12 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-19 |  |  |  | 2421479 | 5390 | 0 | STANDARD | Factory of Ideal Precast Concrete System Company | SAR | 2095473 | APPROVED |  |  | 2024-04-30 | 326006 | 71 | Tananeh, Khalid Jamal | -45341 | 71
105-125 | Uruba 115/13.8kv Substation | 2745 | Uruba 115/13.8kv Substation-Main AC/DC Panel Boards Including Sub DB's, Indoor and Outdoor Lighting Panels | APPROVED | No | 2024-03-04 | Abas, Mohammed Fekry | 2024-03-05 | 2024-03-07 |  |  |  | 420000 | 5407 | 0 | STANDARD | ALFANAR CO | SAR | 420000 | APPROVED |  |  | 2024-04-30 | 0 | 54 | Mohammed, Faisal Ansari | -45358 | 54
105-125 | Uruba 115/13.8kv Substation | 2776 | Uruba 115/13.8kv Substation-Temporary Fencing and Gate Works | APPROVED | No | 2024-03-05 | Abas, Mohammed Fekry | 2024-03-06 | 2024-03-07 |  |  |  | 91650 | 5312 | 0 | STANDARD | Construction Expertise Est. | SAR | 91650 | APPROVED |  |  | 2024-04-08 | 0 | 32 | Alhadi, Khalid | -45358 | 32
105-125 | Uruba 115/13.8kv Substation | 2866 | Uruba 115/13.8kv Substation-Site Offices (Additional PR) | APPROVED | No | 2024-03-20 | Abas, Mohammed Fekry | 2024-03-21 | 2024-03-24 |  |  |  | 17080 | 5113 | 0 | STANDARD | Construction Expertise Est. | SAR | 17080 | APPROVED |  |  | 2024-04-02 | 0 | 9 | Muhammad, Muhammad Atif | -45375 | 9
105-125 | Uruba 115/13.8kv Substation | 3043 | Uruba 115/13.8kv Substation-5 Ton Over Head Travelling Crane with all required Accessories | APPROVED | No | 2024-04-16 | Abas, Mohammed Fekry | 2024-04-17 | 2024-04-24 |  |  |  | 130000 | 5467 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 126870 | APPROVED |  |  | 2024-05-16 | 3130 | 22 | Muhammad, Muhammad Atif | -45406 | 22
105-125 | Uruba 115/13.8kv Substation | 3097 | Uruba 115/13.8kv Substation-Topographic Survey of Project Area | APPROVED | No | 2024-04-22 | Abas, Mohammed Fekry | 2024-04-25 | 2024-04-25 |  |  |  | 5125 | 5720 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 5125 | APPROVED |  |  | 2024-07-01 | 0 | 67 | Alhadi, Khalid | -45407 | 67
105-125 | Uruba 115/13.8kv Substation | 3134 | Uruba 115/13.8kv Substation-Supply & Apply of Roof Waterproofing System & Underground Waterproofing System | APPROVED | No | 2024-04-25 | Abas, Mohammed Fekry | 2024-04-25 | 2024-04-28 |  |  |  | 355000 | 5650 | 0 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 347826.5 | APPROVED |  |  | 2024-06-13 | 7173.5 | 46 | Tananeh, Khalid Jamal | -45410 | 46
105-125 | Uruba 115/13.8kv Substation | 3357 | Uruba 115/13.8kv Substation-Rentel Generator, 400kVA, 3Ph, 380V, 60Hz, for 3 Months | APPROVED | No | 2024-05-09 | Abas, Mohammed Fekry | 2024-05-12 | 2024-05-13 |  |  |  | 34998 | 5541 | 0 | STANDARD | Nour Communications Co. | SAR | 28500 | APPROVED |  |  | 2024-05-21 | 6498 | 8 | Akhtar, Farhan | -45425 | 8
105-125 | Uruba 115/13.8kv Substation | 3365 | Uruba 115/13.8kv Substation-Electronic Materials requirments for Site Office | APPROVED | No | 2024-05-09 | Sherif, Marwa | 2024-06-03 | 2024-06-03 |  |  |  | 33800 | 5688 | 0 | STANDARD | Construction Expertise Est. | SAR | 33800 | APPROVED |  |  | 2024-07-02 | 0 | 29 | Muhammad, Muhammad Atif | -45446 | 29
105-125 | Uruba 115/13.8kv Substation | 3382 | Uruba 115/13.8kv Substation-150Sq.mm Tinned Copper Conductor | APPROVED | No | 2024-05-12 | Abas, Mohammed Fekry | 2024-05-16 | 2024-05-17 |  |  |  | 38500 | 5359 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 38455.41 | APPROVED |  |  | 2024-05-27 | 44.59 | 10 | Muhammad, Muhammad Atif | -45429 | 10
105-125 | Uruba 115/13.8kv Substation | 3520 | Uruba 115/13.8kv Substation-Batteries & Chargers | APPROVED | No | 2024-05-28 | Sherif, Marwa | 2024-06-03 | 2024-06-05 |  |  |  | 550000 | 5744 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 457000 | APPROVED |  |  | 2024-07-10 | 93000 | 35 | Muhammad, Muhammad Atif | -45448 | 35
105-125 | Uruba 115/13.8kv Substation | 3656 | Uruba 115/13.8kv Substation-Grounding Material & Accessories | APPROVED | No | 2024-06-13 | Issa, Amr Ali | 2024-07-02 | 2024-07-03 |  |  |  | 73475 | 5562 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 72850 | APPROVED |  |  | 2024-07-12 | 625 | 9 | Muhammad, Muhammad Atif | -45476 | 9
105-125 | Uruba 115/13.8kv Substation | 3696 | Uruba 115/13.8kv Substation-Supply of Non Potable Water for Site offices Use | APPROVED | No | 2024-06-30 | Abas, Mohammed Fekry | 2024-07-05 | 2024-07-07 |  |  |  | 18000 | 5841 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 16800 | APPROVED |  |  | 2024-08-01 | 1200 | 25 | Akhtar, Farhan | -45480 | 25
105-125 | Uruba 115/13.8kv Substation | 3789 | Uruba 115/13.8kv Substation-Garbage Waste Container, 12 Cu. M (1-year) | APPROVED | No | 2024-07-07 | Abas, Mohammed Fekry | 2024-07-09 | 2024-07-09 |  |  |  | 28800 | 5959 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 19200 | APPROVED |  |  | 2024-08-20 | 9600 | 42 | Akhtar, Farhan | -45482 | 42
105-125 | Uruba 115/13.8kv Substation | 3863 | Uruba 115/13.8kv Substation-Control Cables | APPROVED | No | 2024-07-12 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 716000 | 5830 | 0 | STANDARD | ALFANAR CO | SAR | 531752.8 | APPROVED |  |  | 2024-08-28 | 184247.2 | 43 | Muhammad, Muhammad Atif | -45489 | 43
105-125 | Uruba 115/13.8kv Substation | 3917 | Uruba 115/13.8kv Substation-RTV Coating for Transformer HV Busings and GIB HV Bushings | APPROVED | No | 2024-07-16 | Malek, Warren | 2024-07-25 | 2024-07-25 |  |  |  | 250000 | 6182 | 0 | STANDARD | SAUDI CONDUIT COATING CO. (S3C) | SAR | 35268 | APPROVED |  |  | 2024-10-13 | 214732 | 80 | Muaz, Alaa | -45498 | 80
105-125 | Uruba 115/13.8kv Substation | 3921 | Uruba 115/13.8kv Substation-Testing & Commissioning Works | APPROVED | No | 2024-07-16 | Malek, Warren | 2024-07-25 | 2024-07-25 |  |  |  | 1860297 | 6451 | 0 | STANDARD | Al Fanar Technical Services | SAR | 1808041 | APPROVED |  |  | 2025-02-25 | 52256 | 215 | Alqadhi, Abdulrahman Abdulghani | -45498 | 215
105-125 | Uruba 115/13.8kv Substation | 3925 | Uruba 115/13.8kv Substation-MV Termination Kits | APPROVED | No | 2024-07-16 | Malek, Warren | 2024-07-25 | 2024-07-25 |  |  |  | 98839 | 5990 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 95871.89 | APPROVED |  |  | 2024-09-19 | 2967.11 | 56 | Badhman, Saeed | -45498 | 56
105-125 | Uruba 115/13.8kv Substation | 4059 | Uruba 115/13.8kv Substation-Cable Trays, Ladders and related accessories | APPROVED | No | 2024-07-30 | Abas, Mohammed Fekry | 2024-08-01 | 2024-08-01 |  |  |  | 552885 | 5920 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 505784.96 | APPROVED |  |  | 2024-09-18 | 47100.04 | 48 | Muhammad, Muhammad Atif | -45505 | 48
105-125 | Uruba 115/13.8kv Substation | 4074 | Uruba 115/13.8kv Substation-Lighting Cum Lightning Mast | APPROVED | No | 2024-08-01 | Abas, Mohammed Fekry | 2024-08-03 | 2024-08-04 |  |  |  | 59075 | 6035 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 59075 | APPROVED |  |  | 2024-10-07 | 0 | 64 | Badhman, Saeed | -45508 | 64
105-125 | Uruba 115/13.8kv Substation | 4200 | Uruba 115/13.8kv Substation-Hazardous and Non Hazardous Waste Collection | APPROVED | No | 2024-08-19 | Issa, Amr Ali | 2024-08-25 | 2024-08-25 |  |  |  | 5000 | 6125 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 3650 | APPROVED |  |  | 2024-09-19 | 1350 | 25 | Akhtar, Farhan | -45529 | 25
105-125 | Uruba 115/13.8kv Substation | 4222 | Uruba 115/13.8kv Substation-LV AC / DC Cable and Lighting Wires | APPROVED | No | 2024-08-19 | Issa, Amr Ali | 2024-08-25 | 2024-08-25 |  |  |  | 1611070 | 6085 | 0 | STANDARD | ALFANAR CO | SAR | 1110509.38 | APPROVED |  |  | 2024-10-06 | 500560.62 | 42 | Badhman, Saeed | -45529 | 42
105-125 | Uruba 115/13.8kv Substation | 4242 | Uruba 115/13.8kv Substation-Grounding Conductor and Cables | APPROVED | No | 2024-08-21 | Abas, Mohammed Fekry | 2024-08-27 | 2024-09-01 |  |  |  | 244150 | 6069 | 0 | STANDARD | ALFANAR CO | SAR | 226756.52 | APPROVED |  |  | 2024-09-24 | 17393.48 | 23 | Muhammad, Muhammad Atif | -45536 | 23
105-125 | Uruba 115/13.8kv Substation | 4362 | Uruba 115/13.8kv Substation-3rd Party Inspector For Precast Concrete Production Lab Test | APPROVED | No | 2024-09-04 | Abas, Mohammed Fekry | 2024-09-22 | 2024-09-22 |  |  |  | 84190 | 6302 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 84190 | APPROVED |  |  | 2024-10-06 | 0 | 14 | Tananeh, Khalid Jamal | -45557 | 14
105-125 | Uruba 115/13.8kv Substation | 4364 | Uruba 115/13.8kv Substation-Station Service Transformer 750kVA | APPROVED | No | 2024-09-04 | Abas, Mohammed Fekry | 2024-09-09 | 2024-09-09 |  |  |  | 164000 | 5913 | 0 | STANDARD | ALFANAR CO | SAR | 164000 | APPROVED |  |  | 2024-10-08 | 0 | 29 | Muhammad, Muhammad Atif | -45544 | 29
105-125 | Uruba 115/13.8kv Substation | 4444 | Uruba 115/13.8kv Substation-Fire Alarm & Fire Suppression System | APPROVED | No | 2024-09-14 | Abas, Mohammed Fekry | 2024-09-17 | 2024-09-17 |  |  |  | 2095567 | 5997 | 0 | STANDARD | Reda Trading & Development Co. for Machinery & Equipment Ltd(S) | SAR | 2095567 | APPROVED |  |  | 2024-09-26 | 0 | 9 | Muhammad, Muhammad Atif | -45552 | 9
105-125 | Uruba 115/13.8kv Substation | 4470 | Uruba 115/13.8kv Substation-Excavation and Bakfilling Works | APPROVED | No | 2024-09-18 | Abas, Mohammed Fekry | 2024-09-19 | 2024-09-22 |  |  |  | 346912 | 5267 | 0 | STANDARD | Eastern Union Contracting Est | SAR | 346912 | APPROVED |  |  | 2024-11-03 | 0 | 42 | Alhadi, Khalid | -45557 | 42
105-125 | Uruba 115/13.8kv Substation | 4595 | Uruba 115/13.8kv Substation-Electrical Installation - Contract | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-09 |  |  |  | 2992521 | 6371 | 0 | STANDARD | Hussain Ali Hussain Contracting Company | SAR | 2280085 | APPROVED |  |  | 2025-01-07 | 712436 | 90 | Muhammad, Muhammad Atif | -45574 | 90
105-125 | Uruba 115/13.8kv Substation | 4645 | Uruba 115/13.8kv Substation-13.8kV MV Power Cable | APPROVED | No | 2024-10-09 | Abas, Mohammed Fekry | 2024-10-23 | 2024-10-27 |  |  |  | 1223740 | 6403 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 1093970.6 | APPROVED |  |  | 2024-11-10 | 129769.4 | 14 | Badhman, Saeed | -45592 | 14
105-125 | Uruba 115/13.8kv Substation | 4755 | Uruba 115/13.8kv Substation-Complete Substation HVAC System Works | APPROVED | No | 2024-10-21 | Abas, Mohammed Fekry | 2024-11-04 | 2024-11-04 |  |  |  | 2220000 | 6205 | 0 | STANDARD | Ramz Alataa Company for Trading | SAR | 2050000 | APPROVED |  |  | 2024-11-14 | 170000 | 10 | Muhammad, Muhammad Atif | -45600 | 10
105-125 | Uruba 115/13.8kv Substation | 4926 | Uruba 115/13.8kv Substation-Sewage Water Removal Services, 10000 Ltrs - 10 Trips | APPROVED | No | 2024-11-13 | Abas, Mohammed Fekry | 2024-11-17 | 2024-11-17 |  |  |  | 3500 | 6525 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 3000 | APPROVED |  |  | 2024-12-01 | 500 | 14 | Akhtar, Farhan | -45613 | 14
105-125 | Uruba 115/13.8kv Substation | 4963 | Uruba 115/13.8kv Substation-Supply of Indoor & Outdoor Lighting fixtures | APPROVED | No | 2024-11-17 | Abas, Mohammed Fekry | 2024-11-20 | 2024-11-20 |  |  |  | 88037 | 6476 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 88037 | APPROVED |  |  | 2024-11-28 | 0 | 8 | Muhammad, Muhammad Atif | -45616 | 8
105-125 | Uruba 115/13.8kv Substation | 5034 | Uruba 115/13.8kv Substation-3rd Party Inspector For Precast Concrete Production Lab Test | APPROVED | No | 2024-11-24 | Abas, Mohammed Fekry | 2024-11-28 | 2024-11-28 |  |  |  | 84190 | 6745 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 84190 | APPROVED |  |  | 2025-02-04 | 0 | 68 | Tananeh, Khalid Jamal | -45624 | 68
105-125 | Uruba 115/13.8kv Substation | 5083 | Uruba 115/13.8kv Substation-HCIS Consultancy for Security System | APPROVED | No | 2024-11-28 | Abas, Mohammed Fekry | 2025-01-15 | 2025-01-16 |  |  |  | 33500 | 6515 | 0 | STANDARD | Khaled Drewesh Office for Consulting Security (KDOCS) | SAR | 33500 | APPROVED |  |  | 2025-03-09 | 0 | 52 | Abdulqader, Ahmed Abdulhalim | -45673 | 52
105-125 | Uruba 115/13.8kv Substation | 5196 | Uruba 115/13.8kv Substation-HV Clamps & Connectors / Terminal Hardwares | APPROVED | No | 2024-12-08 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-12 |  |  |  | 4616 | 6422 | 0 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 4505.16 | APPROVED |  |  | 2025-01-02 | 110.84 | 21 | Mohammed, Faisal Ansari | -45638 | 21
105-125 | Uruba 115/13.8kv Substation | 5237 | Uruba 115/13.8kv Substation-150Sq.mm Tinned Copper Conductor for Substation Grid Earthing | APPROVED | No | 2024-12-16 | Abas, Mohammed Fekry | 2024-12-22 | 2024-12-25 |  |  |  | 114000 | 6757 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 105484.8 | APPROVED |  |  | 2025-02-25 | 8515.2 | 62 | Alhadi, Khalid | -45651 | 62
105-125 | Uruba 115/13.8kv Substation | 5252 | Uruba 115/13.8kv Substation-Raw Water Supply for site & Accomodation, 10000 Liters/Trip for 6 months | APPROVED | No | 2024-12-22 | Abas, Mohammed Fekry | 2024-12-23 | 2024-12-25 |  |  |  | 21000 | 6705 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 21000 | APPROVED |  |  | 2025-01-02 | 0 | 8 | Akhtar, Farhan | -45651 | 8
105-125 | Uruba 115/13.8kv Substation | 5252 | Uruba 115/13.8kv Substation-Raw Water Supply for site & Accomodation, 10000 Liters/Trip for 6 months | APPROVED | No | 2024-12-22 | Abas, Mohammed Fekry | 2024-12-23 | 2024-12-25 |  |  |  | 21000 | 6705 | 1 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 21000 | REQUIRES REAPPROVAL |  |  |  | 0 | 403 | Akhtar, Farhan | -45651 | -45651
105-125 | Uruba 115/13.8kv Substation | 5260 | Uruba 115/13.8kv Substation-Supply and Installation of Boundary Fence Works | APPROVED | No | 2024-12-23 | Abas, Mohammed Fekry | 2024-12-29 | 2024-12-30 |  |  |  | 639818 | 5642 | 1 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 639818 | APPROVED |  |  | 2025-11-18 | 0 | 323 | Hegazy, Ayman | -45656 | 323
105-125 | Uruba 115/13.8kv Substation | 5320 | Uruba 115/13.8kv Substation-7X2.5 Sq.mm, Control Cabels for SAS Alarm (with Blue Color wires) | APPROVED | No | 2025-01-01 | Abas, Mohammed Fekry | 2025-01-06 | 2025-01-06 |  |  |  | 55000 | 6787 | 0 | STANDARD | ALFANAR CO | SAR | 52600 | APPROVED |  |  | 2025-04-16 | 2400 | 100 | Muaz, Alaa | -45663 | 100
105-125 | Uruba 115/13.8kv Substation | 5330 | Uruba 115/13.8kv Substation-Supply of Conduits and Fittings | APPROVED | No | 2025-01-02 | Abas, Mohammed Fekry | 2025-01-06 | 2025-01-06 |  |  |  | 342909.3 | 6691 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 342909.3 | APPROVED |  |  | 2025-01-22 | 0 | 16 | Muaz, Alaa | -45663 | 16
105-125 | Uruba 115/13.8kv Substation | 5611 | Uruba 115/13.8kv Substation-FO Cables and Patch Cords | APPROVED | No | 2025-01-26 | Abas, Mohammed Fekry | 2025-01-28 | 2025-01-30 |  |  |  | 300000 | 7028 | 0 | STANDARD | RASHID SAEED AHMED AL GHAMDI COMM INFO TRAD EST | SAR | 210000 | APPROVED |  |  | 2025-04-16 | 90000 | 76 | Abdulqader, Ahmed Abdulhalim | -45687 | 76
105-125 | Uruba 115/13.8kv Substation | 5719 | Uruba 115/13.8kv Substation-CTPU & CTPU BOX | APPROVED | No | 2025-01-29 | Abas, Mohammed Fekry | 2025-02-02 | 2025-02-05 |  |  |  | 68000 | 6291 | 0 | STANDARD | Energy Tracks For Contracting | SAR | 68000 | APPROVED |  |  | 2025-03-02 | 0 | 25 | Kumar, Mr. Ranjan | -45693 | 25
105-125 | Uruba 115/13.8kv Substation | 5781 | Uruba 115/13.8kv Substation-Sub Contractor for Complete Civil Works (Main Scope) | APPROVED | No | 2025-02-04 | Abas, Mohammed Fekry | 2025-02-08 | 2025-02-09 |  |  |  | 9600000 | 5642 | 0 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 9600000 | APPROVED |  |  | 2025-02-24 | 0 | 15 | Tananeh, Khalid Jamal | -45697 | 15
105-125 | Uruba 115/13.8kv Substation | 5921 | Uruba 115/13.8kv Substation-Security System Complete as per HCIS Standard and Requirment | APPROVED | No | 2025-02-17 | Abas, Mohammed Fekry | 2025-02-19 | 2025-02-19 |  |  |  | 795249 | 6626 | 0 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 795249 | APPROVED |  |  | 2025-03-05 | 0 | 14 | Abdulqader, Ahmed Abdulhalim | -45707 | 14
105-125 | Uruba 115/13.8kv Substation | 6064 | Uruba 115/13.8kv Substation-Shifting of Temporary Site Fence | APPROVED | No | 2025-02-26 | Abas, Mohammed Fekry | 2025-05-22 | 2025-05-27 |  |  | Line Item # 2.20, Shifting of Temporary Site Fence | 41450 | 7105 | 0 | STANDARD | Construction Expertise Est. | SAR | 30030 | APPROVED |  |  | 2025-08-17 | 11420 | 82 | Abdulqader, Ahmed Abdulhalim | -45804 | 82
105-125 | Uruba 115/13.8kv Substation | 6097 | Uruba 115/13.8kv Substation-IFC Drawings, A2 Size, Printing, Scanning and Copying | APPROVED | No | 2025-03-03 | Abas, Mohammed Fekry | 2025-03-04 | 2025-03-05 |  |  | Line Item #2.33, IFC Drawings, A2 Size, Printing, Scanning and Copying | 31000 | 7059 | 0 | STANDARD | Print Magaies Al abdaa Printing | SAR | 30999 | APPROVED |  |  | 2025-04-07 | 1 | 33 | Abuhammad, Samir | -45721 | 33
105-125 | Uruba 115/13.8kv Substation | 6463 | Uruba 115/13.8kv Substation-Supply & install Gypsum board Partitions for URUBA SS | APPROVED | No | 2025-04-27 | Abas, Mohammed Fekry | 2025-04-30 | 2025-05-04 |  |  | 2.20 - Supply & Install Gypsum board partition at URUBA SS | 6000 | 7205 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 6000 | APPROVED |  |  | 2025-05-07 | 0 | 3 | Abuhammad, Samir | -45781 | 3
105-125 | Uruba 115/13.8kv Substation | 6463 | Uruba 115/13.8kv Substation-Supply & install Gypsum board Partitions for URUBA SS | APPROVED | No | 2025-04-27 | Abas, Mohammed Fekry | 2025-04-30 | 2025-05-04 |  |  | 2.20 - Supply & Install Gypsum board partition at URUBA SS | 6000 | 7246 | 0 | STANDARD | Tamim Company (PVT) LTD | SAR | 6000 | APPROVED |  |  | 2025-05-12 | 0 | 8 | Abuhammad, Samir | -45781 | 8
105-125 | Uruba 115/13.8kv Substation | 6572 | Uruba 115/13.8kv Substation-4P x 1.5mm2 Cu/XLPE/CT/PVC 0.6/1kV Gray Control Cables with Numbering for URUBA SS | APPROVED | No | 2025-05-10 | Abas, Mohammed Fekry | 2025-05-12 | 2025-05-14 |  |  | 2.13 - 4Px1.5mm2 Cu/XLPE/CT/PVC 0.6/1kV Gray Control Cables with Numbering for URUBA SS | 9000 | 7320 | 0 | STANDARD | Middle East Specialized Cables Mesc | SAR | 7500 | APPROVED |  |  | 2025-05-27 | 1500 | 13 | Abuhammad, Samir | -45791 | 13
105-125 | Uruba 115/13.8kv Substation | 6587 | Uruba 115/13.8kv Substation-Asphalt Works for URUBA Substation | APPROVED | No | 2025-05-11 | Abas, Mohammed Fekry | 2025-05-22 | 2025-05-27 |  |  | 2.20 - Asphalt Works | 406750 | 5642 | 1 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 406750 | APPROVED |  |  | 2025-11-18 | 0 | 175 | Hegazy, Ayman | -45804 | 175
105-125 | Uruba 115/13.8kv Substation | 6632 | Uruba 115/13.8kv Substation-Standing AC units 5 Tons | APPROVED | No | 2025-05-18 | Abas, Mohammed Fekry | 2025-05-22 | 2025-05-27 |  |  | 2.33, Standing AC units 5 Tons | 72000 | 7251 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 61600 | APPROVED |  |  | 2025-06-01 | 10400 | 5 | Abuhammad, Samir | -45804 | 5
105-125 | Uruba 115/13.8kv Substation | 6662 | Uruba 115/13.8kv Substation-Supply For Fire stop materials for URUBA Substation | APPROVED | No | 2025-05-19 | Abas, Mohammed Fekry | 2025-05-25 | 2025-05-26 |  |  | 2.2 - Supply For Fire stop materials for URUBA Substation | 83375 | 7334 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 72500 | APPROVED |  |  | 2025-09-17 | 10875 | 114 | Tananeh, Khalid Jamal | -45803 | 114
105-125 | Uruba 115/13.8kv Substation | 6731 | Uruba 115/13.8kv Substation-2.2 - Metal Doors and Hardware Fittings (Activate Optional Scope in PO#5642) | APPROVED | No | 2025-05-27 | Abas, Mohammed Fekry | 2025-05-28 | 2025-05-28 |  |  | 2.2 - Metal Doors and Hardware Fittings for URUBA SS (Activate Optional Scope in PO#5642 | 117585 | 5642 | 1 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 117585 | APPROVED |  |  | 2025-11-18 | 0 | 174 | Hegazy, Ayman | -45805 | 174
105-125 | Uruba 115/13.8kv Substation | 6790 | Uruba 115/13.8kv Substation-Telecommunication System | APPROVED | No | 2025-06-12 | Abas, Mohammed Fekry | 2025-06-16 | 2025-06-16 |  |  | Line Item #2.4, Telecommunication System | 2058683.49 | 5855 | 0 | STANDARD | ALFANAR CO | SAR | 2058683.49 | APPROVED |  |  | 2025-06-24 | 0 | 8 | Kumar, Mr. Ranjan | -45824 | 8
105-125 | Uruba 115/13.8kv Substation | 6793 | Uruba 115/13.8kv Substation-FDT Testing for 340 Points and 34 visits | RETURNED | No | 2025-06-12 | Tananeh, Khalid Jamal | 2025-09-22 | 2025-06-16 | 2025-09-22 |  | "The PR are being returned in reference to the email sent on Tuesday, 09/09/2025 at 4:14 PM, as the works were carried out without prior approval from the Procurement Department and the payment shall be made from petty cash." | 12750 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45824 | -45824
105-125 | Uruba 115/13.8kv Substation | 6898 | Uruba 115/13.8kv Substation-Safety Miscellaneous Materials (Breathing Apparatus-1No., Fire Blankets-3Nos, First Aid Box - 1No., Stretcher - 1No.) | RETURNED | No | 2025-06-25 | Akhtar, Farhan | 2025-10-12 | 2025-07-01 | 2025-10-12 |  | No responce from the Poject team | 60000 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45839 | -45839
105-125 | Uruba 115/13.8kv Substation | 6921 | Uruba 115/13.8kv Substation-Switches & Sockets (Wiring Devices) | APPROVED | No | 2025-06-29 | Abas, Mohammed Fekry | 2025-07-01 | 2025-07-01 |  |  | Line Item #2.23, Switches & Sockets (Wiring Devices) | 96720 | 7176 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 96720 | APPROVED |  |  | 2025-07-14 | 0 | 13 | Muaz, Alaa | -45839 | 13
105-125 | Uruba 115/13.8kv Substation | 6987 | Uruba 115/13.8kv Substation-Manpower supply - Testing Technicians, 6 Persons for 3 months | APPROVED | No | 2025-07-06 | Abas, Mohammed Fekry | 2025-07-12 | 2025-07-12 |  |  | 2.31 - Manpower supply - Testing Technicians, 6 Persons for 3 months | 131040 | 7508 | 0 | STANDARD | Jasem M.AlJasem Contracting Est. | SAR | 131040 | APPROVED |  |  | 2025-08-02 | 0 | 21 | Babic, Marian | -45850 | 21
105-125 | Uruba 115/13.8kv Substation | 7029 | Uruba 115/13.8kv Substation-Supply of Clamps/cleats for MV cables | APPROVED | No | 2025-07-09 | Abas, Mohammed Fekry | 2025-07-13 | 2025-07-14 |  |  | Line Item #2.13, Supply of Clamps/cleats for MV cables | 56525 | 7394 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 56525 | APPROVED |  |  | 2025-07-28 | 0 | 14 | Hegazy, Ayman | -45852 | 14
105-125 | Uruba 115/13.8kv Substation | 7036 | Uruba 115/13.8kv Substation-Supply of HV & MV Cable Supports | APPROVED | No | 2025-07-09 | Abas, Mohammed Fekry | 2025-07-13 | 2025-07-14 |  |  | Line Item #2.19, Supply of HV & MV Cable Supports | 70086.5 | 7382 | 0 | STANDARD | ISAM KABBANI &Partners | SAR | 70086.5 | APPROVED |  |  | 2025-07-28 | 0 | 14 | Hegazy, Ayman | -45852 | 14
105-125 | Uruba 115/13.8kv Substation | 7043 | Uruba 115/13.8kv Substation-Supply of Diesel for Generator at Site | RETURNED | No | 2025-07-09 | Akhtar, Farhan | 2025-07-23 | 2025-07-14 | 2025-07-23 |  | As per PMT not required the diesel | 14890 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45852 | -45852
105-125 | Uruba 115/13.8kv Substation | 7068 | Uruba 115/13.8kv Substation-Laboratory Testing of Transformer Oils | APPROVED | No | 2025-07-13 | Abas, Mohammed Fekry | 2025-07-15 | 2025-07-16 |  |  | 2.38, Laboratory Testing of Transformer Oils | 37300 | 7534 | 0 | STANDARD | Saudi Arabian Engineering Company | SAR | 37300 | APPROVED |  |  | 2025-08-03 | 0 | 18 | Abdulqader, Ahmed Abdulhalim | -45854 | 18
105-125 | Uruba 115/13.8kv Substation | 7120 | Uruba 115/13.8kv Substation-Complete PDS System | APPROVED | No | 2025-07-17 | Abas, Mohammed Fekry | 2025-07-22 | 2025-07-22 |  |  | 2.5, PDS System | 250000 | 7764 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 140000 | APPROVED |  |  | 2025-11-18 | 110000 | 119 | Hegazy, Ayman | -45860 | 119
105-125 | Uruba 115/13.8kv Substation | 7128 | Uruba 115/13.8kv Substation-Rental Safety office for 3 months | RETURNED | No | 2025-07-17 | Alhadi, Khalid | 2025-10-05 | 2025-08-10 | 2025-10-05 |  | No feedback from project manager and approved CV's from Safety manager | 18200 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45879 | -45879
105-125 | Uruba 115/13.8kv Substation | 7217 | Uruba 115/13.8kv Substation-Supply and delivery of Raw Water to Uruba Site- 10000 Litres/Trip - 60 Trips | APPROVED | No | 2025-07-27 | Abas, Mohammed Fekry | 2025-08-03 | 2025-08-03 |  |  | 2.33 Supply and delivery of Raw Water - 10000 Litres/Trip - 60 Trips | 18000 | 7554 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 18000 | APPROVED |  |  | 2025-08-17 | 0 | 14 | Akhtar, Farhan | -45872 | 14
105-125 | Uruba 115/13.8kv Substation | 7349 | Uruba 115/13.8kv Substation-Rental of T&C coordinator for URUBA S/S | RETURNED | No | 2025-08-13 | Alhadi, Khalid | 2025-10-05 | 2025-09-21 | 2025-10-05 |  | No feedback from T&C manager | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45921 | -45921
105-125 | Uruba 115/13.8kv Substation | 7472 | Cable Glands and Lugs | INCOMPLETE | No | [6 empty] | No feedback from T&C manager | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | 0 | 0
105-125 | Uruba 115/13.8kv Substation | 7540 | Lugs and Glands | RETURNED | No | 2025-08-27 | Abdulqader, Ahmed Abdulhalim | 2025-10-02 | 2025-09-03 | 2025-10-02 |  | Not required PO approved in system | 0 | 7621 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 18507.3 | APPROVED |  |  | 2025-09-29 | -18507.3 |  | Abdulqader, Ahmed Abdulhalim | -45903 | 26
105-125 | Uruba 115/13.8kv Substation | 7540 | Lugs and Glands | RETURNED | No | 2025-08-27 | Abdulqader, Ahmed Abdulhalim | 2025-10-02 | 2025-09-03 | 2025-10-02 |  | Not required PO approved in system | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45903 | -45903
105-125 | Uruba 115/13.8kv Substation | 7689 | Rental Technicians - 10 Nos. | APPROVED | No | 2025-09-09 | Abas, Mohammed Fekry | 2025-09-16 | 2025-09-21 |  |  | Line Item 2.31, Rental Technicians - 10 Nos. | 0 | 7508 | 1 | STANDARD | Jasem M.AlJasem Contracting Est. | SAR | 151160 | IN PROCESS | 2025-11-27 | 2026-01-20 |  | -151160 | 133 | Babic, Marian | 121 | -45921
105-125 | Uruba 115/13.8kv Substation | 7689 | Rental Technicians - 10 Nos. | APPROVED | No | 2025-09-09 | Abas, Mohammed Fekry | 2025-09-16 | 2025-09-21 |  |  | Line Item 2.31, Rental Technicians - 10 Nos. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45921 | -45921
105-125 | Uruba 115/13.8kv Substation | 7744 | DCDB - 2Nos. for Telecom Room_Uruba SS | APPROVED | No | 2025-09-15 | Abas, Mohammed Fekry | 2025-12-01 | 2025-12-02 | 2025-09-25 |  | As per PM request | 0 | 7738 | 0 | STANDARD | Factory Meaden Al-Khalij for Manufacturing (GTE). | SAR | 25300 | APPROVED |  |  | 2025-12-14 | -25300 | 12 | Abuhammad, Samir | -45993 | 12
105-125 | Uruba 115/13.8kv Substation | 7756 | Lugs and Glands, Rev.02 | APPROVED | No | 2025-09-15 | Abas, Mohammed Fekry | 2025-09-16 | 2025-09-21 |  |  | Line 2.13, Lugs and Glands, Rev.02 | 0 | 7621 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 1281.84 | APPROVED |  |  | 2025-09-29 | -1281.84 | 8 | Abdulqader, Ahmed Abdulhalim | -45921 | 8
105-125 | Uruba 115/13.8kv Substation | 7766 | Miscellaneous Materials - Office Supply Materials to SS | APPROVED | No | 2025-09-16 | Abas, Mohammed Fekry | 2025-09-21 | 2025-09-21 |  |  | Line item #2.33, Miscellaneous Materials - Office Supply Materials to SS | 0 | 7694 | 0 | STANDARD | ALISMAIL INDUSTRIAL CO.(S) | SAR | 17590 | APPROVED |  |  | 2025-10-09 | -17590 | 18 | Abdulqader, Ahmed Abdulhalim | -45921 | 18
105-125 | Uruba 115/13.8kv Substation | 7853 | Metal Works (Optional Scope Activation in PO #5642) | APPROVED | No | 2025-09-29 | Abas, Mohammed Fekry | 2025-09-29 | 2025-10-02 |  |  | Line Item #2.20, Metal Works (Optional Scope Activation in PO #5642) | 0 | 5642 | 1 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 370120 | APPROVED |  |  | 2025-11-18 | -370120 | 47 | Hegazy, Ayman | -45932 | 47
105-125 | Uruba 115/13.8kv Substation | 8008 | Swing Gate Motor-Including All Accesssories, Procurement, Installation, testig and commissioning_Uruba SS | APPROVED | No | 2025-10-20 | Abas, Mohammed Fekry | 2025-12-11 | 2025-12-14 | 2025-10-30 |  | missing clear requirements | 0 | 7968 | 0 | STANDARD | ALMOSALLAMY INDUSTRIAL COMPANY | SAR | 9330 | APPROVED |  |  | 2025-12-25 | -9330 | 11 | Abdelraouf, Islam ِAdel Hanafy | -46005 | 11
105-125 | Uruba 115/13.8kv Substation | 8162 | Supply of Groundign Materials with Accessories_Uruba SS | APPROVED | No | 2025-11-10 | Abas, Mohammed Fekry | 2025-11-12 | 2025-11-13 |  |  | Line Item, 2.21, Supply of Grounding Materials with Accessories_Uruba SS | 0 | 7076 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 48097.2 | APPROVED |  |  | 2025-12-21 | -48097.2 | 38 | Abdulqader, Ahmed Abdulhalim | -45974 | 38
105-125 | Uruba 115/13.8kv Substation | 8574 | Lighting Control System (Motion Sensor)_Uruba SS | APPROVED | No | 2025-12-23 | Abas, Mohammed Fekry | 2026-01-06 | 2026-01-08 |  |  | Line Item 2.22, Lighting Control System (Motion Sensor)_Uruba SS | 0 | 7348 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 72407 | IN PROCESS | 2026-01-19 | 2026-01-21 |  | -72407 | 24 | Hegazy, Ayman | 13 | -46030
105-125 | Uruba 115/13.8kv Substation | 8574 | Lighting Control System (Motion Sensor)_Uruba SS | APPROVED | No | 2025-12-23 | Abas, Mohammed Fekry | 2026-01-06 | 2026-01-08 |  |  | Line Item 2.22, Lighting Control System (Motion Sensor)_Uruba SS | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -46030 | -46030
105-126 | Qatif Shati 115/13.8kv Substat | 2045 | Qatif Shati 115/13.8kv Substat-Qatif Shati SS Engineering Design | APPROVED | No | 2023-12-26 | Abas, Mohammed Fekry | 2023-12-28 | 2023-12-28 |  |  |  | 581250 | 4890 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 570000 | APPROVED |  |  | 2024-01-08 | 11250 | 11 | Kumar, Mr. Ranjan | -45288 | 11
105-126 | Qatif Shati 115/13.8kv Substat | 2051 | Qatif Shati 115/13.8kv Substat-Qatif Shati -13.8kV Switch Gear | APPROVED | No | 2023-12-28 | Abas, Mohammed Fekry | 2024-01-01 | 2024-01-01 |  |  |  | 8210000 | 4859 | 0 | STANDARD | ALFANAR CO | SAR | 8210000 | APPROVED |  |  | 2024-01-18 | 0 | 17 | Alhadi, Khalid | -45292 | 17
105-126 | Qatif Shati 115/13.8kv Substat | 2120 | Qatif Shati 115/13.8kv Substat-Temporary Project Sign Board | APPROVED | No | 2024-01-08 | Abas, Mohammed Fekry | 2024-01-09 | 2024-01-09 |  |  |  | 20000 | 4975 | 0 | STANDARD | Construction Expertise Est. | SAR | 20000 | APPROVED |  |  | 2024-01-21 | 0 | 12 | Alhadi, Khalid | -45300 | 12
105-126 | Qatif Shati 115/13.8kv Substat | 2187 | Qatif Shati 115/13.8kv Substat-C&P SAS AMI | APPROVED | No | 2024-01-16 | Abas, Mohammed Fekry | 2024-01-16 | 2024-01-17 |  |  |  | 7700000 | 4844 | 0 | STANDARD | ALFANAR CO | SAR | 7700000 | APPROVED |  |  | 2024-01-29 | 0 | 12 | Kumar, Mr. Ranjan | -45308 | 12
105-126 | Qatif Shati 115/13.8kv Substat | 2202 | Qatif Shati 115/13.8kv Substat-Cyber Security | APPROVED | No | 2024-01-18 | Abas, Mohammed Fekry | 2024-01-21 | 2024-01-21 |  |  |  | 1000000 | 5051 | 0 | STANDARD | ALFANAR CO | SAR | 1000000 | APPROVED |  |  | 2024-02-18 | 0 | 28 | Babic, Marian | -45312 | 28
105-126 | Qatif Shati 115/13.8kv Substat | 2253 | Qatif Shati 115/13.8kv Substat-Fencing Work | APPROVED | No | 2024-01-23 | Abas, Mohammed Fekry | 2024-01-24 | 2024-01-25 |  |  |  | 92858.33 | 5139 | 0 | STANDARD | Construction Expertise Est. | SAR | 91000 | APPROVED |  |  | 2024-03-24 | 1858.33 | 59 | Alhadi, Khalid | -45316 | 59
105-126 | Qatif Shati 115/13.8kv Substat | 2353 | Qatif Shati 115/13.8kv Substat-UG Scanning | APPROVED | No | 2024-01-29 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 1900 | 5061 | 0 | STANDARD | Construction Expertise Est. | SAR | 1900 | APPROVED |  |  | 2024-02-15 | 0 | 11 | Alhadi, Khalid | -45326 | 11
105-126 | Qatif Shati 115/13.8kv Substat | 2518 | Qatif Shati 115/13.8kv Substat-Geotechnical Investigation | APPROVED | No | 2024-02-11 | Abas, Mohammed Fekry | 2024-02-11 | 2024-02-12 |  |  |  | 16000 | 5709 | 0 | STANDARD | International Agent Commercial Company(S) | SAR | 16000 | APPROVED |  |  | 2024-06-26 | 0 | 135 | Alhadi, Khalid | -45334 | 135
105-126 | Qatif Shati 115/13.8kv Substat | 2539 | Qatif Shati 115/13.8kv Substat-Super Structure Precast including Fire Walls | APPROVED | No | 2024-02-12 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-19 |  |  |  | 2421479 | 5379 | 0 | STANDARD | Factory of Ideal Precast Concrete System Company | SAR | 2095473 | APPROVED |  |  | 2024-04-30 | 326006 | 71 | Tananeh, Khalid Jamal | -45341 | 71
105-126 | Qatif Shati 115/13.8kv Substat | 2643 | Qatif Shati 115/13.8kv Substat-Temporary Fence and Gate Works | APPROVED | No | 2024-02-21 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 97730 | 5139 | 0 | STANDARD | Construction Expertise Est. | SAR | 10480 | APPROVED |  |  | 2024-03-24 | 87250 | 27 | Alhadi, Khalid | -45348 | 27
105-126 | Qatif Shati 115/13.8kv Substat | 2645 | Qatif Shati 115/13.8kv Substat-Excavation and at Baladiyah Disposal | APPROVED | No | 2024-02-21 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 80000 | 5268 | 0 | STANDARD | Eastern Union Contracting Est | SAR | 72000 | APPROVED |  |  | 2024-04-15 | 8000 | 49 | Alhadi, Khalid | -45348 | 49
105-126 | Qatif Shati 115/13.8kv Substat | 2647 | Qatif Shati 115/13.8kv Substat-General Backfilling | APPROVED | No | 2024-02-21 | Abas, Mohammed Fekry | 2024-02-24 | 2024-02-26 |  |  |  | 92000 | 5268 | 0 | STANDARD | Eastern Union Contracting Est | SAR | 92000 | APPROVED |  |  | 2024-04-15 | 0 | 49 | Alhadi, Khalid | -45348 | 49
105-126 | Qatif Shati 115/13.8kv Substat | 2744 | Qatif Shati 115/13.8kv Substat-Main AC/DC Panel Boards Including Sub DB's, Indoor and Outdoor Lighting Panels | APPROVED | No | 2024-03-04 | Abas, Mohammed Fekry | 2024-03-05 | 2024-03-07 |  |  |  | 869999 | 5404 | 0 | STANDARD | ALFANAR CO | SAR | 869999 | APPROVED |  |  | 2024-05-19 | 0 | 73 | Mohammed, Faisal Ansari | -45358 | 73
105-126 | Qatif Shati 115/13.8kv Substat | 2767 | Qatif Shati 115/13.8kv Substat-Shoring for 4 Months Duration | APPROVED | No | 2024-03-04 | Abas, Mohammed Fekry | 2024-03-05 | 2024-03-07 |  |  |  | 124000 | 5268 | 0 | STANDARD | Eastern Union Contracting Est | SAR | 124000 | APPROVED |  |  | 2024-04-15 | 0 | 39 | Alhadi, Khalid | -45358 | 39
105-126 | Qatif Shati 115/13.8kv Substat | 2856 | Qatif Shati 115/13.8kv Substat-1000mm thick with Aggregate SUB BASEclass-"A(1A)" with CBR not less than 50 | APPROVED | No | 2024-03-20 | Abas, Mohammed Fekry | 2024-03-21 | 2024-03-24 |  |  |  | 49500 | 5268 | 0 | STANDARD | Eastern Union Contracting Est | SAR | 49500 | APPROVED |  |  | 2024-04-15 | 0 | 22 | Alhadi, Khalid | -45375 | 22
105-126 | Qatif Shati 115/13.8kv Substat | 2857 | Qatif Shati 115/13.8kv Substat-600mm thick Aggregate BASE COARSE (crashed stones) class-"A(1A) or A(1B)" with CBR not less than 100 | APPROVED | No | 2024-03-20 | Abas, Mohammed Fekry | 2024-03-21 | 2024-03-24 |  |  |  | 29700 | 5268 | 0 | STANDARD | Eastern Union Contracting Est | SAR | 29700 | APPROVED |  |  | 2024-04-15 | 0 | 22 | Alhadi, Khalid | -45375 | 22
105-126 | Qatif Shati 115/13.8kv Substat | 2896 | Qatif Shati 115/13.8kv Substat-Topographic Survey of Project Area | APPROVED | No | 2024-03-25 | Abas, Mohammed Fekry | 2024-03-27 | 2024-03-28 |  |  |  | 5125 | 5376 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 5125 | APPROVED |  |  | 2024-04-24 | 0 | 27 | Alhadi, Khalid | -45379 | 27
105-126 | Qatif Shati 115/13.8kv Substat | 3042 | Qatif Shati 115/13.8kv Substat-5 Ton Over Head Travelling Crane with all required Accessories | APPROVED | No | 2024-04-16 | Abas, Mohammed Fekry | 2024-04-17 | 2024-04-24 |  |  |  | 130000 | 5456 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 126870 | APPROVED |  |  | 2024-05-16 | 3130 | 22 | Muhammad, Muhammad Atif | -45406 | 22
105-126 | Qatif Shati 115/13.8kv Substat | 3133 | Qatif Shati 115/13.8kv Substat-Supply & Apply of Roof Waterproofing System & Underground Waterproofing System | APPROVED | No | 2024-04-25 | Abas, Mohammed Fekry | 2024-04-25 | 2024-04-28 |  |  |  | 355000 | 5649 | 0 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 347826.5 | APPROVED |  |  | 2024-06-13 | 7173.5 | 46 | Tananeh, Khalid Jamal | -45410 | 46
105-126 | Qatif Shati 115/13.8kv Substat | 3228 | Qatif Shati 115/13.8kv Substat-AC/DC Panel Boards with Sub-Panels and Lighting Panels | APPROVED | No | 2024-04-30 | Abas, Mohammed Fekry | 2024-05-01 | 2024-05-01 |  |  |  | 1 | 5404 | 0 | STANDARD | ALFANAR CO | SAR | 1 | APPROVED |  |  | 2024-05-19 | 0 | 18 | Mohammed, Faisal Ansari | -45413 | 18
105-126 | Qatif Shati 115/13.8kv Substat | 3364 | Qatif Shati 115/13.8kv Substat-Electronic Materials requirments for Site Office | APPROVED | No | 2024-05-09 | Sherif, Marwa | 2024-06-03 | 2024-06-03 |  |  |  | 29150 | 5687 | 0 | STANDARD | Construction Expertise Est. | SAR | 29150 | APPROVED |  |  | 2024-07-02 | 0 | 29 | Muhammad, Muhammad Atif | -45446 | 29
105-126 | Qatif Shati 115/13.8kv Substat | 3381 | Qatif Shati 115/13.8kv Substat-150Sq.mm Tinned Copper Conductor | APPROVED | No | 2024-05-12 | Abas, Mohammed Fekry | 2024-05-16 | 2024-05-17 |  |  |  | 38500 | 5347 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 38455.41 | APPROVED |  |  | 2024-06-03 | 44.59 | 17 | Muhammad, Muhammad Atif | -45429 | 17
105-126 | Qatif Shati 115/13.8kv Substat | 3517 | Qatif Shati 115/13.8kv Substat-Batteries & Chargers | APPROVED | No | 2024-05-28 | Abas, Mohammed Fekry | 2024-05-29 | 2024-05-29 |  |  |  | 550000 | 5732 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 457000 | APPROVED |  |  | 2024-07-09 | 93000 | 41 | Muhammad, Muhammad Atif | -45441 | 41
105-126 | Qatif Shati 115/13.8kv Substat | 3659 | Qatif Shati 115/13.8kv Substat-Grounding Material and Accessories | APPROVED | No | 2024-06-13 | Issa, Amr Ali | 2024-07-02 | 2024-07-03 |  |  |  | 73475 | 5550 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 72850 | APPROVED |  |  | 2024-07-12 | 625 | 9 | Muhammad, Muhammad Atif | -45476 | 9
105-126 | Qatif Shati 115/13.8kv Substat | 3698 | Qatif Shati 115/13.8kv Substat-Supply of Non Potable Water for Site offices Use | APPROVED | No | 2024-06-30 | Abas, Mohammed Fekry | 2024-07-05 | 2024-07-07 |  |  |  | 18000 | 5840 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 16800 | APPROVED |  |  | 2024-08-01 | 1200 | 25 | Akhtar, Farhan | -45480 | 25
105-126 | Qatif Shati 115/13.8kv Substat | 3700 | Qatif Shati 115/13.8kv Substat-Testing for Plate Load Test - 4 Points | APPROVED | No | 2024-06-30 | Abas, Mohammed Fekry | 2024-07-04 | 2024-07-04 |  |  |  | 8400 | 5804 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 7540 | APPROVED |  |  | 2024-10-13 | 860 | 101 | Tananeh, Khalid Jamal | -45477 | 101
105-126 | Qatif Shati 115/13.8kv Substat | 3791 | Qatif Shati 115/13.8kv Substat-Garbage Waste Container, 12 Cu. M (1-year) | IN PROCESS | No | 2024-07-07 | Sherif, Marwa | 2024-07-08 | 2024-07-09 |  |  |  | 28800 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45482 | -45482
105-126 | Qatif Shati 115/13.8kv Substat | 3864 | Qatif Shati 115/13.8kv Substat-Control Cables | APPROVED | No | 2024-07-12 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 716000 | 5819 | 0 | STANDARD | ALFANAR CO | SAR | 531752.8 | APPROVED |  |  | 2024-08-28 | 184247.2 | 43 | Muhammad, Muhammad Atif | -45489 | 43
105-126 | Qatif Shati 115/13.8kv Substat | 3915 | Qatif Shati 115/13.8kv Substat-RTV Coating for Transformer HV Busings and GIB HV Bushings | APPROVED | No | 2024-07-16 | Malek, Warren | 2024-07-25 | 2024-07-25 |  |  |  | 250000 | 6184 | 0 | STANDARD | SAUDI CONDUIT COATING CO. (S3C) | SAR | 35268 | APPROVED |  |  | 2024-10-13 | 214732 | 80 | Muaz, Alaa | -45498 | 80
105-126 | Qatif Shati 115/13.8kv Substat | 3919 | Qatif Shati 115/13.8kv Substat-Testing & Commissioning Works | APPROVED | No | 2024-07-16 | Malek, Warren | 2024-07-25 | 2024-07-25 |  |  |  | 1860297 | 6439 | 0 | STANDARD | Al Fanar Technical Services | SAR | 1808041 | APPROVED |  |  | 2025-02-25 | 52256 | 215 | Alqadhi, Abdulrahman Abdulghani | -45498 | 215
105-126 | Qatif Shati 115/13.8kv Substat | 3923 | Qatif Shati 115/13.8kv Substat-MV Termination Kits | APPROVED | No | 2024-07-16 | Malek, Warren | 2024-07-25 | 2024-07-25 |  |  |  | 98839 | 5978 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 95871.89 | APPROVED |  |  | 2024-09-19 | 2967.11 | 56 | Badhman, Saeed | -45498 | 56
105-126 | Qatif Shati 115/13.8kv Substat | 4060 | Qatif Shati 115/13.8kv Substat-Cable Trays, Ladders & Related Accessories | APPROVED | No | 2024-07-30 | Abas, Mohammed Fekry | 2024-08-01 | 2024-08-01 |  |  |  | 552885 | 5900 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 505784.96 | APPROVED |  |  | 2024-09-18 | 47100.04 | 48 | Muhammad, Muhammad Atif | -45505 | 48
105-126 | Qatif Shati 115/13.8kv Substat | 4075 | Qatif Shati 115/13.8kv Substat-Lighting Cum Lightning Mast | APPROVED | No | 2024-08-01 | Abas, Mohammed Fekry | 2024-08-03 | 2024-08-04 |  |  |  | 59075 | 6032 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 59075 | APPROVED |  |  | 2024-10-07 | 0 | 64 | Badhman, Saeed | -45508 | 64
105-126 | Qatif Shati 115/13.8kv Substat | 4198 | Qatif Shati 115/13.8kv Substat-Hazardous and Non Hazardous Waste Collection | APPROVED | No | 2024-08-19 | Issa, Amr Ali | 2024-08-25 | 2024-08-25 |  |  |  | 5000 | 6126 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 3650 | APPROVED |  |  | 2024-09-19 | 1350 | 25 | Akhtar, Farhan | -45529 | 25
105-126 | Qatif Shati 115/13.8kv Substat | 4230 | Qatif Shati 115/13.8kv Substat-LV Power Cable | APPROVED | No | 2024-08-21 | Issa, Amr Ali | 2024-08-25 | 2024-08-25 |  |  |  | 1611070 | 6073 | 0 | STANDARD | ALFANAR CO | SAR | 1110509.38 | APPROVED |  |  | 2024-09-26 | 500560.62 | 32 | Badhman, Saeed | -45529 | 32
105-126 | Qatif Shati 115/13.8kv Substat | 4252 | Qatif Shati 115/13.8kv Substat-Grounding Cable | APPROVED | No | 2024-08-24 | Abas, Mohammed Fekry | 2024-08-27 | 2024-09-01 |  |  |  | 244150 | 6057 | 0 | STANDARD | ALFANAR CO | SAR | 226756.52 | APPROVED |  |  | 2024-09-18 | 17393.48 | 17 | Muhammad, Muhammad Atif | -45536 | 17
105-126 | Qatif Shati 115/13.8kv Substat | 4365 | Qatif Shati 115/13.8kv Substat-Station Service Transformer 750kVA | APPROVED | No | 2024-09-04 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-09 |  |  |  | 164000 | 5901 | 0 | STANDARD | ALFANAR CO | SAR | 164000 | APPROVED |  |  | 2024-10-24 | 0 | 15 | Muhammad, Muhammad Atif | -45574 | 15
105-126 | Qatif Shati 115/13.8kv Substat | 4445 | Qatif Shati 115/13.8kv Substat-Fire Alarm & Fire Suppression System | APPROVED | No | 2024-09-14 | Abas, Mohammed Fekry | 2024-09-17 | 2024-09-17 |  |  |  | 2043191 | 5994 | 0 | STANDARD | Reda Trading & Development Co. for Machinery & Equipment Ltd(S) | SAR | 2043191 | APPROVED |  |  | 2024-09-24 | 0 | 7 | Muhammad, Muhammad Atif | -45552 | 7
105-126 | Qatif Shati 115/13.8kv Substat | 4593 | Qatif Shati 115/13.8kv Substat-Electrical Installation - Contract | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-09 |  |  |  | 2992521 | 6552 | 0 | STANDARD | Hussain Ali Hussain Contracting Company | SAR | 2352585 | APPROVED |  |  | 2025-01-14 | 639936 | 97 | Muhammad, Muhammad Atif | -45574 | 97
105-126 | Qatif Shati 115/13.8kv Substat | 4644 | Qatif Shati 115/13.8kv Substat-13.8kV MV Power Cable | APPROVED | No | 2024-10-09 | Abas, Mohammed Fekry | 2024-10-22 | 2024-10-23 |  |  |  | 1223740 | 6404 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 1093970.6 | APPROVED |  |  | 2024-11-09 | 129769.4 | 17 | Badhman, Saeed | -45588 | 17
105-126 | Qatif Shati 115/13.8kv Substat | 4756 | Qatif Shati 115/13.8kv Substat-Complete Substation HVAC System Works | APPROVED | No | 2024-10-21 | Abas, Mohammed Fekry | 2024-11-04 | 2024-11-04 |  |  |  | 2220000 | 6206 | 0 | STANDARD | Ramz Alataa Company for Trading | SAR | 2050000 | APPROVED |  |  | 2024-11-14 | 170000 | 10 | Muhammad, Muhammad Atif | -45600 | 10
105-126 | Qatif Shati 115/13.8kv Substat | 4856 | Qatif Shati 115/13.8kv Substat-2.20 Subcontractor for Civil & Architectural Works | APPROVED | No | 2024-11-07 | Abas, Mohammed Fekry | 2024-12-01 | 2024-12-01 |  |  |  | 9562124 | 6595 | 0 | STANDARD | Intelligent System General Contracting Company | SAR | 9562124 | APPROVED |  |  | 2024-12-19 | 0 | 18 | Tananeh, Khalid Jamal | -45627 | 18
105-126 | Qatif Shati 115/13.8kv Substat | 4927 | Qatif Shati 115/13.8kv Substat-Sewage Water Removal Services, 10000 Ltrs - 10 Trips | APPROVED | No | 2024-11-13 | Abas, Mohammed Fekry | 2024-11-20 | 2024-11-20 |  |  |  | 3500 | 6542 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 3000 | APPROVED |  |  | 2024-12-01 | 500 | 11 | Akhtar, Farhan | -45616 | 11
105-126 | Qatif Shati 115/13.8kv Substat | 4964 | Qatif Shati 115/13.8kv Substat-Supply of Indoor & Outdoor Lighting fixtures | APPROVED | No | 2024-11-17 | Abas, Mohammed Fekry | 2024-11-20 | 2024-11-20 |  |  |  | 88037 | 6464 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 88037 | APPROVED |  |  | 2024-11-28 | 0 | 8 | Muhammad, Muhammad Atif | -45616 | 8
105-126 | Qatif Shati 115/13.8kv Substat | 5081 | Qatif Shati 115/13.8kv Substat-HCIS Consultancy for Security System | APPROVED | No | 2024-11-28 | Abas, Mohammed Fekry | 2025-01-15 | 2025-01-16 |  |  |  | 33500 | 6503 | 0 | STANDARD | Khaled Drewesh Office for Consulting Security (KDOCS) | SAR | 33500 | APPROVED |  |  | 2025-03-09 | 0 | 52 | Abdulqader, Ahmed Abdulhalim | -45673 | 52
105-126 | Qatif Shati 115/13.8kv Substat | 5125 | Qatif Shati 115/13.8kv Substat-Garbage Waste Container, 4 Trips/Month, disposal of waste | APPROVED | No | 2024-12-04 | Abas, Mohammed Fekry | 2024-12-05 | 2024-12-08 |  |  |  | 19200 | 6607 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 19200 | APPROVED |  |  | 2024-12-18 | 0 | 10 | Akhtar, Farhan | -45634 | 10
105-126 | Qatif Shati 115/13.8kv Substat | 5194 | Qatif Shati 115/13.8kv Substat-HV Clamps & Connectors / Terminal Hardwares | APPROVED | No | 2024-12-08 | Abas, Mohammed Fekry | 2024-12-10 | 2024-12-12 |  |  |  | 4616 | 6419 | 0 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 4505.16 | APPROVED |  |  | 2025-01-02 | 110.84 | 21 | Mohammed, Faisal Ansari | -45638 | 21
105-126 | Qatif Shati 115/13.8kv Substat | 5283 | Qatif Shati 115/13.8kv Substat-150Sq.mm Tinned Cu. Cable | APPROVED | No | 2024-12-29 | Abas, Mohammed Fekry | 2024-12-29 | 2024-12-30 |  |  |  | 142500 | 6749 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 131856 | APPROVED |  |  | 2025-02-25 | 10644 | 57 | Alhadi, Khalid | -45656 | 57
105-126 | Qatif Shati 115/13.8kv Substat | 5321 | Qatif Shati 115/13.8kv Substat-7X2.5 Sq.mm, Control Cabels for SAS Alarm (with Blue Color wires) | APPROVED | No | 2025-01-01 | Abas, Mohammed Fekry | 2025-01-06 | 2025-01-06 |  |  |  | 55000 | 6775 | 0 | STANDARD | ALFANAR CO | SAR | 52600 | APPROVED |  |  | 2025-04-16 | 2400 | 100 | Muaz, Alaa | -45663 | 100
105-126 | Qatif Shati 115/13.8kv Substat | 5612 | Qatif Shati 115/13.8kv Substat-FO Cables and Patch Cords | APPROVED | No | 2025-01-26 | Abas, Mohammed Fekry | 2025-01-28 | 2025-01-30 |  |  |  | 300000 | 6965 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 210000 | APPROVED |  |  | 2025-03-11 | 90000 | 40 | Abdulqader, Ahmed Abdulhalim | -45687 | 40
105-126 | Qatif Shati 115/13.8kv Substat | 5633 | Qatif Shati 115/13.8kv Substat-Site Office and Facilites | APPROVED | No | 2025-01-27 | Abas, Mohammed Fekry | 2025-01-29 | 2025-01-30 |  |  |  | 562550 | 5428 | 0 | STANDARD | Construction Expertise Est. | SAR | 562550 | APPROVED |  |  | 2025-02-20 | 0 | 21 | Abdulqader, Ahmed Abdulhalim | -45687 | 21
105-126 | Qatif Shati 115/13.8kv Substat | 5659 | Qatif Shati 115/13.8kv Substat-Switches & Sockets, Power Receptacles | RETURNED | No | 2025-01-27 | Muaz, Alaa | 2025-07-30 | 2025-02-02 | 2025-07-30 |  | This PR was raised by mistake due to changes in the BOQ made by PMT | 35000 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -45690 | -45690
105-126 | Qatif Shati 115/13.8kv Substat | 5795 | Qatif Shati 115/13.8kv Substat-CTPU & CTPU BOX | APPROVED | No | 2025-02-05 | Abas, Mohammed Fekry | 2025-02-10 | 2025-02-11 |  |  |  | 68000 | 6253 | 0 | STANDARD | Energy Tracks For Contracting | SAR | 68000 | APPROVED |  |  | 2025-03-02 | 0 | 19 | Kumar, Mr. Ranjan | -45699 | 19
105-126 | Qatif Shati 115/13.8kv Substat | 5922 | Qatif Shati 115/13.8kv Substat-Security System Complete as per HCIS Standard and Requirment | APPROVED | No | 2025-02-17 | Abas, Mohammed Fekry | 2025-02-19 | 2025-02-19 |  |  |  | 793742 | 6629 | 0 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 793742 | APPROVED |  |  | 2025-03-05 | 0 | 14 | Abdulqader, Ahmed Abdulhalim | -45707 | 14
105-126 | Qatif Shati 115/13.8kv Substat | 6071 | Qatif Shati 115/13.8kv Substat-Manufacturing, Fabrication, Supply and Installation of Steel Parapet Works | APPROVED | No | 2025-02-26 | Abas, Mohammed Fekry | 2025-05-25 | 2025-05-26 |  |  | Line Item #2.20, Manufacturing, Fabrication, Supply and Installation of Steel Parapet Works | 39060 | 6823 | 0 | STANDARD | RAFCO Factory Company For Metal Industries | SAR | 39060 | APPROVED |  |  | 2025-08-31 | 0 | 97 | Hegazy, Ayman | -45803 | 97
105-126 | Qatif Shati 115/13.8kv Substat | 6573 | Qatif Shati 115/13.8kv Substat-4P x 1.5mm2 Cu/XLPE/CT/PVC 0.6/1kV Gray Control Cables with Numbering for QATIF SHATI SS | APPROVED | No | 2025-05-10 | Abas, Mohammed Fekry | 2025-05-12 | 2025-05-14 |  |  | 2.13 - 4P x 1.5mm2 Cu/XLPE/CT/PVC 0.6/1kV Gray Control Cables with Numbering for QATIF SHATI SS | 9000 | 7308 | 0 | STANDARD | Middle East Specialized Cables Mesc | SAR | 7500 | APPROVED |  |  | 2025-05-27 | 1500 | 13 | Abuhammad, Samir | -45791 | 13
105-126 | Qatif Shati 115/13.8kv Substat | 6789 | Qatif Shati 115/13.8kv Substat-Telecommunication System | APPROVED | No | 2025-06-12 | Abas, Mohammed Fekry | 2025-06-16 | 2025-06-16 |  |  | Line Item #2.4, Telecommunication System | 1958621.93 | 5848 | 0 | STANDARD | ALFANAR CO | SAR | 1958621.93 | APPROVED |  |  | 2025-06-24 | 0 | 8 | Kumar, Mr. Ranjan | -45824 | 8
105-126 | Qatif Shati 115/13.8kv Substat | 6899 | Qatif Shati 115/13.8kv Substat-Safety Miscellaneous Materials (Breathing Apparatus-1No., Fire Blankets-3Nos, First Aid Box - 1No., Stretcher - 1No.) | RETURNED | No | 2025-06-25 | Akhtar, Farhan | 2025-10-12 | 2025-07-01 | 2025-10-12 |  | No responce from the PMT | 60000 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45839 | -45839
105-126 | Qatif Shati 115/13.8kv Substat | 6922 | Qatif Shati 115/13.8kv Substat-Switches & Sockets (Wiring Devices) | APPROVED | No | 2025-06-29 | Abas, Mohammed Fekry | 2025-07-01 | 2025-07-01 |  |  | Line Item #2.23, Switches & Sockets (Wiring Devices) | 96720 | 7173 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 96720 | APPROVED |  |  | 2025-07-14 | 0 | 13 | Muaz, Alaa | -45839 | 13
105-126 | Qatif Shati 115/13.8kv Substat | 7030 | Qatif Shati 115/13.8kv Substat-Supply of Clamps/cleats for MV cables | APPROVED | No | 2025-07-09 | Abas, Mohammed Fekry | 2025-07-13 | 2025-07-14 |  |  | Line Item #2.13, Supply of Clamps/cleats for MV cables | 56525 | 7392 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 56525 | APPROVED |  |  | 2025-07-27 | 0 | 13 | Hegazy, Ayman | -45852 | 13
105-126 | Qatif Shati 115/13.8kv Substat | 7037 | Qatif Shati 115/13.8kv Substat-Supply of HV & MV Cable Supports | APPROVED | No | 2025-07-09 | Abas, Mohammed Fekry | 2025-07-12 | 2025-07-12 |  |  | Line Item 32.19, Supply of HV & MV Cable Supports | 110214.5 | 7380 | 0 | STANDARD | Power Solution Industries | SAR | 110214.5 | APPROVED |  |  | 2025-08-02 | 0 | 21 | Hegazy, Ayman | -45850 | 21
105-126 | Qatif Shati 115/13.8kv Substat | 7069 | Qatif Shati 115/13.8kv Substat-Laboratory Testing of Transformer Oils | APPROVED | No | 2025-07-13 | Abas, Mohammed Fekry | 2025-07-15 | 2025-07-16 |  |  | 2.38, Laboratory Testing of Transformer Oils | 37300 | 7535 | 0 | STANDARD | Saudi Arabian Engineering Company | SAR | 37300 | APPROVED |  |  | 2025-08-03 | 0 | 18 | Abdulqader, Ahmed Abdulhalim | -45854 | 18
105-126 | Qatif Shati 115/13.8kv Substat | 7121 | Qatif Shati 115/13.8kv Substat-Complete PDS System | APPROVED | No | 2025-07-17 | Abas, Mohammed Fekry | 2025-07-22 | 2025-07-22 |  |  | 2.5, PDS System | 250000 | 7765 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 140000 | APPROVED |  |  | 2025-11-18 | 110000 | 119 | Hegazy, Ayman | -45860 | 119
105-126 | Qatif Shati 115/13.8kv Substat | 7350 | Qatif Shati 115/13.8kv Substat-Shifting of Temporary Site Fence at Qatif Shati S/S | APPROVED | No | 2025-08-13 | Abas, Mohammed Fekry | 2025-08-17 | 2025-08-18 |  |  | 2.20- Relocation of the temporary site fence at Qatif Shati S/S | 35000 | 7636 | 0 | STANDARD | Shabkat Al Mansurah Co.for Electric Contracting | SAR | 35000 | APPROVED |  |  | 2025-09-09 | 0 | 22 | Abuhammad, Samir | -45887 | 22
105-126 | Qatif Shati 115/13.8kv Substat | 7462 | Qatif Shati 115/13.8kv Substat-Manufacturing, Fabrication, Supply and Installation of Steel Parapet Works for Qatif Shati SS | REJECTED | No | 2025-08-25 | Khan, Muhammad Safdar | 2025-08-25 | 2025-08-25 |  | 2025-08-25 |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45894 | -45894
105-126 | Qatif Shati 115/13.8kv Substat | 7551 | Lugs & Glands | RETURNED | No | 2025-08-28 | Abdulqader, Ahmed Abdulhalim | 2025-10-02 | 2025-09-03 | 2025-10-02 |  | Not required PO approved in system | 0 | 7620 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 8558.86 | APPROVED |  |  | 2025-09-29 | -8558.86 |  | Abdulqader, Ahmed Abdulhalim | -45903 | 26
105-126 | Qatif Shati 115/13.8kv Substat | 7551 | Lugs & Glands | RETURNED | No | 2025-08-28 | Abdulqader, Ahmed Abdulhalim | 2025-10-02 | 2025-09-03 | 2025-10-02 |  | Not required PO approved in system | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45903 | -45903
105-126 | Qatif Shati 115/13.8kv Substat | 7561 | Metal Doors & Accessories | REJECTED | No | 2025-08-28 | Sherif, Marwa | 2025-08-28 | 2025-08-28 |  | 2025-09-02 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45897 | -45897
105-126 | Qatif Shati 115/13.8kv Substat | 7691 | 3rd Party Lab Inspector for Precast Concrete Production Test | APPROVED | No | 2025-09-09 | Abas, Mohammed Fekry | 2025-09-16 | 2025-09-21 |  |  | Line Item #2.20, 3rd Party Lab Inspector for Precast Concrete Production Test | 0 | 7358 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 84190 | APPROVED |  |  | 2025-10-06 | -84190 | 15 | Tananeh, Khalid Jamal | -45921 | 15
105-126 | Qatif Shati 115/13.8kv Substat | 7745 | DCDB - 2Nos. for Telecom Room_Qatif Shati SS | APPROVED | No | 2025-09-15 | Abas, Mohammed Fekry | 2025-12-01 | 2025-12-02 | 2025-09-25 |  | As per PM request | 0 | 7739 | 0 | STANDARD | Factory Meaden Al-Khalij for Manufacturing (GTE). | SAR | 25300 | APPROVED |  |  | 2025-12-14 | -25300 | 12 | Abuhammad, Samir | -45993 | 12
105-126 | Qatif Shati 115/13.8kv Substat | 7757 | Lugs and Glands, Rev.02 | APPROVED | No | 2025-09-15 | Abas, Mohammed Fekry | 2025-09-16 | 2025-09-21 |  |  | Line Item 2.13, Lugs and Glands, Rev.02 | 0 | 7620 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 16748.9 | APPROVED |  |  | 2025-09-29 | -16748.9 | 8 | Abdulqader, Ahmed Abdulhalim | -45921 | 8
105-126 | Qatif Shati 115/13.8kv Substat | 7768 | Miscellaneous Materials - Office Supply Materials to SS | APPROVED | No | 2025-09-16 | Abas, Mohammed Fekry | 2025-09-21 | 2025-09-21 |  |  | Line Item #2.33, Miscellaneous Materials - Office Supply Materials to SS | 0 | 7716 | 0 | STANDARD | ALISMAIL INDUSTRIAL CO.(S) | SAR | 17590 | APPROVED |  |  | 2025-10-09 | -17590 | 18 | Abdulqader, Ahmed Abdulhalim | -45921 | 18
105-126 | Qatif Shati 115/13.8kv Substat | 7796 | Manufacturing, Supply & Installation of Steel Decorative Fence and chain Link Fence with all accessories | APPROVED | No | 2025-09-18 | Abas, Mohammed Fekry | 2025-09-21 | 2025-09-21 |  |  | Line Item 2.20, Manufacturing, Supply & Installation of Steel Decorative Fence and chain Link Fence with all accessories | 0 | 6801 | 0 | STANDARD | Fursan Construction Industry Factory Industry Factory | SAR | 572290 | APPROVED |  |  | 2025-10-08 | -572290 | 17 | Hegazy, Ayman | -45921 | 17
105-126 | Qatif Shati 115/13.8kv Substat | 7819 | Supply and installation of Hollow Metal Doors and Accessories | APPROVED | No | 2025-09-24 | Abas, Mohammed Fekry | 2025-09-29 | 2025-10-02 |  |  | Line Item #2.20, Supply and installation of Hollow Metal Doors and Accessories | 0 | 7811 | 0 | STANDARD | AL MANASHY COMPANY | SAR | 126986.6 | APPROVED |  |  | 2025-10-27 | -126986.6 | 25 | Abdelraouf, Islam ِAdel Hanafy | -45932 | 25
105-126 | Qatif Shati 115/13.8kv Substat | 7957 | Reparing Cost for damaged C&P panel (3UF.2 Panel)_Qatif Shati SS | REJECTED | No | 2025-10-15 | Abdel Naiem, Tarek Ali | 2025-10-15 |  |  | 2025-10-15 | Line Item, 2.3; Repairing cost for damagem C&P panel, Qatif Shati SS | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | 0 | 0
105-126 | Qatif Shati 115/13.8kv Substat | 7969 | Reparing Cost for damaged C&P panel (3UF.2 Panel)_Qatif Shati SS | REJECTED | No | 2025-10-15 | Sherif, Marwa | 2025-10-23 | 2025-10-15 |  | 2025-10-29 |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45945 | -45945
105-126 | Qatif Shati 115/13.8kv Substat | 8002 | General Fill works at Qatif Shati S/S | APPROVED | No | 2025-10-20 | Abas, Mohammed Fekry | 2025-10-21 | 2025-10-21 |  |  | 2.20- General Fill Works at Qatif Shati S/S | 0 | 7950 | 0 | STANDARD |  | SAR | 7205 | INCOMPLETE |  |  |  | -7205 | 103 | Alhadi, Khalid | -45951 | -45951
105-126 | Qatif Shati 115/13.8kv Substat | 8002 | General Fill works at Qatif Shati S/S | APPROVED | No | 2025-10-20 | Abas, Mohammed Fekry | 2025-10-21 | 2025-10-21 |  |  | 2.20- General Fill Works at Qatif Shati S/S | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45951 | -45951
105-126 | Qatif Shati 115/13.8kv Substat | 8009 | Swing Gate Motor-Including All Accesssories, Procurement, Installation, testig and commissioning_Qatif Shati SS | APPROVED | No | 2025-10-20 | Abas, Mohammed Fekry | 2025-12-11 | 2025-12-14 | 2025-10-30 |  | missing clear requirements | 0 | 7988 | 0 | STANDARD | ALMOSALLAMY INDUSTRIAL COMPANY | SAR | 9330 | APPROVED |  |  | 2025-12-25 | -9330 | 11 | Abdelraouf, Islam ِAdel Hanafy | -46005 | 11
105-126 | Qatif Shati 115/13.8kv Substat | 8047 | Repairing Charges for Damagaed C&P Panel_Qatif Shai SS | RETURNED | No | 2025-10-26 | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | 2025-12-03 | 2025-11-29 | 2025-12-03 |  | as per PMT instructions, order is already completed | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -45990 | -45990
105-126 | Qatif Shati 115/13.8kv Substat | 8170 | Supply of Grounding materials and Accessories_Qatif Shati SS | APPROVED | No | 2025-11-10 | Abas, Mohammed Fekry | 2025-11-12 | 2025-11-13 |  |  | Line Item, 2.21, Supply of Grounding materials and Accessories_Qatif Shati SS | 0 | 7098 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 69784.7 | APPROVED |  |  | 2025-11-23 | -69784.7 | 10 | Hegazy, Ayman | -45974 | 10
105-126 | Qatif Shati 115/13.8kv Substat | 8223 | Hazardous and Non Hazardous Waste Removal_Qatif Shati SS | APPROVED | No | 2025-11-13 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-13 | 2025-12-10 |  | Kindly provide the budget PR (chnage the UOM,UNIT PRICE) | 1 | 7605 | 0 | STANDARD | Expertise Contracting Co. | SAR | 18300 | APPROVED | 2026-01-22 | 2026-01-26 | 2026-01-29 | -18299 | 16 | Akhtar, Farhan | 13 | 16
105-126 | Qatif Shati 115/13.8kv Substat | 8540 | Supply of Diesel for Generator at Site | APPROVED | No | 2025-12-17 | Abas, Mohammed Fekry | 2025-12-20 | 2025-12-21 |  |  | 2.33 - Supply of Diesel for Generator at Qatif Shati Site | 0 | 7947 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 11895.6 | APPROVED |  |  | 2025-12-29 | -11895.6 | 8 | Akhtar, Farhan | -46012 | 8
105-126 | Qatif Shati 115/13.8kv Substat | 8575 | Lighting Control System (Motion Sensor)_Qatif Shati SS | APPROVED | No | 2025-12-23 | Abas, Mohammed Fekry | 2025-12-31 | 2026-01-01 |  |  | Line Item 2.22, Lighting Control System (Motion Sensor)_Qatif Shati SS | 0 | 7344 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 72407 | IN PROCESS | 2026-01-19 | 2026-01-21 |  | -72407 | 31 | Hegazy, Ayman | 20 | -46023
105-126 | Qatif Shati 115/13.8kv Substat | 8575 | Lighting Control System (Motion Sensor)_Qatif Shati SS | APPROVED | No | 2025-12-23 | Abas, Mohammed Fekry | 2025-12-31 | 2026-01-01 |  |  | Line Item 2.22, Lighting Control System (Motion Sensor)_Qatif Shati SS | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -46023 | -46023
105-126 | Qatif Shati 115/13.8kv Substat | 8681 | Supply of lighting wires for Qatif Shati S/S | APPROVED | No | 2026-01-11 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  | 2026-01-19 | 2.13 - Supply of lighting wires for Qatif Shati S/S | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46050 | -46050
105-127 | Senaeya-2 115/13.8kV Substatio | 1929 | Senaeya-2 115/13.8kV Substatio-Engineering & Design- Senaeya-2 | APPROVED | No | 2023-12-11 | Abas, Mohammed Fekry | 2023-12-12 | 2023-12-12 |  |  |  | 581250 | 4891 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 580000 | APPROVED |  |  | 2024-01-08 | 1250 | 27 | Kumar, Mr. Ranjan | -45272 | 27
105-127 | Senaeya-2 115/13.8kV Substatio | 1935 | Senaeya-2 115/13.8kV Substatio-Control, Protection & SAS Senaeya-2 | APPROVED | No | 2023-12-12 | Abas, Mohammed Fekry | 2023-12-13 | 2023-12-14 |  |  |  | 9700000 | 4840 | 0 | STANDARD | ALFANAR CO | SAR | 9700000 | APPROVED |  |  | 2024-01-18 | 0 | 35 | Kumar, Mr. Ranjan | -45274 | 35
105-127 | Senaeya-2 115/13.8kV Substatio | 1952 | Senaeya-2 115/13.8kV Substatio-13.8kV Switchgear | APPROVED | No | 2023-12-13 | Abas, Mohammed Fekry | 2023-12-13 | 2023-12-13 |  |  |  | 8210000 | 4841 | 0 | STANDARD | ALFANAR CO | SAR | 8210000 | APPROVED |  |  | 2024-01-18 | 0 | 36 | Alhadi, Khalid | -45273 | 36
105-127 | Senaeya-2 115/13.8kV Substatio | 2107 | Senaeya-2 115/13.8kV Substatio-Temporary Project Sign Board | APPROVED | No | 2024-01-08 | Abas, Mohammed Fekry | 2024-01-09 | 2024-01-09 |  |  |  | 20000 | 4977 | 0 | STANDARD | Construction Expertise Est. | SAR | 20000 | APPROVED |  |  | 2024-01-17 | 0 | 8 | Alhadi, Khalid | -45300 | 8
105-127 | Senaeya-2 115/13.8kV Substatio | 2242 | Senaeya-2 115/13.8kV Substatio-Cyber Security | APPROVED | No | 2024-01-21 | Abas, Mohammed Fekry | 2024-01-22 | 2024-01-22 |  |  |  | 1100000 | 5052 | 0 | STANDARD | ALFANAR CO | SAR | 1100000 | APPROVED |  |  | 2024-02-20 | 0 | 29 | Babic, Marian | -45313 | 29
105-127 | Senaeya-2 115/13.8kV Substatio | 2355 | Senaeya-2 115/13.8kV Substatio- UG Scanning | APPROVED | No | 2024-01-29 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 1900 | 5068 | 0 | STANDARD | Construction Expertise Est. | SAR | 1900 | APPROVED |  |  | 2024-02-15 | 0 | 11 | Alhadi, Khalid | -45326 | 11
105-127 | Senaeya-2 115/13.8kV Substatio | 2492 | Senaeya-2 115/13.8kV Substatio-Security Cabin | RETURNED | No | 2024-02-07 | Alhadi, Khalid | 2024-04-21 | 2024-02-10 | 2024-04-21 |  | Incomplete scope | 9000 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45332 | -45332
105-127 | Senaeya-2 115/13.8kV Substatio | 2536 | Senaeya-2 115/13.8kV Substatio-Super Structure Precast including Fire Walls | APPROVED | No | 2024-02-12 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-19 |  |  |  | 2421479 | 5380 | 0 | STANDARD | Factory of Ideal Precast Concrete System Company | SAR | 1921165 | APPROVED |  |  | 2024-04-24 | 500314 | 65 | Tananeh, Khalid Jamal | -45341 | 65
105-127 | Senaeya-2 115/13.8kV Substatio | 2934 | Senaeya-2 115/13.8kV Substatio-AC/DB and DCDB & Lighting Panels | APPROVED | No | 2024-03-28 | Abas, Mohammed Fekry | 2024-03-31 | 2024-03-31 |  |  |  | 870000 | 5335 | 0 | STANDARD | ALFANAR CO | SAR | 870000 | APPROVED |  |  | 2024-04-28 | 0 | 28 | Mohammed, Faisal Ansari | -45382 | 28
105-127 | Senaeya-2 115/13.8kV Substatio | 2961 | Senaeya-2 115/13.8kV Substatio-Topographic Survey of Project Area | APPROVED | No | 2024-04-01 | Abas, Mohammed Fekry | 2024-04-03 | 2024-04-04 |  |  |  | 5125 | 5721 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 5125 | APPROVED |  |  | 2024-06-24 | 0 | 81 | Alhadi, Khalid | -45386 | 81
105-127 | Senaeya-2 115/13.8kV Substatio | 3040 | Senaeya-2 115/13.8kV Substatio-Electric Overhead Travelling Crane (5 TON, 27.800 m Traviling dist., span 11.515 m) | APPROVED | No | 2024-04-16 | Abas, Mohammed Fekry | 2024-04-17 | 2024-04-24 |  |  |  | 130000 | 5457 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 126870 | APPROVED |  |  | 2024-05-16 | 3130 | 22 | Muhammad, Muhammad Atif | -45406 | 22
105-127 | Senaeya-2 115/13.8kV Substatio | 3101 | Senaeya-2 115/13.8kV Substatio-Site Fencing and Asphalt road for Site Main Gate | APPROVED | No | 2024-04-22 | Abas, Mohammed Fekry | 2024-04-25 | 2024-04-28 |  |  |  | 78000 | 5582 | 0 | STANDARD | Construction Expertise Est. | SAR | 46400 | APPROVED |  |  | 2024-05-27 | 31600 | 29 | Alhadi, Khalid | -45410 | 29
105-127 | Senaeya-2 115/13.8kV Substatio | 3159 | Senaeya-2 115/13.8kV Substatio-Supply & Apply (Roof Waterproofing system & Underground Waterproofing Tanking system ) | APPROVED | No | 2024-04-27 | Abas, Mohammed Fekry | 2024-05-02 | 2024-05-02 |  |  |  | 392625 | 5647 | 0 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 347826.5 | APPROVED |  |  | 2024-06-16 | 44798.5 | 45 | Tananeh, Khalid Jamal | -45414 | 45
105-127 | Senaeya-2 115/13.8kV Substatio | 3159 | Senaeya-2 115/13.8kV Substatio-Supply & Apply (Roof Waterproofing system & Underground Waterproofing Tanking system ) | APPROVED | No | 2024-04-27 | Abas, Mohammed Fekry | 2024-05-02 | 2024-05-02 |  |  |  | 392625 | 5647 | 1 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 347826.5 | IN PROCESS |  |  |  | 44798.5 | 640 | Tananeh, Khalid Jamal | -45414 | -45414
105-127 | Senaeya-2 115/13.8kV Substatio | 3305 | Senaeya-2 115/13.8kV Substatio-Site Office Facility- Electronic items | APPROVED | No | 2024-05-05 | Abas, Mohammed Fekry | 2024-05-09 | 2024-05-12 |  |  |  | 33800 | 5602 | 0 | STANDARD | Construction Expertise Est. | SAR | 33800 | APPROVED |  |  | 2024-06-03 | 0 | 22 | Muhammad, Muhammad Atif | -45424 | 22
105-127 | Senaeya-2 115/13.8kV Substatio | 3408 | Senaeya-2 115/13.8kV Substatio-150sq.mm, Tinned copper conductor | APPROVED | No | 2024-05-15 | Abas, Mohammed Fekry | 2024-05-16 | 2024-05-17 |  |  |  | 38500 | 5348 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 38455.41 | APPROVED |  |  | 2024-05-21 | 44.59 | 4 | Muhammad, Muhammad Atif | -45429 | 4
105-127 | Senaeya-2 115/13.8kV Substatio | 3524 | Senaeya-2 115/13.8kV Substatio-125 V DC System (Battery GEL Type & Chargers ) | APPROVED | No | 2024-05-28 | Sherif, Marwa | 2024-06-03 | 2024-06-03 |  |  |  | 550000 | 5733 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 457000 | APPROVED |  |  | 2024-07-10 | 93000 | 37 | Muhammad, Muhammad Atif | -45446 | 37
105-127 | Senaeya-2 115/13.8kV Substatio | 3529 | Senaeya-2 115/13.8kV Substatio-125 KVA and 300 KV GENERATORS | APPROVED | No | 2024-05-29 | Sherif, Marwa | 2024-06-03 | 2024-06-05 |  |  |  | 270000 | 5730 | 0 | STANDARD | Mohammed A. AlFaddaghi & Partners | SAR | 268350 | APPROVED |  |  | 2024-07-17 | 1650 | 42 | Akhtar, Farhan | -45448 | 42
105-127 | Senaeya-2 115/13.8kV Substatio | 3620 | Senaeya-2 115/13.8kV Substatio-Grounding material accessories | APPROVED | No | 2024-06-08 | Abas, Mohammed Fekry | 2024-06-09 | 2024-06-09 |  |  |  | 72850 | 5551 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 72850 | APPROVED |  |  | 2024-07-07 | 0 | 28 | Muhammad, Muhammad Atif | -45452 | 28
105-127 | Senaeya-2 115/13.8kV Substatio | 3738 | Senaeya-2 115/13.8kV Substatio-MV Power Cable (1C x 630mm2 & 3C x 300mm2) | APPROVED | No | 2024-07-02 | Malek, Warren | 2024-07-25 | 2024-07-25 |  |  |  | 1056472.72 | 6017 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 944356.49 | APPROVED |  |  | 2024-10-09 | 112116.24 | 76 | Badhman, Saeed | -45498 | 76
105-127 | Senaeya-2 115/13.8kV Substatio | 3745 | Senaeya-2 115/13.8kV Substatio-sewage Water removal services, 10,000 ltr. | APPROVED | No | 2024-07-02 | Abas, Mohammed Fekry | 2024-07-04 | 2024-07-07 |  |  |  | 10000 | 5867 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 300 | APPROVED |  |  | 2024-08-18 | 9700 | 42 | Akhtar, Farhan | -45480 | 42
105-127 | Senaeya-2 115/13.8kV Substatio | 3746 | Senaeya-2 115/13.8kV Substatio-Supply & Delivery of Raw Water, 10 Cu. M Tanker | APPROVED | No | 2024-07-02 | Abas, Mohammed Fekry | 2024-07-06 | 2024-07-07 |  |  |  | 2000 | 5867 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 1800 | APPROVED |  |  | 2024-08-18 | 200 | 42 | Akhtar, Farhan | -45480 | 42
105-127 | Senaeya-2 115/13.8kV Substatio | 3749 | Senaeya-2 115/13.8kV Substatio-Diesel Supply (15000 Lt/Month) | APPROVED | No | 2024-07-02 | Abas, Mohammed Fekry | 2024-07-06 | 2024-07-07 |  |  |  | 17250 | 5795 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 15652.2 | APPROVED |  |  | 2024-07-18 | 1597.8 | 11 | Akhtar, Farhan | -45480 | 11
105-127 | Senaeya-2 115/13.8kV Substatio | 3779 | Senaeya-2 115/13.8kV Substatio-Garbage Waste Container, 12 Cu. M (1 year) | APPROVED | No | 2024-07-07 | Abas, Mohammed Fekry | 2024-07-09 | 2024-07-09 |  |  |  | 28800 | 5881 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 19200 | APPROVED |  |  | 2024-08-20 | 9600 | 42 | Akhtar, Farhan | -45482 | 42
105-127 | Senaeya-2 115/13.8kV Substatio | 3882 | Senaeya-2 115/13.8kV Substatio-LV Control Cables | APPROVED | No | 2024-07-14 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 716000 | 5820 | 0 | STANDARD | ALFANAR CO | SAR | 531752.8 | APPROVED |  |  | 2024-08-25 | 184247.2 | 40 | Muhammad, Muhammad Atif | -45489 | 40
105-127 | Senaeya-2 115/13.8kV Substatio | 3936 | Senaeya-2 115/13.8kV Substatio-MV Cable Termination Kit | APPROVED | No | 2024-07-16 | Issa, Amr Ali | 2024-07-21 | 2024-07-21 |  |  |  | 98837 | 5979 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 95871.89 | APPROVED |  |  | 2024-09-19 | 2965.11 | 60 | Badhman, Saeed | -45494 | 60
105-127 | Senaeya-2 115/13.8kV Substatio | 3965 | Senaeya-2 115/13.8kV Substatio-Testing & Commissioning | APPROVED | No | 2024-07-21 | Abas, Mohammed Fekry | 2024-07-23 | 2024-07-25 |  |  |  | 1969324 | 6440 | 0 | STANDARD | Al Fanar Technical Services | SAR | 1914006 | APPROVED |  |  | 2025-03-13 | 55318 | 231 | Alqadhi, Abdulrahman Abdulghani | -45498 | 231
105-127 | Senaeya-2 115/13.8kV Substatio | 4070 | Senaeya-2 115/13.8kV Substatio-Supply & Delivery of Drinking Water | INCOMPLETE | No |  | Basharat, Ameen Ahmed | 2024-08-01 |  |  |  |  | 3500 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-127 | Senaeya-2 115/13.8kV Substatio | 4080 | Senaeya-2 115/13.8kV Substatio-Soil Resistivity | APPROVED | No | 2024-08-01 | Abas, Mohammed Fekry | 2024-08-05 | 2024-08-05 |  |  |  | 7360 | 6055 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 6400 | APPROVED |  |  | 2024-10-13 | 960 | 69 | Tananeh, Khalid Jamal | -45509 | 69
105-127 | Senaeya-2 115/13.8kV Substatio | 4084 | Senaeya-2 115/13.8kV Substatio-Supply & Delivery of Drinking Water, | APPROVED | No | 2024-08-04 | Abas, Mohammed Fekry | 2024-08-06 | 2024-08-06 |  |  |  | 3500 | 5867 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 3000 | APPROVED |  |  | 2024-08-18 | 500 | 12 | Akhtar, Farhan | -45510 | 12
105-127 | Senaeya-2 115/13.8kV Substatio | 4190 | Senaeya-2 115/13.8kV Substatio-Hazardous and No-Hazardous Waste | APPROVED | No | 2024-08-19 | Abas, Mohammed Fekry | 2024-08-19 | 2024-08-19 |  |  |  | 5000 | 6121 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 3650 | APPROVED |  |  | 2024-09-19 | 1350 | 31 | Akhtar, Farhan | -45523 | 31
105-127 | Senaeya-2 115/13.8kV Substatio | 4192 | Senaeya-2 115/13.8kV Substatio-LV Power Cables | APPROVED | No | 2024-08-19 | Abas, Mohammed Fekry | 2024-08-19 | 2024-08-19 |  |  |  | 1611070 | 6074 | 0 | STANDARD | ALFANAR CO | SAR | 1110509.38 | APPROVED |  |  | 2024-09-26 | 500560.62 | 38 | Badhman, Saeed | -45523 | 38
105-127 | Senaeya-2 115/13.8kV Substatio | 4249 | Senaeya-2 115/13.8kV Substatio-Grounding Cables | APPROVED | No | 2024-08-24 | Abas, Mohammed Fekry | 2024-08-25 | 2024-08-25 |  |  |  | 91150 | 6058 | 0 | STANDARD | ALFANAR CO | SAR | 83943.19 | APPROVED |  |  | 2024-09-18 | 7206.81 | 24 | Muhammad, Muhammad Atif | -45529 | 24
105-127 | Senaeya-2 115/13.8kV Substatio | 4267 | Senaeya-2 115/13.8kV Substatio-Grounding Cable | APPROVED | No | 2024-08-26 | Abas, Mohammed Fekry | 2024-08-27 | 2024-09-01 |  |  |  | 153000 | 6058 | 0 | STANDARD | ALFANAR CO | SAR | 142813.33 | APPROVED |  |  | 2024-09-18 | 10186.67 | 17 | Muhammad, Muhammad Atif | -45536 | 17
105-127 | Senaeya-2 115/13.8kV Substatio | 4270 | Senaeya-2 115/13.8kV Substatio-Pest Control | APPROVED | No | 2024-08-26 | Abas, Mohammed Fekry | 2024-08-27 | 2024-09-01 |  |  |  | 1400 | 6229 | 0 | STANDARD | Trap Pest Control &Garden Maintenance Co. LTD | SAR | 1200 | APPROVED |  |  | 2024-09-30 | 200 | 29 | Akhtar, Farhan | -45536 | 29
105-127 | Senaeya-2 115/13.8kV Substatio | 4426 | Senaeya-2 115/13.8kV Substatio-Diesel Supply for Generator (10000 liter/Month) for Ten Months | APPROVED | No | 2024-09-12 | Abas, Mohammed Fekry | 2024-09-16 | 2024-09-17 |  |  |  | 104350 | 6274 | 0 | STANDARD | Al-Masar Al-Monasib Company for Logistics Services | SAR | 101000 | APPROVED |  |  | 2024-10-09 | 3350 | 22 | Akhtar, Farhan | -45552 | 22
105-127 | Senaeya-2 115/13.8kV Substatio | 4448 | Senaeya-2 115/13.8kV Substatio-Cable Tray | APPROVED | No | 2024-09-14 | Abas, Mohammed Fekry | 2024-09-16 | 2024-09-17 |  |  |  | 462701.68 | 6148 | 0 | STANDARD | Electrolink Co Ltd | SAR | 459950.05 | APPROVED |  |  | 2024-09-26 | 2751.63 | 9 | Muhammad, Muhammad Atif | -45552 | 9
105-127 | Senaeya-2 115/13.8kV Substatio | 4455 | Senaeya-2 115/13.8kV Substatio-Fire Alarm and Fire Protection System | APPROVED | No | 2024-09-15 | Abas, Mohammed Fekry | 2024-09-16 | 2024-09-17 |  |  |  | 2197362.42 | 5998 | 0 | STANDARD | Al Majal Group Four S for Security & Safety | SAR | 2197362.42 | APPROVED |  |  | 2024-09-26 | 0 | 9 | Muhammad, Muhammad Atif | -45552 | 9
105-127 | Senaeya-2 115/13.8kV Substatio | 4490 | Senaeya-2 115/13.8kV Substatio-Site Office facility | APPROVED | No | 2024-09-22 | Abas, Mohammed Fekry | 2024-09-24 | 2024-09-24 |  |  |  | 562550 | 5423 | 0 | STANDARD | Construction Expertise Est. | SAR | 562550 | APPROVED |  |  | 2024-10-06 | 0 | 12 | Muhammad, Muhammad Atif | -45559 | 12
105-127 | Senaeya-2 115/13.8kV Substatio | 4579 | Senaeya-2 115/13.8kV Substatio-Station Service Transformer | APPROVED | No | 2024-10-02 | Abas, Mohammed Fekry | 2024-10-03 | 2024-10-04 |  |  |  | 164000 | 5902 | 0 | STANDARD | ALFANAR CO | SAR | 164000 | APPROVED |  |  | 2024-10-08 | 0 | 4 | Muhammad, Muhammad Atif | -45569 | 4
105-127 | Senaeya-2 115/13.8kV Substatio | 4583 | Senaeya-2 115/13.8kV Substatio-RTV Coating | APPROVED | No | 2024-10-02 | Abas, Mohammed Fekry | 2024-10-03 | 2024-10-04 |  |  |  | 250000 | 6337 | 0 | STANDARD | SAUDI CONDUIT COATING CO. (S3C) | SAR | 35268 | APPROVED |  |  | 2024-10-23 | 214732 | 19 | Muaz, Alaa | -45569 | 19
105-127 | Senaeya-2 115/13.8kV Substatio | 4599 | Senaeya-2 115/13.8kV Substatio-Electrical Installation Subcontractor | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-06 | 2024-10-06 |  |  |  | 2992521 | 6532 | 0 | STANDARD | SMART LINES INDUSTRIAL & SERVCIES COMPANY | SAR | 2385000 | APPROVED |  |  | 2024-12-29 | 607521 | 84 | Muhammad, Muhammad Atif | -45571 | 84
105-127 | Senaeya-2 115/13.8kV Substatio | 4637 | Senaeya-2 115/13.8kV Substatio-HVAC System | APPROVED | No | 2024-10-09 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-10 |  |  |  | 2025000 | 6212 | 0 | STANDARD | Hamad Fahad Al Awad for Contracting Est | SAR | 2025000 | APPROVED |  |  | 2024-10-30 | 0 | 20 | Muhammad, Muhammad Atif | -45575 | 20
105-127 | Senaeya-2 115/13.8kV Substatio | 4680 | Senaeya-2 115/13.8kV Substatio-Telecom System | APPROVED | No | 2024-10-15 | Abas, Mohammed Fekry | 2024-10-16 | 2024-10-17 |  |  |  | 1772560 | 5849 | 0 | STANDARD | ALFANAR CO | SAR | 1772560 | APPROVED |  |  | 2025-03-27 | 0 | 161 | Kumar, Mr. Ranjan | -45582 | 161
105-127 | Senaeya-2 115/13.8kV Substatio | 4747 | Senaeya-2 115/13.8kV Substatio-Subcontractor for Civil Works | APPROVED | No | 2024-10-20 | Abas, Mohammed Fekry | 2024-10-21 | 2024-10-21 |  |  |  | 9079925 | 5636 | 0 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 9079925 | APPROVED |  |  | 2024-11-04 | 0 | 14 | Tananeh, Khalid Jamal | -45586 | 14
105-127 | Senaeya-2 115/13.8kV Substatio | 4820 | Senaeya-2 115/13.8kV Substatio-Removal of existing Bounder Wall | APPROVED | No | 2024-11-01 | Abas, Mohammed Fekry | 2024-11-04 | 2024-11-04 |  |  |  | 55000 | 6431 | 0 | STANDARD | Construction Expertise Est. | SAR | 55000 | APPROVED |  |  | 2024-11-10 | 0 | 6 | Alhadi, Khalid | -45600 | 6
105-127 | Senaeya-2 115/13.8kV Substatio | 4830 | Senaeya-2 115/13.8kV Substatio-Lightning System | APPROVED | No | 2024-11-04 | Abas, Mohammed Fekry | 2024-11-06 | 2024-11-06 |  |  |  | 59075 | 6458 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 59075 | APPROVED |  |  | 2024-11-13 | 0 | 7 | Badhman, Saeed | -45602 | 7
105-127 | Senaeya-2 115/13.8kV Substatio | 4966 | Senaeya-2 115/13.8kV Substatio-Lighting Fixtures | APPROVED | No | 2024-11-17 | Abas, Mohammed Fekry | 2024-11-19 | 2024-11-19 |  |  |  | 71998 | 6465 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 71998 | APPROVED |  |  | 2024-11-28 | 0 | 9 | Muhammad, Muhammad Atif | -45615 | 9
105-127 | Senaeya-2 115/13.8kV Substatio | 5097 | Senaeya-2 115/13.8kV Substatio-HCIS Consultant | APPROVED | No | 2024-11-30 | Abas, Mohammed Fekry | 2025-01-08 | 2025-01-08 |  |  |  | 33500 | 6504 | 0 | STANDARD | Khaled Drewesh Office for Consulting Security (KDOCS) | SAR | 33500 | APPROVED |  |  | 2025-01-15 | 0 | 7 | Muhammad, Muhammad Atif | -45665 | 7
105-127 | Senaeya-2 115/13.8kV Substatio | 5191 | Senaeya-2 115/13.8kV Substatio-Clamps & Connectors | APPROVED | No | 2024-12-08 | Abas, Mohammed Fekry | 2024-12-09 | 2024-12-12 |  |  |  | 4512 | 6420 | 0 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 4505.16 | APPROVED |  |  | 2025-01-02 | 6.84 | 21 | Mohammed, Faisal Ansari | -45638 | 21
105-127 | Senaeya-2 115/13.8kV Substatio | 5288 | Senaeya-2 115/13.8kV Substatio-Tinned Copper Conductor | APPROVED | No | 2024-12-29 | Abas, Mohammed Fekry | 2024-12-31 | 2025-01-01 |  |  |  | 153900 | 6750 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 142404.48 | APPROVED |  |  | 2025-02-25 | 11495.52 | 55 | Alhadi, Khalid | -45658 | 55
105-127 | Senaeya-2 115/13.8kV Substatio | 5317 | Senaeya-2 115/13.8kV Substatio-Control Cable for SAS Alarm (Blue Color) | APPROVED | No | 2025-01-01 | Abas, Mohammed Fekry | 2025-01-06 | 2025-01-06 |  |  |  | 55000 | 6776 | 0 | STANDARD | ALFANAR CO | SAR | 52600 | APPROVED |  |  | 2025-04-14 | 2400 | 98 | Muaz, Alaa | -45663 | 98
105-127 | Senaeya-2 115/13.8kV Substatio | 5354 | Senaeya-2 115/13.8kV Substatio-Lighting Conduits & Fittings | APPROVED | No | 2025-01-05 | Abas, Mohammed Fekry | 2025-01-08 | 2025-01-12 |  |  |  | 342909.3 | 6692 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 342909.3 | APPROVED |  |  | 2025-01-22 | 0 | 10 | Muaz, Alaa | -45669 | 10
105-127 | Senaeya-2 115/13.8kV Substatio | 5369 | Senaeya-2 115/13.8kV Substatio-Security System | APPROVED | No | 2025-01-07 | Abas, Mohammed Fekry | 2025-04-24 | 2025-04-24 |  |  | Security System - Line Item 2.7 | 817000.64 | 6640 | 0 | STANDARD | CEGELEC NETWORK AND SECURITY SYSTEMS | SAR | 817000.64 | APPROVED |  |  | 2025-05-13 | 0 | 19 | Abdulqader, Ahmed Abdulhalim | -45771 | 19
105-127 | Senaeya-2 115/13.8kV Substatio | 5441 | Senaeya-2 115/13.8kV Substatio-3rd Party Lab Inspector for Pre-cast | APPROVED | No | 2025-01-16 | Abas, Mohammed Fekry | 2025-04-21 | 2025-04-21 |  |  | 3rd Party Inspector for Pre-cast Line Item 2.20 | 81400 | 7413 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 81190 | APPROVED |  |  | 2025-06-22 | 210 | 62 | Tananeh, Khalid Jamal | -45768 | 62
105-127 | Senaeya-2 115/13.8kV Substatio | 5508 | Senaeya-2 115/13.8kV Substatio-CTPU & CTPU Box | APPROVED | No | 2025-01-21 | Abas, Mohammed Fekry | 2025-01-26 | 2025-01-27 |  |  |  | 68000 | 6280 | 0 | STANDARD | Energy Tracks For Contracting | SAR | 68000 | APPROVED |  |  | 2025-03-02 | 0 | 34 | Kumar, Mr. Ranjan | -45684 | 34
105-127 | Senaeya-2 115/13.8kV Substatio | 5579 | Senaeya-2 115/13.8kV Substatio-FO Cables | APPROVED | No | 2025-01-25 | Abas, Mohammed Fekry | 2025-01-27 | 2025-01-30 |  |  |  | 500000 | 6947 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 220000 | APPROVED |  |  | 2025-03-11 | 280000 | 40 | Abdulqader, Ahmed Abdulhalim | -45687 | 40
105-127 | Senaeya-2 115/13.8kV Substatio | 5621 | Senaeya-2 115/13.8kV Substatio-Steel Parapet Works | APPROVED | No | 2025-01-26 | Abas, Mohammed Fekry | 2025-01-28 | 2025-01-30 |  |  |  | 36520 | 6824 | 0 | STANDARD | RAFCO Factory Company For Metal Industries | SAR | 36520 | APPROVED |  |  | 2025-03-03 | 0 | 32 | Hegazy, Ayman | -45687 | 32
105-127 | Senaeya-2 115/13.8kV Substatio | 6099 | Senaeya-2 115/13.8kV Substatio-Drawing Printing A2 | APPROVED | No | 2025-03-03 | Abas, Mohammed Fekry | 2025-03-03 | 2025-03-05 |  |  | Drawing Printing - Line Item 2.33 | 31000 | 7061 | 0 | STANDARD | Print Magaies Al abdaa Printing | SAR | 30999 | APPROVED |  |  | 2025-04-07 | 1 | 33 | Abuhammad, Samir | -45721 | 33
105-127 | Senaeya-2 115/13.8kV Substatio | 6505 | Senaeya-2 115/13.8kV Substatio-Air conditioner | APPROVED | No | 2025-05-04 | Abas, Mohammed Fekry | 2025-05-05 | 2025-05-05 |  |  | Air conditioner - 2.20 | 77000 | 7233 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 77000 | APPROVED |  |  | 2025-05-12 | 0 | 7 | Abuhammad, Samir | -45782 | 7
105-127 | Senaeya-2 115/13.8kV Substatio | 6505 | Senaeya-2 115/13.8kV Substatio-Air conditioner | APPROVED | No | 2025-05-04 | Abas, Mohammed Fekry | 2025-05-05 | 2025-05-05 |  |  | Air conditioner - 2.20 | 77000 | 7233 | 1 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 77000 | REQUIRES REAPPROVAL |  |  |  | 0 | 272 | Abuhammad, Samir | -45782 | -45782
105-127 | Senaeya-2 115/13.8kV Substatio | 6521 | Senaeya-2 115/13.8kV Substatio-4P x 1.5mm2 Cable | APPROVED | No | 2025-05-05 | Abas, Mohammed Fekry | 2025-05-06 | 2025-05-06 |  |  | 4P x 1.5mm2 Cable - Line Item 2.13 | 9000 | 7309 | 0 | STANDARD | Middle East Specialized Cables Mesc | SAR | 7500 | APPROVED |  |  | 2025-05-27 | 1500 | 21 | Abuhammad, Samir | -45783 | 21
105-127 | Senaeya-2 115/13.8kV Substatio | 6547 | Senaeya-2 115/13.8kV Substatio-Diesel for Generator | APPROVED | No | 2025-05-06 | Abas, Mohammed Fekry | 2025-05-08 | 2025-05-08 |  |  | Diesel - 2.34 | 76360.13 | 7264 | 0 | STANDARD | Al-Masar Al-Monasib Company for Logistics Services | SAR | 76360.13 | APPROVED |  |  | 2025-05-15 | 0 | 7 | Akhtar, Farhan | -45785 | 7
105-127 | Senaeya-2 115/13.8kV Substatio | 6660 | Senaeya-2 115/13.8kV Substatio-Fire rated materials | APPROVED | No | 2025-05-19 | Abas, Mohammed Fekry | 2025-05-26 | 2025-05-26 |  |  | Fire rated materials - Line Item 2.20 | 125000 | 7333 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 72500 | APPROVED |  |  | 2025-10-09 | 52500 | 136 | Tananeh, Khalid Jamal | -45803 | 136
105-127 | Senaeya-2 115/13.8kV Substatio | 6663 | Senaeya-2 115/13.8kV Substatio-Additional cable tray | INCOMPLETE | No |  | Basharat, Ameen Ahmed | 2025-05-20 |  |  |  | Fire rated materials - Line Item 2.20 | 25000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | 0 | 0
105-127 | Senaeya-2 115/13.8kV Substatio | 6763 | Senaeya-2 115/13.8kV Substatio-Generator for Testing Activities | APPROVED | No | 2025-06-01 | Abas, Mohammed Fekry | 2025-06-02 | 2025-06-02 |  |  | Generator for testing - 2.34 | 73000 | 7419 | 0 | STANDARD | Rawafd AlQwt Litaqt Est. | SAR | 73000 | APPROVED |  |  | 2025-07-01 | 0 | 29 | Akhtar, Farhan | -45810 | 29
105-127 | Senaeya-2 115/13.8kV Substatio | 6939 | Senaeya-2 115/13.8kV Substatio-Sockets & Switches | APPROVED | No | 2025-06-30 | Abas, Mohammed Fekry | 2025-07-03 | 2025-07-03 |  |  | Switches & Sockets - Line Item 2.23 | 99975 | 7174 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 99975 | APPROVED |  |  | 2025-08-07 | 0 | 35 | Muaz, Alaa | -45841 | 35
105-127 | Senaeya-2 115/13.8kV Substatio | 6992 | Senaeya-2 115/13.8kV Substatio-Testing Technicians | APPROVED | No | 2025-07-07 | Abas, Mohammed Fekry | 2025-07-09 | 2025-07-09 |  |  | Testing Techinicians (2.31) | 340000 | 7509 | 0 | STANDARD | Jasem M.AlJasem Contracting Est. | SAR | 340000 | APPROVED |  |  | 2025-07-29 | 0 | 20 | Babic, Marian | -45847 | 20
105-127 | Senaeya-2 115/13.8kV Substatio | 7108 | Senaeya-2 115/13.8kV Substatio-Decorative steel fence | APPROVED | No | 2025-07-15 | Abas, Mohammed Fekry | 2025-07-17 | 2025-07-20 |  |  | decorative steel fence - 2.20 | 148663 | 5636 | 1 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 148663 | APPROVED |  |  | 2025-12-17 | 0 | 150 | Tananeh, Khalid Jamal | -45858 | 150
105-127 | Senaeya-2 115/13.8kV Substatio | 7109 | Senaeya-2 115/13.8kV Substatio-Precast Walls | APPROVED | No | 2025-07-15 | Abas, Mohammed Fekry | 2025-07-17 | 2025-07-20 |  |  | Precast wall - 2.20 | 121175 | 5380 | 1 | STANDARD | Factory of Ideal Precast Concrete System Company | SAR | 121175 | APPROVED |  |  | 2025-09-14 | 0 | 56 | Tananeh, Khalid Jamal | -45858 | 56
105-127 | Senaeya-2 115/13.8kV Substatio | 7110 | Senaeya-2 115/13.8kV Substatio-Metal works | APPROVED | No | 2025-07-15 | Abas, Mohammed Fekry | 2025-07-17 | 2025-07-20 |  |  | Metal works - 2.20 | 343045 | 5636 | 1 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 343045 | APPROVED |  |  | 2025-12-17 | 0 | 150 | Tananeh, Khalid Jamal | -45858 | 150
105-127 | Senaeya-2 115/13.8kV Substatio | 7111 | Senaeya-2 115/13.8kV Substatio-Metallic Doors | APPROVED | No | 2025-07-15 | Abas, Mohammed Fekry | 2025-07-17 | 2025-07-20 |  |  | Metallic Doors - 2.20 | 105083 | 5636 | 1 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 106083 | APPROVED |  |  | 2025-12-17 | -1000 | 150 | Tananeh, Khalid Jamal | -45858 | 150
105-127 | Senaeya-2 115/13.8kV Substatio | 7161 | Senaeya-2 115/13.8kV Substatio-Telecom DCDB | APPROVED | No | 2025-07-21 | Abas, Mohammed Fekry | 2025-07-23 | 2025-07-23 |  |  | Telecom DCDB - 2.12 | 29700 | 7584 | 0 | STANDARD | HAWA ELECTRIC PANEL BOARD FAC | SAR | 29700 | APPROVED |  |  | 2025-08-07 | 0 | 15 | Abuhammad, Samir | -45861 | 15
105-127 | Senaeya-2 115/13.8kV Substatio | 7185 | Senaeya-2 115/13.8kV Substatio-Amedment for Diesel Supply for Senaeya-2 PO#7264-HV-1497 | APPROVED | No | 2025-07-22 | Abas, Mohammed Fekry | 2025-07-23 | 2025-07-23 |  |  | Task no.2.33 PO should be with Almasar co. | 50097.45 | 7264 | 1 | STANDARD | Al-Masar Al-Monasib Company for Logistics Services | SAR | 50097.45 | APPROVED |  |  | 2025-08-09 | 0 | 17 | Akhtar, Farhan | -45861 | 17
105-127 | Senaeya-2 115/13.8kV Substatio | 7255 | Senaeya-2 115/13.8kV Substatio-Additional LV Power Cable - 1C x 500mm2 | RETURNED | No | 2025-08-03 | Mohammed, Mohammed Adel Fahmy | 2026-01-15 | 2025-08-04 | 2026-01-15 |  | Not Have POCR Until Now and PR incorrect qty. | 42000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Mohammed Adel Fahmy | -45873 | -45873
105-127 | Senaeya-2 115/13.8kV Substatio | 7269 | Senaeya-2 115/13.8kV Substatio-Grounding Accessories | APPROVED | No | 2025-08-03 | Abas, Mohammed Fekry | 2025-08-05 | 2025-08-06 |  |  | 2.21 - ground accessories | 54106.2 | 7084 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 54106.2 | APPROVED |  |  | 2025-08-20 | 0 | 14 | Abdulqader, Ahmed Abdulhalim | -45875 | 14
105-127 | Senaeya-2 115/13.8kV Substatio | 7327 | Senaeya-2 115/13.8kV Substatio-POCR for ABSAR | APPROVED | No | 2025-08-11 | Abas, Mohammed Fekry | 2025-08-14 | 2025-08-18 |  |  | POCR for ABSAR - 2.20 | 27302.47 | 5647 | 1 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 27302.47 | IN PROCESS |  |  |  | 0 | 167 | Tananeh, Khalid Jamal | -45887 | -45887
105-127 | Senaeya-2 115/13.8kV Substatio | 7327 | Senaeya-2 115/13.8kV Substatio-POCR for ABSAR | APPROVED | No | 2025-08-11 | Abas, Mohammed Fekry | 2025-08-14 | 2025-08-18 |  |  | POCR for ABSAR - 2.20 | 27302.47 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45887 | -45887
105-127 | Senaeya-2 115/13.8kV Substatio | 7475 | Clamps | APPROVED | No | 2025-08-25 | Abas, Mohammed Fekry | 2025-08-27 | 2025-08-28 |  |  | Clamps for Senaeya - 2.19 | 0 | 7266 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 58425 | APPROVED |  |  | 2025-09-08 | -58425 | 11 | Hegazy, Ayman | -45897 | 11
105-127 | Senaeya-2 115/13.8kV Substatio | 7487 | Cable Support | APPROVED | No | 2025-08-25 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-03 |  |  | Cable Support - 2.19 | 0 | 7378 | 0 | STANDARD | ISAM KABBANI &Partners | SAR | 67405 | APPROVED |  |  | 2025-09-15 | -67405 | 12 | Hegazy, Ayman | -45903 | 12
105-127 | Senaeya-2 115/13.8kV Substatio | 7567 | Lugs and Glands for Senaeya-2 | APPROVED | No | 2025-08-28 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-03 |  |  | Revised PR for Lugs & Glands - Senaeya-2 - 2.13 | 0 | 7610 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 20402.24 | APPROVED |  |  | 2025-09-10 | -20402.24 | 7 | Abdulqader, Ahmed Abdulhalim | -45903 | 7
105-127 | Senaeya-2 115/13.8kV Substatio | 7613 | Additional Lighting Wires - Senaeya-2 | APPROVED | No | 2025-09-02 | Abas, Mohammed Fekry | 2025-09-07 | 2025-09-08 |  |  | Additional Lighting Materials - Senaeya-2 | 0 | 7963 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 15994.26 | APPROVED | 2026-01-19 | 2026-01-25 | 2026-01-28 | -15994.26 | 142 | Mohammed, Mohammed Adel Fahmy | 139 | 142
105-127 | Senaeya-2 115/13.8kV Substatio | 7914 | Office furniture - Senaeya-2 | APPROVED | No | 2025-10-07 | Abas, Mohammed Fekry | 2025-10-07 | 2025-10-08 |  |  | Office furniture - 2.33 - Senaeya-2 | 0 | 7707 | 0 | STANDARD | ALISMAIL INDUSTRIAL CO.(S) | SAR | 17590 | IN PROCESS |  |  |  | -17590 | 116 | Abdulqader, Ahmed Abdulhalim | -45938 | -45938
105-127 | Senaeya-2 115/13.8kV Substatio | 7914 | Office furniture - Senaeya-2 | APPROVED | No | 2025-10-07 | Abas, Mohammed Fekry | 2025-10-07 | 2025-10-08 |  |  | Office furniture - 2.33 - Senaeya-2 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45938 | -45938
105-127 | Senaeya-2 115/13.8kV Substatio | 8249 | PDS System | APPROVED | No | 2025-11-18 | Abas, Mohammed Fekry | 2025-11-18 | 2025-11-19 |  |  | Budget line 2.5 - PDS System | 0 | 7762 | 0 | STANDARD | RASHID SAEED AHMED AL GHAMDI COMM INFO TRAD EST | SAR | 140000 | APPROVED |  |  | 2025-12-25 | -140000 | 36 | Abdulqader, Ahmed Abdulhalim | -45980 | 36
105-127 | Senaeya-2 115/13.8kV Substatio | 8258 | Copper Tape 40x6 | APPROVED | No | 2025-11-18 | Abas, Mohammed Fekry | 2025-11-18 | 2025-11-19 |  |  | Budget line 2.21 - Grounding & Shielding system | 0 | 7662 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 31944 | APPROVED |  |  | 2025-11-24 | -31944 | 5 | Abdulqader, Ahmed Abdulhalim | -45980 | 5
105-127 | Senaeya-2 115/13.8kV Substatio | 8267 | Asphalt works (Activation of Optional Scope for PO# 5636) | APPROVED | No | 2025-11-18 | Abas, Mohammed Fekry | 2025-11-18 | 2025-11-19 |  |  | Budget line 2.20 - Civil & Structural Works | 0 | 5636 | 1 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 392250 | APPROVED |  |  | 2025-12-17 | -392250 | 28 | Tananeh, Khalid Jamal | -45980 | 28
105-127 | Senaeya-2 115/13.8kV Substatio | 8447 | Swing Gate Motor | APPROVED | No | 2025-12-04 | Abas, Mohammed Fekry | 2025-12-07 | 2025-12-09 |  |  |  | 0 | 7986 | 0 | STANDARD | ALMOSALLAMY INDUSTRIAL COMPANY | SAR | 9330 | APPROVED |  |  | 2025-12-15 | -9330 | 6 | Abdelraouf, Islam ِAdel Hanafy | -46000 | 6
105-127 | Senaeya-2 115/13.8kV Substatio | 8462 | ACs for Site 5 ton | RETURNED | No | 2025-12-07 | Abuhammad, Samir | 2025-12-16 | 2025-12-09 | 2025-12-16 |  | Due Budget modification | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46000 | -46000
105-127 | Senaeya-2 115/13.8kV Substatio | 8503 | Motion System - Lighting Control - Senaeya2 | APPROVED | No | 2025-12-11 | Abas, Mohammed Fekry | 2025-12-15 | 2025-12-17 |  |  | Line Item 2.22 - Lighting System | 0 | 7346 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 68054 | APPROVED |  |  | 2025-12-29 | -68054 | 12 | Hegazy, Ayman | -46008 | 12
105-127 | Senaeya-2 115/13.8kV Substatio | 8569 | Transformer Oil Sampling - Senaeya-2 | APPROVED | No | 2025-12-23 | Abas, Mohammed Fekry | 2025-12-24 | 2025-12-26 |  |  | Transformer Oil Sampling - 2.38 - Senaeya-2 | 0 | 7918 | 0 | STANDARD | Saudi Arabian Engineering Company | SAR | 37300 | IN PROCESS |  |  |  | -37300 | 37 | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46017 | -46017
105-127 | Senaeya-2 115/13.8kV Substatio | 8569 | Transformer Oil Sampling - Senaeya-2 | APPROVED | No | 2025-12-23 | Abas, Mohammed Fekry | 2025-12-24 | 2025-12-26 |  |  | Transformer Oil Sampling - 2.38 - Senaeya-2 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46017 | -46017
105-128 | Defaa 115/13.8kv Substation | 2042 | Defaa 115/13.8kv Substation-Defaa SS Engineering & Design | INCOMPLETE | No |  | Mughal, Aurang | 2023-12-26 |  |  |  | Transformer Oil Sampling - 2.38 - Senaeya-2 | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-128 | Defaa 115/13.8kv Substation | 2043 | Defaa 115/13.8kv Substation-Defaa SS Engineering & Design | APPROVED | No | 2023-12-26 | Abas, Mohammed Fekry | 2023-12-28 | 2023-12-28 |  |  |  | 581249 | 4899 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 570000 | APPROVED |  |  | 2024-01-08 | 11249 | 11 | Kumar, Mr. Ranjan | -45288 | 11
105-128 | Defaa 115/13.8kv Substation | 2054 | Defaa 115/13.8kv Substation-Defaa-13.8Kv Switch Gear | APPROVED | No | 2023-12-28 | Abas, Mohammed Fekry | 2024-01-01 | 2024-01-01 |  |  |  | 8210000 | 4865 | 0 | STANDARD | ALFANAR CO | SAR | 8210000 | APPROVED |  |  | 2024-03-13 | 0 | 72 | Alhadi, Khalid | -45292 | 72
105-128 | Defaa 115/13.8kv Substation | 2113 | Defaa 115/13.8kv Substation-Temporary Project Sign Board | APPROVED | No | 2024-01-08 | Abas, Mohammed Fekry | 2024-01-09 | 2024-01-09 |  |  |  | 20000 | 4969 | 0 | STANDARD | Construction Expertise Est. | SAR | 20000 | APPROVED |  |  | 2024-01-17 | 0 | 8 | Alhadi, Khalid | -45300 | 8
105-128 | Defaa 115/13.8kv Substation | 2159 | Defaa 115/13.8kv Substation-General backfill | APPROVED | No | 2024-01-11 | Abas, Mohammed Fekry | 2024-01-11 | 2024-01-14 |  |  |  | 300000 | 5086 | 0 | STANDARD | RADI AHMED AL MANHAL CO. LTD | SAR | 300000 | APPROVED |  |  | 2024-02-25 | 0 | 42 | Babic, Marian | -45305 | 42
105-128 | Defaa 115/13.8kv Substation | 2184 | Defaa 115/13.8kv Substation-C&P SAS AMI | APPROVED | No | 2024-01-16 | Abas, Mohammed Fekry | 2024-02-11 | 2024-02-12 |  |  |  | 10100000 | 4848 | 0 | STANDARD | ALFANAR CO | SAR | 10100000 | APPROVED |  |  | 2024-03-13 | 0 | 30 | Babic, Marian | -45334 | 30
105-128 | Defaa 115/13.8kv Substation | 2191 | Defaa 115/13.8kv Substation-13.8KV SWITCHGEAR | APPROVED | No | 2024-01-17 | Abas, Mohammed Fekry | 2024-02-11 | 2024-02-12 |  |  |  | 740000 | 4865 | 0 | STANDARD | ALFANAR CO | SAR | 740000 | APPROVED |  |  | 2024-03-13 | 0 | 30 | Alhadi, Khalid | -45334 | 30
105-128 | Defaa 115/13.8kv Substation | 2241 | Defaa 115/13.8kv Substation-Cyber Security | APPROVED | No | 2024-01-21 | Abas, Mohammed Fekry | 2024-01-22 | 2024-01-22 |  |  |  | 1100000 | 5060 | 0 | STANDARD | ALFANAR CO | SAR | 1100000 | APPROVED |  |  | 2024-02-18 | 0 | 27 | Babic, Marian | -45313 | 27
105-128 | Defaa 115/13.8kv Substation | 2495 | Defaa 115/13.8kv Substation-Security Cabin | RETURNED | No | 2024-02-07 | Alhadi, Khalid | 2024-04-21 | 2024-02-10 | 2024-04-21 |  | Incomplete scope | 9000 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45332 | -45332
105-128 | Defaa 115/13.8kv Substation | 2544 | Defaa 115/13.8kv Substation-Super Structure Precast including Fire Walls | APPROVED | No | 2024-02-13 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-19 |  |  |  | 2421479 | 5387 | 0 | STANDARD | Factory of Ideal Precast Concrete System Company | SAR | 2095473 | APPROVED |  |  | 2024-04-24 | 326006 | 65 | Tananeh, Khalid Jamal | -45341 | 65
105-128 | Defaa 115/13.8kv Substation | 2910 | Defaa 115/13.8kv Substation-Topographic Survey of Project Area | APPROVED | No | 2024-03-26 | Abas, Mohammed Fekry | 2024-03-31 | 2024-03-31 |  |  |  | 5125 | 5722 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 5125 | APPROVED |  |  | 2024-06-24 | 0 | 85 | Alhadi, Khalid | -45382 | 85
105-128 | Defaa 115/13.8kv Substation | 2935 | Defaa 115/13.8kv Substation-AC/DB and DCDB & Lighting Panels | APPROVED | No | 2024-03-28 | Abas, Mohammed Fekry | 2024-03-31 | 2024-03-31 |  |  |  | 870000 | 5369 | 0 | STANDARD | ALFANAR CO | SAR | 870000 | APPROVED |  |  | 2024-04-30 | 0 | 30 | Mohammed, Faisal Ansari | -45382 | 30
105-128 | Defaa 115/13.8kv Substation | 3038 | Defaa 115/13.8kv Substation-Electric Overhead Travelling Crane (5 TON, 30.695 m Traviling dist., span 12 m) | APPROVED | No | 2024-04-16 | Abas, Mohammed Fekry | 2024-04-17 | 2024-04-24 |  |  |  | 130000 | 5464 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 126870 | APPROVED |  |  | 2024-05-16 | 3130 | 22 | Muhammad, Muhammad Atif | -45406 | 22
105-128 | Defaa 115/13.8kv Substation | 3161 | Defaa 115/13.8kv Substation-Supply & Apply (Roof Waterproofing system & Underground Waterproofing Tanking system ) | APPROVED | No | 2024-04-27 | Abas, Mohammed Fekry | 2024-05-02 | 2024-05-02 |  |  |  | 392625 | 5648 | 0 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 347826.5 | APPROVED |  |  | 2024-06-16 | 44798.5 | 45 | Tananeh, Khalid Jamal | -45414 | 45
105-128 | Defaa 115/13.8kv Substation | 3306 | Defaa 115/13.8kv Substation-Site Office Facility- Electronic items | APPROVED | No | 2024-05-05 | Abas, Mohammed Fekry | 2024-05-09 | 2024-05-12 |  |  |  | 33800 | 5610 | 0 | STANDARD | Construction Expertise Est. | SAR | 33800 | APPROVED |  |  | 2024-06-03 | 0 | 22 | Muhammad, Muhammad Atif | -45424 | 22
105-128 | Defaa 115/13.8kv Substation | 3391 | Defaa 115/13.8kv Substation-Supply and install Site Temporary Chain Link fence | APPROVED | No | 2024-05-13 | Abas, Mohammed Fekry | 2024-05-16 | 2024-05-17 |  |  |  | 61500 | 5581 | 0 | STANDARD | Construction Expertise Est. | SAR | 61500 | APPROVED |  |  | 2024-05-27 | 0 | 10 | Alhadi, Khalid | -45429 | 10
105-128 | Defaa 115/13.8kv Substation | 3409 | Defaa 115/13.8kv Substation-150sq.mm, Tinned copper conductor | APPROVED | No | 2024-05-15 | Abas, Mohammed Fekry | 2024-05-16 | 2024-05-17 |  |  |  | 38500 | 5356 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 38455.41 | APPROVED |  |  | 2024-05-21 | 44.59 | 4 | Muhammad, Muhammad Atif | -45429 | 4
105-128 | Defaa 115/13.8kv Substation | 3506 | Defaa 115/13.8kv Substation-125 KVA and 300 KV GENERATORS | REJECTED | Yes | 2024-05-28 | Basharat, Ameen Ahmed | 2024-05-29 | 2024-05-28 |  | 2024-05-29 |  | 270000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45440 | -45440
105-128 | Defaa 115/13.8kv Substation | 3525 | Defaa 115/13.8kv Substation-125 V DC System (Battery GEL Type & Chargers ) | APPROVED | No | 2024-05-28 | Sherif, Marwa | 2024-06-03 | 2024-06-03 |  |  |  | 550000 | 5741 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 457000 | APPROVED |  |  | 2024-07-15 | 93000 | 42 | Muhammad, Muhammad Atif | -45446 | 42
105-128 | Defaa 115/13.8kv Substation | 3532 | Defaa 115/13.8kv Substation-125 KVA and 300 KV GENERATOR | APPROVED | No | 2024-05-29 | Sherif, Marwa | 2024-06-03 | 2024-06-05 |  |  |  | 270000 | 5729 | 0 | STANDARD | Mohammed A. AlFaddaghi & Partners | SAR | 268350 | APPROVED |  |  | 2024-07-17 | 1650 | 42 | Akhtar, Farhan | -45448 | 42
105-128 | Defaa 115/13.8kv Substation | 3621 | Defaa 115/13.8kv Substation-Grounding material accessories | APPROVED | No | 2024-06-08 | Abas, Mohammed Fekry | 2024-06-09 | 2024-06-09 |  |  |  | 72850 | 5559 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 72850 | APPROVED |  |  | 2024-07-07 | 0 | 28 | Muhammad, Muhammad Atif | -45452 | 28
105-128 | Defaa 115/13.8kv Substation | 3740 | Defaa 115/13.8kv Substation-MV Power Cable (1C x 630mm2 & 3C x 300mm2) | APPROVED | No | 2024-07-02 | Abas, Mohammed Fekry | 2024-07-05 | 2024-07-07 |  |  |  | 1250303.34 | 6025 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 1117800.18 | APPROVED |  |  | 2024-10-09 | 132503.16 | 94 | Badhman, Saeed | -45480 | 94
105-128 | Defaa 115/13.8kv Substation | 3750 | Defaa 115/13.8kv Substation-Sewage Water removal services, 10,000 Ltrs. | APPROVED | No | 2024-07-02 | Abas, Mohammed Fekry | 2024-07-05 | 2024-07-07 |  |  |  | 10000 | 5932 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 300 | APPROVED |  |  | 2024-08-18 | 9700 | 42 | Akhtar, Farhan | -45480 | 42
105-128 | Defaa 115/13.8kv Substation | 3751 | Defaa 115/13.8kv Substation-Supply & Delivery of Raw Water, 10 Cu. M Tanker | APPROVED | No | 2024-07-02 | Abas, Mohammed Fekry | 2024-07-05 | 2024-07-07 |  |  |  | 2000 | 5932 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 1800 | APPROVED |  |  | 2024-08-18 | 200 | 42 | Akhtar, Farhan | -45480 | 42
105-128 | Defaa 115/13.8kv Substation | 3754 | Defaa 115/13.8kv Substation-Diesel Supply 1.15 SAR/ Ltr. (15000 Lt/Month) | APPROVED | No | 2024-07-02 | Abas, Mohammed Fekry | 2024-07-05 | 2024-07-07 |  |  |  | 17250 | 5796 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 15652.2 | APPROVED |  |  | 2024-07-18 | 1597.8 | 11 | Akhtar, Farhan | -45480 | 11
105-128 | Defaa 115/13.8kv Substation | 3778 | Defaa 115/13.8kv Substation-Garbage Waste Container, 12 Cu. M (1 year) | APPROVED | No | 2024-07-07 | Abas, Mohammed Fekry | 2024-07-09 | 2024-07-09 |  |  |  | 28800 | 5882 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 19200 | APPROVED |  |  | 2024-08-20 | 9600 | 42 | Akhtar, Farhan | -45482 | 42
105-128 | Defaa 115/13.8kv Substation | 3878 | Defaa 115/13.8kv Substation-LV Control Cables | APPROVED | No | 2024-07-14 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 716000 | 5827 | 0 | STANDARD | ALFANAR CO | SAR | 531752.8 | APPROVED |  |  | 2024-08-25 | 184247.2 | 40 | Muhammad, Muhammad Atif | -45489 | 40
105-128 | Defaa 115/13.8kv Substation | 3937 | Defaa 115/13.8kv Substation-MV Cable Termination Kit | APPROVED | No | 2024-07-16 | Issa, Amr Ali | 2024-07-21 | 2024-07-21 |  |  |  | 98837 | 5987 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 95871.89 | APPROVED |  |  | 2024-09-19 | 2965.11 | 60 | Badhman, Saeed | -45494 | 60
105-128 | Defaa 115/13.8kv Substation | 3966 | Defaa 115/13.8kv Substation-Testing & Commissioning | APPROVED | No | 2024-07-21 | Abas, Mohammed Fekry | 2024-07-23 | 2024-07-25 |  |  |  | 1914810 | 6448 | 0 | STANDARD | Al Fanar Technical Services | SAR | 1861024 | APPROVED |  |  | 2025-03-13 | 53786 | 231 | Alqadhi, Abdulrahman Abdulghani | -45498 | 231
105-128 | Defaa 115/13.8kv Substation | 4047 | Defaa 115/13.8kv Substation-Lightning System | APPROVED | No | 2024-07-29 | Abas, Mohammed Fekry | 2024-08-01 | 2024-08-01 |  |  |  | 59075 | 6034 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 59075 | APPROVED |  |  | 2024-10-06 | 0 | 66 | Badhman, Saeed | -45505 | 66
105-128 | Defaa 115/13.8kv Substation | 4067 | Defaa 115/13.8kv Substation-Cable Tray | APPROVED | No | 2024-07-31 | Abas, Mohammed Fekry | 2024-08-01 | 2024-08-01 |  |  |  | 552885 | 5919 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 505784.96 | APPROVED |  |  | 2024-09-18 | 47100.04 | 48 | Muhammad, Muhammad Atif | -45505 | 48
105-128 | Defaa 115/13.8kv Substation | 4079 | Defaa 115/13.8kv Substation-Soil Resistivity | APPROVED | No | 2024-08-01 | Abas, Mohammed Fekry | 2024-08-05 | 2024-08-05 |  |  |  | 7360 | 6056 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 6400 | APPROVED |  |  | 2024-10-10 | 960 | 66 | Tananeh, Khalid Jamal | -45509 | 66
105-128 | Defaa 115/13.8kv Substation | 4083 | Defaa 115/13.8kv Substation-Supply & Delivery of Drinking Water, | APPROVED | No | 2024-08-04 | Abas, Mohammed Fekry | 2024-08-06 | 2024-08-06 |  |  |  | 3500 | 5932 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 3000 | APPROVED |  |  | 2024-08-18 | 500 | 12 | Akhtar, Farhan | -45510 | 12
105-128 | Defaa 115/13.8kv Substation | 4191 | Defaa 115/13.8kv Substation-Hazardous and Non-Hazardous Waste | APPROVED | No | 2024-08-19 | Abas, Mohammed Fekry | 2024-08-19 | 2024-08-19 |  |  |  | 5000 | 6122 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 3650 | APPROVED |  |  | 2024-09-19 | 1350 | 31 | Akhtar, Farhan | -45523 | 31
105-128 | Defaa 115/13.8kv Substation | 4194 | Defaa 115/13.8kv Substation-LV Power Cables | APPROVED | No | 2024-08-19 | Abas, Mohammed Fekry | 2024-08-19 | 2024-08-20 |  |  |  | 1611070 | 6082 | 0 | STANDARD | ALFANAR CO | SAR | 1110509.38 | APPROVED |  |  | 2024-10-01 | 500560.62 | 42 | Badhman, Saeed | -45524 | 42
105-128 | Defaa 115/13.8kv Substation | 4250 | Defaa 115/13.8kv Substation-Grounding Cables | APPROVED | No | 2024-08-24 | Abas, Mohammed Fekry | 2024-08-27 | 2024-09-01 |  |  |  | 91150 | 6066 | 0 | STANDARD | ALFANAR CO | SAR | 83943.19 | APPROVED |  |  | 2024-09-18 | 7206.81 | 17 | Muhammad, Muhammad Atif | -45536 | 17
105-128 | Defaa 115/13.8kv Substation | 4268 | Defaa 115/13.8kv Substation-Grounding Cable | APPROVED | No | 2024-08-26 | Abas, Mohammed Fekry | 2024-08-27 | 2024-09-01 |  |  |  | 153000 | 6066 | 0 | STANDARD | ALFANAR CO | SAR | 142813.33 | APPROVED |  |  | 2024-09-18 | 10186.67 | 17 | Muhammad, Muhammad Atif | -45536 | 17
105-128 | Defaa 115/13.8kv Substation | 4271 | Defaa 115/13.8kv Substation-Pest Control | APPROVED | No | 2024-08-26 | Abas, Mohammed Fekry | 2024-08-27 | 2024-09-01 |  |  |  | 1400 | 6230 | 0 | STANDARD | Trap Pest Control &Garden Maintenance Co. LTD | SAR | 1200 | APPROVED |  |  | 2024-09-30 | 200 | 29 | Akhtar, Farhan | -45536 | 29
105-128 | Defaa 115/13.8kv Substation | 4427 | Defaa 115/13.8kv Substation-Diesel Supply for Generator (10000 liter/Month) for Ten Months | APPROVED | No | 2024-09-12 | Abas, Mohammed Fekry | 2024-09-16 | 2024-09-17 |  |  |  | 104350 | 6278 | 0 | STANDARD | Al-Masar Al-Monasib Company for Logistics Services | SAR | 101000 | APPROVED |  |  | 2024-10-09 | 3350 | 22 | Akhtar, Farhan | -45552 | 22
105-128 | Defaa 115/13.8kv Substation | 4458 | Defaa 115/13.8kv Substation-Fire Alaram and Fire Protection System | APPROVED | No | 2024-09-15 | Abas, Mohammed Fekry | 2024-09-16 | 2024-09-17 |  |  |  | 2274336.9 | 6001 | 0 | STANDARD | Al Majal Group Four S for Security & Safety | SAR | 2274336.9 | APPROVED |  |  | 2024-09-26 | 0 | 9 | Muhammad, Muhammad Atif | -45552 | 9
105-128 | Defaa 115/13.8kv Substation | 4494 | Defaa 115/13.8kv Substation-Site Office facility | APPROVED | No | 2024-09-22 | Abas, Mohammed Fekry | 2024-09-24 | 2024-09-24 |  |  |  | 562550 | 5426 | 0 | STANDARD | Construction Expertise Est. | SAR | 562550 | APPROVED |  |  | 2024-10-06 | 0 | 12 | Muhammad, Muhammad Atif | -45559 | 12
105-128 | Defaa 115/13.8kv Substation | 4580 | Defaa 115/13.8kv Substation-Station Service Transformer | APPROVED | No | 2024-10-02 | Abas, Mohammed Fekry | 2024-10-03 | 2024-10-04 |  |  |  | 164000 | 5910 | 0 | STANDARD | ALFANAR CO | SAR | 164000 | APPROVED |  |  | 2024-10-08 | 0 | 4 | Muhammad, Muhammad Atif | -45569 | 4
105-128 | Defaa 115/13.8kv Substation | 4582 | Defaa 115/13.8kv Substation-RTV Coating | APPROVED | No | 2024-10-02 | Abas, Mohammed Fekry | 2024-10-03 | 2024-10-04 |  |  |  | 250000 | 6336 | 0 | STANDARD | SAUDI CONDUIT COATING CO. (S3C) | SAR | 35268 | APPROVED |  |  | 2024-10-23 | 214732 | 19 | Muaz, Alaa | -45569 | 19
105-128 | Defaa 115/13.8kv Substation | 4601 | Defaa 115/13.8kv Substation-Electrical Installation Contractor | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-06 | 2024-10-06 |  |  |  | 2992521 | 6434 | 0 | STANDARD | Construction Expertise Est. | SAR | 2230000 | APPROVED |  |  | 2024-12-29 | 762521 | 84 | Muhammad, Muhammad Atif | -45571 | 84
105-128 | Defaa 115/13.8kv Substation | 4638 | Defaa 115/13.8kv Substation-HVAC System | APPROVED | No | 2024-10-09 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-10 |  |  |  | 2050000 | 6204 | 0 | STANDARD | Ramz Alataa Company for Trading | SAR | 2050000 | APPROVED |  |  | 2024-10-30 | 0 | 20 | Muhammad, Muhammad Atif | -45575 | 20
105-128 | Defaa 115/13.8kv Substation | 4681 | Defaa 115/13.8kv Substation-Telecom System | APPROVED | No | 2024-10-15 | Abas, Mohammed Fekry | 2024-10-16 | 2024-10-17 |  |  |  | 1882004 | 5852 | 0 | STANDARD | ALFANAR CO | SAR | 1882004 | APPROVED |  |  | 2025-03-18 | 0 | 152 | Kumar, Mr. Ranjan | -45582 | 152
105-128 | Defaa 115/13.8kv Substation | 4748 | Defaa 115/13.8kv Substation-Subcontractor for Civil Works | APPROVED | No | 2024-10-20 | Abas, Mohammed Fekry | 2024-10-21 | 2024-10-21 |  |  |  | 9354935 | 5638 | 0 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 9354935 | APPROVED |  |  | 2024-11-04 | 0 | 14 | Tananeh, Khalid Jamal | -45586 | 14
105-128 | Defaa 115/13.8kv Substation | 4941 | Defaa 115/13.8kv Substation-Third Party lab Inspector for Precast Concrete Prodaction Test | APPROVED | No | 2024-11-14 | Abas, Mohammed Fekry | 2024-11-14 | 2024-11-14 |  |  |  | 84190 | 6547 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 84190 | APPROVED |  |  | 2024-12-18 | 0 | 34 | Tananeh, Khalid Jamal | -45610 | 34
105-128 | Defaa 115/13.8kv Substation | 4967 | Defaa 115/13.8kv Substation-Lighting Fixtures | APPROVED | No | 2024-11-17 | Abas, Mohammed Fekry | 2024-11-19 | 2024-11-19 |  |  |  | 88037 | 6473 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 88037 | APPROVED |  |  | 2024-11-27 | 0 | 8 | Muhammad, Muhammad Atif | -45615 | 8
105-128 | Defaa 115/13.8kv Substation | 5098 | Defaa 115/13.8kv Substation-HCIS Consultant | APPROVED | No | 2024-11-30 | Abas, Mohammed Fekry | 2025-01-08 | 2025-01-08 |  |  |  | 33500 | 6512 | 0 | STANDARD | Khaled Drewesh Office for Consulting Security (KDOCS) | SAR | 33500 | APPROVED |  |  | 2025-01-15 | 0 | 7 | Muhammad, Muhammad Atif | -45665 | 7
105-128 | Defaa 115/13.8kv Substation | 5193 | Defaa 115/13.8kv Substation-Clamps & Connectors | APPROVED | No | 2024-12-08 | Abas, Mohammed Fekry | 2024-12-09 | 2024-12-12 |  |  |  | 4512 | 6418 | 0 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 4505.16 | APPROVED |  |  | 2025-01-02 | 6.84 | 21 | Mohammed, Faisal Ansari | -45638 | 21
105-128 | Defaa 115/13.8kv Substation | 5287 | Defaa 115/13.8kv Substation-Tinned Copper Conductor | APPROVED | No | 2024-12-29 | Abas, Mohammed Fekry | 2024-12-31 | 2025-01-01 |  |  |  | 142500 | 6755 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 131856 | APPROVED |  |  | 2025-03-03 | 10644 | 61 | Alhadi, Khalid | -45658 | 61
105-128 | Defaa 115/13.8kv Substation | 5318 | Defaa 115/13.8kv Substation-Control Cable for SAS Alarm (Blue Color) | APPROVED | No | 2025-01-01 | Abas, Mohammed Fekry | 2025-01-07 | 2025-01-07 |  |  |  | 55000 | 6784 | 0 | STANDARD | ALFANAR CO | SAR | 52600 | APPROVED |  |  | 2025-04-14 | 2400 | 97 | Muaz, Alaa | -45664 | 97
105-128 | Defaa 115/13.8kv Substation | 5356 | Defaa 115/13.8kv Substation-Lighting Conduits & Fittings | APPROVED | No | 2025-01-05 | Abas, Mohammed Fekry | 2025-01-08 | 2025-01-12 |  |  |  | 342909.3 | 6689 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 342909.3 | APPROVED |  |  | 2025-01-22 | 0 | 10 | Muaz, Alaa | -45669 | 10
105-128 | Defaa 115/13.8kv Substation | 5370 | Defaa 115/13.8kv Substation-Security System | APPROVED | No | 2025-01-07 | Abas, Mohammed Fekry | 2025-04-24 | 2025-04-24 |  |  | Security System - Line Item 5.7 | 810532.85 | 6641 | 0 | STANDARD | CEGELEC NETWORK AND SECURITY SYSTEMS | SAR | 810532.85 | APPROVED |  |  | 2025-05-13 | 0 | 19 | Abdulqader, Ahmed Abdulhalim | -45771 | 19
105-128 | Defaa 115/13.8kv Substation | 5509 | Defaa 115/13.8kv Substation-CTPU & CTPU Box | APPROVED | No | 2025-01-21 | Abas, Mohammed Fekry | 2025-01-26 | 2025-01-27 |  |  |  | 68000 | 6288 | 0 | STANDARD | Energy Tracks For Contracting | SAR | 68000 | APPROVED |  |  | 2025-03-04 | 0 | 36 | Kumar, Mr. Ranjan | -45684 | 36
105-128 | Defaa 115/13.8kv Substation | 5529 | Defaa 115/13.8kv Substation-Crash Barrier | APPROVED | No | 2025-01-22 | Abas, Mohammed Fekry | 2025-02-03 | 2025-02-05 |  |  |  | 20000 | 6879 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 20000 | APPROVED |  |  | 2025-02-10 | 0 | 5 | Abuhammad, Samir | -45693 | 5
105-128 | Defaa 115/13.8kv Substation | 5580 | Defaa 115/13.8kv Substation-FO Cables | APPROVED | No | 2025-01-25 | Abas, Mohammed Fekry | 2025-01-27 | 2025-01-30 |  |  |  | 500000 | 6951 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 210000 | APPROVED |  |  | 2025-03-11 | 290000 | 40 | Abdulqader, Ahmed Abdulhalim | -45687 | 40
105-128 | Defaa 115/13.8kv Substation | 5586 | Defaa 115/13.8kv Substation-Remote Ends Modification | APPROVED | No | 2025-01-25 | Abas, Mohammed Fekry | 2025-01-27 | 2025-01-30 |  |  |  | 200000 | 7324 | 0 | STANDARD | TRINERGY TECHNOLOGIES SA | SAR | 200000 | APPROVED |  |  | 2025-05-25 | 0 | 115 | Babic, Marian | -45687 | 115
105-128 | Defaa 115/13.8kv Substation | 5819 | Defaa 115/13.8kv Substation-Boxes and fittings for Sockets | APPROVED | No | 2025-02-09 | Abas, Mohammed Fekry | 2025-02-09 | 2025-02-11 |  |  |  | 49999 | 6931 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 12118 | APPROVED |  |  | 2025-02-26 | 37881 | 15 | Abuhammad, Samir | -45699 | 15
105-128 | Defaa 115/13.8kv Substation | 5868 | Defaa 115/13.8kv Substation-HV Cable Support | APPROVED | No | 2025-02-16 | Abas, Mohammed Fekry | 2025-02-17 | 2025-02-18 |  |  |  | 200000 | 7002 | 0 | STANDARD | ABDULLAH M. AL-SHAHRANI FACTORY | SAR | 97327.5 | APPROVED |  |  | 2025-03-20 | 102672.5 | 30 | Hegazy, Ayman | -45706 | 30
105-128 | Defaa 115/13.8kv Substation | 5868 | Defaa 115/13.8kv Substation-HV Cable Support | APPROVED | No | 2025-02-16 | Abas, Mohammed Fekry | 2025-02-17 | 2025-02-18 |  |  |  | 200000 | 7002 | 1 | STANDARD | ABDULLAH M. AL-SHAHRANI FACTORY | SAR | 97327.5 | REQUIRES REAPPROVAL |  |  |  | 102672.5 | 348 | Hegazy, Ayman | -45706 | -45706
105-128 | Defaa 115/13.8kv Substation | 6033 | Defaa 115/13.8kv Substation-Additional Materials for Rooftop Cable Tray | APPROVED | No | 2025-02-24 | Abas, Mohammed Fekry | 2025-02-25 | 2025-02-25 |  |  | Additional Materials for Rooftop Cable Tray - Line Item 2.19 | 10000 | 6960 | 0 | STANDARD | Essa Al Asmakh Trading Est. | SAR | 9315 | APPROVED |  |  | 2025-03-09 | 685 | 12 | Abuhammad, Samir | -45713 | 12
105-128 | Defaa 115/13.8kv Substation | 6100 | Defaa 115/13.8kv Substation-Drawing Printing A2 | APPROVED | No | 2025-03-03 | Abas, Mohammed Fekry | 2025-03-03 | 2025-03-05 |  |  | Drawing Printing - Line Tem 2.33 | 31000 | 7062 | 0 | STANDARD | Print Magaies Al abdaa Printing | SAR | 30999 | APPROVED |  |  | 2025-04-07 | 1 | 33 | Abuhammad, Samir | -45721 | 33
105-128 | Defaa 115/13.8kv Substation | 6198 | Defaa 115/13.8kv Substation-Rental Generator | APPROVED | No | 2025-03-18 | Abas, Mohammed Fekry | 2025-03-18 | 2025-03-20 |  |  | Rental Generator for Testing works - 2.34 | 48000 | 7245 | 0 | STANDARD | Rawafd AlQwt Litaqt Est. | SAR | 48000 | APPROVED |  |  | 2025-05-18 | 0 | 59 | Akhtar, Farhan | -45736 | 59
105-128 | Defaa 115/13.8kv Substation | 6428 | Defaa 115/13.8kv Substation-Gypsum Boards | APPROVED | No | 2025-04-23 | Abas, Mohammed Fekry | 2025-04-24 | 2025-04-24 |  |  | Gypsum Board - Line Item 2.20 | 6000 | 7198 | 0 | STANDARD | Tamim Company (PVT) LTD | SAR | 6000 | APPROVED |  |  | 2025-05-05 | 0 | 11 | Abuhammad, Samir | -45771 | 11
105-128 | Defaa 115/13.8kv Substation | 6495 | Defaa 115/13.8kv Substation-Rental Generator | APPROVED | No | 2025-05-01 | Abas, Mohammed Fekry | 2025-05-05 | 2025-05-05 |  |  | Generator for Testing Activity - Defaa | 25000 | 7245 | 0 | STANDARD | Rawafd AlQwt Litaqt Est. | SAR | 25000 | APPROVED |  |  | 2025-05-18 | 0 | 13 | Akhtar, Farhan | -45782 | 13
105-128 | Defaa 115/13.8kv Substation | 6503 | Defaa 115/13.8kv Substation-Air Conditioner | APPROVED | No | 2025-05-04 | Abas, Mohammed Fekry | 2025-05-05 | 2025-05-05 |  |  | Air Conditioner - 2.20 | 15400 | 7231 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 15400 | APPROVED |  |  | 2025-05-12 | 0 | 7 | Abuhammad, Samir | -45782 | 7
105-128 | Defaa 115/13.8kv Substation | 6518 | Defaa 115/13.8kv Substation-4P x 1.5mm2 Cable | APPROVED | No | 2025-05-05 | Abas, Mohammed Fekry | 2025-05-06 | 2025-05-06 |  |  | 4P x 1.5mm2 Cable | 9000 | 7317 | 0 | STANDARD | Middle East Specialized Cables Mesc | SAR | 7500 | APPROVED |  |  | 2025-05-27 | 1500 | 21 | Abuhammad, Samir | -45783 | 21
105-128 | Defaa 115/13.8kv Substation | 6546 | Defaa 115/13.8kv Substation-Diesel for Generator | APPROVED | No | 2025-05-06 | Abas, Mohammed Fekry | 2025-05-08 | 2025-05-08 |  |  | Diesel for generator - Line Item 2.38 | 76360.13 | 7263 | 0 | STANDARD | Al-Masar Al-Monasib Company for Logistics Services | SAR | 76360.13 | APPROVED |  |  | 2025-05-15 | 0 | 7 | Akhtar, Farhan | -45785 | 7
105-128 | Defaa 115/13.8kv Substation | 6633 | Defaa 115/13.8kv Substation-Testing technicians | APPROVED | No | 2025-05-18 | Abas, Mohammed Fekry | 2025-05-20 | 2025-05-20 |  |  | Testing technicians - 2.31 | 324480 | 7243 | 0 | STANDARD | SMART LINES INDUSTRIAL & SERVCIES COMPANY | SAR | 324480 | APPROVED |  |  | 2025-07-10 | 0 | 51 | Babic, Marian | -45797 | 51
105-128 | Defaa 115/13.8kv Substation | 6639 | Defaa 115/13.8kv Substation-Grounding Accessories | APPROVED | No | 2025-05-19 | Abas, Mohammed Fekry | 2025-05-25 | 2025-05-26 |  |  | Grounding Accessories | 11600 | 7366 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 11100 | APPROVED |  |  | 2025-07-22 | 500 | 57 | Abuhammad, Samir | -45803 | 57
105-128 | Defaa 115/13.8kv Substation | 6659 | Defaa 115/13.8kv Substation-Fire rated materials | APPROVED | No | 2025-05-19 | Abas, Mohammed Fekry | 2025-05-26 | 2025-05-26 |  |  | Fire rated materials - Line Item 2.20 | 150000 | 7332 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 87493 | APPROVED |  |  | 2025-09-10 | 62507 | 107 | Tananeh, Khalid Jamal | -45803 | 107
105-128 | Defaa 115/13.8kv Substation | 6802 | Defaa 115/13.8kv Substation-Additional Lighting conduits | APPROVED | No | 2025-06-15 | Abas, Mohammed Fekry | 2025-06-23 | 2025-06-25 |  |  | Additional Lighting Materils - Line Item 2.23 | 49999 | 7431 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 23328 | APPROVED |  |  | 2025-07-03 | 26671 | 8 | Abuhammad, Samir | -45833 | 8
105-128 | Defaa 115/13.8kv Substation | 6940 | Defaa 115/13.8kv Substation-Sokcets & Switches | APPROVED | No | 2025-06-30 | Abas, Mohammed Fekry | 2025-07-03 | 2025-07-03 |  |  | Sockets & Switches - Line Item 2.23 | 96720 | 6725 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 96720 | APPROVED |  |  | 2025-08-10 | 0 | 38 | Muaz, Alaa | -45841 | 38
105-128 | Defaa 115/13.8kv Substation | 7104 | Defaa 115/13.8kv Substation-Steel decorative fence | APPROVED | No | 2025-07-15 | Abas, Mohammed Fekry | 2025-07-17 | 2025-11-19 |  |  | Steel decorative fence - 2.20 | 585315 | 5638 | 1 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 2216303 | APPROVED | 2026-01-13 | 2026-01-25 | 2026-01-29 | 0 | 193 | Tananeh, Khalid Jamal | 67 | 71
105-128 | Defaa 115/13.8kv Substation | 7130 | Defaa 115/13.8kv Substation-Testing Technicians | APPROVED | No | 2025-07-17 | Abas, Mohammed Fekry | 2025-07-21 | 2025-07-22 |  |  | Testing Technicians - 2.31 | 182520 | 7243 | 1 | STANDARD | SMART LINES INDUSTRIAL & SERVCIES COMPANY | SAR | 182520 | APPROVED |  |  | 2025-08-02 | 0 | 11 | Babic, Marian | -45860 | 11
105-128 | Defaa 115/13.8kv Substation | 7158 | Defaa 115/13.8kv Substation-Telecom DCDB | APPROVED | No | 2025-07-21 | Abas, Mohammed Fekry | 2025-07-23 | 2025-07-23 |  |  | Telecom DCDB - 2.12 | 29700 | 7583 | 0 | STANDARD | HAWA ELECTRIC PANEL BOARD FAC | SAR | 29700 | APPROVED |  |  | 2025-08-07 | 0 | 15 | Abuhammad, Samir | -45861 | 15
105-128 | Defaa 115/13.8kv Substation | 7184 | Defaa 115/13.8kv Substation-Amedment for Diesel Supply for Defaa PO#7263-HV-1497 | APPROVED | No | 2025-07-22 | Abas, Mohammed Fekry | 2025-07-23 | 2025-07-23 |  |  | taskNo.2.33 | 108907.5 | 7263 | 1 | STANDARD | Al-Masar Al-Monasib Company for Logistics Services | SAR | 108907.5 | APPROVED |  |  | 2025-08-10 | 0 | 18 | Akhtar, Farhan | -45861 | 18
105-128 | Defaa 115/13.8kv Substation | 7267 | Defaa 115/13.8kv Substation-Grounding Accessories | APPROVED | No | 2025-08-03 | Abas, Mohammed Fekry | 2025-08-05 | 2025-08-06 |  |  | Grounding Accessories | 58469.7 | 7086 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 58469.7 | APPROVED |  |  | 2025-08-21 | 0 | 15 | Abdulqader, Ahmed Abdulhalim | -45875 | 15
105-128 | Defaa 115/13.8kv Substation | 7324 | Defaa 115/13.8kv Substation-POCR for Absar | APPROVED | No | 2025-08-11 | Abas, Mohammed Fekry | 2025-08-14 | 2025-08-18 |  |  | POCR for Absar | 37264.54 | 5648 | 1 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 37264.54 | APPROVED |  |  | 2025-09-17 | 0 | 30 | Tananeh, Khalid Jamal | -45887 | 30
105-128 | Defaa 115/13.8kv Substation | 7392 | Additional Lighting Wires | APPROVED | No | 2025-08-25 | Abas, Mohammed Fekry | 2025-08-27 | 2025-08-28 |  |  | Additional Lighting Wires - 2.13 | 0 | 7966 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 2308.4 | APPROVED | 2026-01-19 | 2026-01-25 | 2026-01-28 | -2308.4 | 153 | Mohammed, Mohammed Adel Fahmy | 150 | 153
105-128 | Defaa 115/13.8kv Substation | 7460 | Cable Clamps | APPROVED | No | 2025-08-25 | Abas, Mohammed Fekry | 2025-08-27 | 2025-08-28 |  |  | Cable Clamps (Defaa) - 2.19 | 0 | 7659 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 49400 | APPROVED |  |  | 2025-09-08 | -49400 | 11 | Hegazy, Ayman | -45897 | 11
105-128 | Defaa 115/13.8kv Substation | 7478 | Cable Supports | APPROVED | No | 2025-08-25 | Abas, Mohammed Fekry | 2025-08-27 | 2025-08-28 |  |  | MV Cable Support - 2.19 | 0 | 7474 | 0 | STANDARD | ISAM KABBANI &Partners | SAR | 37191 | APPROVED |  |  | 2025-09-08 | -37191 | 11 | Hegazy, Ayman | -45897 | 11
105-128 | Defaa 115/13.8kv Substation | 7684 | Terminal Clamps and Connectors | RETURNED | No | 2025-09-08 | Abdulqader, Ahmed Abdulhalim | 2025-10-06 | 2025-09-10 | 2025-10-06 |  | Not required new PR#7860 issued for all sites | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45910 | -45910
105-128 | Defaa 115/13.8kv Substation | 7856 | PDS System for Defaa | APPROVED | No | 2025-09-30 | Abas, Mohammed Fekry | 2025-10-12 | 2025-10-12 |  |  | PDS Sytem - 2.5 | 0 | 7760 | 0 | STANDARD | RASHID SAEED AHMED AL GHAMDI COMM INFO TRAD EST | SAR | 140000 | APPROVED |  |  | 2025-11-20 | -140000 | 39 | Abdulqader, Ahmed Abdulhalim | -45942 | 39
105-128 | Defaa 115/13.8kv Substation | 7912 | Office Furniture - Defaa | APPROVED | No | 2025-10-07 | Abas, Mohammed Fekry | 2025-11-06 | 2025-11-09 |  |  | Office furniture - Defaa - 2.33 | 0 | 7708 | 0 | STANDARD | ALISMAIL INDUSTRIAL CO.(S) | SAR | 17590 | IN PROCESS |  |  |  | -17590 | 84 | Abdulqader, Ahmed Abdulhalim | -45970 | -45970
105-128 | Defaa 115/13.8kv Substation | 7912 | Office Furniture - Defaa | APPROVED | No | 2025-10-07 | Abas, Mohammed Fekry | 2025-11-06 | 2025-11-09 |  |  | Office furniture - Defaa - 2.33 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -45970 | -45970
105-128 | Defaa 115/13.8kv Substation | 8075 | Motors for Gates - Defaa | RETURNED | No | 2025-10-28 | Abdelraouf, Islam ِAdel Hanafy | 2026-01-18 |  | 2026-01-18 |  | CASH BY SITE | 2 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelraouf, Islam ِAdel Hanafy | 0 | 0
105-128 | Defaa 115/13.8kv Substation | 8126 | Transformer Oil Sampling - Defaa | APPROVED | No | 2025-11-04 | Abas, Mohammed Fekry | 2025-11-06 | 2025-11-09 |  |  | Transformer Oil Sampling - 2.38 - Defaa | 0 | 7750 | 0 | STANDARD | Saudi Arabian Engineering Company | SAR | 37300 | APPROVED |  |  | 2025-11-18 | -37300 | 9 | Babic, Marian | -45970 | 9
105-128 | Defaa 115/13.8kv Substation | 8260 | Copper Tape 40x6 | APPROVED | No | 2025-11-18 | Abas, Mohammed Fekry | 2025-11-18 | 2025-11-19 |  |  | Budget line 2.21 - Grounding & Shielding system | 0 | 7663 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 11048 | APPROVED |  |  | 2025-11-24 | -11048 | 5 | Abdulqader, Ahmed Abdulhalim | -45980 | 5
105-128 | Defaa 115/13.8kv Substation | 8501 | Motion Sensor - Defaa | APPROVED | No | 2025-12-11 | Abas, Mohammed Fekry | 2025-12-15 | 2025-12-17 |  |  | Line Item 2.22 - Lighting System | 0 | 7338 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 72407 | APPROVED | 2025-12-23 | 2025-12-26 | 2026-01-21 | -72407 | 35 | Muaz, Alaa | 9 | 35
105-128 | Defaa 115/13.8kv Substation | 8533 | Lugs & Glands for Defaa | APPROVED | No | 2025-12-16 | Abas, Mohammed Fekry | 2025-12-21 | 2025-12-21 |  |  | Lugs & Glands - 2.13 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46012 | -46012
105-129 | Dana-2 115/13.8kV Substation | 1928 | Dana-2 115/13.8kV Substation-Engineering & Design- Dana-2 | APPROVED | No | 2023-12-11 | Abas, Mohammed Fekry | 2023-12-12 | 2023-12-12 |  |  |  | 581250 | 4903 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 570000 | APPROVED |  |  | 2024-01-08 | 11250 | 27 | Kumar, Mr. Ranjan | -45272 | 27
105-129 | Dana-2 115/13.8kV Substation | 2050 | Dana-2 115/13.8kV Substation-Dana-2 -13.8kV Switch Gear | APPROVED | No | 2023-12-28 | Abas, Mohammed Fekry | 2024-01-01 | 2024-01-01 |  |  |  | 8210000 | 4869 | 0 | STANDARD | ALFANAR CO | SAR | 8210000 | APPROVED |  |  | 2024-01-18 | 0 | 17 | Alhadi, Khalid | -45292 | 17
105-129 | Dana-2 115/13.8kV Substation | 2062 | Dana-2 115/13.8kV Substation-C&P,SAS for DANA-2 SS | APPROVED | No | 2023-12-31 | Abas, Mohammed Fekry | 2024-01-02 | 2024-01-02 |  |  |  | 8500000 | 4852 | 0 | STANDARD | ALFANAR CO | SAR | 8500000 | APPROVED |  |  | 2024-01-21 | 0 | 19 | Kumar, Mr. Ranjan | -45293 | 19
105-129 | Dana-2 115/13.8kV Substation | 2105 | Dana-2 115/13.8kV Substation-Temporary Project Sign Board | APPROVED | No | 2024-01-08 | Abas, Mohammed Fekry | 2024-01-09 | 2024-01-09 |  |  |  | 20000 | 4968 | 0 | STANDARD | Construction Expertise Est. | SAR | 20000 | APPROVED |  |  | 2024-01-18 | 0 | 9 | Alhadi, Khalid | -45300 | 9
105-129 | Dana-2 115/13.8kV Substation | 2236 | Dana-2 115/13.8kV Substation-Cyber Security | APPROVED | No | 2024-01-21 | Abas, Mohammed Fekry | 2024-01-22 | 2024-01-22 |  |  |  | 1000000 | 5064 | 0 | STANDARD | ALFANAR CO | SAR | 1000000 | APPROVED |  |  | 2024-02-18 | 0 | 27 | Babic, Marian | -45313 | 27
105-129 | Dana-2 115/13.8kV Substation | 2351 | Dana-2 115/13.8kV Substation-Demolish work | APPROVED | No | 2024-01-29 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 148658 | 5076 | 0 | STANDARD | ABDUL JABBAR AHMAD ALI SHARAHILI CONTRACTING EST. (AJASCO) | SAR | 148658 | APPROVED |  |  | 2024-02-14 | 0 | 10 | Alhadi, Khalid | -45326 | 10
105-129 | Dana-2 115/13.8kV Substation | 2354 | Dana-2 115/13.8kV Substation- UG Scanning | APPROVED | No | 2024-01-29 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-04 |  |  |  | 1900 | 5067 | 0 | STANDARD | Construction Expertise Est. | SAR | 1900 | APPROVED |  |  | 2024-02-15 | 0 | 11 | Alhadi, Khalid | -45326 | 11
105-129 | Dana-2 115/13.8kV Substation | 2401 | Dana-2 115/13.8kV Substation-Site Office facility | APPROVED | No | 2024-02-04 | Abas, Mohammed Fekry | 2024-02-05 | 2024-02-05 |  |  |  | 325197 | 5114 | 0 | STANDARD | Construction Expertise Est. | SAR | 192080 | APPROVED |  |  | 2024-03-27 | 133117 | 51 | Muhammad, Muhammad Atif | -45327 | 51
105-129 | Dana-2 115/13.8kV Substation | 2412 | Dana-2 115/13.8kV Substation-Gel type VRLA battery bank and 400A Battery Chargers | APPROVED | No | 2024-02-05 | Abas, Mohammed Fekry | 2024-02-07 | 2024-02-10 |  |  |  | 550000 | 5745 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 457000 | APPROVED |  |  | 2024-07-09 | 93000 | 150 | Muhammad, Muhammad Atif | -45332 | 150
105-129 | Dana-2 115/13.8kV Substation | 2497 | Dana-2 115/13.8kV Substation-Security Cabin | APPROVED | No | 2024-02-07 | Abas, Mohammed Fekry | 2024-02-09 | 2024-02-10 |  |  |  | 9000 | 5143 | 0 | STANDARD | Construction Expertise Est. | SAR | 9000 | APPROVED |  |  | 2024-03-14 | 0 | 33 | Alhadi, Khalid | -45332 | 33
105-129 | Dana-2 115/13.8kV Substation | 2522 | Dana-2 115/13.8kV Substation-Geotechnical Investigation | APPROVED | No | 2024-02-11 | Abas, Mohammed Fekry | 2024-02-11 | 2024-02-12 |  |  |  | 16000 | 5710 | 0 | STANDARD | International Agent Commercial Company(S) | SAR | 16000 | APPROVED |  |  | 2024-06-24 | 0 | 133 | Alhadi, Khalid | -45334 | 133
105-129 | Dana-2 115/13.8kV Substation | 2531 | Dana-2 115/13.8kV Substation-Super Structure Precast including Fire Walls | APPROVED | No | 2024-02-12 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-19 |  |  |  | 2421479 | 5391 | 0 | STANDARD | Factory of Ideal Precast Concrete System Company | SAR | 1921165 | APPROVED |  |  | 2024-04-30 | 500314 | 71 | Tananeh, Khalid Jamal | -45341 | 71
105-129 | Dana-2 115/13.8kV Substation | 2714 | Dana-2 115/13.8kV Substation-ACDB/DCDB & Lighting Panel | APPROVED | No | 2024-02-28 | Abas, Mohammed Fekry | 2024-02-28 | 2024-03-03 |  |  |  | 870000 | 5368 | 0 | STANDARD | ALFANAR CO | SAR | 870000 | APPROVED |  |  | 2024-04-30 | 0 | 58 | Mohammed, Faisal Ansari | -45354 | 58
105-129 | Dana-2 115/13.8kV Substation | 2758 | Dana-2 115/13.8kV Substation- OVERHEAD TRAVELING CRANE | APPROVED | No | 2024-03-04 | Abas, Mohammed Fekry | 2024-03-05 | 2024-03-07 |  |  |  | 130000 | 5468 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 126870 | APPROVED |  |  | 2024-05-16 | 3130 | 70 | Muhammad, Muhammad Atif | -45358 | 70
105-129 | Dana-2 115/13.8kV Substation | 2883 | Dana-2 115/13.8kV Substation-Topographic Survey | APPROVED | No | 2024-03-24 | Abas, Mohammed Fekry | 2024-03-25 | 2024-03-25 |  |  |  | 5125 | 5374 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 5125 | APPROVED |  |  | 2024-04-24 | 0 | 30 | Alhadi, Khalid | -45376 | 30
105-129 | Dana-2 115/13.8kV Substation | 2984 | Dana-2 115/13.8kV Substation-Excavation work | APPROVED | No | 2024-04-03 | Abas, Mohammed Fekry | 2024-04-04 | 2024-04-07 |  |  |  | 36864 | 5451 | 0 | STANDARD | RADI AHMED AL MANHAL CO. LTD | SAR | 36864 | APPROVED |  |  | 2024-05-14 | 0 | 37 | Alhadi, Khalid | -45389 | 37
105-129 | Dana-2 115/13.8kV Substation | 3173 | Dana-2 115/13.8kV Substation-Water Proofing | APPROVED | No | 2024-04-28 | Abas, Mohammed Fekry | 2024-04-29 | 2024-04-29 |  |  |  | 392625 | 5659 | 0 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 347826.5 | APPROVED |  |  | 2024-06-16 | 44798.5 | 48 | Tananeh, Khalid Jamal | -45411 | 48
105-129 | Dana-2 115/13.8kV Substation | 3175 | Dana-2 115/13.8kV Substation-Hollow Metal Doors Works | APPROVED | No | 2024-04-28 | Abas, Mohammed Fekry | 2024-04-29 | 2024-04-29 |  |  |  | 152037 | 6047 | 0 | STANDARD | AL MANASHY COMPANY | SAR | 102583 | APPROVED |  |  | 2024-10-21 | 49454 | 175 | Tananeh, Khalid Jamal | -45411 | 175
105-129 | Dana-2 115/13.8kV Substation | 3378 | Dana-2 115/13.8kV Substation-150sq.mm, Tinned copper conductor | APPROVED | No | 2024-05-12 | Abas, Mohammed Fekry | 2024-05-16 | 2024-05-17 |  |  |  | 38500 | 5360 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 38455.41 | APPROVED |  |  | 2024-05-21 | 44.59 | 4 | Muhammad, Muhammad Atif | -45429 | 4
105-129 | Dana-2 115/13.8kV Substation | 3456 | Dana-2 115/13.8kV Substation-Site Office facility Electronic Items | APPROVED | No | 2024-05-21 | Abas, Mohammed Fekry | 2024-05-21 | 2024-05-22 |  |  |  | 18200 | 5613 | 0 | STANDARD | Construction Expertise Est. | SAR | 18200 | APPROVED |  |  | 2024-06-05 | 0 | 14 | Muhammad, Muhammad Atif | -45434 | 14
105-129 | Dana-2 115/13.8kV Substation | 3479 | Dana-2 115/13.8kV Substation-Trial Mix test for Precast | APPROVED | No | 2024-05-23 | Abas, Mohammed Fekry | 2024-05-27 | 2024-05-28 |  |  |  | 7000 | 5805 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 4220 | APPROVED |  |  | 2024-10-13 | 2780 | 138 | Tananeh, Khalid Jamal | -45440 | 138
105-129 | Dana-2 115/13.8kV Substation | 3574 | Dana-2 115/13.8kV Substation-Grounding Material Accessories | APPROVED | No | 2024-06-03 | Issa, Amr Ali | 2024-06-05 | 2024-06-05 |  |  |  | 73475 | 5563 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 72850 | APPROVED |  |  | 2024-07-07 | 625 | 32 | Muhammad, Muhammad Atif | -45448 | 32
105-129 | Dana-2 115/13.8kV Substation | 3716 | Dana-2 115/13.8kV Substation-MV POWER CABLE ( 1C × 630mm2 & 1×3C×300mm2 ) | APPROVED | No | 2024-07-01 | Abas, Mohammed Fekry | 2024-07-02 | 2024-07-03 |  |  |  | 1069560 | 6028 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 956014.2 | APPROVED |  |  | 2024-10-14 | 113545.8 | 103 | Badhman, Saeed | -45476 | 103
105-129 | Dana-2 115/13.8kV Substation | 3784 | Dana-2 115/13.8kV Substation-Garbage Waste Container, 12 Cu. M (1-year) | APPROVED | No | 2024-07-07 | Abas, Mohammed Fekry | 2024-07-09 | 2024-07-09 |  |  |  | 28800 | 5891 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 19200 | APPROVED |  |  | 2024-08-20 | 9600 | 42 | Akhtar, Farhan | -45482 | 42
105-129 | Dana-2 115/13.8kV Substation | 3849 | Dana-2 115/13.8kV Substation-Control Cable | APPROVED | No | 2024-07-11 | Abas, Mohammed Fekry | 2024-07-16 | 2024-07-16 |  |  |  | 716000 | 5831 | 0 | STANDARD | ALFANAR CO | SAR | 531752.8 | APPROVED |  |  | 2024-08-25 | 184247.2 | 40 | Muhammad, Muhammad Atif | -45489 | 40
105-129 | Dana-2 115/13.8kV Substation | 3899 | Dana-2 115/13.8kV Substation-Testing & Commissioning | APPROVED | No | 2024-07-15 | Abas, Mohammed Fekry | 2024-07-18 | 2024-07-18 |  |  |  | 1854163 | 6452 | 0 | STANDARD | Al Fanar Technical Services | SAR | 1802080 | APPROVED |  |  | 2025-03-13 | 52083 | 238 | Alqadhi, Abdulrahman Abdulghani | -45491 | 238
105-129 | Dana-2 115/13.8kV Substation | 3908 | Dana-2 115/13.8kV Substation-RTV Coating | APPROVED | No | 2024-07-15 | Abas, Mohammed Fekry | 2024-07-18 | 2024-07-18 |  |  |  | 250000 | 6180 | 0 | STANDARD | SAUDI CONDUIT COATING CO. (S3C) | SAR | 35268 | APPROVED |  |  | 2024-10-13 | 214732 | 87 | Muaz, Alaa | -45491 | 87
105-129 | Dana-2 115/13.8kV Substation | 3913 | Dana-2 115/13.8kV Substation-MV TERMINATION KITS ( 1C × 630mm2 & 3C×300mm2 ) | APPROVED | No | 2024-07-16 | Abas, Mohammed Fekry | 2024-07-18 | 2024-07-18 |  |  |  | 98839 | 5991 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 95871.89 | APPROVED |  |  | 2024-09-19 | 2967.11 | 63 | Badhman, Saeed | -45491 | 63
105-129 | Dana-2 115/13.8kV Substation | 3959 | Dana-2 115/13.8kV Substation-Communication System | REJECTED | No | 2024-07-20 | Issa, Amr Ali | 2024-09-16 | 2024-07-22 |  | 2024-09-16 |  | 90000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45495 | -45495
105-129 | Dana-2 115/13.8kV Substation | 4025 | Dana-2 115/13.8kV Substation-LCLM | APPROVED | No | 2024-07-25 | Abas, Mohammed Fekry | 2024-07-29 | 2024-07-29 |  |  |  | 59075 | 5967 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 59075 | APPROVED |  |  | 2024-10-06 | 0 | 69 | Badhman, Saeed | -45502 | 69
105-129 | Dana-2 115/13.8kV Substation | 4040 | Dana-2 115/13.8kV Substation-Electrical Resistivity Soil test | APPROVED | No | 2024-07-28 | Abas, Mohammed Fekry | 2024-07-29 | 2024-07-29 |  |  |  | 7400 | 5955 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 6400 | APPROVED |  |  | 2024-10-10 | 1000 | 73 | Tananeh, Khalid Jamal | -45502 | 73
105-129 | Dana-2 115/13.8kV Substation | 4169 | Dana-2 115/13.8kV Substation-LV AC / DC Cables and Lighitng Wires | APPROVED | No | 2024-08-17 | Malek, Warren | 2024-08-25 | 2024-08-25 |  |  |  | 1611070 | 6086 | 0 | STANDARD | ALFANAR CO | SAR | 1110509.38 | APPROVED |  |  | 2024-10-06 | 500560.62 | 42 | Badhman, Saeed | -45529 | 42
105-129 | Dana-2 115/13.8kV Substation | 4183 | Dana-2 115/13.8kV Substation-Hazardou and Non Hazardous Waste | APPROVED | No | 2024-08-18 | Abas, Mohammed Fekry | 2024-08-19 | 2024-08-19 |  |  |  | 5000 | 6115 | 0 | STANDARD | Cebent for General Cont. Est. | SAR | 3650 | APPROVED |  |  | 2024-09-16 | 1350 | 28 | Akhtar, Farhan | -45523 | 28
105-129 | Dana-2 115/13.8kV Substation | 4183 | Dana-2 115/13.8kV Substation-Hazardou and Non Hazardous Waste | APPROVED | No | 2024-08-18 | Abas, Mohammed Fekry | 2024-08-19 | 2024-08-19 |  |  |  | 5000 | 6115 | 1 | STANDARD | Cebent for General Cont. Est. | SAR | 3650 | REQUIRES REAPPROVAL |  |  |  | 1350 | 531 | Akhtar, Farhan | -45523 | -45523
105-129 | Dana-2 115/13.8kV Substation | 4202 | Dana-2 115/13.8kV Substation-Supply and delivery of drinking Water 6 Cu. M Fiber Glass tank | APPROVED | No | 2024-08-19 | Malek, Warren | 2024-08-25 | 2024-08-25 |  |  |  | 3000 | 6129 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 3000 | APPROVED |  |  | 2024-09-10 | 0 | 16 | Akhtar, Farhan | -45529 | 16
105-129 | Dana-2 115/13.8kV Substation | 4209 | Dana-2 115/13.8kV Substation-Supply and delivery of Raw Water 10 Cu. M tanker | APPROVED | No | 2024-08-19 | Malek, Warren | 2024-08-25 | 2024-08-25 |  |  |  | 1800 | 6129 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 1800 | APPROVED |  |  | 2024-09-10 | 0 | 16 | Akhtar, Farhan | -45529 | 16
105-129 | Dana-2 115/13.8kV Substation | 4214 | Dana-2 115/13.8kV Substation-Sewage water removal services 10,000 liters | APPROVED | No | 2024-08-19 | Malek, Warren | 2024-08-25 | 2024-08-25 |  |  |  | 300 | 6129 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 300 | APPROVED |  |  | 2024-09-10 | 0 | 16 | Akhtar, Farhan | -45529 | 16
105-129 | Dana-2 115/13.8kV Substation | 4234 | Dana-2 115/13.8kV Substation-Grounding cables, 0.6/1 KV, Y/G | APPROVED | No | 2024-08-21 | Malek, Warren | 2024-08-25 | 2024-08-25 |  |  |  | 244150 | 6070 | 0 | STANDARD | ALFANAR CO | SAR | 226756.52 | APPROVED |  |  | 2024-09-18 | 17393.48 | 24 | Muhammad, Muhammad Atif | -45529 | 24
105-129 | Dana-2 115/13.8kV Substation | 4288 | Dana-2 115/13.8kV Substation-Cable Tray and its accessories | APPROVED | No | 2024-08-27 | Abas, Mohammed Fekry | 2024-08-29 | 2024-09-01 |  |  |  | 460016.15 | 6153 | 0 | STANDARD | Electrolink Co Ltd | SAR | 459950.65 | APPROVED |  |  | 2024-09-26 | 65.5 | 25 | Muhammad, Muhammad Atif | -45536 | 25
105-129 | Dana-2 115/13.8kV Substation | 4323 | Dana-2 115/13.8kV Substation-Station Service Transformer-750KVA | APPROVED | No | 2024-08-29 | Abas, Mohammed Fekry | 2024-10-02 | 2024-10-02 |  |  |  | 164000 | 5914 | 0 | STANDARD | ALFANAR CO | SAR | 164000 | APPROVED |  |  | 2024-10-14 | 0 | 12 | Muhammad, Muhammad Atif | -45567 | 12
105-129 | Dana-2 115/13.8kV Substation | 4355 | Dana-2 115/13.8kV Substation-General Fill (Back fill) materialwith Aggregate base coarse Class A or B | INCOMPLETE | No |  | Mughal, Aurang | 2024-09-03 |  |  |  |  | 56700 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-129 | Dana-2 115/13.8kV Substation | 4372 | Dana-2 115/13.8kV Substation-Fire Protection System | APPROVED | No | 2024-09-04 | Abas, Mohammed Fekry | 2024-09-05 | 2024-09-05 |  |  |  | 2125389 | 6009 | 0 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 2125389 | APPROVED |  |  | 2024-09-18 | 0 | 13 | Muhammad, Muhammad Atif | -45540 | 13
105-129 | Dana-2 115/13.8kV Substation | 4382 | Dana-2 115/13.8kV Substation-Civil Subcontractor Work + Metal work | APPROVED | No | 2024-09-05 | Abas, Mohammed Fekry | 2024-09-06 | 2024-09-08 |  |  |  | 8009000 | 5544 | 0 | STANDARD | Al Rawy Al Arabia | SAR | 7625000 | APPROVED |  |  | 2024-11-26 | 384000 | 79 | Tananeh, Khalid Jamal | -45543 | 79
105-129 | Dana-2 115/13.8kV Substation | 4591 | Dana-2 115/13.8kV Substation-Electrical Installation Sub Contractor | APPROVED | No | 2024-10-03 | Abas, Mohammed Fekry | 2024-10-06 | 2024-10-06 |  |  |  | 2992521 | 6398 | 0 | STANDARD | Future Vision Company | SAR | 2280000 | APPROVED |  |  | 2024-12-29 | 712521 | 84 | Muhammad, Muhammad Atif | -45571 | 84
105-129 | Dana-2 115/13.8kV Substation | 4636 | Dana-2 115/13.8kV Substation-Demolishing of existing precast wall and disposal to Baldia | APPROVED | No | 2024-10-09 | Abas, Mohammed Fekry | 2024-10-12 | 2024-10-12 |  |  |  | 114550 | 6430 | 0 | STANDARD | Construction Expertise Est. | SAR | 16000 | APPROVED |  |  | 2024-11-17 | 98550 | 36 | Alhadi, Khalid | -45577 | 36
105-129 | Dana-2 115/13.8kV Substation | 4673 | Dana-2 115/13.8kV Substation-Demolishing of existing precast wall | APPROVED | No | 2024-10-14 | Abas, Mohammed Fekry | 2024-10-15 | 2024-10-15 |  |  |  | 169000 | 6430 | 0 | STANDARD | Construction Expertise Est. | SAR | 169000 | APPROVED |  |  | 2024-11-17 | 0 | 33 | Alhadi, Khalid | -45580 | 33
105-129 | Dana-2 115/13.8kV Substation | 4678 | Dana-2 115/13.8kV Substation-HVAC SYSTEM | APPROVED | No | 2024-10-15 | Abas, Mohammed Fekry | 2024-10-15 | 2024-10-15 |  |  |  | 2220000 | 6207 | 0 | STANDARD | MAINTENANCE OF AIRCONDITION AND REFRIGERATION COMPANY LTD.(MARCO) | SAR | 2050000 | APPROVED |  |  | 2024-11-05 | 170000 | 21 | Muhammad, Muhammad Atif | -45580 | 21
105-129 | Dana-2 115/13.8kV Substation | 4949 | Dana-2 115/13.8kV Substation-Lighting Fixtures | APPROVED | No | 2024-11-14 | Abas, Mohammed Fekry | 2024-11-14 | 2024-11-17 |  |  |  | 71998 | 6477 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 71998 | APPROVED |  |  | 2024-11-20 | 0 | 3 | Muhammad, Muhammad Atif | -45613 | 3
105-129 | Dana-2 115/13.8kV Substation | 5091 | Dana-2 115/13.8kV Substation-Fiber Optic Cables & Accessories,Installation and Testing Services | APPROVED | No | 2024-11-30 | Abas, Mohammed Fekry | 2024-12-01 | 2024-12-03 |  |  |  | 220000 | 6621 | 0 | STANDARD | Arabian Power Trading Est. | SAR | 188000 | APPROVED |  |  | 2024-12-24 | 32000 | 21 | Muhammad, Muhammad Atif | -45629 | 21
105-129 | Dana-2 115/13.8kV Substation | 5094 | Dana-2 115/13.8kV Substation-HCIS-3 Consultancy for Security System | APPROVED | No | 2024-11-30 | Abas, Mohammed Fekry | 2025-01-08 | 2025-01-08 |  |  |  | 33500 | 6516 | 0 | STANDARD | Khaled Drewesh Office for Consulting Security (KDOCS) | SAR | 33500 | APPROVED |  |  | 2025-01-13 | 0 | 5 | Muhammad, Muhammad Atif | -45665 | 5
105-129 | Dana-2 115/13.8kV Substation | 5135 | Dana-2 115/13.8kV Substation-Al. Connector for GIB Bushing-2.13 | APPROVED | No | 2024-12-04 | Abas, Mohammed Fekry | 2024-12-04 | 2024-12-08 |  |  |  | 5675 | 6423 | 0 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 4617.79 | APPROVED |  |  | 2025-01-02 | 1057.21 | 25 | Mohammed, Faisal Ansari | -45634 | 25
105-129 | Dana-2 115/13.8kV Substation | 5144 | Dana-2 115/13.8kV Substation-Supply and delivery of drinking Water 6 Cu. M Fiber Glass tank | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-15 | 2024-12-15 |  |  |  | 5250 | 6687 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 4500 | APPROVED |  |  | 2025-01-02 | 750 | 18 | Akhtar, Farhan | -45641 | 18
105-129 | Dana-2 115/13.8kV Substation | 5149 | Dana-2 115/13.8kV Substation-Supply and delivery of Raw Water 10 Cu. M tanker | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-15 | 2024-12-15 |  |  |  | 2100 | 6687 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 1800 | APPROVED |  |  | 2025-01-02 | 300 | 18 | Akhtar, Farhan | -45641 | 18
105-129 | Dana-2 115/13.8kV Substation | 5154 | Dana-2 115/13.8kV Substation-Sewage water removal services 10,000 liters | APPROVED | No | 2024-12-05 | Abas, Mohammed Fekry | 2024-12-11 | 2024-12-12 |  |  |  | 300 | 6687 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 300 | APPROVED |  |  | 2025-01-02 | 0 | 21 | Akhtar, Farhan | -45638 | 21
105-129 | Dana-2 115/13.8kV Substation | 5280 | Dana-2 115/13.8kV Substation-150mm2 Tinned Copper Conductor Extra | APPROVED | No | 2024-12-28 | Abas, Mohammed Fekry | 2024-12-31 | 2025-01-01 |  |  |  | 131100 | 6758 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 121307.52 | APPROVED |  |  | 2025-02-27 | 9792.48 | 57 | Alhadi, Khalid | -45658 | 57
105-129 | Dana-2 115/13.8kV Substation | 5357 | Dana-2 115/13.8kV Substation-Supply of Conduits and Fittings | APPROVED | No | 2025-01-05 | Abas, Mohammed Fekry | 2025-01-08 | 2025-01-12 |  |  |  | 337272.4 | 6715 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 337271.55 | APPROVED |  |  | 2025-01-23 | 0.85 | 11 | Muaz, Alaa | -45669 | 11
105-129 | Dana-2 115/13.8kV Substation | 5481 | Dana-2 115/13.8kV Substation-CT Junction Box with 9 Single Phase CTPU - including all accessories | APPROVED | No | 2025-01-20 | Abas, Mohammed Fekry | 2025-01-26 | 2025-01-26 |  |  |  | 68000 | 6292 | 0 | STANDARD | Energy Tracks For Contracting | SAR | 68000 | APPROVED |  |  | 2025-03-04 | 0 | 37 | Kumar, Mr. Ranjan | -45683 | 37
105-129 | Dana-2 115/13.8kV Substation | 5542 | Dana-2 115/13.8kV Substation-Remote end modification for TFR , DSM | APPROVED | No | 2025-01-23 | Abas, Mohammed Fekry | 2025-01-26 | 2025-01-26 |  |  |  | 100000 | 7453 | 0 | STANDARD | TRINERGY TECHNOLOGIES SA | SAR | 30615 | APPROVED |  |  | 2025-07-06 | 69385 | 161 | Babic, Marian | -45683 | 161
105-129 | Dana-2 115/13.8kV Substation | 5558 | Dana-2 115/13.8kV Substation-Security System Class-3 | APPROVED | No | 2025-01-23 | Abas, Mohammed Fekry | 2025-02-25 | 2025-02-25 |  |  | line item 2.7-Security System Class-3 | 779005 | 6631 | 0 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 779005 | APPROVED |  |  | 2025-03-05 | 0 | 8 | Abdulqader, Ahmed Abdulhalim | -45713 | 8
105-129 | Dana-2 115/13.8kV Substation | 5558 | Dana-2 115/13.8kV Substation-Security System Class-3 | APPROVED | No | 2025-01-23 | Abas, Mohammed Fekry | 2025-02-25 | 2025-02-25 |  |  | line item 2.7-Security System Class-3 | 779005 | 6631 | 1 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 779005 | REQUIRES REAPPROVAL |  |  |  | 0 | 341 | Abdulqader, Ahmed Abdulhalim | -45713 | -45713
105-129 | Dana-2 115/13.8kV Substation | 6105 | Dana-2 115/13.8kV Substation-Drawing Printing & Scanning | APPROVED | No | 2025-03-03 | Abas, Mohammed Fekry | 2025-03-05 | 2025-03-05 |  |  | Line Item: 2.33 - Drawing Printing & Scanning | 35000 | 7067 | 0 | STANDARD | Print Magaies Al abdaa Printing | SAR | 35000 | APPROVED |  |  | 2025-04-07 | 0 | 33 | Abuhammad, Samir | -45721 | 33
105-129 | Dana-2 115/13.8kV Substation | 6133 | Dana-2 115/13.8kV Substation-Supply of Total station and automatic level | APPROVED | No | 2025-03-06 | Abas, Mohammed Fekry | 2025-03-10 | 2025-03-12 |  |  | line item 2.33-Supply of Total station and automatic level | 36000 | 7180 | 0 | STANDARD | Saudi International Trading & Marketing Ltd. (SITML) | SAR | 32500 | APPROVED |  |  | 2025-04-27 | 3500 | 46 | Abuhammad, Samir | -45728 | 46
105-129 | Dana-2 115/13.8kV Substation | 6171 | Dana-2 115/13.8kV Substation-Excavation as per the SEC Standard. Baladiha Disposal | RETURNED | No | 2025-03-12 | Tananeh, Khalid Jamal | 2025-09-22 | 2025-03-17 | 2025-09-22 |  | "As no response was received by the deadline of 21-09-2025 to the clarification request sent on Tue 16/09/2025 at 10:29 AM, the PR is being cancelled accordingly." | 14805 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45733 | -45733
105-129 | Dana-2 115/13.8kV Substation | 6233 | Dana-2 115/13.8kV Substation-Technicians for Testing & Commissioning | APPROVED | No | 2025-03-23 | Abas, Mohammed Fekry | 2025-03-23 | 2025-03-24 |  |  | line item 2.30-Technicians for Testing & Commissioning | 191000 | 7480 | 0 | STANDARD | City Crowns Energy | SAR | 190976 | APPROVED |  |  | 2025-07-18 | 24 | 116 | Babic, Marian | -45740 | 116
105-129 | Dana-2 115/13.8kV Substation | 6233 | Dana-2 115/13.8kV Substation-Technicians for Testing & Commissioning | APPROVED | No | 2025-03-23 | Abas, Mohammed Fekry | 2025-03-23 | 2025-03-24 |  |  | line item 2.30-Technicians for Testing & Commissioning | 191000 | 7562 | 0 | STANDARD | Jasem M.AlJasem Contracting Est. | SAR | 191000 | APPROVED |  |  | 2025-08-05 | 0 | 134 | Babic, Marian | -45740 | 134
105-129 | Dana-2 115/13.8kV Substation | 6311 | Dana-2 115/13.8kV Substation-Tower AC-5T0N | APPROVED | No | 2025-04-09 | Abas, Mohammed Fekry | 2025-04-10 | 2025-04-13 |  |  | line item 2.33-Tower AC-5T0N | 71760 | 7146 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 61600 | APPROVED |  |  | 2025-04-24 | 10160 | 11 | Abuhammad, Samir | -45760 | 11
105-129 | Dana-2 115/13.8kV Substation | 6313 | Dana-2 115/13.8kV Substation-diesel supply | APPROVED | No | 2025-04-09 | Abas, Mohammed Fekry | 2025-04-09 | 2025-04-13 |  |  | line item 2.33-diesel supply | 33400 | 7155 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 29739 | APPROVED |  |  | 2025-05-19 | 3661 | 36 | Akhtar, Farhan | -45760 | 36
105-129 | Dana-2 115/13.8kV Substation | 6331 | Dana-2 115/13.8kV Substation-Excavation work | APPROVED | No | 2025-04-14 | Abas, Mohammed Fekry | 2025-04-14 | 2025-04-15 |  |  | line item 2.20-Excavation work | 14805 | 7470 | 0 | STANDARD | RADI AHMED AL MANHAL CO. LTD | SAR | 14805 | APPROVED | 2026-01-14 | 2026-01-19 | 2026-01-21 | 0 | 281 | Alhadi, Khalid | 279 | 281
105-129 | Dana-2 115/13.8kV Substation | 6364 | Dana-2 115/13.8kV Substation-7X2.5 mm2 CU/XLPE/CTS/PVC | APPROVED | No | 2025-04-17 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-21 |  |  | line item 2.13-7X2.5 mm2 CU/XLPE/CTS/PVC | 52600 | 6788 | 0 | STANDARD | ALFANAR CO | SAR | 52600 | APPROVED |  |  | 2025-05-01 | 0 | 10 | Muaz, Alaa | -45768 | 10
|  |  | 0.6/1 KV – Blue Color | [8 empty] | 0.6/1 KV – Blue Color | [14 empty] | 0 | 0
105-129 | Dana-2 115/13.8kV Substation | 6398 | Dana-2 115/13.8kV Substation-Foam Concrete and Excavation work | RETURNED | No | 2025-04-20 | Tananeh, Khalid Jamal | 2025-09-22 | 2025-04-21 | 2025-09-22 |  | "As no response was received by the deadline of 21-09-2025 to the clarification request sent on Tue 16/09/2025 at 10:29 AM, the PR is being cancelled accordingly." | 70371 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45768 | -45768
105-129 | Dana-2 115/13.8kV Substation | 6415 | Dana-2 115/13.8kV Substation-Sealant work for External Wall | REJECTED | No | 2025-04-22 | Ibrahim, Mahmoud Hassan Ali | 2025-06-24 | 2025-04-22 |  | 2025-06-25 |  | 55000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45769 | -45769
105-129 | Dana-2 115/13.8kV Substation | 6434 | Dana-2 115/13.8kV Substation-Supply & Delivery of Raw Water,Drinking Water & Sweage Removal | APPROVED | No | 2025-04-23 | Abas, Mohammed Fekry | 2025-04-23 | 2025-04-24 |  |  | line item 2.33-Supply & Delivery of Raw Water,Drinking Water & Sweage Removal | 6600 | 6687 | 1 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 6600 | APPROVED |  |  | 2025-05-11 | 0 | 17 | Akhtar, Farhan | -45771 | 17
105-129 | Dana-2 115/13.8kV Substation | 6512 | Dana-2 115/13.8kV Substation-4P x 1.5 sqmm Cable | APPROVED | No | 2025-05-05 | Abas, Mohammed Fekry | 2025-05-06 | 2025-05-06 |  |  | Line Item: 2.13 - 4P x 1.5 sqmm Cable | 9000 | 7321 | 0 | STANDARD | Middle East Specialized Cables Mesc | SAR | 7500 | APPROVED |  |  | 2025-05-27 | 1500 | 21 | Abuhammad, Samir | -45783 | 21
105-129 | Dana-2 115/13.8kV Substation | 6648 | Dana-2 115/13.8kV Substation-T&C Technicians (Rental) | APPROVED | No | 2025-05-19 | Abas, Mohammed Fekry | 2025-05-25 | 2025-05-26 |  |  | Line Item - 2.31: T&C Technicians (Rental) | 80000 | 7480 | 0 | STANDARD | City Crowns Energy | SAR | 80000 | APPROVED |  |  | 2025-07-18 | 0 | 53 | Babic, Marian | -45803 | 53
105-129 | Dana-2 115/13.8kV Substation | 6648 | Dana-2 115/13.8kV Substation-T&C Technicians (Rental) | APPROVED | No | 2025-05-19 | Abas, Mohammed Fekry | 2025-05-25 | 2025-05-26 |  |  | Line Item - 2.31: T&C Technicians (Rental) | 80000 | 7562 | 0 | STANDARD | Jasem M.AlJasem Contracting Est. | SAR | 80000 | APPROVED |  |  | 2025-08-05 | 0 | 71 | Babic, Marian | -45803 | 71
105-129 | Dana-2 115/13.8kV Substation | 6691 | Dana-2 115/13.8kV Substation-Grounding Accessories | APPROVED | No | 2025-05-22 | Abas, Mohammed Fekry | 2025-06-01 | 2025-06-02 |  |  | Line Item 2.21 - Grounding Accessories | 69784.7 | 7100 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 69784.7 | APPROVED |  |  | 2025-06-22 | 0 | 20 | Abdulqader, Ahmed Abdulhalim | -45810 | 20
105-129 | Dana-2 115/13.8kV Substation | 6742 | Dana-2 115/13.8kV Substation-125V DC DB for Communication System | APPROVED | No | 2025-05-28 | Abas, Mohammed Fekry | 2025-07-06 | 2025-07-07 |  |  | Line Item: 2.12 - 125V DC DB for Communication System | 35000 | 7523 | 0 | STANDARD | HAWA ELECTRIC PANEL BOARD FAC | SAR | 29700 | APPROVED |  |  | 2025-07-27 | 5300 | 20 | Abuhammad, Samir | -45845 | 20
105-129 | Dana-2 115/13.8kV Substation | 6784 | Dana-2 115/13.8kV Substation-Communication System | APPROVED | No | 2025-06-12 | Abas, Mohammed Fekry | 2025-06-15 | 2025-06-15 |  |  | line item 2.4-Communication System | 1881999 | 5856 | 0 | STANDARD | ALFANAR CO | SAR | 1881998.09 | APPROVED |  |  | 2025-06-24 | 0.91 | 9 | Kumar, Mr. Ranjan | -45823 | 9
105-129 | Dana-2 115/13.8kV Substation | 6913 | Dana-2 115/13.8kV Substation-Wiring devices( Switches, Socket and Push Buttons) | APPROVED | No | 2025-06-26 | Abas, Mohammed Fekry | 2025-06-30 | 2025-07-01 |  |  | line item 2.23-Wiring devices( Switches, Socket and Push Buttons) | 99975 | 7168 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 99975 | APPROVED |  |  | 2025-07-14 | 0 | 13 | Muaz, Alaa | -45839 | 13
105-129 | Dana-2 115/13.8kV Substation | 7016 | Dana-2 115/13.8kV Substation-HV MV Cable Supports | APPROVED | No | 2025-07-08 | Abas, Mohammed Fekry | 2025-07-09 | 2025-07-09 |  |  | LINE ITEM 2.19-HV MV Cable Supports | 121336.2 | 7299 | 0 | STANDARD | Power Solution Industries | SAR | 121336.2 | APPROVED |  |  | 2025-09-14 | 0 | 67 | Hegazy, Ayman | -45847 | 67
105-129 | Dana-2 115/13.8kV Substation | 7049 | Dana-2 115/13.8kV Substation-MV Cable Clamps | APPROVED | No | 2025-07-09 | Abas, Mohammed Fekry | 2025-07-10 | 2025-07-10 |  |  | line item 2.13-MV Cable Clamps | 56525 | 7253 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 56525 | APPROVED |  |  | 2025-08-10 | 0 | 31 | Hegazy, Ayman | -45848 | 31
105-129 | Dana-2 115/13.8kV Substation | 7066 | Dana-2 115/13.8kV Substation-Supply of Diesal Genrator | APPROVED | No | 2025-07-12 | Abas, Mohammed Fekry | 2025-07-14 | 2025-07-14 |  |  | line item 2.33-Diesel for Generator | 5215 | 7155 | 1 | STANDARD | Talaea Alahlam Trading Company | SAR | 5204.32 | APPROVED |  |  | 2025-07-22 | 10.68 | 8 | Akhtar, Farhan | -45852 | 8
105-129 | Dana-2 115/13.8kV Substation | 7081 | Dana-2 115/13.8kV Substation-Supply with installation of AC units Stand Type 5 Ton | APPROVED | No | 2025-07-13 | Abas, Mohammed Fekry | 2025-07-14 | 2025-07-14 |  |  | line item 2.33-Supply with installation of AC units Stand Type 5 Ton | 30000 | 7531 | 0 | STANDARD | Versatile Advanced Limited Company. | SAR | 27000 | APPROVED |  |  | 2025-07-25 | 3000 | 11 | Akhtar, Farhan | -45852 | 11
105-129 | Dana-2 115/13.8kV Substation | 7088 | Dana-2 115/13.8kV Substation-PDS System | APPROVED | No | 2025-07-14 | Abas, Mohammed Fekry | 2025-07-22 | 2025-07-22 |  |  | line item 2.5-PDS System | 200000 | 7758 | 0 | STANDARD | RASHID SAEED AHMED AL GHAMDI COMM INFO TRAD EST | SAR | 140000 | APPROVED |  |  | 2025-11-04 | 60000 | 105 | Abdulqader, Ahmed Abdulhalim | -45860 | 105
105-129 | Dana-2 115/13.8kV Substation | 7115 | Dana-2 115/13.8kV Substation-Supply of Raw Water, Drinking Water and Sweage Removal-2.33 | APPROVED | No | 2025-07-16 | Abas, Mohammed Fekry | 2025-07-17 | 2025-07-20 |  |  | line item 2.33-Supply of Raw Water, Drinking Water and Sweage Removal | 6600 | 6687 | 2 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 6600 | APPROVED |  |  | 2025-07-24 | 0 | 4 | Akhtar, Farhan | -45858 | 4
105-129 | Dana-2 115/13.8kV Substation | 7241 | Dana-2 115/13.8kV Substation-Diesel Generator | APPROVED | No | 2025-07-29 | Abas, Mohammed Fekry | 2025-07-30 | 2025-08-04 |  |  | line item 2.33-Diesel Generator | 50660 | 7155 | 2 | STANDARD | Talaea Alahlam Trading Company | SAR | 50556.3 | APPROVED |  |  | 2025-08-10 | 103.7 | 6 | Akhtar, Farhan | -45873 | 6
105-129 | Dana-2 115/13.8kV Substation | 7248 | Dana-2 115/13.8kV Substation-1Cx500 Sq. mm 0.6/1 KV, Cu / | RETURNED | No | 2025-07-30 | Mohammed, Mohammed Adel Fahmy | 2026-01-15 | 2025-08-04 | 2026-01-15 |  | Not Have POCR Until Now and PR incorrect qty. | 221400 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Mohammed Adel Fahmy | -45873 | -45873
|  |  | XLPE / PVC | [23 empty] | 0 | 0
105-129 | Dana-2 115/13.8kV Substation | 7249 | Dana-2 115/13.8kV Substation-12X2.5 mm2 CU/XLPE/CTS/PVC | RETURNED | No | 2025-07-30 | Mohammed, Mohammed Adel Fahmy | 2026-01-15 | 2025-08-04 | 2026-01-15 |  | Not Have POCR Until Now and PR incorrect qty. | 34000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Mohammed Adel Fahmy | -45873 | -45873
|  |  | 0.6/1 KV | [23 empty] | 0 | 0
105-129 | Dana-2 115/13.8kV Substation | 7281 | Dana-2 115/13.8kV Substation-Water Proofing work | APPROVED | No | 2025-08-04 | Abas, Mohammed Fekry | 2025-08-05 | 2025-08-06 |  |  | LINE ITEM 2.20-Water Proofing work | 27303 | 5659 | 1 | STANDARD | Arabian Buliding Support and Rehabitation Co. | SAR | 27302.47 | APPROVED |  |  | 2025-09-17 | 0.53 | 42 | Tananeh, Khalid Jamal | -45875 | 42
105-129 | Dana-2 115/13.8kV Substation | 7506 | Steel Parapet Works | APPROVED | No | 2025-08-26 | Abas, Mohammed Fekry | 2025-08-27 | 2025-08-28 |  |  | Line item 2.20-Steel Parapet Works | 0 | 6822 | 0 | STANDARD | RAFCO Factory Company For Metal Industries | SAR | 36520 | APPROVED |  |  | 2025-09-07 | -36520 | 10 | Hegazy, Ayman | -45897 | 10
105-129 | Dana-2 115/13.8kV Substation | 7529 | Porta Cabin | REJECTED | No | 2025-08-27 | Sherif, Marwa | 2025-09-14 | 2025-08-27 |  | 2025-09-15 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45896 | -45896
105-129 | Dana-2 115/13.8kV Substation | 7545 | Rental Saftey Officer | RETURNED | No | 2025-08-27 | Alhadi, Khalid | 2025-10-05 | 2025-09-08 | 2025-10-05 |  | No feedback from project manager and approved CV's from Safety manager | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45908 | -45908
105-129 | Dana-2 115/13.8kV Substation | 7548 | Lugs and Glands | RETURNED | No | 2025-08-27 | Abdulqader, Ahmed Abdulhalim | 2025-10-02 | 2025-09-03 | 2025-10-02 |  | Not required PO approved in sysytem | 0 | 7581 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 17862.24 | APPROVED |  |  | 2025-09-15 | -17862.24 |  | Abdulqader, Ahmed Abdulhalim | -45903 | 12
105-129 | Dana-2 115/13.8kV Substation | 7548 | Lugs and Glands | RETURNED | No | 2025-08-27 | Abdulqader, Ahmed Abdulhalim | 2025-10-02 | 2025-09-03 | 2025-10-02 |  | Not required PO approved in sysytem | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45903 | -45903
105-129 | Dana-2 115/13.8kV Substation | 7555 | diesel for Genrator | APPROVED | No | 2025-08-28 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-03 |  |  | line item 2.33-diesel for genrator | 0 | 7720 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 29800 | APPROVED |  |  | 2025-10-02 | -29800 | 29 | Abdulqader, Ahmed Abdulhalim | -45903 | 29
105-129 | Dana-2 115/13.8kV Substation | 7604 | Excavation work | RETURNED | No | 2025-09-01 | Tananeh, Khalid Jamal | 2025-09-22 | 2025-09-03 | 2025-09-22 |  | "As no response was received by the deadline of 21-09-2025 to the clarification request sent on Tue 16/09/2025 at 10:29 AM, the PR is being cancelled accordingly." | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45903 | -45903
105-129 | Dana-2 115/13.8kV Substation | 7621 | Supply of Raw Water, Drinking Water and Sweage Removal | APPROVED | No | 2025-09-02 | Abas, Mohammed Fekry | 2025-09-07 | 2025-09-08 |  |  | line item 2.33-Supply of Raw Water, Drinking Water and Sewage Removal | 0 | 6687 | 3 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 13500 | APPROVED |  |  | 2025-10-08 | -13500 | 30 | Akhtar, Farhan | -45908 | 30
105-129 | Dana-2 115/13.8kV Substation | 7651 | Lugs and glands | APPROVED | No | 2025-09-04 | Abas, Mohammed Fekry | 2025-09-08 | 2025-09-08 |  |  | LINE ITEM 2.13-Lugs and glands | 0 | 7581 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 6483.36 | APPROVED |  |  | 2025-09-15 | -6483.36 | 7 | Abdulqader, Ahmed Abdulhalim | -45908 | 7
105-129 | Dana-2 115/13.8kV Substation | 7693 | Security Cabin, Porta Cabin and System Desktop | RETURNED | No | 2025-09-09 | Abdulqader, Ahmed Abdulhalim | 2025-10-12 | 2025-09-10 | 2025-10-12 |  | not required PO already uploaded in system | 0 | 7681 | 0 | STANDARD | Al Arab Modern Contracting Est | SAR | 13500 | APPROVED |  |  | 2025-10-07 | -13500 |  | Abdulqader, Ahmed Abdulhalim | -45910 | 27
105-129 | Dana-2 115/13.8kV Substation | 7693 | Security Cabin, Porta Cabin and System Desktop | RETURNED | No | 2025-09-09 | Abdulqader, Ahmed Abdulhalim | 2025-10-12 | 2025-09-10 | 2025-10-12 |  | not required PO already uploaded in system | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45910 | -45910
105-129 | Dana-2 115/13.8kV Substation | 7749 | 150KVA Diesel Genrator | RETURNED | No | 2025-09-15 | Badhman, Saeed | 2025-10-27 | 2025-09-16 | 2025-10-27 |  | PR isnt compleate | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45916 | -45916
105-129 | Dana-2 115/13.8kV Substation | 7779 | Substation Office Furniture | APPROVED | No | 2025-09-17 | Abas, Mohammed Fekry | 2025-09-18 | 2025-09-19 |  |  | Line Item 2.33 - Substation Office Furniture. | 0 | 7718 | 0 | STANDARD | ALISMAIL INDUSTRIAL CO.(S) | SAR | 17590 | APPROVED |  |  | 2025-10-07 | -17590 | 18 | Abdulqader, Ahmed Abdulhalim | -45919 | 18
105-129 | Dana-2 115/13.8kV Substation | 7812 | Asphalt Work,Metal work and Boundary fence | APPROVED | No | 2025-09-22 | Abas, Mohammed Fekry | 2026-01-25 | 2026-01-26 |  |  | line item 2.20-for Asphalt work, Metal work, and Boundary fence work | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -46048 | -46048
105-129 | Dana-2 115/13.8kV Substation | 7845 | Transportation Charges | REJECTED | No | 2025-09-28 | Ibrahim, Mahmoud Hassan Ali | 2025-11-18 | 2025-09-29 |  | 2025-11-18 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45929 | -45929
105-129 | Dana-2 115/13.8kV Substation | 7936 | Lighting Control System/Motion Sensor | APPROVED | No | 2025-10-09 | Abas, Mohammed Fekry | 2025-10-15 | 2025-10-15 |  |  | line item 2.22-Lighting Control System/Motion Sensor | 0 | 7337 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 68054 | APPROVED |  |  | 2025-10-26 | -68054 | 11 | Muaz, Alaa | -45945 | 11
105-129 | Dana-2 115/13.8kV Substation | 8040 | Swing Gate Motor | REJECTED | No | 2025-10-23 | Mughal, Aurang | 2025-11-17 | 2025-10-26 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -45956 | -45956
105-129 | Dana-2 115/13.8kV Substation | 8067 | 40MM*6MM Bare Copper Tapes | APPROVED | No | 2025-10-27 | Abas, Mohammed Fekry | 2025-10-29 | 2025-10-30 |  |  | line item 2.21-40MM*6MM Bare Copper Tapes-(DANA-2 SS) | 0 | 7664 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 21496 | APPROVED |  |  | 2025-11-19 | -21496 | 20 | Hegazy, Ayman | -45960 | 20
105-129 | Dana-2 115/13.8kV Substation | 8069 | 150kVA Diesel Generator | APPROVED | No | 2025-10-27 | Abas, Mohammed Fekry | 2025-10-29 | 2025-10-30 |  |  | line item 2.33-150kVA Diesel Generator -1nos. ( for 6 months) -DANA-2 | 0 | 7882 | 0 | STANDARD | Energia Model General Contracting Company | SAR | 44400 | APPROVED |  |  | 2025-12-28 | -44400 | 59 | Badhman, Saeed | -45960 | 59
105-129 | Dana-2 115/13.8kV Substation | 8219 | Hazardou and Non Hazardous Waste | APPROVED | No | 2025-11-13 | Abas, Mohammed Fekry | 2026-01-27 | 2026-01-28 |  |  | line item 2.33-Hazardou and Non Hazardous Waste | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46050 | -46050
105-129 | Dana-2 115/13.8kV Substation | 8239 | Swing Gate Motor | APPROVED | No | 2025-11-17 | Abas, Mohammed Fekry | 2025-11-18 | 2025-11-19 |  |  | line item 2.20-Swing Gate Motor | 0 | 7929 | 0 | STANDARD | ALMOSALLAMY INDUSTRIAL COMPANY | SAR | 9330 | APPROVED |  |  | 2025-12-15 | -9330 | 26 | Abdelraouf, Islam ِAdel Hanafy | -45980 | 26
105-129 | Dana-2 115/13.8kV Substation | 8268 | Copper Tape 40x6 | REJECTED | No | 2025-11-18 | Mughal, Aurang | 2025-11-18 |  |  | 2025-11-18 | Budget line 2.21 - Grounding & Shielding system | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | 0 | 0
105-129 | Dana-2 115/13.8kV Substation | 8513 | LCLM | APPROVED | No | 2025-12-18 | Abas, Mohammed Fekry | 2025-12-24 | 2025-12-26 |  |  | Line Item 2.18-LCLM-DANA-2 SS-POCR Alreday approved | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -46017 | -46017
105-129 | Dana-2 115/13.8kV Substation | 8607 | Supply of Fire Stop Materials - North Khobar | REJECTED | No | 2025-12-29 | Ibrahim, Mahmoud Hassan Ali | 2026-01-25 | 2025-12-30 |  | 2026-01-25 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46021 | -46021
105-129 | Dana-2 115/13.8kV Substation | 8642 | Metal Doors (Change Order) - Dana-2 | APPROVED | No | 2026-01-05 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-13 |  |  | Budget line 2.20 - Civil Works | 0 | 6047 | 1 | STANDARD | AL MANASHY COMPANY | SAR | 10595.2 | APPROVED | 2026-01-21 | 2026-01-25 | 2026-01-28 | -10595.2 | 15 | Tananeh, Khalid Jamal | 12 | 15
105-129 | Dana-2 115/13.8kV Substation | 8776 | Disposal of Hazardous & Non-Hazardous Waste | IN PROCESS | No | 2026-01-25 | Mughal, Aurang | 2026-01-29 | 2026-01-27 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46049 | -46049
105-129 | Dana-2 115/13.8kV Substation | 8777 | Supply of Fire Stop Material | IN PROCESS | No | 2026-01-25 | Abas, Mohammed Fekry | 2026-01-29 | 2026-01-29 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46051 | -46051
105-129 | Dana-2 115/13.8kV Substation | 8778 | Supply of Fire Stop Material | IN PROCESS | No | 2026-01-25 | Abas, Mohammed Fekry | 2026-01-29 | 2026-01-29 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46051 | -46051
105-129 | Dana-2 115/13.8kV Substation | 8781 | Substation Grounding Material | IN PROCESS | No | 2026-01-25 | Abas, Mohammed Fekry | 2026-01-29 | 2026-01-29 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46051 | -46051
105-129 | Dana-2 115/13.8kV Substation | 8790 | Rental Manpower | APPROVED | No | 2026-01-25 | Abas, Mohammed Fekry | 2026-01-29 | 2026-02-01 |  |  | Line Item - 2.31 - Rental Manpower (Testing Technicians) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46054 | -46054
105-129 | Dana-2 115/13.8kV Substation | 8826 | 150mm.sq Tinned Copper Conductor | IN PROCESS | No | 2026-01-28 | Abas, Mohammed Fekry | 2026-01-29 | 2026-01-29 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46051 | -46051
105-130 | L'Azure Hotel CCTV | 4632 | L'Azure Hotel CCTV-Supply with testing commissioning of Dahua solution | APPROVED | No | 2024-10-08 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-10 |  |  |  | 247543 | 6359 | 0 | STANDARD | Zamil Group Trade & Service Co | SAR | 247543 | APPROVED |  |  | 2024-10-27 | 0 | 17 | Abuhammad, Samir | -45575 | 17
105-130 | L'Azure Hotel CCTV | 4642 | L'Azure Hotel CCTV-Supply of Huawei solution | APPROVED | No | 2024-10-09 | Abas, Mohammed Fekry | 2024-10-10 | 2024-10-10 |  |  |  | 175125.29 | 6358 | 0 | STANDARD | REDINGTON SAUDI ARABIA DISTRIBUTION CO. | SAR | 171026.64 | APPROVED |  |  | 2024-10-31 | 4098.65 | 21 | Abuhammad, Samir | -45575 | 21
105-130 | L'Azure Hotel CCTV | 4690 | L'Azure Hotel CCTV-Supply, installtion and civil work for passive material | APPROVED | No | 2024-10-15 | Abas, Mohammed Fekry | 2024-10-16 | 2024-10-17 |  |  |  | 307830 | 6362 | 0 | STANDARD | High Point Technology Co, | SAR | 299200 | APPROVED |  |  | 2024-11-04 | 8630 | 18 | Abuhammad, Samir | -45582 | 18
105-130 | L'Azure Hotel CCTV | 5349 | L'Azure Hotel CCTV-Supply and installtion of laptop Core i7 and 65" Monitor | APPROVED | No | 2025-01-05 | Abas, Mohammed Fekry | 2025-01-06 | 2025-01-06 |  |  |  | 3635.87 | 6738 | 0 | STANDARD | High Point Technology Co, | SAR | 3635.87 | APPROVED |  |  | 2025-01-15 | 0 | 9 | Abuhammad, Samir | -45663 | 9
105-131 | Farasan Island 132/33/13.8 kV | 2912 | Farasan Island 132/33/13.8 kV-Design and Engineering Services | APPROVED | No | 2024-03-27 | Abas, Mohammed Fekry | 2024-03-28 | 2024-03-28 |  |  |  | 1100000 | 5331 | 0 | STANDARD | BAHRAWY Gulf CONSULTANCY GROUP | SAR | 1100000 | APPROVED |  |  | 2024-04-18 | 0 | 21 | Alhadi, Khalid | -45379 | 21
105-131 | Farasan Island 132/33/13.8 kV | 2919 | Farasan Island 132/33/13.8 kV-Design, Manufacturing, FAT and Supply of 13.8kV MV Metalclad Switchgear | APPROVED | No | 2024-03-27 | Abas, Mohammed Fekry | 2024-03-28 | 2024-03-28 |  |  |  | 8771237 | 5333 | 0 | STANDARD | SIEMENS LIMITED | SAR | 8771237 | APPROVED |  |  | 2024-04-21 | 0 | 24 | Muhammad, Muhammad Atif | -45379 | 24
105-131 | Farasan Island 132/33/13.8 kV | 2920 | Farasan Island 132/33/13.8 kV-80 & 50 MVA Power transformers | APPROVED | No | 2024-03-28 | Abas, Mohammed Fekry | 2024-03-28 | 2024-03-28 |  |  |  | 21967500 | 5282 | 0 | STANDARD | VOLTAMP POWER SAOC | USD | 21899999.99 | APPROVED |  |  | 2024-04-21 | 67500.01 | 24 | Muhammad, Muhammad Atif | -45379 | 24
105-131 | Farasan Island 132/33/13.8 kV | 2921 | Farasan Island 132/33/13.8 kV-Supply of 33kV MV Metalclad Switchgear | APPROVED | No | 2024-03-28 | Abas, Mohammed Fekry | 2024-03-28 | 2024-03-28 |  |  |  | 5428763 | 5317 | 0 | STANDARD | SIEMENS LIMITED | SAR | 5428763 | APPROVED |  |  | 2024-04-21 | 0 | 24 | Muhammad, Muhammad Atif | -45379 | 24
105-131 | Farasan Island 132/33/13.8 kV | 2956 | Farasan Island 132/33/13.8 kV-Topographic Survey | APPROVED | No | 2024-03-31 | Abas, Mohammed Fekry | 2024-04-01 | 2024-04-02 |  |  |  | 17000 | 5724 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 17000 | APPROVED |  |  | 2024-06-26 | 0 | 85 | Alhadi, Khalid | -45384 | 85
105-131 | Farasan Island 132/33/13.8 kV | 2957 | Farasan Island 132/33/13.8 kV-Geotechnical Investigation | APPROVED | No | 2024-03-31 | Abas, Mohammed Fekry | 2024-04-01 | 2024-04-02 |  |  |  | 49000 | 5723 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 49000 | APPROVED |  |  | 2024-06-24 | 0 | 83 | Alhadi, Khalid | -45384 | 83
105-131 | Farasan Island 132/33/13.8 kV | 2972 | Farasan Island 132/33/13.8 kV-132kV SF6 Gas-insulated Switchgear | APPROVED | No | 2024-04-01 | Abas, Mohammed Fekry | 2024-04-03 | 2024-04-04 |  |  |  | 19774664.98 | 5364 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 19774664.98 | APPROVED |  |  | 2024-04-23 | 0 | 19 | Muhammad, Muhammad Atif | -45386 | 19
105-131 | Farasan Island 132/33/13.8 kV | 2974 | Farasan Island 132/33/13.8 kV-AMI, Protection,Control System | APPROVED | No | 2024-04-02 | Abas, Mohammed Fekry | 2024-04-03 | 2024-04-04 |  |  |  | 5262948.55 | 5336 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 5190204 | APPROVED |  |  | 2024-04-21 | 72744.55 | 17 | Alhadi, Khalid | -45386 | 17
105-131 | Farasan Island 132/33/13.8 kV | 2976 | Farasan Island 132/33/13.8 kV-Communication System | APPROVED | No | 2024-04-02 | Abas, Mohammed Fekry | 2024-04-03 | 2024-04-04 |  |  |  | 5737214.4 | 5336 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 5657915 | APPROVED |  |  | 2024-04-21 | 79299.4 | 17 | Alhadi, Khalid | -45386 | 17
105-131 | Farasan Island 132/33/13.8 kV | 2977 | Farasan Island 132/33/13.8 kV-SAS system Including Remote end SAS/Scada modification | APPROVED | No | 2024-04-02 | Abas, Mohammed Fekry | 2024-04-03 | 2024-04-04 |  |  |  | 3682784.89 | 5336 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 3631881 | APPROVED |  |  | 2024-04-21 | 50903.89 | 17 | Alhadi, Khalid | -45386 | 17
105-131 | Farasan Island 132/33/13.8 kV | 2978 | Farasan Island 132/33/13.8 kV-Design, Manufacturing, Test and Supply of 150MVA Power Transformers | APPROVED | No | 2024-04-02 | Abas, Mohammed Fekry | 2024-04-03 | 2024-04-04 |  |  |  | 21538716.64 | 5594 | 0 | STANDARD | Energy Technical Services (ETS) | USD | 19387500 | APPROVED |  |  | 2024-09-26 | 2151216.64 | 175 | Muhammad, Muhammad Atif | -45386 | 175
105-131 | Farasan Island 132/33/13.8 kV | 3000 | Farasan Island 132/33/13.8 kV-132kV GIB | APPROVED | No | 2024-04-05 | Abas, Mohammed Fekry | 2024-04-07 | 2024-04-07 |  |  |  | 820264.23 | 5364 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 820264.23 | APPROVED |  |  | 2024-04-23 | 0 | 16 | Muhammad, Muhammad Atif | -45389 | 16
105-131 | Farasan Island 132/33/13.8 kV | 3001 | Farasan Island 132/33/13.8 kV-132kV GIB Connectors | APPROVED | No | 2024-04-05 | Abas, Mohammed Fekry | 2024-04-07 | 2024-04-07 |  |  |  | 202535.66 | 5364 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 202535.66 | APPROVED |  |  | 2024-04-23 | 0 | 16 | Muhammad, Muhammad Atif | -45389 | 16
105-131 | Farasan Island 132/33/13.8 kV | 3002 | Farasan Island 132/33/13.8 kV-132kV GIB Support Structures | APPROVED | No | 2024-04-05 | Abas, Mohammed Fekry | 2024-04-07 | 2024-04-07 |  |  |  | 101267.28 | 5364 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 101267.28 | APPROVED |  |  | 2024-04-23 | 0 | 16 | Muhammad, Muhammad Atif | -45389 | 16
105-131 | Farasan Island 132/33/13.8 kV | 3003 | Farasan Island 132/33/13.8 kV-132kV GIS Termination | APPROVED | No | 2024-04-05 | Abas, Mohammed Fekry | 2024-04-07 | 2024-04-07 |  |  |  | 101267.83 | 5364 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 101267.83 | APPROVED |  |  | 2024-04-23 | 0 | 16 | Muhammad, Muhammad Atif | -45389 | 16
105-131 | Farasan Island 132/33/13.8 kV | 3004 | Farasan Island 132/33/13.8 kV- 13.8KV and 33KV Capacitor Banks | APPROVED | No | 2024-04-05 | Abas, Mohammed Fekry | 2024-04-07 | 2024-04-07 |  |  |  | 4507000 | 5366 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 4050000 | APPROVED |  |  | 2024-04-23 | 457000 | 16 | Muhammad, Muhammad Atif | -45389 | 16
105-131 | Farasan Island 132/33/13.8 kV | 3004 | Farasan Island 132/33/13.8 kV- 13.8KV and 33KV Capacitor Banks | APPROVED | No | 2024-04-05 | Abas, Mohammed Fekry | 2024-04-07 | 2024-04-07 |  |  |  | 4507000 | [5 empty] | 0 |  |  |  |  | 0 |  | Muhammad, Muhammad Atif | -45389 | -45389
105-131 | Farasan Island 132/33/13.8 kV | 3014 | Farasan Island 132/33/13.8 kV-Site office | APPROVED | No | 2024-04-08 | Abas, Mohammed Fekry | 2024-04-16 | 2024-04-16 |  |  |  | 519727 | 5578 | 0 | STANDARD | Construction Expertise Est. | SAR | 519727 | APPROVED |  |  | 2024-06-13 | 0 | 58 | Babic, Marian | -45398 | 58
105-131 | Farasan Island 132/33/13.8 kV | 3014 | Farasan Island 132/33/13.8 kV-Site office | APPROVED | No | 2024-04-08 | Abas, Mohammed Fekry | 2024-04-16 | 2024-04-16 |  |  |  | 519727 | 6166 | 0 | STANDARD | Dynamic Solutions Est. | SAR | 519727 | APPROVED |  |  | 2024-09-17 | 0 | 154 | Babic, Marian | -45398 | 154
105-131 | Farasan Island 132/33/13.8 kV | 3174 | Farasan Island 132/33/13.8 kV-Control and Protection of DRPC | APPROVED | No | 2024-04-28 | Abas, Mohammed Fekry | 2024-04-29 | 2024-04-29 |  |  |  | 920941.56 | 5669 | 0 | STANDARD | NR Engineering Co.Ltd | USD | 525000 | APPROVED |  |  | 2024-07-17 | 395941.56 | 79 | Muhammad, Muhammad Atif | -45411 | 79
105-131 | Farasan Island 132/33/13.8 kV | 3176 | Farasan Island 132/33/13.8 kV-DRPC HMI | APPROVED | No | 2024-04-28 | Abas, Mohammed Fekry | 2024-04-29 | 2024-04-29 |  |  |  | 442052.06 | 5669 | 0 | STANDARD | NR Engineering Co.Ltd | USD | 300000 | APPROVED |  |  | 2024-07-17 | 142052.06 | 79 | Muhammad, Muhammad Atif | -45411 | 79
105-131 | Farasan Island 132/33/13.8 kV | 3177 | Farasan Island 132/33/13.8 kV-DRPC Surge Capacitors | APPROVED | No | 2024-04-28 | Abas, Mohammed Fekry | 2024-04-29 | 2024-04-29 |  |  |  | 221026.03 | 5669 | 0 | STANDARD | NR Engineering Co.Ltd | USD | 187500 | APPROVED |  |  | 2024-07-17 | 33526.03 | 79 | Muhammad, Muhammad Atif | -45411 | 79
105-131 | Farasan Island 132/33/13.8 kV | 3180 | Farasan Island 132/33/13.8 kV-Statcom System_150Mvar VSC System | APPROVED | No | 2024-04-28 | Abas, Mohammed Fekry | 2024-04-29 | 2024-04-29 |  |  |  | 15195538.18 | 5669 | 0 | STANDARD | NR Engineering Co.Ltd | USD | 14925000 | APPROVED |  |  | 2024-07-17 | 270538.18 | 79 | Muhammad, Muhammad Atif | -45411 | 79
105-131 | Farasan Island 132/33/13.8 kV | 3182 | Farasan Island 132/33/13.8 kV-Statcom System_DRPC MV Bus | APPROVED | No | 2024-04-28 | Abas, Mohammed Fekry | 2024-04-29 | 2024-04-29 |  |  |  | 2275368.14 | 5669 | 0 | STANDARD | NR Engineering Co.Ltd | USD | 2137500 | APPROVED |  |  | 2024-07-17 | 137868.14 | 79 | Muhammad, Muhammad Atif | -45411 | 79
105-131 | Farasan Island 132/33/13.8 kV | 3221 | Farasan Island 132/33/13.8 kV-Neutral Grounding Resistor 13.8kV, 800A, 10 Ohms | APPROVED | No | 2024-04-29 | Abas, Mohammed Fekry | 2024-05-06 | 2024-05-12 |  |  |  | 150000 | 5748 | 0 | STANDARD | METAL DEPLOYE RESISTOR | EUR | 105209.49 | APPROVED |  |  | 2024-07-25 | 44790.51 | 74 | Muhammad, Muhammad Atif | -45424 | 74
105-131 | Farasan Island 132/33/13.8 kV | 3234 | Farasan Island 132/33/13.8 kV-Cyber Security System | APPROVED | No | 2024-04-30 | Abas, Mohammed Fekry | 2024-05-06 | 2024-05-12 |  |  |  | 2004000 | 5789 | 0 | STANDARD | ACET SOLUTIONS LLC | SAR | 924991.48 | APPROVED |  |  | 2024-07-21 | 1079008.52 | 70 | Badhman, Saeed | -45424 | 70
105-131 | Farasan Island 132/33/13.8 kV | 3282 | Farasan Island 132/33/13.8 kV-Site office power generator | APPROVED | No | 2024-05-02 | Abas, Mohammed Fekry | 2024-05-07 | 2024-05-09 |  |  |  | 219000 | 5578 | 0 | STANDARD | Construction Expertise Est. | SAR | 219000 | APPROVED |  |  | 2024-06-13 | 0 | 35 | Babic, Marian | -45421 | 35
105-131 | Farasan Island 132/33/13.8 kV | 3282 | Farasan Island 132/33/13.8 kV-Site office power generator | APPROVED | No | 2024-05-02 | Abas, Mohammed Fekry | 2024-05-07 | 2024-05-09 |  |  |  | 219000 | 6166 | 0 | STANDARD | Dynamic Solutions Est. | SAR | 83100 | APPROVED |  |  | 2024-09-17 | 135900 | 131 | Babic, Marian | -45421 | 131
105-131 | Farasan Island 132/33/13.8 kV | 3290 | Farasan Island 132/33/13.8 kV-Site leveling & access preparation | APPROVED | No | 2024-05-05 | Abas, Mohammed Fekry | 2024-05-07 | 2024-05-09 |  |  |  | 129000 | 5522 | 0 | STANDARD | Ibrahim Hussein Ibrahim Sayyadi General Contracting Est. | SAR | 129000 | APPROVED |  |  | 2024-06-09 | 0 | 31 | Muhammad, Muhammad Atif | -45421 | 31
105-131 | Farasan Island 132/33/13.8 kV | 3388 | Farasan Island 132/33/13.8 kV-Building Permit | APPROVED | No | 2024-05-13 | Abas, Mohammed Fekry | 2024-05-13 | 2024-05-14 |  |  |  | 20000 | 5545 | 0 | STANDARD | AlAtas for Engineering Consultants Office | SAR | 20000 | APPROVED |  |  | 2024-05-21 | 0 | 7 | Alhadi, Khalid | -45426 | 7
105-131 | Farasan Island 132/33/13.8 kV | 3393 | Farasan Island 132/33/13.8 kV-Site office Facility | APPROVED | No | 2024-05-14 | Abas, Mohammed Fekry | 2024-05-19 | 2024-05-19 |  |  |  | 300727 | 5578 | 0 | STANDARD | Construction Expertise Est. | SAR | 300727 | APPROVED |  |  | 2024-06-13 | 0 | 25 | Babic, Marian | -45431 | 25
105-131 | Farasan Island 132/33/13.8 kV | 3393 | Farasan Island 132/33/13.8 kV-Site office Facility | APPROVED | No | 2024-05-14 | Abas, Mohammed Fekry | 2024-05-19 | 2024-05-19 |  |  |  | 300727 | 6166 | 0 | STANDARD | Dynamic Solutions Est. | SAR | 300727 | APPROVED |  |  | 2024-09-17 | 0 | 121 | Babic, Marian | -45431 | 121
105-131 | Farasan Island 132/33/13.8 kV | 3396 | Farasan Island 132/33/13.8 kV-Provision of Site storage | APPROVED | No | 2024-05-14 | Abas, Mohammed Fekry | 2024-05-19 | 2024-05-19 |  |  |  | 196446 | 5578 | 0 | STANDARD | Construction Expertise Est. | SAR | 196446 | APPROVED |  |  | 2024-06-13 | 0 | 25 | Babic, Marian | -45431 | 25
105-131 | Farasan Island 132/33/13.8 kV | 3396 | Farasan Island 132/33/13.8 kV-Provision of Site storage | APPROVED | No | 2024-05-14 | Abas, Mohammed Fekry | 2024-05-19 | 2024-05-19 |  |  |  | 196446 | 6166 | 0 | STANDARD | Dynamic Solutions Est. | SAR | 196446 | APPROVED |  |  | 2024-09-17 | 0 | 121 | Babic, Marian | -45431 | 121
105-131 | Farasan Island 132/33/13.8 kV | 3724 | Farasan Island 132/33/13.8 kV-Statcom System 150Mvar(1) | APPROVED | No | 2024-07-01 | Abas, Mohammed Fekry | 2024-07-03 | 2024-07-03 |  |  |  | 1040610 | 5669 | 0 | STANDARD | NR Engineering Co.Ltd | USD | 1012500 | APPROVED |  |  | 2024-07-17 | 28110 | 14 | Muhammad, Muhammad Atif | -45476 | 14
105-131 | Farasan Island 132/33/13.8 kV | 3725 | Farasan Island 132/33/13.8 kV-Statcom System 150Mvar (S) | APPROVED | No | 2024-07-01 | Abas, Mohammed Fekry | 2024-07-03 | 2024-07-03 |  |  |  | 1350000 | 5669 | 0 | STANDARD | NR Engineering Co.Ltd | USD | 1350000 | APPROVED |  |  | 2024-07-17 | 0 | 14 | Muhammad, Muhammad Atif | -45476 | 14
105-131 | Farasan Island 132/33/13.8 kV | 3956 | Farasan Island 132/33/13.8 kV-Supply of Surge Arrestor 120kV & 15kV | APPROVED | No | 2024-07-18 | Abas, Mohammed Fekry | 2024-09-26 | 2024-09-26 | 2024-09-03 |  | Duplicated item in the same PR. | 125532 | 5871 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 61200 | APPROVED |  |  | 2024-10-06 | 64332 | 10 | Abdulqader, Ahmed Abdulhalim | -45561 | 10
105-131 | Farasan Island 132/33/13.8 kV | 4039 | Farasan Island 132/33/13.8 kV-Supply of 750kVA Station Transformers with Impedance Voltage (7.5Vk ) | APPROVED | No | 2024-07-28 | Abas, Mohammed Fekry | 2024-07-29 | 2024-07-30 |  |  |  | 352000 | 6130 | 0 | STANDARD | ALFANAR CO | SAR | 352000 | APPROVED |  |  | 2024-10-09 | 0 | 71 | Badhman, Saeed | -45503 | 71
105-131 | Farasan Island 132/33/13.8 kV | 4115 | Farasan Island 132/33/13.8 kV-Overhead Traveling Crane- 5T | APPROVED | No | 2024-08-07 | Abas, Mohammed Fekry | 2024-08-12 | 2024-08-13 |  |  |  | 200000 | 6174 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 174850 | APPROVED |  |  | 2024-10-06 | 25150 | 54 | Muhammad, Muhammad Atif | -45517 | 54
105-131 | Farasan Island 132/33/13.8 kV | 4132 | Farasan Island 132/33/13.8 kV-CIF for POST INSULATOR | APPROVED | No | 2024-08-11 | Abas, Mohammed Fekry | 2024-08-25 | 2024-08-25 |  |  |  | 6000 | 6134 | 0 | STANDARD | PPC ČAB a.s. | EUR | 5474 | APPROVED |  |  | 2024-12-29 | 526 | 126 | Muhammad, Muhammad Atif | -45529 | 126
105-131 | Farasan Island 132/33/13.8 kV | 4145 | Farasan Island 132/33/13.8 kV-132kV, Single core, Copper, XLPE cable 2000 mm2 | APPROVED | No | 2024-08-12 | Abas, Mohammed Fekry | 2024-08-21 | 2024-08-22 |  |  |  | 574997.76 | 6176 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 313155.72 | APPROVED |  |  | 2024-09-24 | 261842.04 | 33 | Badhman, Saeed | -45526 | 33
105-131 | Farasan Island 132/33/13.8 kV | 4294 | Farasan Island 132/33/13.8 kV-Supply of Post Insulator 132 KV | APPROVED | No | 2024-08-28 | Abas, Mohammed Fekry | 2024-09-05 | 2024-09-05 |  |  |  | 106500 | 6134 | 0 | STANDARD | PPC ČAB a.s. | EUR | 96754.72 | APPROVED |  |  | 2024-12-29 | 9745.28 | 115 | Muhammad, Muhammad Atif | -45540 | 115
105-131 | Farasan Island 132/33/13.8 kV | 4478 | Farasan Island 132/33/13.8 kV-MV Cable (13.8 KV and 33 KV) | RETURNED | No | 2024-09-18 | Badhman, Saeed | 2025-09-08 | 2024-11-07 |  |  |  | 2135538.18 | 6170 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 2135538.18 | APPROVED |  |  | 2024-12-26 | 0 |  | Badhman, Saeed | -45603 | 49
105-131 | Farasan Island 132/33/13.8 kV | 4478 | Farasan Island 132/33/13.8 kV-MV Cable (13.8 KV and 33 KV) | RETURNED | No | 2024-09-18 | Badhman, Saeed | 2025-09-08 | 2024-11-07 |  |  |  | 569750.42 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45603 | -45603
105-131 | Farasan Island 132/33/13.8 kV | 4485 | Farasan Island 132/33/13.8 kV-Site levelling, excavation, Removal of debries | APPROVED | No | 2024-09-19 | Abas, Mohammed Fekry | 2024-09-25 | 2024-09-26 |  |  |  | 538200 | 6223 | 0 | STANDARD | Ibrahim Hussein Ibrahim Sayyadi General Contracting Est. | SAR | 468000 | APPROVED |  |  | 2024-10-06 | 70200 | 10 | Muhammad, Muhammad Atif | -45561 | 10
105-131 | Farasan Island 132/33/13.8 kV | 4550 | Farasan Island 132/33/13.8 kV-Geo Physical Investigation study | IN PROCESS | No | 2024-09-29 | Mydeen, Shaik Peer Mohamed | 2024-09-29 |  |  |  |  | 235000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-131 | Farasan Island 132/33/13.8 kV | 4570 | Farasan Island 132/33/13.8 kV-Site Preparation and access | APPROVED | No | 2024-10-01 | Abas, Mohammed Fekry | 2024-10-06 | 2024-10-07 |  |  |  | 73680 | 6224 | 0 | STANDARD | Ibrahim Hussein Ibrahim Sayyadi General Contracting Est. | SAR | 73680 | APPROVED |  |  | 2024-10-13 | 0 | 6 | Muhammad, Muhammad Atif | -45572 | 6
105-131 | Farasan Island 132/33/13.8 kV | 4660 | Farasan Island 132/33/13.8 kV-MV power Cable Termination 13.8KV and 33KV | APPROVED | No | 2024-10-13 | Abas, Mohammed Fekry | 2024-10-13 | 2024-10-14 |  |  |  | 212375.92 | 6273 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 212375.92 | APPROVED |  |  | 2024-10-30 | 0 | 16 | Muhammad, Muhammad Atif | -45579 | 16
105-131 | Farasan Island 132/33/13.8 kV | 4702 | Farasan Island 132/33/13.8 kV-Fire Fighting System Substation portion | APPROVED | No | 2024-10-16 | Abas, Mohammed Fekry | 2024-10-17 | 2024-10-17 |  |  |  | 4320000 | 6378 | 0 | STANDARD | Al Majal Group Four S for Security & Safety | SAR | 3840000 | APPROVED |  |  | 2024-10-31 | 480000 | 14 | Mohammed, Faisal Ansari | -45582 | 14
105-131 | Farasan Island 132/33/13.8 kV | 4764 | Farasan Island 132/33/13.8 kV-Soil Improvement Pressure Grouting Works | APPROVED | No | 2024-10-21 | Abas, Mohammed Fekry | 2024-10-24 | 2024-10-27 |  |  |  | 1500000 | 6409 | 0 | STANDARD | TALEED GULF CONTRACTING EST. | SAR | 480400 | APPROVED |  |  | 2024-11-05 | 1019600 | 9 | Tananeh, Khalid Jamal | -45592 | 9
105-131 | Farasan Island 132/33/13.8 kV | 4785 | Farasan Island 132/33/13.8 kV-Fire Fighting System for STATCOM Portion | APPROVED | No | 2024-10-24 | Abas, Mohammed Fekry | 2024-10-24 | 2024-10-27 |  |  |  | 1100000 | 6378 | 0 | STANDARD | Al Majal Group Four S for Security & Safety | SAR | 1100000 | APPROVED |  |  | 2024-10-31 | 0 | 4 | Mohammed, Faisal Ansari | -45592 | 4
105-131 | Farasan Island 132/33/13.8 kV | 4832 | Farasan Island 132/33/13.8 kV-Security Guard For Site | APPROVED | No | 2024-11-04 | Abas, Mohammed Fekry | 2024-11-06 | 2024-11-07 |  |  |  | 450000 | 6456 | 0 | STANDARD | Saad Al-Gazereh For Security Services Company | SAR | 74700 | APPROVED |  |  | 2024-11-12 | 375300 | 5 | Abuhammad, Samir | -45603 | 5
105-131 | Farasan Island 132/33/13.8 kV | 4832 | Farasan Island 132/33/13.8 kV-Security Guard For Site | APPROVED | No | 2024-11-04 | Abas, Mohammed Fekry | 2024-11-06 | 2024-11-07 |  |  |  | 450000 | 6456 | 1 | STANDARD | Saad Al-Gazereh For Security Services Company | SAR | 34362 | APPROVED |  |  | 2025-08-31 | 415638 | 297 | Abuhammad, Samir | -45603 | 297
105-131 | Farasan Island 132/33/13.8 kV | 4835 | Farasan Island 132/33/13.8 kV-Applus Engineer for supervision of pressure grouting asper SEC comments | APPROVED | No | 2024-11-05 | Abas, Mohammed Fekry | 2024-11-06 | 2024-11-07 |  |  |  | 90000 | 6501 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 35100 | APPROVED |  |  | 2025-02-16 | 54900 | 101 | Tananeh, Khalid Jamal | -45603 | 101
105-131 | Farasan Island 132/33/13.8 kV | 4887 | Farasan Island 132/33/13.8 kV-Shielding System | REJECTED | No | 2024-11-10 | Yamama, Loai Mohamed | 2025-03-01 |  |  | 2025-03-02 | Budget line item - 1.4.3.1.1.22 | 300000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-131 | Farasan Island 132/33/13.8 kV | 5026 | Farasan Island 132/33/13.8 kV-Supply of Water and removal of Sewage | APPROVED | No | 2024-11-23 | Abas, Mohammed Fekry | 2024-12-01 | 2024-12-03 |  |  |  | 27000 | 6765 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 26800 | APPROVED |  |  | 2025-01-28 | 200 | 56 | Akhtar, Farhan | -45629 | 56
105-131 | Farasan Island 132/33/13.8 kV | 5027 | Farasan Island 132/33/13.8 kV-Supply of Diesel for Site Generator | APPROVED | No | 2024-11-23 | Abas, Mohammed Fekry | 2024-12-01 | 2024-12-03 |  |  |  | 135900 | 6674 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 135900 | APPROVED |  |  | 2024-12-29 | 0 | 26 | Akhtar, Farhan | -45629 | 26
105-131 | Farasan Island 132/33/13.8 kV | 5103 | Farasan Island 132/33/13.8 kV-SEC site Requirements - Printer , computers and laptop | APPROVED | No | 2024-12-01 | Mydeen, Shaik Peer Mohamed | 2024-12-08 | 2024-12-08 |  |  |  | 25000 | 6603 | 0 | STANDARD | Mohammad Abdul Rahman Mohd Al Zahid Information Technology Co | SAR | 18924 | APPROVED |  |  | 2024-12-26 | 6076 | 18 | Akhtar, Farhan | -45634 | 18
105-131 | Farasan Island 132/33/13.8 kV | 5235 | Farasan Island 132/33/13.8 kV-Post insulator 132 KV | APPROVED | No | 2024-12-16 | Abas, Mohammed Fekry | 2024-12-17 | 2024-12-18 |  |  |  | 10710 | 6134 | 0 | STANDARD | PPC ČAB a.s. | EUR | 9675.47 | APPROVED |  |  | 2024-12-29 | 1034.53 | 11 | Muhammad, Muhammad Atif | -45644 | 11
105-131 | Farasan Island 132/33/13.8 kV | 5243 | Farasan Island 132/33/13.8 kV-Geophysical investigation study MASW | IN PROCESS | No | 2024-12-18 | Mydeen, Shaik Peer Mohamed | 2024-12-26 | 2024-12-26 |  |  |  | 100000 | [5 empty] | 0 |  |  |  |  | 0 |  | Muhammad, Muhammad Atif | -45652 | -45652
105-131 | Farasan Island 132/33/13.8 kV | 5290 | Farasan Island 132/33/13.8 kV-Bonding Cable Y/G and Black | REJECTED | No | 2024-12-29 | Yamama, Loai Mohamed | 2025-03-01 | 2024-12-30 |  | 2025-03-02 |  | 12498 | [5 empty] | 0 |  |  |  |  | 0 |  | Muhammad, Muhammad Atif | -45656 | -45656
105-131 | Farasan Island 132/33/13.8 kV | 5308 | Farasan Island 132/33/13.8 kV-5G Routers and Projector for Site | APPROVED | No | 2024-12-31 | Abas, Mohammed Fekry | 2025-01-02 | 2025-01-02 |  |  |  | 3900 | 6740 | 0 | STANDARD | Excellence Arabia Trading Company | SAR | 3600 | APPROVED |  |  | 2025-01-28 | 300 | 26 | Akhtar, Farhan | -45659 | 26
105-131 | Farasan Island 132/33/13.8 kV | 5309 | Farasan Island 132/33/13.8 kV-CCTV System for site Security including monitor | APPROVED | No | 2024-12-31 | Abas, Mohammed Fekry | 2025-03-18 | 2025-03-20 | 2025-02-16 |  | details not provided | 15000 | 7056 | 0 | STANDARD | BURK AL-SAMMAN For Security Surveillance Est. | SAR | 6460.87 | APPROVED |  |  | 2025-04-06 | 8539.13 | 17 | Babic, Marian | -45736 | 17
105-131 | Farasan Island 132/33/13.8 kV | 5599 | Farasan Island 132/33/13.8 kV-Testing, Commissioning for Subsation , STATCOM and Remote End | APPROVED | No | 2025-01-26 | Abas, Mohammed Fekry | 2025-03-03 | 2025-03-05 |  |  | Budget line item 1.4.3.1.4 and 1.4.3.2.4 | 3783593 | 7692 | 0 | STANDARD | Al Fanar Technical Services | SAR | 3654797 | APPROVED |  |  | 2025-10-30 | 128796 | 239 | Babic, Marian | -45721 | 239
105-131 | Farasan Island 132/33/13.8 kV | 5601 | Farasan Island 132/33/13.8 kV-132 KV cable HV test for STATCOM | APPROVED | No | 2025-01-26 | Abas, Mohammed Fekry | 2025-03-03 | 2025-03-05 |  |  | 1.4.3.2.4 budget line item | 150000 | 7692 | 0 | STANDARD | Al Fanar Technical Services | SAR | 150000 | APPROVED |  |  | 2025-10-30 | 0 | 239 | Babic, Marian | -45721 | 239
105-131 | Farasan Island 132/33/13.8 kV | 5850 | Farasan Island 132/33/13.8 kV-Aluminum Clamps and connector | RETURNED | No | 2025-02-11 | Abdulqader, Ahmed Abdulhalim | 2025-02-26 | 2025-02-18 | 2025-02-26 |  | PR is not as per shared BOQ | 36000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45706 | -45706
105-131 | Farasan Island 132/33/13.8 kV | 6004 | Farasan Island 132/33/13.8 kV-MV Cables 1x185 SQMM | APPROVED | No | 2025-02-19 | Abas, Mohammed Fekry | 2025-02-24 | 2025-02-24 |  |  | 1.4.3.1.1.11 budget line | 168480 | 6170 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 157483.87 | APPROVED |  |  | 2025-04-24 | 10996.13 | 59 | Abdulqader, Ahmed Abdulhalim | -45712 | 59
105-131 | Farasan Island 132/33/13.8 kV | 6018 | Farasan Island 132/33/13.8 kV-Air Freight For OH Crane | REJECTED | No | 2025-02-20 | Yamama, Loai Mohamed | 2025-02-27 | 2025-02-20 |  | 2025-03-02 |  | 30000 | [5 empty] | 0 |  |  |  |  | 0 |  | Muhammad, Muhammad Atif | -45708 | -45708
105-131 | Farasan Island 132/33/13.8 kV | 6075 | Farasan Island 132/33/13.8 kV-Rental vehical for Site Use | RETURNED | No | 2025-02-27 | Badhman, Saeed | 2025-04-14 | 2025-03-05 | 2025-04-14 |  | more information is needed, You may coordinate with facility team since we have existing contracts | 60000 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45721 | -45721
105-131 | Farasan Island 132/33/13.8 kV | 6076 | Farasan Island 132/33/13.8 kV-crane Freight | RETURNED | No | 2025-02-27 | Kumar, Mr. Ranjan | 2025-03-17 | 2025-03-05 | 2025-03-17 |  | Vendor accepted to expedite the delivery without cost | 30000 | [5 empty] | 0 |  |  |  |  | 0 |  | Muhammad, Muhammad Atif | -45721 | -45721
105-131 | Farasan Island 132/33/13.8 kV | 6079 | Farasan Island 132/33/13.8 kV-Heavy lifting placing the transformer on foundation | APPROVED | No | 2025-02-27 | Abas, Mohammed Fekry | 2025-03-03 | 2025-03-05 |  |  |  | 150000 | 7276 | 0 | STANDARD | Branch Of: OFSAT LIMITED CO | SAR | 117000 | APPROVED |  |  | 2025-06-04 | 33000 | 91 | Badhman, Saeed | -45721 | 91
105-131 | Farasan Island 132/33/13.8 kV | 6084 | Farasan Island 132/33/13.8 kV-MV Cable | APPROVED | No | 2025-02-27 | Abas, Mohammed Fekry | 2025-03-03 | 2025-03-05 |  |  |  | 51840 | 6170 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 51238.66 | APPROVED |  |  | 2025-04-24 | 601.34 | 50 | Abdulqader, Ahmed Abdulhalim | -45721 | 50
105-131 | Farasan Island 132/33/13.8 kV | 6089 | Farasan Island 132/33/13.8 kV-Security System | APPROVED | No | 2025-02-27 | Abas, Mohammed Fekry | 2025-03-04 | 2025-03-05 |  |  |  | 1000000 | 6554 | 0 | STANDARD | CEGELEC NETWORK AND SECURITY SYSTEMS | SAR | 970000 | APPROVED |  |  | 2025-03-17 | 30000 | 12 | Mohammed, Faisal Ansari | -45721 | 12
105-131 | Farasan Island 132/33/13.8 kV | 6117 | Farasan Island 132/33/13.8 kV-Site Security Guard | APPROVED | No | 2025-03-05 | Abas, Mohammed Fekry | 2025-03-12 | 2025-03-13 |  |  |  | 200000 | 6998 | 0 | STANDARD | Rukn Al Kateibah Company for Security Guards. | SAR | 153000 | APPROVED |  |  | 2025-03-23 | 47000 | 10 | Abuhammad, Samir | -45729 | 10
105-131 | Farasan Island 132/33/13.8 kV | 6138 | Farasan Island 132/33/13.8 kV-HVAC System | APPROVED | No | 2025-03-09 | Abas, Mohammed Fekry | 2025-03-12 | 2025-03-13 |  |  |  | 5380000 | 6551 | 0 | STANDARD | MAINTENANCE OF AIRCONDITION AND REFRIGERATION COMPANY LTD.(MARCO) | SAR | 5380000 | APPROVED |  |  | 2025-03-23 | 0 | 10 | Mohammed, Faisal Ansari | -45729 | 10
105-131 | Farasan Island 132/33/13.8 kV | 6139 | Farasan Island 132/33/13.8 kV-Transportaion for NGR,NGT, Surge arrestor etc | RETURNED | No | 2025-03-09 | Badhman, Saeed | 2025-08-17 | 2025-03-13 | 2025-08-17 |  | Not needed, | 200000 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45729 | -45729
105-131 | Farasan Island 132/33/13.8 kV | 6199 | Farasan Island 132/33/13.8 kV-MV Termination plugin Type | RETURNED | No | 2025-03-18 | Mohammed, Faisal Ansari | 2025-10-23 | 2025-03-25 | 2025-10-23 |  | Could you please clarify the requirement and explain why it has been pending since March 2025? | 68400 | 6657 | 0 | STANDARD | Bright Wire Company | SAR | 68400 | APPROVED |  |  | 2025-04-06 | 0 |  | Mohammed, Faisal Ansari | -45741 | 12
105-131 | Farasan Island 132/33/13.8 kV | 6199 | Farasan Island 132/33/13.8 kV-MV Termination plugin Type | RETURNED | No | 2025-03-18 | Mohammed, Faisal Ansari | 2025-10-23 | 2025-03-25 | 2025-10-23 |  | Could you please clarify the requirement and explain why it has been pending since March 2025? | 68400 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45741 | -45741
105-131 | Farasan Island 132/33/13.8 kV | 6205 | Farasan Island 132/33/13.8 kV-45 KV grounding transformer | IN PROCESS | No | 2025-03-19 | Hayajneh, Ahmed Abdelaziz Moha | 2025-03-23 | 2025-03-20 |  |  |  | 1000000 | [5 empty] | 0 |  |  |  |  | 0 |  | Muhammad, Muhammad Atif | -45736 | -45736
105-131 | Farasan Island 132/33/13.8 kV | 6212 | Farasan Island 132/33/13.8 kV-Civil Works complete Scope | APPROVED | No | 2025-03-19 | Abas, Mohammed Fekry | 2025-03-24 | 2025-03-25 |  |  |  | 40021101 | 7131 | 0 | STANDARD | Intelligent System General Contracting Company | SAR | 40000000 | APPROVED |  |  | 2025-04-14 | 21101 | 20 | Tananeh, Khalid Jamal | -45741 | 20
105-131 | Farasan Island 132/33/13.8 kV | 6223 | Farasan Island 132/33/13.8 kV-activation of optional items and additional item for Hitachi PO | APPROVED | No | 2025-03-20 | Abas, Mohammed Fekry | 2025-03-24 | 2025-03-24 |  |  |  | 4220000 | 5336 | 1 | STANDARD | Hitachi Energy Ltd | SAR | 6327000 | APPROVED |  |  | 2025-08-18 | -2107000 | 147 | Alhadi, Khalid | -45740 | 147
105-131 | Farasan Island 132/33/13.8 kV | 6227 | Farasan Island 132/33/13.8 kV-Link Box | APPROVED | No | 2025-03-22 | Abas, Mohammed Fekry | 2025-03-25 | 2025-03-25 |  |  | PO-6435 itemized PR | 10200 | 6435 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 10200 | APPROVED |  |  | 2025-05-19 | 0 | 55 | Abdulqader, Ahmed Abdulhalim | -45741 | 55
105-131 | Farasan Island 132/33/13.8 kV | 6229 | Farasan Island 132/33/13.8 kV-Battery and Charger sytem for Statcom and Substation | REJECTED | No | 2025-03-23 | Yamama, Loai Mohamed | 2025-08-11 | 2025-08-04 | 2025-07-30 | 2025-08-11 | PR amount is Insufficient | 3391726.58 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45873 | -45873
105-131 | Farasan Island 132/33/13.8 kV | 6294 | Farasan Island 132/33/13.8 kV-TPI for Transformer inspection | APPROVED | No | 2025-04-06 | Abas, Mohammed Fekry | 2025-04-06 | 2025-04-06 |  |  | TPI for Transfomer | 150000 | 7128 | 0 | STANDARD | SGS GULF LIMITED | USD | 138844.5 | APPROVED |  |  | 2025-05-25 | 11155.5 | 49 | Akhtar, Farhan | -45753 | 49
105-131 | Farasan Island 132/33/13.8 kV | 6305 | Farasan Island 132/33/13.8 kV-Neutral Grounding Resistor 13.8kV, 1500A, 5.31 Ohms Statcom portion | RETURNED | No | 2025-04-07 | Kumar, Mr. Ranjan | 2025-06-29 | 2025-04-13 | 2025-06-29 |  | PO already revised with old PR | 104790 | [5 empty] | 0 |  |  |  |  | 0 |  | Muhammad, Muhammad Atif | -45760 | -45760
105-131 | Farasan Island 132/33/13.8 kV | 6345 | Farasan Island 132/33/13.8 kV-Cable Tray | APPROVED | No | 2025-04-15 | Abas, Mohammed Fekry | 2025-04-17 | 2025-04-21 |  |  | PO-6768 | 805694.92 | 6768 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 800000 | APPROVED |  |  | 2025-04-28 | 5694.92 | 7 | Muaz, Alaa | -45768 | 7
105-131 | Farasan Island 132/33/13.8 kV | 6346 | Farasan Island 132/33/13.8 kV-Ring Main Unit | APPROVED | No | 2025-04-15 | Abas, Mohammed Fekry | 2025-04-17 | 2025-04-21 |  |  | PO-6165 | 179500 | 6165 | 0 | STANDARD | ALFANAR CO | SAR | 179500 | APPROVED |  |  | 2025-09-04 | 0 | 136 | Abdulqader, Ahmed Abdulhalim | -45768 | 136
105-131 | Farasan Island 132/33/13.8 kV | 6387 | Farasan Island 132/33/13.8 kV-Inpsection for Capacitor bank unit | RETURNED | No | 2025-04-20 | Kumar, Mr. Ranjan | 2025-06-15 | 2025-04-20 | 2025-06-15 |  | As discussed, It can be done under blanket agreement with SGS. | 3000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45767 | -45767
105-131 | Farasan Island 132/33/13.8 kV | 6601 | Farasan Island 132/33/13.8 kV-FAT for Post insulator | REJECTED | No | 2025-05-13 | Hayajneh, Ahmed Abdelaziz Moha | 2025-05-16 | 2025-05-14 | 2025-05-15 | 2025-05-19 | change the QTY | 225000000 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45791 | -45791
105-131 | Farasan Island 132/33/13.8 kV | 6610 | Farasan Island 132/33/13.8 kV-LAB booking For FAT - UPS- HUWAWIE CHINA | APPROVED | No | 2025-05-13 | Abas, Mohammed Fekry | 2025-05-14 | 2025-05-14 |  |  |  | 35000 | 5669 | 1 | STANDARD | NR Engineering Co.Ltd | USD | 32820 | APPROVED |  |  | 2025-07-14 | 2180 | 61 | Abdulqader, Ahmed Abdulhalim | -45791 | 61
105-131 | Farasan Island 132/33/13.8 kV | 6625 | Farasan Island 132/33/13.8 kV-Heavy lifting For Transformer- batch 02 | APPROVED | No | 2025-05-15 | Abas, Mohammed Fekry | 2025-05-19 | 2025-05-19 |  |  |  | 200000 | 7276 | 0 | STANDARD | Branch Of: OFSAT LIMITED CO | SAR | 200000 | APPROVED |  |  | 2025-06-04 | 0 | 16 | Badhman, Saeed | -45796 | 16
105-131 | Farasan Island 132/33/13.8 kV | 6629 | Farasan Island 132/33/13.8 kV-Site Security- increase manpower | APPROVED | No | 2025-05-16 | Abas, Mohammed Fekry | 2025-06-10 | 2025-06-12 |  |  |  | 100000 | 7458 | 0 | STANDARD | Rukn Al Kateibah Company for Security Guards. | SAR | 76500 | APPROVED |  |  | 2025-08-06 | 23500 | 55 | Abuhammad, Samir | -45820 | 55
105-131 | Farasan Island 132/33/13.8 kV | 6649 | Farasan Island 132/33/13.8 kV-Transformer offloading | APPROVED | No | 2025-05-19 | Abas, Mohammed Fekry | 2025-05-21 | 2025-05-21 |  |  |  | 33000 | 7276 | 0 | STANDARD | Branch Of: OFSAT LIMITED CO | SAR | 33000 | APPROVED |  |  | 2025-06-04 | 0 | 14 | Badhman, Saeed | -45798 | 14
105-131 | Farasan Island 132/33/13.8 kV | 6650 | Farasan Island 132/33/13.8 kV-POST insulator FAT TPI | APPROVED | No | 2025-05-19 | Abas, Mohammed Fekry | 2025-05-21 | 2025-05-21 |  |  |  | 15000 | 7241 | 0 | STANDARD | SGS GULF LIMITED | USD | 13766.51 | APPROVED |  |  | 2025-06-15 | 1233.49 | 25 | Akhtar, Farhan | -45798 | 25
105-131 | Farasan Island 132/33/13.8 kV | 6858 | Farasan Island 132/33/13.8 kV-Cable Clamps | INCOMPLETE | No |  | Oracle Consultant, | 2025-06-23 |  |  |  |  | 1755 | [5 empty] | 0 |  |  |  |  | 0 |  | Ahmed, Ahmed Salah Ahmed Mohamed | 0 | 0
105-131 | Farasan Island 132/33/13.8 kV | 6886 | Farasan Island 132/33/13.8 kV-Security for Jizan Ware hose | REJECTED | No | 2025-06-24 | Ahmed, Ahmed Salah Ahmed Mohamed | 2025-06-24 |  |  | 2025-06-24 |  | 150000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | 0 | 0
105-131 | Farasan Island 132/33/13.8 kV | 7038 | Farasan Island 132/33/13.8 kV-Surge Arrestor for substation portion | APPROVED | No | 2025-07-09 | Abas, Mohammed Fekry | 2025-07-14 | 2025-07-14 |  |  |  | 115500 | 7608 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 104142.2 | APPROVED |  |  | 2025-08-21 | 11357.8 | 38 | Abdulqader, Ahmed Abdulhalim | -45852 | 38
105-131 | Farasan Island 132/33/13.8 kV | 7038 | Farasan Island 132/33/13.8 kV-Surge Arrestor for substation portion | APPROVED | No | 2025-07-09 | Abas, Mohammed Fekry | 2025-07-14 | 2025-07-14 |  |  |  | 115500 | 7608 | 1 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 48286.8 | REQUIRES REAPPROVAL |  |  |  | 67213.2 | 202 | Abdulqader, Ahmed Abdulhalim | -45852 | -45852
105-131 | Farasan Island 132/33/13.8 kV | 7353 | Farasan Island 132/33/13.8 kV-Farasan -GR-10-05-Addl for transportation (Barge) 1.2.10.5-PO- 7259 | APPROVED | No | 2025-08-13 | Abas, Mohammed Fekry | 2025-08-14 | 2025-08-18 |  |  |  | 2920000 | 7259 | 0 | STANDARD | NAMMA CARGO SERVICES CO LTD - Jeddah | SAR | 2920000 | APPROVED |  |  | 2025-10-21 | 0 | 64 | Babic, Marian | -45887 | 64
105-131 | Farasan Island 132/33/13.8 kV | 7353 | Farasan Island 132/33/13.8 kV-Farasan -GR-10-05-Addl for transportation (Barge) 1.2.10.5-PO- 7259 | APPROVED | No | 2025-08-13 | Abas, Mohammed Fekry | 2025-08-14 | 2025-08-18 |  |  |  | 2920000 | 7259 | 1 | STANDARD | NAMMA CARGO SERVICES CO LTD - Jeddah | SAR | 2920000 | IN PROCESS |  |  |  | 0 | 167 | Babic, Marian | -45887 | -45887
105-131 | Farasan Island 132/33/13.8 kV | 7395 | Lighting Fixture Statcom | APPROVED | No | 2025-08-20 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | PR for the manual PO- 6720 | 0 | 6720 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 19794 | APPROVED |  |  | 2025-09-04 | -19794 | 10 | Abdulqader, Ahmed Abdulhalim | -45894 | 10
105-131 | Farasan Island 132/33/13.8 kV | 7404 | Lighting Fixture Statcom-02 | APPROVED | No | 2025-08-20 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | PR fpr Manual PO 6728 Lighting Fixture Statcom02 | 0 | 6720 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 34726 | APPROVED |  |  | 2025-09-04 | -34726 | 10 | Abdulqader, Ahmed Abdulhalim | -45894 | 10
105-131 | Farasan Island 132/33/13.8 kV | 7423 | Replacment of Damaged GIB | RETURNED | No | 2025-08-22 | Kumar, Mr. Ranjan | 2025-12-01 | 2025-08-25 | 2025-12-01 |  | Please attach a copy of approved POCR (Purchase order Change request) and resubmit the PR. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45894 | -45894
105-131 | Farasan Island 132/33/13.8 kV | 7426 | Lighting Fixture Substation | APPROVED | No | 2025-08-23 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | PO for Lighting Fixture Manual PO-6720 | 0 | 6720 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 75476 | APPROVED |  |  | 2025-09-04 | -75476 | 10 | Abdulqader, Ahmed Abdulhalim | -45894 | 10
105-131 | Farasan Island 132/33/13.8 kV | 7428 | 13.8 KV zig zag grounding Transformer | APPROVED | No | 2025-08-23 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | PR for the manual PO- 6480 | 0 | 6480 | 0 | STANDARD | Koncar- Distribution and Special Transformation d.d.Zagreb | EUR | 2072400 | APPROVED |  |  | 2025-09-08 | -2072400 | 14 | Babic, Marian | -45894 | 14
105-131 | Farasan Island 132/33/13.8 kV | 7429 | Post insulator MV BUS | APPROVED | No | 2025-08-23 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | PR for Power trading which have stock -LAP insulator 6 PCS | 0 | 7639 | 0 | STANDARD | Power Trading T&D | EUR | 20808 | APPROVED |  |  | 2025-09-15 | -20808 | 21 | Abdulqader, Ahmed Abdulhalim | -45894 | 21
105-131 | Farasan Island 132/33/13.8 kV | 7442 | 1000 mm2 33KV CABLE | APPROVED | No | 2025-08-24 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | PR for Manual P0-7560 | 0 | 7560 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 533880 | APPROVED |  |  | 2025-09-08 | -533880 | 14 | Abdulqader, Ahmed Abdulhalim | -45894 | 14
105-131 | Farasan Island 132/33/13.8 kV | 7442 | 1000 mm2 33KV CABLE | APPROVED | No | 2025-08-24 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | PR for Manual P0-7560 | 0 | 7560 | 1 | STANDARD | Riyadh Cables Group Company | SAR | 533880 | REQUIRES REAPPROVAL |  |  |  | -533880 | 160 | Mohammed, Faisal Ansari | -45894 | -45894
105-131 | Farasan Island 132/33/13.8 kV | 7444 | Cable Sealing End | APPROVED | No | 2025-08-24 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | PR for manual PO - 6379 | 0 | 6379 | 0 | STANDARD | PFISTERER Switzerland AG | EUR | 170726.69 | APPROVED |  |  | 2025-09-08 | -170726.69 | 14 | Abdulqader, Ahmed Abdulhalim | -45894 | 14
105-131 | Farasan Island 132/33/13.8 kV | 7446 | Cable sealing End Mobilization | APPROVED | No | 2025-08-24 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | PR for manual PO-6379 | 0 | 6379 | 0 | STANDARD | PFISTERER Switzerland AG | EUR | 7213.44 | APPROVED |  |  | 2025-09-08 | -7213.44 | 14 | Abdulqader, Ahmed Abdulhalim | -45894 | 14
105-131 | Farasan Island 132/33/13.8 kV | 7450 | Aluminuim Tubular basbar | APPROVED | No | 2025-08-24 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | PR for Manual PO-6581 | 0 | 6581 | 0 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 102010.12 | APPROVED |  |  | 2025-09-14 | -102010.12 | 20 | Abdulqader, Ahmed Abdulhalim | -45894 | 20
105-131 | Farasan Island 132/33/13.8 kV | 7452 | Grounding Conductor | APPROVED | No | 2025-08-24 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | PR for manual PO-6608 | 0 | 6608 | 0 | STANDARD | Hesham El-Sewedy Trading Co. LTD. | SAR | 1097304.38 | APPROVED |  |  | 2025-09-24 | -1097304.38 | 30 | Abdulqader, Ahmed Abdulhalim | -45894 | 30
105-131 | Farasan Island 132/33/13.8 kV | 7454 | Lighting pole Lighting Mast | APPROVED | No | 2025-08-24 | Abas, Mohammed Fekry | 2025-08-27 | 2025-08-28 |  | 2025-08-25 | revised with correct quantity | 0 | 7010 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 190190 | APPROVED |  |  | 2025-10-27 | -190190 | 60 | Muaz, Alaa | -45897 | 60
105-131 | Farasan Island 132/33/13.8 kV | 7455 | Conduit and accesories | INCOMPLETE | No | [6 empty] | revised with correct quantity | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | 0 | 0
105-131 | Farasan Island 132/33/13.8 kV | 7456 | Fiber Optic Cable supply and installation, Patch panel and FOMR | APPROVED | No | 2025-08-24 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | PR for supply and installation of Fiber optic | 0 | 7793 | 0 | STANDARD | SMART TECH | SAR | 425000 | APPROVED |  |  | 2025-10-23 | -425000 | 59 | Babic, Marian | -45894 | 59
105-131 | Farasan Island 132/33/13.8 kV | 7467 | Battery and charger for Substation portion | APPROVED | No | 2025-08-25 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | PR for the manual PO-6349 | 0 | 6349 | 0 | STANDARD | Sela for Power, Automation & Safety Systems Co | EUR | 756000 | APPROVED |  |  | 2025-11-04 | -756000 | 71 | Abdulqader, Ahmed Abdulhalim | -45894 | 71
105-131 | Farasan Island 132/33/13.8 kV | 7467 | Battery and charger for Substation portion | APPROVED | No | 2025-08-25 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | PR for the manual PO-6349 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45894 | -45894
105-131 | Farasan Island 132/33/13.8 kV | 7468 | Battery and charger Statcom | APPROVED | No | 2025-08-25 | Abas, Mohammed Fekry | 2025-09-04 | 2025-09-04 | 2025-09-03 |  | raise with diffrent item code since during the merge its showing two lots | 0 | 6349 | 0 | STANDARD | Sela for Power, Automation & Safety Systems Co | EUR | 294000 | APPROVED |  |  | 2025-11-04 | -294000 | 61 | Abdulqader, Ahmed Abdulhalim | -45904 | 61
105-131 | Farasan Island 132/33/13.8 kV | 7468 | Battery and charger Statcom | APPROVED | No | 2025-08-25 | Abas, Mohammed Fekry | 2025-09-04 | 2025-09-04 | 2025-09-03 |  | raise with diffrent item code since during the merge its showing two lots | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45904 | -45904
105-131 | Farasan Island 132/33/13.8 kV | 7470 | ACDB and DCDB , Lighting panels | APPROVED | No | 2025-08-25 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | PR for the manual PO-6279 | 0 | 6279 | 0 | STANDARD | ALFANAR CO | SAR | 1380000 | APPROVED |  |  | 2025-10-23 | -1380000 | 59 | Abdulqader, Ahmed Abdulhalim | -45894 | 59
105-131 | Farasan Island 132/33/13.8 kV | 7471 | Neutral Grounding Resistor Statcom | APPROVED | No | 2025-08-25 | Abas, Mohammed Fekry | 2025-08-25 | 2025-08-25 |  |  | PR for the manula PO- 6365 | 0 | 6365 | 0 | STANDARD | METAL DEPLOYE RESISTOR | EUR | 81110.4 | APPROVED |  |  | 2025-09-07 | -81110.4 | 13 | Abdulqader, Ahmed Abdulhalim | -45894 | 13
105-131 | Farasan Island 132/33/13.8 kV | 7473 | Portacabin | RETURNED | No | 2025-08-25 | Abdulqader, Ahmed Abdulhalim | 2025-09-21 | 2025-08-25 | 2025-09-21 |  | PR is not matching with PO line items | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45894 | -45894
105-131 | Farasan Island 132/33/13.8 kV | 7482 | Wire for modification | RETURNED | No | 2025-08-25 | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | 2025-11-03 | 2025-08-26 | 2025-11-03 |  | will be purchased by petty cash as per PM instructions | 0 | 7814 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 4051.3 | APPROVED |  |  | 2025-10-29 | -4051.3 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -45895 | 64
105-131 | Farasan Island 132/33/13.8 kV | 7482 | Wire for modification | RETURNED | No | 2025-08-25 | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | 2025-11-03 | 2025-08-26 | 2025-11-03 |  | will be purchased by petty cash as per PM instructions | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -45895 | -45895
105-131 | Farasan Island 132/33/13.8 kV | 7483 | Airconidton for site | RETURNED | No | 2025-08-25 | Hegazy, Ayman | 2026-01-19 | 2026-01-14 |  |  | the required amount has been incorporated in CTC | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -46036 | -46036
105-131 | Farasan Island 132/33/13.8 kV | 7484 | Marshaling box for Capacitor bank | APPROVED | No | 2025-08-25 | Abas, Mohammed Fekry | 2025-08-26 | 2025-08-26 |  |  | site requirement | 0 | 7823 | 0 | STANDARD | Energy Tracks For Contracting | SAR | 37205 | APPROVED |  |  | 2025-11-03 | -37205 | 69 | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -45895 | 69
105-131 | Farasan Island 132/33/13.8 kV | 7492 | 132 KV disconnector Swtich | APPROVED | No | 2025-08-25 | Abas, Mohammed Fekry | 2025-08-26 | 2025-08-26 |  |  | PR for the Manual PO-6112 | 0 | 6112 | 0 | STANDARD | ENERGY POWER SERVICE TRADING EST. | EUR | 297840 | APPROVED |  |  | 2025-09-30 | -297840 | 35 | Abdulqader, Ahmed Abdulhalim | -45895 | 35
105-131 | Farasan Island 132/33/13.8 kV | 7492 | 132 KV disconnector Swtich | APPROVED | No | 2025-08-25 | Abas, Mohammed Fekry | 2025-08-26 | 2025-08-26 |  |  | PR for the Manual PO-6112 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45895 | -45895
105-131 | Farasan Island 132/33/13.8 kV | 7493 | Voltage Stabilizer | APPROVED | No | 2025-08-25 | Abas, Mohammed Fekry | 2025-09-15 | 2025-09-16 | 2025-09-14 |  | as requested | 0 | 7214 | 0 | STANDARD | Suzhou Lingfran Electric Co., Ltd | USD | 170625 | APPROVED |  |  | 2025-09-21 | -170625 | 5 | Babic, Marian | -45916 | 5
105-131 | Farasan Island 132/33/13.8 kV | 7494 | Dummy Plug S2 and S3 for SWGR | APPROVED | No | 2025-08-25 | Abas, Mohammed Fekry | 2025-08-26 | 2025-08-26 |  |  | PR for the dummy plug need to amend the orginal PO siemns | 0 | 5317 | 1 | STANDARD | SIEMENS LIMITED | SAR | 81600 | APPROVED | 2026-01-14 | 2026-01-19 | 2026-01-22 | -81600 | 149 | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | 146 | 149
105-131 | Farasan Island 132/33/13.8 kV | 7498 | Water supply | RETURNED | No | 2025-08-26 | Akhtar, Farhan | 2025-10-01 | 2025-09-08 | 2025-10-01 | 2025-08-27 | Repeated PR | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45908 | -45908
105-131 | Farasan Island 132/33/13.8 kV | 7532 | LV control Cables | APPROVED | No | 2025-08-27 | Abas, Mohammed Fekry | 2025-09-01 | 2025-09-01 |  |  | PR for the manual PO- 6667 | 0 | 6667 | 0 | STANDARD | ALFANAR CO | SAR | 1163416.97 | APPROVED |  |  | 2025-10-28 | -1163416.97 | 57 | Abdulqader, Ahmed Abdulhalim | -45901 | 57
105-131 | Farasan Island 132/33/13.8 kV | 7568 | Supply of diesel | APPROVED | No | 2025-08-28 | Abas, Mohammed Fekry | 2025-08-30 | 2025-08-31 |  |  | For site requirement | 0 | 7250 | 0 | STANDARD | The Fishermen's Investment Cooperative Society | SAR | 50000 | APPROVED |  |  | 2025-10-14 | -50000 | 44 | Akhtar, Farhan | -45900 | 44
105-131 | Farasan Island 132/33/13.8 kV | 7572 | Addtional Cable Tray | APPROVED | No | 2025-08-31 | Abas, Mohammed Fekry | 2025-09-01 | 2025-09-01 |  |  | PR for Manual PO - 7617 additional cable tray | 0 | 7617 | 0 | STANDARD | Power Solution Industries | SAR | 12030.68 | APPROVED |  |  | 2025-09-16 | -12030.68 | 15 | Muaz, Alaa | -45901 | 15
105-131 | Farasan Island 132/33/13.8 kV | 7574 | LV power cables | APPROVED | No | 2025-08-31 | Abas, Mohammed Fekry | 2025-09-01 | 2025-09-01 |  |  | PR for the manual PO- 7566 | 0 | 7566 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 839132.41 | IN PROCESS |  |  |  | -839132.41 | 153 | Abdulqader, Ahmed Abdulhalim | -45901 | -45901
105-131 | Farasan Island 132/33/13.8 kV | 7574 | LV power cables | APPROVED | No | 2025-08-31 | Abas, Mohammed Fekry | 2025-09-01 | 2025-09-01 |  |  | PR for the manual PO- 7566 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45901 | -45901
105-131 | Farasan Island 132/33/13.8 kV | 7584 | Buidling lighting Wire | APPROVED | No | 2025-08-31 | Abas, Mohammed Fekry | 2025-09-01 | 2025-09-01 |  |  | PR for the Manual PO- 7385 | 0 | 7385 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 119467.62 | APPROVED |  |  | 2025-09-14 | -119467.62 | 13 | Abdulqader, Ahmed Abdulhalim | -45901 | 13
105-131 | Farasan Island 132/33/13.8 kV | 7586 | Grounding Material | APPROVED | No | 2025-08-31 | Abas, Mohammed Fekry | 2025-09-01 | 2025-09-01 |  |  | PR for the manual PO- 6612 | 0 | 6612 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 362800 | APPROVED |  |  | 2025-09-24 | -362800 | 23 | Abdulqader, Ahmed Abdulhalim | -45901 | 23
105-131 | Farasan Island 132/33/13.8 kV | 7587 | RTV Coating for Substation and Statcom | APPROVED | No | 2025-08-31 | Alfaiya, Majed | 2025-12-26 | 2025-12-26 | 2025-12-14 | 2025-08-31 | becouse the PR is Lump., and we need new PR to be itemized as per approved Po | 0 | 7938 | 0 | STANDARD | Y.S.G Global Arabia Contracting Co. | SAR | 249999.9 | APPROVED | 2025-12-30 | 2026-01-19 | 2026-01-21 | -249999.9 | 26 | Mohammed, Mohammed Adel Fahmy | 24 | 26
105-131 | Farasan Island 132/33/13.8 kV | 7588 | Cable Cleats | INCOMPLETE | No | [6 empty] | becouse the PR is Lump., and we need new PR to be itemized as per approved Po | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | 0 | 0
105-131 | Farasan Island 132/33/13.8 kV | 7595 | 45 KV Grounding transformer and related equipment | RETURNED | No | 2025-08-31 | Abdulqader, Ahmed Abdulhalim | 2025-09-18 | 2025-09-04 | 2025-09-18 |  | in order to proceed with variation with NR approved POCR shall be received | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45904 | -45904
105-131 | Farasan Island 132/33/13.8 kV | 7598 | clamps & Connector for Aluminuim Tublar busbar, conductor | APPROVED | No | 2025-09-01 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-04 |  |  | 1.4.3.2.1.1 task and itemized PR for PO- 7615 | 0 | 7615 | 0 | STANDARD | Arruti Subestaciones , S.A.U | EUR | 87020.8 | APPROVED |  |  | 2025-09-24 | -87020.8 | 20 | Abdulqader, Ahmed Abdulhalim | -45904 | 20
105-131 | Farasan Island 132/33/13.8 kV | 7601 | HV & MV Cable Clamps | APPROVED | No | 2025-09-01 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-04 |  |  | PR-6039 Cancelled and make new itemized PR | 0 | 7139 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 144425 | APPROVED |  |  | 2025-09-17 | -144425 | 13 | Hegazy, Ayman | -45904 | 13
105-131 | Farasan Island 132/33/13.8 kV | 7603 | Additional Lighting fixture for raised floor | APPROVED | No | 2025-09-01 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-04 |  |  | addtional lighting fixture as per sec comment | 0 | 6720 | 1 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 4804 | APPROVED |  |  | 2025-10-15 | -4804 | 41 | Abdulqader, Ahmed Abdulhalim | -45904 | 41
105-131 | Farasan Island 132/33/13.8 kV | 7605 | Geo phyiscal study | APPROVED | No | 2025-09-01 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-04 |  |  | PR for the maual PO- 6257 | 0 | 6680 | 0 | STANDARD | Applus Arabia for Geotechnical And Environmental Works Co. Ltd | SAR | 81000 | APPROVED |  |  | 2025-10-09 | -81000 | 35 | Alhadi, Khalid | -45904 | 35
105-131 | Farasan Island 132/33/13.8 kV | 7631 | Installation for statcom and substation | INCOMPLETE | No | [6 empty] | PR for the maual PO- 6257 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | 0 | 0
105-131 | Farasan Island 132/33/13.8 kV | 7634 | GEO Physical Survey after Pressure grouting | REJECTED | No | 2025-09-03 | Yamama, Loai Mohamed | 2025-09-04 | 2025-09-03 |  | 2025-09-04 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45903 | -45903
105-131 | Farasan Island 132/33/13.8 kV | 7636 | installation for Substation and statcom portion | APPROVED | No | 2025-09-03 | Abas, Mohammed Fekry | 2025-09-04 | 2025-09-04 |  |  | PR for Installation | 0 | 7446 | 0 | STANDARD | Intelligent System General Contracting Company | SAR | 5200000 | APPROVED |  |  | 2025-09-24 | -5200000 | 20 | Babic, Marian | -45904 | 20
105-131 | Farasan Island 132/33/13.8 kV | 7659 | Supply drinking water , waste water Removal, and | APPROVED | No | 2025-09-07 | Abas, Mohammed Fekry | 2025-09-09 | 2025-09-10 |  |  | New PR | 0 | 6765 | 1 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 51000 | APPROVED |  |  | 2025-11-11 | -51000 | 62 | Akhtar, Farhan | -45910 | 62
105-131 | Farasan Island 132/33/13.8 kV | 7660 | addon qunatity for PR 7574 LV power cable | APPROVED | No | 2025-09-07 | Abas, Mohammed Fekry | 2025-09-09 | 2025-09-10 |  |  | addon quantity 0f 114 meters for PR-7574 | 0 | 7566 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 10470.23 | IN PROCESS |  |  |  | -10470.23 | 144 | Abdulqader, Ahmed Abdulhalim | -45910 | -45910
105-131 | Farasan Island 132/33/13.8 kV | 7660 | addon qunatity for PR 7574 LV power cable | APPROVED | No | 2025-09-07 | Abas, Mohammed Fekry | 2025-09-09 | 2025-09-10 |  |  | addon quantity 0f 114 meters for PR-7574 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45910 | -45910
105-131 | Farasan Island 132/33/13.8 kV | 7736 | Technician for Testing | APPROVED | No | 2025-09-14 |  |  | 2026-01-13 | 2025-10-12 |  | Exceeding the budget and wrong quantity | 0 | 7748 | 0 | STANDARD | Jasem M.AlJasem Contracting Est. | SAR | 312000 | APPROVED | 2026-01-14 | 2026-01-19 | 2026-01-21 | -312000 | 8 | Alhadi, Khalid | 6 | 8
105-131 | Farasan Island 132/33/13.8 kV | 7786 | Stationary | RETURNED | No | 2025-09-17 | Akhtar, Farhan | 2025-10-13 | 2025-09-21 | 2025-10-13 |  | Not Budget in the PR | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45921 | -45921
105-131 | Farasan Island 132/33/13.8 kV | 7803 | SAS console Desk | APPROVED | No | 2025-09-21 | Abas, Mohammed Fekry | 2025-12-29 | 2026-01-01 | 2025-10-26 |  | No Budget Available to cover the PO Value | 0 | 6803 | 0 | STANDARD | ALFANAR CO | SAR | 55000 | APPROVED | 2026-01-11 | 2026-01-13 | 2026-01-15 | -55000 | 14 | Hegazy, Ayman | 12 | 14
105-131 | Farasan Island 132/33/13.8 kV | 7822 | Wiring Devices revised | APPROVED | No | 2025-09-28 | Abas, Mohammed Fekry | 2025-10-01 | 2025-10-02 |  |  | Previous PR cancelled , revised according to procurement team | 0 | 6989 | 0 | STANDARD | Tawasul International Trad.Est. | SAR | 220678.15 | APPROVED |  |  | 2025-10-28 | -220678.15 | 26 | Muaz, Alaa | -45932 | 26
105-131 | Farasan Island 132/33/13.8 kV | 7840 | Portacabine with complete setup | APPROVED | No | 2025-09-27 | Abas, Mohammed Fekry | 2026-01-12 | 2026-01-13 | 2025-12-23 |  | PR has no budget to proceed with oracle PO | 0 | 7730 | 0 | STANDARD | Al Arab Modern Contracting Est | SAR | 0 | INCOMPLETE |  |  |  | 0 | 19 | Abdulqader, Ahmed Abdulhalim | -46035 | -46035
105-131 | Farasan Island 132/33/13.8 kV | 7840 | Portacabine with complete setup | APPROVED | No | 2025-09-27 | Abas, Mohammed Fekry | 2026-01-12 | 2026-01-13 | 2025-12-23 |  | PR has no budget to proceed with oracle PO | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46035 | -46035
105-131 | Farasan Island 132/33/13.8 kV | 7841 | Duplex paiting for lighiting pole and Mast | APPROVED | No | 2025-09-27 | Abas, Mohammed Fekry | 2025-09-28 | 2025-09-28 |  |  |  | 0 | 7741 | 0 | STANDARD | Zamil Industrial Coatings Factory Ltd. Company | SAR | 53264.6 | APPROVED |  |  | 2025-10-29 | -53264.6 | 31 | Muaz, Alaa | -45928 | 31
105-131 | Farasan Island 132/33/13.8 kV | 7842 | 13.8 KV outdoor busbar - Statcom | APPROVED | No | 2025-09-27 | Abas, Mohammed Fekry | 2025-09-28 | 2025-09-28 |  |  |  | 0 | 7885 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 6295.95 | APPROVED |  |  | 2025-12-21 | -6295.95 | 84 | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -45928 | 84
105-131 | Farasan Island 132/33/13.8 kV | 7847 | Inspection for Neutral grounding Transformer | APPROVED | No | 2025-09-28 | Abas, Mohammed Fekry | 2025-09-29 | 2025-10-02 |  |  | Due to urgeceny of the project ,we book the inspector as lumsump 3315 for three days as per Blanket it is =860*3=2580 plus travlling allowance. Croatia NGR | 0 | 7786 | 0 | STANDARD | SGS GULF LIMITED | USD | 12431.25 | APPROVED |  |  | 2025-10-14 | -12431.25 | 12 | Akhtar, Farhan | -45932 | 12
105-131 | Farasan Island 132/33/13.8 kV | 7941 | Lighting Conduit and accesories | APPROVED | No | 2025-10-27 | Abas, Mohammed Fekry | 2025-12-29 | 2026-01-01 | 2025-11-12 |  | to update according to the Ack. PO | 0 | 7835 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 389339.27 | APPROVED | 2026-01-15 | 2026-01-19 | 2026-01-21 | -389339.27 | 20 | Hegazy, Ayman | 18 | 20
105-131 | Farasan Island 132/33/13.8 kV | 8000 | 33KV MV Termination suitable for 1000mm2 cable | APPROVED | No | 2025-10-20 | Alfaiya, Majed | 2025-12-26 | 2025-12-26 |  |  | Will remove this item from NKT PO | 0 | 7846 | 0 | STANDARD |  | SAR | 0 | INCOMPLETE |  |  |  | 0 | 37 | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46017 | -46017
105-131 | Farasan Island 132/33/13.8 kV | 8000 | 33KV MV Termination suitable for 1000mm2 cable | APPROVED | No | 2025-10-20 | Alfaiya, Majed | 2025-12-26 | 2025-12-26 |  |  | Will remove this item from NKT PO | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46017 | -46017
105-131 | Farasan Island 132/33/13.8 kV | 8388 | Copper Busbar | APPROVED | No | 2025-11-30 | Abas, Mohammed Fekry | 2025-12-02 | 2025-12-02 |  |  | addtion to PR-7842 | 0 | 7885 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 2098.65 | APPROVED |  |  | 2025-12-21 | -2098.65 | 19 | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -45993 | 19
105-131 | Farasan Island 132/33/13.8 kV | 8389 | 7x6 mm contorl cable | RETURNED | No | 2025-11-29 | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | 2025-12-22 | 2025-12-02 | 2025-12-22 |  | No Technical data received and not following PR criteria, please raise PR with all cable requirements and technical specs as instructed by PMT | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45993 | -45993
105-131 | Farasan Island 132/33/13.8 kV | 8390 | Fire Retardent paint for MV cables | APPROVED | No | 2025-11-29 | Abas, Mohammed Fekry | 2025-12-02 | 2025-12-02 |  |  | Fire retardent paint for MV cables | 0 | 8025 | 0 | STANDARD |  | SAR | 0 | INCOMPLETE |  |  |  | 0 | 61 | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -45993 | -45993
105-131 | Farasan Island 132/33/13.8 kV | 8390 | Fire Retardent paint for MV cables | APPROVED | No | 2025-11-29 | Abas, Mohammed Fekry | 2025-12-02 | 2025-12-02 |  |  | Fire retardent paint for MV cables | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -45993 | -45993
105-131 | Farasan Island 132/33/13.8 kV | 8520 | Remote end -132 KV free standing CT | IN PROCESS | No | 2025-12-15 | Ahmed, Ahmed Salah Ahmed Mohamed | 2025-12-18 | 2025-12-16 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -46007 | -46007
105-131 | Farasan Island 132/33/13.8 kV | 8528 | PDS System | APPROVED | No | 2025-12-16 | Abas, Mohammed Fekry | 2025-12-18 | 2025-12-18 |  |  | SEC has given the comment to provide the PDS system , in IP telephony submital | 0 | 15053 | 0 | STANDARD |  | SAR | 0 | INCOMPLETE |  |  |  | 0 | 45 | Alhadi, Khalid | -46009 | -46009
105-131 | Farasan Island 132/33/13.8 kV | 8528 | PDS System | APPROVED | No | 2025-12-16 | Abas, Mohammed Fekry | 2025-12-18 | 2025-12-18 |  |  | SEC has given the comment to provide the PDS system , in IP telephony submital | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46009 | -46009
105-131 | Farasan Island 132/33/13.8 kV | 8599 | Control Cable NR-Shortage | APPROVED | No | 2025-12-28 | Abas, Mohammed Fekry | 2026-01-04 | 2026-01-06 |  |  | Shortage for Substation , Statcom and NR scope ( not considered before) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46028 | -46028
105-131 | Farasan Island 132/33/13.8 kV | 8600 | LV DC cables | IN PROCESS | No | 2025-12-28 | Ahmed, Ahmed Salah Ahmed Mohamed | 2025-12-30 | 2025-12-29 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46020 | -46020
105-131 | Farasan Island 132/33/13.8 kV | 8601 | LV AC cables NR portion | IN PROCESS | No | 2025-12-28 | Ahmed, Ahmed Salah Ahmed Mohamed | 2025-12-30 | 2025-12-29 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46020 | -46020
105-131 | Farasan Island 132/33/13.8 kV | 8602 | MV Cable 1000mm2 shortage | APPROVED | No | 2025-12-29 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 | 2026-01-25 | 2026-01-06 | Please change the quantity to 520 meters to match the PO quantity. | 0 | 7560 | 1 | STANDARD | Riyadh Cables Group Company | SAR | 293582.6 | REQUIRES REAPPROVAL |  |  |  | -293582.6 | 4 | Mohammed, Faisal Ansari | -46050 | -46050
105-131 | Farasan Island 132/33/13.8 kV | 8602 | MV Cable 1000mm2 shortage | APPROVED | No | 2025-12-29 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 | 2026-01-25 | 2026-01-06 | Please change the quantity to 520 meters to match the PO quantity. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46050 | -46050
105-131 | Farasan Island 132/33/13.8 kV | 8670 | Testing Technicaian MTF | APPROVED | No | 2026-01-08 |  |  | 2026-01-13 |  |  | BEF-75 approved and baslinied | 0 | 7830 | 0 | STANDARD | Modern Technical Fields Contracting Est | SAR | 226200 | APPROVED | 2026-01-13 | 2026-01-14 | 2026-01-20 | -226200 | 7 | Babic, Marian | 1 | 7
105-131 | Farasan Island 132/33/13.8 kV | 8693 | Modified Battery rack | IN PROCESS | No | 2026-01-12 | Ahmed, Ahmed Salah Ahmed Mohamed | 2026-01-14 | 2026-01-12 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46034 | -46034
105-131 | Farasan Island 132/33/13.8 kV | 8717 | Oil Sample Testing LAB | IN PROCESS | No | 2026-01-15 | Ahmed, Ahmed Salah Ahmed Mohamed | 2026-01-18 | 2026-01-15 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46037 | -46037
105-131 | Farasan Island 132/33/13.8 kV | 8720 | Transportion of Transformer from Dammam to Farasan | APPROVED | No | 2026-01-15 | Abas, Mohammed Fekry | 2026-01-19 | 2026-01-20 |  |  | For Namma Cargo Transfomrer transporation from DAMMAM to Farasan | 0 | 7259 | 1 | STANDARD | NAMMA CARGO SERVICES CO LTD - Jeddah | SAR | 538225 | IN PROCESS |  |  |  | -538225 | 12 | Babic, Marian | -46042 | -46042
105-131 | Farasan Island 132/33/13.8 kV | 8720 | Transportion of Transformer from Dammam to Farasan | APPROVED | No | 2026-01-15 | Abas, Mohammed Fekry | 2026-01-19 | 2026-01-20 |  |  | For Namma Cargo Transfomrer transporation from DAMMAM to Farasan | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46042 | -46042
105-131 | Farasan Island 132/33/13.8 kV | 8817 | TFR configration for Remote End | IN PROCESS | No | 2026-01-28 | Abas, Mohammed Fekry | 2026-01-29 | 2026-01-29 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46051 | -46051
105-132 | INSTALLATION OF 67MVA JMC SS | 3682 | INSTALLATION OF 67MVA JMC SS-Power Transformer | APPROVED | No | 2024-06-26 | Abas, Mohammed Fekry | 2024-06-30 | 2024-06-30 |  |  |  | 5100000 | 5758 | 0 | STANDARD | VOLTAMP POWER SAOC | USD | 4661250 | APPROVED |  |  | 2024-07-25 | 438750 | 25 | Muhammad, Muhammad Atif | -45473 | 25
105-132 | INSTALLATION OF 67MVA JMC SS | 3683 | INSTALLATION OF 67MVA JMC SS-Design & Engineering | REJECTED | No | 2024-06-26 | Khalid, Saber Mohammed | 2024-07-01 | 2024-06-30 | 2024-07-01 | 2024-07-01 | The quantity is inaccurate. | 150000 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45473 | -45473
105-132 | INSTALLATION OF 67MVA JMC SS | 3711 | INSTALLATION OF 67MVA JMC SS-Supervision of Transformer installation and testing | APPROVED | No | 2024-07-01 | Abas, Mohammed Fekry | 2024-07-07 | 2024-07-07 |  |  |  | 26500 | 5758 | 0 | STANDARD | VOLTAMP POWER SAOC | USD | 26250 | APPROVED |  |  | 2024-07-25 | 250 | 18 | Muhammad, Muhammad Atif | -45480 | 18
105-132 | INSTALLATION OF 67MVA JMC SS | 3713 | INSTALLATION OF 67MVA JMC SS-Design and Engineering | APPROVED | No | 2024-07-01 | Abas, Mohammed Fekry | 2024-07-07 | 2024-07-07 |  |  |  | 70000 | 5759 | 0 | STANDARD | JAWDA ENGINEERING CONSUL | SAR | 60000 | APPROVED |  |  | 2024-07-12 | 10000 | 5 | Alhadi, Khalid | -45480 | 5
105-132 | INSTALLATION OF 67MVA JMC SS | 4620 | INSTALLATION OF 67MVA JMC SS-132KV Cable sealing end | APPROVED | No | 2024-10-07 | Abas, Mohammed Fekry | 2025-04-15 | 2025-04-15 | 2025-01-22 |  | The PR value is less than the PO value. Please amend the PR value to match with the PO value. | 78777.6 | 6699 | 0 | STANDARD | PFISTERER Switzerland AG | EUR | 78669.24 | APPROVED |  |  | 2025-04-22 | 108.36 | 7 | Mohammed, Faisal Ansari | -45762 | 7
105-132 | INSTALLATION OF 67MVA JMC SS | 4621 | INSTALLATION OF 67MVA JMC SS-MV Termination Kit | REJECTED | No | 2024-10-07 | Ghith, Saad Gamal | 2024-10-07 |  |  | 2024-10-14 |  | 20800 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-132 | INSTALLATION OF 67MVA JMC SS | 4846 | INSTALLATION OF 67MVA JMC SS-HV & MV cables | APPROVED | No | 2024-11-06 | Abas, Mohammed Fekry | 2024-11-10 | 2024-11-11 |  |  |  | 478160 | 6462 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 430966 | APPROVED |  |  | 2025-07-10 | 47194 | 241 | Badhman, Saeed | -45607 | 241
105-132 | INSTALLATION OF 67MVA JMC SS | 5056 | INSTALLATION OF 67MVA JMC SS-JMC - MV Termination Kits | APPROVED | No | 2024-11-26 | Abas, Mohammed Fekry | 2024-12-03 | 2024-12-03 |  |  |  | 45190 | 6557 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 34190 | APPROVED |  |  | 2024-12-12 | 11000 | 9 | Mohammed, Faisal Ansari | -45629 | 9
105-132 | INSTALLATION OF 67MVA JMC SS | 5630 | INSTALLATION OF 67MVA JMC SS-JMC - Link Box | RETURNED | No | 2025-01-27 | Alhadi, Khalid | 2025-04-24 | 2025-02-11 |  |  |  | 10000 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45699 | -45699
105-132 | INSTALLATION OF 67MVA JMC SS | 5631 | INSTALLATION OF 67MVA JMC SS-JMC - Bonding Cable | REJECTED | No | 2025-01-27 | Khalid, Saber Mohammed | 2025-02-09 | 2025-02-02 | 2025-02-09 | 2025-02-09 | The required size is not identified | 2000 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45690 | -45690
105-132 | INSTALLATION OF 67MVA JMC SS | 5632 | INSTALLATION OF 67MVA JMC SS-JMC - Installation of CSE | APPROVED | No | 2025-01-27 | Abas, Mohammed Fekry | 2025-04-15 | 2025-04-15 |  |  |  | 66250.16 | 6699 | 0 | STANDARD | PFISTERER Switzerland AG | EUR | 125458.49 | APPROVED |  |  | 2025-04-22 | -59208.33 | 7 | Mohammed, Faisal Ansari | -45762 | 7
105-132 | INSTALLATION OF 67MVA JMC SS | 5837 | INSTALLATION OF 67MVA JMC SS-JMC - Bonding Cable 300mm2 | RETURNED | No | 2025-02-09 | Alhadi, Khalid | 2025-07-23 | 2025-02-11 | 2025-07-23 |  | It will be included with installation PO | 6000 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45699 | -45699
105-132 | INSTALLATION OF 67MVA JMC SS | 6456 | INSTALLATION OF 67MVA JMC SS-JMC- Link box | APPROVED | No | 2025-04-27 | Abas, Mohammed Fekry | 2025-04-28 | 2025-04-28 |  |  |  | 10800 | 7213 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 10800 | APPROVED |  |  | 2025-05-18 | 0 | 20 | Alhadi, Khalid | -45775 | 20
105-132 | INSTALLATION OF 67MVA JMC SS | 6684 | INSTALLATION OF 67MVA JMC SS-JMC - Power Transformer Rails And steel cable support | RETURNED | No | 2025-05-22 | Alhadi, Khalid | 2025-06-04 | 2025-05-26 | 2025-06-04 |  | please send complete details and dimensions for cable support and transformer rail | 50000 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45803 | -45803
105-132 | INSTALLATION OF 67MVA JMC SS | 6815 | INSTALLATION OF 67MVA JMC SS-JMC - PR for Subcontractor for Instaaltion works | RETURNED | No | 2025-06-17 | Alhadi, Khalid | 2025-07-23 | 2025-06-25 |  |  | Kindly refer to mail sent on 22 June | 150000 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45833 | -45833
105-132 | INSTALLATION OF 67MVA JMC SS | 7244 | INSTALLATION OF 67MVA JMC SS-Installation | REJECTED | No | 2025-07-30 | Khalid, Saber Mohammed | 2025-07-30 |  |  | 2025-07-30 |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
105-132 | INSTALLATION OF 67MVA JMC SS | 7245 | INSTALLATION OF 67MVA JMC SS-Installation of Jazan medical city | RETURNED | No | 2025-07-30 | Alhadi, Khalid | 2025-11-24 | 2025-08-10 | 2025-11-24 |  | It will be implemented though InHouse approache - PR was utilized under rejected PO | 275000 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45879 | -45879
105-132 | INSTALLATION OF 67MVA JMC SS | 7995 | Power Transformer Rail | RETURNED | No | 2025-10-19 | Alhadi, Khalid | 2025-11-11 | 2025-10-25 | 2025-11-11 |  | PR is not sufficint, another PR was submitted | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45955 | -45955
105-132 | INSTALLATION OF 67MVA JMC SS | 7996 | Cable Supports | RETURNED | No | 2025-10-19 | Alhadi, Khalid | 2025-11-09 | 2025-10-25 | 2025-11-09 |  | It will be an optional scope with Transformer rail | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45955 | -45955
105-132 | INSTALLATION OF 67MVA JMC SS | 7997 | Cable Cleats (Clamps) | RETURNED | No | 2025-10-19 | Alhadi, Khalid | 2025-11-09 | 2025-10-27 | 2025-11-09 |  | It will be secured through Pitty Cash or with Rail PO. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45957 | -45957
105-132 | INSTALLATION OF 67MVA JMC SS | 7998 | Bonding Cables | RETURNED | No | 2025-10-19 | Alhadi, Khalid | 2025-11-09 | 2025-10-25 | 2025-11-09 |  | It will be secured internally OR MOQ | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45955 | -45955
105-132 | INSTALLATION OF 67MVA JMC SS | 7999 | Cable Stand | RETURNED | No | 2025-10-19 | Alhadi, Khalid | 2025-11-09 | 2025-10-25 | 2025-11-09 |  | It is related to different project. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45955 | -45955
105-132 | INSTALLATION OF 67MVA JMC SS | 8104 | Oil Filteration Machine | RETURNED | No | 2025-11-02 | Alhadi, Khalid | 2025-11-09 | 2025-11-06 | 2025-11-09 |  | According to PM, it will be secured internally | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45967 | -45967
105-132 | INSTALLATION OF 67MVA JMC SS | 8148 | Power Transformer Rails | APPROVED | No | 2025-11-06 | Abas, Mohammed Fekry | 2025-11-09 | 2025-11-09 |  |  |  | 0 | 7881 | 0 | STANDARD | Construction Expertise Est. | SAR | 25000 | APPROVED |  |  | 2025-11-19 | -25000 | 10 | Alhadi, Khalid | -45970 | 10
105-132 | INSTALLATION OF 67MVA JMC SS | 8160 | Testing and Comissioning | APPROVED | No | 2025-11-09 | Abas, Mohammed Fekry | 2025-11-15 | 2025-11-16 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45977 | -45977
105-132 | INSTALLATION OF 67MVA JMC SS | 8304 | Security Services - JMC | APPROVED | No | 2025-11-20 | Abas, Mohammed Fekry | 2025-12-03 | 2025-12-03 | 2025-11-30 |  | dut to change the budget | 23200 | 7955 | 0 | STANDARD | Al-Nufuth Al-Mutamayiza For Security Company | SAR | 23200 | APPROVED |  |  | 2025-12-29 | 0 | 26 | Abuhammad, Samir | -45994 | 26
105-132 | INSTALLATION OF 67MVA JMC SS | 8524 | Transformer Offloading | APPROVED | No | 2025-12-15 | Abas, Mohammed Fekry | 2025-12-20 | 2025-12-21 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -46012 | -46012
105-132 | INSTALLATION OF 67MVA JMC SS | 8763 | Security services -JMC | APPROVED | No | 2026-01-21 | Abas, Mohammed Fekry | 2026-01-25 | 2026-01-26 |  |  | increase one security guard at JMC | 0 | 7955 | 1 | STANDARD | Al-Nufuth Al-Mutamayiza For Security Company | SAR | 34800 | IN PROCESS | 2026-01-27 | 2026-01-28 |  | -34800 | 6 | Abuhammad, Samir | 2 | -46048
105-132 | INSTALLATION OF 67MVA JMC SS | 8763 | Security services -JMC | APPROVED | No | 2026-01-21 | Abas, Mohammed Fekry | 2026-01-25 | 2026-01-26 |  |  | increase one security guard at JMC | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46048 | -46048
105-133 | ADDITION OF SG FOR TAIBAH UNIV | 3154 | ADDITION OF SG FOR TAIBAH UNIV-13.8kV MV SWGR - Taiba Uni Extension Project | RETURNED | No | 2024-04-26 | Alhadi, Khalid | 2024-09-09 | 2024-04-29 | 2024-09-09 |  | As per PM confirmation | 653632.44 | 5512 | 0 | STANDARD | ALFANAR CO | SAR | 545000 | APPROVED |  |  | 2024-07-15 | 108632.44 |  | Muhammad, Muhammad Atif | -45411 | 77
105-133 | ADDITION OF SG FOR TAIBAH UNIV | 3155 | ADDITION OF SG FOR TAIBAH UNIV-SCADA System - TAIBA University Extension Project | APPROVED | No | 2024-04-26 | Abas, Mohammed Fekry | 2024-04-29 | 2024-04-29 |  |  |  | 1100000 | 5846 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 680000 | APPROVED |  |  | 2024-08-11 | 420000 | 104 | Muhammad, Muhammad Atif | -45411 | 104
105-133 | ADDITION OF SG FOR TAIBAH UNIV | 3156 | ADDITION OF SG FOR TAIBAH UNIV-Protection system - Taiba University Extension Project | APPROVED | No | 2024-04-26 | Abas, Mohammed Fekry | 2024-04-29 | 2024-04-29 |  |  |  | 434498.84 | 5513 | 0 | STANDARD | ALFANAR CO | SAR | 415000 | APPROVED |  |  | 2024-07-17 | 19498.84 | 79 | Muhammad, Muhammad Atif | -45411 | 79
105-133 | ADDITION OF SG FOR TAIBAH UNIV | 4819 | ADDITION OF SG FOR TAIBAH UNIV-Taiba University Extension Project: Engineering & Design Services | APPROVED | No | 2024-10-31 | Abas, Mohammed Fekry | 2024-11-05 | 2024-11-05 |  |  |  | 125000 | 5763 | 0 | STANDARD | JAWDA ENGINEERING CONSUL | SAR | 125000 | APPROVED |  |  | 2024-12-26 | 0 | 51 | Alhadi, Khalid | -45601 | 51
105-133 | ADDITION OF SG FOR TAIBAH UNIV | 5121 | ADDITION OF SG FOR TAIBAH UNIV-TAIBA Extension Project: Testing & Comissioning Service | APPROVED | No | 2024-12-03 | Abas, Mohammed Fekry | 2024-12-04 | 2024-12-04 |  |  |  | 200000 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45630 | -45630
105-133 | ADDITION OF SG FOR TAIBAH UNIV | 7794 | Control and LV Cables | RETURNED | No | 2025-09-18 | Alhadi, Khalid | 2025-11-09 | 2025-09-23 | 2025-11-09 |  | The defined Manufactures don't match with available quantity in the market. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45923 | -45923
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3240 | CONS OF JAZERA ROYAL PALACE SS-Test PR Construction of Aljazera S/S | REJECTED | No | 2024-05-01 | Alnaeem, Rami Mayraghany alkaram | 2024-05-03 | 2024-05-01 |  | 2024-05-01 |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45413 | -45413
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3244 | CONS OF JAZERA ROYAL PALACE SS-Test PR for ALjazera Project | REJECTED | No | 2024-07-28 | Yamama, Loai Mohamed | 2024-07-29 |  |  | 2024-07-29 | Rejected as per Eng Ahmed Elthubati Request | 40000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3284 | CONS OF JAZERA ROYAL PALACE SS-NTT-Projects Services-Design adn Engineering | APPROVED | No | 2024-05-04 | Abas, Mohammed Fekry | 2024-05-06 | 2024-05-06 |  |  |  | 1400000 | 5577 | 0 | STANDARD | BAHRAWY Gulf CONSULTANCY GROUP | SAR | 1150000 | APPROVED |  |  | 2024-05-29 | 250000 | 23 | Kumar, Mr. Ranjan | -45418 | 23
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3298 | CONS OF JAZERA ROYAL PALACE SS-110 KV Gas Insulated Switchgeat (GIS) | REJECTED | No | 2024-05-05 | Issa, Amr Ali | 2024-05-23 | 2024-05-23 |  | 2024-05-23 |  | 16544000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45435 | -45435
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3341 | CONS OF JAZERA ROYAL PALACE SS-Geotechnical investigations for substation-PO#8683-1.3.4.1.1.1---1.4.3.1.1.1 | APPROVED | No | 2024-05-08 | Abas, Mohammed Fekry | 2024-05-12 | 2024-05-12 |  |  |  | 107160 | 5725 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 107160 | APPROVED |  |  | 2024-07-10 | 0 | 59 | Alhadi, Khalid | -45424 | 59
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3344 | CONS OF JAZERA ROYAL PALACE SS-PO#8684-1.3.4.1.1.1-1.4.3.1.1.1 | APPROVED | No | 2024-05-08 | Abas, Mohammed Fekry | 2024-05-12 | 2024-05-12 |  |  |  | 150000.02 | 5726 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 150000.02 | APPROVED |  |  | 2024-07-10 | 0 | 59 | Alhadi, Khalid | -45424 | 59
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3344 | CONS OF JAZERA ROYAL PALACE SS-PO#8684-1.3.4.1.1.1-1.4.3.1.1.1 | APPROVED | No | 2024-05-08 | Abas, Mohammed Fekry | 2024-05-12 | 2024-05-12 |  |  |  | 150000.02 | 5726 | 1 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 150000.02 | REQUIRES REAPPROVAL |  |  |  | 0 | 630 | Alhadi, Khalid | -45424 | -45424
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3345 | CONS OF JAZERA ROYAL PALACE SS-PO#8685-1.4.3.1.1.1 | REJECTED | No | 2024-05-08 | Moussa, Mohamed Fathi | 2024-05-23 | 2024-05-08 |  | 2024-05-29 |  | 240000.01 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45420 | -45420
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3454 | CONS OF JAZERA ROYAL PALACE SS-AMI, Protection, Control & SAS Including Remote end SAS/Scada modification | REJECTED | No | 2024-05-21 | Alnaeem, Rami Mayraghany alkaram | 2024-05-21 |  |  | 2024-05-21 |  | 2500000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3458 | CONS OF JAZERA ROYAL PALACE SS-GIS Jazera SS-HICO- ACK | REJECTED | No | 2024-05-21 | Alnaeem, Rami Mayraghany alkaram | 2024-05-21 |  |  | 2024-05-21 |  | 2000000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3460 | CONS OF JAZERA ROYAL PALACE SS-GIS Jazera SS-HICO- ACK | REJECTED | No | 2024-05-21 | Alnaeem, Rami Mayraghany alkaram | 2024-05-21 |  |  | 2024-05-21 |  | 20000000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3463 | CONS OF JAZERA ROYAL PALACE SS-1.3.3.1.1.1- | REJECTED | No | 2024-05-21 | Alnaeem, Rami Mayraghany alkaram | 2024-05-21 |  |  | 2024-05-21 |  | 16544000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3482 | CONS OF JAZERA ROYAL PALACE SS-8692-HV1577-0 13.8 MV Switchgear Jazera -Al Fanar | REJECTED | No | 2024-05-23 | Moussa, Mohamed Fathi | 2024-05-23 | 2024-05-23 |  | 2024-05-29 |  | 6514750 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45435 | -45435
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3521 | CONS OF JAZERA ROYAL PALACE SS-New PR to compelete the PR 3323- PO 5540 is under approval in Oracle | REJECTED | No | 2024-05-28 | Moussa, Mohamed Fathi | 2024-05-28 | 2024-05-28 |  | 2024-06-03 |  | 4312500 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45440 | -45440
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3537 | CONS OF JAZERA ROYAL PALACE SS-110kV Surge Arrester | REJECTED | No | 2024-05-29 | Moussa, Mohamed Fathi | 2024-05-29 | 2024-05-29 |  | 2024-07-03 |  | 150000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45441 | -45441
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3538 | CONS OF JAZERA ROYAL PALACE SS-96 kV outdoor surge arresters | REJECTED | No | 2024-05-29 | Moussa, Mohamed Fathi | 2024-05-29 | 2024-05-29 |  | 2024-07-03 |  | 150000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45441 | -45441
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3539 | CONS OF JAZERA ROYAL PALACE SS-96 kV outdoor surge arresters | REJECTED | No | 2024-05-29 | Moussa, Mohamed Fathi | 2024-05-29 | 2024-05-29 |  | 2024-07-03 |  | 150000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45441 | -45441
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3544 | CONS OF JAZERA ROYAL PALACE SS-HV CABLE+BONDING CABLE+GROUNDING CABLE-1.3.3.1.8.1 | REJECTED | No | 2024-06-01 | Moussa, Mohamed Fathi | 2024-06-01 | 2024-06-01 |  | 2024-06-03 |  | 123862564.48 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45444 | -45444
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3545 | CONS OF JAZERA ROYAL PALACE SS- UGFOC - NON METTALIC FIBER OPTIC CABLE- | REJECTED | No | 2024-06-01 | Moussa, Mohamed Fathi | 2024-06-01 | 2024-06-01 |  | 2024-07-03 | Budegt Line UGFOC - NON METTALIC FIBER OPTIC CABLE-1.3.3.1.8.1 | 727056 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45444 | -45444
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3629 | CONS OF JAZERA ROYAL PALACE SS-Cyber Security | REJECTED | No | 2024-06-09 | Moussa, Mohamed Fathi | 2024-06-12 | 2024-06-12 |  | 2024-07-03 |  | 1000000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45455 | -45455
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3630 | CONS OF JAZERA ROYAL PALACE SS-Soil Investigation For OHTL | APPROVED | No | 2024-06-09 | Abas, Mohammed Fekry | 2024-07-11 | 2024-07-11 |  |  |  | 259832 | 5930 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 259832 | APPROVED |  |  | 2024-08-15 | 0 | 35 | Alhadi, Khalid | -45484 | 35
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3631 | CONS OF JAZERA ROYAL PALACE SS-GPR Survey- Radar Scan | APPROVED | No | 2024-06-09 | Abas, Mohammed Fekry | 2024-07-11 | 2024-07-11 |  |  |  | 120000 | 5931 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 120000 | APPROVED |  |  | 2024-08-15 | 0 | 35 | Alhadi, Khalid | -45484 | 35
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3635 | CONS OF JAZERA ROYAL PALACE SS-OHTC | REJECTED | No | 2024-06-10 | Moussa, Mohamed Fathi | 2024-06-12 | 2024-06-12 |  | 2024-07-03 |  | 150000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45455 | -45455
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3644 | CONS OF JAZERA ROYAL PALACE SS-Battery & Chargers 125V | REJECTED | No | 2024-06-12 | Issa, Amr Ali | 2024-07-03 | 2024-07-03 |  | 2024-07-03 | Over Budget by 40,500 Please submit Budget Exception Request to Amend the Budget | 579000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45476 | -45476
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3653 | CONS OF JAZERA ROYAL PALACE SS-Bare Copper - 150sqmm | REJECTED | No | 2024-06-12 | Moussa, Mohamed Fathi | 2024-06-18 | 2024-06-18 |  | 2024-07-03 |  | 88000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45461 | -45461
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3679 | CONS OF JAZERA ROYAL PALACE SS-NGR PR | REJECTED | No | 2024-06-25 | Abas, Mohammed Fekry | 2024-07-09 | 2024-07-08 | 2024-07-04 | 2024-07-09 | PO qty is 2 , PR received for 1, We can not increase the Qty while preparing the PO , Please issue PR with 2 QTY | 47500 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45481 | -45481
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3685 | CONS OF JAZERA ROYAL PALACE SS-Latticed steel towers | APPROVED | No | 2024-06-27 | Abas, Mohammed Fekry | 2024-07-04 | 2024-07-04 |  |  |  | 7704450 | 5778 | 0 | STANDARD | Hesham Helal Elsewedy & Partners for Construction Co., Ltd. | SAR | 7704450 | APPROVED |  |  | 2024-07-18 | 0 | 14 | Kumar, Mr. Ranjan | -45477 | 14
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3687 | CONS OF JAZERA ROYAL PALACE SS-Line insulator PR | APPROVED | No | 2024-06-27 | Abas, Mohammed Fekry | 2024-07-21 | 2024-07-22 | 2024-07-14 |  | Please correct the qty and prices to match the BOQ and offer | 1158500 | 5864 | 0 | STANDARD | LAPP Insulators GmbH | EUR | 2041800 | APPROVED |  |  | 2024-08-11 | -883300 | 20 | Babic, Marian | -45495 | 20
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3772 | CONS OF JAZERA ROYAL PALACE SS-Battery & Chargers 125V | REJECTED | No | 2024-07-04 | Abas, Mohammed Fekry | 2024-07-10 | 2024-07-08 |  | 2024-07-10 |  | 538000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45481 | -45481
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3792 | CONS OF JAZERA ROYAL PALACE SS-UGFOC - NON METTALIC FIBER OPTIC CABLE | APPROVED | No | 2024-07-07 | Abas, Mohammed Fekry | 2024-07-08 | 2024-07-09 |  |  |  | 230234.4 | 5922 | 0 | STANDARD | MIDDLE EAST FIBER CABLE MANUFACTURING CO. | SAR | 230234.4 | APPROVED |  |  | 2024-08-15 | 0 | 37 | Kumar, Mr. Ranjan | -45482 | 37
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3793 | CONS OF JAZERA ROYAL PALACE SS-Bare Copper - 150sqmm | REJECTED | No | 2024-07-07 | Althubaiti, Ahmed | 2024-07-08 |  |  | 2024-07-08 |  | 88000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3808 | CONS OF JAZERA ROYAL PALACE SS-OHTC | REJECTED | No | 2024-07-09 | Abdelgelel, Mostafa | 2024-07-09 |  |  | 2024-07-10 | Over budget by 163,000 SAR, please proceed with budget exception. | 301500 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3831 | CONS OF JAZERA ROYAL PALACE SS-Cyber Security System | APPROVED | No | 2024-07-11 | Abas, Mohammed Fekry | 2024-07-15 | 2024-07-15 |  |  |  | 1000000 | 5816 | 0 | STANDARD | ALFANAR CO | SAR | 1000000 | APPROVED |  |  | 2024-07-23 | 0 | 8 | Kumar, Mr. Ranjan | -45488 | 8
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3834 | CONS OF JAZERA ROYAL PALACE SS-ACSR | REJECTED | No | 2024-07-11 | Moussa, Mohamed Fathi | 2024-07-28 | 2024-07-28 | 2024-07-25 | 2024-07-28 | Unit Price is no correct. Unit price shall be SAR 18.84/Meter | 230234.4 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45501 | -45501
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3841 | CONS OF JAZERA ROYAL PALACE SS-Grounding, Coxian, Bounding Cable | REJECTED | No | 2024-07-11 | Yamama, Loai Mohamed | 2024-07-29 | 2024-07-15 | 2024-07-28 |  | Please issue new PR with updated unit rate as per PO | 1418501.2 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45488 | -45488
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3853 | CONS OF JAZERA ROYAL PALACE SS-NGR PR | APPROVED | No | 2024-07-11 | Abas, Mohammed Fekry | 2024-07-15 | 2024-07-15 |  |  |  | 94000 | 5753 | 0 | STANDARD | METAL DEPLOYE RESISTOR | EUR | 93252 | APPROVED |  |  | 2024-07-23 | 748 | 8 | Kumar, Mr. Ranjan | -45488 | 8
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3885 | CONS OF JAZERA ROYAL PALACE SS-13.8 KV SWGR | APPROVED | No | 2024-07-14 | Abas, Mohammed Fekry | 2024-07-15 | 2024-07-15 |  |  |  | 5665000 | 5817 | 0 | STANDARD | ALFANAR CO | SAR | 5665000 | APPROVED |  |  | 2024-07-23 | 0 | 8 | Kumar, Mr. Ranjan | -45488 | 8
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3887 | CONS OF JAZERA ROYAL PALACE SS-Link Box | APPROVED | No | 2024-07-14 | Abas, Mohammed Fekry | 2024-07-15 | 2024-07-15 |  |  |  | 518800 | 5791 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 518800 | APPROVED |  |  | 2024-07-25 | 0 | 10 | Kumar, Mr. Ranjan | -45488 | 10
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3891 | CONS OF JAZERA ROYAL PALACE SS-SCADA/RTU | REJECTED | No | 2024-07-14 | Abdelgelel, Mostafa | 2024-07-14 |  |  | 2024-07-15 | There was no budget for this Activity, It was missing from the Tender budget sheet. Please proceed with the Budget exception form. | 940000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3895 | CONS OF JAZERA ROYAL PALACE SS-AC/DC Panel | APPROVED | No | 2024-07-15 | Abas, Mohammed Fekry | 2024-07-15 | 2024-07-16 |  |  |  | 925000 | 5790 | 0 | STANDARD | ALFANAR CO | SAR | 925000 | APPROVED |  |  | 2024-08-19 | 0 | 34 | Kumar, Mr. Ranjan | -45489 | 34
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3950 | CONS OF JAZERA ROYAL PALACE SS-Telecomunication -Jazera Place SS - AlFanar | APPROVED | No | 2024-07-18 | Abas, Mohammed Fekry | 2024-07-22 | 2024-07-22 |  |  |  | 3550000 | 5815 | 0 | STANDARD | ALFANAR CO | SAR | 3550000 | APPROVED |  |  | 2024-08-11 | 0 | 20 | Kumar, Mr. Ranjan | -45495 | 20
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3950 | CONS OF JAZERA ROYAL PALACE SS-Telecomunication -Jazera Place SS - AlFanar | APPROVED | No | 2024-07-18 | Abas, Mohammed Fekry | 2024-07-22 | 2024-07-22 |  |  |  | 3550000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45495 | -45495
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3953 | CONS OF JAZERA ROYAL PALACE SS-Reactor - Jazera Royal Place Project- BEST-ACK | REJECTED | No | 2024-07-18 | Yamama, Loai Mohamed | 2024-07-18 |  |  | 2024-07-18 |  | 2682800 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3954 | CONS OF JAZERA ROYAL PALACE SS-Supply , whole scope Protection & Control Panels AMI, Revenue metering and SAS system | REJECTED | No | 2024-07-18 | Yamama, Loai Mohamed | 2024-07-18 |  |  | 2024-07-18 |  | 8500000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3962 | CONS OF JAZERA ROYAL PALACE SS-Control Protection scope for jazera | APPROVED | No | 2024-07-21 | Abas, Mohammed Fekry | 2024-07-22 | 2024-07-22 |  |  |  | 8500000 | 5680 | 0 | STANDARD | ALFANAR CO | SAR | 8500000 | APPROVED |  |  | 2024-08-11 | 0 | 20 | Kumar, Mr. Ranjan | -45495 | 20
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3962 | CONS OF JAZERA ROYAL PALACE SS-Control Protection scope for jazera | APPROVED | No | 2024-07-21 | Abas, Mohammed Fekry | 2024-07-22 | 2024-07-22 |  |  |  | 8500000 | 5680 | 1 | STANDARD | ALFANAR CO | SAR | 8500000 | IN PROCESS |  |  |  | 0 | 559 | Kumar, Mr. Ranjan | -45495 | -45495
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3967 | CONS OF JAZERA ROYAL PALACE SS-Reactor - Jazera Royal Place Project- BEST-ACK | APPROVED | No | 2024-07-21 | Abas, Mohammed Fekry | 2024-07-22 | 2024-07-23 |  |  |  | 2437500 | 5679 | 0 | STANDARD | BEST-BALIKESIR ELECTROMEKANIK SANAYI TESISLERI A.S. | USD | 2437500 | APPROVED |  |  | 2024-08-11 | 0 | 19 | Kumar, Mr. Ranjan | -45496 | 19
105-135 | CONS OF JAZERA ROYAL PALACE SS | 3998 | CONS OF JAZERA ROYAL PALACE SS-TinedCopper - 150sqmm | REJECTED | No | 2024-07-24 | Abas, Mohammed Fekry | 2024-07-28 | 2024-07-28 |  | 2024-07-29 |  | 86000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45501 | -45501
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4037 | CONS OF JAZERA ROYAL PALACE SS-8687-HV1577-0 110kV GIS Jazera SS-HICO- ACK | APPROVED | No | 2024-07-28 | Abas, Mohammed Fekry | 2024-07-28 | 2024-07-29 |  |  |  | 14625000 | 5879 | 0 | STANDARD | Hyosung Heavy Industries Corporation | USD | 14550000 | APPROVED |  |  | 2024-08-22 | 75000 | 24 | Kumar, Mr. Ranjan | -45502 | 24
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4037 | CONS OF JAZERA ROYAL PALACE SS-8687-HV1577-0 110kV GIS Jazera SS-HICO- ACK | APPROVED | No | 2024-07-28 | Abas, Mohammed Fekry | 2024-07-28 | 2024-07-29 |  |  |  | 14625000 | 5879 | 2 | STANDARD | Hyosung Heavy Industries Corporation | USD | 14550000 | REQUIRES REAPPROVAL |  |  |  | 75000 | 552 | Kumar, Mr. Ranjan | -45502 | -45502
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4043 | CONS OF JAZERA ROYAL PALACE SS-ACSR | REJECTED | No | 2024-07-29 | Yamama, Loai Mohamed | 2024-07-29 |  |  | 2024-07-29 |  | 760985.28 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4052 | CONS OF JAZERA ROYAL PALACE SS-TinedCopper - 150sqmm PR | REJECTED | No | 2024-07-30 | Yamama, Loai Mohamed | 2024-08-07 |  |  | 2024-08-08 | Rejected as per PMs request due to increase of price. | 100000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
[12 empty] | Procurement team should provide quotation for the price exchange. | [14 empty] | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4058 | CONS OF JAZERA ROYAL PALACE SS-ACSR | APPROVED | No | 2024-07-30 | Abas, Mohammed Fekry | 2024-11-19 | 2024-11-19 | 2024-09-09 |  | Please share all the PRs at the same time for Riyadg cable PO, so that we can route the PO in Oracle for approval | 5390821.08 | 5786 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 5390821.08 | APPROVED |  |  | 2025-01-14 | 0 | 56 | Kumar, Mr. Ranjan | -45615 | 56
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4068 | CONS OF JAZERA ROYAL PALACE SS-AUX-trans-750 kVA, | APPROVED | No | 2024-07-31 | Abas, Mohammed Fekry | 2024-08-04 | 2024-08-05 |  |  |  | 210000 | 5872 | 0 | STANDARD | ALFANAR CO | SAR | 210000 | APPROVED |  |  | 2024-08-15 | 0 | 10 | Kumar, Mr. Ranjan | -45509 | 10
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4071 | CONS OF JAZERA ROYAL PALACE SS-MV Cable PR | REJECTED | No | 2024-08-01 | Yamama, Loai Mohamed | 2024-08-01 |  |  | 2024-08-01 |  | 1055632.97 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4108 | CONS OF JAZERA ROYAL PALACE SS-Generator PR with its fuel tank | REJECTED | No | 2024-08-06 | Yamama, Loai Mohamed | 2024-08-08 |  |  | 2024-08-10 |  | 173500 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4109 | CONS OF JAZERA ROYAL PALACE SS-Mobilization PR | REJECTED | No | 2024-08-06 | Yamama, Loai Mohamed | 2024-08-08 |  |  | 2024-08-10 |  | 784860 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4110 | CONS OF JAZERA ROYAL PALACE SS-Fire fighting & Fire alarm system | APPROVED | No | 2024-08-06 | Abas, Mohammed Fekry | 2024-08-08 | 2024-08-08 |  |  |  | 2512345 | 5892 | 0 | STANDARD | Advanced Elements Co. | SAR | 2512345 | APPROVED |  |  | 2024-08-19 | 0 | 11 | Kumar, Mr. Ranjan | -45512 | 11
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4121 | CONS OF JAZERA ROYAL PALACE SS-Tinned copper PR | APPROVED | No | 2024-08-08 | Abas, Mohammed Fekry | 2024-08-11 | 2024-08-12 |  |  |  | 101116.4 | 5957 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 101116.4 | APPROVED |  |  | 2024-08-28 | 0 | 16 | Kumar, Mr. Ranjan | -45516 | 16
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4130 | CONS OF JAZERA ROYAL PALACE SS-Mobilization PR | REJECTED | No | 2024-08-11 | Yamama, Loai Mohamed | 2024-08-13 |  |  | 2024-08-14 | Rejected till performing budget exception form | 784860 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4152 | CONS OF JAZERA ROYAL PALACE SS-Access road & Structure pad | APPROVED | No | 2024-08-14 | Abas, Mohammed Fekry | 2024-09-15 | 2024-09-16 | 2024-09-12 |  | As per the project manager's shahed request to modify the budget | 1692000 | 6221 | 0 | STANDARD | Mashael Aseer Contracting Company. | SAR | 1692000 | APPROVED |  |  | 2024-10-17 | 0 | 31 | Tananeh, Khalid Jamal | -45551 | 31
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4243 | CONS OF JAZERA ROYAL PALACE SS-Generator PR with its fuel tank | APPROVED | No | 2024-08-21 | Abas, Mohammed Fekry | 2024-11-14 | 2024-11-14 | 2024-09-09 |  | Please issue the complete PR for Mobilization at once | 173500 | 6015 | 0 | STANDARD | Construction Expertise Est. | SAR | 173500 | APPROVED |  |  | 2025-01-14 | 0 | 61 | Kumar, Mr. Ranjan | -45610 | 61
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4244 | CONS OF JAZERA ROYAL PALACE SS-HVAC PR | APPROVED | No | 2024-08-22 | Abas, Mohammed Fekry | 2024-09-01 | 2024-09-01 |  |  |  | 2200000 | 6164 | 0 | STANDARD | MARINE SERVICES CO LTD. | SAR | 1970000 | APPROVED |  |  | 2024-09-26 | 230000 | 25 | Kumar, Mr. Ranjan | -45536 | 25
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4274 | CONS OF JAZERA ROYAL PALACE SS-Diesel Supplier | APPROVED | No | 2024-08-26 | Abas, Mohammed Fekry | 2024-09-01 | 2024-09-01 |  |  |  | 150000 | 6270 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 150000 | APPROVED |  |  | 2024-10-31 | 0 | 60 | Akhtar, Farhan | -45536 | 60
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4277 | CONS OF JAZERA ROYAL PALACE SS-LEEEC PR | APPROVED | No | 2024-08-26 | Abas, Mohammed Fekry | 2024-09-01 | 2024-09-01 |  |  |  | 8625000 | 5929 | 0 | STANDARD | Liaoning-Efacec Electrical Equipment Co., Ltd. | USD | 8625000 | APPROVED |  |  | 2024-09-24 | 0 | 23 | Kumar, Mr. Ranjan | -45536 | 23
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4295 | CONS OF JAZERA ROYAL PALACE SS-PDS | REJECTED | No | 2024-08-28 | Yamama, Loai Mohamed | 2024-11-21 | 2024-09-02 | 2024-10-06 |  | PR value less than Offer valued, as discussed over email please issue new PR. If FOC work has to be included in the PR then include another line item | 100000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45537 | -45537
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4392 | CONS OF JAZERA ROYAL PALACE SS-Additional Scope for changing the route - GPR Survey- Radar Scan | APPROVED | No | 2024-09-08 | Abas, Mohammed Fekry | 2024-09-15 | 2024-09-16 |  |  |  | 102000 | 5931 | 1 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 80000 | APPROVED |  |  | 2025-01-15 | 22000 | 121 | Alhadi, Khalid | -45551 | 121
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4400 | CONS OF JAZERA ROYAL PALACE SS-Water Level for UGC- PR | APPROVED | No | 2024-09-09 | Abas, Mohammed Fekry | 2024-09-15 | 2024-09-16 |  |  |  | 110000 | 6329 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 54000 | APPROVED |  |  | 2024-10-22 | 56000 | 36 | Alhadi, Khalid | -45551 | 36
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4403 | CONS OF JAZERA ROYAL PALACE SS-RTV Coating for Insulator | REJECTED | No | 2024-09-10 | Yamama, Loai Mohamed | 2024-09-16 |  |  | 2024-09-16 |  | 228750 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4423 | CONS OF JAZERA ROYAL PALACE SS-Precast PR | APPROVED | No | 2024-09-12 | Abas, Mohammed Fekry | 2024-09-15 | 2024-09-16 |  |  |  | 2588451 | 6220 | 0 | STANDARD | Factory of Qanbar Dywidag Precast Concrete Co.Ltd | SAR | 2588451 | APPROVED |  |  | 2024-10-17 | 0 | 31 | Tananeh, Khalid Jamal | -45551 | 31
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4438 | CONS OF JAZERA ROYAL PALACE SS-Supervision of excavation works for the purpose of issuing excavation permits related to the route of the underground cables project | APPROVED | No | 2024-09-12 | Abas, Mohammed Fekry | 2024-09-16 | 2024-09-17 |  |  |  | 60000 | 6235 | 0 | STANDARD | Abnia Engineering Consultants Co | SAR | 42000 | APPROVED |  |  | 2024-10-13 | 18000 | 26 | Alhadi, Khalid | -45552 | 26
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4552 | CONS OF JAZERA ROYAL PALACE SS-Jazera Project - Security Guard PO | APPROVED | No | 2024-09-29 | Abas, Mohammed Fekry | 2024-10-02 | 2024-10-03 |  |  |  | 167700 | 6306 | 0 | STANDARD | Saad Al-Gazereh For Security Services Company | SAR | 165750 | APPROVED |  |  | 2024-10-14 | 1950 | 11 | Abuhammad, Samir | -45568 | 11
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4630 | CONS OF JAZERA ROYAL PALACE SS-Security System PR | APPROVED | No | 2024-10-08 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-10 |  |  |  | 805000 | 6319 | 0 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 804526 | APPROVED |  |  | 2024-10-29 | 474 | 19 | Kumar, Mr. Ranjan | -45575 | 19
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4640 | CONS OF JAZERA ROYAL PALACE SS-Geotechnical investigations FAFCO | APPROVED | No | 2024-10-09 | Abas, Mohammed Fekry | 2024-10-22 | 2024-10-23 | 2024-10-17 |  | PR budget does not cover PO value | 72200 | 6328 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 72200 | APPROVED |  |  | 2024-10-29 | 0 | 6 | Alhadi, Khalid | -45588 | 6
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4651 | CONS OF JAZERA ROYAL PALACE SS-UGC topographic survey - additional | APPROVED | No | 2024-10-10 | Abas, Mohammed Fekry | 2024-10-14 | 2024-10-14 |  |  |  | 27000 | 5726 | 1 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 13750 | REQUIRES REAPPROVAL |  |  |  | 13250 | 475 | Alhadi, Khalid | -45579 | -45579
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4651 | CONS OF JAZERA ROYAL PALACE SS-UGC topographic survey - additional | APPROVED | No | 2024-10-10 | Abas, Mohammed Fekry | 2024-10-14 | 2024-10-14 |  |  |  | 27000 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45579 | -45579
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4760 | CONS OF JAZERA ROYAL PALACE SS-Soil Improvement - Menard | APPROVED | No | 2024-10-21 | Abas, Mohammed Fekry | 2024-10-22 | 2024-10-23 |  |  |  | 2466000 | 6408 | 0 | STANDARD | FREYSSINET MENARD SAUDI ARABIA LTD | SAR | 2466000 | APPROVED |  |  | 2024-11-14 | 0 | 22 | Tananeh, Khalid Jamal | -45588 | 22
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4777 | CONS OF JAZERA ROYAL PALACE SS-Indoor & outdoor lighting fixture | APPROVED | No | 2024-10-23 | Abas, Mohammed Fekry | 2024-10-27 | 2024-10-27 |  |  |  | 77940 | 6386 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 70767.32 | APPROVED |  |  | 2024-11-05 | 7172.68 | 9 | Alqadhi, Abdulrahman Abdulghani | -45592 | 9
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4784 | CONS OF JAZERA ROYAL PALACE SS-Soil quality control test | APPROVED | No | 2024-10-24 | Abas, Mohammed Fekry | 2024-10-27 | 2024-10-27 |  |  |  | 65000 | 6426 | 0 | STANDARD | Sameer S. Aboghailia Consultation Office | SAR | 65000 | APPROVED |  |  | 2024-11-28 | 0 | 32 | Alhadi, Khalid | -45592 | 32
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4793 | CONS OF JAZERA ROYAL PALACE SS- 3rd Party lab Inspector For Precast Concrete Prodaction Test - 1.3.4.1.1.10 | REJECTED | No | 2024-10-27 | Yamama, Loai Mohamed | 2024-10-28 |  |  | 2024-10-29 |  | 1250 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4809 | CONS OF JAZERA ROYAL PALACE SS-3rd Party lab Inspector For Precast Concrete Prodaction Test - | APPROVED | No | 2024-10-29 | Abas, Mohammed Fekry | 2024-11-03 | 2024-11-04 |  |  |  | 1250 | 6457 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 1250 | APPROVED |  |  | 2024-11-12 | 0 | 8 | Tananeh, Khalid Jamal | -45600 | 8
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4850 | CONS OF JAZERA ROYAL PALACE SS-Earthing Accessories | APPROVED | No | 2024-11-06 | Abas, Mohammed Fekry | 2024-11-09 | 2024-11-10 |  |  |  | 176477.93 | 6461 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 176477.93 | APPROVED |  |  | 2024-11-21 | 0 | 11 | Alqadhi, Abdulrahman Abdulghani | -45606 | 11
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4851 | CONS OF JAZERA ROYAL PALACE SS-Grounding conductors | APPROVED | No | 2024-11-06 | Abas, Mohammed Fekry | 2024-11-14 | 2024-11-14 |  |  |  | 217160.2 | 6549 | 0 | STANDARD | ALFANAR CO | SAR | 200200.48 | APPROVED |  |  | 2024-12-17 | 16959.72 | 33 | Alqadhi, Abdulrahman Abdulghani | -45610 | 33
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4867 | CONS OF JAZERA ROYAL PALACE SS-UGC Dewatering | REJECTED | No | 2024-11-07 | Yamama, Loai Mohamed | 2024-11-10 |  |  |  |  | 300000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4885 | CONS OF JAZERA ROYAL PALACE SS-UGC Dewatering | APPROVED | No | 2024-11-10 | Abas, Mohammed Fekry | 2024-11-10 | 2024-11-11 |  |  |  | 500000 | 6854 | 0 | STANDARD | UPPER HEIGHT FOR CONTRACTING COMPANY | SAR | 450000 | APPROVED |  |  | 2025-04-22 | 50000 | 162 | Tananeh, Khalid Jamal | -45607 | 162
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4905 | CONS OF JAZERA ROYAL PALACE SS-Civil PR | REJECTED | No | 2024-11-12 | Moussa, Mohamed Fathi | 2024-11-12 | 2024-11-12 |  | 2024-11-13 |  | 15500000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45608 | -45608
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4906 | CONS OF JAZERA ROYAL PALACE SS-IT supply | APPROVED | No | 2024-11-12 | Abas, Mohammed Fekry | 2024-11-14 | 2024-11-14 |  |  |  | 22000 | 6502 | 0 | STANDARD | Mohammad Abdul Rahman Mohd Al Zahid Information Technology Co | SAR | 19900 | APPROVED |  |  | 2024-11-27 | 2100 | 13 | Akhtar, Farhan | -45610 | 13
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4921 | CONS OF JAZERA ROYAL PALACE SS-125V DC System - | APPROVED | No | 2024-11-13 | Abas, Mohammed Fekry | 2024-11-21 | 2024-11-24 |  |  |  | 565400 | 5754 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 565400 | APPROVED |  |  | 2025-01-16 | 0 | 53 | Kumar, Mr. Ranjan | -45620 | 53
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4923 | CONS OF JAZERA ROYAL PALACE SS-MV Termination Kit - | APPROVED | No | 2024-11-13 | Abas, Mohammed Fekry | 2024-11-19 | 2024-11-19 |  |  |  | 101160 | 5792 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 101160 | APPROVED |  |  | 2024-12-08 | 0 | 19 | Kumar, Mr. Ranjan | -45615 | 19
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4930 | CONS OF JAZERA ROYAL PALACE SS-Civil PR | APPROVED | No | 2024-11-13 | Abas, Mohammed Fekry | 2024-11-14 | 2024-11-14 |  |  |  | 15500000 | 6534 | 0 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 15500000 | APPROVED |  |  | 2024-12-08 | 0 | 24 | Tananeh, Khalid Jamal | -45610 | 24
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4930 | CONS OF JAZERA ROYAL PALACE SS-Civil PR | APPROVED | No | 2024-11-13 | Abas, Mohammed Fekry | 2024-11-14 | 2024-11-14 |  |  |  | 15500000 | 6534 | 1 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 15500000 | REQUIRES REAPPROVAL |  |  |  | 0 | 444 | Tananeh, Khalid Jamal | -45610 | -45610
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4950 | CONS OF JAZERA ROYAL PALACE SS-Over head crane & JIB crane | APPROVED | No | 2024-11-14 | Abas, Mohammed Fekry | 2024-11-19 | 2024-11-19 |  |  |  | 321800 | 5798 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 321800 | APPROVED |  |  | 2024-12-08 | 0 | 19 | Kumar, Mr. Ranjan | -45615 | 19
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4951 | CONS OF JAZERA ROYAL PALACE SS-Towers Duplex Paint | REJECTED | No | 2024-11-14 | Yamama, Loai Mohamed | 2024-12-11 |  |  | 2024-12-12 |  | 3350000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 4988 | CONS OF JAZERA ROYAL PALACE SS-Connectors and Clamps | APPROVED | No | 2024-11-19 | Abas, Mohammed Fekry | 2024-12-30 | 2025-01-01 | 2024-12-25 |  | the budget is not enough | 21607 | 6481 | 0 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 18014.64 | APPROVED |  |  | 2025-01-12 | 3592.36 | 11 | Muaz, Alaa | -45658 | 11
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5002 | CONS OF JAZERA ROYAL PALACE SS-UGC - HV CABLE | APPROVED | No | 2024-11-20 | Abas, Mohammed Fekry | 2024-11-24 | 2024-11-24 |  |  |  | 95737407.2 | 5786 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 95737407.2 | APPROVED |  |  | 2025-01-14 | 0 | 51 | Kumar, Mr. Ranjan | -45620 | 51
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5003 | CONS OF JAZERA ROYAL PALACE SS- UGC Grounding, Bounding Cable | APPROVED | No | 2024-11-20 | Abas, Mohammed Fekry | 2024-11-24 | 2024-11-24 |  |  |  | 787462 | 5786 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 787462 | APPROVED |  |  | 2025-01-14 | 0 | 51 | Kumar, Mr. Ranjan | -45620 | 51
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5005 | CONS OF JAZERA ROYAL PALACE SS-Surge Arrestor | APPROVED | No | 2024-11-20 | Abas, Mohammed Fekry | 2024-11-24 | 2024-11-24 |  |  |  | 131312 | 5755 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 131311.06 | APPROVED |  |  | 2025-01-26 | 0.94 | 63 | Kumar, Mr. Ranjan | -45620 | 63
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5013 | CONS OF JAZERA ROYAL PALACE SS-PDS - 1.3.3.1.8.38. | RETURNED | Yes | 2024-11-21 | Abdelrahman, Ahmed Shaaban | 2025-05-21 | 2024-11-24 | 2024-12-23 |  | Please issue new PR covering the value of PDS and SAS Cabling | 100000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45620 | -45620
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5015 | CONS OF JAZERA ROYAL PALACE SS-Warehouse for OHTL | REJECTED | No | 2024-11-21 | Yamama, Loai Mohamed | 2024-12-11 |  |  | 2024-12-11 |  | 200000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5035 | CONS OF JAZERA ROYAL PALACE SS-Lighting pole & Lightning mast 1.3.3.1.8.19 | APPROVED | No | 2024-11-24 | Abas, Mohammed Fekry | 2024-12-19 | 2024-12-19 |  |  |  | 71450 | 6870 | 0 | STANDARD | Hesham Helal Elsewedy & Partners for Construction Co., Ltd. | SAR | 70000 | APPROVED |  |  | 2025-03-02 | 1450 | 73 | Alqadhi, Abdulrahman Abdulghani | -45645 | 73
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5047 | CONS OF JAZERA ROYAL PALACE SS-Mobilization PR | REJECTED | No | 2024-11-25 | Yamama, Loai Mohamed | 2024-12-11 |  |  | 2024-12-11 |  | 701180 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5058 | CONS OF JAZERA ROYAL PALACE SS-Switches & sockets -1.3.3.1.8.19 | REJECTED | No | 2024-11-27 | Issa, Amr Ali | 2024-11-27 |  |  | 2024-11-27 |  | 131243.4 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5066 | CONS OF JAZERA ROYAL PALACE SS-Switches & Sockets -1.3.3.1.8.19 | APPROVED | No | 2024-11-27 | Abas, Mohammed Fekry | 2024-12-19 | 2024-12-19 |  |  |  | 129906.9 | 6568 | 0 | STANDARD | Tawasul International Trad.Est. | SAR | 129906.9 | APPROVED |  |  | 2025-01-05 | 0 | 17 | Alqadhi, Abdulrahman Abdulghani | -45645 | 17
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5206 | CONS OF JAZERA ROYAL PALACE SS-Auguring - OHTL - 1.4.3.1.1.5 | APPROVED | No | 2024-12-10 | Abas, Mohammed Fekry | 2024-12-18 | 2024-12-19 |  |  |  | 2374890 | 6652 | 0 | STANDARD | Giant Foundation Contracting Co | SAR | 2374890 | APPROVED |  |  | 2024-12-29 | 0 | 10 | Abuhammad, Samir | -45645 | 10
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5207 | CONS OF JAZERA ROYAL PALACE SS-Steel -OHTL - 1.4.3.1.1.5 | APPROVED | No | 2024-12-10 | Abas, Mohammed Fekry | 2024-12-18 | 2024-12-19 |  |  |  | 1044300 | 6653 | 0 | STANDARD | AL FAISAL STEEL PRODUCT CO. | SAR | 1044300 | APPROVED |  |  | 2025-01-05 | 0 | 17 | Abuhammad, Samir | -45645 | 17
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5208 | CONS OF JAZERA ROYAL PALACE SS-Concrete - OHTL-1.4.3.1.1.5 | APPROVED | No | 2024-12-10 | Abas, Mohammed Fekry | 2024-12-18 | 2024-12-19 |  |  |  | 1371800 | 6654 | 0 | STANDARD | Rawaee Al Tashid for Industry Co. | SAR | 1138700 | APPROVED |  |  | 2025-01-16 | 233100 | 28 | Abuhammad, Samir | -45645 | 28
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5210 | CONS OF JAZERA ROYAL PALACE SS-HDD -UGC - 1.4.3.1.1.5 | APPROVED | No | 2024-12-10 | Abas, Mohammed Fekry | 2024-12-18 | 2024-12-19 |  |  |  | 1026955 | 6682 | 0 | STANDARD | Saleh Mohammed Al Yahya Contracting Company | SAR | 971250 | APPROVED |  |  | 2025-01-07 | 55705 | 19 | Abuhammad, Samir | -45645 | 19
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5218 | CONS OF JAZERA ROYAL PALACE SS-Warehouse for OHTL - 1.4.3.1.1.13 | RETURNED | Yes | 2024-12-11 | Abdelrahman, Ahmed Shaaban | 2025-09-16 | 2024-12-19 | 2025-09-01 |  | as per request from PM on email to cancellation email was in Mon 1/9/2025 4:36 PM | 200000 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45645 | -45645
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5219 | CONS OF JAZERA ROYAL PALACE SS-Mobilization PR | APPROVED | No | 2024-12-11 | Abas, Mohammed Fekry | 2024-12-18 | 2024-12-19 |  |  |  | 701180 | 6015 | 0 | STANDARD | Construction Expertise Est. | SAR | 701180 | APPROVED |  |  | 2025-01-14 | 0 | 26 | Kumar, Mr. Ranjan | -45645 | 26
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5231 | CONS OF JAZERA ROYAL PALACE SS-Supply of Cable Trays and Ladders with Accessories | APPROVED | No | 2024-12-16 | Abas, Mohammed Fekry | 2024-12-18 | 2024-12-19 |  |  |  | 534944.56 | 6650 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 534944.56 | APPROVED |  |  | 2025-01-14 | 0 | 26 | Alqadhi, Abdulrahman Abdulghani | -45645 | 26
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5232 | CONS OF JAZERA ROYAL PALACE SS-Supply of OPGW and Joint boxes | APPROVED | No | 2024-12-16 | Abas, Mohammed Fekry | 2024-12-18 | 2024-12-19 |  |  |  | 600056.62 | 6728 | 0 | STANDARD | ZTT International Limited. | SAR | 600056.62 | APPROVED |  |  | 2025-01-16 | 0 | 28 | Alqadhi, Abdulrahman Abdulghani | -45645 | 28
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5234 | CONS OF JAZERA ROYAL PALACE SS-Security Guard PO for OHTL WH & UGC | APPROVED | No | 2024-12-16 | Abas, Mohammed Fekry | 2024-12-18 | 2024-12-19 |  |  |  | 250000 | 6679 | 0 | STANDARD | Saad Al-Gazereh For Security Services Company | SAR | 237000 | APPROVED |  |  | 2024-12-29 | 13000 | 10 | Abuhammad, Samir | -45645 | 10
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5240 | CONS OF JAZERA ROYAL PALACE SS-Installation of GIS termination indoor and outdoor- Brugg Installation PR | REJECTED | No | 2024-12-17 | Yamama, Loai Mohamed | 2025-01-19 | 2024-12-23 |  | 2025-01-22 |  | 66000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45649 | -45649
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5272 | CONS OF JAZERA ROYAL PALACE SS-Gantry Design for Latticed steel towers - 1.4.2.1.1.1 | REJECTED | No | 2024-12-25 | Yamama, Loai Mohamed | 2025-01-07 |  |  | 2025-01-07 |  | 38000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5310 | CONS OF JAZERA ROYAL PALACE SS-MV Cables for SS ( Final Quantaties) | APPROVED | No | 2024-12-31 | Abas, Mohammed Fekry | 2025-01-01 | 2025-01-02 |  |  |  | 1055632.97 | 5786 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 1055632.97 | APPROVED |  |  | 2025-01-14 | 0 | 12 | Kumar, Mr. Ranjan | -45659 | 12
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5325 | CONS OF JAZERA ROYAL PALACE SS-Construction of 1st stage & 2nd Stage Pile Foundation for OHTL-JRP | APPROVED | No | 2025-01-01 | Abas, Mohammed Fekry | 2025-01-06 | 2025-01-06 |  |  |  | 828800 | 6729 | 0 | STANDARD | Base and Target Contracting company | SAR | 828800 | APPROVED |  |  | 2025-01-16 | 0 | 10 | Abuhammad, Samir | -45663 | 10
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5325 | CONS OF JAZERA ROYAL PALACE SS-Construction of 1st stage & 2nd Stage Pile Foundation for OHTL-JRP | APPROVED | No | 2025-01-01 | Abas, Mohammed Fekry | 2025-01-06 | 2025-01-06 |  |  |  | 828800 | 6729 | 1 | STANDARD | Base and Target Contracting company | SAR | 313600 | APPROVED |  |  | 2025-03-05 | 515200 | 58 | Abuhammad, Samir | -45663 | 58
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5325 | CONS OF JAZERA ROYAL PALACE SS-Construction of 1st stage & 2nd Stage Pile Foundation for OHTL-JRP | APPROVED | No | 2025-01-01 | Abas, Mohammed Fekry | 2025-01-06 | 2025-01-06 |  |  |  | 828800 | 6729 | 2 | STANDARD | Base and Target Contracting company | SAR | 257600 | APPROVED |  |  | 2025-05-19 | 571200 | 133 | Abuhammad, Samir | -45663 | 133
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5326 | CONS OF JAZERA ROYAL PALACE SS-Towers Stringing works -JRP | APPROVED | No | 2025-01-01 | Abas, Mohammed Fekry | 2025-01-06 | 2025-01-06 |  |  |  | 1035000 | 6853 | 0 | STANDARD | Saudi Pakistani Advanced Construction Company | SAR | 1034940.5 | APPROVED |  |  | 2025-03-13 | 59.5 | 66 | Abuhammad, Samir | -45663 | 66
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5341 | CONS OF JAZERA ROYAL PALACE SS-CABLE LADDERS AND Trays 2 | APPROVED | No | 2025-01-02 | Abas, Mohammed Fekry | 2025-01-08 | 2025-01-08 |  |  |  | 55.44 | 6650 | 0 | STANDARD | Mid-East Cable Support Solutions | SAR | 55.44 | APPROVED |  |  | 2025-01-14 | 0 | 6 | Alqadhi, Abdulrahman Abdulghani | -45665 | 6
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5373 | CONS OF JAZERA ROYAL PALACE SS-Supply of Spacer Dampers #1 -JRP | APPROVED | No | 2025-01-08 | Abas, Mohammed Fekry | 2025-01-09 | 2025-01-12 |  |  |  | 1071860 | 6104 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 1071860 | APPROVED |  |  | 2025-01-28 | 0 | 16 | Kumar, Mr. Ranjan | -45669 | 16
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5374 | CONS OF JAZERA ROYAL PALACE SS-Supply of Spacer Dampers #2 -JRP | APPROVED | No | 2025-01-08 | Abas, Mohammed Fekry | 2025-01-09 | 2025-01-12 |  |  |  | 64000 | 6104 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 64000 | APPROVED |  |  | 2025-01-28 | 0 | 16 | Kumar, Mr. Ranjan | -45669 | 16
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5375 | CONS OF JAZERA ROYAL PALACE SS-Gantry Design for Latticed steel towers | APPROVED | No | 2025-01-08 | Abas, Mohammed Fekry | 2025-01-09 | 2025-01-12 |  |  |  | 38000 | 5778 | 1 | STANDARD | Hesham Helal Elsewedy & Partners for Construction Co., Ltd. | SAR | 38000 | APPROVED |  |  | 2025-01-28 | 0 | 16 | Kumar, Mr. Ranjan | -45669 | 16
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5453 | CONS OF JAZERA ROYAL PALACE SS-Supply and apply of Duplex paint for Steel towers - JRP | APPROVED | No | 2025-01-18 | Abas, Mohammed Fekry | 2025-01-19 | 2025-01-19 |  |  |  | 3819300 | 5778 | 1 | STANDARD | Hesham Helal Elsewedy & Partners for Construction Co., Ltd. | SAR | 3819300 | APPROVED |  |  | 2025-01-28 | 0 | 9 | Kumar, Mr. Ranjan | -45676 | 9
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5454 | CONS OF JAZERA ROYAL PALACE SS-SSupply of Duplex paint for Touch up- Steel Towers- JRP | APPROVED | No | 2025-01-18 | Abas, Mohammed Fekry | 2025-01-19 | 2025-01-19 |  |  |  | 6750 | 5778 | 1 | STANDARD | Hesham Helal Elsewedy & Partners for Construction Co., Ltd. | SAR | 6750 | APPROVED |  |  | 2025-01-28 | 0 | 9 | Kumar, Mr. Ranjan | -45676 | 9
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5479 | CONS OF JAZERA ROYAL PALACE SS-Supply of Grounding Material of OHTL-JRP | RETURNED | No | 2025-01-20 | Babic, Marian | 2025-02-25 | 2025-01-23 | 2025-02-25 |  | this item not required (included in unit rates) | 232576.43 | 6880 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 224045.43 | APPROVED |  |  | 2025-02-19 | 8531 |  | Babic, Marian | -45680 | 27
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5479 | CONS OF JAZERA ROYAL PALACE SS-Supply of Grounding Material of OHTL-JRP | RETURNED | No | 2025-01-20 | Babic, Marian | 2025-02-25 | 2025-01-23 | 2025-02-25 |  | this item not required (included in unit rates) | 1200 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45680 | -45680
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5513 | CONS OF JAZERA ROYAL PALACE SS-Testing and Commissioning | APPROVED | No | 2025-01-21 | Abas, Mohammed Fekry | 2025-01-22 | 2025-01-23 |  |  |  | 2234000 | 7034 | 0 | STANDARD | Al Fanar Technical Services | SAR | 2100000 | APPROVED |  |  | 2025-05-08 | 134000 | 105 | Mohammed, Faisal Ansari | -45680 | 105
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5731 | CONS OF JAZERA ROYAL PALACE SS-JAZ - Forms Boxes - OHTL Civil (Tower Foundation) | APPROVED | No | 2025-01-29 | Abas, Mohammed Fekry | 2025-02-03 | 2025-02-05 |  |  |  | 160000 | 6867 | 0 | STANDARD | Fatima International construction Est. | SAR | 73200 | APPROVED |  |  | 2025-02-13 | 86800 | 8 | Abuhammad, Samir | -45693 | 8
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5802 | CONS OF JAZERA ROYAL PALACE SS-Supply of Grounding Material of OHTL 2 -JRP | APPROVED | No | 2025-02-05 | Abas, Mohammed Fekry | 2025-02-12 | 2025-02-12 |  |  |  | 32142.88 | 6880 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 30431.68 | APPROVED |  |  | 2025-02-19 | 1711.2 | 7 | Babic, Marian | -45700 | 7
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5815 | CONS OF JAZERA ROYAL PALACE SS-JAZ - Substation Electrical Equipment Installation Services | RETURNED | No | 2025-02-07 | Mohammed, Faisal Ansari | 2025-05-19 | 2025-02-18 | 2025-05-19 |  | This PR value does not match the PO value. A new PR shall be generated after the budget is revised and approved in Oracle to match the PO value. | 1140496.88 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45706 | -45706
105-135 | CONS OF JAZERA ROYAL PALACE SS | 5950 | CONS OF JAZERA ROYAL PALACE SS-Mobilization of Rental Land / Storage -JRP | APPROVED | No | 2025-02-18 | Abas, Mohammed Fekry | 2025-02-24 | 2025-02-24 |  |  | BUDGET ITEM 1.1.10.2 | 140900 | 6015 | 1 | STANDARD | Construction Expertise Est. | SAR | 120000 | APPROVED |  |  | 2025-03-04 | 20900 | 8 | Kumar, Mr. Ranjan | -45712 | 8
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6037 | CONS OF JAZERA ROYAL PALACE SS-JRP - OHTL Concrete Barrier | APPROVED | No | 2025-02-24 | Abas, Mohammed Fekry | 2025-02-27 | 2025-02-27 |  |  | Budget Line Item # 1.4.3.1.1.1 | 48000 | 6967 | 0 | STANDARD | Anhar Alyhari Contracting Co | SAR | 47008 | APPROVED |  |  | 2025-03-13 | 992 | 14 | Abuhammad, Samir | -45715 | 14
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6045 | CONS OF JAZERA ROYAL PALACE SS-Outdoor Equipment Steel Support Structure | RETURNED | Yes | 2025-02-25 | Abdelrahman, Ahmed Shaaban | 2025-09-16 | 2025-03-05 | 2025-04-28 |  | to update budgete | 54000 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -45721 | -45721
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6058 | CONS OF JAZERA ROYAL PALACE SS-Dewatering System for JRP Project | INCOMPLETE | Yes | 2025-02-26 | Abdelrahman, Ahmed Shaaban | 2025-09-30 |  |  | 2025-02-26 | 1.4.3.1.1.1 | 450000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6081 | CONS OF JAZERA ROYAL PALACE SS-OFMR & FSTP | APPROVED | No | 2025-02-27 | Abas, Mohammed Fekry | 2025-06-24 | 2025-06-25 | 2025-05-11 |  | Amount not Sufficient | 22500 | 7427 | 0 | STANDARD | AMWAJ TELECOMMUNICATION MFG. CO. | SAR | 22500 | APPROVED |  |  | 2025-07-09 | 0 | 14 | Abdulqader, Ahmed Abdulhalim | -45833 | 14
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6083 | CONS OF JAZERA ROYAL PALACE SS-Uplif Test | RETURNED | No | 2025-02-27 | Abuhammad, Samir | 2025-04-14 | 2025-03-05 | 2025-04-14 |  | Once request is clear PMT shall be raised | 15000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45721 | -45721
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6095 | CONS OF JAZERA ROYAL PALACE SS-UGC Civil Works#1 Anhar Al Yahari | APPROVED | No | 2025-03-02 | Abas, Mohammed Fekry | 2025-03-03 | 2025-03-03 |  |  | 1.4.3.1.1.13 | 8202125 | 6980 | 0 | STANDARD | Anhar Alyhari Contracting Co | SAR | 8202125 | APPROVED |  |  | 2025-03-13 | 0 | 10 | Abuhammad, Samir | -45719 | 10
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6095 | CONS OF JAZERA ROYAL PALACE SS-UGC Civil Works#1 Anhar Al Yahari | APPROVED | No | 2025-03-02 | Abas, Mohammed Fekry | 2025-03-03 | 2025-03-03 |  |  | 1.4.3.1.1.13 | 8202125 | 6980 | 1 | STANDARD | Anhar Alyhari Contracting Co | SAR | 4921275 | APPROVED |  |  | 2025-09-03 | 3280850 | 184 | Abuhammad, Samir | -45719 | 184
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6127 | CONS OF JAZERA ROYAL PALACE SS-PDS and FOC | REJECTED | No | 2025-03-06 | Yamama, Loai Mohamed | 2025-03-12 | 2025-03-11 |  | 2025-03-12 |  | 350000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45727 | -45727
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6129 | CONS OF JAZERA ROYAL PALACE SS-Pre cast for Qanbar | APPROVED | No | 2025-03-06 | Abas, Mohammed Fekry | 2025-03-12 | 2025-03-13 |  |  | 1.3.4.1.1.10 | 635000 | 6220 | 1 | STANDARD | Factory of Qanbar Dywidag Precast Concrete Co.Ltd | SAR | 635000 | APPROVED |  |  | 2025-04-24 | 0 | 42 | Tananeh, Khalid Jamal | -45729 | 42
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6132 | CONS OF JAZERA ROYAL PALACE SS-Construction of 1st stage & 2nd Stage Pile Foundation for OHTL-JRP (Power Linx) | REJECTED | No | 2025-03-06 | Alharbi, Atef Saud | 2025-03-06 | 2025-03-06 |  | 2025-03-10 |  | 515200 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45722 | -45722
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6140 | CONS OF JAZERA ROYAL PALACE SS-FSTP & PDS | APPROVED | No | 2025-03-10 | Abas, Mohammed Fekry | 2025-03-12 | 2025-03-13 |  |  | 1.4.3.1.1.5 | 688300 | 7027 | 0 | STANDARD | Global Power Linx. Company | SAR | 688300 | APPROVED |  |  | 2025-03-23 | 0 | 10 | Abuhammad, Samir | -45729 | 10
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6141 | CONS OF JAZERA ROYAL PALACE SS-NSCON UGC Civil Works | APPROVED | No | 2025-03-10 | Abas, Mohammed Fekry | 2025-03-12 | 2025-03-13 |  |  | 1.4.3.1.1.13 | 4939275 | 7026 | 0 | STANDARD | NSCON NEU CONTRACTING | SAR | 4939275 | APPROVED |  |  | 2025-03-18 | 0 | 5 | Abuhammad, Samir | -45729 | 5
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6142 | CONS OF JAZERA ROYAL PALACE SS-Digital Cables UGC Civil Works | APPROVED | No | 2025-03-10 | Abas, Mohammed Fekry | 2025-03-12 | 2025-03-13 |  |  | 1.4.3.1.1.13 | 4950000 | 7025 | 0 | STANDARD | Digital Cables Contracting Co | SAR | 4950000 | APPROVED |  |  | 2025-03-18 | 0 | 5 | Abuhammad, Samir | -45729 | 5
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6179 | CONS OF JAZERA ROYAL PALACE SS-UGC Civil Works (Al Badour) | APPROVED | No | 2025-03-20 | Abas, Mohammed Fekry | 2025-03-24 | 2025-03-25 |  |  |  | 4422030 | 7085 | 0 | STANDARD | Al Badour Electrical Contarcting Est | SAR | 4422030 | APPROVED |  |  | 2025-04-09 | 0 | 15 | Abuhammad, Samir | -45741 | 15
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6193 | CONS OF JAZERA ROYAL PALACE SS-Lot#3 (5 Gantries) Expediting Cost of Delivery By Energya | REJECTED | No | 2025-03-17 | Abdelrahman, Ahmed Shaaban | 2025-03-17 |  |  | 2025-03-17 | 1.4.2.1.1.1 | 400000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6194 | CONS OF JAZERA ROYAL PALACE SS-Lot#3 (7 Gantries) Expediting Cost of Delivery By Energya | REJECTED | Yes | 2025-03-17 | Abdelrahman, Ahmed Shaaban | 2025-04-22 | 2025-03-24 | 2025-04-22 | 2025-04-22 | Please edit the Qty to 180 MT | 400000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45740 | -45740
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6214 | CONS OF JAZERA ROYAL PALACE SS-UGC CIVIL WORKS HALAWANI | APPROVED | No | 2025-03-19 | Abas, Mohammed Fekry | 2025-03-23 | 2025-03-24 |  |  | 1.4.4.1.1.25 | 4440030 | 7071 | 0 | STANDARD | SHAREEF ABDULSAMED HASHIM HALAWANI Co, | SAR | 4440030 | APPROVED |  |  | 2025-04-09 | 0 | 16 | Abuhammad, Samir | -45740 | 16
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6215 | CONS OF JAZERA ROYAL PALACE SS-Soil & Foundation Co. Civil Testing Works | APPROVED | No | 2025-03-19 | Abas, Mohammed Fekry | 2025-03-23 | 2025-03-24 |  |  | 1.4.4.1.1.25 & 1.3.4.1.1.10 | 393723 | 7054 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 393723 | APPROVED |  |  | 2025-04-28 | 0 | 35 | Tananeh, Khalid Jamal | -45740 | 35
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6219 | CONS OF JAZERA ROYAL PALACE SS-Supply & Apply of RTV Coating (Manual PO#6952 Alraedy Released) | APPROVED | No | 2025-03-20 | Abas, Mohammed Fekry | 2025-03-24 | 2025-03-25 |  |  | 1.3.5.1.1.40 | 350562 | 6952 | 0 | STANDARD | Y.S.G Global Arabia Contracting Co. | SAR | 350562 | APPROVED |  |  | 2025-04-07 | 0 | 13 | Kumar, Mr. Ranjan | -45741 | 13
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6371 | CONS OF JAZERA ROYAL PALACE SS-DPO-Erection Al Jazera OHTL | APPROVED | No | 2025-04-17 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-20 |  |  |  | 1124550 | 7177 | 0 | STANDARD | Global Power Linx. Company | SAR | 1122800 | APPROVED |  |  | 2025-04-24 | 1750 | 4 | Abuhammad, Samir | -45767 | 4
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6371 | CONS OF JAZERA ROYAL PALACE SS-DPO-Erection Al Jazera OHTL | APPROVED | No | 2025-04-17 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-20 |  |  |  | 1124550 | 7177 | 1 | STANDARD | Global Power Linx. Company | SAR | 661400 | APPROVED |  |  | 2025-05-22 | 463150 | 32 | Abuhammad, Samir | -45767 | 32
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6371 | CONS OF JAZERA ROYAL PALACE SS-DPO-Erection Al Jazera OHTL | APPROVED | No | 2025-04-17 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-20 |  |  |  | 1124550 | 7177 | 2 | STANDARD | Global Power Linx. Company | SAR | 465477.5 | APPROVED |  |  | 2025-10-01 | 659072.5 | 164 | Abuhammad, Samir | -45767 | 164
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6391 | CONS OF JAZERA ROYAL PALACE SS-OPGW TESTING | APPROVED | No | 2025-04-20 | Abas, Mohammed Fekry | 2025-04-21 | 2025-04-21 |  |  | 1.4.4.2.1.1 | 150000 | 7186 | 0 | STANDARD | NAIF AWADH LAVI AL-HUDHAYLI AL-BAQMI For Contracting. | SAR | 137300 | APPROVED |  |  | 2025-04-24 | 12700 | 3 | Babic, Marian | -45768 | 3
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6399 | CONS OF JAZERA ROYAL PALACE SS-Amendment for PO 5798 | APPROVED | No | 2025-04-21 | Abas, Mohammed Fekry | 2025-04-22 | 2025-04-22 |  |  | 1.3.3.1.8.1 | 21600 | 5798 | 1 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 21600 | APPROVED |  |  | 2025-08-26 | 0 | 126 | Kumar, Mr. Ranjan | -45769 | 126
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6400 | CONS OF JAZERA ROYAL PALACE SS-PR to Amend PO 6654 | APPROVED | No | 2025-04-21 | Abas, Mohammed Fekry | 2025-04-22 | 2025-04-22 |  |  | 1.4.3.1.1.5 | 295000 | 6654 | 1 | STANDARD | Rawaee Al Tashid for Industry Co. | SAR | 295000 | APPROVED |  |  | 2025-04-28 | 0 | 6 | Abuhammad, Samir | -45769 | 6
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6408 | CONS OF JAZERA ROYAL PALACE SS-PR to Amend PO 5778#1 | APPROVED | No | 2025-04-22 | Abas, Mohammed Fekry | 2025-04-22 | 2025-04-22 |  |  | 1.4.3.1.1.13 & 1.4.2.1.1.1 | 813750 | 5778 | 2 | STANDARD | Hesham Helal Elsewedy & Partners for Construction Co., Ltd. | SAR | 813750 | APPROVED |  |  | 2025-05-15 | 0 | 23 | Kumar, Mr. Ranjan | -45769 | 23
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6409 | CONS OF JAZERA ROYAL PALACE SS-Installation of Joints#1 with Digital Cables (for Pfisterer Joints) | RETURNED | Yes | 2025-04-22 | Abdelrahman, Ahmed Shaaban | 2025-05-07 | 2025-04-22 | 2025-05-07 |  | Kindly revise the PR value to align with the PO value. | 450000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45769 | -45769
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6410 | CONS OF JAZERA ROYAL PALACE SS-Installation of Joints with BRUGG | RETURNED | Yes | 2025-04-22 | Abdelrahman, Ahmed Shaaban | 2025-05-07 | 2025-04-22 | 2025-05-05 |  | Please correct the Qty and resubmit the PR as informed via email | 759000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45769 | -45769
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6411 | CONS OF JAZERA ROYAL PALACE SS-Installation Termination Kits | APPROVED | No | 2025-04-22 | Abas, Mohammed Fekry | 2025-04-22 | 2025-04-22 |  |  | 1.4.4.1.1.38 | 66000 | 6014 | 0 | STANDARD | BRUGG CABLES COMAPNY | SAR | 66000 | APPROVED |  |  | 2025-05-22 | 0 | 30 | Kumar, Mr. Ranjan | -45769 | 30
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6417 | CONS OF JAZERA ROYAL PALACE SS-Acceleration Cost for Gantry | APPROVED | No | 2025-04-22 | Abas, Mohammed Fekry | 2025-04-24 | 2025-04-24 |  |  | 1.4.2.1.1.1 | 360000 | 5778 | 2 | STANDARD | Hesham Helal Elsewedy & Partners for Construction Co., Ltd. | SAR | 360000 | APPROVED |  |  | 2025-05-15 | 0 | 21 | Kumar, Mr. Ranjan | -45771 | 21
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6437 | CONS OF JAZERA ROYAL PALACE SS-Joints & Terminations | REJECTED | No | 2025-04-23 | Yamama, Loai Mohamed | 2025-04-24 | 2025-04-23 |  | 2025-04-24 |  | 3222187.2 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45770 | -45770
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6440 | CONS OF JAZERA ROYAL PALACE SS-OHTL Clamps & Connectors | REJECTED | No | 2025-04-23 | Yamama, Loai Mohamed | 2025-04-23 | 2025-04-23 |  | 2025-04-24 |  | 20700 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45770 | -45770
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6473 | CONS OF JAZERA ROYAL PALACE SS-Supply of SA Steel Structure (ALNAFIE METAL) | APPROVED | No | 2025-04-28 | Abas, Mohammed Fekry | 2025-04-29 | 2025-04-30 |  |  | 1.4.3.1.1.13 | 21600 | 7111 | 0 | STANDARD | Alnafie Metal Industries Company | SAR | 21600 | APPROVED |  |  | 2025-06-04 | 0 | 35 | Hegazy, Ayman | -45777 | 35
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6474 | CONS OF JAZERA ROYAL PALACE SS-Supply of CSE Steel Structure (Alnafie Metal) | APPROVED | No | 2025-04-28 | Abas, Mohammed Fekry | 2025-04-29 | 2025-04-30 |  |  | 1.4.3.1.1.13 | 15000 | 7111 | 0 | STANDARD | Alnafie Metal Industries Company | SAR | 15000 | APPROVED |  |  | 2025-06-04 | 0 | 35 | Hegazy, Ayman | -45777 | 35
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6493 | CONS OF JAZERA ROYAL PALACE SS-Diesel Generator and Water Supply | APPROVED | No | 2025-05-01 | Abas, Mohammed Fekry | 2025-05-05 | 2025-05-06 |  |  | 1.1.7.1.2 | 66000 | 7306 | 0 | STANDARD | NETAQ ALTAMEER | SAR | 66000 | APPROVED |  |  | 2025-06-22 | 0 | 47 | Akhtar, Farhan | -45783 | 47
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6552 | CONS OF JAZERA ROYAL PALACE SS-Installation of Joints (Digital Cable PO#7228) | APPROVED | No | 2025-05-07 | Abas, Mohammed Fekry | 2025-05-11 | 2025-05-11 |  |  | 1.4.4.1.1.38 | 588000 | 7228 | 0 | STANDARD | Digital Cables Contracting Co | SAR | 588000 | APPROVED |  |  | 2025-05-22 | 0 | 11 | Mohammed, Faisal Ansari | -45788 | 11
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6553 | CONS OF JAZERA ROYAL PALACE SS-Installation of Link Box (Digital Cables PO#7228) | REJECTED | No | 2025-05-07 | Yamama, Loai Mohamed | 2025-05-12 | 2025-05-11 |  | 2025-05-12 |  | 28000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45788 | -45788
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6592 | CONS OF JAZERA ROYAL PALACE SS-Installation of Link Box (Digital Cables PO#7228) | APPROVED | No | 2025-05-12 | Abas, Mohammed Fekry | 2025-05-13 | 2025-05-14 |  |  | 1.4.4.1.1.31 | 28000 | 7228 | 0 | STANDARD | Digital Cables Contracting Co | SAR | 28000 | APPROVED |  |  | 2025-05-22 | 0 | 8 | Mohammed, Faisal Ansari | -45791 | 8
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6596 | CONS OF JAZERA ROYAL PALACE SS-HDD#2 | RETURNED | Yes | 2025-05-12 | Abdelrahman, Ahmed Shaaban | 2025-09-16 | 2025-05-14 | 2025-08-06 |  | No need | 234500 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45791 | -45791
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6597 | CONS OF JAZERA ROYAL PALACE SS-6652 Chage Order | APPROVED | No | 2025-05-12 | Abas, Mohammed Fekry | 2025-05-13 | 2025-05-14 |  |  | 1.4.3.1.1.5 | 1006000 | 6652 | 1 | STANDARD | Giant Foundation Contracting Co | SAR | 250970 | APPROVED |  |  | 2025-05-29 | 755030 | 15 | Abuhammad, Samir | -45791 | 15
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6613 | CONS OF JAZERA ROYAL PALACE SS-HDD#2 - 2 | RETURNED | Yes | 2025-05-14 | Abdelrahman, Ahmed Shaaban | 2025-09-16 | 2025-05-20 | 2025-08-06 |  | No need | 47514 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45797 | -45797
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6674 | CONS OF JAZERA ROYAL PALACE SS-Steel Rebars | APPROVED | No | 2025-05-20 | Abas, Mohammed Fekry | 2025-05-21 | 2025-05-21 |  |  | 1.4.3.1.1.5 | 150000 | 6653 | 1 | STANDARD | AL FAISAL STEEL PRODUCT CO. | SAR | 112875 | APPROVED |  |  | 2025-05-28 | 37125 | 7 | Abuhammad, Samir | -45798 | 7
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6759 | CONS OF JAZERA ROYAL PALACE SS-Tower Erection work (Amal Al Nahrain) | APPROVED | No | 2025-06-01 | Abas, Mohammed Fekry | 2025-06-02 | 2025-06-02 |  |  |  | 520000 | 7386 | 0 | STANDARD | Amal Al nahrain Contracting Company | SAR | 520000 | APPROVED |  |  | 2025-06-15 | 0 | 13 | Abuhammad, Samir | -45810 | 13
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6820 | CONS OF JAZERA ROYAL PALACE SS-LV & Control Cable for PO 6111 | APPROVED | No | 2025-06-18 | Abas, Mohammed Fekry | 2025-06-22 | 2025-06-25 |  |  | 1.3.3.1.8.10 | 58299.78 | 6111 | 0 | STANDARD | ALFANAR CO | SAR | 58299.78 | APPROVED |  |  | 2025-07-10 | 0 | 15 | Badhman, Saeed | -45833 | 15
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6821 | CONS OF JAZERA ROYAL PALACE SS-Additional Cable Type for PO#6111 | APPROVED | No | 2025-06-18 | Abas, Mohammed Fekry | 2025-06-22 | 2025-06-25 |  |  | 1.3.3.1.8.10 | 32732.5 | 6111 | 0 | STANDARD | ALFANAR CO | SAR | 32732.5 | APPROVED |  |  | 2025-07-10 | 0 | 15 | Badhman, Saeed | -45833 | 15
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6895 | CONS OF JAZERA ROYAL PALACE SS-For Control Cables | REJECTED | No | 2025-06-25 | Abdelrahman, Ahmed Shaaban | 2025-06-25 |  |  | 2025-06-25 |  | 868778.27 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 6897 | CONS OF JAZERA ROYAL PALACE SS-LV Control Cables | APPROVED | No | 2025-06-25 | Abas, Mohammed Fekry | 2025-06-29 | 2025-07-01 |  |  | 1.3.3.1.8.10 | 884983.52 | 6111 | 0 | STANDARD | ALFANAR CO | SAR | 884983.52 | APPROVED |  |  | 2025-07-10 | 0 | 9 | Badhman, Saeed | -45839 | 9
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7092 | CONS OF JAZERA ROYAL PALACE SS-Installation of HCIS (Marine Services) | APPROVED | No | 2025-07-15 | Abas, Mohammed Fekry | 2025-07-20 | 2025-07-20 |  |  | Task No. 1.3.5.1.1.36 | 2399779 | 7136 | 0 | STANDARD | MARINE SERVICES CO LTD. | SAR | 2399779 | APPROVED |  |  | 2025-07-24 | 0 | 4 | Mohammed, Faisal Ansari | -45858 | 4
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7166 | CONS OF JAZERA ROYAL PALACE SS-Supply and Application of Backfiilling Materials (Mashael Aseer Contracting Company) | APPROVED | No | 2025-07-21 | Abas, Mohammed Fekry | 2025-07-22 | 2025-07-22 |  |  | 1.4.4.1.1.25 for UGC Works. | 840000 | 7248 | 0 | STANDARD | Mashael Aseer Contracting Company. | SAR | 840000 | APPROVED |  |  | 2025-08-21 | 0 | 30 | Tananeh, Khalid Jamal | -45860 | 30
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7167 | CONS OF JAZERA ROYAL PALACE SS-Supply and Application of Backfiilling Materials (Al Badour) | REJECTED | No | 2025-07-21 | Yamama, Loai Mohamed | 2025-07-22 | 2025-07-21 |  | 2025-07-22 |  | 840000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45859 | -45859
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7171 | CONS OF JAZERA ROYAL PALACE SS-Rebar Steel (Faisal Steel) | APPROVED | No | 2025-07-21 | Abas, Mohammed Fekry | 2025-07-22 | 2025-07-22 |  |  | 1.4.3.1.1.5 | 157920 | 6653 | 2 | STANDARD | AL FAISAL STEEL PRODUCT CO. | SAR | 157920 | APPROVED |  |  | 2025-08-06 | 0 | 15 | Abuhammad, Samir | -45860 | 15
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7172 | CONS OF JAZERA ROYAL PALACE SS-Concrete Supply for OHTL (RTCO) | APPROVED | No | 2025-07-21 | Abas, Mohammed Fekry | 2025-07-22 | 2025-07-22 |  |  | 1.4.3.1.1.5 | 79650 | 6654 | 2 | STANDARD | Rawaee Al Tashid for Industry Co. | SAR | 79650 | APPROVED |  |  | 2025-08-02 | 0 | 11 | Abuhammad, Samir | -45860 | 11
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7174 | CONS OF JAZERA ROYAL PALACE SS-UGC Cables (RIYADH CABLE) | REJECTED | No | 2025-07-21 | Abdelrahman, Ahmed Shaaban | 2025-07-21 |  |  | 2025-07-21 |  | 1706184 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7176 | CONS OF JAZERA ROYAL PALACE SS-UGC Cable (Riyadh Cable) | APPROVED | No | 2025-07-21 | Abas, Mohammed Fekry | 2025-07-22 | 2025-07-22 |  |  | 1.4.2.1.1.46 | 1706227.2 | 5786 | 1 | STANDARD | Riyadh Cables Group Company | SAR | 1706227.2 | APPROVED |  |  | 2025-08-16 | 0 | 25 | Kumar, Mr. Ranjan | -45860 | 25
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7177 | CONS OF JAZERA ROYAL PALACE SS-Stringing Works for OHTL | REJECTED | No | 2025-07-21 | Alharbi, Atef Saud | 2025-07-22 | 2025-07-22 |  | 2025-07-22 |  | 66000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45860 | -45860
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7183 | CONS OF JAZERA ROYAL PALACE SS-Supply of Backfilling Materials for OHTL (ALBADOUR) | APPROVED | No | 2025-07-22 | Abas, Mohammed Fekry | 2025-07-28 | 2025-07-29 |  |  | 1.4.4.1.1.25 | 896000 | 7249 | 0 | STANDARD | Al Badour Electrical Contarcting Est | SAR | 896000 | APPROVED |  |  | 2025-08-21 | 0 | 23 | Tananeh, Khalid Jamal | -45867 | 23
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7186 | CONS OF JAZERA ROYAL PALACE SS-Rebar Steel (Faisal Steel 2) | APPROVED | No | 2025-07-22 | Abas, Mohammed Fekry | 2025-07-28 | 2025-07-29 |  |  | 1.4.3.1.1.5 | 3600 | 6653 | 2 | STANDARD | AL FAISAL STEEL PRODUCT CO. | SAR | 3600 | APPROVED |  |  | 2025-08-06 | 0 | 8 | Abuhammad, Samir | -45867 | 8
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7187 | CONS OF JAZERA ROYAL PALACE SS-Cost Repair of the Existing Overhead Transmission Line (OHTL) Incident | RETURNED | No | 2025-07-22 | Abuhammad, Samir | 2026-01-12 | 2025-07-29 | 2026-01-12 |  | due to provid mangamnet approval in order to issue the PO as manual payment done by PMT. | 60000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45867 | -45867
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7199 | CONS OF JAZERA ROYAL PALACE SS-Supply of Lighting Conduits (SESCO) | APPROVED | No | 2025-07-24 | Abas, Mohammed Fekry | 2025-07-28 | 2025-07-29 |  |  | 1.3.3.1.8.19 | 179967 | 7443 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 179967 | APPROVED |  |  | 2025-08-21 | 0 | 23 | Muaz, Alaa | -45867 | 23
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7202 | CONS OF JAZERA ROYAL PALACE SS-Supply of Cable Clamps (PTE) | APPROVED | No | 2025-07-24 | Abas, Mohammed Fekry | 2025-07-28 | 2025-07-29 |  |  | 1.3.3.1.8.72 | 94405 | 7375 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 87796.65 | APPROVED |  |  | 2025-08-26 | 6608.35 | 28 | Kumar, Mr. Ranjan | -45867 | 28
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7219 | CONS OF JAZERA ROYAL PALACE SS-UGC Cable 2 (Riyadh Cable) | APPROVED | No | 2025-07-27 | Abas, Mohammed Fekry | 2025-08-04 | 2025-08-04 |  |  | 1.4.2.1.1.46 | 1194359.04 | 5786 | 1 | STANDARD | Riyadh Cables Group Company | SAR | 1194359.04 | APPROVED |  |  | 2025-08-16 | 0 | 12 | Kumar, Mr. Ranjan | -45873 | 12
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7231 | CONS OF JAZERA ROYAL PALACE SS-FOC Works & PDS System (FASTCOMM) | APPROVED | No | 2025-07-28 | Abas, Mohammed Fekry | 2025-08-04 | 2025-08-04 |  |  | 1.3.3.1.8.38 | 430000 | 7210 | 0 | STANDARD | FASTCOMM CONTRACTING EST. | SAR | 430000 | APPROVED |  |  | 2025-08-21 | 0 | 17 | Abdulqader, Ahmed Abdulhalim | -45873 | 17
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7264 | CONS OF JAZERA ROYAL PALACE SS-Supply of Cable Clamps 2 (PTE) | REJECTED | No | 2025-08-03 | Abdelrahman, Ahmed Shaaban | 2025-08-03 |  |  | 2025-08-03 |  | 63480 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7265 | CONS OF JAZERA ROYAL PALACE SS-Supply of Cable Clamps 2 (PTE) | APPROVED | No | 2025-08-03 | Abas, Mohammed Fekry | 2025-08-05 | 2025-08-06 |  |  | 1.3.3.1.8.72- | 63480 | 7375 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 59036.4 | APPROVED |  |  | 2025-08-26 | 4443.6 | 20 | Kumar, Mr. Ranjan | -45875 | 20
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7266 | CONS OF JAZERA ROYAL PALACE SS-UGC-HDD Supply and Installation (Al Yahya) | APPROVED | No | 2025-08-03 | Abas, Mohammed Fekry | 2025-08-05 | 2025-08-06 |  |  | 1.4.3.1.1.5 | 223250 | 6682 | 1 | STANDARD | Saleh Mohammed Al Yahya Contracting Company | SAR | 223250 | APPROVED |  |  | 2025-09-04 | 0 | 29 | Abuhammad, Samir | -45875 | 29
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7301 | CONS OF JAZERA ROYAL PALACE SS-UGC-HDD Supply and Installation 2 (Al Yahya) | APPROVED | No | 2025-08-06 | Abas, Mohammed Fekry | 2025-08-10 | 2025-08-10 |  |  | 1.4.3.1.1.5 | 9500 | 6682 | 1 | STANDARD | Saleh Mohammed Al Yahya Contracting Company | SAR | 9500 | APPROVED |  |  | 2025-09-04 | 0 | 25 | Abuhammad, Samir | -45879 | 25
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7317 | CONS OF JAZERA ROYAL PALACE SS-UGC Civil Works (AL BADOUR) | APPROVED | No | 2025-08-07 | Abas, Mohammed Fekry | 2025-08-10 | 2025-08-10 |  |  | 1.4.4.1.1.25 | 2211015 | 7085 | 1 | STANDARD | Al Badour Electrical Contarcting Est | SAR | 2211015 | APPROVED |  |  | 2025-08-21 | 0 | 11 | Abuhammad, Samir | -45879 | 11
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7329 | CONS OF JAZERA ROYAL PALACE SS-COPAS - Provision of Technical Assistance Services Conductor and OPGW Pulling over HHR train bridge between two towers | APPROVED | No | 2025-08-11 | Abas, Mohammed Fekry | 2025-08-13 | 2025-08-13 |  |  | 1.4.4.1.1.11 | 150000 | 7616 | 0 | STANDARD | SA DE OBRAS Y SERVICIOS COPASA Branch | SAR | 150000 | APPROVED |  |  | 2025-08-31 | 0 | 18 | Alhadi, Khalid | -45882 | 18
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7329 | CONS OF JAZERA ROYAL PALACE SS-COPAS - Provision of Technical Assistance Services Conductor and OPGW Pulling over HHR train bridge between two towers | APPROVED | No | 2025-08-11 | Abas, Mohammed Fekry | 2025-08-13 | 2025-08-13 |  |  | 1.4.4.1.1.11 | 150000 | 7616 | 1 | STANDARD | SA DE OBRAS Y SERVICIOS COPASA Branch | SAR | 150000 | REQUIRES REAPPROVAL |  |  |  | 0 | 172 | Alhadi, Khalid | -45882 | -45882
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7351 | CONS OF JAZERA ROYAL PALACE SS-Busbar Protection Panel (Alfanar) | APPROVED | No | 2025-08-13 | Abas, Mohammed Fekry | 2025-08-14 | 2025-08-18 |  |  | 1.3.3.1.8.26 | 600000 | 5680 | 1 | STANDARD | ALFANAR CO | SAR | 600000 | IN PROCESS |  |  |  | 0 | 167 | Kumar, Mr. Ranjan | -45887 | -45887
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7351 | CONS OF JAZERA ROYAL PALACE SS-Busbar Protection Panel (Alfanar) | APPROVED | No | 2025-08-13 | Abas, Mohammed Fekry | 2025-08-14 | 2025-08-18 |  |  | 1.3.3.1.8.26 | 600000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45887 | -45887
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7368 | UGNMFOC | APPROVED | No | 2025-08-18 | Abas, Mohammed Fekry | 2025-08-19 | 2025-08-19 |  |  | 1.4.2.1.1.68 | 22435.2 | 5922 | 1 | STANDARD | MIDDLE EAST FIBER CABLE MANUFACTURING CO. | SAR | 22435.2 | APPROVED |  |  | 2025-09-17 | 0 | 29 | Kumar, Mr. Ranjan | -45888 | 29
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7375 | OPGW & NMFOC SPLICING & TESTING | REJECTED | No | 2025-08-18 | Yamama, Loai Mohamed | 2025-08-20 | 2025-08-18 |  | 2025-08-20 |  | 137300 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45887 | -45887
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7405 | OPGW & NMFOC | RETURNED | No | 2025-08-21 | Kumar, Mr. Ranjan | 2025-08-26 | 2025-08-25 | 2025-08-26 |  | Incomplete details for RFQ , Please resubmit the PR with PR acceptance criteria | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45894 | -45894
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7443 | Grounding material | RETURNED | No | 2025-08-24 | Muaz, Alaa | 2025-10-29 | 2025-08-25 | 2025-10-29 |  | it's not right PR ant not aligned with PO Annex | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -45894 | -45894
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7447 | Safety Engineer | RETURNED | No | 2025-08-24 | Alhadi, Khalid | 2025-09-29 | 2025-08-25 | 2025-09-29 |  | No feedback regarding the requirements, | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45894 | -45894
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7520 | Diesel Supply | REJECTED | No | 2025-08-27 | Issa, Amr Ali | 2025-08-27 | 2025-08-27 |  | 2025-08-27 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45896 | -45896
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7530 | Diesel Supply | APPROVED | No | 2025-08-27 | Abas, Mohammed Fekry | 2025-08-27 | 2025-08-28 |  |  | 1.1.7.1.2 | 0 | 7306 | 1 | STANDARD | NETAQ ALTAMEER | SAR | 144000 | APPROVED |  |  | 2025-10-30 | -144000 | 63 | Akhtar, Farhan | -45897 | 63
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7565 | Backfilling works to perform the Stringing of OHTL above Haramain High Speed Railway | APPROVED | No | 2025-08-28 | Abas, Mohammed Fekry | 2025-08-30 | 2025-08-31 |  |  | 1.4.3.1.1.1 | 0 | 7682 | 0 | STANDARD | Mashael Aseer Contracting Company. | SAR | 105000 | APPROVED |  |  | 2025-12-14 | -105000 | 105 | Tananeh, Khalid Jamal | -45900 | 105
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7615 | Additional Material with Duplex Paint & Fasteners | RETURNED | No | 2025-09-02 | Kumar, Mr. Ranjan | 2025-11-16 | 2025-09-04 | 2025-11-16 |  | 2. Resubmit the PR 7615 after correction– UoM for both items shall be "Ton" instead of Meter. Line 1 Quantity shall be 9.8 MT (as per updated Quantity), In PR its 8.5 Meter. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45904 | -45904
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7629 | UGC Civil Works 3km(Digital Cable) | APPROVED | No | 2025-09-03 | Abas, Mohammed Fekry | 2025-09-04 | 2025-09-04 |  |  | 1.4.3.1.1.13 and 1.4.4.1.1.25 | 4950000 | 7638 | 0 | STANDARD | Digital Cables Contracting Co | SAR | 4950000 | APPROVED |  |  | 2025-09-17 | 0 | 13 | Abuhammad, Samir | -45904 | 13
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7641 | NMFOC Testing | APPROVED | No | 2025-09-04 | Abas, Mohammed Fekry | 2025-09-04 | 2025-09-04 |  |  | 1.4.4.2.1.1 | 0 | 7186 | 1 | STANDARD | NAIF AWADH LAVI AL-HUDHAYLI AL-BAQMI For Contracting. | SAR | 84600 | APPROVED |  |  | 2025-10-15 | -84600 | 41 | Babic, Marian | -45904 | 41
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7673 | LV Wires (Alfanar) | RETURNED | No | 2025-09-08 | Muaz, Alaa | 2025-11-12 | 2025-09-10 | 2025-11-12 |  | The PO is issued and acknowledged from vendor and procurement, but we didn't receive the full approved waive memo | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -45910 | -45910
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7682 | COPASA Backfilling Supervision cost to perform the 06 cranes platform for the Stringing of OHTL above Haramain High Speed Railway | REJECTED | No | 2025-09-08 | Yamama, Loai Mohamed | 2025-09-09 | 2025-09-09 |  | 2025-09-09 |  | 212500 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45909 | -45909
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7687 | CO for VT | APPROVED | No | 2025-09-08 | Abas, Mohammed Fekry | 2025-09-09 | 2025-09-10 |  |  | 1.3.3.1.1.1 | 0 | 5879 | 1 | STANDARD | Hyosung Heavy Industries Corporation | USD | 63750 | APPROVED |  |  | 2025-10-21 | -63750 | 41 | Kumar, Mr. Ranjan | -45910 | 41
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7687 | CO for VT | APPROVED | No | 2025-09-08 | Abas, Mohammed Fekry | 2025-09-09 | 2025-09-10 |  |  | 1.3.3.1.1.1 | 0 | 5879 | 2 | STANDARD | Hyosung Heavy Industries Corporation | USD | 63750 | REQUIRES REAPPROVAL |  |  |  | -63750 | 144 | Kumar, Mr. Ranjan | -45910 | -45910
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7702 | Backfilling works to perform the Stringing of OHTL above Haramain High Speed Railway 2 | APPROVED | No | 2025-09-09 | Abas, Mohammed Fekry | 2025-09-11 | 2025-09-12 |  |  | 1.4.3.1.1.1 | 0 | 7682 | 0 | STANDARD | Mashael Aseer Contracting Company. | SAR | 52500 | APPROVED |  |  | 2025-12-14 | -52500 | 93 | Tananeh, Khalid Jamal | -45912 | 93
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7703 | Supply of Security Guards | REJECTED | No | 2025-09-09 | Yamama, Loai Mohamed | 2025-09-11 | 2025-09-11 |  | 2025-09-11 |  | 222000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45911 | -45911
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7714 | COPASA Backfilling Supervision cost to perform the 06 cranes platform for the Stringing of OHTL above Haramain High Speed Railway | APPROVED | No | 2025-09-10 | Abas, Mohammed Fekry | 2025-09-11 | 2025-09-12 |  |  | 1.4.3.1.1.1 | 0 | 7696 | 0 | STANDARD | SA DE OBRAS Y SERVICIOS COPASA Branch | SAR | 212500 | APPROVED |  |  | 2025-09-30 | -212500 | 18 | Alhadi, Khalid | -45912 | 18
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7723 | Supply of Security Guards | REJECTED | No | 2025-09-11 | Abdelrahman, Ahmed Shaaban | 2026-01-15 | 2025-09-21 | 2025-10-01 |  | for modifiation. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45921 | -45921
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7727 | Supply of HV Cable Joints and Termination Kits (Brugg) | APPROVED | No | 2025-09-14 | Abas, Mohammed Fekry | 2025-09-15 | 2025-09-16 |  |  | 1.4.2.1.1.59 | 0 | 6013 | 0 | STANDARD | Brugg Kable AG | CHF | 2910844.2 | APPROVED |  |  | 2025-10-30 | -2910844.2 | 44 | Babic, Marian | -45916 | 44
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7729 | Jet Washing Facilities | RETURNED | No | 2025-09-14 | Babic, Marian | 2025-11-02 | 2025-09-19 | 2025-11-02 |  | not required | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45919 | -45919
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7730 | Nameplates for Tower | APPROVED | No | 2025-09-14 | Abas, Mohammed Fekry | 2025-09-16 | 2025-09-21 |  |  | 1.4.2.1.1.1 | 0 | 7753 | 0 | STANDARD | REMOZ ARABIAN TRADING EST. | SAR | 42453.79 | APPROVED |  |  | 2025-10-15 | -42453.79 | 24 | Babic, Marian | -45921 | 24
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7738 | Extension of SOE & SCADA | APPROVED | No | 2025-09-15 | Abas, Mohammed Fekry | 2025-09-15 | 2025-09-16 |  |  | 1.3.3.2.1.10 | 0 | 7787 | 0 | STANDARD | TRINERGY TECHNOLOGIES SA | SAR | 398000 | APPROVED |  |  | 2025-10-28 | -398000 | 42 | Babic, Marian | -45916 | 42
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7741 | Extension of DFR | APPROVED | No | 2025-09-15 | Abas, Mohammed Fekry | 2025-09-15 | 2025-09-16 |  |  | 1.3.3.2.1.10 | 0 | 7816 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 210000 | APPROVED |  |  | 2025-10-30 | -210000 | 44 | Babic, Marian | -45916 | 44
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7742 | Installation of Cable Joints (Digital Cables#2) | RETURNED | Yes | 2025-09-15 | Abdelrahman, Ahmed Shaaban | 2025-09-24 | 2025-09-21 | 2025-09-24 |  | I am unable to enter the price. Kindly select another option, i.e., 'Services by Quantity,' when creating the PR. | 6 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45921 | -45921
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7771 | Uplift Test | APPROVED | No | 2025-09-17 | Abas, Mohammed Fekry | 2025-09-18 | 2025-09-19 |  |  | 1.4.3.1.1.5 | 0 | 7641 | 0 | STANDARD | FUGRO SUHAIMI LTD. | SAR | 135630 | IN PROCESS |  |  |  | -135630 | 135 | Babic, Marian | -45919 | -45919
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7771 | Uplift Test | APPROVED | No | 2025-09-17 | Abas, Mohammed Fekry | 2025-09-18 | 2025-09-19 |  |  | 1.4.3.1.1.5 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45919 | -45919
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7776 | Tower Erection (Amal) | RETURNED | No | 2025-09-17 | Abuhammad, Samir | 2025-11-02 | 2025-10-02 | 2025-11-02 |  | PMT to submit POC, then they can submit again. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45932 | -45932
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7815 | Installation of Cable Joints (Digital Cables#2) | APPROVED | No | 2025-09-24 | Abas, Mohammed Fekry | 2025-09-25 | 2025-09-28 |  |  | 1.4.4.1.1.38 | 0 | 7228 | 1 | STANDARD | Digital Cables Contracting Co | SAR | 42000 | APPROVED |  |  | 2025-10-16 | -42000 | 18 | Mohammed, Faisal Ansari | -45928 | 18
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7849 | IT Requirements for CSD | APPROVED | No | 2025-09-29 | Abas, Mohammed Fekry | 2025-10-01 | 2025-10-03 |  |  | 1.1.8.1.9 | 0 | 6502 | 1 | STANDARD | Mohammad Abdul Rahman Mohd Al Zahid Information Technology Co | SAR | 9900 | APPROVED | 2025-10-26 | 2025-10-27 | 2026-01-05 | -9900 | 94 | Akhtar, Farhan | 24 | 94
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7854 | PTE for Conenctors | APPROVED | No | 2025-09-29 | Abas, Mohammed Fekry | 2025-10-01 | 2025-10-01 |  |  | 1.4.2.1.1.25 | 0 | 7789 | 0 | STANDARD | ENERGY POWER SERVICE TRADING EST. | SAR | 45000 | APPROVED |  |  | 2025-10-15 | -45000 | 14 | Babic, Marian | -45931 | 14
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7862 | Free Standing CT | REJECTED | No | 2025-09-30 | Yamama, Loai Mohamed | 2025-12-30 | 2025-09-30 |  | 2025-12-30 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45930 | -45930
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7880 | Voltage Transformer | REJECTED | No | 2025-10-02 | Yamama, Loai Mohamed | 2025-10-07 | 2025-10-05 |  | 2025-10-07 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45935 | -45935
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7907 | Power Transformer Heavy Lift Crane | APPROVED | No | 2025-10-06 | Abas, Mohammed Fekry | 2025-10-08 | 2025-10-08 |  |  | 1.1.6.1.3 | 0 | 7773 | 0 | STANDARD | MOHAMMED HAMAD AL-AHMADE FOR TRADING AND CONSTRACTION | SAR | 80000 | APPROVED |  |  | 2025-10-14 | -80000 | 6 | Badhman, Saeed | -45938 | 6
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7908 | Containers Rental for Cable Joints Installations | RETURNED | No | 2025-10-06 | Mohammed, Faisal Ansari | 2025-11-17 | 2025-10-08 | 2025-11-17 |  | Not Required! | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45938 | -45938
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7923 | Installation of 132kV Link Box for Joints & Termination | APPROVED | No | 2025-10-07 | Abas, Mohammed Fekry | 2025-10-08 | 2025-10-08 |  |  | 1.4.4.1.1.31 | 0 | 7228 | 1 | STANDARD | Digital Cables Contracting Co | SAR | 52000 | APPROVED |  |  | 2025-10-16 | -52000 | 8 | Mohammed, Faisal Ansari | -45938 | 8
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7964 | Grounding Materials | APPROVED | No | 2025-10-15 | Abas, Mohammed Fekry | 2025-10-15 | 2025-10-15 |  |  | 1.4.2.1.1.42 | 0 | 7794 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 34430.75 | APPROVED |  |  | 2025-11-10 | -34430.75 | 26 | Muaz, Alaa | -45945 | 26
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7970 | Supply of Fire Stop Material | REJECTED | No | 2025-10-15 | Abdelrahman, Ahmed Shaaban | 2025-10-19 | 2025-10-16 |  | 2025-10-19 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45946 | -45946
105-135 | CONS OF JAZERA ROYAL PALACE SS | 7989 | Stolen Material (Gantry) | APPROVED | No | 2025-10-19 | Abas, Mohammed Fekry | 2025-10-19 | 2025-10-19 |  |  | 1.4.2.1.1.1 | 0 | 5778 | 3 | STANDARD | Hesham Helal Elsewedy & Partners for Construction Co., Ltd. | SAR | 122550 | APPROVED |  |  | 2025-11-06 | -122550 | 18 | Kumar, Mr. Ranjan | -45949 | 18
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8017 | FABRICATION AND SUPPLY OF GRATINGS | APPROVED | No | 2025-10-20 | Abas, Mohammed Fekry | 2025-10-22 | 2025-10-23 |  |  | 1.4.2.1.1.1 | 0 | 7970 | 0 | STANDARD | DROOB AL RIYADAH Est | SAR | 12000 | APPROVED |  |  | 2025-12-17 | -12000 | 55 | Babic, Marian | -45953 | 55
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8031 | Cable Sealing and Joints | APPROVED | No | 2025-10-22 | Abas, Mohammed Fekry | 2025-10-27 | 2025-10-27 |  |  | 1.4.4.1.1.38 | 0 | 6014 | 2 | STANDARD | BRUGG CABLES COMAPNY | SAR | 759000 | APPROVED |  |  | 2025-11-30 | -759000 | 34 | Kumar, Mr. Ranjan | -45957 | 34
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8032 | CONS OF JAZERA ROYAL PALACE SS-HARDWARE FITTINGS (PFISTERER Switzerland | APPROVED | No | 2025-10-22 | Abas, Mohammed Fekry | 2025-10-27 | 2025-10-27 |  |  | 1.4.2.1.1.30 | 0 | 6031 | 0 | STANDARD | PFISTERER Switzerland AG | USD | 1108577.25 | APPROVED |  |  | 2025-11-05 | -1108577.25 | 9 | Babic, Marian | -45957 | 9
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8090 | Fire Stop Supply | INCOMPLETE | No | [6 empty] | 1.4.2.1.1.30 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8094 | Supply of Fire Stop | APPROVED | No | 2025-10-29 | Abas, Mohammed Fekry | 2025-11-02 | 2025-11-04 |  |  | 1.3.3.1.8.59 | 0 | 7878 | 0 | STANDARD | Advanced Destination Company | SAR | 72020 | APPROVED |  |  | 2025-11-27 | -72020 | 23 | Babic, Marian | -45965 | 23
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8129 | Technicians for Testing | REJECTED | No | 2025-11-04 | Yamama, Loai Mohamed | 2025-11-05 | 2025-11-04 |  | 2025-11-05 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45965 | -45965
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8137 | Cable Coating Fire Stop Supply | APPROVED | No | 2025-11-05 | Abas, Mohammed Fekry | 2025-11-06 | 2025-11-09 |  |  | 1.3.3.1.8.59 | 0 | 7878 | 0 | STANDARD | Advanced Destination Company | SAR | 16750 | APPROVED |  |  | 2025-11-27 | -16750 | 18 | Babic, Marian | -45970 | 18
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8145 | Testing Technicians (Manpower Supply) | APPROVED | No | 2025-11-06 | Abas, Mohammed Fekry | 2025-11-06 | 2025-11-09 |  |  | 1.3.5.2.1.1 | 0 | 7829 | 0 | STANDARD | Modern Technical Fields Contracting Est | SAR | 113100 | APPROVED |  |  | 2025-11-17 | -113100 | 8 | Babic, Marian | -45970 | 8
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8149 | LV Lighting Wires(Alfanar) | APPROVED | No | 2025-11-09 | Abas, Mohammed Fekry | 2025-12-23 | 2025-12-24 | 2025-11-17 |  | As we don't have the final approved memo, we will wait until the memo being approved then will proceed with raising the PR | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -46015 | -46015
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8176 | Temporary Solution (telecom) | REJECTED | No | 2025-11-11 | Yamama, Loai Mohamed | 2025-12-17 | 2025-11-13 |  | 2025-12-17 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45974 | -45974
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8234 | Provision of Technical Assistance Services Conductor and OPGW Pulling over HHR Train Bridge between Two Towers | RETURNED | No | 2025-11-16 | Alhadi, Khalid | 2025-12-29 | 2025-11-19 | 2025-12-29 |  | Budget is not sufficient | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45980 | -45980
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8257 | Stolen Busbar - Alfanar | APPROVED | No | 2025-11-18 | Abas, Mohammed Fekry | 2025-11-19 | 2025-11-23 |  |  | 1.3.3.1.8.26 | 0 | 5680 | 1 | STANDARD | ALFANAR CO | SAR | 250000 | IN PROCESS |  |  |  | -250000 | 70 | Kumar, Mr. Ranjan | -45984 | -45984
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8257 | Stolen Busbar - Alfanar | APPROVED | No | 2025-11-18 | Abas, Mohammed Fekry | 2025-11-19 | 2025-11-23 |  |  | 1.3.3.1.8.26 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45984 | -45984
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8345 | ADDITIONAL 60 MTRS UGC CIVIL WORKS | APPROVED | No | 2025-11-25 | Abas, Mohammed Fekry | 2025-11-26 | 2025-11-29 |  |  | 1.4.3.1.1.13 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45990 | -45990
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8383 | Supply & Installation Chain Link Fence | APPROVED | No | 2025-11-27 | Abas, Mohammed Fekry | 2025-12-02 | 2025-12-02 |  |  | 1.3.4.1.1.10 | 0 | 7951 | 0 | STANDARD | MODERN OROUBA GENERAL CONTRACTING CO. | SAR | 191688 | APPROVED |  |  | 2025-12-14 | -191688 | 12 | Abdelraouf, Islam ِAdel Hanafy | -45993 | 12
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8393 | LV Power & Control Cables | RETURNED | No | 2025-11-30 | Badhman, Saeed | 2025-12-10 | 2025-12-02 | 2025-12-10 |  | Douple check qtys (Differ from whats been shared via email) & attach the POCR | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45993 | -45993
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8427 | Remaining Works for Stringing Works | RETURNED | No | 2025-12-02 | Abuhammad, Samir | 2026-01-04 | 2026-01-01 | 2026-01-04 |  | due to budget modification | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46023 | -46023
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8440 | Technicians for Testing | APPROVED | No | 2025-12-03 | Abas, Mohammed Fekry | 2025-12-09 | 2025-12-10 |  |  | 1.3.5.2.1.1 | 0 | 7829 | 1 | STANDARD | Modern Technical Fields Contracting Est | SAR | 86884 | APPROVED |  |  | 2025-12-17 | -86884 | 7 | Babic, Marian | -46001 | 7
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8482 | Supervision during Gassing and De Gassing of 110kV Gas Insulated Switchgear | APPROVED | No | 2025-12-09 | Abas, Mohammed Fekry | 2025-12-11 | 2025-12-11 |  |  | 1.3.3.1.1.1 | 0 | 5879 | 2 | STANDARD | Hyosung Heavy Industries Corporation | USD | 0 | REQUIRES REAPPROVAL |  |  |  | 0 | 52 | Kumar, Mr. Ranjan | -46002 | -46002
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8482 | Supervision during Gassing and De Gassing of 110kV Gas Insulated Switchgear | APPROVED | No | 2025-12-09 | Abas, Mohammed Fekry | 2025-12-11 | 2025-12-11 |  |  | 1.3.3.1.1.1 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46002 | -46002
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8538 | Civil Works | APPROVED | No | 2025-12-17 | Abas, Mohammed Fekry | 2026-01-27 | 2026-01-28 | 2026-01-19 |  | Due to budjet Unavailabilty | 0 | 6534 | 1 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 0 | REQUIRES REAPPROVAL |  |  |  | 0 | 4 | Tananeh, Khalid Jamal | -46050 | -46050
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8538 | Civil Works | APPROVED | No | 2025-12-17 | Abas, Mohammed Fekry | 2026-01-27 | 2026-01-28 | 2026-01-19 |  | Due to budjet Unavailabilty | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -46050 | -46050
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8556 | MV Termination | APPROVED | No | 2025-12-18 | Abas, Mohammed Fekry | 2025-12-30 | 2026-01-01 |  |  | 1.3.5.1.1.36 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46023 | -46023
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8608 | STOLEN MATERIAL (ENERGYA) | APPROVED | No | 2025-12-30 | Abas, Mohammed Fekry | 2025-12-30 | 2026-01-01 |  |  | 1.4.2.1.1.1 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46023 | -46023
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8632 | ACSR Conductor Testing | APPROVED | No | 2026-01-04 | Abas, Mohammed Fekry | 2026-01-12 | 2026-01-13 |  | 2026-01-05 | 1.4.4.2.1.1 | 0 | 15032 | 0 | STANDARD | GCC Electrical power Lab Co. | SAR | 132505 | IN PROCESS | 2026-01-28 | 2026-01-28 |  | -132505 | 19 | Babic, Marian | 15 | -46035
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8632 | ACSR Conductor Testing | APPROVED | No | 2026-01-04 | Abas, Mohammed Fekry | 2026-01-12 | 2026-01-13 |  | 2026-01-05 | 1.4.4.2.1.1 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46035 | -46035
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8669 | Rental of Puller- Tensioner Machine with Operator | RETURNED | No | 2026-01-08 | Abuhammad, Samir | 2026-01-13 | 2026-01-13 | 2026-01-13 |  | Due budget modification. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46035 | -46035
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8691 | Testing Technicians (Manpower Supply) | IN PROCESS | No | 2026-01-12 | Abdelrahman, Ahmed Shaaban | 2026-01-29 | 2026-01-29 |  | 2026-01-14 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46051 | -46051
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8710 | New Drum for FOC | RETURNED | No | 2026-01-15 | Kumar, Mr. Ranjan | 2026-01-29 | 2026-01-19 | 2026-01-29 |  | As informed by PMT this material Purchase by petty cash, PR is returned | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46041 | -46041
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8711 | Supply of Security Guards | INCOMPLETE | No | [6 empty] | As informed by PMT this material Purchase by petty cash, PR is returned | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8753 | COPASA-SAR Foreman | APPROVED | No | 2026-01-21 | Abas, Mohammed Fekry | 2026-01-25 | 2026-01-26 |  |  | 1.4.4.1.1.11 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46048 | -46048
105-135 | CONS OF JAZERA ROYAL PALACE SS | 8823 | SUPPLY AND SUPERVISION AND INSTALLATION OF SHUNT REACTOR | IN PROCESS | No | 2026-01-28 | Abas, Mohammed Fekry | 2026-01-29 | 2026-01-29 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46051 | -46051
105-136 | NEOS core product management | 4435 | NEOS core product management-Supply and deployment of Neos solution | APPROVED | No | 2024-09-12 | Abas, Mohammed Fekry | 2024-09-12 | 2024-09-14 |  |  |  | 18148800 | 6192 | 0 | STANDARD | MeshX PTE LTD | SAR | 18148800 | APPROVED |  |  | 2024-09-16 | 0 | 2 | Abuhammad, Samir | -45549 | 2
105-138 | EXTENSION WORK AT ABU HADRIYAH | 5554 | EXTENSION WORK AT ABU HADRIYAH-Design & Engineering | APPROVED | No | 2025-01-23 | Abas, Mohammed Fekry | 2025-01-26 | 2025-01-27 |  |  |  | 936201.13 | 6658 | 0 | STANDARD | AL-JAZIRAH ENGINEERS & CONSULTANTS Est. | SAR | 770000 | APPROVED |  |  | 2025-02-11 | 166201.13 | 15 | Alqadhi, Abdulrahman Abdulghani | -45684 | 15
105-138 | EXTENSION WORK AT ABU HADRIYAH | 6150 | EXTENSION WORK AT ABU HADRIYAH-Abu Hadriyah-115kV GIS | APPROVED | No | 2025-03-11 | Abas, Mohammed Fekry | 2025-03-20 | 2025-03-20 |  |  | 1.18.3.1.1 | 6253729.03 | 7051 | 0 | STANDARD | HYUNDAI ELECTRIC & ENERGY SYSTEMS CO. LTD | USD | 6000000 | APPROVED |  |  | 2025-04-16 | 253729.03 | 27 | Kumar, Mr. Ranjan | -45736 | 27
105-138 | EXTENSION WORK AT ABU HADRIYAH | 6160 | EXTENSION WORK AT ABU HADRIYAH-Cyber Security Systems for Abu Hadriyah and Remote Ends | APPROVED | No | 2025-03-11 | Abas, Mohammed Fekry | 2025-03-24 | 2025-03-25 |  |  | 1.18.3.6.1 | 877463.11 | 6926 | 0 | STANDARD | ALFANAR CO | SAR | 490000 | APPROVED |  |  | 2025-04-22 | 387463.11 | 28 | Babic, Marian | -45741 | 28
[12 empty] | 1.18.3.11.4.1 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.12.4.1 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.13.4.1 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.14.4.1 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.14.12.1 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.14.15.16 | [14 empty] | 0 | 0
105-138 | EXTENSION WORK AT ABU HADRIYAH | 6177 | EXTENSION WORK AT ABU HADRIYAH-Soil Investigation and Thermal Resistivity and Route Survey for the OHTL | APPROVED | No | 2025-03-12 | Abas, Mohammed Fekry | 2025-03-13 | 2025-03-17 |  |  | 1.19.1.3.1 | 58125 | 7191 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 50000 | APPROVED |  |  | 2025-04-29 | 8125 | 43 | Alhadi, Khalid | -45733 | 43
105-138 | EXTENSION WORK AT ABU HADRIYAH | 6213 | EXTENSION WORK AT ABU HADRIYAH-Protection & Control for Abu Hadriyah and Remote Ends | APPROVED | No | 2025-03-19 | Abas, Mohammed Fekry | 2025-04-08 | 2025-04-08 |  |  | 1.18.3.3.1 | 9316406.73 | 6996 | 0 | STANDARD | ALFANAR CO | SAR | 6510000 | APPROVED |  |  | 2025-04-17 | 2806406.73 | 9 | Babic, Marian | -45755 | 9
[12 empty] | 1.18.3.11.1.1 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.12.1.1 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.13.1.1 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.14.1.1 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.14.9.1 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.14.15.2 | [14 empty] | 0 | 0
105-138 | EXTENSION WORK AT ABU HADRIYAH | 6260 | EXTENSION WORK AT ABU HADRIYAH-Electrical Equipment at Ganty Area for Abu Hadriyah | APPROVED | No | 2025-03-24 | Abas, Mohammed Fekry | 2025-04-13 | 2025-04-14 |  |  | 1.18.3.2.2 | 77296.14 | 7079 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 43764 | APPROVED |  |  | 2025-05-24 | 33532.14 | 40 | Kumar, Mr. Ranjan | -45761 | 40
105-138 | EXTENSION WORK AT ABU HADRIYAH | 6307 | EXTENSION WORK AT ABU HADRIYAH-Abu Hadriyah Site Office | APPROVED | No | 2025-04-08 | Abas, Mohammed Fekry | 2025-04-13 | 2025-04-14 |  |  | 1.18.1.1 | 1022794 | 7404 | 0 | STANDARD | Dynamic Solutions Est. | SAR | 695000 | APPROVED |  |  | 2025-08-02 | 327794 | 110 | Babic, Marian | -45761 | 110
105-138 | EXTENSION WORK AT ABU HADRIYAH | 6328 | EXTENSION WORK AT ABU HADRIYAH-Soil Investigation and Thermal Resistivity Measurement | APPROVED | No | 2025-04-14 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-20 |  |  | 1.19.1.6.1 | 58125 | 7191 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 40000 | APPROVED |  |  | 2025-04-29 | 18125 | 9 | Alhadi, Khalid | -45767 | 9
105-138 | EXTENSION WORK AT ABU HADRIYAH | 6329 | EXTENSION WORK AT ABU HADRIYAH-Soil Investigation and Thermal Resistivity Measurement | APPROVED | No | 2025-04-14 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-20 |  |  | 1.19.1.9.1 | 31875 | 7192 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 30000 | APPROVED |  |  | 2025-04-29 | 1875 | 9 | Alhadi, Khalid | -45767 | 9
105-138 | EXTENSION WORK AT ABU HADRIYAH | 6369 | EXTENSION WORK AT ABU HADRIYAH-Post Insulator for Abu Hadriyah | APPROVED | No | 2025-04-17 | Abas, Mohammed Fekry | 2025-06-02 | 2025-06-02 |  |  | Post Insulator is included in this No. 1.18.3.2.1 of Operation Budget Line. | 78000 | 7481 | 0 | STANDARD | Power Trading T&D | EUR | 66000 | APPROVED |  |  | 2025-07-14 | 12000 | 42 | Babic, Marian | -45810 | 42
[12 empty] | We will raise exception request for over budget. | [14 empty] | 0 | 0
105-138 | EXTENSION WORK AT ABU HADRIYAH | 6464 | EXTENSION WORK AT ABU HADRIYAH-Steel Latticed and Tower Stub Angles for Abu Hadriyah and remote ends | APPROVED | No | 2025-04-27 | Abas, Mohammed Fekry | 2025-06-02 | 2025-06-02 |  |  | 1.18.3.14.16.1 | 4485442.5 | 6977 | 0 | STANDARD | Hesham Helal Elsewedy & Partners for Construction Co., Ltd. | SAR | 4485442.5 | APPROVED |  |  | 2025-06-15 | 0 | 13 | Babic, Marian | -45810 | 13
[12 empty] | 1.18.3.14.17.1 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.14.27.1 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.14.28.1 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.14.35.1 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.14.36.1 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.14.43.1 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.14.44.1 | [14 empty] | 0 | 0
105-138 | EXTENSION WORK AT ABU HADRIYAH | 6471 | EXTENSION WORK AT ABU HADRIYAH-Supply of CVT for Abu Hadriyah | APPROVED | No | 2025-04-28 | Abas, Mohammed Fekry | 2025-06-02 | 2025-06-02 |  |  | 1.18.3.2.1 | 304560 | 7401 | 0 | STANDARD | KONCAR INSTRUMENT TRANSFORMERS | EUR | 282040 | APPROVED |  |  | 2025-08-02 | 22520 | 61 | Babic, Marian | -45810 | 61
105-138 | EXTENSION WORK AT ABU HADRIYAH | 6532 | EXTENSION WORK AT ABU HADRIYAH-Supply of ACSR Conductor for Abu Hadriyah and remote End substations | APPROVED | No | 2025-05-06 | Abas, Mohammed Fekry | 2025-05-12 | 2025-05-14 |  |  | 1.18.3.14.19.1 | 472580.4 | 6852 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 459535.68 | APPROVED |  |  | 2025-05-22 | 13044.72 | 8 | Babic, Marian | -45791 | 8
[12 empty] | 1.18.3.14.25.1 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.14.30.1 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.14.38.1 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.14.46.1 | [14 empty] | 0 | 0
105-138 | EXTENSION WORK AT ABU HADRIYAH | 6891 | EXTENSION WORK AT ABU HADRIYAH-SCADA & DSM | APPROVED | No | 2025-06-25 | Abas, Mohammed Fekry | 2025-06-29 | 2025-06-29 |  |  | 1.18.3.5.1 | 3278123.2 | 7648 | 0 | STANDARD | INNOVATIVE SYSTEMS COMPANY LTD. | SAR | 2250000 | APPROVED |  |  | 2025-09-30 | 1028123.2 | 93 | Alhadi, Khalid | -45837 | 93
[12 empty] | 1.18.3.5.2 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.11.3.1 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.13.3.1 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.13.3.2 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.14.3.1 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.14.3.2 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.14.11.1 | [14 empty] | 0 | 0
[12 empty] | 1.18.3.14.11.2 | [14 empty] | 0 | 0
105-138 | EXTENSION WORK AT ABU HADRIYAH | 6896 | EXTENSION WORK AT ABU HADRIYAH-OPGW and Joint boxes | APPROVED | No | 2025-06-25 | Abas, Mohammed Fekry | 2025-07-03 | 2025-07-03 | 2025-06-29 |  | wrong amount: the PO is 797,960 USD, not 797,960 SAR | 2992350 | 6945 | 0 | STANDARD | ZTT International Limited. | USD | 2992350 | APPROVED |  |  | 2025-07-14 | 0 | 11 | Babic, Marian | -45841 | 11
105-138 | EXTENSION WORK AT ABU HADRIYAH | 6896 | EXTENSION WORK AT ABU HADRIYAH-OPGW and Joint boxes | APPROVED | No | 2025-06-25 | Abas, Mohammed Fekry | 2025-07-03 | 2025-07-03 | 2025-06-29 |  | wrong amount: the PO is 797,960 USD, not 797,960 SAR | 2992350 | 6945 | 1 | STANDARD | ZTT International Limited. | USD | 2992350 | REQUIRES REAPPROVAL |  |  |  | 0 | 213 | Babic, Marian | -45841 | -45841
105-138 | EXTENSION WORK AT ABU HADRIYAH | 6950 | EXTENSION WORK AT ABU HADRIYAH-ACSR Conductor for Abu Hadriyah and remote end substations_additional portion | APPROVED | No | 2025-07-01 | Abas, Mohammed Fekry | 2025-07-03 | 2025-07-03 |  |  | 1.18.3.14.19.1 | 106374 | 6852 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 106374 | APPROVED |  |  | 2025-07-10 | 0 | 7 | Babic, Marian | -45841 | 7
105-138 | EXTENSION WORK AT ABU HADRIYAH | 7026 | EXTENSION WORK AT ABU HADRIYAH-Soil Investigation, Soil scanning for under ground utilities | APPROVED | No | 2025-07-09 | Abas, Mohammed Fekry | 2025-07-14 | 2025-07-14 |  |  | 1.19.1.9.1 | 19500 | 7191 | 1 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 13000 | APPROVED |  |  | 2025-08-02 | 6500 | 19 | Alhadi, Khalid | -45852 | 19
105-138 | EXTENSION WORK AT ABU HADRIYAH | 7165 | EXTENSION WORK AT ABU HADRIYAH-Post Insulator suspended at Gantry to fix AL. Tube | APPROVED | No | 2025-07-21 | Abas, Mohammed Fekry | 2025-07-22 | 2025-07-22 |  |  | 1.18.3.14.18.1 | 33000 | 7481 | 1 | STANDARD | Power Trading T&D | EUR | 33000 | APPROVED |  |  | 2025-07-29 | 0 | 7 | Babic, Marian | -45860 | 7
105-138 | EXTENSION WORK AT ABU HADRIYAH | 7252 | EXTENSION WORK AT ABU HADRIYAH-Site Survey for Abu Hadriyah and Tanajib and Drawing Existing Towers | APPROVED | No | 2025-07-31 | Abas, Mohammed Fekry | 2025-08-03 | 2025-08-03 |  |  | 1.19.1.6.1 | 9000 | 7192 | 1 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 7000 | APPROVED |  |  | 2025-08-28 | 2000 | 25 | Alhadi, Khalid | -45872 | 25
105-138 | EXTENSION WORK AT ABU HADRIYAH | 7270 | EXTENSION WORK AT ABU HADRIYAH-Supply and Apply Grading, Leveling and General fill compaction (with big roller) for the Access road with thickness of 30cm in two layers | APPROVED | No | 2025-08-04 | Abas, Mohammed Fekry | 2025-08-05 | 2025-08-05 |  |  | 1.18.1.1 | 21060 | 7404 | 1 | STANDARD | Dynamic Solutions Est. | SAR | 19560 | APPROVED |  |  | 2025-10-05 | 1500 | 61 | Babic, Marian | -45874 | 61
105-138 | EXTENSION WORK AT ABU HADRIYAH | 7366 | Construction of Access Road | RETURNED | No | 2025-08-17 | Tananeh, Khalid Jamal | 2025-10-23 | 2025-08-25 | 2025-10-23 |  | This PR has been returned because all civil works will be assigned to a single contractor. Therefore, please raise a new PR that includes all civil works as per the latest Civil BOQ. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45894 | -45894
105-138 | EXTENSION WORK AT ABU HADRIYAH | 7451 | Grounding Materials & Accessories | RETURNED | No | 2025-08-24 | Babic, Marian | 2025-09-22 | 2025-08-28 | 2025-09-22 |  | this is not in SEICO scope. please try to buy by petty cash | 0 | 7677 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 63715.1 | APPROVED |  |  | 2025-09-16 | -63715.1 |  | Babic, Marian | -45897 | 19
105-138 | EXTENSION WORK AT ABU HADRIYAH | 7451 | Grounding Materials & Accessories | RETURNED | No | 2025-08-24 | Babic, Marian | 2025-09-22 | 2025-08-28 | 2025-09-22 |  | this is not in SEICO scope. please try to buy by petty cash | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45897 | -45897
105-138 | EXTENSION WORK AT ABU HADRIYAH | 7534 | Telecommunication | APPROVED | No | 2025-08-27 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-03 |  |  | Please approve | 0 | 7678 | 0 | STANDARD | AMWAJ TELECOMMUNICATION MFG. CO. | SAR | 30548 | APPROVED |  |  | 2025-09-29 | -30548 | 26 | Babic, Marian | -45903 | 26
105-138 | EXTENSION WORK AT ABU HADRIYAH | 7534 | Telecommunication | APPROVED | No | 2025-08-27 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-03 |  |  | Please approve | 0 | 7678 | 1 | STANDARD | AMWAJ TELECOMMUNICATION MFG. CO. | SAR | 19600 | APPROVED |  |  | 2025-10-14 | -19600 | 41 | Babic, Marian | -45903 | 41
105-138 | EXTENSION WORK AT ABU HADRIYAH | 7619 | Auxiliary Power Supply Reinforcement items | APPROVED | No | 2025-09-02 | Abas, Mohammed Fekry | 2025-09-09 | 2025-09-10 |  |  | Please approve | 0 | 7849 | 0 | STANDARD | META SWITCHGEAR Factory | SAR | 35000 | APPROVED |  |  | 2025-11-12 | -35000 | 63 | Babic, Marian | -45910 | 63
105-138 | EXTENSION WORK AT ABU HADRIYAH | 7623 | Connectors and Terminals | APPROVED | No | 2025-09-02 | Abas, Mohammed Fekry | 2025-09-09 | 2025-09-10 |  |  | Please approve | 0 | 7570 | 0 | STANDARD | Arruti Subestaciones , S.A.U | EUR | 45539.64 | APPROVED |  |  | 2025-09-25 | -45539.64 | 15 | Babic, Marian | -45910 | 15
105-138 | EXTENSION WORK AT ABU HADRIYAH | 7675 | Tower Foundation | RETURNED | No | 2025-09-08 | Tananeh, Khalid Jamal | 2025-10-23 | 2025-09-10 | 2025-10-23 |  | This PR has been returned because all civil works will be assigned to a single contractor. Therefore, please raise a new PR that includes all civil works as per the latest Civil BOQ. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45910 | -45910
105-138 | EXTENSION WORK AT ABU HADRIYAH | 7694 | OPGW and Joint Box | RETURNED | No | 2025-09-09 | Babic, Marian | 2025-10-26 | 2025-09-10 | 2025-10-26 |  | please resubmit after clearing open points with vendor and client | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45910 | -45910
105-138 | EXTENSION WORK AT ABU HADRIYAH | 7719 | connectors and terminals | APPROVED | No | 2025-09-11 | Abas, Mohammed Fekry | 2025-09-14 | 2025-09-16 |  |  | Please approve | 0 | 7570 | 0 | STANDARD | Arruti Subestaciones , S.A.U | EUR | 2802.2 | APPROVED |  |  | 2025-09-25 | -2802.2 | 9 | Babic, Marian | -45916 | 9
105-138 | EXTENSION WORK AT ABU HADRIYAH | 7721 | Custom Duty Fees for imported Materials for Hardware Connector's | APPROVED | No | 2025-09-11 | Abas, Mohammed Fekry | 2025-09-14 | 2025-09-16 |  |  | Custom Duty Fees for imported Materials for Hardware and connector's | 0 | 7570 | 0 | STANDARD | Arruti Subestaciones , S.A.U | EUR | 9163 | APPROVED |  |  | 2025-09-25 | -9163 | 9 | Babic, Marian | -45916 | 9
105-138 | EXTENSION WORK AT ABU HADRIYAH | 7724 | OPGW and Joint Box | RETURNED | No | 2025-09-11 | Babic, Marian | 2025-10-26 | 2025-09-17 | 2025-10-26 |  | please resubmit after clearing open points with vendor and client | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45917 | -45917
105-138 | EXTENSION WORK AT ABU HADRIYAH | 7726 | Spacer Dampers and Vibration Dampers | APPROVED | No | 2025-09-14 | Abas, Mohammed Fekry | 2025-09-16 | 2025-09-17 |  |  | Please approve | 0 | 7725 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 118750 | APPROVED |  |  | 2025-09-29 | -118750 | 12 | Babic, Marian | -45917 | 12
105-138 | EXTENSION WORK AT ABU HADRIYAH | 7735 | Security Guard | APPROVED | No | 2025-09-14 | Abas, Mohammed Fekry | 2025-09-16 | 2025-09-16 |  |  | Please approve | 0 | 7734 | 0 | STANDARD | Al-Nufuth Al-Mutamayiza For Security Company | SAR | 323000 | APPROVED |  |  | 2025-09-30 | -323000 | 14 | Abuhammad, Samir | -45916 | 14
105-138 | EXTENSION WORK AT ABU HADRIYAH | 7735 | Security Guard | APPROVED | No | 2025-09-14 | Abas, Mohammed Fekry | 2025-09-16 | 2025-09-16 |  |  | Please approve | 0 | 7778 | 0 | STANDARD | Al-Nufuth Al-Mutamayiza For Security Company | SAR | 323000 | APPROVED |  |  | 2025-10-28 | -323000 | 42 | Abuhammad, Samir | -45916 | 42
105-138 | EXTENSION WORK AT ABU HADRIYAH | 7827 | Aluminium Tube Bus Bars | APPROVED | No | 2025-09-25 | Abas, Mohammed Fekry | 2025-10-01 | 2025-10-01 |  |  | Please approve | 0 | 7776 | 0 | STANDARD | LORUNSER AUSTRIA GmbH | EUR | 58761.2 | APPROVED |  |  | 2025-11-30 | -58761.2 | 60 | Babic, Marian | -45931 | 60
105-138 | EXTENSION WORK AT ABU HADRIYAH | 7828 | Small, back up generator for emergency and small site office loads | APPROVED | No | 2025-09-25 | Abas, Mohammed Fekry | 2025-10-01 | 2025-10-01 |  |  | please approve | 0 | 7807 | 0 | STANDARD | Mohammed A. AlFaddaghi & Partners | SAR | 64000 | APPROVED |  |  | 2025-10-27 | -64000 | 26 | Babic, Marian | -45931 | 26
105-138 | EXTENSION WORK AT ABU HADRIYAH | 7928 | Telecom Tower Relocation | APPROVED | No | 2025-10-08 | Abas, Mohammed Fekry | 2025-10-12 | 2025-10-12 |  |  | Please approve | 0 | 7274 | 0 | STANDARD | BAUD TELECOM COMPANY | SAR | 1200000 | APPROVED |  |  | 2025-10-21 | -1200000 | 9 | Babic, Marian | -45942 | 9
105-138 | EXTENSION WORK AT ABU HADRIYAH | 8085 | Communication System | APPROVED | No | 2025-10-28 | Abas, Mohammed Fekry | 2025-10-29 | 2025-10-30 |  |  | Please approve | 0 | 6997 | 0 | STANDARD | ALFANAR CO | SAR | 15000000 | APPROVED |  |  | 2025-11-11 | -15000000 | 12 | Babic, Marian | -45960 | 12
105-138 | EXTENSION WORK AT ABU HADRIYAH | 8089 | Grounding, Shielding system & Lightning Protection for SS | APPROVED | No | 2025-10-29 | Abas, Mohammed Fekry | 2026-01-06 | 2026-01-07 | 2025-12-31 |  | please update as per latest BOQ | 0 | 7677 | 2 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 11101.85 | APPROVED | 2025-12-25 | 2026-01-01 | 2026-01-07 | -11101.85 | 0 | Babic, Marian | -6 | 0
105-138 | EXTENSION WORK AT ABU HADRIYAH | 8089 | Grounding, Shielding system & Lightning Protection for SS | APPROVED | No | 2025-10-29 | Abas, Mohammed Fekry | 2026-01-06 | 2026-01-07 | 2025-12-31 |  | please update as per latest BOQ | 0 | 8035 | 0 | STANDARD |  | SAR | 0 | INCOMPLETE |  |  |  | 0 | 25 | Mohammed, Mohammed Adel Fahmy | -46029 | -46029
105-138 | EXTENSION WORK AT ABU HADRIYAH | 8089 | Grounding, Shielding system & Lightning Protection for SS | APPROVED | No | 2025-10-29 | Abas, Mohammed Fekry | 2026-01-06 | 2026-01-07 | 2025-12-31 |  | please update as per latest BOQ | 0 | 15035 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 21892.87 | APPROVED | 2026-01-11 | 2026-01-13 | 2026-01-18 | -21892.87 | 11 | Babic, Marian | 6 | 11
105-138 | EXTENSION WORK AT ABU HADRIYAH | 8089 | Grounding, Shielding system & Lightning Protection for SS | APPROVED | No | 2025-10-29 | Abas, Mohammed Fekry | 2026-01-06 | 2026-01-07 | 2025-12-31 |  | please update as per latest BOQ | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46029 | -46029
105-138 | EXTENSION WORK AT ABU HADRIYAH | 8211 | Diesel for Generator | REJECTED | No | 2025-11-13 | Ibrahim, Mahmoud Hassan Ali | 2025-11-13 | 2025-11-13 |  | 2025-11-13 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45974 | -45974
105-138 | EXTENSION WORK AT ABU HADRIYAH | 8212 | Raw Water | REJECTED | No | 2025-11-13 | Ibrahim, Mahmoud Hassan Ali | 2025-11-13 | 2025-11-13 |  | 2025-11-13 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45974 | -45974
105-138 | EXTENSION WORK AT ABU HADRIYAH | 8214 | Water for Septic Tank | REJECTED | No | 2025-11-13 | Ibrahim, Mahmoud Hassan Ali | 2025-11-13 | 2025-11-13 |  | 2025-11-13 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45974 | -45974
105-138 | EXTENSION WORK AT ABU HADRIYAH | 8220 | Diesel for Generator | APPROVED | No | 2025-11-13 | Abas, Mohammed Fekry | 2025-11-20 | 2025-11-23 |  | 2025-11-17 | Please approve this superseded PR for Diesel of Generator | 0 | 7932 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 102900 | APPROVED |  |  | 2025-12-03 | -102900 | 10 | Akhtar, Farhan | -45984 | 10
105-138 | EXTENSION WORK AT ABU HADRIYAH | 8221 | Raw Water & Septic Tank | RETURNED | No | 2025-11-13 | Akhtar, Farhan | 2025-12-08 | 2025-11-23 | 2025-12-08 | 2025-11-13 | Kindly submit the budgted PR | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45984 | -45984
105-138 | EXTENSION WORK AT ABU HADRIYAH | 8232 | Grounding & Accessories Additional_3 | RETURNED | No | 2025-11-16 | Babic, Marian | 2025-12-31 | 2025-11-19 | 2025-12-31 |  | please update as per latest BOQ | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45980 | -45980
105-138 | EXTENSION WORK AT ABU HADRIYAH | 8328 | Safety PPE Requirments | REJECTED | No | 2025-11-24 | Ibrahim, Mahmoud Hassan Ali | 2025-11-24 | 2025-11-24 |  | 2025-11-26 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45985 | -45985
105-138 | EXTENSION WORK AT ABU HADRIYAH | 8379 | Composite Insulator | APPROVED | No | 2025-11-27 | Abas, Mohammed Fekry | 2025-12-07 | 2025-12-09 |  |  | Revised PR based on a final Quotation | 0 | 7901 | 0 | STANDARD | PFISTERER Switzerland AG | USD | 1479639.38 | APPROVED |  |  | 2025-12-24 | -1479639.38 | 15 | Babic, Marian | -46000 | 15
105-138 | EXTENSION WORK AT ABU HADRIYAH | 8408 | LV, Control & F.O Cable with Termination | APPROVED | No | 2025-12-01 | Abas, Mohammed Fekry | 2025-12-07 | 2025-12-09 |  |  | Modified as per Updated Quotation | 0 | 8011 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 836084.18 | APPROVED | 2025-12-23 | 2026-01-01 | 2026-01-05 | -836084.18 | 27 | Alhadi, Khalid | 23 | 27
105-138 | EXTENSION WORK AT ABU HADRIYAH | 8455 | Transient fault recorder panel | APPROVED | No | 2025-12-07 | Abas, Mohammed Fekry | 2025-12-09 | 2025-12-09 |  |  | Revised TFR Please approve | 0 | 15023 | 0 | STANDARD | SAUDI ARABIAN INDUSTRIAL & TRADING Co. | SAR | 280000 | IN PROCESS | 2026-01-15 | 2026-01-20 |  | -280000 | 54 | Babic, Marian | 42 | -46000
105-138 | EXTENSION WORK AT ABU HADRIYAH | 8455 | Transient fault recorder panel | APPROVED | No | 2025-12-07 | Abas, Mohammed Fekry | 2025-12-09 | 2025-12-09 |  |  | Revised TFR Please approve | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46000 | -46000
105-138 | EXTENSION WORK AT ABU HADRIYAH | 8456 | SOE System | APPROVED | No | 2025-12-07 | Abas, Mohammed Fekry | 2026-01-19 | 2026-01-20 | 2026-01-15 |  | as discussed, PR to be issud from different task line with sufficient budget | 0 | 15025 | 0 | STANDARD | TRINERGY TECHNOLOGIES SA | SAR | 300000 | IN PROCESS | 2026-01-22 | 2026-01-26 |  | -300000 | 12 | Babic, Marian | 6 | -46042
105-138 | EXTENSION WORK AT ABU HADRIYAH | 8456 | SOE System | APPROVED | No | 2025-12-07 | Abas, Mohammed Fekry | 2026-01-19 | 2026-01-20 | 2026-01-15 |  | as discussed, PR to be issud from different task line with sufficient budget | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46042 | -46042
105-138 | EXTENSION WORK AT ABU HADRIYAH | 8457 | DSM System | APPROVED | No | 2025-12-07 | Abas, Mohammed Fekry | 2025-12-09 | 2025-12-09 |  |  | Revised DSM please approve | 0 | 15026 | 0 | STANDARD | Al-Haider Company For Cont.- Hadi Saleh Al-Haider & Partner Co. | SAR | 487950 | IN PROCESS | 2026-01-15 | 2026-01-20 |  | -487950 | 54 | Babic, Marian | 42 | -46000
105-138 | EXTENSION WORK AT ABU HADRIYAH | 8457 | DSM System | APPROVED | No | 2025-12-07 | Abas, Mohammed Fekry | 2025-12-09 | 2025-12-09 |  |  | Revised DSM please approve | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46000 | -46000
105-138 | EXTENSION WORK AT ABU HADRIYAH | 8630 | Civil Work for Abu Hadriyah Extention | APPROVED | No | 2026-01-01 | Abas, Mohammed Fekry | 2026-01-06 | 2026-01-07 |  | 2026-01-01 | Civil Work for Abu Hadriyah Extention | 0 | 7851 | 0 | STANDARD | Termez Al - Mataqdema ltd. | SAR | 5574763.66 | APPROVED | 2026-01-07 | 2026-01-13 | 2026-01-19 | -5574763.66 | 12 | Tananeh, Khalid Jamal | 6 | 12
105-138 | EXTENSION WORK AT ABU HADRIYAH | 8692 | OHTL Installation Works | RETURNED | No | 2026-01-12 | Abuhammad, Samir | 2026-01-27 | 2026-01-14 | 2026-01-27 |  | Due Budget Modification | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46036 | -46036
105-138 | EXTENSION WORK AT ABU HADRIYAH | 8752 | Installation Activities inside Substations | APPROVED | No | 2026-01-20 | Abas, Mohammed Fekry | 2026-01-21 | 2026-01-22 |  |  | Task - 1.6.1 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46044 | -46044
105-139 | Neom NC1 School CCTV | 5389 | Neom NC1 School CCTV-PR for Neom School Project-Ethernet Switches & Accessories | REJECTED | No | 2025-01-12 | Yamama, Loai Mohamed | 2025-01-16 | 2025-01-13 |  | 2025-01-16 |  | 66282.94 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45670 | -45670
105-139 | Neom NC1 School CCTV | 5390 | Neom NC1 School CCTV-NC1 -Old &New School-Camera Supply & Professional Service | REJECTED | No | 2025-01-12 | Yamama, Loai Mohamed | 2025-01-16 | 2025-01-13 |  | 2025-01-16 |  | 172508 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45670 | -45670
105-139 | Neom NC1 School CCTV | 5446 | Neom NC1 School CCTV-PR For Neom School Project-Ethernet Accessories | APPROVED | No | 2025-01-16 | Abas, Mohammed Fekry | 2025-01-22 | 2025-01-23 |  |  |  | 66282.58 | 6834 | 0 | STANDARD | Bayt Al Egada for Trading and Technology | SAR | 66268 | APPROVED |  |  | 2025-02-05 | 14.58 | 13 | Abuhammad, Samir | -45680 | 13
105-139 | Neom NC1 School CCTV | 5455 | Neom NC1 School CCTV-NC1 -Old School-Camera Supply & Professional Service | APPROVED | No | 2025-01-19 | Abas, Mohammed Fekry | 2025-01-22 | 2025-01-23 |  |  |  | 128632 | 6812 | 0 | STANDARD | Zamil Group Trade & Service Co | SAR | 152211 | APPROVED |  |  | 2025-02-05 | -23579 | 13 | Abuhammad, Samir | -45680 | 13
105-139 | Neom NC1 School CCTV | 5457 | Neom NC1 School CCTV-Neom NC1 School CCTV-NC1 -New School-Camera Supply & Professional Service | APPROVED | No | 2025-01-19 | Abas, Mohammed Fekry | 2025-01-22 | 2025-01-23 |  |  |  | 43876 | 6812 | 0 | STANDARD | Zamil Group Trade & Service Co | SAR | 150784 | APPROVED |  |  | 2025-02-05 | -106908 | 13 | Abuhammad, Samir | -45680 | 13
105-140 | 380kV BSP#9077 RUMAH A&B | 5506 | 380kV BSP#9077 RUMAH A&B-Engineering Design Service ( BCG ) | INCOMPLETE | No |  | Jaber, Mohammed Ali | 2025-01-21 |  |  |  |  | 7 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
105-140 | 380kV BSP#9077 RUMAH A&B | 5512 | 380kV BSP#9077 RUMAH A&B-Engineering Design Service ( BCG ) to convert manual PO# 8857 to Oracle PO | APPROVED | No | 2025-01-21 | Abas, Mohammed Fekry | 2025-01-26 | 2025-01-27 |  |  |  | 3262500.41 | 6850 | 0 | STANDARD | Bahrawy Consultancy Group B.C.G | USD | 5756523.04 | APPROVED |  |  | 2025-02-05 | -2494022.63 | 9 | Kumar, Mr. Ranjan | -45684 | 9
105-140 | 380kV BSP#9077 RUMAH A&B | 5526 | 380kV BSP#9077 RUMAH A&B-Site Office, Mobilization (budget line item 1.9.1.1 ) | APPROVED | No | 2025-01-21 | Abas, Mohammed Fekry | 2025-01-26 | 2025-01-27 |  |  |  | 2400000 | 6888 | 0 | STANDARD | Dynamic Solutions Est. | SAR | 2250765 | APPROVED |  |  | 2025-02-13 | 149235 | 17 | Kumar, Mr. Ranjan | -45684 | 17
105-140 | 380kV BSP#9077 RUMAH A&B | 5708 | 380kV BSP#9077 RUMAH A&B-HGIS and GIB for PS3 (Convert Manual PO#8862 to Oracle PO) | APPROVED | No | 2025-01-28 | Abas, Mohammed Fekry | 2025-01-30 | 2025-01-30 |  |  |  | 63561855.26 | 6851 | 0 | STANDARD | BRANCH OF COGELECX | SAR | 63400000 | APPROVED |  |  | 2025-02-16 | 161855.26 | 17 | Kumar, Mr. Ranjan | -45687 | 17
105-140 | 380kV BSP#9077 RUMAH A&B | 5710 | 380kV BSP#9077 RUMAH A&B-33Kv SWGR - RUMAH | APPROVED | No | 2025-01-28 | Abas, Mohammed Fekry | 2025-01-30 | 2025-01-30 |  |  |  | 2984999.99 | 6889 | 0 | STANDARD | SIEMENS LIMITED | SAR | 1875000 | APPROVED |  |  | 2025-02-19 | 1109999.99 | 20 | Kumar, Mr. Ranjan | -45687 | 20
105-140 | 380kV BSP#9077 RUMAH A&B | 5841 | 380kV BSP#9077 RUMAH A&B-Environmental & Social Impact Assessment for RUMAH BSP | APPROVED | No | 2025-02-10 | Abas, Mohammed Fekry | 2025-02-16 | 2025-02-16 |  |  |  | 196613.59 | 6927 | 0 | STANDARD | Abnia Environmental Consultants Est. | SAR | 38700 | APPROVED |  |  | 2025-02-25 | 157913.59 | 9 | Alhadi, Khalid | -45704 | 9
105-140 | 380kV BSP#9077 RUMAH A&B | 5842 | 380kV BSP#9077 RUMAH A&B-ESIA Study Airport North BSP | APPROVED | No | 2025-02-10 | Abas, Mohammed Fekry | 2025-02-16 | 2025-02-16 |  |  |  | 5462.14 | 6927 | 0 | STANDARD | Abnia Environmental Consultants Est. | SAR | 5400 | APPROVED |  |  | 2025-02-25 | 62.14 | 9 | Alhadi, Khalid | -45704 | 9
105-140 | 380kV BSP#9077 RUMAH A&B | 5843 | 380kV BSP#9077 RUMAH A&B-Environmental & Social Impact Assessment - PS3 | APPROVED | No | 2025-02-10 | Abas, Mohammed Fekry | 2025-02-16 | 2025-02-16 |  |  |  | 10924 | 6927 | 0 | STANDARD | Abnia Environmental Consultants Est. | SAR | 10900 | APPROVED |  |  | 2025-02-25 | 24 | 9 | Alhadi, Khalid | -45704 | 9
105-140 | 380kV BSP#9077 RUMAH A&B | 6013 | 380kV BSP#9077 RUMAH A&B-municipality permit | APPROVED | No | 2025-02-20 | Abas, Mohammed Fekry | 2025-03-02 | 2025-03-03 |  |  |  | 50000 | 6924 | 0 | STANDARD | AlGhanem Engineering Co | SAR | 25000 | APPROVED |  |  | 2025-04-14 | 25000 | 42 | Alhadi, Khalid | -45719 | 42
105-140 | 380kV BSP#9077 RUMAH A&B | 6082 | 380kV BSP#9077 RUMAH A&B-240mm bare copper | APPROVED | No | 2025-02-27 | Abas, Mohammed Fekry | 2025-03-04 | 2025-03-05 |  |  |  | 1783948.72 | 6959 | 0 | STANDARD | Hesham El-Sewedy Trading Co. LTD. | SAR | 1780853.02 | APPROVED |  |  | 2025-04-23 | 3095.7 | 49 | Badhman, Saeed | -45721 | 49
105-140 | 380kV BSP#9077 RUMAH A&B | 6082 | 380kV BSP#9077 RUMAH A&B-240mm bare copper | APPROVED | No | 2025-02-27 | Abas, Mohammed Fekry | 2025-03-04 | 2025-03-05 |  |  |  | 1783948.72 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45721 | -45721
105-140 | 380kV BSP#9077 RUMAH A&B | 6086 | 380kV BSP#9077 RUMAH A&B-PT / Reactors | APPROVED | No | 2025-02-27 | Abas, Mohammed Fekry | 2025-03-04 | 2025-03-05 |  |  |  | 82500000 | 6999 | 0 | STANDARD | Hitachi Energy Ltd | USD | 82500000 | APPROVED |  |  | 2025-03-18 | 0 | 13 | Kumar, Mr. Ranjan | -45721 | 13
105-140 | 380kV BSP#9077 RUMAH A&B | 6086 | 380kV BSP#9077 RUMAH A&B-PT / Reactors | APPROVED | No | 2025-02-27 | Abas, Mohammed Fekry | 2025-03-04 | 2025-03-05 |  |  |  | 82500000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45721 | -45721
105-140 | 380kV BSP#9077 RUMAH A&B | 6101 | 380kV BSP#9077 RUMAH A&B-Station Service Transformer | APPROVED | No | 2025-03-03 | Abas, Mohammed Fekry | 2025-03-12 | 2025-03-13 |  |  |  | 390000 | 7007 | 0 | STANDARD | UNITED TRANSFORMERS ELECTRIC COMPANY (UTEC) | SAR | 376000 | APPROVED |  |  | 2025-03-24 | 14000 | 11 | Kumar, Mr. Ranjan | -45729 | 11
105-140 | 380kV BSP#9077 RUMAH A&B | 6196 | 380kV BSP#9077 RUMAH A&B-Precast Structures | APPROVED | No | 2025-03-18 | Abas, Mohammed Fekry | 2025-03-23 | 2025-03-24 |  |  |  | 14927403 | 7009 | 0 | STANDARD | Rabiah Nassar and Zamil Concrete Industries Co. Ltd | SAR | 14927403 | APPROVED |  |  | 2025-04-17 | 0 | 24 | Tananeh, Khalid Jamal | -45740 | 24
105-140 | 380kV BSP#9077 RUMAH A&B | 6197 | 380kV BSP#9077 RUMAH A&B-Access Road | APPROVED | No | 2025-03-18 | Abas, Mohammed Fekry | 2025-03-23 | 2025-03-24 |  |  |  | 312000 | 7149 | 0 | STANDARD | Sam OG Construction | SAR | 280000 | APPROVED |  |  | 2025-04-17 | 32000 | 24 | Tananeh, Khalid Jamal | -45740 | 24
105-140 | 380kV BSP#9077 RUMAH A&B | 6286 | 380kV BSP#9077 RUMAH A&B-C&P, Telecom and SAS | APPROVED | No | 2025-04-09 | Abas, Mohammed Fekry | 2025-04-13 | 2025-04-14 |  |  |  | 47974950 | 6886 | 1 | STANDARD | SIEMENS LIMITED | SAR | 47974950 | APPROVED |  |  | 2025-04-21 | 0 | 7 | Kumar, Mr. Ranjan | -45761 | 7
105-140 | 380kV BSP#9077 RUMAH A&B | 6287 | 380kV BSP#9077 RUMAH A&B-Civil Subcontractor | APPROVED | No | 2025-03-28 | Abas, Mohammed Fekry | 2025-04-07 | 2025-04-08 |  |  |  | 79500000 | 7113 | 0 | STANDARD | AL JABAL AL ARABIA CONTRACTING CO | SAR | 79500000 | APPROVED |  |  | 2025-04-17 | 0 | 9 | Tananeh, Khalid Jamal | -45755 | 9
105-140 | 380kV BSP#9077 RUMAH A&B | 6288 | 380kV BSP#9077 RUMAH A&B-Topographic Survey | APPROVED | No | 2025-03-28 | Abas, Mohammed Fekry | 2025-04-06 | 2025-04-06 |  |  |  | 73000 | 7134 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 73000 | APPROVED |  |  | 2025-04-15 | 0 | 9 | Kumar, Mr. Ranjan | -45753 | 9
105-140 | 380kV BSP#9077 RUMAH A&B | 6301 | 380kV BSP#9077 RUMAH A&B-Third Party lab Inspector For Precast Concrete Prodaction Test | APPROVED | No | 2025-04-07 | Abas, Mohammed Fekry | 2025-04-14 | 2025-04-15 |  |  |  | 162780 | 7153 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 162780 | APPROVED |  |  | 2025-04-24 | 0 | 9 | Tananeh, Khalid Jamal | -45762 | 9
105-140 | 380kV BSP#9077 RUMAH A&B | 6308 | 380kV BSP#9077 RUMAH A&B-site mobilization | APPROVED | No | 2025-04-08 | Abas, Mohammed Fekry | 2025-04-14 | 2025-04-15 |  |  |  | 185000 | 6888 | 2 | STANDARD | Dynamic Solutions Est. | SAR | 122750 | APPROVED |  |  | 2025-06-24 | 62250 | 70 | Kumar, Mr. Ranjan | -45762 | 70
105-140 | 380kV BSP#9077 RUMAH A&B | 6309 | 380kV BSP#9077 RUMAH A&B-Geotechnical Investigation | APPROVED | No | 2025-04-09 | Abas, Mohammed Fekry | 2025-04-14 | 2025-04-15 |  |  |  | 86250 | 7307 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 83000 | APPROVED |  |  | 2025-05-24 | 3250 | 39 | Alhadi, Khalid | -45762 | 39
105-140 | 380kV BSP#9077 RUMAH A&B | 6347 | 380kV BSP#9077 RUMAH A&B-Earthing Materials | APPROVED | No | 2025-04-16 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-20 |  |  |  | 157112.83 | 6975 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 157112.83 | APPROVED |  |  | 2025-06-19 | 0 | 60 | Badhman, Saeed | -45767 | 60
105-140 | 380kV BSP#9077 RUMAH A&B | 6349 | 380kV BSP#9077 RUMAH A&B-EOT for RUMAH A | APPROVED | No | 2025-04-16 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-20 |  |  |  | 250000 | 7148 | 0 | STANDARD | SAUDI CRANES & STEEL WORKS FACTORY LTD | SAR | 232000 | APPROVED |  |  | 2025-04-28 | 18000 | 8 | Kumar, Mr. Ranjan | -45767 | 8
105-140 | 380kV BSP#9077 RUMAH A&B | 6350 | 380kV BSP#9077 RUMAH A&B-EOT for RUMAH B | APPROVED | No | 2025-04-16 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-20 |  |  |  | 250000 | 7148 | 0 | STANDARD | SAUDI CRANES & STEEL WORKS FACTORY LTD | SAR | 233000 | APPROVED |  |  | 2025-04-28 | 17000 | 8 | Kumar, Mr. Ranjan | -45767 | 8
105-140 | 380kV BSP#9077 RUMAH A&B | 6351 | 380kV BSP#9077 RUMAH A&B-PDMS | APPROVED | No | 2025-04-16 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-20 |  |  |  | 3222319 | 7548 | 0 | STANDARD | Qualitrol Hathaway Instruments Company | USD | 2589236.25 | APPROVED |  |  | 2025-10-27 | 633082.75 | 190 | Kumar, Mr. Ranjan | -45767 | 190
105-140 | 380kV BSP#9077 RUMAH A&B | 6378 | 380kV BSP#9077 RUMAH A&B-HCIS Security system cnsultancy | APPROVED | No | 2025-04-19 | Abas, Mohammed Fekry | 2025-04-21 | 2025-04-22 |  |  |  | 195000 | 7150 | 0 | STANDARD | ARMADA Security Consulting | SAR | 195000 | APPROVED |  |  | 2025-05-01 | 0 | 9 | Kumar, Mr. Ranjan | -45769 | 9
105-140 | 380kV BSP#9077 RUMAH A&B | 6407 | 380kV BSP#9077 RUMAH A&B-Cyber Security | APPROVED | No | 2025-04-21 | Abas, Mohammed Fekry | 2025-04-22 | 2025-04-22 |  |  |  | 1200000 | 7156 | 0 | STANDARD | ACET SOLUTIONS LLC | SAR | 1149999 | APPROVED |  |  | 2025-04-29 | 50001 | 7 | Kumar, Mr. Ranjan | -45769 | 7
105-140 | 380kV BSP#9077 RUMAH A&B | 6444 | 380kV BSP#9077 RUMAH A&B-GIS / HGIS for RUMAH and Airport North | APPROVED | No | 2025-04-24 | Abas, Mohammed Fekry | 2025-04-27 | 2025-04-27 |  |  |  | 270014659.39 | 7206 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 270000000 | APPROVED |  |  | 2025-04-28 | 14659.39 | 1 | Kumar, Mr. Ranjan | -45774 | 1
105-140 | 380kV BSP#9077 RUMAH A&B | 6465 | 380kV BSP#9077 RUMAH A&B-Diesel supply | APPROVED | No | 2025-04-27 | Abas, Mohammed Fekry | 2025-04-28 | 2025-04-28 |  |  |  | 1329310 | 7289 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 2600812.35 | APPROVED |  |  | 2025-06-03 | -1271502.35 | 36 | Akhtar, Farhan | -45775 | 36
105-140 | 380kV BSP#9077 RUMAH A&B | 6565 | 380kV BSP#9077 RUMAH A&B-surveying equipment | APPROVED | No | 2025-05-07 | Abas, Mohammed Fekry | 2025-05-12 | 2025-05-14 |  |  |  | 113200 | 7280 | 0 | STANDARD | ALBOKSOMATTI FOR SURVEYING COMPANY(S) | SAR | 103200 | APPROVED |  |  | 2025-06-24 | 10000 | 41 | Kumar, Mr. Ranjan | -45791 | 41
105-140 | 380kV BSP#9077 RUMAH A&B | 6603 | 380kV BSP#9077 RUMAH A&B-Kitchen Items | APPROVED | No | 2025-05-13 | Abas, Mohammed Fekry | 2025-05-15 | 2025-05-15 |  |  |  | 115000 | 7290 | 0 | STANDARD | Versatile Advanced Limited Company. | SAR | 108860 | APPROVED |  |  | 2025-05-25 | 6140 | 10 | Akhtar, Farhan | -45792 | 10
105-140 | 380kV BSP#9077 RUMAH A&B | 6608 | 380kV BSP#9077 RUMAH A&B-water & sewage | APPROVED | No | 2025-05-13 | Abas, Mohammed Fekry | 2025-05-15 | 2025-05-15 |  |  |  | 114800 | 7330 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 111240 | APPROVED |  |  | 2025-05-29 | 3560 | 14 | Akhtar, Farhan | -45792 | 14
105-140 | 380kV BSP#9077 RUMAH A&B | 6609 | 380kV BSP#9077 RUMAH A&B-Substation Security | APPROVED | No | 2025-05-13 | Abas, Mohammed Fekry | 2025-05-15 | 2025-05-15 |  |  |  | 1600000 | 7287 | 0 | STANDARD | Amnalawtan Security Company for civil security Guards | SAR | 1503000 | APPROVED |  |  | 2025-05-29 | 97000 | 14 | Abuhammad, Samir | -45792 | 14
105-140 | 380kV BSP#9077 RUMAH A&B | 6665 | 380kV BSP#9077 RUMAH A&B-Fire Detection System | APPROVED | No | 2025-05-20 | Abas, Mohammed Fekry | 2025-05-21 | 2025-05-21 |  |  |  | 15734757 | 7517 | 0 | STANDARD | Al Majal Group Four S for Security & Safety | SAR | 9978072 | APPROVED |  |  | 2025-08-05 | 5756685 | 76 | Kumar, Mr. Ranjan | -45798 | 76
105-140 | 380kV BSP#9077 RUMAH A&B | 6666 | 380kV BSP#9077 RUMAH A&B-HVAC SYSTEM | APPROVED | No | 2025-05-20 | Abas, Mohammed Fekry | 2025-05-25 | 2025-05-25 |  |  |  | 9500000 | 7425 | 0 | STANDARD | Ramz Alataa Company for Trading | SAR | 8590000 | APPROVED |  |  | 2025-07-29 | 910000 | 65 | Kumar, Mr. Ranjan | -45802 | 65
105-140 | 380kV BSP#9077 RUMAH A&B | 6666 | 380kV BSP#9077 RUMAH A&B-HVAC SYSTEM | APPROVED | No | 2025-05-20 | Abas, Mohammed Fekry | 2025-05-25 | 2025-05-25 |  |  |  | 9500000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45802 | -45802
105-140 | 380kV BSP#9077 RUMAH A&B | 6747 | 380kV BSP#9077 RUMAH A&B- SAS desk | APPROVED | No | 2025-05-28 | Abas, Mohammed Fekry | 2025-06-15 | 2025-06-15 |  |  |  | 75000 | 7992 | 0 | STANDARD | ALFANAR CO | SAR | 50000 | APPROVED | 2025-12-28 | 2026-01-01 | 2026-01-05 | 25000 | 204 | Kumar, Mr. Ranjan | 200 | 204
105-140 | 380kV BSP#9077 RUMAH A&B | 6751 | 380kV BSP#9077 RUMAH A&B-PDS | RETURNED | No | 2025-05-28 | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | 2025-12-29 | 2025-06-12 | 2025-12-29 |  | new PR 8514 is raised and this one is returned as per PM's instructions | 499500 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -45820 | -45820
105-140 | 380kV BSP#9077 RUMAH A&B | 6765 | 380kV BSP#9077 RUMAH A&B-33KV NEUTRAL EARTHING RESISTOR | RETURNED | No | 2025-06-02 | Kumar, Mr. Ranjan | 2025-11-11 | 2025-06-22 | 2025-11-11 |  | PO 7668 in Oracle is rejected by Mr. Ismail. You are requested to comply the remark and issue new PR. | 120 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45830 | -45830
105-140 | 380kV BSP#9077 RUMAH A&B | 6773 | 380kV BSP#9077 RUMAH A&B-125V Battery Bank & charger | APPROVED | No | 2025-06-11 | Abas, Mohammed Fekry | 2025-06-15 | 2025-06-15 |  |  |  | 2800000 | 7493 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 1786000 | APPROVED |  |  | 2025-07-24 | 1014000 | 39 | Kumar, Mr. Ranjan | -45823 | 39
105-140 | 380kV BSP#9077 RUMAH A&B | 6798 | 380kV BSP#9077 RUMAH A&B-Stationary Items | APPROVED | No | 2025-06-15 | Abas, Mohammed Fekry | 2025-06-15 | 2025-06-15 |  |  |  | 44000 | 7414 | 0 | STANDARD | TALABAT AL MAKTAB CO.LTD | SAR | 36766 | APPROVED |  |  | 2025-06-29 | 7234 | 14 | Akhtar, Farhan | -45823 | 14
105-140 | 380kV BSP#9077 RUMAH A&B | 6799 | 380kV BSP#9077 RUMAH A&B-IT Items | APPROVED | No | 2025-06-15 | Abas, Mohammed Fekry | 2025-06-15 | 2025-06-15 |  |  |  | 202000 | 7421 | 0 | STANDARD | Retam Alsharq Company | SAR | 163884 | APPROVED |  |  | 2025-07-03 | 38116 | 18 | Muaz, Alaa | -45823 | 18
105-140 | 380kV BSP#9077 RUMAH A&B | 6816 | 380kV BSP#9077 RUMAH A&B-Geotechnical investigation for Airport North & PS3 | APPROVED | No | 2025-06-17 | Abas, Mohammed Fekry | 2025-06-22 | 2025-06-25 |  |  |  | 40000 | 7460 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 25520 | APPROVED |  |  | 2025-07-14 | 14480 | 19 | Alhadi, Khalid | -45833 | 19
105-140 | 380kV BSP#9077 RUMAH A&B | 6817 | 380kV BSP#9077 RUMAH A&B-Indoor & Outdoor Socket and D.S | APPROVED | No | 2025-06-18 | Abas, Mohammed Fekry | 2025-06-29 | 2025-07-01 |  |  |  | 600000 | 7539 | 0 | STANDARD | Power House Company | SAR | 384825.8 | APPROVED |  |  | 2025-08-16 | 215174.2 | 46 | Hegazy, Ayman | -45839 | 46
105-140 | 380kV BSP#9077 RUMAH A&B | 6857 | 380kV BSP#9077 RUMAH A&B-ACSR Conductor & Connectors | RETURNED | No | 2025-06-22 | Babic, Marian | 2025-11-12 | 2025-07-04 | 2025-11-12 |  | please revise it to be itemized | 69060 | 7724 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 21052 | APPROVED |  |  | 2025-10-29 | 48008 |  | Kumar, Mr. Ranjan | -45842 | 117
105-140 | 380kV BSP#9077 RUMAH A&B | 6857 | 380kV BSP#9077 RUMAH A&B-ACSR Conductor & Connectors | RETURNED | No | 2025-06-22 | Babic, Marian | 2025-11-12 | 2025-07-04 | 2025-11-12 |  | please revise it to be itemized | 222000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45842 | -45842
105-140 | 380kV BSP#9077 RUMAH A&B | 6941 | 380kV BSP#9077 RUMAH A&B-cable ladder & tray | APPROVED | No | 2025-07-01 | Abas, Mohammed Fekry | 2025-07-07 | 2025-07-07 |  |  |  | 800000 | 7432 | 0 | STANDARD | AL-AMAL ELECTRICAL SWITCHBOARDS | SAR | 800000 | APPROVED |  |  | 2025-09-29 | 0 | 84 | Badhman, Saeed | -45845 | 84
105-140 | 380kV BSP#9077 RUMAH A&B | 6941 | 380kV BSP#9077 RUMAH A&B-cable ladder & tray | APPROVED | No | 2025-07-01 | Abas, Mohammed Fekry | 2025-07-07 | 2025-07-07 |  |  |  | 800000 | 7432 | 1 | STANDARD | AL-AMAL ELECTRICAL SWITCHBOARDS | SAR | 800000 | REQUIRES REAPPROVAL |  |  |  | 0 | 209 | Badhman, Saeed | -45845 | -45845
105-140 | 380kV BSP#9077 RUMAH A&B | 7046 | 380kV BSP#9077 RUMAH A&B-Male nurse | APPROVED | No | 2025-07-09 | Abas, Mohammed Fekry | 2025-07-14 | 2025-07-14 |  |  |  | 74400 | 7498 | 0 | STANDARD | Modern Response Company | SAR | 74400 | APPROVED |  |  | 2025-07-21 | 0 | 7 | Kumar, Mr. Ranjan | -45852 | 7
105-140 | 380kV BSP#9077 RUMAH A&B | 7093 | 380kV BSP#9077 RUMAH A&B-240MM BARE COPPER LOT-2 | APPROVED | No | 2025-07-15 | Abas, Mohammed Fekry | 2025-07-20 | 2025-07-20 |  |  |  | 712000 | 6959 | 1 | STANDARD | Hesham El-Sewedy Trading Co. LTD. | SAR | 677920 | APPROVED |  |  | 2025-08-26 | 34080 | 37 | Badhman, Saeed | -45858 | 37
105-140 | 380kV BSP#9077 RUMAH A&B | 7145 | 380kV BSP#9077 RUMAH A&B-walkie-talkie | APPROVED | No | 2025-07-20 | Abas, Mohammed Fekry | 2025-07-23 | 2025-07-23 |  |  |  | 7200 | 7555 | 0 | STANDARD | Versatile Advanced Limited Company. | SAR | 6320 | APPROVED |  |  | 2025-08-04 | 880 | 12 | Akhtar, Farhan | -45861 | 12
105-140 | 380kV BSP#9077 RUMAH A&B | 7314 | 380kV BSP#9077 RUMAH A&B-ACDB / DCDB | INCOMPLETE | No |  | Jaber, Mohammed Ali | 2025-08-07 |  |  |  |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
105-140 | 380kV BSP#9077 RUMAH A&B | 7410 | LV & Control cables | RETURNED | No | 2025-08-26 | Badhman, Saeed | 2025-09-08 | 2025-08-31 | 2025-09-08 |  | not needed, superseeded by PR No. 7639 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45900 | -45900
105-140 | 380kV BSP#9077 RUMAH A&B | 7582 | MV cable | INCOMPLETE | No | [6 empty] | not needed, superseeded by PR No. 7639 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
105-140 | 380kV BSP#9077 RUMAH A&B | 7620 | Lighting fixtures | APPROVED | No | 2025-09-02 | Abas, Mohammed Fekry | 2025-09-04 | 2025-09-04 |  |  |  | 0 | 7501 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 423977.5 | APPROVED |  |  | 2025-10-16 | -423977.5 | 42 | Alhadi, Khalid | -45904 | 42
105-140 | 380kV BSP#9077 RUMAH A&B | 7626 | FOC & communication Cable | RETURNED | No | 2025-09-02 | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | 2025-12-07 | 2025-09-04 | 2025-12-07 |  | new PR will be raised with the required budget as per PM instructions | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -45904 | -45904
105-140 | 380kV BSP#9077 RUMAH A&B | 7639 | LV & Control Cables | APPROVED | No | 2025-09-04 | Abas, Mohammed Fekry | 2025-12-17 | 2025-12-18 | 2025-12-15 |  | Returned based on Project instruction since there is a budget issue | 0 | 7434 | 0 | STANDARD | Hesham El-Sewedy Trading Co. LTD. | SAR | 16440609.99 | INCOMPLETE |  |  |  | -16440609.99 | 45 | Badhman, Saeed | -46009 | -46009
105-140 | 380kV BSP#9077 RUMAH A&B | 7639 | LV & Control Cables | APPROVED | No | 2025-09-04 | Abas, Mohammed Fekry | 2025-12-17 | 2025-12-18 | 2025-12-15 |  | Returned based on Project instruction since there is a budget issue | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -46009 | -46009
105-140 | 380kV BSP#9077 RUMAH A&B | 7643 | Lighting wires | APPROVED | No | 2025-09-04 | Abas, Mohammed Fekry | 2025-09-04 | 2025-09-04 |  |  |  | 0 | 7612 | 0 | STANDARD | SAUDI ELECTRIC SUPPLY COMPANY | SAR | 308556.02 | APPROVED |  |  | 2025-09-29 | -308556.02 | 25 | Muaz, Alaa | -45904 | 25
105-140 | 380kV BSP#9077 RUMAH A&B | 7661 | Installation Work | APPROVED | No | 2025-09-07 | Abas, Mohammed Fekry | 2026-01-18 | 2026-01-19 |  |  |  | 0 | 7795 | 0 | STANDARD | Hussain Ali Hussain Contracting Company | SAR | 13750000 | APPROVED | 2026-01-19 | 2026-01-25 | 2026-01-28 | -13750000 | 9 | Mohammed, Faisal Ansari | 6 | 9
105-140 | 380kV BSP#9077 RUMAH A&B | 7667 | EOT for pump house | APPROVED | No | 2025-09-07 | Abas, Mohammed Fekry | 2025-09-17 | 2025-09-21 |  |  |  | 0 | 7752 | 0 | STANDARD | SAUDI CRANES & STEEL WORKS FACTORY LTD | SAR | 18000 | APPROVED |  |  | 2025-10-15 | -18000 | 24 | Abuhammad, Samir | -45921 | 24
105-140 | 380kV BSP#9077 RUMAH A&B | 7672 | cable ladder and tray REV.01 | APPROVED | No | 2025-09-08 | Abas, Mohammed Fekry | 2025-09-14 | 2025-09-16 |  |  |  | 0 | 7432 | 1 | STANDARD | AL-AMAL ELECTRICAL SWITCHBOARDS | SAR | 295334.9 | REQUIRES REAPPROVAL |  |  |  | -295334.9 | 138 | Badhman, Saeed | -45916 | -45916
105-140 | 380kV BSP#9077 RUMAH A&B | 7672 | cable ladder and tray REV.01 | APPROVED | No | 2025-09-08 | Abas, Mohammed Fekry | 2025-09-14 | 2025-09-16 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45916 | -45916
105-140 | 380kV BSP#9077 RUMAH A&B | 7680 | 33Kv heat shirinkable MV termination | APPROVED | No | 2025-09-08 | Abas, Mohammed Fekry | 2025-09-14 | 2025-09-16 |  |  |  | 0 | 7599 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 59012 | APPROVED |  |  | 2025-09-25 | -59012 | 9 | Kumar, Mr. Ranjan | -45916 | 9
105-140 | 380kV BSP#9077 RUMAH A&B | 7712 | Ring CT | APPROVED | No | 2025-09-10 | Abas, Mohammed Fekry | 2025-09-14 | 2025-09-16 |  |  |  | 0 | 7770 | 0 | STANDARD | Power Trading T&D | EUR | 543010.5 | INCOMPLETE |  |  |  | -543010.5 | 138 | Kumar, Mr. Ranjan | -45916 | -45916
105-140 | 380kV BSP#9077 RUMAH A&B | 7712 | Ring CT | APPROVED | No | 2025-09-10 | Abas, Mohammed Fekry | 2025-09-14 | 2025-09-16 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45916 | -45916
105-140 | 380kV BSP#9077 RUMAH A&B | 7720 | free stand CT | RETURNED | No | 2025-09-11 | Kumar, Mr. Ranjan | 2025-11-11 | 2025-09-16 | 2025-11-11 |  | PR dont have enough budget as per PO and showing error code "You exceede the available budget". | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45916 | -45916
105-140 | 380kV BSP#9077 RUMAH A&B | 7759 | design consultant for fire fighting | APPROVED | No | 2025-09-16 | Abas, Mohammed Fekry | 2025-09-18 | 2025-09-19 |  |  |  | 0 | 7746 | 0 | STANDARD | Aman al-Alamiyyah Al-Muttahidah For Engineering | SAR | 222000 | APPROVED |  |  | 2025-10-21 | -222000 | 32 | Abuhammad, Samir | -45919 | 32
105-140 | 380kV BSP#9077 RUMAH A&B | 7760 | earthing materials REV.01 | APPROVED | No | 2025-09-17 | Abas, Mohammed Fekry | 2025-09-18 | 2025-09-19 |  |  |  | 0 | 6975 | 1 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 863189.39 | APPROVED |  |  | 2025-11-16 | -863189.39 | 58 | Badhman, Saeed | -45919 | 58
105-140 | 380kV BSP#9077 RUMAH A&B | 7778 | Lighting Accessories | APPROVED | No | 2025-09-17 | Abas, Mohammed Fekry | 2025-09-18 | 2025-09-19 |  |  |  | 0 | 7697 | 0 | STANDARD | Ahmed Essa Mohammed Al Muslim Est. | SAR | 457900 | APPROVED |  |  | 2025-11-02 | -457900 | 44 | Badhman, Saeed | -45919 | 44
105-140 | 380kV BSP#9077 RUMAH A&B | 7810 | medical items | APPROVED | No | 2025-09-22 | Abas, Mohammed Fekry | 2025-09-24 | 2025-09-24 |  |  |  | 0 | 7736 | 0 | STANDARD | Branch Bots Inc | SAR | 29510 | APPROVED |  |  | 2025-10-02 | -29510 | 8 | Abuhammad, Samir | -45924 | 8
105-140 | 380kV BSP#9077 RUMAH A&B | 7846 | Security | APPROVED | No | 2025-09-28 | Abas, Mohammed Fekry | 2025-10-01 | 2025-10-02 |  |  |  | 0 | 7790 | 0 | STANDARD | Al-Nufuth Al-Mutamayiza For Security Company | SAR | 751500 | APPROVED |  |  | 2025-10-14 | -751500 | 12 | Abuhammad, Samir | -45932 | 12
105-140 | 380kV BSP#9077 RUMAH A&B | 7886 | Vehicles for SEC | RETURNED | No | 2025-10-02 | Mohammed, Faisal Ansari | 2025-11-06 | 2025-10-08 | 2025-11-06 |  | To be taken care by the Facility Department. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45938 | -45938
105-140 | 380kV BSP#9077 RUMAH A&B | 7910 | PDMS for Airport North | APPROVED | No | 2025-10-06 | Abas, Mohammed Fekry | 2025-10-08 | 2025-10-08 |  |  |  | 0 | 7671 | 0 | STANDARD | APM Technologies, Inc. | USD | 431250 | APPROVED |  |  | 2025-11-11 | -431250 | 34 | Kumar, Mr. Ranjan | -45938 | 34
105-140 | 380kV BSP#9077 RUMAH A&B | 7911 | MV cable termination kit | APPROVED | No | 2025-10-06 | Abas, Mohammed Fekry | 2025-10-08 | 2025-10-08 |  |  |  | 0 | 7600 | 0 | STANDARD | CONSTRUCTION MATERIAL Valley EST | EUR | 103840 | APPROVED |  |  | 2025-10-30 | -103840 | 22 | Babic, Marian | -45938 | 22
105-140 | 380kV BSP#9077 RUMAH A&B | 7922 | MV Cable | APPROVED | No | 2025-10-07 | Abas, Mohammed Fekry | 2025-10-08 | 2025-10-08 |  |  |  | 0 | 7435 | 0 | STANDARD | Hesham El-Sewedy Trading Co. LTD. | SAR | 455882.15 | APPROVED |  |  | 2025-11-19 | -455882.15 | 42 | Badhman, Saeed | -45938 | 42
105-140 | 380kV BSP#9077 RUMAH A&B | 7937 | Container for HGIS | APPROVED | No | 2025-10-09 | Abas, Mohammed Fekry | 2025-10-12 | 2025-10-12 |  |  |  | 0 | 7791 | 0 | STANDARD | Rawabi Electric Company | SAR | 525000 | APPROVED |  |  | 2025-11-26 | -525000 | 45 | Kumar, Mr. Ranjan | -45942 | 45
105-140 | 380kV BSP#9077 RUMAH A&B | 7937 | Container for HGIS | APPROVED | No | 2025-10-09 | Abas, Mohammed Fekry | 2025-10-12 | 2025-10-12 |  |  |  | 0 | 8047 | 0 | STANDARD | Nour Industries Branch of Nour Communication | SAR | 498000 | IN PROCESS | 2025-12-24 | 2026-01-01 |  | -498000 | 112 | Kumar, Mr. Ranjan | 81 | -45942
105-140 | 380kV BSP#9077 RUMAH A&B | 7948 | Y/G Cable | APPROVED | No | 2025-10-15 | Abas, Mohammed Fekry | 2025-10-15 | 2025-10-16 |  |  |  | 0 | 7699 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 811349.42 | APPROVED |  |  | 2025-10-30 | -811349.42 | 14 | Muaz, Alaa | -45946 | 14
105-140 | 380kV BSP#9077 RUMAH A&B | 7962 | Lighting Poles & Lightning Mast | APPROVED | No | 2025-10-15 | Abas, Mohammed Fekry | 2025-10-15 | 2025-10-16 |  |  |  | 0 | 7572 | 0 | STANDARD | Hesham Helal Elsewedy & Partners for Construction Co., Ltd. | SAR | 545080 | APPROVED |  |  | 2025-10-30 | -545080 | 14 | Muaz, Alaa | -45946 | 14
105-140 | 380kV BSP#9077 RUMAH A&B | 8021 | MV CABLES CLAMPS | APPROVED | No | 2025-10-21 | Abas, Mohammed Fekry | 2025-10-27 | 2025-10-27 |  |  |  | 0 | 7914 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 34540 | APPROVED |  |  | 2025-12-14 | -34540 | 48 | Mohammed, Mohammed Adel Fahmy | -45957 | 48
105-140 | 380kV BSP#9077 RUMAH A&B | 8030 | Third Party lab Inspector For Precast Concrete | APPROVED | No | 2025-10-22 | Abas, Mohammed Fekry | 2025-10-27 | 2025-10-27 |  |  |  | 0 | 7153 | 1 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 100000 | APPROVED |  |  | 2025-11-16 | -100000 | 20 | Tananeh, Khalid Jamal | -45957 | 20
105-140 | 380kV BSP#9077 RUMAH A&B | 8065 | Delivery for earthing materials | APPROVED | No | 2025-10-27 | Abas, Mohammed Fekry | 2025-10-29 | 2025-10-30 |  |  |  | 0 | 6975 | 1 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 5000 | APPROVED |  |  | 2025-11-16 | -5000 | 17 | Badhman, Saeed | -45960 | 17
105-140 | 380kV BSP#9077 RUMAH A&B | 8125 | Third Party lab Inspector For Precast Concrete | REJECTED | No | 2025-11-03 | Abas, Mohammed Fekry | 2025-11-05 | 2025-11-05 |  | 2025-11-05 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45966 | -45966
105-140 | 380kV BSP#9077 RUMAH A&B | 8138 | site mobilization for APN | RETURNED | No | 2025-11-05 | Abuhammad, Samir | 2025-12-29 | 2025-12-26 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46017 | -46017
105-140 | 380kV BSP#9077 RUMAH A&B | 8139 | site mobilization for PS3 | RETURNED | No | 2025-11-05 | Abuhammad, Samir | 2025-12-29 | 2025-12-26 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46017 | -46017
105-140 | 380kV BSP#9077 RUMAH A&B | 8203 | ACSR Connectors | APPROVED | No | 2025-11-12 | Abas, Mohammed Fekry | 2025-11-13 | 2025-11-16 |  |  |  | 0 | 7893 | 0 | STANDARD | Arruti Subestaciones , S.A.U | EUR | 185369.54 | APPROVED |  |  | 2025-11-25 | -185369.54 | 9 | Babic, Marian | -45977 | 9
105-140 | 380kV BSP#9077 RUMAH A&B | 8210 | DSM , TFR , FL | APPROVED | No | 2025-11-13 | Abas, Mohammed Fekry | 2025-11-16 | 2025-11-17 |  |  |  | 0 | 15022 | 0 | STANDARD |  | SAR | 0 | INCOMPLETE |  |  |  | 0 | 76 | Kumar, Mr. Ranjan | -45978 | -45978
105-140 | 380kV BSP#9077 RUMAH A&B | 8210 | DSM , TFR , FL | APPROVED | No | 2025-11-13 | Abas, Mohammed Fekry | 2025-11-16 | 2025-11-17 |  |  |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45978 | -45978
105-140 | 380kV BSP#9077 RUMAH A&B | 8215 | Surge Arrestor | RETURNED | No | 2025-11-13 | Kumar, Mr. Ranjan | 2026-01-04 | 2025-11-17 | 2026-01-04 |  | This is consided in PR 8282, and PO 7039 is approved. Hence this line is not required and returned | 0 | 7039 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 934201.17 | APPROVED |  |  | 2025-12-30 | -934201.17 |  | Kumar, Mr. Ranjan | -45978 | 43
105-140 | 380kV BSP#9077 RUMAH A&B | 8215 | Surge Arrestor | RETURNED | No | 2025-11-13 | Kumar, Mr. Ranjan | 2026-01-04 | 2025-11-17 | 2026-01-04 |  | This is consided in PR 8282, and PO 7039 is approved. Hence this line is not required and returned | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45978 | -45978
105-140 | 380kV BSP#9077 RUMAH A&B | 8238 | NGR | RETURNED | No | 2025-11-17 | Kumar, Mr. Ranjan | 2025-12-08 | 2025-11-19 | 2025-12-08 |  | New PR 8359 received and PO 7774 routed for approval, This was old PR in which task number was wrong | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45980 | -45980
105-140 | 380kV BSP#9077 RUMAH A&B | 8282 | FAT for Surge arrester | APPROVED | No | 2025-11-19 | Abas, Mohammed Fekry | 2025-12-21 | 2025-12-21 | 2025-12-08 |  | In Discription showing as "PSSB - Factory Traning Expenses FAT" | 0 | 7039 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 3858.75 | APPROVED |  |  | 2025-12-30 | -3858.75 | 9 | Kumar, Mr. Ranjan | -46012 | 9
105-140 | 380kV BSP#9077 RUMAH A&B | 8330 | NER | REJECTED | No | 2025-11-24 | Alharbi, Atef Saud | 2025-12-11 | 2025-12-11 | 2025-12-08 | 2025-12-11 | Following correction needed:1. Type shall be "Goods" not "Service", 2. Quantity -2, If we are Increasing the value from 0.53333 to 2, Its showing error, 3. Amount -0, It shall be editable, but its fixed. | 2 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46002 | -46002
105-140 | 380kV BSP#9077 RUMAH A&B | 8331 | ACDB,DCDB and lighting panels | INCOMPLETE | No | [6 empty] | Following correction needed:1. Type shall be "Goods" not "Service", 2. Quantity -2, If we are Increasing the value from 0.53333 to 2, Its showing error, 3. Amount -0, It shall be editable, but its fixed. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
105-140 | 380kV BSP#9077 RUMAH A&B | 8332 | ACDB , DCDB , LIGHTING Panels | INCOMPLETE | No | [6 empty] | Following correction needed:1. Type shall be "Goods" not "Service", 2. Quantity -2, If we are Increasing the value from 0.53333 to 2, Its showing error, 3. Amount -0, It shall be editable, but its fixed. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-140 | 380kV BSP#9077 RUMAH A&B | 8333 | ACDB,DCDB,Ligting panels | APPROVED | No | 2025-11-24 | Abas, Mohammed Fekry | 2025-12-17 | 2025-12-18 | 2025-12-10 | 2025-11-26 | Shows Budget Exceeded. Please check the budget and revise the PR. | 0 | 8009 | 0 | STANDARD | Nour Industries Branch of Nour Communication | SAR | 3700000 | APPROVED |  |  | 2025-12-30 | -3700000 | 12 | Mohammed, Faisal Ansari | -46009 | 12
105-140 | 380kV BSP#9077 RUMAH A&B | 8358 | NGR | INCOMPLETE | No | [6 empty] | Shows Budget Exceeded. Please check the budget and revise the PR. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
105-140 | 380kV BSP#9077 RUMAH A&B | 8359 | NGR | APPROVED | No | 2025-11-26 | Abas, Mohammed Fekry | 2025-11-30 | 2025-12-01 |  |  |  | 0 | 7774 | 0 | STANDARD | Trench Austria GmbH | EUR | 2135200 | APPROVED |  |  | 2025-12-16 | -2135200 | 15 | Kumar, Mr. Ranjan | -45992 | 15
105-140 | 380kV BSP#9077 RUMAH A&B | 8386 | T&C | RETURNED | No | 2025-11-27 | Babic, Marian | 2025-12-28 | 2025-12-11 | 2025-12-28 |  | Not matching with project timeline stages, shall be received as per procurement plan dates. Also item description should not have PSSA project mentioned | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46002 | -46002
105-140 | 380kV BSP#9077 RUMAH A&B | 8474 | EOT for Pump House | APPROVED | No | 2025-12-08 | Abas, Mohammed Fekry | 2025-12-14 | 2025-12-14 |  |  |  | 0 | 7752 | 1 | STANDARD | SAUDI CRANES & STEEL WORKS FACTORY LTD | SAR | 2000 | APPROVED |  |  | 2025-12-29 | -2000 | 15 | Abuhammad, Samir | -46005 | 15
105-140 | 380kV BSP#9077 RUMAH A&B | 8514 | PDS & FOC | APPROVED | No | 2025-12-14 | Abas, Mohammed Fekry | 2025-12-17 | 2025-12-18 |  |  |  | 0 | 7913 | 0 | STANDARD | RASHID SAEED AHMED AL GHAMDI COMM INFO TRAD EST | SAR | 940500 | INCOMPLETE |  |  |  | -940500 | 45 | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46009 | -46009
105-140 | 380kV BSP#9077 RUMAH A&B | 8514 | PDS & FOC | APPROVED | No | 2025-12-14 | Abas, Mohammed Fekry | 2025-12-17 | 2025-12-18 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46009 | -46009
105-140 | 380kV BSP#9077 RUMAH A&B | 8523 | NER | APPROVED | No | 2025-12-15 | Abas, Mohammed Fekry | 2025-12-17 | 2025-12-18 |  |  |  | 0 | 7668 | 0 | STANDARD | National Switchgears | USD | 98250 | APPROVED |  |  | 2025-12-28 | -98250 | 10 | Kumar, Mr. Ranjan | -46009 | 10
105-140 | 380kV BSP#9077 RUMAH A&B | 8527 | Cable tray | APPROVED | No | 2025-12-16 | Abas, Mohammed Fekry | 2025-12-17 | 2025-12-18 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -46009 | -46009
105-140 | 380kV BSP#9077 RUMAH A&B | 8598 | SUBSTATION SECURITY (HCIS) | APPROVED | No | 2025-12-28 | Abas, Mohammed Fekry | 2025-12-29 | 2026-01-01 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46023 | -46023
105-140 | 380kV BSP#9077 RUMAH A&B | 8615 | Testing & commissioning | APPROVED | No | 2025-12-31 | Abas, Mohammed Fekry | 2026-01-06 | 2026-01-08 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46030 | -46030
105-140 | 380kV BSP#9077 RUMAH A&B | 8616 | Additional Security guards | APPROVED | No | 2025-12-31 | Abas, Mohammed Fekry | 2026-01-06 | 2026-01-08 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46030 | -46030
105-140 | 380kV BSP#9077 RUMAH A&B | 8655 | Fire rated Materials | REJECTED | No | 2026-01-06 | Hashish, Ismail Elsayed Hani Abdullah | 2026-01-06 | 2026-01-06 |  | 2026-01-14 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46028 | -46028
105-140 | 380kV BSP#9077 RUMAH A&B | 8768 | TPI for GIS | APPROVED | No | 2026-01-21 | Abas, Mohammed Fekry | 2026-01-22 | 2026-01-25 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46047 | -46047
105-141 | BISHA-PV 380/132 KV BSP | 5412 | BISHA-PV 380/132 KV BSP-Engineering & Design | RETURNED | No | 2025-01-13 | Kumar, Mr. Ranjan | 2025-02-17 | 2025-01-23 | 2025-02-17 |  | These are addiona values which was not used in the PO, PO is approved , henece returning these lines. | 3879246.74 | 6857 | 0 | STANDARD | BAHRAWY Gulf CONSULTANCY GROUP | SAR | 3815000 | APPROVED |  |  | 2025-02-11 | 64246.74 |  | Kumar, Mr. Ranjan | -45680 | 19
105-141 | BISHA-PV 380/132 KV BSP | 5412 | BISHA-PV 380/132 KV BSP-Engineering & Design | RETURNED | No | 2025-01-13 | Kumar, Mr. Ranjan | 2025-02-17 | 2025-01-23 | 2025-02-17 |  | These are addiona values which was not used in the PO, PO is approved , henece returning these lines. | 389003.26 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45680 | -45680
105-141 | BISHA-PV 380/132 KV BSP | 5449 | BISHA-PV 380/132 KV BSP-Site Security Service | APPROVED | No | 2025-01-17 | Abas, Mohammed Fekry | 2025-01-22 | 2025-01-23 |  |  |  | 1004956.25 | 6843 | 0 | STANDARD | Rukn Al Kateibah Company for Security Guards. | SAR | 696000 | APPROVED |  |  | 2025-02-05 | 308956.25 | 13 | Abuhammad, Samir | -45680 | 13
105-141 | BISHA-PV 380/132 KV BSP | 5493 | BISHA-PV 380/132 KV BSP- Power Transformer (380/132kV) & Accessories | APPROVED | No | 2025-01-20 | Abas, Mohammed Fekry | 2025-01-22 | 2025-01-23 |  |  |  | 140062500 | 6856 | 0 | STANDARD | Hyosung Heavy Industries Corporation | USD | 140062500.11 | APPROVED |  |  | 2025-02-10 | -0.11 | 18 | Kumar, Mr. Ranjan | -45680 | 18
105-141 | BISHA-PV 380/132 KV BSP | 5524 | BISHA-PV 380/132 KV BSP-Site Mobilization | APPROVED | No | 2025-01-21 | Abas, Mohammed Fekry | 2025-01-23 | 2025-01-23 |  |  |  | 1721615 | 6887 | 0 | STANDARD | Construction Expertise Est. | SAR | 1721000 | APPROVED |  |  | 2025-02-26 | 615 | 34 | Kumar, Mr. Ranjan | -45680 | 34
105-141 | BISHA-PV 380/132 KV BSP | 5569 | BISHA-PV 380/132 KV BSP-360KV Outdoor Surge Arreste | APPROVED | No | 2025-01-23 | Abas, Mohammed Fekry | 2025-01-26 | 2025-01-26 |  |  |  | 946572 | 7042 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 573388.2 | APPROVED |  |  | 2025-05-08 | 373183.8 | 102 | Kumar, Mr. Ranjan | -45683 | 102
105-141 | BISHA-PV 380/132 KV BSP | 5572 | BISHA-PV 380/132 KV BSP-(120KV-96KV-21KV-15KV) Outdoor/Indoor Surge Arrester | REJECTED | No | 2025-01-23 | Ahmed, Shehata Said Ahmed | 2026-01-01 | 2025-01-26 | 2025-08-03 | 2026-01-01 | Its optional in PO, cant add or else it will be added in total PO value., PMT to issue the PR once requirement is finalized. | 630000 | 7042 | 0 | STANDARD | TRIDELTA UBERSPANNUNGSABLEITER GMBH | EUR | 408807 | APPROVED |  |  | 2025-05-08 | 221193 |  | Kumar, Mr. Ranjan | -45683 | 102
105-141 | BISHA-PV 380/132 KV BSP | 5572 | BISHA-PV 380/132 KV BSP-(120KV-96KV-21KV-15KV) Outdoor/Indoor Surge Arrester | REJECTED | No | 2025-01-23 | Ahmed, Shehata Said Ahmed | 2026-01-01 | 2025-01-26 | 2025-08-03 | 2026-01-01 | Its optional in PO, cant add or else it will be added in total PO value., PMT to issue the PR once requirement is finalized. | 144000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45683 | -45683
105-141 | BISHA-PV 380/132 KV BSP | 5699 | BISHA-PV 380/132 KV BSP-BISHA - Shunt Reactors & Accessories | APPROVED | No | 2025-01-28 | Abas, Mohammed Fekry | 2025-01-30 | 2025-01-31 |  |  |  | 30675000 | 6318 | 0 | STANDARD | BEST-BALIKESIR ELECTROMEKANIK SANAYI TESISLERI A.S. | USD | 30675000 | APPROVED |  |  | 2025-02-10 | 0 | 10 | Kumar, Mr. Ranjan | -45688 | 10
105-141 | BISHA-PV 380/132 KV BSP | 5702 | BISHA-PV 380/132 KV BSP-BISHA - Grounding Transformer (13.8 KV, ZN, 3 ph, 60 HZ ) & Accessories | APPROVED | No | 2025-01-28 | Abas, Mohammed Fekry | 2025-01-30 | 2025-01-31 |  |  |  | 6288585 | 6855 | 0 | STANDARD | Koncar- Distribution and Special Transformation d.d.Zagreb | EUR | 4737600 | APPROVED |  |  | 2025-03-13 | 1550985 | 41 | Kumar, Mr. Ranjan | -45688 | 41
105-141 | BISHA-PV 380/132 KV BSP | 5732 | BISHA-PV 380/132 KV BSP-BISHA - Station Service Transformer 2500 KVA | REJECTED | No | 2025-01-29 | Mourad, Ahmed Mohamed Mohsen Elsayed | 2025-02-02 | 2025-02-02 |  | 2025-02-02 |  | 1519244 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45690 | -45690
105-141 | BISHA-PV 380/132 KV BSP | 5835 | BISHA-PV 380/132 KV BSP-JIB Crane | REJECTED | No | 2025-02-09 | Mourad, Ahmed Mohamed Mohsen Elsayed | 2025-02-16 | 2025-02-11 |  | 2025-02-17 |  | 200000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45699 | -45699
105-141 | BISHA-PV 380/132 KV BSP | 5844 | BISHA-PV 380/132 KV BSP-Station Service Transformer | APPROVED | No | 2025-02-10 | Abas, Mohammed Fekry | 2025-02-11 | 2025-02-13 |  |  |  | 740000 | 6971 | 0 | STANDARD | UNITED TRANSFORMERS ELECTRIC COMPANY (UTEC) | SAR | 732000 | APPROVED |  |  | 2025-03-24 | 8000 | 39 | Kumar, Mr. Ranjan | -45701 | 39
105-141 | BISHA-PV 380/132 KV BSP | 5879 | BISHA-PV 380/132 KV BSP-HCIS Security System | REJECTED | No | 2025-02-16 | Mydeen, Shaik Peer Mohamed | 2025-06-24 | 2025-02-18 | 2025-05-22 | 2025-06-24 | As informed by Budget & Cost Control department, please create a new Purchase Request (PR) for the new task | 220990.41 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45706 | -45706
105-141 | BISHA-PV 380/132 KV BSP | 5962 | BISHA-PV 380/132 KV BSP-Cable Trays & Supports with Accessories | REJECTED | No | 2025-02-18 | Mydeen, Shaik Peer Mohamed | 2025-06-23 | 2025-03-03 | 2025-04-14 | 2025-06-23 | Please issue itemized PR (all the items as per BOQ), Its an inventory material, Can not be with 1 Lot. | 1614581 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45719 | -45719
105-141 | BISHA-PV 380/132 KV BSP | 6136 | BISHA-PV 380/132 KV BSP-Earthing Material & Accessories | APPROVED | No | 2025-03-09 | Abas, Mohammed Fekry | 2025-06-01 | 2025-06-02 | 2025-03-19 |  | QTYs not as per the BOQ, please adjust them as discussed | 402428.95 | 6973 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 382427.52 | APPROVED |  |  | 2025-04-24 | 20001.43 | -39 | Badhman, Saeed | -45810 | -39
105-141 | BISHA-PV 380/132 KV BSP | 6147 | BISHA-PV 380/132 KV BSP-Bisha Access Road | APPROVED | No | 2025-03-10 | Abas, Mohammed Fekry | 2025-03-13 | 2025-03-17 |  |  | Budget Line item : Access Road | 600000 | 7072 | 0 | STANDARD | Sam OG Construction | SAR | 600000 | APPROVED |  |  | 2025-04-16 | 0 | 30 | Tananeh, Khalid Jamal | -45733 | 30
105-141 | BISHA-PV 380/132 KV BSP | 6176 | BISHA-PV 380/132 KV BSP-Bisha Precast Panels Superstructure works | APPROVED | No | 2025-03-12 | Abas, Mohammed Fekry | 2025-03-13 | 2025-03-17 |  |  | Budget Line Item : Precast Superstucture Works | 19822848 | 7008 | 0 | STANDARD | Rabiah Nassar and Zamil Concrete Industries Co. Ltd | SAR | 19822847 | APPROVED |  |  | 2025-04-16 | 1 | 30 | Tananeh, Khalid Jamal | -45733 | 30
105-141 | BISHA-PV 380/132 KV BSP | 6182 | BISHA-PV 380/132 KV BSP-Bisha Soil Investigation | APPROVED | No | 2025-03-13 | Abas, Mohammed Fekry | 2025-03-19 | 2025-03-20 |  |  | Budget line item : 1.5.1.1.1 | 80000 | 7050 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 80000 | APPROVED |  |  | 2025-04-06 | 0 | 17 | Kumar, Mr. Ranjan | -45736 | 17
105-141 | BISHA-PV 380/132 KV BSP | 6183 | BISHA-PV 380/132 KV BSP-Topography survey | APPROVED | No | 2025-03-13 | Abas, Mohammed Fekry | 2025-03-16 | 2025-03-17 |  |  | Tpography Survey | 87000 | 7036 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 87000 | APPROVED |  |  | 2025-04-06 | 0 | 20 | Kumar, Mr. Ranjan | -45733 | 20
105-141 | BISHA-PV 380/132 KV BSP | 6195 | BISHA-PV 380/132 KV BSP-132 KV HV Cables 2500 Sqmm | APPROVED | No | 2025-03-18 | Abas, Mohammed Fekry | 2025-03-23 | 2025-03-24 |  |  | Budget Line Item : HV Cable | 15049650 | 6903 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 15049650 | APPROVED |  |  | 2025-04-16 | 0 | 23 | Kumar, Mr. Ranjan | -45740 | 23
105-141 | BISHA-PV 380/132 KV BSP | 6204 | BISHA-PV 380/132 KV BSP-Link Boxes with Accessories | APPROVED | No | 2025-03-19 | Abas, Mohammed Fekry | 2025-03-23 | 2025-03-24 |  |  | Budget Line Item | 231000 | 7038 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 205065 | APPROVED |  |  | 2025-04-24 | 25935 | 31 | Kumar, Mr. Ranjan | -45740 | 31
105-141 | BISHA-PV 380/132 KV BSP | 6230 | BISHA-PV 380/132 KV BSP-Grounding Material & Accessories | APPROVED | No | 2025-03-23 | Abas, Mohammed Fekry | 2025-03-24 | 2025-03-25 |  |  | Budget Line item | 7203 | 6973 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 6898 | APPROVED |  |  | 2025-04-24 | 305 | 30 | Badhman, Saeed | -45741 | 30
105-141 | BISHA-PV 380/132 KV BSP | 6265 | BISHA-PV 380/132 KV BSP-240 sq mm copper conductor | APPROVED | No | 2025-03-25 | Abas, Mohammed Fekry | 2025-06-01 | 2025-06-02 |  |  | budget line item: 240sqmm copper conductor | 2985464.72 | 6972 | 0 | STANDARD | Hesham El-Sewedy Trading Co. LTD. | SAR | 2980284.02 | APPROVED |  |  | 2025-08-26 | 5180.7 | 85 | Badhman, Saeed | -45810 | 85
105-141 | BISHA-PV 380/132 KV BSP | 6282 | BISHA-PV 380/132 KV BSP-13.8 KV MV Cable Termination KIT | APPROVED | No | 2025-03-26 | Abas, Mohammed Fekry | 2025-05-15 | 2025-05-15 |  |  | Budget line item : MV cable termination Kit | 281586 | 7035 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 58420 | APPROVED |  |  | 2025-05-26 | 223166 | 11 | Kumar, Mr. Ranjan | -45792 | 11
105-141 | BISHA-PV 380/132 KV BSP | 6283 | BISHA-PV 380/132 KV BSP-13.8KV MV power cable | APPROVED | No | 2025-03-26 | Abas, Mohammed Fekry | 2025-05-15 | 2025-05-15 |  |  | Budget Line Item : MV Power Cable | 790835.77 | 7053 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 658542.44 | APPROVED |  |  | 2025-05-28 | 132293.33 | 13 | Kumar, Mr. Ranjan | -45792 | 13
105-141 | BISHA-PV 380/132 KV BSP | 6283 | BISHA-PV 380/132 KV BSP-13.8KV MV power cable | APPROVED | No | 2025-03-26 | Abas, Mohammed Fekry | 2025-05-15 | 2025-05-15 |  |  | Budget Line Item : MV Power Cable | 790835.77 | 7053 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 521823.3 | APPROVED |  |  | 2025-12-04 | 269012.47 | 203 | Kumar, Mr. Ranjan | -45792 | 203
105-141 | BISHA-PV 380/132 KV BSP | 6392 | BISHA-PV 380/132 KV BSP-Civil and Architectural Works | APPROVED | No | 2025-04-20 | Abas, Mohammed Fekry | 2025-04-22 | 2025-04-22 |  |  | PO-7052 | 97922019 | 7052 | 0 | STANDARD | Intelligent System General Contracting Company | SAR | 97800000 | APPROVED |  |  | 2025-04-28 | 122019 | 6 | Tananeh, Khalid Jamal | -45769 | 6
105-141 | BISHA-PV 380/132 KV BSP | 6545 | BISHA-PV 380/132 KV BSP-Protection & Control & Communication & SAS | REJECTED | No | 2025-05-06 | Mydeen, Shaik Peer Mohamed | 2025-05-06 |  |  | 2025-05-06 |  | 59701049.08 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
105-141 | BISHA-PV 380/132 KV BSP | 6561 | BISHA-PV 380/132 KV BSP-Siemens-Protection, Control, SAS, Communicatiom | APPROVED | No | 2025-05-07 | Abas, Mohammed Fekry | 2025-05-13 | 2025-05-14 |  |  |  | 59726293 | 7282 | 0 | STANDARD | Siemens Energy Ltd | SAR | 59726293 | APPROVED |  |  | 2025-05-19 | 0 | 5 | Kumar, Mr. Ranjan | -45791 | 5
105-141 | BISHA-PV 380/132 KV BSP | 6563 | BISHA-PV 380/132 KV BSP-Surveying Equipment | APPROVED | No | 2025-05-07 | Abas, Mohammed Fekry | 2025-05-12 | 2025-05-14 |  |  |  | 113200 | 7288 | 0 | STANDARD | ALBOKSOMATTI FOR SURVEYING COMPANY(S) | SAR | 103200 | APPROVED |  |  | 2025-06-24 | 10000 | 41 | Kumar, Mr. Ranjan | -45791 | 41
105-141 | BISHA-PV 380/132 KV BSP | 6706 | BISHA-PV 380/132 KV BSP-Bisha PV BSP: MV Cable | REJECTED | No | 2025-05-25 | Mourad, Ahmed Mohamed Mohsen Elsayed | 2025-05-28 | 2025-05-27 |  | 2025-05-28 |  | 658542.44 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45804 | -45804
105-141 | BISHA-PV 380/132 KV BSP | 6710 | BISHA-PV 380/132 KV BSP-Bisha PV BSP: EOT for 380kV GIS Building | APPROVED | No | 2025-05-26 | Abas, Mohammed Fekry | 2025-05-28 | 2025-05-28 |  |  |  | 270199.8 | 7492 | 0 | STANDARD | SAUDI CRANES & STEEL WORKS FACTORY LTD | SAR | 239000 | APPROVED |  |  | 2025-07-22 | 31199.8 | 55 | Kumar, Mr. Ranjan | -45805 | 55
105-141 | BISHA-PV 380/132 KV BSP | 6711 | BISHA-PV 380/132 KV BSP-Bisha PV BSP: EOT for 132 or 115 or 110kV GIS Building | REJECTED | No | 2025-05-26 | Mydeen, Shaik Peer Mohamed | 2025-06-23 | 2025-05-28 | 2025-06-01 | 2025-06-23 | it will have 3 EOT whereas in PR Unit of measurement is "1 Lot", It need to be correct. PR will be returned for correction. Issue PR with 3 Lines, each for one EOT because each will have different price. | 772000.19 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45805 | -45805
105-141 | BISHA-PV 380/132 KV BSP | 6712 | BISHA-PV 380/132 KV BSP-Bisha PV BSP: EOT for Pump House | REJECTED | No | 2025-05-26 | Mydeen, Shaik Peer Mohamed | 2025-06-23 | 2025-05-28 | 2025-06-01 |  | PR is without details, Cant float the RFQ. | 21000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45805 | -45805
105-141 | BISHA-PV 380/132 KV BSP | 6714 | BISHA-PV 380/132 KV BSP-Bisha PV BSP: 132kV Free Standing Current Transformer with Junction Box | APPROVED | No | 2025-05-26 | Abas, Mohammed Fekry | 2025-11-24 | 2025-11-24 | 2025-06-22 |  | Please issue the PR once requirement is finalized by client- We will re validate the Offers and issue the PO accordingly. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45985 | -45985
105-141 | BISHA-PV 380/132 KV BSP | 6715 | BISHA-PV 380/132 KV BSP-Bisha PV BSP: 380kV Free Standing Current Transformer with Junction Box | APPROVED | No | 2025-05-26 | Abas, Mohammed Fekry | 2025-11-25 | 2025-11-29 | 2025-06-22 |  | Please issue the PR once requirement is finalized by client- We will re validate the Offers and issue the PO accordingly. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45990 | -45990
105-141 | BISHA-PV 380/132 KV BSP | 6732 | BISHA-PV 380/132 KV BSP-Bisha PV BSP: Fire Protection/Detection System | APPROVED | No | 2025-05-27 | Abas, Mohammed Fekry | 2025-05-27 | 2025-05-27 |  |  |  | 15532390.53 | 7519 | 0 | STANDARD | SALEM AGENCIES &SERVICES CO.. LTD | SAR | 11650000 | APPROVED |  |  | 2025-08-06 | 3882390.53 | 71 | Kumar, Mr. Ranjan | -45804 | 71
105-141 | BISHA-PV 380/132 KV BSP | 6733 | BISHA-PV 380/132 KV BSP-Bisha PV BSP: ACDB Maiin & Sub-Panels | APPROVED | No | 2025-05-27 | Abas, Mohammed Fekry | 2025-12-23 | 2025-12-24 |  |  |  | 0 | 7672 | 0 | STANDARD | META SWITCHGEAR Factory | SAR | 0 | INCOMPLETE |  |  |  | 0 | 39 | Kumar, Mr. Ranjan | -46015 | -46015
105-141 | BISHA-PV 380/132 KV BSP | 6733 | BISHA-PV 380/132 KV BSP-Bisha PV BSP: ACDB Maiin & Sub-Panels | APPROVED | No | 2025-05-27 | Abas, Mohammed Fekry | 2025-12-23 | 2025-12-24 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46015 | -46015
105-141 | BISHA-PV 380/132 KV BSP | 6779 | BISHA-PV 380/132 KV BSP-Bisha PV BSP: Consultant Service for a Building Permit | IN PROCESS | No | 2025-06-12 | Mydeen, Shaik Peer Mohamed | 2025-06-15 | 2025-06-15 |  |  |  | 100000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45823 | -45823
105-141 | BISHA-PV 380/132 KV BSP | 6780 | BISHA-PV 380/132 KV BSP-Bisha PV BSP: Hydrological Study on Access Roads | APPROVED | No | 2025-06-12 | Abas, Mohammed Fekry | 2025-07-31 | 2025-08-05 |  |  |  | 200000 | 7637 | 0 | STANDARD | Applus Arabia for Geotechnical And Environmental Works Co. Ltd | SAR | 40000 | APPROVED |  |  | 2025-08-28 | 160000 | 23 | Alhadi, Khalid | -45874 | 23
105-141 | BISHA-PV 380/132 KV BSP | 6786 | BISHA-PV 380/132 KV BSP-Bisha PV BSP: EOT for 132kV GIS Building | REJECTED | No | 2025-06-12 | Yamama, Loai Mohamed | 2025-09-07 | 2025-06-15 |  | 2025-09-07 |  | 120000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45823 | -45823
105-141 | BISHA-PV 380/132 KV BSP | 6791 | BISHA-PV 380/132 KV BSP-Bisha PV BSP: 125V Battery Bank and Charger | APPROVED | No | 2025-06-12 | Abas, Mohammed Fekry | 2025-11-24 | 2025-11-24 | 2025-09-28 |  | Please correct the Quantity and issue new PR. Also please not that if we are considering the actual value of Battery and charger then line is showing over budget for battery. | 0 | 7633 | 0 | STANDARD | ERAM Power Electronics Company | SAR | 2735000 | APPROVED |  |  | 2025-12-14 | -2735000 | 20 | Kumar, Mr. Ranjan | -45985 | 20
105-141 | BISHA-PV 380/132 KV BSP | 6841 | BISHA-PV 380/132 KV BSP-Site Office Services (IT- Sewerage & Garbage disposal- Portable Water) | REJECTED | No | 2025-06-19 | Mydeen, Shaik Peer Mohamed | 2025-06-19 |  |  | 2025-06-19 |  | 52800 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
105-141 | BISHA-PV 380/132 KV BSP | 6842 | BISHA-PV 380/132 KV BSP-Site Office Services (IT Supply- Protable Water- Sewerage & Garbege Disposal) | APPROVED | No | 2025-06-19 | Abas, Mohammed Fekry | 2025-06-23 | 2025-06-25 |  |  |  | 36000 | 7459 | 0 | STANDARD | Al-Hamdha Trade & Contracting | SAR | 28600 | APPROVED |  |  | 2025-07-16 | 7400 | 21 | Akhtar, Farhan | -45833 | 21
105-141 | BISHA-PV 380/132 KV BSP | 6842 | BISHA-PV 380/132 KV BSP-Site Office Services (IT Supply- Protable Water- Sewerage & Garbege Disposal) | APPROVED | No | 2025-06-19 | Abas, Mohammed Fekry | 2025-06-23 | 2025-06-25 |  |  |  | 30000 | 7465 | 0 | STANDARD | Mohammad Abdul Rahman Mohd Al Zahid Information Technology Co | SAR | 28400 | APPROVED |  |  | 2025-07-17 | 1600 | 22 | Akhtar, Farhan | -45833 | 22
105-141 | BISHA-PV 380/132 KV BSP | 6880 | BISHA-PV 380/132 KV BSP-MV Cable- 1X185 | REJECTED | No | 2025-06-24 | Yamama, Loai Mohamed | 2025-06-24 | 2025-06-24 |  | 2025-06-24 |  | 683672.24 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45832 | -45832
105-141 | BISHA-PV 380/132 KV BSP | 6901 | BISHA-PV 380/132 KV BSP-MV Termination KITs-Indoor | REJECTED | No | 2025-06-26 | Yamama, Loai Mohamed | 2025-07-16 | 2025-07-02 |  | 2025-07-16 |  | 51588 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45840 | -45840
105-141 | BISHA-PV 380/132 KV BSP | 6910 | BISHA-PV 380/132 KV BSP-Supply of 132 KV HV Cable Cealing End (CSE) | REJECTED | No | 2025-06-26 | Yamama, Loai Mohamed | 2025-07-16 | 2025-07-02 |  | 2025-07-16 |  | 1715652.54 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45840 | -45840
105-141 | BISHA-PV 380/132 KV BSP | 6964 | BISHA-PV 380/132 KV BSP-EOT FOR 132 KV GIS BUILDING | APPROVED | No | 2025-07-01 | Abas, Mohammed Fekry | 2025-07-03 | 2025-07-04 |  |  |  | 772000.19 | 7492 | 0 | STANDARD | SAUDI CRANES & STEEL WORKS FACTORY LTD | SAR | 511000 | APPROVED |  |  | 2025-07-22 | 261000.19 | 18 | Kumar, Mr. Ranjan | -45842 | 18
105-141 | BISHA-PV 380/132 KV BSP | 6971 | BISHA-PV 380/132 KV BSP-Dynamic System Monitring (DSM) | REJECTED | No | 2025-07-02 | Yamama, Loai Mohamed | 2025-07-02 | 2025-07-02 |  | 2025-07-03 |  | 2500000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45840 | -45840
105-141 | BISHA-PV 380/132 KV BSP | 6973 | BISHA-PV 380/132 KV BSP-PDMS | REJECTED | No | 2025-07-02 | Mydeen, Shaik Peer Mohamed | 2025-07-02 |  |  | 2025-07-02 |  | 2885000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
105-141 | BISHA-PV 380/132 KV BSP | 6974 | BISHA-PV 380/132 KV BSP-Transient Fault Recorder (TFR) | REJECTED | No | 2025-07-02 | Yamama, Loai Mohamed | 2025-07-02 | 2025-07-02 |  | 2025-07-03 |  | 2885000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45840 | -45840
105-141 | BISHA-PV 380/132 KV BSP | 6975 | BISHA-PV 380/132 KV BSP-PDMS | REJECTED | No | 2025-07-02 | Yamama, Loai Mohamed | 2025-07-09 | 2025-07-02 |  | 2025-07-09 |  | 4000000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45840 | -45840
105-141 | BISHA-PV 380/132 KV BSP | 7007 | BISHA-PV 380/132 KV BSP-Cable Tray-Ladder & Accessories for [132 - 380 - Control - Tunnel P&C - Customer] Buildings | REJECTED | No | 2025-07-08 | Yamama, Loai Mohamed | 2025-08-11 | 2025-07-08 |  | 2025-08-12 |  | 1652993.21 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45846 | -45846
105-141 | BISHA-PV 380/132 KV BSP | 7011 | BISHA-PV 380/132 KV BSP-Transient Fault Recorder (TFR) | APPROVED | No | 2025-07-08 | Abas, Mohammed Fekry | 2025-07-10 | 2025-07-10 |  |  |  | 2000000 | 7833 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 2345000 | APPROVED |  |  | 2025-12-14 | -345000 | 157 | Kumar, Mr. Ranjan | -45848 | 157
105-141 | BISHA-PV 380/132 KV BSP | 7013 | BISHA-PV 380/132 KV BSP-PDMS | APPROVED | No | 2025-07-08 | Abas, Mohammed Fekry | 2025-11-24 | 2025-11-24 | 2025-08-11 |  | RFQ details not received | 0 | 7976 | 0 | STANDARD | APM Technologies, Inc. | USD | 2737500 | APPROVED |  |  | 2025-12-30 | -2737500 | 36 | Kumar, Mr. Ranjan | -45985 | 36
105-141 | BISHA-PV 380/132 KV BSP | 7147 | BISHA-PV 380/132 KV BSP-Supply of Cable Cealing Eng (CSE) Indoor /Outdoor | REJECTED | No | 2025-07-20 | Yamama, Loai Mohamed | 2025-07-22 | 2025-07-21 |  | 2025-07-22 |  | 472500 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45859 | -45859
105-141 | BISHA-PV 380/132 KV BSP | 7151 | BISHA-PV 380/132 KV BSP-Installation of Cable Cealing Eng (CSE) Indoor | APPROVED | No | 2025-07-20 | Abas, Mohammed Fekry | 2025-07-22 | 2025-07-22 |  |  |  | 362250 | 7586 | 0 | STANDARD | BRUGG CABLES COMAPNY | SAR | 362250 | INCOMPLETE |  |  |  | 0 | 194 | Kumar, Mr. Ranjan | -45860 | -45860
105-141 | BISHA-PV 380/132 KV BSP | 7151 | BISHA-PV 380/132 KV BSP-Installation of Cable Cealing Eng (CSE) Indoor | APPROVED | No | 2025-07-20 | Abas, Mohammed Fekry | 2025-07-22 | 2025-07-22 |  |  |  | 362250 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45860 | -45860
105-141 | BISHA-PV 380/132 KV BSP | 7274 | BISHA-PV 380/132 KV BSP-Supply of HVAC System | APPROVED | No | 2025-08-04 | Abas, Mohammed Fekry | 2025-08-05 | 2025-08-06 |  |  | plesae approve | 8578997.11 | 7649 | 0 | STANDARD | Magna Contracting Co | SAR | 8578997.11 | REJECTED |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45875 | -45875
105-141 | BISHA-PV 380/132 KV BSP | 7274 | BISHA-PV 380/132 KV BSP-Supply of HVAC System | APPROVED | No | 2025-08-04 | Abas, Mohammed Fekry | 2025-08-05 | 2025-08-06 |  |  | plesae approve | 8578997.11 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45875 | -45875
105-141 | BISHA-PV 380/132 KV BSP | 7275 | BISHA-PV 380/132 KV BSP-Installation of HVAC System | APPROVED | No | 2025-08-04 | Abas, Mohammed Fekry | 2025-08-05 | 2025-08-06 |  |  |  | 311155.89 | 7649 | 0 | STANDARD | Magna Contracting Co | SAR | 311155.89 | REJECTED |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45875 | -45875
105-141 | BISHA-PV 380/132 KV BSP | 7275 | BISHA-PV 380/132 KV BSP-Installation of HVAC System | APPROVED | No | 2025-08-04 | Abas, Mohammed Fekry | 2025-08-05 | 2025-08-06 |  |  |  | 311155.89 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45875 | -45875
105-141 | BISHA-PV 380/132 KV BSP | 7292 | BISHA-PV 380/132 KV BSP-Supply of 795 KCMIL ACSR/AW Conductor for 132 KV and 380 KV Gantries | APPROVED | No | 2025-08-05 | Abas, Mohammed Fekry | 2025-08-11 | 2025-08-11 |  |  | plesae approve | 150000 | 7723 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 47538 | APPROVED |  |  | 2025-11-11 | 102462 | 92 | Kumar, Mr. Ranjan | -45880 | 92
105-141 | BISHA-PV 380/132 KV BSP | 7294 | BISHA-PV 380/132 KV BSP-Internet Services for the Site | APPROVED | No | 2025-08-05 | Abas, Mohammed Fekry | 2025-08-10 | 2025-08-10 |  |  | plesae approve | 318500 | 7511 | 0 | STANDARD | Zone Network Information Technology Est. | SAR | 318500 | APPROVED |  |  | 2025-09-08 | 0 | 29 | Kumar, Mr. Ranjan | -45879 | 29
105-141 | BISHA-PV 380/132 KV BSP | 7330 | BISHA-PV 380/132 KV BSP-Supplyof Cable Sealing Eng (CSE) Indoor/Oudoor | APPROVED | No | 2025-08-11 | Abas, Mohammed Fekry | 2025-08-14 | 2025-08-18 |  |  |  | 472500 | 7587 | 0 | STANDARD | Brugg Kable AG | CHF | 2230200 | APPROVED | 2025-09-22 | 2026-01-01 | 2026-01-05 | -1757700 | 140 | Kumar, Mr. Ranjan | 136 | 140
105-141 | BISHA-PV 380/132 KV BSP | 7331 | BISHA-PV 380/132 KV BSP-Install of Cable Sealing End (CSE) Oudoor | REJECTED | No | 2025-08-11 | Mydeen, Shaik Peer Mohamed | 2025-12-02 | 2025-09-21 | 2025-11-09 | 2025-12-02 | While creating the PO, is showing budget error as showin in the email sent to you, Please check the budget and submit the PR again. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45921 | -45921
105-141 | BISHA-PV 380/132 KV BSP | 7332 | BISHA-PV 380/132 KV BSP-Dynamic System Monitring (DSM) | APPROVED | No | 2025-08-11 | Abas, Mohammed Fekry | 2025-12-03 | 2025-12-03 | 2025-11-06 |  | As per comment from PMO, please make Qty 1 and Unit price 2,000,000 | 0 | 7833 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 1255000 | APPROVED |  |  | 2025-12-14 | -1255000 | 11 | Kumar, Mr. Ranjan | -45994 | 11
105-141 | BISHA-PV 380/132 KV BSP | 7334 | BISHA-PV 380/132 KV BSP-LV Control and Power Cables | REJECTED | No | 2025-08-12 | Ahmed, Shehata Said Ahmed | 2025-12-22 | 2025-09-04 | 2025-09-30 | 2025-12-22 | submit the pr on item wise | 8020599.82 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45904 | -45904
105-141 | BISHA-PV 380/132 KV BSP | 7337 | BISHA-PV 380/132 KV BSP-Cable Tray-Ladder & Accessories for [132 - 380 - Control - Tunnel P&C - Customer] Buildings | APPROVED | No | 2025-08-12 | Abas, Mohammed Fekry | 2025-08-14 | 2025-08-18 |  |  |  | 1614581.95 | 7281 | 0 | STANDARD | ISAM KABBANI &Partners | SAR | 1612987.98 | APPROVED |  |  | 2025-10-27 | 1593.97 | 70 | Kumar, Mr. Ranjan | -45887 | 70
105-141 | BISHA-PV 380/132 KV BSP | 7339 | BISHA-PV 380/132 KV BSP-Clamps/Accessories of ACSR/AW Conductor for 132 KV and 380 KV Gantries | RETURNED | No | 2025-08-12 | Kumar, Mr. Ranjan | 2026-01-01 | 2025-12-26 |  |  | Plesae approve (Task line 1.4.1.1.40) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46017 | -46017
105-141 | BISHA-PV 380/132 KV BSP | 7435 | Y/G Earthing Cables | APPROVED | No | 2025-08-23 | Abas, Mohammed Fekry | 2025-11-24 | 2025-11-24 | 2025-11-11 |  | As the PMT didn't reply to my mail regarding the offer for Bahra to proceed further with PO although I sent mail to follow up with them but there is no response from their side. | 0 | 7838 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 182578.94 | INCOMPLETE |  |  |  | -182578.94 | 69 | Hegazy, Ayman | -45985 | -45985
105-141 | BISHA-PV 380/132 KV BSP | 7435 | Y/G Earthing Cables | APPROVED | No | 2025-08-23 | Abas, Mohammed Fekry | 2025-11-24 | 2025-11-24 | 2025-11-11 |  | As the PMT didn't reply to my mail regarding the offer for Bahra to proceed further with PO although I sent mail to follow up with them but there is no response from their side. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -45985 | -45985
105-141 | BISHA-PV 380/132 KV BSP | 7436 | Lighting System Indoor/Outdoor | REJECTED | No | 2025-08-23 | Ahmed, Shehata Said Ahmed | 2025-12-21 | 2025-08-25 | 2025-10-23 | 2025-12-21 | The PR should be itemized not in LOT | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -45894 | -45894
105-141 | BISHA-PV 380/132 KV BSP | 7437 | Shielding System | REJECTED | No | 2025-08-23 | Ahmed, Shehata Said Ahmed | 2025-12-21 | 2025-08-25 | 2025-10-23 | 2025-12-21 | The PR is only one line item not itemized.. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Muaz, Alaa | -45894 | -45894
105-141 | BISHA-PV 380/132 KV BSP | 7509 | PDS System | APPROVED | No | 2025-08-26 | Abas, Mohammed Fekry | 2025-12-23 | 2025-12-24 | 2025-10-28 |  | Becnause we have sent offers to PMT and we didn't get any feedback also we have followed with PMT with no response. Also there is some documents with Code C | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -46015 | -46015
105-141 | BISHA-PV 380/132 KV BSP | 7511 | Fiber Patch Panel | APPROVED | No | 2025-08-26 | Abas, Mohammed Fekry | 2025-12-23 | 2025-12-24 | 2025-10-28 |  | Because we have sent offers to PMT and we didn't get any feedback also we have followed with PMT with no response. Also there is some documents with Code C | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -46015 | -46015
105-141 | BISHA-PV 380/132 KV BSP | 7606 | 13.8 KV MVSWGR | APPROVED | No | 2025-09-01 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-04 |  |  | task line (1.4.1.1.6) | 0 | 6928 | 0 | STANDARD | SIEMENS LIMITED | SAR | 1825000 | APPROVED |  |  | 2025-09-17 | -1825000 | 13 | Kumar, Mr. Ranjan | -45904 | 13
105-141 | BISHA-PV 380/132 KV BSP | 7670 | HCIS Consultant | APPROVED | No | 2025-09-08 | Abas, Mohammed Fekry | 2025-09-09 | 2025-09-10 |  |  | Task line (1.2.1.1) | 1 | 7151 | 0 | STANDARD | ARMADA Security Consulting | SAR | 120000 | APPROVED |  |  | 2025-09-24 | -119999 | 14 | Kumar, Mr. Ranjan | -45910 | 14
105-141 | BISHA-PV 380/132 KV BSP | 7696 | Fiber Optica Cables, Communication Cables, Fibe Optica Patch Cords | APPROVED | No | 2025-09-09 | Abas, Mohammed Fekry | 2025-12-23 | 2025-12-24 | 2025-09-18 | 2025-09-09 | No data shared from PMT to proceed further. | 0 | 7993 | 0 | STANDARD | RASHID SAEED AHMED AL GHAMDI COMM INFO TRAD EST | SAR | 959900 | IN PROCESS |  |  |  | -959900 | 39 | Hegazy, Ayman | -46015 | -46015
105-141 | BISHA-PV 380/132 KV BSP | 7696 | Fiber Optica Cables, Communication Cables, Fibe Optica Patch Cords | APPROVED | No | 2025-09-09 | Abas, Mohammed Fekry | 2025-12-23 | 2025-12-24 | 2025-09-18 | 2025-09-09 | No data shared from PMT to proceed further. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -46015 | -46015
105-141 | BISHA-PV 380/132 KV BSP | 7924 | NGR for BISHA PV BSP 380/132 | APPROVED | No | 2025-10-07 | Abas, Mohammed Fekry | 2025-11-24 | 2025-11-24 | 2025-10-29 |  | One remote end Sizing is not approved | 0 | 7974 | 0 | STANDARD |  | SAR | 0 | INCOMPLETE |  |  |  | 0 | 69 | Kumar, Mr. Ranjan | -45985 | -45985
105-141 | BISHA-PV 380/132 KV BSP | 7924 | NGR for BISHA PV BSP 380/132 | APPROVED | No | 2025-10-07 | Abas, Mohammed Fekry | 2025-11-24 | 2025-11-24 | 2025-10-29 |  | One remote end Sizing is not approved | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45985 | -45985
105-141 | BISHA-PV 380/132 KV BSP | 7951 | Diesel For Generator | APPROVED | No | 2025-10-14 | Abas, Mohammed Fekry | 2025-11-24 | 2025-11-24 | 2025-11-13 |  | no responce from project team | 0 | 7936 | 0 | STANDARD | Talaea Alahlam Trading Company | SAR | 294000 | APPROVED |  |  | 2025-12-07 | -294000 | 13 | Akhtar, Farhan | -45985 | 13
105-141 | BISHA-PV 380/132 KV BSP | 8131 | Extention of Store-Bisha | APPROVED | No | 2025-11-04 | Abas, Mohammed Fekry | 2025-11-13 | 2025-11-16 | 2025-11-10 |  | PR dont have complete details to float the RFQ. Please share the details of extension, drawing, dimension, Signed PR acceptance form. | 0 | 7841 | 0 | STANDARD | Amjad Al Youm Contracting. | SAR | 450780 | APPROVED |  |  | 2025-12-03 | -450780 | 17 | Abuhammad, Samir | -45977 | 17
105-141 | BISHA-PV 380/132 KV BSP | 8325 | Grounding Material-Equipment Earthing & Reinforecement Earthing-01 | APPROVED | No | 2025-11-23 | Abas, Mohammed Fekry | 2025-12-23 | 2025-12-24 | 2025-12-09 |  | As I didn't receive any feedback from the PMT for all quotations sent to them from (2-Dec-2025 & 3-Dec-2025) ... | 0 | 15052 | 0 | STANDARD |  | SAR | 0 | INCOMPLETE |  |  |  | 0 | 39 | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46015 | -46015
105-141 | BISHA-PV 380/132 KV BSP | 8325 | Grounding Material-Equipment Earthing & Reinforecement Earthing-01 | APPROVED | No | 2025-11-23 | Abas, Mohammed Fekry | 2025-12-23 | 2025-12-24 | 2025-12-09 |  | As I didn't receive any feedback from the PMT for all quotations sent to them from (2-Dec-2025 & 3-Dec-2025) ... | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46015 | -46015
105-141 | BISHA-PV 380/132 KV BSP | 8337 | Earthing Material for Sheilding-01 | APPROVED | No | 2025-11-25 | Abas, Mohammed Fekry | 2025-12-18 | 2025-12-18 | 2025-12-09 |  | As I didn't receive any feedback from the PMT for all quotations sent to them from (2-Dec-2025 & 3-Dec-2025) ... | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46009 | -46009
105-141 | BISHA-PV 380/132 KV BSP | 8338 | Chain Hoist For Pumb House | REJECTED | No | 2025-11-26 | Mydeen, Shaik Peer Mohamed | 2025-11-26 |  |  | 2025-11-26 | plesae reject as another PR has been uploaded | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
105-141 | BISHA-PV 380/132 KV BSP | 8340 | chain Hoist For Pump Room | APPROVED | No | 2025-11-25 | Abas, Mohammed Fekry | 2025-11-27 | 2025-11-29 |  |  | Please approve (Task line 1.4.1.1.17) | 0 | 7956 | 0 | STANDARD | SAUDI CRANES & STEEL WORKS FACTORY LTD | SAR | 20000 | APPROVED |  |  | 2025-12-15 | -20000 | 16 | Abuhammad, Samir | -45990 | 16
105-141 | BISHA-PV 380/132 KV BSP | 8344 | Third Party Inspector for Precast installation | APPROVED | No | 2025-11-25 | Abas, Mohammed Fekry | 2025-12-18 | 2025-12-18 | 2025-12-15 |  | Return of PR # 8344 Due to Budget Exceedance as per email sent to Mr. Ahmed Shehata Mon 12/15/2025 9:34 AMin | 0 | 7219 | 0 | STANDARD | SOIL & FOUNDATION CO. LTD | SAR | 151788 | APPROVED |  |  | 2025-12-30 | -151788 | 12 | Tananeh, Khalid Jamal | -46009 | 12
105-141 | BISHA-PV 380/132 KV BSP | 8370 | Container for LCP of HGIS | APPROVED | No | 2025-11-26 | Abas, Mohammed Fekry | 2025-12-29 | 2026-01-01 | 2025-12-24 |  | Please issue the PR with required quantity 6, instead of 1- UOM shall be Nos. not Lump Sum | 0 | 15000 | 0 | STANDARD | Nour Industries Branch of Nour Communication | SAR | 600000 | APPROVED | 2026-01-04 | 2026-01-14 | 2026-01-22 | -600000 | 21 | Kumar, Mr. Ranjan | 13 | 21
105-141 | BISHA-PV 380/132 KV BSP | 8371 | Lighting Fixtures-01 | APPROVED | No | 2025-11-26 | Abas, Mohammed Fekry | 2025-11-30 | 2025-12-02 |  |  | Please Approve (Task No.1.4.1.1.33) | 0 | 7848 | 0 | STANDARD | NATIONAL LIGHTING CO.LTD | SAR | 380000 | APPROVED |  |  | 2025-12-14 | -380000 | 12 | Muaz, Alaa | -45993 | 12
105-141 | BISHA-PV 380/132 KV BSP | 8387 | Electrical Installtion for Substation | APPROVED | No | 2025-11-29 | Abas, Mohammed Fekry | 2025-12-02 | 2025-12-02 |  |  | Please Approve (Task line 1.7.1.15) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45993 | -45993
105-141 | BISHA-PV 380/132 KV BSP | 8417 | Supply of 132kV Outdoor Cable Sealing End XLPE/Air- Gantry Area as per SEC Standard. | REJECTED | No | 2025-12-02 | Yamama, Loai Mohamed | 2025-12-21 | 2025-12-02 |  | 2025-12-23 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45993 | -45993
105-141 | BISHA-PV 380/132 KV BSP | 8542 | Supply of LV & Control Cable | APPROVED | No | 2025-12-21 | Alfaiya, Majed | 2025-12-26 | 2025-12-26 |  |  | Please Approve (Task Line 1.4.1.1.24) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -46017 | -46017
105-141 | BISHA-PV 380/132 KV BSP | 8544 | Conduits for lighting and Small Power | APPROVED | No | 2025-12-17 | Abas, Mohammed Fekry | 2026-01-19 | 2026-01-21 | 2025-12-31 |  | BOQ and Sizing Calculation Not Final | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Mohammed Adel Fahmy | -46043 | -46043
105-141 | BISHA-PV 380/132 KV BSP | 8546 | Electrical Instllation Items-380 KV GIS | APPROVED | No | 2025-12-17 | Alfaiya, Majed | 2025-12-26 | 2025-12-26 |  |  | Please approve (Task line 1.7.1.15) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46017 | -46017
105-141 | BISHA-PV 380/132 KV BSP | 8547 | Electrical Instllation Items-132 KV GIS | APPROVED | No | 2025-12-17 | Alfaiya, Majed | 2025-12-26 | 2025-12-26 |  |  | Please approve (Task line 1.7.1.15) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46017 | -46017
105-141 | BISHA-PV 380/132 KV BSP | 8548 | Electrical Instllation Items-502 MVA Power Transformer | APPROVED | No | 2025-12-17 | Alfaiya, Majed | 2025-12-26 | 2025-12-26 |  |  | Plaeas Approve (Task 1.7.1.15) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46017 | -46017
105-141 | BISHA-PV 380/132 KV BSP | 8549 | Electrical Instllation Items-Other Main Equipment (Reactors, SA, NGR, FSCTs, Sheiding, ACCSR) | APPROVED | No | 2025-12-17 | Alfaiya, Majed | 2025-12-26 | 2025-12-26 |  |  | Plesae approve (Task 1.7.1.15) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46017 | -46017
105-141 | BISHA-PV 380/132 KV BSP | 8550 | Electrical Instllation Items-Protection, Control, SAS, Communication | APPROVED | No | 2025-12-17 | Alfaiya, Majed | 2025-12-26 | 2025-12-26 |  |  | Please Approve (Task 1.7.1.15) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46017 | -46017
105-141 | BISHA-PV 380/132 KV BSP | 8552 | Electrical Instllation Items-Raceways and Cable laying | APPROVED | No | 2025-12-17 | Alfaiya, Majed | 2025-12-26 | 2025-12-26 |  |  | Please approve (Task 1.7.1.15) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46017 | -46017
105-141 | BISHA-PV 380/132 KV BSP | 8553 | Electrical Instllation Items-Termination | APPROVED | No | 2025-12-17 | Alfaiya, Majed | 2025-12-26 | 2025-12-26 |  |  | Please Approve (Task 1.7.1.15) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46017 | -46017
105-141 | BISHA-PV 380/132 KV BSP | 8554 | Electrical Instllation Items-AUX system | APPROVED | No | 2025-12-17 | Alfaiya, Majed | 2025-12-26 | 2025-12-26 |  |  | Please Approve (Task 1.7.1.15) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46017 | -46017
105-141 | BISHA-PV 380/132 KV BSP | 8555 | Shielding Material-30 Meter Mast | APPROVED | No | 2025-12-18 | Alfaiya, Majed | 2025-12-26 | 2025-12-26 |  |  | Please Approve (Task Line. 1.4.1.1.38) | 0 | 15046 | 0 | STANDARD |  | SAR | 0 | INCOMPLETE |  |  |  | 0 | 37 | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46017 | -46017
105-141 | BISHA-PV 380/132 KV BSP | 8555 | Shielding Material-30 Meter Mast | APPROVED | No | 2025-12-18 | Alfaiya, Majed | 2025-12-26 | 2025-12-26 |  |  | Please Approve (Task Line. 1.4.1.1.38) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46017 | -46017
105-141 | BISHA-PV 380/132 KV BSP | 8570 | Lighting Panels Indoor/outdoor | APPROVED | No | 2025-12-23 | Alfaiya, Majed | 2025-12-26 | 2025-12-26 |  |  | Please approve (Task line 1.4.1.1.33) | 0 | 15028 | 0 | STANDARD |  | SAR | 0 | INCOMPLETE |  |  |  | 0 | 37 | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46017 | -46017
105-141 | BISHA-PV 380/132 KV BSP | 8570 | Lighting Panels Indoor/outdoor | APPROVED | No | 2025-12-23 | Alfaiya, Majed | 2025-12-26 | 2025-12-26 |  |  | Please approve (Task line 1.4.1.1.33) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | -46017 | -46017
105-141 | BISHA-PV 380/132 KV BSP | 8571 | Lighting Poles-10 & 5 Meter | APPROVED | No | 2025-12-25 | Abas, Mohammed Fekry | 2025-12-29 | 2026-01-01 |  |  | Please Approve. (Task Line No. 1.4.1.1.33) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -46023 | -46023
105-141 | BISHA-PV 380/132 KV BSP | 8577 | Sockets and Disconnect Switches-01 | RETURNED | No | 2025-12-23 | Mohammed, Mohammed Adel Fahmy | 2026-01-26 | 2026-01-01 | 2026-01-26 |  | Don't have technical response from PMT about offers from 12/1/2026 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Mohammed Adel Fahmy | -46023 | -46023
105-141 | BISHA-PV 380/132 KV BSP | 8579 | Supply for 132 KV Clamps | APPROVED | No | 2025-12-24 | Abas, Mohammed Fekry | 2025-12-29 | 2026-01-01 |  |  | Please Approve (Task Line. 1.4.1.1.40) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46023 | -46023
105-141 | BISHA-PV 380/132 KV BSP | 8584 | 380 KV Clamps and Accessories | APPROVED | No | 2025-12-25 | Abas, Mohammed Fekry | 2025-12-29 | 2026-01-01 |  |  | Please Approve (Task Line. 1.4.1.1.40) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46023 | -46023
105-141 | BISHA-PV 380/132 KV BSP | 8610 | 132 KV Surge Arrestor for NGR as per ICS Study | APPROVED | No | 2025-12-30 | Abas, Mohammed Fekry | 2025-12-31 | 2026-01-01 |  |  | Please Approve (Task Line No. 1.4.1.1.2) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46023 | -46023
105-141 | BISHA-PV 380/132 KV BSP | 8611 | 380 KV Ring type CT for NGR | REJECTED | No | 2025-12-30 | Yamama, Loai Mohamed | 2025-12-31 | 2025-12-30 |  | 2025-12-31 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46021 | -46021
105-141 | BISHA-PV 380/132 KV BSP | 8627 | 380 KV Ring type CT for NGR | APPROVED | No | 2026-01-01 | Abas, Mohammed Fekry | 2026-01-04 | 2026-01-06 |  |  | Please Approve (Task Line No. 1.4.1.1.7) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46028 | -46028
105-141 | BISHA-PV 380/132 KV BSP | 8628 | BISHA-PV 380/132 KV BSP-(120KV-96KV-21KV-15KV) Outdoor/Indoor Surge Arrester | APPROVED | No | 2026-01-01 | Abas, Mohammed Fekry | 2026-01-04 | 2026-01-06 |  |  | Please Approve (Task Line. No1.4.1.1.2) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46028 | -46028
105-141 | BISHA-PV 380/132 KV BSP | 8702 | HCIS Security Materials (Fence Excluded) | APPROVED | No | 2026-01-14 | Abas, Mohammed Fekry | 2026-01-15 | 2026-01-19 |  |  | Please Approve Task Line. (1.4.1.1.86) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46041 | -46041
105-142 | Marine Water sampling HDD-NEOM | 7397 | Marine Water Sampling-NEOM | APPROVED | No | 2025-08-21 | Abas, Mohammed Fekry | 2025-10-08 | 2025-10-08 |  |  | PR For Marine Water Sampling-Budget Task#1.9.1 &1.9.2 | 0 | 7772 | 0 | STANDARD | Power Sub Link SA | EUR | 99873.13 | APPROVED |  |  | 2025-10-26 | -99873.13 | 18 | Abuhammad, Samir | -45938 | 18
105-144 | UNIFIED CONTRACT-NORTHERN SEC | 8775 | Civil work subcontracting | APPROVED | No | 2026-01-22 | Abas, Mohammed Fekry | 2026-01-26 | 2026-01-26 |  |  | Please Approve | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46048 | -46048
105-146 | INTERCONNECTION OF NAWARYAH SS | 6729 | INTERCONNECTION OF NAWARYAH SS-Supply of HV,MV Power Cables | REJECTED | No | 2025-05-27 | Habash, Hany Hassan | 2025-06-04 | 2025-05-27 |  | 2025-06-04 |  | 7998186.51 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45804 | -45804
105-146 | INTERCONNECTION OF NAWARYAH SS | 7156 | INTERCONNECTION OF NAWARYAH SS-Supply of Protection & SAS ,System | APPROVED | No | 2025-07-20 | Abas, Mohammed Fekry | 2025-07-22 | 2025-07-23 |  |  | Budget Line Item # 1.14.7 | 1200000 | 7568 | 0 | STANDARD | ALFANAR CO | SAR | 951000 | APPROVED |  |  | 2025-09-25 | 249000 | 64 | Mohammed, Faisal Ansari | -45861 | 64
105-146 | INTERCONNECTION OF NAWARYAH SS | 7173 | INTERCONNECTION OF NAWARYAH SS-Supply of Telecom Panels | REJECTED | No | 2025-07-21 | Ibrahim, Mr. Ahmed Abdulkadir | 2025-07-21 |  |  | 2025-07-22 | Budget Line Item 1.14.9 | 1900000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | 0 | 0
105-146 | INTERCONNECTION OF NAWARYAH SS | 7189 | INTERCONNECTION OF NAWARYAH SS-Civil Work | APPROVED | No | 2025-07-23 | Abas, Mohammed Fekry | 2025-07-28 | 2025-07-28 |  |  |  | 3000538.74 | 7751 | 0 | STANDARD | Al Badour Electrical Contarcting Est | SAR | 2822070 | APPROVED |  |  | 2025-10-23 | 178468.74 | 87 | Abdelraouf, Islam ِAdel Hanafy | -45866 | 87
105-146 | INTERCONNECTION OF NAWARYAH SS | 7190 | INTERCONNECTION OF NAWARYAH SS-Horizontal Directional Drilling complete (LUMP SUM) | APPROVED | No | 2025-07-23 | Abas, Mohammed Fekry | 2025-07-28 | 2025-07-28 |  |  |  | 837900 | 7740 | 0 | STANDARD | YAHYA SALMAN ALGHAZWANI CONT.EST. | SAR | 691500 | APPROVED |  |  | 2025-10-23 | 146400 | 87 | Abdelraouf, Islam ِAdel Hanafy | -45866 | 87
105-146 | INTERCONNECTION OF NAWARYAH SS | 7193 | INTERCONNECTION OF NAWARYAH SS-Geotechnical investigations, Topographic survey and Ground Protection radar (GPR) Services | APPROVED | No | 2025-07-23 | Abas, Mohammed Fekry | 2025-07-28 | 2025-07-28 |  |  |  | 85100 | 7542 | 0 | STANDARD | Saden Specialized Company for Geological Consulting | SAR | 85100 | APPROVED |  |  | 2025-08-13 | 0 | 16 | Alhadi, Khalid | -45866 | 16
105-146 | INTERCONNECTION OF NAWARYAH SS | 7204 | INTERCONNECTION OF NAWARYAH SS-Desmintling Scope | RETURNED | No | 2025-07-24 | Abdelraouf, Islam ِAdel Hanafy | 2025-10-16 | 2025-07-28 | 2025-10-16 |  | The proposed budget is not sufficient to execute the required scope of work | 749815.25 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelraouf, Islam ِAdel Hanafy | -45866 | -45866
105-146 | INTERCONNECTION OF NAWARYAH SS | 7235 | INTERCONNECTION OF NAWARYAH SS-Supply of HV,MV Power Cables | RETURNED | No | 2025-07-29 | Mohammed, Faisal Ansari | 2025-10-23 | 2025-07-31 | 2025-10-23 |  | This PR line item is not required, as a separate PO has already been issued for NMFOC. | 9702884.55 | 7115 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 9702884.55 | APPROVED |  |  | 2025-08-10 | 0 |  | Mohammed, Faisal Ansari | -45869 | 10
105-146 | INTERCONNECTION OF NAWARYAH SS | 7235 | INTERCONNECTION OF NAWARYAH SS-Supply of HV,MV Power Cables | RETURNED | No | 2025-07-29 | Mohammed, Faisal Ansari | 2025-10-23 | 2025-07-31 | 2025-10-23 |  | This PR line item is not required, as a separate PO has already been issued for NMFOC. | 26015 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45869 | -45869
105-146 | INTERCONNECTION OF NAWARYAH SS | 7801 | Complete civil work for UGC | REJECTED | No | 2025-09-21 | Yamama, Loai Mohamed | 2025-09-28 | 2025-09-25 |  | 2025-09-28 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45925 | -45925
105-146 | INTERCONNECTION OF NAWARYAH SS | 7867 | Telecom System | REJECTED | No | 2025-09-30 | Yamama, Loai Mohamed | 2025-10-16 | 2025-10-05 |  | 2025-10-16 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45935 | -45935
105-146 | INTERCONNECTION OF NAWARYAH SS | 7869 | Cyber Security | APPROVED | No | 2025-09-30 | Abas, Mohammed Fekry | 2025-10-07 | 2025-10-08 |  |  |  | 0 | 7595 | 0 | STANDARD | ACET SOLUTIONS LLC | SAR | 95000 | APPROVED |  |  | 2025-10-14 | -95000 | 6 | Mohammed, Faisal Ansari | -45938 | 6
105-146 | INTERCONNECTION OF NAWARYAH SS | 7883 | Cyber Security | REJECTED | No | 2025-10-02 | Yamama, Loai Mohamed | 2025-10-06 | 2025-10-05 |  | 2025-10-07 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45935 | -45935
105-146 | INTERCONNECTION OF NAWARYAH SS | 7884 | HV Sealing Ends & Joints | REJECTED | No | 2025-10-02 | Yamama, Loai Mohamed | 2025-10-07 | 2025-10-05 |  | 2025-10-07 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45935 | -45935
105-146 | INTERCONNECTION OF NAWARYAH SS | 7885 | NMFOC | APPROVED | No | 2025-10-02 | Abas, Mohammed Fekry | 2025-10-06 | 2025-10-08 |  |  |  | 0 | 7775 | 0 | STANDARD | MIDDLE EAST FIBER CABLE MANUFACTURING CO. | SAR | 45500 | APPROVED |  |  | 2025-10-14 | -45500 | 6 | Mohammed, Faisal Ansari | -45938 | 6
105-146 | INTERCONNECTION OF NAWARYAH SS | 7893 | Site Mobilization | APPROVED | No | 2025-10-02 | Abas, Mohammed Fekry | 2025-10-05 | 2025-10-06 |  |  |  | 0 | 7781 | 0 | STANDARD | MODERN OROUBA GENERAL CONTRACTING CO. | SAR | 398960 | APPROVED |  |  | 2025-11-05 | -398960 | 30 | Abdelraouf, Islam ِAdel Hanafy | -45936 | 30
105-146 | INTERCONNECTION OF NAWARYAH SS | 7894 | Civil Works | REJECTED | No | 2025-10-02 | Yamama, Loai Mohamed | 2025-10-07 | 2025-10-05 |  | 2025-10-07 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45935 | -45935
105-146 | INTERCONNECTION OF NAWARYAH SS | 7925 | HV Sealing Ends & Joints | REJECTED | No | 2025-10-07 | Yamama, Loai Mohamed | 2025-10-16 | 2025-10-09 |  | 2025-10-16 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45939 | -45939
105-146 | INTERCONNECTION OF NAWARYAH SS | 7926 | Link Boxes and SVLs | REJECTED | No | 2025-10-07 | Yamama, Loai Mohamed | 2025-10-16 | 2025-10-09 |  | 2025-10-16 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45939 | -45939
105-146 | INTERCONNECTION OF NAWARYAH SS | 7927 | Installation of GIS Cable Sealing Ends, Insulated Joints and Link Boxes | REJECTED | No | 2025-10-07 | Yamama, Loai Mohamed | 2025-10-16 | 2025-10-09 |  | 2025-10-16 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45939 | -45939
105-146 | INTERCONNECTION OF NAWARYAH SS | 7940 | SCADA & Replacement of RTU | REJECTED | No | 2025-10-09 | Yamama, Loai Mohamed | 2025-10-20 | 2025-10-12 |  | 2025-10-20 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45942 | -45942
105-146 | INTERCONNECTION OF NAWARYAH SS | 7949 | Generator | REJECTED | No | 2025-10-13 | Yamama, Loai Mohamed | 2025-10-20 | 2025-10-15 |  | 2025-10-20 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45945 | -45945
105-146 | INTERCONNECTION OF NAWARYAH SS | 7963 | Fiber Termination Components | REJECTED | No | 2025-10-15 | Yamama, Loai Mohamed | 2025-10-20 | 2025-10-16 |  | 2025-10-20 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45946 | -45946
105-146 | INTERCONNECTION OF NAWARYAH SS | 7972 | Engineering & Design | REJECTED | No | 2025-10-16 | Yamama, Loai Mohamed | 2025-10-21 | 2025-10-16 |  | 2025-10-21 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45946 | -45946
105-146 | INTERCONNECTION OF NAWARYAH SS | 7980 | HV Sealing Ends & Joints | RETURNED | No | 2025-10-16 | Mohammed, Faisal Ansari | 2025-10-26 | 2025-10-23 | 2025-10-26 |  | Shows Budget Exceeded. Kindly revise the PR and submit again. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45953 | -45953
105-146 | INTERCONNECTION OF NAWARYAH SS | 7981 | Link Boxes | INCOMPLETE | No | [6 empty] | Shows Budget Exceeded. Kindly revise the PR and submit again. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | 0 | 0
105-146 | INTERCONNECTION OF NAWARYAH SS | 7984 | Link Boxes | REJECTED | No | 2025-10-16 | Ghaleb, Nour Mahmoud Omaya | 2025-11-05 | 2025-10-30 |  | 2025-11-05 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45960 | -45960
105-146 | INTERCONNECTION OF NAWARYAH SS | 8015 | Fiber Termination Components | APPROVED | No | 2025-10-20 | Abas, Mohammed Fekry | 2025-10-22 | 2025-10-23 |  |  |  | 0 | 7808 | 0 | STANDARD | AMWAJ TELECOMMUNICATION MFG. CO. | SAR | 19212 | APPROVED |  |  | 2025-10-29 | -19212 | 6 | Mohammed, Faisal Ansari | -45953 | 6
105-146 | INTERCONNECTION OF NAWARYAH SS | 8020 | Generator | RETURNED | No | 2025-10-21 | Abdelraouf, Islam ِAdel Hanafy | 2025-11-10 | 2025-11-04 | 2025-11-10 |  | Already Generator provided by Company Asset | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelraouf, Islam ِAdel Hanafy | -45965 | -45965
105-146 | INTERCONNECTION OF NAWARYAH SS | 8035 | Engineering & Design | REJECTED | No | 2025-10-22 | Yamama, Loai Mohamed | 2025-10-23 | 2025-10-23 |  | 2025-10-28 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45953 | -45953
105-146 | INTERCONNECTION OF NAWARYAH SS | 8046 | Dismantling Works | REJECTED | No | 2025-10-23 | Yamama, Loai Mohamed | 2025-11-02 | 2025-10-27 |  | 2025-11-02 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45957 | -45957
105-146 | INTERCONNECTION OF NAWARYAH SS | 8077 | Laptop Device - SEC PM | REJECTED | No | 2025-10-28 | Alharbi, Atef Saud | 2025-10-29 | 2025-10-29 |  | 2025-10-30 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45959 | -45959
105-146 | INTERCONNECTION OF NAWARYAH SS | 8079 | Engineering & Design | REJECTED | No | 2025-10-28 | Ghaleb, Nour Mahmoud Omaya | 2025-11-05 | 2025-10-30 |  | 2025-11-05 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45960 | -45960
105-146 | INTERCONNECTION OF NAWARYAH SS | 8084 | Telecommunication System | REJECTED | No | 2025-10-28 | Yamama, Loai Mohamed | 2025-11-02 | 2025-10-29 |  | 2025-11-02 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45959 | -45959
105-146 | INTERCONNECTION OF NAWARYAH SS | 8086 | HV Sealing Ends and Joints | REJECTED | No | 2025-10-28 | Ghaleb, Nour Mahmoud Omaya | 2025-11-05 | 2025-10-29 |  | 2025-11-05 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45959 | -45959
105-146 | INTERCONNECTION OF NAWARYAH SS | 8087 | Installation of GIS Cable Sealing Ends, Insulated Joints, and Link Boxes | REJECTED | No | 2025-10-29 | Ghaleb, Nour Mahmoud Omaya | 2025-11-12 | 2025-11-10 |  | 2025-11-18 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45971 | -45971
105-146 | INTERCONNECTION OF NAWARYAH SS | 8132 | Security Guard | REJECTED | No | 2025-11-04 | Barasayn, Mohammed Talal Mohammed | 2025-11-05 |  |  | 2025-11-05 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | 0 | 0
105-146 | INTERCONNECTION OF NAWARYAH SS | 8136 | Security Guard | REJECTED | No | 2025-11-05 | Ghaleb, Nour Mahmoud Omaya | 2025-11-12 | 2025-11-08 |  | 2025-11-13 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45969 | -45969
105-146 | INTERCONNECTION OF NAWARYAH SS | 8187 | Security Guard | REJECTED | No | 2025-11-11 | Ghaleb, Nour Mahmoud Omaya | 2025-11-13 | 2025-11-13 |  | 2025-11-13 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45974 | -45974
105-146 | INTERCONNECTION OF NAWARYAH SS | 8204 | Dismantling Works | APPROVED | No | 2025-11-12 | Abas, Mohammed Fekry | 2025-11-13 | 2025-11-16 |  |  |  | 0 | 7917 | 0 | STANDARD | Takatuf Al Hayat Contracting Establishment | SAR | 1900000 | APPROVED |  |  | 2025-12-07 | -1900000 | 21 | Abdelraouf, Islam ِAdel Hanafy | -45977 | 21
105-146 | INTERCONNECTION OF NAWARYAH SS | 8206 | Grounding Material | REJECTED | No | 2025-11-12 | Ghaleb, Nour Mahmoud Omaya | 2025-11-17 | 2025-11-13 |  | 2025-11-18 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45974 | -45974
105-146 | INTERCONNECTION OF NAWARYAH SS | 8207 | Design & Engineering | REJECTED | No | 2025-11-12 | Ghaleb, Nour Mahmoud Omaya | 2025-11-17 | 2025-11-13 |  | 2025-11-18 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45974 | -45974
105-146 | INTERCONNECTION OF NAWARYAH SS | 8208 | Installation of GIS Cable Sealing Ends, Insulated Joints, and Link Boxes | REJECTED | No | 2025-11-12 | Ghaleb, Nour Mahmoud Omaya | 2025-11-17 | 2025-11-13 |  | 2025-11-18 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45974 | -45974
105-146 | INTERCONNECTION OF NAWARYAH SS | 8270 | Design & Engineering | RETURNED | No | 2025-11-18 | Alhadi, Khalid | 2025-12-09 | 2025-11-23 | 2025-12-09 |  | PM didn't dend clear feedback about Price breakdown, therefore PR line shall be aligned with PO line to avoid any delay during invoicing process | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45984 | -45984
105-146 | INTERCONNECTION OF NAWARYAH SS | 8320 | Installation of GIS Cable Sealing Ends, Insulated Joints, and Link Boxes | APPROVED | No | 2025-11-22 | Abas, Mohammed Fekry | 2025-11-25 | 2025-11-29 |  |  |  | 0 | 7803 | 0 | STANDARD | Al-Sharhan Company for Contracting | SAR | 280000 | APPROVED |  |  | 2025-12-07 | -280000 | 8 | Mohammed, Faisal Ansari | -45990 | 8
105-146 | INTERCONNECTION OF NAWARYAH SS | 8324 | Grounding Material | RETURNED | No | 2025-11-23 | Mohammed, Faisal Ansari | 2025-12-08 | 2025-11-29 | 2025-12-08 |  | Please check wth the designer for the complete BOQ | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45990 | -45990
105-146 | INTERCONNECTION OF NAWARYAH SS | 8385 | Site Mobilization | RETURNED | No | 2025-11-27 | Abdelraouf, Islam ِAdel Hanafy | 2025-12-22 | 2025-12-02 | 2025-12-22 |  | POCR not attached + Signboard not available in PR | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelraouf, Islam ِAdel Hanafy | -45993 | -45993
105-146 | INTERCONNECTION OF NAWARYAH SS | 8397 | Splicing and Testing of NMFOC SC | APPROVED | No | 2025-12-01 | Abas, Mohammed Fekry | 2025-12-03 | 2025-12-03 |  |  | 1.7.4 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45994 | -45994
105-146 | INTERCONNECTION OF NAWARYAH SS | 8398 | Testing and Commissioning SC | RETURNED | No | 2025-12-01 | Mohammed, Faisal Ansari | 2025-12-07 | 2025-12-03 | 2025-12-07 |  | Please submit the BOQ along with all required documents, and also confirm whether NIT will handle this in-house. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45994 | -45994
105-146 | INTERCONNECTION OF NAWARYAH SS | 8399 | Grounding Material | RETURNED | No | 2025-12-01 | Mohammed, Faisal Ansari | 2025-12-08 | 2025-12-03 | 2025-12-08 |  | Please check with the designer for the complete BOQ and issue a single PR for all the Earthing Materials. Do not make multiple PRs for the same subject. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45994 | -45994
105-146 | INTERCONNECTION OF NAWARYAH SS | 8401 | Gassing and Degassing SC | RETURNED | No | 2025-12-01 | Mohammed, Faisal Ansari | 2025-12-07 | 2025-12-03 | 2025-12-07 |  | Please submit BOQ along with all required documents. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45994 | -45994
105-146 | INTERCONNECTION OF NAWARYAH SS | 8402 | SCADA & Replacement of RTU | APPROVED | No | 2025-12-01 | Abas, Mohammed Fekry | 2025-12-03 | 2025-12-03 |  |  | 1.7.4 | 0 | 8034 | 0 | STANDARD |  | SAR | 1500000 | INCOMPLETE |  |  |  | -1500000 | 60 | Mohammed, Faisal Ansari | -45994 | -45994
105-146 | INTERCONNECTION OF NAWARYAH SS | 8402 | SCADA & Replacement of RTU | APPROVED | No | 2025-12-01 | Abas, Mohammed Fekry | 2025-12-03 | 2025-12-03 |  |  | 1.7.4 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45994 | -45994
105-146 | INTERCONNECTION OF NAWARYAH SS | 8411 | Security Guard & Security Car | REJECTED | No | 2025-12-02 | Ghaleb, Nour Mahmoud Omaya | 2025-12-02 | 2025-12-02 |  | 2025-12-07 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45993 | -45993
105-146 | INTERCONNECTION OF NAWARYAH SS | 8420 | HV Cable Joints & Termination | APPROVED | No | 2025-12-02 | Abas, Mohammed Fekry | 2025-12-14 | 2025-12-14 |  |  | 1.16.9.1 | 0 | 7567 | 0 | STANDARD | Taihan Electric Wire Saudi Co. | SAR | 396000 | APPROVED |  |  | 2025-12-17 | -396000 | 3 | Mohammed, Faisal Ansari | -46005 | 3
105-146 | INTERCONNECTION OF NAWARYAH SS | 8421 | Supply of Link Boxes | APPROVED | No | 2025-12-02 | Abas, Mohammed Fekry | 2025-12-11 | 2025-12-14 |  |  | 1.16.9.1 | 0 | 7701 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 56500 | APPROVED |  |  | 2025-12-21 | -56500 | 7 | Mohammed, Faisal Ansari | -46005 | 7
105-146 | INTERCONNECTION OF NAWARYAH SS | 8424 | Telecom Panels | APPROVED | No | 2025-12-02 | Abas, Mohammed Fekry | 2025-12-03 | 2025-12-03 |  |  | 1.14.9 | 0 | 7594 | 0 | STANDARD | ALFANAR CO | SAR | 1829000 | APPROVED |  |  | 2025-12-14 | -1829000 | 11 | Mohammed, Faisal Ansari | -45994 | 11
105-146 | INTERCONNECTION OF NAWARYAH SS | 8829 | Security Guards in Portion (Dismantling & demolition for the three substations) | IN PROCESS | No | 2026-01-29 | Ghaleb, Nour Mahmoud Omaya | 2026-01-29 | 2026-01-29 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46051 | -46051
105-148 | Awawdeh Project 20250418 | 6377 | 148-1 | RETURNED | No | 2025-04-18 | Kumar, Mr. Ranjan | 2025-04-23 | 2025-04-18 | 2025-04-23 |  | No RFQ details received with the PR | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45765 | -45765
105-149 | KFCA-Electrical Power Project | 7563 | Design an Engineering Services | RETURNED | No | 2025-08-28 | Mohammed, Faisal Ansari | 2025-10-23 | 2025-09-04 |  |  | Please Approve | 1 | 7546 | 0 | STANDARD | Fahd Alireza Engineering Consultants | SAR | 630000 | APPROVED |  |  | 2025-09-17 | -629999 |  | Mohammed, Faisal Ansari | -45904 | 13
105-149 | KFCA-Electrical Power Project | 7563 | Design an Engineering Services | RETURNED | No | 2025-08-28 | Mohammed, Faisal Ansari | 2025-10-23 | 2025-09-04 |  |  | Please Approve | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45904 | -45904
105-149 | KFCA-Electrical Power Project | 7564 | Geotechnical investigations, Topographic survey, and Ground penetration radar (GPR) services | RETURNED | No | 2025-08-28 | Alhadi, Khalid | 2025-10-06 | 2025-09-01 | 2025-10-06 |  | Line price can't be changed, please submit another PR (The type should be Service by quantity) | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45901 | -45901
105-149 | KFCA-Electrical Power Project | 7832 | RMU for relaimer island | APPROVED | No | 2025-09-25 | Abas, Mohammed Fekry | 2025-09-29 | 2025-10-01 |  |  | please approve the PR for RMUs | 0 | 7745 | 0 | STANDARD | META SWITCHGEAR Factory | SAR | 91000 | APPROVED |  |  | 2025-10-09 | -91000 | 8 | Mohammed, Faisal Ansari | -45931 | 8
105-149 | KFCA-Electrical Power Project | 7833 | Auxiliary transformer | APPROVED | No | 2025-09-25 | Abas, Mohammed Fekry | 2025-10-01 | 2025-10-02 |  |  | please approve the pr for Auxiliary transformer | 0 | 7661 | 0 | STANDARD | META SWITCHGEAR Factory | SAR | 100000 | APPROVED |  |  | 2025-10-14 | -100000 | 12 | Mohammed, Faisal Ansari | -45932 | 12
105-149 | KFCA-Electrical Power Project | 7834 | SWG | APPROVED | No | 2025-09-25 | Abas, Mohammed Fekry | 2025-10-02 | 2025-10-02 |  |  | please approve the PR for SWGR | 0 | 7747 | 0 | STANDARD | ABB ELECTRICAL INDUSTRIES LTD. | SAR | 6322000 | APPROVED |  |  | 2025-10-16 | -6322000 | 14 | Mohammed, Faisal Ansari | -45932 | 14
105-149 | KFCA-Electrical Power Project | 7835 | JIB Crane | APPROVED | No | 2025-09-25 | Abas, Mohammed Fekry | 2025-10-01 | 2025-10-02 |  |  | Please approve the PR for JIB crane | 0 | 7799 | 0 | STANDARD | SAUDI CRANES & STEEL WORKS FACTORY LTD | SAR | 128000 | APPROVED |  |  | 2025-11-25 | -128000 | 54 | Mohammed, Faisal Ansari | -45932 | 54
105-149 | KFCA-Electrical Power Project | 7836 | AVR Trnasformers | APPROVED | No | 2025-09-26 | Abas, Mohammed Fekry | 2025-10-01 | 2025-10-03 |  |  | please approve the PR for AVR Transformers | 0 | 7801 | 0 | STANDARD | UNITED TRANSFORMERS ELECTRIC COMPANY (UTEC) | SAR | 2100000 | APPROVED |  |  | 2025-12-14 | -2100000 | 72 | Mohammed, Faisal Ansari | -45933 | 72
105-149 | KFCA-Electrical Power Project | 7837 | MV Cables | APPROVED | No | 2025-09-26 | Abas, Mohammed Fekry | 2025-10-01 | 2025-10-03 |  |  | Pls approve the MV cable PR | 0 | 7844 | 0 | STANDARD | Hesham El-Sewedy Trading Co. LTD. | SAR | 14248927.5 | INCOMPLETE |  |  |  | -14248927.5 | 121 | Badhman, Saeed | -45933 | -45933
105-149 | KFCA-Electrical Power Project | 7837 | MV Cables | APPROVED | No | 2025-09-26 | Abas, Mohammed Fekry | 2025-10-01 | 2025-10-03 |  |  | Pls approve the MV cable PR | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45933 | -45933
105-149 | KFCA-Electrical Power Project | 7838 | MV cables Reclaimer island | RETURNED | No | 2025-09-26 | Badhman, Saeed | 2025-10-26 | 2025-10-02 | 2025-10-26 |  | Descreption is not right | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45932 | -45932
105-149 | KFCA-Electrical Power Project | 7839 | MV cables for saudi/Bahrain Islands | APPROVED | No | 2025-09-26 | Abas, Mohammed Fekry | 2025-09-29 | 2025-10-02 |  |  | Please approve the MV cables PR for Saudi/Bahrain Islands | 0 | 7844 | 0 | STANDARD | Hesham El-Sewedy Trading Co. LTD. | SAR | 4105500 | INCOMPLETE |  |  |  | -4105500 | 122 | Badhman, Saeed | -45932 | -45932
105-149 | KFCA-Electrical Power Project | 7839 | MV cables for saudi/Bahrain Islands | APPROVED | No | 2025-09-26 | Abas, Mohammed Fekry | 2025-09-29 | 2025-10-02 |  |  | Please approve the MV cables PR for Saudi/Bahrain Islands | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45932 | -45932
105-149 | KFCA-Electrical Power Project | 7915 | site office & hording | REJECTED | No | 2025-10-07 | Sendi, Fahad Fawaz | 2025-10-08 | 2025-10-08 |  | 2025-10-13 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45938 | -45938
105-149 | KFCA-Electrical Power Project | 7917 | Top, GPR survey & soil investgation | APPROVED | No | 2025-10-07 | Abas, Mohammed Fekry | 2025-10-15 | 2025-10-15 |  |  | re intiated due to technical issue | 0 | 7818 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 112961 | APPROVED |  |  | 2025-10-20 | -112961 | 5 | Alhadi, Khalid | -45945 | 5
105-149 | KFCA-Electrical Power Project | 7918 | construction of 19B , Shobaily SS & UG infrustructure including material suply | RETURNED | No | 2025-10-07 | Tananeh, Khalid Jamal | 2025-10-28 | 2025-10-27 | 2025-10-28 |  | Return of PR # 7918 Due to Budget Exceedance adjust the budget amount accordingly and create a new PR once the budget has been updated. as email ( Tue 10/28/2025 11:54 AM) to Mr Ali | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Tananeh, Khalid Jamal | -45957 | -45957
105-149 | KFCA-Electrical Power Project | 8051 | Moblization and site office | APPROVED | No | 2025-10-26 | Abas, Mohammed Fekry | 2025-10-29 | 2025-10-29 |  |  | PLS approve the PR for site office | 0 | 7798 | 0 | STANDARD | Al Arab Modern Contracting Est | SAR | 235111 | APPROVED |  |  | 2025-11-11 | -235111 | 13 | Mohammed, Faisal Ansari | -45959 | 13
105-149 | KFCA-Electrical Power Project | 8053 | Grounding wire for reclaimer island | APPROVED | No | 2025-10-26 | Abas, Mohammed Fekry | 2025-11-12 | 2025-11-13 |  |  | please approve the PR for the reclaimer island | 0 | 7844 | 0 | STANDARD | Hesham El-Sewedy Trading Co. LTD. | SAR | 149120 | INCOMPLETE |  |  |  | -149120 | 80 | Badhman, Saeed | -45974 | -45974
105-149 | KFCA-Electrical Power Project | 8053 | Grounding wire for reclaimer island | APPROVED | No | 2025-10-26 | Abas, Mohammed Fekry | 2025-11-12 | 2025-11-13 |  |  | please approve the PR for the reclaimer island | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45974 | -45974
105-149 | KFCA-Electrical Power Project | 8074 | Civil construction and ducting works | APPROVED | No | 2025-10-28 | Abas, Mohammed Fekry | 2025-10-29 | 2025-10-29 |  |  | please approve the revised PR for civil construction and UG duct bank works | 0 | 7847 | 0 | STANDARD | Suliman Ahmad Khader General Contracting Est (SAK) | SAR | 13379517 | APPROVED |  |  | 2025-11-04 | -13379517 | 6 | Tananeh, Khalid Jamal | -45959 | 6
105-149 | KFCA-Electrical Power Project | 8103 | cables for reclaimer island | APPROVED | No | 2025-11-02 | Abas, Mohammed Fekry | 2025-11-04 | 2025-11-06 |  |  | please Approve the PR for MV cables (Resubmitted due to charge account issue) | 0 | 7844 | 0 | STANDARD | Hesham El-Sewedy Trading Co. LTD. | SAR | 14248927.5 | INCOMPLETE |  |  |  | -14248927.5 | 87 | Badhman, Saeed | -45967 | -45967
105-149 | KFCA-Electrical Power Project | 8103 | cables for reclaimer island | APPROVED | No | 2025-11-02 | Abas, Mohammed Fekry | 2025-11-04 | 2025-11-06 |  |  | please Approve the PR for MV cables (Resubmitted due to charge account issue) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45967 | -45967
105-149 | KFCA-Electrical Power Project | 8120 | earthing material for KFCA | REJECTED | No | 2025-11-03 | Elnour, Ali | 2025-11-17 | 2025-11-04 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45965 | -45965
105-149 | KFCA-Electrical Power Project | 8124 | FOC For KFCA | APPROVED | No | 2025-11-03 | Abas, Mohammed Fekry | 2025-11-09 |  |  |  |  | 0 | 7800 | 0 | STANDARD | MIDDLE EAST FIBER CABLE MANUFACTURING CO. | SAR | 165200 | APPROVED |  |  | 2025-12-04 | -165200 | 25 | Mohammed, Faisal Ansari | 0 | 45995
105-149 | KFCA-Electrical Power Project | 8182 | grounding material for KFSA project | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
105-149 | KFCA-Electrical Power Project | 8192 | PR For Grounding Material | REJECTED | No | 2025-11-12 | Sendi, Fahad Fawaz | 2025-11-13 | 2025-11-13 |  | 2025-11-20 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45974 | -45974
105-149 | KFCA-Electrical Power Project | 8209 | PR for MV Cable Joint kits | RETURNED | No | 2025-11-13 | Mohammed, Faisal Ansari | 2025-12-24 | 2025-11-19 | 2025-12-24 |  | Kindly issue the PR once the technical issues related to the joints are closed, and share the final BOQ with us. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45980 | -45980
105-149 | KFCA-Electrical Power Project | 8224 | Lighting for KFCA | INCOMPLETE | No | [6 empty] | Kindly issue the PR once the technical issues related to the joints are closed, and share the final BOQ with us. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
105-149 | KFCA-Electrical Power Project | 8233 | lighting for kfca | INCOMPLETE | No | [6 empty] | Kindly issue the PR once the technical issues related to the joints are closed, and share the final BOQ with us. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
105-149 | KFCA-Electrical Power Project | 8241 | PR for KFCA Project Lighting System Materials | REJECTED | No | 2025-11-17 | Hashish, Ismail Elsayed Hani Abdullah | 2025-12-02 | 2025-11-18 |  | 2025-12-18 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45979 | -45979
105-149 | KFCA-Electrical Power Project | 8247 | Termination Kits for KFCA Project | RETURNED | No | 2025-11-18 | Mohammed, Faisal Ansari | 2025-12-21 | 2025-12-02 | 2025-12-21 |  | PR shall be issued once the BOQ is finalized. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45993 | -45993
105-149 | KFCA-Electrical Power Project | 8283 | Earthing Material for KFCA Project | INCOMPLETE | No | [6 empty] | PR shall be issued once the BOQ is finalized. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
105-149 | KFCA-Electrical Power Project | 8290 | earthing material for KFCA project | RETURNED | No | 2025-11-20 | Mohammed, Faisal Ansari | 2026-01-27 | 2025-12-22 | 2026-01-27 |  | This is an old PR and does not include all quantities as per the latest BOQ. Kindly revise it at the time of PO finalization to avoid any wastage of time. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46013 | -46013
105-149 | KFCA-Electrical Power Project | 8294 | cable raceway for KFCA project | RETURNED | No | 2025-11-20 | Mohammed, Faisal Ansari | 2026-01-27 | 2025-12-02 | 2026-01-27 |  | Please issue the PR once the BOQ and the final quantity is finalized. The submitted PR is old and doesn't have all the materials listed. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45993 | -45993
105-149 | KFCA-Electrical Power Project | 8412 | SCADA system for KFCA | APPROVED | No | 2025-12-02 | Abas, Mohammed Fekry | 2025-12-09 | 2025-12-11 |  |  | please approve the PR for communication and SCADA syatem | 0 | 15031 | 0 | STANDARD | ABB ELECTRICAL INDUSTRIES LTD. | SAR | 0 | INCOMPLETE |  |  |  | 0 | 52 | Mohammed, Faisal Ansari | -46002 | -46002
105-149 | KFCA-Electrical Power Project | 8412 | SCADA system for KFCA | APPROVED | No | 2025-12-02 | Abas, Mohammed Fekry | 2025-12-09 | 2025-12-11 |  |  | please approve the PR for communication and SCADA syatem | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46002 | -46002
105-149 | KFCA-Electrical Power Project | 8414 | Protection & AMI | RETURNED | No | 2025-12-02 | Mohammed, Faisal Ansari | 2026-01-13 | 2025-12-11 | 2026-01-13 |  | Kindly issue the PR for CRP. For SCADA/ RTU, a separate PO will be issued. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46002 | -46002
105-149 | KFCA-Electrical Power Project | 8415 | fir fighting system for KFCA Project | RETURNED | No | 2025-12-02 | Mohammed, Faisal Ansari | 2025-12-24 | 2025-12-11 | 2025-12-24 |  | Kindly raise the PR once the subject scope is handed over to the Procurement Team by the Mechanical Team. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46002 | -46002
105-149 | KFCA-Electrical Power Project | 8419 | HVAC system for KFCA project | RETURNED | No | 2025-12-02 | Mohammed, Faisal Ansari | 2025-12-24 | 2025-12-11 | 2025-12-24 |  | Kindly raise the PR once the subject scope is handed over to the Procurement Team by the Mechanical Team. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46002 | -46002
105-149 | KFCA-Electrical Power Project | 8432 | Lightning & Sheilding system for KFCA Project | RETURNED | No | 2025-12-03 | Mohammed, Faisal Ansari | 2026-01-27 | 2025-12-11 | 2026-01-27 |  | This is an old PR and does not include all quantities as per the latest BOQ. Kindly revise it at the time of PO finalization to avoid any wastage of time. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46002 | -46002
105-149 | KFCA-Electrical Power Project | 8444 | security system for KFCA project | INCOMPLETE | No | [6 empty] | This is an old PR and does not include all quantities as per the latest BOQ. Kindly revise it at the time of PO finalization to avoid any wastage of time. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
105-149 | KFCA-Electrical Power Project | 8453 | security system for KFCA project | INCOMPLETE | No | [6 empty] | This is an old PR and does not include all quantities as per the latest BOQ. Kindly revise it at the time of PO finalization to avoid any wastage of time. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
105-149 | KFCA-Electrical Power Project | 8458 | LV cables for KFCA project | RETURNED | No | 2025-12-07 | Badhman, Saeed | 2025-12-23 | 2025-12-22 | 2025-12-23 |  | PR criteria is not attached , also there is no approved sizing calculation with final quantities attached | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -46013 | -46013
105-149 | KFCA-Electrical Power Project | 8459 | PR for security system KFCA project | INCOMPLETE | No | [6 empty] | PR criteria is not attached , also there is no approved sizing calculation with final quantities attached | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-149 | KFCA-Electrical Power Project | 8472 | security system for KFCA project | RETURNED | No | 2025-12-07 | Mohammed, Faisal Ansari | 2025-12-24 | 2025-12-22 | 2025-12-24 |  | Kindly raise the PR once the subject scope is handed over to the Procurement Team by the Mechanical Team. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46013 | -46013
105-149 | KFCA-Electrical Power Project | 8564 | lighting system for KFCA project | IN PROCESS | No | 2025-12-22 | Hashish, Ismail Elsayed Hani Abdullah | 2025-12-25 | 2025-12-22 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46013 | -46013
105-149 | KFCA-Electrical Power Project | 8605 | DC power System for KFCA project | APPROVED | No | 2025-12-29 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-13 |  |  | please PProve PR for DC system (Battery,Battery Charger, Battery CB) & DC Panelpoards for Shobaily & 19B Buildings | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46035 | -46035
105-149 | KFCA-Electrical Power Project | 8606 | Control Cables for KFCA project | REJECTED | No | 2025-12-29 | Hashish, Ismail Elsayed Hani Abdullah | 2026-01-15 | 2025-12-30 |  | 2026-01-20 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46021 | -46021
105-149 | KFCA-Electrical Power Project | 8665 | PR for Underground Utility Scanning Survey | APPROVED | No | 2026-01-08 | Abas, Mohammed Fekry | 2026-01-14 | 2026-01-14 |  |  | It is urgently requested to state the construction activities on the Saudi islands | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46036 | -46036
105-149 | KFCA-Electrical Power Project | 8682 | PR for security system for KFCA project | APPROVED | No | 2026-01-11 | Abas, Mohammed Fekry | 2026-01-21 | 2026-01-25 |  |  | please approve PR for security system | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46047 | -46047
105-149 | KFCA-Electrical Power Project | 8684 | PR for Fire Protectione system for KFCA project | IN PROCESS | No | 2026-01-11 | Ahmed, Mohamed Gamal Abdalla | 2026-01-25 | 2026-01-12 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46034 | -46034
105-149 | KFCA-Electrical Power Project | 8687 | PR for Security Cards for KFCA | IN PROCESS | No | 2026-01-12 | Hashish, Ismail Elsayed Hani Abdullah | 2026-01-13 | 2026-01-13 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46035 | -46035
105-149 | KFCA-Electrical Power Project | 8698 | LV cables for KFCA project | IN PROCESS | No | 2026-01-13 | Hashish, Ismail Elsayed Hani Abdullah | 2026-01-14 | 2026-01-14 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46036 | -46036
105-149 | KFCA-Electrical Power Project | 8699 | PR for control cables for KFCA project | IN PROCESS | No | 2026-01-14 | Hashish, Ismail Elsayed Hani Abdullah | 2026-01-14 | 2026-01-14 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46036 | -46036
105-149 | KFCA-Electrical Power Project | 8700 | PR for LV cables at Shobaily building for KFCA project | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-149 | KFCA-Electrical Power Project | 8701 | PR for LV cables at shobaily building for KFCA project | IN PROCESS | No | 2026-01-14 | Hashish, Ismail Elsayed Hani Abdullah | 2026-01-14 | 2026-01-14 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46036 | -46036
105-149 | KFCA-Electrical Power Project | 8703 | PR for Cable laying for KFCA project | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-149 | KFCA-Electrical Power Project | 8704 | PR for Cable Laying for KFCA project | APPROVED | No | 2026-01-14 | Abas, Mohammed Fekry | 2026-01-25 | 2026-01-25 |  |  | please approve PR for Cable Laying, Joints and TR kits at KFCA project | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46047 | -46047
105-149 | KFCA-Electrical Power Project | 8715 | PR for Termination Kits at KFCA project | APPROVED | No | 2026-01-15 | Abas, Mohammed Fekry | 2026-01-25 | 2026-01-26 |  |  | Please approve PR for Cable termination kits for KFCA project | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46048 | -46048
105-149 | KFCA-Electrical Power Project | 8722 | PR for MV joints at KFCA project | APPROVED | No | 2026-01-18 | Abas, Mohammed Fekry | 2026-01-21 | 2026-01-25 |  |  | please approve PR for MV cable Joints at KFCA project | 0 | 8040 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 133050 | IN PROCESS | 2026-01-25 | 2026-01-28 |  | -133050 | 7 | Mohammed, Faisal Ansari | 3 | -46047
105-149 | KFCA-Electrical Power Project | 8722 | PR for MV joints at KFCA project | APPROVED | No | 2026-01-18 | Abas, Mohammed Fekry | 2026-01-21 | 2026-01-25 |  |  | please approve PR for MV cable Joints at KFCA project | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46047 | -46047
105-149 | KFCA-Electrical Power Project | 8741 | pR for Protection & control system for KFCA project | APPROVED | No | 2026-01-20 | Abas, Mohammed Fekry | 2026-01-26 | 2026-01-27 |  |  | please approve PR for Protection & Control system at KFCA project | 0 | 8027 | 0 | STANDARD | INNOVATIVE SYSTEMS COMPANY LTD. | SAR | 2800000 | IN PROCESS | 2026-01-27 | 2026-01-28 |  | -2800000 | 5 | Mohammed, Faisal Ansari | 1 | -46049
105-149 | KFCA-Electrical Power Project | 8741 | pR for Protection & control system for KFCA project | APPROVED | No | 2026-01-20 | Abas, Mohammed Fekry | 2026-01-26 | 2026-01-27 |  |  | please approve PR for Protection & Control system at KFCA project | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -46049 | -46049
105-149 | KFCA-Electrical Power Project | 8772 | PR for HVAC system at KFCA project | IN PROCESS | No | 2026-01-22 | Ahmed, Mohamed Gamal Abdalla | 2026-01-25 | 2026-01-25 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46047 | -46047
105-149 | KFCA-Electrical Power Project | 8828 | PR for Fire Protection Material | IN PROCESS | No | 2026-01-29 | Hashish, Ismail Elsayed Hani Abdullah | 2026-01-30 | 2026-01-30 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46052 | -46052
105-149 | KFCA-Electrical Power Project | 8833 | PR for HVAC System Equipment | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-150 | 230kV Jubail Interties Project | 8191 | Engineering & Design | APPROVED | No | 2025-11-12 | Abas, Mohammed Fekry | 2025-11-13 | 2025-11-16 |  |  |  | 0 | 7886 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 1800000 | APPROVED |  |  | 2025-12-07 | -1800000 | 21 | Alhadi, Khalid | -45977 | 21
105-150 | 230kV Jubail Interties Project | 8193 | Survey and Soil Investigations | APPROVED | No | 2025-11-12 | Abas, Mohammed Fekry | 2025-11-13 | 2025-11-16 |  |  |  | 0 | 7937 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 505997 | APPROVED |  |  | 2025-12-14 | -505997 | 28 | Alhadi, Khalid | -45977 | 28
105-150 | 230kV Jubail Interties Project | 8198 | 110 KV GIS | APPROVED | No | 2025-11-12 | Abas, Mohammed Fekry | 2025-11-13 | 2025-11-16 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45977 | -45977
105-150 | 230kV Jubail Interties Project | 8199 | Protection, SAS & AMI | APPROVED | No | 2025-11-12 | Abas, Mohammed Fekry | 2025-11-13 | 2025-11-16 |  |  |  | 0 | 7960 | 0 | STANDARD | ALFANAR CO | SAR | 7900000 | APPROVED |  |  | 2025-12-14 | -7900000 | 28 | Alhadi, Khalid | -45977 | 28
105-150 | 230kV Jubail Interties Project | 8202 | Telecommunication system | APPROVED | No | 2025-11-12 | Abas, Mohammed Fekry | 2025-11-13 | 2025-11-16 |  |  |  | 0 | 7941 | 0 | STANDARD | ALFANAR CO | SAR | 14000000 | APPROVED |  |  | 2025-12-14 | -14000000 | 28 | Alhadi, Khalid | -45977 | 28
105-150 | 230kV Jubail Interties Project | 8248 | Testing and Commissioning | RETURNED | No | 2025-11-18 | Alhadi, Khalid | 2025-12-08 | 2025-11-23 | 2025-12-08 |  | The project is not near at the stage of T & C. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45984 | -45984
105-150 | 230kV Jubail Interties Project | 8250 | OHTL TESTING & COMMISSIONING | RETURNED | No | 2025-11-18 | Babic, Marian | 2025-12-01 | 2025-11-23 | 2025-12-01 |  | the project is not near the stage of T&C | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45984 | -45984
105-150 | 230kV Jubail Interties Project | 8251 | Nesma Site Office (for Customer) | RETURNED | No | 2025-11-18 | Alhadi, Khalid | 2025-12-01 | 2025-11-23 | 2025-12-01 |  | No scope or details was shared, NOT aligned with PR Criteria | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45984 | -45984
105-150 | 230kV Jubail Interties Project | 8255 | Temporary Store arrangement | RETURNED | No | 2025-11-18 | Alhadi, Khalid | 2025-12-01 | 2025-11-23 | 2025-12-01 |  | No scope or details was shared, NOT aligned with PR Criteria | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45984 | -45984
105-150 | 230kV Jubail Interties Project | 8261 | Power Supply for Site offices | RETURNED | No | 2025-11-18 | Alhadi, Khalid | 2025-12-01 | 2025-11-23 | 2025-12-01 |  | No scope or details was shared, NOT aligned with PR Criteria | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45984 | -45984
105-150 | 230kV Jubail Interties Project | 8263 | Site Mobilization | RETURNED | No | 2025-11-18 | Alhadi, Khalid | 2025-12-01 | 2025-11-23 | 2025-12-01 |  | No scope or details was shared, NOT aligned with PR Criteria | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45984 | -45984
105-150 | 230kV Jubail Interties Project | 8264 | Environmental Studies | RETURNED | No | 2025-11-18 | Alhadi, Khalid | 2025-12-01 | 2025-11-23 | 2025-12-01 |  | No scope or details was shared, it is not aligned with PR criteria. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45984 | -45984
105-150 | 230kV Jubail Interties Project | 8272 | Acces road & Struture pad | RETURNED | No | 2025-11-18 | Alhadi, Khalid | 2025-12-01 | 2025-11-23 | 2025-12-01 |  | No scope or details was shared, it is not aligned with PR criteria. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45984 | -45984
105-150 | 230kV Jubail Interties Project | 8273 | Structure pad | RETURNED | No | 2025-11-18 | Alhadi, Khalid | 2025-12-01 | 2025-11-23 | 2025-12-01 |  | No scope or details was shared, it is not aligned with PR criteria. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45984 | -45984
105-150 | 230kV Jubail Interties Project | 8275 | ACSR Conductor | APPROVED | No | 2025-11-19 | Abas, Mohammed Fekry | 2025-11-23 | 2025-11-23 |  |  | 1.13.3.1.3 ACSR Conductor for 230kV Jubail Intertie. | 0 | 7825 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 9737280 | INCOMPLETE |  |  |  | -9737280 | 70 | Badhman, Saeed | -45984 | -45984
105-150 | 230kV Jubail Interties Project | 8275 | ACSR Conductor | APPROVED | No | 2025-11-19 | Abas, Mohammed Fekry | 2025-11-23 | 2025-11-23 |  |  | 1.13.3.1.3 ACSR Conductor for 230kV Jubail Intertie. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45984 | -45984
105-150 | 230kV Jubail Interties Project | 8277 | Towers - Lattice Steel | APPROVED | No | 2025-11-19 | Abas, Mohammed Fekry | 2025-11-20 | 2025-11-23 |  |  | 1.13.3.1.1 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45984 | -45984
105-150 | 230kV Jubail Interties Project | 8280 | HV cable 2000sqmm | APPROVED | No | 2025-11-19 | Abas, Mohammed Fekry | 2025-11-20 | 2025-11-23 |  |  |  | 0 | 7825 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 381825 | INCOMPLETE |  |  |  | -381825 | 70 | Badhman, Saeed | -45984 | -45984
105-150 | 230kV Jubail Interties Project | 8280 | HV cable 2000sqmm | APPROVED | No | 2025-11-19 | Abas, Mohammed Fekry | 2025-11-20 | 2025-11-23 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45984 | -45984
105-150 | 230kV Jubail Interties Project | 8281 | HV cable - 1200sqmm | APPROVED | No | 2025-11-19 | Abas, Mohammed Fekry | 2025-11-20 | 2025-11-23 |  |  |  | 0 | 7825 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 63421539.6 | INCOMPLETE |  |  |  | -63421539.6 | 70 | Badhman, Saeed | -45984 | -45984
105-150 | 230kV Jubail Interties Project | 8281 | HV cable - 1200sqmm | APPROVED | No | 2025-11-19 | Abas, Mohammed Fekry | 2025-11-20 | 2025-11-23 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45984 | -45984
105-150 | 230kV Jubail Interties Project | 8353 | Civil works | REJECTED | No | 2025-11-26 | Kumar, Soumya Sovan | 2025-11-26 |  |  | 2025-11-26 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
105-150 | 230kV Jubail Interties Project | 8410 | Supply of Surge Arrester | APPROVED | No | 2025-12-01 | Abas, Mohammed Fekry | 2025-12-04 | 2025-12-04 |  |  | 1.13.2.3 - Metal Oxide Surge Arresters | 0 | 15059 | 0 | STANDARD |  | EUR | 80080 | INCOMPLETE |  |  |  | -80080 | 59 | Alhadi, Khalid | -45995 | -45995
105-150 | 230kV Jubail Interties Project | 8410 | Supply of Surge Arrester | APPROVED | No | 2025-12-01 | Abas, Mohammed Fekry | 2025-12-04 | 2025-12-04 |  |  | 1.13.2.3 - Metal Oxide Surge Arresters | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45995 | -45995
105-150 | 230kV Jubail Interties Project | 8433 | Basic Cyber Security | APPROVED | No | 2025-12-03 | Abas, Mohammed Fekry | 2025-12-07 | 2025-12-09 |  |  | TASK - 1.13.2.2 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46000 | -46000
105-150 | 230kV Jubail Interties Project | 8436 | Construction of Access road | RETURNED | No | 2025-12-03 | Abdelraouf, Islam ِAdel Hanafy | 2026-01-18 | 2025-12-09 | 2026-01-18 |  | Returned due to insufficient budget resulting from current site conditions. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelraouf, Islam ِAdel Hanafy | -46000 | -46000
105-150 | 230kV Jubail Interties Project | 8437 | Construction of Structure Pad | RETURNED | No | 2025-12-03 | Abdelraouf, Islam ِAdel Hanafy | 2026-01-18 | 2025-12-09 | 2026-01-18 |  | Returned due to insufficient budget resulting from current site conditions. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelraouf, Islam ِAdel Hanafy | -46000 | -46000
105-150 | 230kV Jubail Interties Project | 8498 | Supply of Insulators | APPROVED | No | 2025-12-10 | Abas, Mohammed Fekry | 2025-12-11 | 2025-12-14 |  |  | 1.13.3.1.2 - Insulators and H/W fittings | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46005 | -46005
105-150 | 230kV Jubail Interties Project | 8499 | Supply of OPGW and OPGW Joint Box | APPROVED | No | 2025-12-10 | Abas, Mohammed Fekry | 2025-12-11 | 2025-12-14 |  |  | TASK - 1.13.3.1.4 | 0 | 7942 | 0 | STANDARD | ZTT International Limited. | USD | 620625 | APPROVED | 2025-12-21 | 2026-01-13 | 2026-01-19 | -583500 | 36 | Alhadi, Khalid | 30 | 36
105-150 | 230kV Jubail Interties Project | 8639 | civil works | REJECTED | No | 2026-01-05 | Kumar, Soumya Sovan | 2026-01-05 |  |  | 2026-01-05 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
105-150 | 230kV Jubail Interties Project | 8736 | Supply of Non Metalic Fiber Optic Cable | APPROVED | No | 2026-01-19 | Abas, Mohammed Fekry | 2026-01-26 | 2026-01-27 |  |  | Task no. - 1.13.3.1.4 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46049 | -46049
105-150 | 230kV Jubail Interties Project | 8791 | Supply of Cable Joints and Termination | APPROVED | No | 2026-01-25 | Abas, Mohammed Fekry | 2026-01-26 | 2026-01-27 |  |  | Task - 1.13.4.1.2 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46049 | -46049
105-150 | 230kV Jubail Interties Project | 8794 | Installation of HV Cable Joints and Termination | APPROVED | No | 2026-01-26 | Abas, Mohammed Fekry | 2026-01-26 | 2026-01-27 |  |  | Task - 1.13.4.2.1 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46049 | -46049
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8105 | Supply & Supervision of Installaiton of Power Transformers and Shunt Reactors_7AB Project | REJECTED | No | 2025-11-02 | Hassane, Hossam Magdi Abdelhamid | 2025-11-06 | 2025-11-03 |  | 2025-11-06 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45964 | -45964
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8107 | Design, Engineering, supply, Installation, Testing & Commissioning, Technical Advising of 115kV GIS_7AB Project | APPROVED | No | 2025-11-02 | Abas, Mohammed Fekry | 2025-11-10 | 2025-11-11 |  |  | Line Item 1.16.4.2, Design, Engineering, supply, Installation, Testing & Commissioning, Technical Advising of 115kV GIS_Jubail Community 7AB Project | 0 | 7804 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 43125000 | APPROVED |  |  | 2025-12-08 | -43125000 | 27 | Alhadi, Khalid | -45972 | 27
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8108 | Design and Engineering Services_7AB Project | APPROVED | No | 2025-11-02 | Abas, Mohammed Fekry | 2025-11-10 | 2025-11-11 |  |  | Line Item 1.16.2.1, Design and Engineering Services_Jubail Community 7AB Project | 0 | 7888 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 2300000 | APPROVED |  |  | 2025-12-04 | -2300000 | 23 | Alhadi, Khalid | -45972 | 23
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8109 | Control & Protection Panels, SAS, AMI | APPROVED | No | 2025-11-02 | Abas, Mohammed Fekry | 2025-11-10 | 2025-11-11 |  |  | Line Item, 1.16.9.1, Control & Protection Panels, SAS, AMI_Jubail Community 7AB Project | 0 | 7898 | 0 | STANDARD | ALFANAR CO | SAR | 13500000 | APPROVED |  |  | 2025-12-08 | -13500000 | 27 | Alhadi, Khalid | -45972 | 27
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8110 | Design, Engineering, Manufacture, Factory Test and Delivery of 13.8kV MV indoor metal-enclosed Switchgear_7AB Project | RETURNED | No | 2025-11-02 | Alhadi, Khalid | 2025-11-12 | 2025-11-11 | 2025-11-12 |  | Overbudget = It shall be 500,000 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45972 | -45972
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8112 | 2.5MVA Station Service Transformers_7AB Project | RETURNED | No | 2025-11-02 | Alhadi, Khalid | 2025-11-13 | 2025-11-11 | 2025-11-13 |  | Oberbudget | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45972 | -45972
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8113 | Project Vehicle to Client as per PTS | RETURNED | No | 2025-11-02 | Alhadi, Khalid | 2025-11-13 | 2025-11-11 | 2025-11-13 |  | Please Contact Facility team | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45972 | -45972
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8114 | 230kV GIS and 230kV Hybrid GIS complete with all Accessories including Design, Engineering, Supply, technical advising, installation supervision, testing & commissioninig_7AB Project | RETURNED | No | 2025-11-03 | Alhadi, Khalid | 2025-11-12 | 2025-11-11 | 2025-11-12 |  | Exceeding the the signed PO value (Overbudget ) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45972 | -45972
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8115 | Supply, Manufacturing, Engineering & Design, FAT, T & C, Configuration /data channels and supervision of Installation for the Telecom system in Main Substation and Remote ends /Control Centers_7AB Project | RETURNED | No | 2025-11-03 | Alhadi, Khalid | 2025-11-13 | 2025-11-11 | 2025-11-13 |  | the budget is not sifficent | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45972 | -45972
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8117 | Soil Investigation_7AB Project | APPROVED | No | 2025-11-03 | Abas, Mohammed Fekry | 2025-11-10 | 2025-11-11 |  |  | Line Item, 1.16.3.1, Soil Investigation_Jubail Community 7AB Project | 0 | 7910 | 0 | STANDARD | Saden Specialized Company for Geological Consulting | SAR | 42500 | APPROVED |  |  | 2025-11-27 | -42500 | 16 | Alhadi, Khalid | -45972 | 16
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8118 | Topographic Survey_7AB Project | APPROVED | No | 2025-11-03 | Abas, Mohammed Fekry | 2025-11-10 | 2025-11-11 |  |  | Line Item: 1.16.3.1, Topographic Survey_Jubail Community 7AB Project | 0 | 7910 | 0 | STANDARD | Saden Specialized Company for Geological Consulting | SAR | 12000 | APPROVED |  |  | 2025-11-27 | -12000 | 16 | Alhadi, Khalid | -45972 | 16
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8119 | Cyber Security Engineering and Supply as per PTS SOW_7AB Project | RETURNED | No | 2025-11-03 | Alhadi, Khalid | 2025-12-31 | 2025-11-11 | 2025-12-31 |  | Scope of work is not defined. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45972 | -45972
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8121 | 150Sq.mm Tinned Copper Conductor_7AB Project | RETURNED | No | 2025-11-03 | Alhadi, Khalid | 2025-11-16 | 2025-11-11 | 2025-11-16 |  | No size calculation | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45972 | -45972
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8122 | 120 Sq.mm Tinned Copper Conductor_Jubail Community 7AB Project | REJECTED | No | 2025-11-03 | Kazmouz, Housam Mohamed Dib | 2025-11-03 |  |  | 2025-11-03 | Line Item 1.16.17.2, 150 Sq.mm Tinned Copper Conductor_Jubail Community 7AB Project | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8123 | 120 Sq.mm Tinned Copper Conductor_Jubail Community 7AB Project | RETURNED | No | 2025-11-03 | Alhadi, Khalid | 2025-11-16 | 2025-11-11 | 2025-11-16 |  | No size calculation | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45972 | -45972
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8146 | Supply & Supervision of Installaiton of Power Transformers and Shunt Reactors_Jubail community 7AB Project | RETURNED | No | 2025-11-06 | Kumar, Mr. Ranjan | 2025-11-23 | 2025-11-11 | 2025-11-23 |  | Ocean Frieght CIF (Dammam is included in Unite price of the material, since we dont have price breakdown this line is returned. PO 7905 approved in Oracle. | 0 | 7905 | 0 | STANDARD | BEST-BALIKESIR ELECTROMEKANIK SANAYI TESISLERI A.S. | USD | 39600000 | APPROVED |  |  | 2025-11-19 | -39600000 |  | Kumar, Mr. Ranjan | -45972 | 8
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8146 | Supply & Supervision of Installaiton of Power Transformers and Shunt Reactors_Jubail community 7AB Project | RETURNED | No | 2025-11-06 | Kumar, Mr. Ranjan | 2025-11-23 | 2025-11-11 | 2025-11-23 |  | Ocean Frieght CIF (Dammam is included in Unite price of the material, since we dont have price breakdown this line is returned. PO 7905 approved in Oracle. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45972 | -45972
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8150 | Design, Manufacturing, Test and Supply of Zigzag Grounding TransformDesign, Manufacturing, Test and Supply of Zigzag Grounding Transformers_7AB | RETURNED | No | 2025-11-09 | Alhadi, Khalid | 2025-11-30 | 2025-11-11 | 2025-11-30 |  | Optional Price, It will be submitted once the item is required by Client. | 0 | 7902 | 0 | STANDARD | Koncar- Distribution and Special Transformation d.d.Zagreb | EUR | 1884400 | APPROVED |  |  | 2025-12-14 | -1884400 |  | Alhadi, Khalid | -45972 | 33
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8150 | Design, Manufacturing, Test and Supply of Zigzag Grounding TransformDesign, Manufacturing, Test and Supply of Zigzag Grounding Transformers_7AB | RETURNED | No | 2025-11-09 | Alhadi, Khalid | 2025-11-30 | 2025-11-11 | 2025-11-30 |  | Optional Price, It will be submitted once the item is required by Client. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45972 | -45972
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8186 | Design, Fabrication, Production, Delivery and Installation of Precast, Structures Elements_7AB Project | RETURNED | No | 2025-11-11 | Abdelraouf, Islam ِAdel Hanafy | 2025-11-18 | 2025-11-16 | 2025-11-18 |  | Required attachment not found: approved/stamped general layout. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45977 | -45977
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8348 | Design consultant for firefighting system_7AB Project | REJECTED | No | 2025-11-25 | Hassane, Hossam Magdi Abdelhamid | 2025-11-26 | 2025-11-25 |  | 2025-11-26 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45986 | -45986
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8573 | Geotechnical Investigations_Jubail Community 7AB | APPROVED | No | 2025-12-23 | Abas, Mohammed Fekry | 2025-12-23 | 2025-12-24 |  |  | Line #1.16.3.1, Geotechnical Investigations_Jubail Community 7AB | 0 | 15004 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 41100 | APPROVED | 2025-12-29 | 2026-01-01 | 2026-01-04 | -41100 | 11 | Alhadi, Khalid | 8 | 11
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8582 | Hiring of an NCEC-approved consultancy, ESIA study_Jubail Community 7AB | RETURNED | No | 2025-12-25 | Alhadi, Khalid | 2026-01-06 | 2026-01-01 | 2026-01-06 |  | It is not required according to the project manager | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46023 | -46023
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8619 | Cyber Security System_Jubail Community-7AB | APPROVED | No | 2025-12-31 | Abas, Mohammed Fekry | 2026-01-01 | 2026-01-01 |  |  | Line Item 1.16.8.4, Cyber Security System_Jubail Community-7AB | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46023 | -46023
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8629 | 240 Sq.mm Tinned Copper Conductor_Jubail Community 7AB | RETURNED | No | 2026-01-01 | Alhadi, Khalid | 2026-01-08 | 2026-01-06 | 2026-01-08 |  | The requester did not submit the approved sizing calculation by client, which may result in quantity changes at a later stage and could affect the overall cost. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46028 | -46028
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8631 | Project Vehicle to Client as per PTS requirment_Jubail Community 7AB | APPROVED | No | 2026-01-03 | Abas, Mohammed Fekry | 2026-01-04 | 2026-01-06 |  |  | Linr Item 1.9.1, Project Vehicle to Client as per PTS requirment_Jubail Community 7AB | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46028 | -46028
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8640 | Hiring HCIS Consultancy_Jubail Community 7AB | APPROVED | No | 2026-01-05 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-13 |  |  | Line Item 1.16.9.2, Hiring HCIS Consultancy_Jubail Community 7AB | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46035 | -46035
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8641 | Precast / Superstructure_Jubail Community 7AB | APPROVED | No | 2026-01-05 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-13 |  |  | Line item 1.16.2.2, Precast / Superstructure_Jubail Community 7AB | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelraouf, Islam ِAdel Hanafy | -46035 | -46035
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8647 | Design Consultant for Fire Alarm & Fire Fighting System_Jubail Community 7AB | APPROVED | No | 2026-01-05 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-13 |  |  | Line item 1.16.14.2, Design Consultant for Fire Alarm & Fire Fighting System_Jubail Community 7AB | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46035 | -46035
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8656 | Subcontractor for Civil Works_Jubail Community 7AB | APPROVED | No | 2026-01-07 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-13 |  |  | Line Item 1.16.2.2, Subcontractor for Civil Works_Jubail Community 7AB | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelraouf, Islam ِAdel Hanafy | -46035 | -46035
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8657 | Excavation & Backfilling Works_Jubail Community 7AB | APPROVED | No | 2026-01-07 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-13 |  |  | Line Item 1.16.2.2, Excavation & Backfilling Works_Jubail Community 7AB | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelraouf, Islam ِAdel Hanafy | -46035 | -46035
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8658 | Site Office for NIT & SEC_Jubail Community 7AB | RETURNED | No | 2026-01-07 | Alhadi, Khalid | 2026-01-15 | 2026-01-13 | 2026-01-15 |  | Based on the the agreement with PM, PR with one line will be submitted for complete mobilization | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46035 | -46035
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8659 | Temporary Project Sign Board_Jubail Community 7AB | RETURNED | No | 2026-01-07 | Alhadi, Khalid | 2026-01-15 | 2026-01-13 | 2026-01-15 |  | Based on the the agreement with PM, PR with one line will be submitted for complete mobilization | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46035 | -46035
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8660 | Fencing Works for Construction plot_Jubail Community 7AB | RETURNED | No | 2026-01-07 | Alhadi, Khalid | 2026-01-15 | 2026-01-13 | 2026-01-15 |  | Based on the the agreement with PM, PR with one line will be submitted for complete mobilization | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46035 | -46035
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8697 | 230kV GIS and 230kV Hybrid GIS_Jubail Community 7AB | APPROVED | No | 2026-01-13 | Abas, Mohammed Fekry | 2026-01-14 | 2026-01-14 |  |  | Lin Item #1.16.4.1, 230kV GIS and 230kV Hybrid GIS_Jubail Community 7AB | 0 | 7805 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 83625000 | IN PROCESS |  |  |  | -83625000 | 18 | Alhadi, Khalid | -46036 | -46036
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8697 | 230kV GIS and 230kV Hybrid GIS_Jubail Community 7AB | APPROVED | No | 2026-01-13 | Abas, Mohammed Fekry | 2026-01-14 | 2026-01-14 |  |  | Lin Item #1.16.4.1, 230kV GIS and 230kV Hybrid GIS_Jubail Community 7AB | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46036 | -46036
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8728 | OHTL Conductor (ACSR/AW) Type CONDOR 795 KMCIL ASTM B549 (Non Greased)_Jubail Community 7AB | REJECTED | No | 2026-01-19 | Hassane, Hossam Magdi Abdelhamid | 2026-01-28 | 2026-01-19 |  | 2026-01-28 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46041 | -46041
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8729 | 230kV Latticed Steel Tower_Jubail Community 7AB | APPROVED | No | 2026-01-19 | Abas, Mohammed Fekry | 2026-01-26 | 2026-01-26 |  |  | Line Item 1.16.2.3, 230kV Latticed Steel Tower_Jubail Community 7AB | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46048 | -46048
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8799 | Under Ground Utilities Scanning_Jubail Community 7AB | APPROVED | No | 2026-01-27 | Abas, Mohammed Fekry | 2026-01-27 | 2026-01-28 |  |  | Line Item #1.16.3.1, Under Ground Utilities Scanning_Jubail Community 7AB | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46050 | -46050
105-151 | JUBAIL COMMUNITY-7AB 230kV BSP | 8818 | Site Mobilization_Jubail Community 7AB | APPROVED | No | 2026-01-28 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  | Line Item, 1.7.1, Site Mobilization Complete_Jubail Community 7AB | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46050 | -46050
105-152 | JUBAIL SOUTH EAST 230kV BSP | 8286 | HV CABLE | APPROVED | No | 2025-11-19 | Abas, Mohammed Fekry | 2025-11-20 | 2025-11-23 |  |  |  | 0 | 7862 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 44507542.5 | APPROVED | 2025-12-23 | 2025-12-26 | 2026-01-04 | -44507542.5 | 42 | Badhman, Saeed | 33 | 42
105-152 | JUBAIL SOUTH EAST 230kV BSP | 8494 | power transformer | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-152 | JUBAIL SOUTH EAST 230kV BSP | 8495 | design & engineering | APPROVED | No | 2025-12-10 | Abas, Mohammed Fekry | 2025-12-14 | 2025-12-14 |  |  |  | 0 | 8018 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 4550000 | APPROVED |  |  | 2025-12-17 | -4550000 | 3 | Babic, Marian | -46005 | 3
105-152 | JUBAIL SOUTH EAST 230kV BSP | 8529 | 115/34.5KV 80/100MVA, Power Transformer | APPROVED | No | 2025-12-16 | Abas, Mohammed Fekry | 2025-12-17 | 2025-12-18 |  |  |  | 0 | 7959 | 0 | STANDARD | Liaoning-Efacec Electrical Equipment Co., Ltd. | USD | 9417825 | APPROVED |  |  | 2025-12-30 | -9417825 | 12 | Babic, Marian | -46009 | 12
105-152 | JUBAIL SOUTH EAST 230kV BSP | 8580 | EISA Study | APPROVED | No | 2025-12-24 | Abas, Mohammed Fekry | 2025-12-29 | 2025-12-30 |  |  |  | 0 | 15044 | 0 | STANDARD | Fursan Alistedamah office for Environmental Consultation ( FIECO) | SAR | 12000 | IN PROCESS | 2026-01-26 | 2026-01-28 |  | -12000 | 33 | Alhadi, Khalid | 29 | -46021
105-152 | JUBAIL SOUTH EAST 230kV BSP | 8580 | EISA Study | APPROVED | No | 2025-12-24 | Abas, Mohammed Fekry | 2025-12-29 | 2025-12-30 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -46021 | -46021
105-152 | JUBAIL SOUTH EAST 230kV BSP | 8581 | HCIS Consultant | APPROVED | No | 2025-12-24 | Abas, Mohammed Fekry | 2025-12-29 | 2025-12-30 |  |  |  | 0 | 15037 | 0 | STANDARD |  | SAR | 0 | INCOMPLETE |  |  |  | 0 | 33 | Babic, Marian | -46021 | -46021
105-152 | JUBAIL SOUTH EAST 230kV BSP | 8581 | HCIS Consultant | APPROVED | No | 2025-12-24 | Abas, Mohammed Fekry | 2025-12-29 | 2025-12-30 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46021 | -46021
105-152 | JUBAIL SOUTH EAST 230kV BSP | 8705 | Soil Investigation | APPROVED | No | 2026-01-14 | Abas, Mohammed Fekry | 2026-01-20 | 2026-01-20 |  |  |  | 0 | 15041 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 90386.25 | APPROVED | 2026-01-21 | 2026-01-25 | 2026-01-29 | -90386.25 | 9 | Babic, Marian | 5 | 9
105-152 | JUBAIL SOUTH EAST 230kV BSP | 8706 | Soil Investigation | RETURNED | No | 2026-01-14 | Babic, Marian | 2026-01-20 | 2026-01-20 | 2026-01-20 |  | not required, PO will be issued from PR 8705 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46042 | -46042
105-152 | JUBAIL SOUTH EAST 230kV BSP | 8707 | Soil Investigation | REJECTED | No | 2026-01-14 | Ali, Mubashir Muhammad Ashrif Naeem | 2026-01-14 |  |  | 2026-01-18 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-152 | JUBAIL SOUTH EAST 230kV BSP | 8751 | 80MVAr Reactors | APPROVED | No | 2026-01-20 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  | 1.25.1, 80Mvar Reactor | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46050 | -46050
105-152 | JUBAIL SOUTH EAST 230kV BSP | 8755 | 402.5MVA Power Transformers | APPROVED | No | 2026-01-21 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  | 1.24.1 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46050 | -46050
105-152 | JUBAIL SOUTH EAST 230kV BSP | 8764 | 230KV GIS Including HGIS and Special Tools As per PTS-24ER208 | APPROVED | No | 2026-01-21 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  |  | 0 | 7953 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 140625000 | IN PROCESS |  |  |  | -140625000 | 4 | Babic, Marian | -46050 | -46050
105-152 | JUBAIL SOUTH EAST 230kV BSP | 8764 | 230KV GIS Including HGIS and Special Tools As per PTS-24ER208 | APPROVED | No | 2026-01-21 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46050 | -46050
105-152 | JUBAIL SOUTH EAST 230kV BSP | 8769 | 115KV GIS including Special Tools as per PTS-24ER208 | APPROVED | No | 2026-01-21 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  |  | 0 | 7954 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 61875000 | IN PROCESS |  |  |  | -61875000 | 4 | Babic, Marian | -46050 | -46050
105-152 | JUBAIL SOUTH EAST 230kV BSP | 8769 | 115KV GIS including Special Tools as per PTS-24ER208 | APPROVED | No | 2026-01-21 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46050 | -46050
105-152 | JUBAIL SOUTH EAST 230kV BSP | 8771 | Telecom System for Main Substation including all Remote Ends as per PTS-24ER208 | APPROVED | No | 2026-01-21 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46050 | -46050
105-152 | JUBAIL SOUTH EAST 230kV BSP | 8784 | 34.5KV MV Switchgear including Special Tools as per PTS-24ER208 | APPROVED | No | 2026-01-25 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  | 1.26.1 34.5 k.v MV Switchgear 2500A -25k/1sec with BC & BS. | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46050 | -46050
105-152 | JUBAIL SOUTH EAST 230kV BSP | 8785 | Control, protection and SAS System as per PTS-24ER208 | APPROVED | No | 2026-01-25 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  | 1.27.2 Protection, SAS & AMI | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46050 | -46050
105-152 | JUBAIL SOUTH EAST 230kV BSP | 8815 | HCIS Consultant for Fire Protection System | IN PROCESS | No | 2026-01-28 | Ghaleb, Nour Mahmoud Omaya | 2026-01-28 | 2026-01-28 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46050 | -46050
105-153 | JUBAIL NORTH 230kV BSP | 8244 | HV Cable | APPROVED | No | 2025-11-17 | Abas, Mohammed Fekry | 2025-11-19 | 2025-11-23 |  |  |  | 0 | 7861 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 36541206 | APPROVED | 2025-12-23 | 2026-01-01 | 2026-01-05 | -36541206 | 43 | Badhman, Saeed | 39 | 43
105-153 | JUBAIL NORTH 230kV BSP | 8287 | Communication System | APPROVED | No | 2025-11-19 | Abas, Mohammed Fekry | 2025-11-20 | 2025-11-23 |  |  |  | 0 | 7906 | 0 | STANDARD | ALFANAR CO | SAR | 24500000 | IN PROCESS |  |  |  | -24500000 | 70 | Babic, Marian | -45984 | -45984
105-153 | JUBAIL NORTH 230kV BSP | 8287 | Communication System | APPROVED | No | 2025-11-19 | Abas, Mohammed Fekry | 2025-11-20 | 2025-11-23 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45984 | -45984
105-153 | JUBAIL NORTH 230kV BSP | 8496 | design & engineering | APPROVED | No | 2025-12-10 | Abas, Mohammed Fekry | 2025-12-14 | 2025-12-14 |  |  |  | 0 | 8019 | 0 | STANDARD | Dar International for Engineering Consultancy | SAR | 3020000 | APPROVED |  |  | 2025-12-17 | -3020000 | 3 | Babic, Marian | -46005 | 3
105-153 | JUBAIL NORTH 230kV BSP | 8583 | Capacitor Bank | APPROVED | No | 2025-12-25 | Abas, Mohammed Fekry | 2025-12-29 | 2025-12-30 |  |  |  | 0 | 8031 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 1990000 | APPROVED | 2026-01-04 | 2026-01-13 | 2026-01-19 | -1990000 | 20 | Kumar, Mr. Ranjan | 14 | 20
105-153 | JUBAIL NORTH 230kV BSP | 8708 | Vehivcle for client as per PTS | APPROVED | No | 2026-01-14 | Abas, Mohammed Fekry | 2026-01-20 | 2026-01-21 |  |  | 1.9.1-Vehivcle for client as per PTS | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46043 | -46043
105-153 | JUBAIL NORTH 230kV BSP | 8709 | Soil Investigation and GBR | APPROVED | No | 2026-01-15 | Abas, Mohammed Fekry | 2026-01-20 | 2026-01-20 |  |  | Soil Investigation-Topographic survey | 1 | 15042 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 88349.35 | APPROVED | 2026-01-25 | 2026-01-26 | 2026-01-29 | -88348.35 | 9 | Babic, Marian | 6 | 9
105-153 | JUBAIL NORTH 230kV BSP | 8713 | supply of 230 KV GIS & HGIS including all applicable accessories | APPROVED | No | 2026-01-15 | Abas, Mohammed Fekry | 2026-01-21 | 2026-01-25 |  |  | 1.23.1 - 230 KV, 3150A, 63kA GIS complete with GIB and Internal UHF PD Sensors Surge arresters | 0 | 7952 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 110100000 | INCOMPLETE |  |  |  | -110100000 | 7 | Babic, Marian | -46047 | -46047
105-153 | JUBAIL NORTH 230kV BSP | 8713 | supply of 230 KV GIS & HGIS including all applicable accessories | APPROVED | No | 2026-01-15 | Abas, Mohammed Fekry | 2026-01-21 | 2026-01-25 |  |  | 1.23.1 - 230 KV, 3150A, 63kA GIS complete with GIB and Internal UHF PD Sensors Surge arresters | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46047 | -46047
105-153 | JUBAIL NORTH 230kV BSP | 8716 | supply 230/34.5/13.8 KV 133 MVA Power Transformers and 230 KV , 80 MVAR Shunt Reactors | INCOMPLETE | No | [6 empty] | 1.23.1 - 230 KV, 3150A, 63kA GIS complete with GIB and Internal UHF PD Sensors Surge arresters | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
105-153 | JUBAIL NORTH 230kV BSP | 8718 | Supply of Power Transformer and Reactors | APPROVED | No | 2026-01-15 | Abas, Mohammed Fekry | 2026-01-21 | 2026-01-25 |  |  | 1.24.1 & 1.25.1 - Supply ,supervision ,testing and commissioning of Power Transformers and Reactors | 0 | 7908 | 0 | STANDARD | BEST-BALIKESIR ELECTROMEKANIK SANAYI TESISLERI A.S. | USD | 43668750 | IN PROCESS | 2026-01-25 | 2026-01-28 |  | -43668750 | 7 | Babic, Marian | 3 | -46047
105-153 | JUBAIL NORTH 230kV BSP | 8718 | Supply of Power Transformer and Reactors | APPROVED | No | 2026-01-15 | Abas, Mohammed Fekry | 2026-01-21 | 2026-01-25 |  |  | 1.24.1 & 1.25.1 - Supply ,supervision ,testing and commissioning of Power Transformers and Reactors | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46047 | -46047
105-153 | JUBAIL NORTH 230kV BSP | 8719 | Supply of Capacitor bank including all accessories | INCOMPLETE | No | [6 empty] | 1.24.1 & 1.25.1 - Supply ,supervision ,testing and commissioning of Power Transformers and Reactors | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | 0 | 0
105-153 | JUBAIL NORTH 230kV BSP | 8723 | Supply e4.5KV Capacitor Bank | APPROVED | No | 2026-01-18 | Abas, Mohammed Fekry | 2026-01-21 | 2026-01-25 |  |  | 1.25.2 - Suuply,installation ,testing and commssioning of 34.5KV 10MVAR Capacitor Bank | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -46047 | -46047
105-153 | JUBAIL NORTH 230kV BSP | 8733 | Engineering, Design & Civil engineering consultant | RETURNED | No | 2026-01-19 | Babic, Marian | 2026-01-25 | 2026-01-25 | 2026-01-25 |  | not required (PO already issued) | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46047 | -46047
105-153 | JUBAIL NORTH 230kV BSP | 8745 | Site mobilization including NESMA AND SEC site offices | APPROVED | No | 2026-01-20 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  | 1.7.1 SEC + Nesma Site Office | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46050 | -46050
105-153 | JUBAIL NORTH 230kV BSP | 8747 | HCIS Consultant | APPROVED | No | 2026-01-20 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  | 1.28.2 SUBSTATION SECURITY (HCIS, CLASS-3) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46050 | -46050
105-153 | JUBAIL NORTH 230kV BSP | 8748 | Fire Alarm and FIre FIghting Systems | RETURNED | No | 2026-01-20 | Babic, Marian | 2026-01-29 | 2026-01-28 | 2026-01-29 |  | shall be raised at later stage | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46050 | -46050
105-153 | JUBAIL NORTH 230kV BSP | 8754 | Telecommunication System | RETURNED | No | 2026-01-21 | Babic, Marian | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-21 | not required, already PR available | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46050 | -46050
105-153 | JUBAIL NORTH 230kV BSP | 8757 | Protection and SAS panels as per PTS | APPROVED | No | 2026-01-21 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  |  | 1.28.1 Protection, SAS & AMI panels as per PTS | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46050 | -46050
105-153 | JUBAIL NORTH 230kV BSP | 8760 | MV Switchgear 34.5KV | APPROVED | No | 2026-01-21 | Abas, Mohammed Fekry | 2026-01-28 | 2026-01-28 |  | 2026-01-21 | 1.26.1 MV Switchgear | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46050 | -46050
105-153 | JUBAIL NORTH 230kV BSP | 8762 | 230KV HV Cables | RETURNED | No | 2026-01-21 | Babic, Marian | 2026-01-28 | 2026-01-28 | 2026-01-28 |  | Not required, already PR available | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46050 | -46050
105-153 | JUBAIL NORTH 230kV BSP | 8807 | ENVIRONMENT & SOCIAL IMPACT ASSESMENT ( ESIA ) | IN PROCESS | No | 2026-01-28 | Abdelaziz, Zaid Adnan Mufadi | 2026-01-28 |  |  |  | Not required, already PR available | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | 0 | 0
105-154 | 380kV OHTL SAMHA BSP #9105 | 8351 | Construction of Access Road & Structural Pads | APPROVED | No | 2025-11-26 | Abas, Mohammed Fekry | 2025-11-27 | 2025-11-29 |  |  | Construction of Access Road & Structural Pads | 0 | 7973 | 0 | STANDARD | Mashael Aseer Contracting Company. | SAR | 1621800 | APPROVED | 2025-12-25 | 2026-01-01 | 2026-01-04 | -1621800 | 36 | Tananeh, Khalid Jamal | 33 | 36
105-154 | 380kV OHTL SAMHA BSP #9105 | 8356 | Geotechnical Investigation | APPROVED | No | 2025-11-26 | Abas, Mohammed Fekry | 2025-11-26 | 2025-11-29 |  |  | Geotechnical Investigation | 0 | 7920 | 0 | STANDARD | Gulf Bridge Laboratory for Technical Consulting and Laboratories | SAR | 402085 | APPROVED |  |  | 2025-12-07 | -402085 | 8 | Babic, Marian | -45990 | 8
105-154 | 380kV OHTL SAMHA BSP #9105 | 8367 | Supply of ACSR Conductor | APPROVED | No | 2025-11-26 | Abas, Mohammed Fekry | 2025-11-27 | 2025-11-29 |  |  | Supply of ACSR Conductor | 0 | 7922 | 0 | STANDARD | Riyadh Cables Group Company | SAR | 22610000 | APPROVED |  |  | 2025-12-16 | -22610000 | 17 | Babic, Marian | -45990 | 17
105-154 | 380kV OHTL SAMHA BSP #9105 | 8376 | Lattice Steel Towers | APPROVED | No | 2025-11-27 | Abas, Mohammed Fekry | 2025-11-27 | 2025-11-29 |  |  | Lattice Steel Towers | 0 | 7921 | 0 | STANDARD | Hesham Helal Elsewedy & Partners for Construction Co., Ltd. | SAR | 35960000 | APPROVED |  |  | 2025-12-16 | -35960000 | 17 | Babic, Marian | -45990 | 17
105-154 | 380kV OHTL SAMHA BSP #9105 | 8380 | OFMR & FSTP | APPROVED | No | 2025-11-27 | Abas, Mohammed Fekry | 2025-11-27 | 2025-11-29 |  |  | OFMR & FSTP | 0 | 7997 | 0 | STANDARD | AMWAJ TELECOMMUNICATION MFG. CO. | SAR | 17800 | APPROVED |  |  | 2025-12-15 | -17800 | 16 | Babic, Marian | -45990 | 16
105-154 | 380kV OHTL SAMHA BSP #9105 | 8381 | Quad Spacer & Vibration Dampers | APPROVED | No | 2025-11-27 | Abas, Mohammed Fekry | 2025-11-27 | 2025-11-29 |  |  | Quad Spacer & Vibration Dampers | 0 | 7923 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 2282900 | APPROVED |  |  | 2025-12-16 | -2282900 | 17 | Babic, Marian | -45990 | 17
105-154 | 380kV OHTL SAMHA BSP #9105 | 8429 | Topographic Survey | APPROVED | No | 2025-12-02 | Abas, Mohammed Fekry | 2025-12-07 | 2025-12-09 |  |  | Topographic Survey-Site Survey | 0 | 7907 | 0 | STANDARD | MAIN INTEGRATED TEAM COMPANY(S) | SAR | 47214.5 | APPROVED |  |  | 2025-12-15 | -47214.5 | 6 | Babic, Marian | -46000 | 6
105-154 | 380kV OHTL SAMHA BSP #9105 | 8560 | Cap & Pin Type insulators | REJECTED | No | 2025-12-18 | Habash, Hany Hassan | 2025-12-28 | 2025-12-22 |  | 2025-12-29 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46013 | -46013
105-154 | 380kV OHTL SAMHA BSP #9105 | 8572 | Supply of OPGW | RETURNED | No | 2025-12-23 | Babic, Marian | 2026-01-05 | 2025-12-30 | 2026-01-05 |  | over budget | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46021 | -46021
105-154 | 380kV OHTL SAMHA BSP #9105 | 8614 | Engineering Design Services | APPROVED | No | 2025-12-31 | Abas, Mohammed Fekry | 2026-01-05 | 2026-01-07 |  |  | Engineering Design Services- BAHRAWY | 0 | 7900 | 0 | STANDARD | Bahrawy Consultancy Group B.C.G | USD | 289999.99 | APPROVED | 2026-01-07 | 2026-01-08 | 2026-01-13 | -289999.99 | 6 | Babic, Marian | 1 | 6
105-154 | 380kV OHTL SAMHA BSP #9105 | 8633 | Hardware Fittings | APPROVED | No | 2026-01-05 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-11 |  |  | Hardware Fittings - OHTL SAMHA | 0 | 7924 | 0 | STANDARD | PFISTERER Switzerland AG | USD | 5737513.12 | APPROVED | 2026-01-11 | 2026-01-13 | 2026-01-19 | -5737513.12 | 8 | Babic, Marian | 2 | 8
105-154 | 380kV OHTL SAMHA BSP #9105 | 8636 | Supply of OPGW | APPROVED | No | 2026-01-05 | Abas, Mohammed Fekry | 2026-01-13 | 2026-01-13 |  |  | Supply of OPGW- OHTL SAMHA | 0 | 7967 | 0 | STANDARD | ZTT International Limited. | USD | 1823287.5 | IN PROCESS |  |  |  | -1823287.5 | 19 | Babic, Marian | -46035 | -46035
105-154 | 380kV OHTL SAMHA BSP #9105 | 8636 | Supply of OPGW | APPROVED | No | 2026-01-05 | Abas, Mohammed Fekry | 2026-01-13 | 2026-01-13 |  |  | Supply of OPGW- OHTL SAMHA | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46035 | -46035
105-154 | 380kV OHTL SAMHA BSP #9105 | 8637 | Cap & Pin Type Insulators | APPROVED | No | 2026-01-05 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-11 |  |  | Cap & Pin Type Insulators- OHTL SAMHA | 0 | 7933 | 0 | STANDARD | GREENGRID (CHINA) TECHNOLOGY CO. LTD. | USD | 11677515.38 | APPROVED | 2026-01-11 | 2026-01-13 | 2026-01-19 | -11677515.38 | 8 | Babic, Marian | 2 | 8
105-154 | 380kV OHTL SAMHA BSP #9105 | 8638 | Grounding Material | APPROVED | No | 2026-01-05 | Abas, Mohammed Fekry | 2026-01-14 | 2026-01-14 |  |  | Grounding Material- OHTL SAMHA | 0 | 15015 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 328135.45 | APPROVED | 2026-01-15 | 2026-01-19 | 2026-01-21 | -328135.45 | 7 | Babic, Marian | 5 | 7
105-154 | 380kV OHTL SAMHA BSP #9105 | 8765 | Civil Works For Towers Foundations | APPROVED | No | 2026-01-21 | Abas, Mohammed Fekry | 2026-01-25 | 2026-01-26 |  |  | Civil Works For Towers Foundations-- SAMHA OHTL | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Hegazy, Ayman | -46048 | -46048
105-154 | 380kV OHTL SAMHA BSP #9105 | 8801 | Ready Mix Concrete | IN PROCESS | No | 2026-01-27 | Hassane, Hossam Magdi Abdelhamid | 2026-01-28 | 2026-01-27 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46049 | -46049
105-154 | 380kV OHTL SAMHA BSP #9105 | 8802 | Supply of Steel Rebars | IN PROCESS | No | 2026-01-27 | Hassane, Hossam Magdi Abdelhamid | 2026-01-28 | 2026-01-27 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46049 | -46049
105-154 | 380kV OHTL SAMHA BSP #9105 | 8804 | Auguring Works | IN PROCESS | No | 2026-01-27 | Hassane, Hossam Magdi Abdelhamid | 2026-01-28 | 2026-01-27 |  |  |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46049 | -46049
10522300004 | PSS - ISP Maintenance NTT-136 | 3 | PSS - NTT136 - Passive | RETURNED | No | 2021-07-06 | Babic, Marian | 2024-04-15 | 2021-07-14 | 2024-04-15 |  | not required | 264450 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44391 | -44391
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 4 | JEC S/S | APPROVED | No | 2021-07-07 | Abas, Mohammed Fekry | 2021-08-10 | 2021-08-11 | 2021-08-08 |  | The PO value is more than requisition price. Please change the value in PR to be same or more than invoice value. | 6150 | 3770 | 0 | STANDARD | SGS GULF LIMITED | USD | 4942.5 | APPROVED |  |  | 2021-08-15 | 1207.5 | 4 | Babic, Marian | -44419 | 4
10521300005 | Modon (TD-0034/HV-1294) | 6 | ACSR Conductor | RETURNED | No | 2021-07-08 | Babic, Marian | 2021-12-29 | 2021-08-17 |  |  |  | 10000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44425 | -44425
10522100006 | MOI Diwan Project | 7 | MOI-Diwan - NTT256 - Qlik | APPROVED | No | 2021-07-13 | Abas, Mohammed Fekry | 2021-08-03 | 2021-08-08 |  |  |  | 451237.5 | 3762 | 0 | STANDARD | Qliktech International Markets AB | USD | 451237.5 | APPROVED |  |  | 2021-09-13 | 0 | 36 | Abuhammad, Samir | -44416 | 36
10522309999 | Infrastructure and Security Projects - Job Orders | 8 | NGHA-Qassim project | APPROVED | No | 2021-07-18 | Abas, Mohammed Fekry | 2021-08-02 | 2021-08-03 |  | 2021-07-27 |  | 54720 | 3752 | 0 | STANDARD | MULTINET COMMUNICATION FZE | SAR | 54720 | APPROVED |  |  | 2021-08-11 | 0 | 8 | Abuhammad, Samir | -44411 | 8
10522309999 | Infrastructure and Security Projects - Job Orders | 9 | NGHA-Qassim Project | RETURNED | No | 2021-07-18 | Abuhammad, Samir | 2022-10-03 | 2022-09-25 |  | 2021-07-27 |  | 210000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44829 | -44829
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 10 | SADAIA - Cloudera | APPROVED | No | 2021-07-25 | Abas, Mohammed Fekry | 2021-07-26 | 2021-07-26 |  | 2021-07-25 |  | 262500 | 3750 | 0 | STANDARD | Cloudera Inc. | USD | 262500 | APPROVED |  |  | 2021-07-29 | 0 | 3 | Abuhammad, Samir | -44403 | 3
10521100008 | King Fahad National Centre for Children's Cancer (ES-0023) | 11 | chillers Mainteance KFNCCC | APPROVED | No | 2021-07-28 | Abas, Mohammed Fekry | 2021-08-01 | 2021-08-01 |  |  |  | 449000 | 3751 | 0 | STANDARD | DAIKIN AIR CONDITIONING SAUDI ARABIA | SAR | 449000 | APPROVED |  |  | 2021-08-05 | 0 | 4 | Abuhammad, Samir | -44409 | 4
10521100008 | King Fahad National Centre for Children's Cancer (ES-0023) | 12 | CPM VAV VFD Maintenance | RETURNED | No | 2021-07-28 | Abuhammad, Samir | 2021-11-02 | 2021-08-01 | 2021-11-02 |  | Due to change the duration of maintenance | 496500 | 3755 | 0 | STANDARD | ARABIAN AIR CONDITIONING COMPANY LTD | SAR | 496500 | APPROVED |  |  | 2021-08-11 | 0 |  | Abuhammad, Samir | -44409 | 10
10521100008 | King Fahad National Centre for Children's Cancer (ES-0023) | 12 | CPM VAV VFD Maintenance | RETURNED | No | 2021-07-28 | Abuhammad, Samir | 2021-11-02 | 2021-08-01 | 2021-11-02 |  | Due to change the duration of maintenance | 496500 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44409 | -44409
10521300006 | Arafat 3 S/S (TD-0037) | 13 | MV Indoor 24KV Termination kit | REJECTED | No | 2021-07-28 | Al-Asmi, Ibrahim Abdulkhaliq | 2021-07-28 |  |  | 2021-07-28 |  | 1350 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10521100008 | King Fahad National Centre for Children's Cancer (ES-0023) | 14 |  | APPROVED | No | 2021-07-29 | Abas, Mohammed Fekry | 2021-08-08 | 2021-08-08 | 2021-08-05 | 2021-07-29 | Pls exlude VAT in PR cost Lines | 60000 | 3756 | 0 | STANDARD | AL HASSAN GHAZI IBRAHIM SHAKER COMPANY | SAR | 60000 | APPROVED |  |  | 2021-08-24 | 0 | 16 | Abuhammad, Samir | -44416 | 16
10521300006 | Arafat 3 S/S (TD-0037) | 15 | MV Termination kit | APPROVED | No | 2021-07-29 | Abas, Mohammed Fekry | 2021-08-22 | 2021-08-24 | 2021-08-11 |  | The value is less than PO value (should be 1940 SAR total) | 1940 | 3780 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 1940 | APPROVED |  |  | 2021-09-01 | 0 | 8 | Babic, Marian | -44432 | 8
10521300006 | Arafat 3 S/S (TD-0037) | 16 | MV cable Clamps | APPROVED | No | 2021-07-29 | Al-Asmi, Ibrahim Abdulkhaliq | 2021-08-08 | 2021-08-11 |  |  |  | 24600 | 3768 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 24600 | APPROVED |  |  | 2021-08-18 | 0 | 7 | Abuhammad, Samir | -44419 | 7
10521300006 | Arafat 3 S/S (TD-0037) | 17 | 185mmsq bare copper conductor | APPROVED | No | 2021-07-29 | Abas, Mohammed Fekry | 2021-08-12 | 2021-08-12 |  |  |  | 55142 | 3771 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 55142 | APPROVED |  |  | 2021-09-25 | 0 | 44 | Babic, Marian | -44420 | 44
10522309999 | Infrastructure and Security Projects - Job Orders | 18 | MEP/1167/Add-09/2021 | APPROVED | No | 2021-07-29 | Abas, Mohammed Fekry | 2021-08-08 | 2021-08-09 |  |  |  | 54575.38 | 3760 | 0 | STANDARD | MULTINET COMMUNICATION FZE | SAR | 54575.38 | APPROVED |  |  | 2021-09-06 | 0 | 28 | Abuhammad, Samir | -44417 | 28
10529140005 | Sarfi Underground Cable (TD-0033) | 19 |  | REJECTED | No | 2021-07-29 | Ilyas, Mohammed | 2023-01-16 | 2021-08-12 |  | 2021-08-03 |  | 35353 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44420 | -44420
10521300003 | Al-Shalal S/S (TD-0028/HV-1222) | 28 | Replacement of batteries and battery charger | APPROVED | No | 2021-08-04 | Azam, Mohammed | 2021-08-08 | 2021-08-08 |  | 2021-08-04 |  | 1268870 | 3757 | 0 | STANDARD | Sela for Power, Automation & Safety Systems Co | EUR | 1268870 | APPROVED |  |  | 2021-08-11 | 0 | 3 | Babic, Marian | -44416 | 3
10521300003 | Al-Shalal S/S (TD-0028/HV-1222) | 29 | HVAC Repair work | APPROVED | No | 2021-08-04 | Abas, Mohammed Fekry | 2021-08-08 | 2021-08-09 |  | 2021-08-04 |  | 93750 | 3759 | 0 | STANDARD | HEXAGON Contracting Company | SAR | 93750 | APPROVED |  |  | 2021-08-16 | 0 | 7 | Babic, Marian | -44417 | 7
10521100003 | Streetlights Jeddah (ES-0015/ESCO) | 30 | LED PR | INCOMPLETE | No | [7 empty] | 141000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10521300003 | Al-Shalal S/S (TD-0028/HV-1222) | 33 | Capacitor Bank testing for replace capacitor units | APPROVED | No | 2021-08-09 | Abas, Mohammed Fekry | 2021-08-10 | 2021-08-11 |  | 2021-08-09 |  | 16000 | 3775 | 0 | STANDARD | YASIR M ALI AL-ZAHRANI EST. | SAR | 15000 | APPROVED |  |  | 2021-08-24 | 1000 | 13 | Babic, Marian | -44419 | 13
10521200003 | Fixed Network Rollout - NEOM | 34 |  | REJECTED | No | 2021-08-11 | AlShehri, Ali | 2021-08-11 |  |  | 2021-08-11 |  | 135000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10521100010 | Eastern Province - EP3 | 35 | Replacemnet of old luminaries and installation of new LEDs with its protection devices and LUX measurmnets for Dammam and Khobar Project (EP3)-Decorative | REJECTED | No | 2021-08-10 | Ashkan, Ashwag | 2021-10-07 | 2021-08-12 |  | 2021-10-10 |  | 198199 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44420 | -44420
10521300006 | Arafat 3 S/S (TD-0037) | 38 | Media Converter Testing | REJECTED | No | 2021-08-11 | Ilyas, Mohammed | 2023-01-16 | 2021-08-15 |  |  |  | 127480 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44423 | -44423
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 39 | Synopsys-licenses | APPROVED | No | 2021-08-11 | Abas, Mohammed Fekry | 2021-08-12 | 2021-08-12 |  |  |  | 392700 | 3842 | 0 | STANDARD | SYNOPSYS INTERNATIONAL LIMITED | USD | 392700 | APPROVED |  |  | 2021-10-28 | 0 | 77 | Abuhammad, Samir | -44420 | 77
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 42 | Hardware | RETURNED | No | 2021-08-12 | Abuhammad, Samir | 2021-11-02 | 2021-09-27 |  |  |  | 231963 | 3776 | 0 | STANDARD | APTEC Saudi Arabia LCC | SAR | 234945 | APPROVED |  |  | 2021-08-24 | -2982 |  | Abuhammad, Samir | -44466 | -34
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 42 | Hardware | RETURNED | No | 2021-08-12 | Abuhammad, Samir | 2021-11-02 | 2021-09-27 |  |  |  | 231963 | 3817 | 0 | STANDARD | APTEC Saudi Arabia LCC | SAR | 231963 | APPROVED |  |  | 2021-10-18 | 0 |  | Abuhammad, Samir | -44466 | 21
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 42 | Hardware | RETURNED | No | 2021-08-12 | Abuhammad, Samir | 2021-11-02 | 2021-09-27 |  |  |  | 13780 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44466 | -44466
10521300003 | Al-Shalal S/S (TD-0028/HV-1222) | 43 | DC Flexible Cable | APPROVED | No | 2021-08-12 | Abas, Mohammed Fekry | 2021-08-22 | 2021-08-22 |  |  |  | 51600 | 3778 | 0 | STANDARD | AFKAR AL ALFIYA EST | SAR | 46000 | APPROVED |  |  | 2021-09-06 | 5600 | 15 | Babic, Marian | -44430 | 15
10521300004 | Al-Quwaiza S/S (TD-0029/HV-1222) | 44 | GIS Earthing Bar | RETURNED | No | 2021-08-12 | Babic, Marian | 2024-04-15 | 2021-08-16 | 2024-04-15 |  | not required, PO 3779 issued long time ago | 10308.75 | 3779 | 0 | STANDARD | LSIS CO.LTD. | USD | 10308.75 | APPROVED |  |  | 2021-09-06 | 0 |  | Babic, Marian | -44424 | 21
10521300004 | Al-Quwaiza S/S (TD-0029/HV-1222) | 44 | GIS Earthing Bar | RETURNED | No | 2021-08-12 | Babic, Marian | 2024-04-15 | 2021-08-16 | 2024-04-15 |  | not required, PO 3779 issued long time ago | 42191.25 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44424 | -44424
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 45 | Supply of Y-G Cables | REJECTED | No | 2021-08-12 | Chughtai, Sameer | 2021-10-06 | 2021-08-24 |  |  |  | 205660 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44432 | -44432
10521300010 | Rehabilitation of NAF SS (TD-0040) | 46 | NAF | APPROVED | No | 2021-08-15 | Abas, Mohammed Fekry | 2021-09-22 | 2021-09-26 |  |  |  | 1775632.5 | 3811 | 0 | STANDARD | Koncar - Switchgear Inc. | EUR | 1661497.27 | APPROVED |  |  | 2021-10-18 | 114135.23 | 22 | Babic, Marian | -44465 | 22
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 48 | TPI for protection panels FAT | APPROVED | No | 2021-08-16 | Abas, Mohammed Fekry | 2021-08-25 | 2021-08-26 |  | 2021-08-22 |  | 13800 | 3781 | 0 | STANDARD | SGS INSPECTION SERVICES SA. LTD | SAR | 13800 | APPROVED |  |  | 2021-09-06 | 0 | 11 | Babic, Marian | -44434 | 11
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 49 | JEC S/S:TPI for protection panrls FAT | REJECTED | No | 2021-08-15 | Ashkan, Ashwag | 2021-08-17 | 2021-08-16 |  | 2021-08-18 |  | 13800 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44424 | -44424
10521300005 | Modon (TD-0034/HV-1294) | 50 | Security System Consumable Materials | APPROVED | No | 2021-08-16 | Abas, Mohammed Fekry | 2021-08-16 | 2021-08-17 |  |  |  | 46366.42 | 3790 | 0 | STANDARD | Asari Operation and Maintenance | SAR | 45399.5 | APPROVED |  |  | 2021-09-25 | 966.92 | 39 | Abuhammad, Samir | -44425 | 39
10529220024 | STC Pay - Micro Focus Implementation Project for STC Pay | 51 | ITSM Implementation - STCPay | APPROVED | No | 2021-08-16 | Abas, Mohammed Fekry | 2021-08-25 | 2021-08-26 |  | 2021-08-16 |  | 140000 | 3782 | 0 | STANDARD | Al Sakhrai Al Hadeth Est | SAR | 140000 | APPROVED |  |  | 2021-09-08 | 0 | 13 | Abuhammad, Samir | -44434 | 13
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 52 | Rabigh Exp. - Over Head Crane | IN PROCESS | No | 2021-08-17 | Abduraouf, Ahmad | 2021-10-31 | 2021-10-29 |  | 2021-09-20 |  | 150000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44498 | -44498
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 53 | Rabigh Exp. - FireFighting | APPROVED | No | 2021-08-17 | Abas, Mohammed Fekry | 2021-09-02 | 2021-09-02 |  | 2021-08-22 |  | 588000 | 3812 | 0 | STANDARD | Reda Trading & Development Co. for Machinery & Equipment Ltd(S) | SAR | 221000 | APPROVED |  |  | 2021-10-07 | 367000 | 35 | Babic, Marian | -44441 | 35
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 54 | Rabigh Exp. HVAC | IN PROCESS | No | 2021-08-17 | Abduraouf, Ahmad | 2021-10-31 | 2021-10-29 | 2021-10-25 | 2021-08-22 | Budget is revised | 800000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44498 | -44498
10521300007 | Bahrain, 66kV Substations (TD-0038/MV-1282) | 55 |  | INCOMPLETE | No | [6 empty] | Budget is revised | 5000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 56 | APSSM | APPROVED | No | 2021-08-17 | Abas, Mohammed Fekry | 2021-08-18 | 2021-08-18 |  | 2021-08-17 |  | 1701612.64 | 3815 | 0 | STANDARD | APTEC Saudi Arabia LCC | SAR | 1693118.6 | APPROVED |  |  | 2021-10-18 | 8494.04 | 61 | Abuhammad, Samir | -44426 | 61
| ORA-01403: no data found | 57 | NEOM HCIE Training | APPROVED | No | 2021-08-17 | Abas, Mohammed Fekry | 2021-08-18 | 2021-08-18 |  | 2021-08-17 |  | 46875 | 3774 | 0 | STANDARD | Corvit Networks Private Limited | USD | 46875 | APPROVED |  |  | 2021-08-18 | 0 | 0 | Babic, Marian | -44426 | 0
10521300010 | Rehabilitation of NAF SS (TD-0040) | 59 | Tinned Copper conductor | APPROVED | No | 2021-08-17 | Abas, Mohammed Fekry | 2021-08-23 | 2021-08-24 |  | 2021-08-17 |  | 18600 | 3800 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 17869.17 | APPROVED |  |  | 2021-10-07 | 730.83 | 44 | Alamri, Nedhal | -44432 | 44
10521300010 | Rehabilitation of NAF SS (TD-0040) | 60 | AC,DC, Lighting Panels | APPROVED | No | 2021-08-17 | Abas, Mohammed Fekry | 2021-10-26 | 2021-10-26 | 2021-10-21 |  | As discussed yesterday please revise and make memo for CEO | 552000 | 3831 | 0 | STANDARD | ETA-PCS SWITCHGEAR MANUFACTRING LLC | SAR | 550000.02 | APPROVED |  |  | 2021-11-03 | 1999.98 | 8 | Babic, Marian | -44495 | 8
10521300006 | Arafat 3 S/S (TD-0037) | 61 | HV Cable PD test | INCOMPLETE | No | [6 empty] | As discussed yesterday please revise and make memo for CEO | 40000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 64 | NER TPI | APPROVED | No | 2021-08-23 | Abas, Mohammed Fekry | 2021-09-14 | 2021-09-15 |  | 2021-08-25 |  | 6000 | 3796 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | USD | 5025 | APPROVED |  |  | 2021-09-25 | 975 | 10 | Babic, Marian | -44454 | 10
10522300004 | PSS - ISP Maintenance NTT-136 | 65 | PSS - NTT-136 -Penetration test | APPROVED | No | 2021-08-23 | Abas, Mohammed Fekry | 2021-09-05 | 2021-09-05 |  |  |  | 180000 | 3787 | 0 | STANDARD | Infratech Co for Communications & IT | SAR | 180000 | APPROVED |  |  | 2021-09-30 | 0 | 25 | Abuhammad, Samir | -44444 | 25
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 66 | TPI for Capacitor Bank ( Capictor Portion) | APPROVED | No | 2021-08-23 | Abas, Mohammed Fekry | 2021-09-13 | 2021-09-14 |  |  |  | 15000 | 3799 | 0 | STANDARD | SGS GULF LIMITED | USD | 15000 | APPROVED |  |  | 2021-09-29 | 0 | 15 | Babic, Marian | -44453 | 15
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 67 | ewq | INCOMPLETE | No | [7 empty] | 10000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10521200003 | Fixed Network Rollout - NEOM | 68 | CS-141 | RETURNED | No | 2021-08-26 | Abuhammad, Samir | 2022-10-17 | 2021-08-31 | 2022-10-17 |  | Due to change spacification. | 27923.2 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44439 | -44439
10511000004 | Energy & Communication Operation Overhead | 73 | GE Light | APPROVED | No | 2021-09-02 | Abas, Mohammed Fekry | 2021-09-07 | 2021-09-07 |  |  |  | 34801.5 | 3789 | 0 | STANDARD | Said For Electrical Materials | SAR | 34801.5 | APPROVED |  |  | 2021-09-29 | 0 | 22 | Babic, Marian | -44446 | 22
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 74 | Instalation | APPROVED | No | 2021-09-02 | Abas, Mohammed Fekry | 2021-09-05 | 2021-09-05 |  |  |  | 1700000 | 3813 | 0 | STANDARD | MASEERAT AL NAMA CONT.EST. | SAR | 1450000 | APPROVED |  |  | 2021-10-12 | 250000 | 37 | Babic, Marian | -44444 | 37
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 74 | Instalation | APPROVED | No | 2021-09-02 | Abas, Mohammed Fekry | 2021-09-05 | 2021-09-05 |  |  |  | 1700000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44444 | -44444
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 75 | Oil Filtration | APPROVED | No | 2021-09-05 | Abas, Mohammed Fekry | 2021-09-14 | 2021-09-15 |  | 2021-09-09 |  | 60000 | 3814 | 0 | STANDARD | MAMDOH BAKHET AL HARBI EST | SAR | 50000 | APPROVED |  |  | 2021-10-07 | 10000 | 22 | Alamri, Nedhal | -44454 | 22
10521300006 | Arafat 3 S/S (TD-0037) | 76 | Underground HV Cable PD & sheath fault/repair | APPROVED | No | 2021-09-05 | Abas, Mohammed Fekry | 2021-10-19 | 2021-10-20 |  | 2021-09-20 |  | 46000 | 3841 | 0 | STANDARD | CIVIL ELECT.PROJECTS CONTG.CO | SAR | 46000 | APPROVED |  |  | 2021-10-31 | 0 | 11 | Babic, Marian | -44489 | 11
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 77 | JEC SS | APPROVED | No | 2021-09-05 | Abas, Mohammed Fekry | 2021-09-20 | 2021-09-21 | 2021-09-14 |  | Please for unit price put the complete budget value, this price is not realistic | 1100000 | 3824 | 0 | STANDARD | National Excellence For Constrution & Energy co. | SAR | 1100000 | APPROVED |  |  | 2021-10-21 | 0 | 30 | Babic, Marian | -44460 | 30
| ORA-01403: no data found | 78 | Nesma Telecom Braning Propopsal - 9SS CREATIVE Design Proposal | APPROVED | No | 2021-09-05 | Abas, Mohammed Fekry | 2021-09-06 | 2021-09-06 |  |  |  | 78680 | 3788 | 0 | STANDARD | 9SS Creative | SAR | 78680 | APPROVED |  |  | 2021-09-14 | 0 | 8 | Babic, Marian | -44445 | 8
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 79 | Lighting System | APPROVED | No | 2021-09-06 | Abas, Mohammed Fekry | 2021-10-10 | 2021-10-10 |  |  |  | 126896 | 3818 | 0 | STANDARD | SAUDI LIGHTING CO LTD | SAR | 126896 | APPROVED |  |  | 2021-10-18 | 0 | 8 | Babic, Marian | -44479 | 8
10521300005 | Modon (TD-0034/HV-1294) | 81 | HV Test | APPROVED | No | 2021-09-07 | Abas, Mohammed Fekry | 2021-10-25 | 2021-10-26 |  |  |  | 47500 | 3845 | 0 | STANDARD | GCC Electrical Testing Laboratory Co | SAR | 47500 | APPROVED |  |  | 2021-10-31 | 0 | 5 | Babic, Marian | -44495 | 5
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 85 | Neo4j | APPROVED | No | 2021-09-13 | Abas, Mohammed Fekry | 2021-09-15 | 2021-09-16 |  | 2021-09-13 |  | 622500 | 3821 | 0 | STANDARD | Neo4j Sweden AB | USD | 622500 | APPROVED |  |  | 2021-10-18 | 0 | 32 | Abuhammad, Samir | -44455 | 32
10521300010 | Rehabilitation of NAF SS (TD-0040) | 86 | Y/G Grounding Cable | RETURNED | No | 2021-09-13 | Babic, Marian | 2025-11-12 | 2021-09-15 | 2025-11-12 |  | not required | 33660 | 3800 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 32246.96 | APPROVED |  |  | 2021-10-07 | 1413.04 |  | Alamri, Nedhal | -44454 | 22
10521300010 | Rehabilitation of NAF SS (TD-0040) | 86 | Y/G Grounding Cable | RETURNED | No | 2021-09-13 | Babic, Marian | 2025-11-12 | 2021-09-15 | 2025-11-12 |  | not required | 2800 | [5 empty] | 0 |  |  |  |  | 0 |  | Alamri, Nedhal | -44454 | -44454
10521100015 | Emarat Al Madinah | 87 | Inverter Type Ac units replacement ( including Civil work) | APPROVED | No | 2021-09-13 | Abas, Mohammed Fekry | 2021-09-15 | 2021-09-15 |  |  |  | 14000 | 3832 | 0 | STANDARD | EXPERIENCE&EXCELLENCE FOR CONTRACTING | SAR | 14000 | APPROVED |  |  | 2021-12-09 | 0 | 85 | Abuhammad, Samir | -44454 | 85
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 88 | Outdoor Lighting Panel | RETURNED | No | 2021-09-13 | Babic, Marian | 2023-06-07 | 2021-09-26 | 2023-06-07 | 2021-09-13 | Not required | 17000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44465 | -44465
10521300010 | Rehabilitation of NAF SS (TD-0040) | 89 | HV,MV,LV Cables | REJECTED | No | 2021-09-13 | Almehmadi, Fahed | 2022-12-13 | 2021-10-10 |  |  | Noted and same shall be considered by procurement team during PO issuance. | 1888064.62 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44479 | -44479
| ORA-01403: no data found | 90 | Power Metres stock | APPROVED | No | 2021-09-13 | Abas, Mohammed Fekry | 2021-09-20 | 2021-09-21 |  |  |  | 90500 | 3805 | 0 | STANDARD | Washa Al Wisam Factory Company | SAR | 90500 | APPROVED |  |  | 2021-10-07 | 0 | 16 | Abuhammad, Samir | -44460 | 16
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 91 | JEC SS - Trafo Offloading | APPROVED | No | 2021-09-14 | Abas, Mohammed Fekry | 2021-10-25 | 2021-10-25 | 2021-10-21 |  | As discussed please resubmit with correct Line/Source | 50000 | 3822 | 0 | STANDARD | HAYTHAM SAEED AL-GHAMDI EST. | SAR | 42000 | APPROVED |  |  | 2021-10-27 | 8000 | 2 | Babic, Marian | -44494 | 2
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 94 | JEC SS - Lightining Mast | APPROVED | No | 2021-09-21 | Abas, Mohammed Fekry | 2021-09-26 | 2021-09-26 |  | 2021-09-21 |  | 81200 | 3809 | 0 | STANDARD | Al-Babtain Power & Telecom | SAR | 81200 | APPROVED |  |  | 2021-10-07 | 0 | 11 | Babic, Marian | -44465 | 11
| ORA-01403: no data found | 95 | To do the civil, mechanical and electricl work for Nesm new office | APPROVED | No | 2021-09-14 | Abas, Mohammed Fekry | 2021-09-15 | 2021-09-15 |  |  | Kindly note that there are an advance payment which represent 5% of the total amount that must be paid once the contract is signed. Also there is 10% that must be paid after 7 days of signing the contract regardless of the work progress as per the contract. | 3150000 | 3797 | 0 | STANDARD | Construction Formation | SAR | 2324720.14 | APPROVED |  |  | 2021-09-20 | 825279.86 | 5 | Babic, Marian | -44454 | 5
10521200006 | Overhead Gantry with Data Sensors- NEOM | 96 | Neom Overhead Gantry Project | APPROVED | No | 2021-09-15 | Abas, Mohammed Fekry | 2021-09-20 | 2021-09-21 |  |  |  | 15000 | 3810 | 0 | STANDARD | Asaar Engineering Consult | SAR | 15000 | APPROVED |  |  | 2021-10-11 | 0 | 20 | Abuhammad, Samir | -44460 | 20
10521300006 | Arafat 3 S/S (TD-0037) | 97 | Arafat-3- Supply of HV Cable Clamps ,Steel supports and Installation/mobilization | APPROVED | No | 2021-09-15 | Abas, Mohammed Fekry | 2021-10-19 | 2021-10-19 |  | 2021-09-26 |  | 60000 | 3838 | 0 | STANDARD | CIVIL ELECT.PROJECTS CONTG.CO | SAR | 60000 | APPROVED |  |  | 2021-10-28 | 0 | 9 | Babic, Marian | -44488 | 9
10521300006 | Arafat 3 S/S (TD-0037) | 98 | Arafat-3 - Supply of Manpower | APPROVED | No | 2021-09-15 | Abas, Mohammed Fekry | 2021-10-19 | 2021-10-19 |  | 2021-09-21 |  | 36120 | 3840 | 0 | STANDARD | Hail Towers For Electrical And Mechanical Contracting | SAR | 36120 | APPROVED |  |  | 2021-10-28 | 0 | 9 | Babic, Marian | -44488 | 9
| ORA-01403: no data found | 99 | To provide professional Supervision Services at Nesma New office | APPROVED | No | 2021-09-15 | Abas, Mohammed Fekry | 2021-09-15 | 2021-09-16 |  |  |  | 80000 | 3798 | 0 | STANDARD | Grid For Trading-Gridesing | SAR | 36000 | APPROVED |  |  | 2021-10-10 | 44000 | 24 | Abuhammad, Samir | -44455 | 24
10531109999 | Trading - Job Orders | 100 | Supply of Insulators 2500A; 17.5kV for Muhammadia SS | APPROVED | No | 2021-09-16 | Abas, Mohammed Fekry | 2021-09-21 | 2021-09-21 |  |  |  | 7421.52 | 3803 | 0 | STANDARD | KONCAR ELECTRICAL EQUIPMENT INC. | EUR | 7421.4 | APPROVED |  |  | 2021-10-06 | 0.12 | 15 | Babic, Marian | -44460 | 15
10529140006 | Jeddah Sea Port (TD-0010/HV-1139) | 102 | Sea - Port SS | APPROVED | No | 2021-09-19 | Abas, Mohammed Fekry | 2021-09-21 | 2021-09-21 |  | 2021-09-19 |  | 325000 | 3804 | 0 | STANDARD | Zone Advertising for Contracting | SAR | 325000 | APPROVED |  |  | 2021-10-10 | 0 | 19 | Babic, Marian | -44460 | 19
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 103 | JEC S/S : TPI for NCT NPT | INCOMPLETE | No | [7 empty] | 10000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10522100006 | MOI Diwan Project | 104 | Moi- Diwan | RETURNED | No | 2021-09-22 | Abuhammad, Samir | 2021-10-03 | 2021-09-26 | 2021-10-03 |  | Technical specification not clear, also we need to share the offers that you used to build the budget as mentioned items unit price. | 1051868.96 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44465 | -44465
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 106 | JEC SS HV-1302 | APPROVED | No | 2021-09-26 | Abas, Mohammed Fekry | 2021-10-03 | 2021-10-03 |  |  |  | 25000 | 3816 | 0 | STANDARD | SGS GULF LIMITED | USD | 15000 | APPROVED |  |  | 2021-10-07 | 10000 | 4 | Babic, Marian | -44472 | 4
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 108 | JEC SS - Termination Kit | APPROVED | No | 2021-09-28 | Abas, Mohammed Fekry | 2021-10-21 | 2021-10-21 |  |  |  | 55880 | 3855 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 55880 | APPROVED |  |  | 2021-11-14 | 0 | 24 | Alamri, Nedhal | -44490 | 24
10529110001 | Dammam Port (DSP-0038) | 109 | Dammam Seaport - SCADA Building furniture | RETURNED | No | 2021-09-28 | Abuhammad, Samir | 2021-12-29 | 2021-10-03 | 2021-12-29 |  | Due to non respond from the project not provied the selection brande since one month ago please resubmit once you are ready | 74800 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44472 | -44472
10529110001 | Dammam Port (DSP-0038) | 110 | Dammam SeaPort-Additional Civil Contractor | APPROVED | No | 2021-10-04 | Abas, Mohammed Fekry | 2021-10-11 | 2021-10-12 |  | 2021-10-07 |  | 2000000 | 3835 | 0 | STANDARD | ALI HAMOUD AL OUFI GEN.CONT.EST. | SAR | 1900000 | APPROVED |  |  | 2021-10-28 | 100000 | 16 | Abuhammad, Samir | -44481 | 16
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 111 | 110KV Rabigh Extension - Civil Scope | IN PROCESS | No | 2021-10-03 | Aminudin, Waleed | 2021-10-25 | 2021-10-12 | 2021-10-25 | 2021-10-05 | The budget is revised | 2200000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44481 | -44481
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 112 | Google Workspace Applications | APPROVED | No | 2021-10-04 | Abas, Mohammed Fekry | 2021-10-05 | 2021-10-05 |  |  |  | 32400 | 3823 | 0 | STANDARD | Invent Solutions | SAR | 32400 | APPROVED |  |  | 2021-10-14 | 0 | 9 | Abuhammad, Samir | -44474 | 9
10529220021 | PSS_PO#6635 | 113 | OutSystem training | APPROVED | No | 2021-10-03 | Abas, Mohammed Fekry | 2021-10-05 | 2021-10-05 |  |  |  | 119452.5 | 3848 | 0 | STANDARD | OUTSYSTEMS-SOFTWARE EM RENE S.A. | USD | 119452.5 | APPROVED |  |  | 2021-11-02 | 0 | 28 | Abuhammad, Samir | -44474 | 28
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 115 | 110KV Rabigh Extension-Earthing Materials | IN PROCESS | No | 2021-10-25 | Aminudin, Waleed | 2021-10-25 |  |  |  |  | 115336.5 | [5 empty] | 0 |  |  |  |  | 0 |  | Alamri, Nedhal | 0 | 0
10529110001 | Dammam Port (DSP-0038) | 116 | Dammam SeaPort- Electrical MV Network | APPROVED | No | 2021-10-06 | Abas, Mohammed Fekry | 2021-10-11 | 2021-10-12 |  | 2021-10-07 |  | 800000 | 3834 | 0 | STANDARD | Energy Waves Co. For Contracting Limited | SAR | 775000 | APPROVED |  |  | 2021-10-21 | 25000 | 9 | Abuhammad, Samir | -44481 | 9
10529110001 | Dammam Port (DSP-0038) | 117 | Dammam Sea Port- HVAC Subcon for SCADA Building | REJECTED | No | 2021-10-06 | Al-Asmi, Ibrahim Abdulkhaliq | 2021-10-07 | 2021-10-06 |  | 2021-10-07 |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44475 | -44475
10521100008 | King Fahad National Centre for Children's Cancer (ES-0023) | 118 | BMS Maintenance - KFNCCC | REJECTED | No | 2021-10-07 | Chughtai, Sameer | 2021-10-07 | 2021-10-07 |  | 2021-10-07 |  | 220500 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -44476 | -44476
10521100008 | King Fahad National Centre for Children's Cancer (ES-0023) | 120 | BMS Maintenance - KFNCCC | REJECTED | No | 2021-10-10 | El Bouz, Baher | 2021-10-10 |  |  | 2021-10-10 |  | 220500 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10521100008 | King Fahad National Centre for Children's Cancer (ES-0023) | 121 | BMS Maintenance - KFNCCC | REJECTED | No | 2021-10-10 | El Bouz, Baher | 2022-03-06 | 2021-11-28 |  | 2022-03-06 |  | 220500 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -44528 | -44528
10521100008 | King Fahad National Centre for Children's Cancer (ES-0023) | 122 | BMS Maintenance - KFNCCC | APPROVED | No | 2021-10-10 | Abas, Mohammed Fekry | 2021-10-12 | 2021-10-12 |  |  |  | 220500 | 3850 | 0 | STANDARD | ARABIAN AIR CONDITIONING COMPANY LTD | SAR | 220500 | APPROVED |  |  | 2021-11-14 | 0 | 33 | Abuhammad, Samir | -44481 | 33
10529110001 | Dammam Port (DSP-0038) | 123 | Dammam Seaport- SCADA Building HVAC Contractor | APPROVED | No | 2021-10-10 | Abas, Mohammed Fekry | 2021-10-11 | 2021-10-12 |  |  |  | 444000 | 3837 | 0 | STANDARD | HEXAGON Contracting Company | SAR | 380000 | APPROVED |  |  | 2021-10-29 | 64000 | 17 | Abuhammad, Samir | -44481 | 17
10521300010 | Rehabilitation of NAF SS (TD-0040) | 124 | NAF - HV1317 | APPROVED | No | 2021-10-10 | Abas, Mohammed Fekry | 2021-10-13 | 2021-10-13 |  |  |  | 4500 | 3827 | 0 | STANDARD | Atlas Support and Services | SAR | 4500 | APPROVED |  |  | 2021-10-24 | 0 | 11 | Alamri, Nedhal | -44482 | 11
10521300006 | Arafat 3 S/S (TD-0037) | 126 | Arafat-3 Supply of Substation furnitures & accessories | APPROVED | No | 2021-10-10 | Abas, Mohammed Fekry | 2021-10-11 | 2021-10-12 |  |  |  | 12280 | 3826 | 0 | STANDARD | DANAH AL RAYEDA ESTABLISHMENT | SAR | 12280 | APPROVED |  |  | 2021-10-18 | 0 | 6 | Babic, Marian | -44481 | 6
10529110001 | Dammam Port (DSP-0038) | 135 | Dammam Seaport- SCADA & Substations Civil finishing Works | APPROVED | No | 2021-10-12 | Abas, Mohammed Fekry | 2021-10-28 | 2021-10-28 |  |  |  | 740000 | 3849 | 0 | STANDARD | Itmam Construction Trading Co. | SAR | 736370 | APPROVED |  |  | 2021-11-03 | 3630 | 6 | Abuhammad, Samir | -44497 | 6
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 141 | JEC SS HV-1302 | APPROVED | No | 2021-10-14 | Abas, Mohammed Fekry | 2021-10-17 | 2021-10-17 |  |  |  | 5175 | 3843 | 0 | STANDARD | Atlas Support and Services | SAR | 4500 | APPROVED |  |  | 2021-10-28 | 675 | 11 | Alamri, Nedhal | -44486 | 11
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 151 | JEC SS HV-1302 | REJECTED | No | 2021-10-18 | Al Dahlawi, Feras Ridha | 2021-10-18 | 2021-10-18 |  |  |  | 40000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -44487 | -44487
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 152 | JEC SS HV-1302 | APPROVED | No | 2021-10-18 | Abas, Mohammed Fekry | 2021-10-31 | 2021-10-31 |  |  |  | 150000 | 3932 | 0 | STANDARD | YAHYA SALMAN ALGHAZWANI CONT.EST. | SAR | 106683 | APPROVED |  |  | 2022-01-13 | 43317 | 74 | Babic, Marian | -44500 | 74
10529110001 | Dammam Port (DSP-0038) | 153 | Dammam Sea port Additional Intercable connection Subcontractor | REJECTED | No | 2021-10-18 | Al-Asmi, Ibrahim Abdulkhaliq | 2021-10-18 | 2021-10-18 |  | 2021-10-18 |  | 550000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -44487 | -44487
10521300010 | Rehabilitation of NAF SS (TD-0040) | 154 | NAF - HV1317 | RETURNED | No | 2021-10-18 | Babic, Marian | 2024-04-15 | 2021-10-25 | 2024-04-15 |  | not required | 15888.56 | 3846 | 0 | STANDARD | Masuoka Manufacturing Co. Ltd. | USD | 15888.56 | APPROVED |  |  | 2021-11-02 | 0 |  | Babic, Marian | -44494 | 8
10521300010 | Rehabilitation of NAF SS (TD-0040) | 154 | NAF - HV1317 | RETURNED | No | 2021-10-18 | Babic, Marian | 2024-04-15 | 2021-10-25 | 2024-04-15 |  | not required | 15888.56 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44494 | -44494
10529140009 | Naga (TD-0013/HV-1164) | 155 | Iskan SS - DS | RETURNED | No | 2021-10-19 | Babic, Marian | 2021-12-29 | 2021-10-25 | 2021-12-29 | 2021-10-19 | Please resubmit after finalizing all tehnical points, as PR is pending for more than 2 months. | 60000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44494 | -44494
10529110001 | Dammam Port (DSP-0038) | 158 | Dammam SeaPort Interconnection Cables- Additional Contractor | APPROVED | No | 2021-10-19 | Abas, Mohammed Fekry | 2021-10-28 | 2021-10-28 | 2021-10-27 |  | Due to change the budget as per PM request | 300000 | 3847 | 0 | STANDARD | Energy Waves Co. For Contracting Limited | SAR | 299990 | APPROVED |  |  | 2021-11-03 | 10 | 6 | Abuhammad, Samir | -44497 | 6
10529110001 | Dammam Port (DSP-0038) | 159 | Dammam Seaport Project | APPROVED | No | 2021-10-20 | Abas, Mohammed Fekry | 2021-11-03 | 2021-11-07 |  |  |  | 220000 | 3856 | 0 | STANDARD | COMMUNICATIONS SOLUTIONS CO. | SAR | 185876 | APPROVED |  |  | 2021-11-16 | 34124 | 9 | Abuhammad, Samir | -44507 | 9
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 161 | JEC SS HV-1302 | REJECTED | No | 2021-10-21 | Ashkan, Ashwag | 2021-10-24 | 2021-10-24 |  | 2021-10-24 |  | 80000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -44493 | -44493
10521300010 | Rehabilitation of NAF SS (TD-0040) | 162 | NAF - HV1317 | APPROVED | No | 2021-10-24 | Abas, Mohammed Fekry | 2021-10-25 | 2021-10-26 |  |  |  | 92751 | 3911 | 0 | STANDARD | REZAYAT TRADING CO. LTD. | SAR | 91128.5 | APPROVED |  |  | 2021-12-16 | 1622.5 | 51 | Babic, Marian | -44495 | 51
10521300010 | Rehabilitation of NAF SS (TD-0040) | 164 | NAF - HV1317 | APPROVED | No | 2021-10-24 | Abas, Mohammed Fekry | 2021-10-27 | 2021-10-27 |  |  |  | 1700000 | 3935 | 0 | STANDARD | Zone Advertising for Contracting | SAR | 1485000 | APPROVED |  |  | 2022-01-26 | 215000 | 91 | Babic, Marian | -44496 | 91
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 165 | CISCO Cabling BOQ | APPROVED | No | 2021-11-03 | Abas, Mohammed Fekry | 2021-11-07 | 2021-11-07 |  |  |  | 65000 | 3862 | 0 | STANDARD | First Flags for Communications and Information Technology Est. | SAR | 65000 | APPROVED |  |  | 2021-11-21 | 0 | 14 | Abuhammad, Samir | -44507 | 14
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 165 | CISCO Cabling BOQ | APPROVED | No | 2021-11-03 | Abas, Mohammed Fekry | 2021-11-07 | 2021-11-07 |  |  |  | 248250 | 3863 | 0 | STANDARD | Hardware Solutions Builders Co Ltd | SAR | 174874 | APPROVED |  |  | 2021-11-21 | 73376 | 14 | Abuhammad, Samir | -44507 | 14
10522309999 | Infrastructure and Security Projects - Job Orders | 166 | SANG Hospitals-Riyadh Project | APPROVED | No | 2021-10-25 | Abas, Mohammed Fekry | 2021-10-31 | 2021-10-31 |  |  |  | 17500 | 3833 | 0 | STANDARD | ORIENTALS TECHNOLOGY EST. FOR CONTRACTING | SAR | 17500 | APPROVED |  |  | 2021-11-02 | 0 | 2 | Abuhammad, Samir | -44500 | 2
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 167 | JEC SS HV-1302 | REJECTED | No | 2021-10-25 | Awad, Belal | 2021-10-25 |  |  | 2021-10-25 |  | 40000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10521300010 | Rehabilitation of NAF SS (TD-0040) | 171 | NAF - HV1317 - SAS Furniture | REJECTED | No | 2021-10-27 | Almehmadi, Fahed | 2022-12-13 | 2021-10-29 |  |  |  | 45000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44498 | -44498
10529110001 | Dammam Port (DSP-0038) | 173 | AC Units Installation | APPROVED | No | 2021-10-27 | Abas, Mohammed Fekry | 2021-10-28 | 2021-10-28 |  |  |  | 106000 | 3861 | 0 | STANDARD | Itmam Construction Trading Co. | SAR | 99852 | APPROVED |  |  | 2021-11-23 | 6148 | 26 | Abuhammad, Samir | -44497 | 26
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 174 | JEC SS: HV 1302 | APPROVED | No | 2021-10-27 | Abas, Mohammed Fekry | 2021-11-02 | 2021-11-02 |  |  |  | 1850 | 3852 | 0 | STANDARD | Atlas Support and Services | SAR | 1850 | APPROVED |  |  | 2021-11-14 | 0 | 12 | Alamri, Nedhal | -44502 | 12
| ORA-01403: no data found | 176 | IMS Certification - ISO | APPROVED | No | 2021-11-02 | Abas, Mohammed Fekry | 2021-11-03 | 2021-11-07 |  |  |  | 92000 | 3857 | 0 | STANDARD | Knowledge Seekers Training Center | SAR | 89000 | APPROVED |  |  | 2021-11-16 | 3000 | 9 | Alamri, Nedhal | -44507 | 9
10522309999 | Infrastructure and Security Projects - Job Orders | 180 | NGHA-Qassim Project PO#S63E00695 | APPROVED | No | 2021-10-31 | Abas, Mohammed Fekry | 2021-11-17 | 2021-11-17 |  |  |  | 28298.25 | 3922 | 0 | STANDARD | Hardware Solutions Builders Co Ltd | SAR | 27616 | APPROVED |  |  | 2021-12-25 | 682.25 | 38 | Abuhammad, Samir | -44517 | 38
10521300005 | Modon (TD-0034/HV-1294) | 181 | PR for Security Camera's cable (outdoor) | RETURNED | No | 2021-11-03 | Babic, Marian | 2024-04-15 | 2021-11-23 | 2024-04-15 | 2021-11-17 | not required | 10400 | 3883 | 0 | STANDARD | Abdullah Jarallah Agencies Trading & Importing | SAR | 10400 | APPROVED |  |  | 2021-12-02 | 0 |  | Babic, Marian | -44523 | 9
10521300005 | Modon (TD-0034/HV-1294) | 181 | PR for Security Camera's cable (outdoor) | RETURNED | No | 2021-11-03 | Babic, Marian | 2024-04-15 | 2021-11-23 | 2024-04-15 | 2021-11-17 | not required | 10400 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -44523 | -44523
| ORA-01403: no data found | 182 | Maintanance | RETURNED | No | 2021-11-03 | Babic, Marian | 2021-12-23 | 2021-11-16 | 2021-12-23 |  | The amount is too small to be purchased through PO, please use petty cash. | 3550 | 3870 | 0 | STANDARD | Kayan Advanced System Trading Est | SAR | 3550 | APPROVED |  |  | 2022-01-05 | 0 |  | Abuhammad, Samir | -44516 | 50
| ORA-01403: no data found | 182 | Maintanance | RETURNED | No | 2021-11-03 | Babic, Marian | 2021-12-23 | 2021-11-16 | 2021-12-23 |  | The amount is too small to be purchased through PO, please use petty cash. | 750 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44516 | -44516
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 183 | JEC SS - 3rd party control cables | APPROVED | No | 2021-11-04 | Abas, Mohammed Fekry | 2021-11-07 | 2021-11-07 |  | 2021-11-04 |  | 5400 | 3859 | 0 | STANDARD | ARAB INSPECTION & Q.A.CO. | SAR | 2600 | APPROVED |  |  | 2021-11-18 | 2800 | 11 | Alamri, Nedhal | -44507 | 11
| ORA-01403: no data found | 184 | Office Supplies | APPROVED | No | 2021-11-04 | Abas, Mohammed Fekry | 2021-11-14 | 2021-11-16 |  |  |  | 5940 | 3870 | 0 | STANDARD | Kayan Advanced System Trading Est | SAR | 5940 | APPROVED |  |  | 2022-01-05 | 0 | 50 | Abuhammad, Samir | -44516 | 50
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 185 | JEC SS - TPI for 13.8kv SWGR | APPROVED | No | 2021-11-11 | Abas, Mohammed Fekry | 2021-11-15 | 2021-11-16 |  |  |  | 8000 | 3892 | 0 | STANDARD | Atlas Support and Services | SAR | 6400 | APPROVED |  |  | 2021-12-07 | 1600 | 21 | Babic, Marian | -44516 | 21
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 186 | JEC SS - TPI for Battery Charger | APPROVED | No | 2021-11-11 | Abas, Mohammed Fekry | 2021-11-23 | 2021-11-24 | 2021-11-22 |  | Please increase the value | 14000 | 3869 | 0 | STANDARD | SGS GULF LIMITED | USD | 12126 | APPROVED |  |  | 2021-12-01 | 1874 | 7 | Babic, Marian | -44524 | 7
10529110001 | Dammam Port (DSP-0038) | 188 | DPP Supply & Installation of Steel Glass frames & Hand Rails | APPROVED | No | 2021-11-13 | Abas, Mohammed Fekry | 2021-11-15 | 2021-11-16 |  |  |  | 100000 | 3894 | 0 | STANDARD | Al Bitar Factory Company | SAR | 74530 | APPROVED |  |  | 2021-12-17 | 25470 | 31 | Abuhammad, Samir | -44516 | 31
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 191 | JEC SS - TPI PACU | APPROVED | No | 2021-11-16 | Abas, Mohammed Fekry | 2021-11-17 | 2021-11-21 |  |  |  | 4000 | 3868 | 0 | STANDARD | ARAB INSPECTION & Q.A.CO. | SAR | 2800 | APPROVED |  |  | 2021-11-28 | 1200 | 7 | Babic, Marian | -44521 | 7
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 192 | JEC SS - TPI DDC | APPROVED | No | 2021-11-16 | Abas, Mohammed Fekry | 2021-11-17 | 2021-11-21 |  |  |  | 4000 | 3915 | 0 | STANDARD | ARAB INSPECTION & Q.A.CO. | SAR | 2800 | APPROVED |  |  | 2021-12-15 | 1200 | 24 | Babic, Marian | -44521 | 24
10521100001 | Streetlights Dammam (ES-0005/ESCO) | 242 | SPD | APPROVED | No | 2021-11-21 | Abas, Mohammed Fekry | 2021-11-22 | 2021-11-23 |  |  |  | 175000 | 3886 | 0 | STANDARD | Dehn Middle East Fze | USD | 143062.5 | APPROVED |  |  | 2021-12-16 | 31937.5 | 23 | Babic, Marian | -44523 | 23
10521100002 | Streetlights Khobar, Dhahran (ES-0007/ESCO) | 243 | SDP | APPROVED | No | 2021-11-21 | Abas, Mohammed Fekry | 2021-11-22 | 2021-11-23 |  |  |  | 75000 | 3887 | 0 | STANDARD | Dehn Middle East Fze | USD | 61312.5 | APPROVED |  |  | 2021-12-12 | 13687.5 | 19 | Babic, Marian | -44523 | 19
10521100003 | Streetlights Jeddah (ES-0015/ESCO) | 244 | SPD | APPROVED | No | 2021-11-21 | Abas, Mohammed Fekry | 2021-11-22 | 2021-11-23 |  |  |  | 51000 | 3888 | 0 | STANDARD | Dehn Middle East Fze | USD | 41692.5 | APPROVED |  |  | 2021-12-12 | 9307.5 | 19 | Babic, Marian | -44523 | 19
10521100004 | Streetlights Jeddah, Phase 2 (ES-0017/ESCO) | 245 | SPD | APPROVED | No | 2021-11-21 | Abas, Mohammed Fekry | 2021-11-22 | 2021-11-23 |  |  |  | 119000 | 3889 | 0 | STANDARD | Dehn Middle East Fze | USD | 97282.5 | APPROVED |  |  | 2021-12-12 | 21717.5 | 19 | Babic, Marian | -44523 | 19
10521100005 | Tarshid Onizaih (ES-0019/ESCO) | 246 | SPD | APPROVED | No | 2021-11-21 | Abas, Mohammed Fekry | 2021-11-23 | 2021-11-23 |  |  |  | 100000 | 3890 | 0 | STANDARD | Dehn Middle East Fze | USD | 81750 | APPROVED |  |  | 2021-12-12 | 18250 | 19 | Babic, Marian | -44523 | 19
10521100009 | Streetlights Tabuk (ES-0024) | 247 | SPD | APPROVED | No | 2021-11-21 | Abas, Mohammed Fekry | 2021-11-22 | 2021-11-23 |  |  |  | 40000 | 3891 | 0 | STANDARD | Dehn Middle East Fze | USD | 32700 | APPROVED |  |  | 2021-12-12 | 7300 | 19 | Babic, Marian | -44523 | 19
10521300005 | Modon (TD-0034/HV-1294) | 283 | PR For substation Furnitures | APPROVED | No | 2021-11-24 | Abas, Mohammed Fekry | 2022-01-16 | 2022-01-18 | 2021-12-29 |  | Due to change the specification. | 14730 | 3955 | 0 | STANDARD | DANAH AL RAYEDA ESTABLISHMENT | SAR | 14730 | APPROVED |  |  | 2022-01-26 | 0 | 8 | Babic, Marian | -44579 | 8
| ORA-01403: no data found | 284 | Furniture for the new office | APPROVED | No | 2021-11-24 | Abas, Mohammed Fekry | 2021-11-24 | 2021-11-24 |  |  |  | 1500000 | 3878 | 0 | STANDARD | MAJESTIC OFFICE FOR FURNITURE | SAR | 427627 | APPROVED |  |  | 2021-11-25 | 1072373 | 1 | Abuhammad, Samir | -44524 | 1
10521100008 | King Fahad National Centre for Children's Cancer (ES-0023) | 285 | Meters supply & intalation in KFNCCC | APPROVED | No | 2021-11-29 | Abas, Mohammed Fekry | 2021-12-01 | 2021-12-05 |  |  |  | 46974 | 3895 | 0 | STANDARD | Energy Tracks For Contracting | SAR | 46974 | APPROVED |  |  | 2021-12-23 | 0 | 18 | Abuhammad, Samir | -44535 | 18
10531109999 | Trading - Job Orders | 290 | Supply of Communication materials - Naval Base Project | APPROVED | No | 2021-12-01 | Abas, Mohammed Fekry | 2021-12-05 | 2021-12-06 |  |  |  | 86810.97 | 3910 | 0 | STANDARD | Hardware Solutions Builders Co Ltd | SAR | 86711 | APPROVED |  |  | 2021-12-15 | 99.97 | 9 | Abuhammad, Samir | -44536 | 9
| ORA-01403: no data found | 297 | Smart system for the new office | APPROVED | No | 2021-12-06 | Abas, Mohammed Fekry | 2021-12-06 | 2021-12-07 |  |  |  | 1500000 | 3896 | 0 | STANDARD | REDINGTON SAUDI ARABIA DISTRIBUTION CO. | SAR | 1133781.33 | APPROVED |  |  | 2021-12-16 | 366218.67 | 9 | Abuhammad, Samir | -44537 | 9
| ORA-01403: no data found | 297 | Smart system for the new office | APPROVED | No | 2021-12-06 | Abas, Mohammed Fekry | 2021-12-06 | 2021-12-07 |  |  |  | 1500000 | 3896 | 1 | STANDARD | REDINGTON SAUDI ARABIA DISTRIBUTION CO. | SAR | 1118781.33 | APPROVED |  |  | 2022-10-16 | 381218.67 | 313 | Abuhammad, Samir | -44537 | 313
| ORA-01403: no data found | 298 | Biometric system for the new office | APPROVED | No | 2021-12-07 | Abas, Mohammed Fekry | 2021-12-08 | 2021-12-08 |  |  |  | 75000 | 3913 | 0 | STANDARD | Advance International Company | SAR | 43670 | APPROVED |  |  | 2021-12-15 | 31330 | 7 | Abuhammad, Samir | -44538 | 7
| ORA-01403: no data found | 310 | FortiGate-201E 1 Year Unified Threat Protection (UTP) (IPS, Advanced Malware Protection, Application Control, Web & Video Filtering, Antispam Service, and 24x7 FortiCare) | APPROVED | No | 2021-12-12 | Abas, Mohammed Fekry | 2021-12-13 | 2021-12-13 |  |  |  | 11997.38 | 3920 | 0 | STANDARD | Exclusive Networks For Information Systems Technology | SAR | 9330 | APPROVED |  |  | 2021-12-27 | 2667.38 | 14 | Abuhammad, Samir | -44543 | 14
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 311 | JEC SS - TPI DC Convertor | APPROVED | No | 2021-12-12 | Abas, Mohammed Fekry | 2021-12-15 | 2021-12-19 |  |  |  | 10000 | 3956 | 0 | STANDARD | SGS GULF LIMITED | USD | 7500 | APPROVED |  |  | 2022-03-08 | 2500 | 79 | Babic, Marian | -44549 | 79
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 312 | JEC SS - TPI for SAS | APPROVED | No | 2021-12-12 | Abas, Mohammed Fekry | 2021-12-15 | 2021-12-19 |  |  |  | 10000 | 3926 | 0 | STANDARD | Atlas Support and Services | SAR | 8000 | APPROVED |  |  | 2022-01-03 | 2000 | 15 | Babic, Marian | -44549 | 15
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 312 | JEC SS - TPI for SAS | APPROVED | No | 2021-12-12 | Abas, Mohammed Fekry | 2021-12-15 | 2021-12-19 |  |  |  | 10000 | 3926 | 2 | STANDARD | Atlas Support and Services | SAR | 8000 | REJECTED |  |  |  | 2000 |  | Babic, Marian | -44549 | -44549
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 315 | JEC SS - TPI for ACDC Panels | APPROVED | No | 2021-12-14 | Abas, Mohammed Fekry | 2021-12-15 | 2021-12-19 |  |  |  | 10000 | 3921 | 0 | STANDARD | SGS GULF LIMITED | USD | 8775 | APPROVED |  |  | 2021-12-23 | 1225 | 4 | Babic, Marian | -44549 | 4
10521300010 | Rehabilitation of NAF SS (TD-0040) | 319 | 13.8KV Switchgear TPI | APPROVED | No | 2021-12-15 | Abas, Mohammed Fekry | 2021-12-23 | 2021-12-26 |  |  |  | 5000 | 3925 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | SAR | 4050 | APPROVED |  |  | 2021-12-29 | 950 | 3 | Babic, Marian | -44556 | 3
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 320 | TFR, DSM & SER | RETURNED | No | 2021-12-16 | Babic, Marian | 2024-04-15 | 2022-04-28 |  | 2021-12-26 |  | 248800 | 4086 | 0 | STANDARD | ADWAN MARKETING CO. | SAR | 243800 | APPROVED |  |  | 2022-05-30 | 5000 |  | Babic, Marian | -44679 | 32
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 320 | TFR, DSM & SER | RETURNED | No | 2021-12-16 | Babic, Marian | 2024-04-15 | 2022-04-28 |  | 2021-12-26 |  | 120000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44679 | -44679
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 320 | TFR, DSM & SER | RETURNED | No | 2021-12-16 | Babic, Marian | 2024-04-15 | 2022-04-28 |  | 2021-12-26 |  | 245000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44679 | -44679
10522309999 | Infrastructure and Security Projects - Job Orders | 331 | Saudico/MEP/1167/Add-09/2021 | APPROVED | No | 2021-12-20 | Abas, Mohammed Fekry | 2021-12-28 | 2021-12-29 |  |  |  | 17000 | 3934 | 0 | STANDARD | Gold Star Information Technology | SAR | 14000 | APPROVED |  |  | 2022-01-12 | 3000 | 14 | Abuhammad, Samir | -44559 | 14
| ORA-01403: no data found | 332 | Chairs for the new office | APPROVED | No | 2021-12-21 | Abas, Mohammed Fekry | 2021-12-21 | 2021-12-21 |  |  |  | 62250 | 3923 | 0 | STANDARD | Riyadh House Branch of Jeraisy Group Company | SAR | 62250 | APPROVED |  |  | 2021-12-28 | 0 | 7 | Abuhammad, Samir | -44551 | 7
10521200006 | Overhead Gantry with Data Sensors- NEOM | 338 | Neom - Gantry - Huawei Equipement | APPROVED | No | 2021-12-23 | Abas, Mohammed Fekry | 2021-12-27 | 2021-12-27 |  |  |  | 587654.24 | 3940 | 0 | STANDARD | REDINGTON SAUDI ARABIA DISTRIBUTION CO. | SAR | 587654.24 | APPROVED |  |  | 2022-01-19 | 0 | 23 | Babic, Marian | -44557 | 23
10531109999 | Trading - Job Orders | 347 | Supply of fiber optic cable | APPROVED | No | 2021-12-26 | Abas, Mohammed Fekry | 2021-12-28 | 2021-12-29 |  |  |  | 65000 | 3933 | 0 | STANDARD | Horizon Dimension Trading Est | SAR | 65000 | APPROVED |  |  | 2022-01-19 | 0 | 21 | Abuhammad, Samir | -44559 | 21
| ORA-01403: no data found | 348 | Board Meeting for the new office | APPROVED | No | 2021-12-26 | Abas, Mohammed Fekry | 2021-12-27 | 2021-12-27 |  |  |  | 40000 | 3931 | 0 | STANDARD | Grid For Trading-Gridesing | SAR | 32760 | APPROVED |  |  | 2022-01-05 | 7240 | 9 | Abuhammad, Samir | -44557 | 9
| ORA-01403: no data found | 349 | Partitions between offices (New office) | APPROVED | No | 2021-12-27 | Abas, Mohammed Fekry | 2021-12-27 | 2021-12-27 |  |  |  | 140000 | 3927 | 0 | STANDARD | Riyadh House Branch of Jeraisy Group Company | SAR | 114433 | APPROVED |  |  | 2021-12-29 | 25567 | 2 | Abuhammad, Samir | -44557 | 2
10529140007 | Jeddah Gate (TD-0011/HV-1144) | 351 | Spare part protection relay testing | APPROVED | No | 2021-12-27 | Abas, Mohammed Fekry | 2021-12-28 | 2021-12-28 |  |  |  | 35000 | 3929 | 0 | STANDARD | ALFANAR CO | SAR | 35000 | APPROVED |  |  | 2022-01-12 | 0 | 15 | Babic, Marian | -44558 | 15
10521100014 | Streetlights Makkah, Phase 2 | 357 | mat1 | INCOMPLETE | No | [7 empty] | 1650 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 360 | Curtains for the new office | APPROVED | No | 2021-12-30 | Abas, Mohammed Fekry | 2022-01-02 | 2022-01-02 |  |  |  | 200000 | 3930 | 0 | STANDARD | Modern Ideas Est | SAR | 82745 | APPROVED |  |  | 2022-01-06 | 117255 | 4 | Abuhammad, Samir | -44563 | 4
| ORA-01403: no data found | 361 | CEO Office Furniture - New Office | RETURNED | No | 2021-12-30 | Babic, Marian | 2024-03-26 | 2022-01-02 | 2024-03-26 |  | PO for this subject already issued, this PR is a balance which is not needed | 800000 | 3936 | 0 | STANDARD | Dunya Al Mashari For Trading | SAR | 606011 | APPROVED |  |  | 2022-01-13 | 193989 |  | Babic, Marian | -44563 | 11
| ORA-01403: no data found | 361 | CEO Office Furniture - New Office | RETURNED | No | 2021-12-30 | Babic, Marian | 2024-03-26 | 2022-01-02 | 2024-03-26 |  | PO for this subject already issued, this PR is a balance which is not needed | 200000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44563 | -44563
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 363 | SDAIA's Cabinets Commercial | RETURNED | No | 2022-01-26 | Abuhammad, Samir | 2023-08-24 | 2022-02-09 | 2023-08-24 |  | Due to change item wise/manual PO. | 587975.28 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44601 | -44601
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 364 | JEC SS - Small Material | RETURNED | No | 2022-01-04 | Babic, Marian | 2024-03-26 | 2022-01-09 | 2024-03-26 |  | PO for this subject already issued, this PR is a balance which is not needed | 66187.2 | 3943 | 0 | STANDARD | SANA FOR ELECTRICAL & TEL.CO. | SAR | 66187.2 | APPROVED |  |  | 2022-01-22 | 0 |  | Babic, Marian | -44570 | 13
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 364 | JEC SS - Small Material | RETURNED | No | 2022-01-04 | Babic, Marian | 2024-03-26 | 2022-01-09 | 2024-03-26 |  | PO for this subject already issued, this PR is a balance which is not needed | 415 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44570 | -44570
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 367 | JEC SS - Fuel Supply | APPROVED | No | 2022-01-05 | Abas, Mohammed Fekry | 2022-01-16 | 2022-01-16 |  | 2022-01-05 |  | 120000 | 3942 | 0 | STANDARD | Othman Hammoud Al-Zaydi Est | SAR | 100000 | APPROVED |  |  | 2022-03-09 | 20000 | 52 | Babic, Marian | -44577 | 52
10521300010 | Rehabilitation of NAF SS (TD-0040) | 370 | PACU Units TPI | APPROVED | No | 2022-01-10 | Abas, Mohammed Fekry | 2022-01-16 | 2022-01-16 |  |  |  | 2800 | 3941 | 0 | STANDARD | ARAB INSPECTION & Q.A.CO. | SAR | 2800 | APPROVED |  |  | 2022-01-19 | 0 | 3 | Babic, Marian | -44577 | 3
10521300010 | Rehabilitation of NAF SS (TD-0040) | 372 | HVAC SYSTEM | APPROVED | No | 2022-01-11 | Abas, Mohammed Fekry | 2022-01-16 | 2022-01-18 |  |  |  | 40000 | 3948 | 0 | STANDARD | ALFANAR CO | SAR | 40000 | APPROVED |  |  | 2022-01-26 | 0 | 8 | Babic, Marian | -44579 | 8
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 373 | OHTC | APPROVED | No | 2022-01-11 | Abas, Mohammed Fekry | 2022-01-16 | 2022-01-16 |  |  |  | 150000 | 3951 | 0 | STANDARD | Eastern Morris Cranes Co. Ltd. | SAR | 150000 | APPROVED |  |  | 2022-02-01 | 0 | 16 | Babic, Marian | -44577 | 16
10529110001 | Dammam Port (DSP-0038) | 374 | Dammam Port UPVC Pipes | APPROVED | No | 2022-01-11 | Abas, Mohammed Fekry | 2022-01-16 | 2022-01-16 |  |  |  | 399000 | 3952 | 0 | STANDARD | NATIONAL KHAM FACTORY FOR PLASTIC IND.CO. | SAR | 306662.4 | APPROVED |  |  | 2022-01-26 | 92337.6 | 10 | Babic, Marian | -44577 | 10
10529220024 | STC Pay - Micro Focus Implementation Project for STC Pay | 376 | Stcpay- smax after go live support | APPROVED | No | 2022-01-16 | Abas, Mohammed Fekry | 2022-01-25 | 2022-01-27 |  |  |  | 90000 | 4022 | 0 | STANDARD | Al Sakhrai Al Hadeth Est | SAR | 90000 | APPROVED |  |  | 2022-03-13 | 0 | 45 | Abuhammad, Samir | -44588 | 45
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 377 | JEC SS - TPI for Telecom Panels | APPROVED | No | 2022-01-16 | Abas, Mohammed Fekry | 2022-01-20 | 2022-01-23 |  |  |  | 10000 | 3981 | 0 | STANDARD | ARAB INSPECTION & Q.A.CO. | SAR | 7000 | APPROVED |  |  | 2022-02-08 | 3000 | 16 | AlQuraish, Sajjad Hazem | -44584 | 16
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 378 | JEC - TPI for AMI | RETURNED | No | 2022-01-16 | AlQuraish, Sajjad Hazem | 2022-02-06 | 2022-01-18 | 2022-02-06 |  | please increase the budget to cover three days @1400 per day without VAT | 3000 | [5 empty] | 0 |  |  |  |  | 0 |  | AlQuraish, Sajjad Hazem | -44579 | -44579
| ORA-01403: no data found | 380 | Material transfer from Baqaiq | APPROVED | No | 2022-01-17 | Abas, Mohammed Fekry | 2022-01-18 | 2022-01-23 |  |  |  | 50000 | 3990 | 0 | STANDARD |  | SAR | 48000 | INCOMPLETE |  |  |  | 2000 | 1470 | AlQuraish, Sajjad Hazem | -44584 | -44584
| ORA-01403: no data found | 380 | Material transfer from Baqaiq | APPROVED | No | 2022-01-17 | Abas, Mohammed Fekry | 2022-01-18 | 2022-01-23 |  |  |  | 50000 | [5 empty] | 0 |  |  |  |  | 0 |  | AlQuraish, Sajjad Hazem | -44584 | -44584
10521300010 | Rehabilitation of NAF SS (TD-0040) | 381 | Lighting wires | APPROVED | No | 2022-01-17 | Abas, Mohammed Fekry | 2022-01-18 | 2022-01-18 |  |  |  | 70000 | 3950 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 70000 | APPROVED |  |  | 2022-01-22 | 0 | 4 | Babic, Marian | -44579 | 4
10521300010 | Rehabilitation of NAF SS (TD-0040) | 382 | HV,MV,LV Cables | APPROVED | No | 2022-01-17 | Abas, Mohammed Fekry | 2022-01-17 | 2022-01-18 |  |  |  | 1880241.24 | 3949 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 1880241.24 | APPROVED |  |  | 2022-01-26 | 0 | 8 | Babic, Marian | -44579 | 8
10521300010 | Rehabilitation of NAF SS (TD-0040) | 383 | LINKBOXS | APPROVED | No | 2022-01-17 | Abas, Mohammed Fekry | 2022-01-20 | 2022-01-23 |  |  |  | 28200 | 3957 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 28200 | APPROVED |  |  | 2022-01-26 | 0 | 3 | Babic, Marian | -44584 | 3
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 384 | HVAC System | APPROVED | No | 2022-01-17 | Abas, Mohammed Fekry | 2022-01-20 | 2022-01-23 |  |  |  | 800000 | 3953 | 0 | STANDARD | Magna Contracting Co | SAR | 800000 | APPROVED |  |  | 2022-01-26 | 0 | 3 | Babic, Marian | -44584 | 3
10521300010 | Rehabilitation of NAF SS (TD-0040) | 385 | Cable trays and Ladders | APPROVED | No | 2022-01-17 | Abas, Mohammed Fekry | 2022-01-20 | 2022-01-23 |  |  |  | 187656.5 | 3954 | 0 | STANDARD | Electrolink Co Ltd | SAR | 154784 | APPROVED |  |  | 2022-01-26 | 32872.5 | 3 | Babic, Marian | -44584 | 3
10521300010 | Rehabilitation of NAF SS (TD-0040) | 386 | MV Termination kits | APPROVED | No | 2022-01-17 | Abas, Mohammed Fekry | 2022-01-23 | 2022-01-23 |  |  |  | 63942 | 4047 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 63942 | APPROVED |  |  | 2022-03-31 | 0 | 67 | Babic, Marian | -44584 | 67
10521100010 | Eastern Province - EP3 | 387 | Installation of decorative light | APPROVED | No | 2022-01-18 | Abas, Mohammed Fekry | 2022-01-19 | 2022-01-23 |  |  |  | 198199 | 3992 | 0 | STANDARD | EXPERIENCE&EXCELLENCE FOR CONTRACTING | SAR | 198199 | APPROVED |  |  | 2022-02-17 | 0 | 25 | Babic, Marian | -44584 | 25
| ORA-01403: no data found | 388 | Purchase four laptops | APPROVED | No | 2022-01-23 | Abas, Mohammed Fekry | 2022-02-24 | 2022-02-27 |  |  |  | 20250 | 4093 | 0 | STANDARD | Fast Computers for Trading Est | SAR | 18900 | APPROVED |  |  | 2022-04-26 | 1350 | 58 | Abuhammad, Samir | -44619 | 58
10522300002 | Training City KAP 5 NTT-137 | 391 | Service Renewal ( Calibration for Fluke Device ) | APPROVED | No | 2022-01-18 | Abas, Mohammed Fekry | 2022-01-26 | 2022-01-30 |  |  |  | 12000 | 3988 | 0 | STANDARD | Bright Wire Company | SAR | 12000 | APPROVED |  |  | 2022-02-10 | 0 | 11 | Abuhammad, Samir | -44591 | 11
10521300010 | Rehabilitation of NAF SS (TD-0040) | 406 | Battery TPI | APPROVED | No | 2022-01-20 | Abas, Mohammed Fekry | 2022-01-23 | 2022-01-23 |  |  |  | 10000 | 3975 | 0 | STANDARD | SGS GULF LIMITED | USD | 7500 | APPROVED |  |  | 2022-02-08 | 2500 | 16 | AlQuraish, Sajjad Hazem | -44584 | 16
10521300010 | Rehabilitation of NAF SS (TD-0040) | 412 | Lighting Switches and Push Buttons | APPROVED | No | 2022-01-21 | Abas, Mohammed Fekry | 2022-02-17 | 2022-02-20 | 2022-02-08 |  | as discussed kindly ammend the request quantities and prices | 213415.27 | 3993 | 0 | STANDARD | ATTAA Al-Mustaqbal Contratcing | SAR | 192389.07 | APPROVED |  |  | 2022-03-09 | 21026.2 | 17 | AlQuraish, Sajjad Hazem | -44612 | 17
10522309999 | Infrastructure and Security Projects - Job Orders | 413 | SANG Hospitals - NGHA - Access Switches Configuration, Testing & Commissioning . | APPROVED | No | 2022-01-23 | Abas, Mohammed Fekry | 2022-01-27 | 2022-01-30 |  | 2022-01-25 |  | 48000 | 3994 | 0 | STANDARD | Advanced Industrial Solutions | SAR | 48000 | APPROVED |  |  | 2022-02-28 | 0 | 29 | Abuhammad, Samir | -44591 | 29
10521100011 | Energy Savings Performance-MOJ | 414 | MOJ lighting stock -1 | RETURNED | No | 2022-01-23 | Abuhammad, Samir | 2022-04-12 | 2022-01-27 | 2022-04-12 |  | As per project request"to buy by sit cash" | 1500 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44588 | -44588
10521100011 | Energy Savings Performance-MOJ | 415 | MOJ stock from Philips | RETURNED | No | 2022-01-23 | Abuhammad, Samir | 2022-04-12 | 2022-01-27 | 2022-04-12 |  | As per project request"to buy by sit cash" | 5500 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44588 | -44588
10522300002 | Training City KAP 5 NTT-137 | 423 | Training city - KAP5 NTT-137 - professional services | APPROVED | No | 2022-01-24 | Abas, Mohammed Fekry | 2022-01-26 | 2022-01-30 |  |  |  | 15000 | 3991 | 0 | STANDARD | Khalid Muhammed Al Dossary Trading Est | SAR | 15000 | APPROVED |  |  | 2022-02-28 | 0 | 29 | Abuhammad, Samir | -44591 | 29
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 425 | JEC SS - Boundary Wall | APPROVED | No | 2022-01-24 | Abas, Mohammed Fekry | 2022-02-15 | 2022-02-17 |  |  |  | 600000 | 4100 | 0 | STANDARD | Precast Manufacturing Company (PREMCO) | SAR | 572628 | APPROVED |  |  | 2022-05-22 | 27372 | 94 | Abuhammad, Samir | -44609 | 94
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 426 | JEC - Transformer Screening | RETURNED | No | 2022-01-24 | Babic, Marian | 2023-07-30 | 2022-02-17 | 2023-07-30 |  | PO will be issued manually (insuffcient amount) | 900000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44609 | -44609
| ORA-01403: no data found | 427 | Disassemble and shifting equipment at Khumra warehouse | APPROVED | No | 2022-01-24 | Abas, Mohammed Fekry | 2022-01-26 | 2022-01-27 |  | 2022-01-24 |  | 60000 | 3984 | 0 | STANDARD | Ahmed Moawad Al Jedaani Est for General Contracting | SAR | 55000 | APPROVED |  |  | 2022-02-10 | 5000 | 14 | Abuhammad, Samir | -44588 | 14
| ORA-01403: no data found | 433 | Pods for the New office | APPROVED | No | 2022-01-26 | Abas, Mohammed Fekry | 2022-01-26 | 2022-01-27 |  |  |  | 99500 | 3996 | 0 | STANDARD | Riyadh House Branch of Jeraisy Group Company | SAR | 45378 | APPROVED |  |  | 2022-02-10 | 54122 | 14 | Abuhammad, Samir | -44588 | 14
| ORA-01403: no data found | 433 | Pods for the New office | APPROVED | No | 2022-01-26 | Abas, Mohammed Fekry | 2022-01-26 | 2022-01-27 |  |  |  | 99500 | 3996 | 1 | STANDARD | Riyadh House Branch of Jeraisy Group Company | SAR | 31400 | APPROVED |  |  | 2022-06-23 | 68100 | 147 | Abuhammad, Samir | -44588 | 147
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 435 | JEC- TPI Revenue | APPROVED | No | 2022-01-26 | Abas, Mohammed Fekry | 2022-01-31 | 2022-01-31 |  |  |  | 5550 | 3852 | 1 | STANDARD | Atlas Support and Services | SAR | 5550 | APPROVED |  |  | 2022-02-17 | 0 | 17 | AlQuraish, Sajjad Hazem | -44592 | 17
| ORA-01403: no data found | 436 | Chairs for the Board meeting | APPROVED | No | 2022-01-26 | Abas, Mohammed Fekry | 2022-01-26 | 2022-01-27 |  |  |  | 42435 | 3977 | 0 | STANDARD | Riyadh House Branch of Jeraisy Group Company | SAR | 42435 | APPROVED |  |  | 2022-02-01 | 0 | 5 | Abuhammad, Samir | -44588 | 5
10521300010 | Rehabilitation of NAF SS (TD-0040) | 442 | HV Termination Kit | RETURNED | No | 2022-01-27 | Babic, Marian | 2022-03-29 | 2022-02-07 | 2022-03-29 |  | PO for HV term.kit already issued from another PR | 299191.2 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -44599 | -44599
| ORA-01403: no data found | 444 | Advanced consulting engineers | APPROVED | No | 2022-01-30 | Abas, Mohammed Fekry | 2022-02-03 | 2022-02-03 |  |  |  | 88000 | 4016 | 0 | STANDARD | Hussein Hassan Biyari Consulting Company | SAR | 88000 | APPROVED |  |  | 2022-03-22 | 0 | 47 | Abuhammad, Samir | -44595 | 47
10521300010 | Rehabilitation of NAF SS (TD-0040) | 448 | TPI for Charger | APPROVED | No | 2022-01-31 | Abas, Mohammed Fekry | 2022-02-03 | 2022-02-07 |  |  |  | 10000 | 4115 | 0 | STANDARD | SGS GULF LIMITED | USD | 8250 | APPROVED |  |  | 2022-05-29 | 1750 | 111 | Babic, Marian | -44599 | 111
10521300010 | Rehabilitation of NAF SS (TD-0040) | 449 | DDC TPI | APPROVED | No | 2022-01-31 | Abas, Mohammed Fekry | 2022-02-03 | 2022-02-07 |  |  |  | 4000 | 4028 | 0 | STANDARD | ARAB INSPECTION & Q.A.CO. | SAR | 2800 | APPROVED |  |  | 2022-03-03 | 1200 | 24 | Babic, Marian | -44599 | 24
| ORA-01403: no data found | 450 | Printers for the new office | REJECTED | No | 2022-01-31 | AlShehri, Ali | 2022-02-01 |  |  | 2022-02-01 |  | 143720 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 452 | EQUIPMENTS MAINTENANCE | APPROVED | No | 2022-02-01 | Abas, Mohammed Fekry | 2022-02-03 | 2022-02-03 |  |  |  | 70900 | 3995 | 0 | STANDARD | SAWARY Trading and Contracting | SAR | 66900 | APPROVED |  |  | 2022-02-13 | 4000 | 10 | Abuhammad, Samir | -44595 | 10
| ORA-01403: no data found | 453 | PRINTERS FOR THE NEW OFFICE | APPROVED | No | 2022-02-01 | Abas, Mohammed Fekry | 2022-02-03 | 2022-02-03 |  |  |  | 143820 | 3983 | 0 | STANDARD | Saudi Xerox Agencies | SAR | 143820 | APPROVED |  |  | 2022-02-28 | 0 | 25 | Babic, Marian | -44595 | 25
| ORA-01403: no data found | 469 | Additional to PO#3913 | APPROVED | No | 2022-02-03 | Abas, Mohammed Fekry | 2022-02-07 | 2022-02-07 |  |  |  | 2160 | 3913 | 1 | STANDARD | Advance International Company | SAR | 2160 | APPROVED |  |  | 2022-02-09 | 0 | 2 | Abuhammad, Samir | -44599 | 2
10522309999 | Infrastructure and Security Projects - Job Orders | 470 | UPS FOR KACND | RETURNED | No | 2022-02-07 | Abuhammad, Samir | 2022-02-17 | 2022-02-10 | 2022-02-17 | 2022-02-07 | Due to cahnge the price / item as per market price, The PR was initiated by estimated cost with consideration of total selling cost as it is an old project which is no reference quote delivered to me | 28000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44602 | -44602
| ORA-01403: no data found | 471 | Extention for PO# 3927-0 (Partitions for the new office | APPROVED | No | 2022-02-07 | Abas, Mohammed Fekry | 2022-02-07 | 2022-02-07 |  |  |  | 5220 | 3927 | 1 | STANDARD | Riyadh House Branch of Jeraisy Group Company | SAR | 5220 | APPROVED |  |  | 2022-02-10 | 0 | 3 | Abuhammad, Samir | -44599 | 3
10521300003 | Al-Shalal S/S (TD-0028/HV-1222) | 473 | TPI SGS for Battery Inspection | APPROVED | No | 2022-02-08 | Abas, Mohammed Fekry | 2022-09-13 | 2022-09-14 | 2022-02-14 |  | Please make it "service by quantity" instead of "service" (this way I cannot convert currency) | 10212.5 | 3997 | 0 | STANDARD | SGS GULF LIMITED | USD | 10312.5 | APPROVED |  |  | 2022-09-25 | -100 | 11 | Babic, Marian | -44818 | 11
10521300005 | Modon (TD-0034/HV-1294) | 474 | Miscellaneous materials - Modon Asfan | APPROVED | No | 2022-02-10 | Abas, Mohammed Fekry | 2022-03-01 | 2022-03-01 |  |  |  | 20377 | 4029 | 0 | STANDARD | Al Nokhba Hardware Est | SAR | 20377 | APPROVED |  |  | 2022-03-08 | 0 | 7 | Babic, Marian | -44621 | 7
| ORA-01403: no data found | 476 | Cabinets for offices | RETURNED | No | 2022-02-10 | Babic, Marian | 2022-02-16 | 2022-02-10 | 2022-02-16 |  | As discussed, this PR is replaced with new one | 12000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44602 | -44602
10529110001 | Dammam Port (DSP-0038) | 487 | DPP SCADA Furniture | APPROVED | No | 2022-02-14 | Abas, Mohammed Fekry | 2022-02-15 | 2022-02-16 |  |  |  | 265000 | 4010 | 0 | STANDARD | Project Way Est | SAR | 180120 | APPROVED |  |  | 2022-03-24 | 84880 | 36 | Abuhammad, Samir | -44608 | 36
10529110001 | Dammam Port (DSP-0038) | 488 | DPP Scada Elevator Repair Works | APPROVED | No | 2022-02-15 | Abas, Mohammed Fekry | 2022-02-15 | 2022-02-16 |  |  |  | 15000 | 4023 | 0 | STANDARD | KONE AREECO LTD | SAR | 15000 | APPROVED |  |  | 2022-03-13 | 0 | 25 | Abuhammad, Samir | -44608 | 25
10529140007 | Jeddah Gate (TD-0011/HV-1144) | 489 | Bushing 30kV / 4500A | APPROVED | No | 2022-02-14 | Abas, Mohammed Fekry | 2022-02-21 | 2022-02-23 |  |  |  | 14978.1 | 4031 | 0 | STANDARD | Preis GmbH | EUR | 14978.1 | APPROVED |  |  | 2022-03-08 | 0 | 13 | Babic, Marian | -44615 | 13
| ORA-01403: no data found | 490 | CEO Office - Reception Area | APPROVED | No | 2022-02-14 | Abas, Mohammed Fekry | 2022-02-15 | 2022-02-15 |  |  |  | 46186 | 4009 | 0 | STANDARD | Dunya Al Mashari For Trading | SAR | 46186 | APPROVED |  |  | 2022-02-17 | 0 | 2 | Babic, Marian | -44607 | 2
| ORA-01403: no data found | 491 | Maiestic Furniture | APPROVED | No | 2022-02-15 | Abas, Mohammed Fekry | 2022-02-15 | 2022-02-16 |  |  |  | 30000 | 4013 | 0 | STANDARD | MAJESTIC OFFICE FOR FURNITURE | SAR | 30000 | APPROVED |  |  | 2022-02-17 | 0 | 1 | Babic, Marian | -44608 | 1
10521300007 | Bahrain, 66kV Substations (TD-0038/MV-1282) | 495 | Acess road works for Al sahalyah, Liya & Salmantown S/S | APPROVED | No | 2022-02-21 | Abas, Mohammed Fekry | 2022-03-01 | 2022-03-01 |  |  |  | 527008 | 4041 | 0 | STANDARD | Interlock Maintenance construction WLL | BHD | 527008 | APPROVED |  |  | 2022-04-18 | 0 | 48 | Abuhammad, Samir | -44621 | 48
10521300007 | Bahrain, 66kV Substations (TD-0038/MV-1282) | 495 | Acess road works for Al sahalyah, Liya & Salmantown S/S | APPROVED | No | 2022-02-21 | Abas, Mohammed Fekry | 2022-03-01 | 2022-03-01 |  |  |  | 527008 | 4041 | 2 | STANDARD | Interlock Maintenance construction WLL | BHD | 527008 | APPROVED |  |  | 2022-05-08 | 0 | 68 | Abuhammad, Samir | -44621 | 68
| ORA-01403: no data found | 505 | Glass Insulation protection for the new office | RETURNED | No | 2022-02-24 | Abuhammad, Samir | 2022-03-08 | 2022-02-27 | 2022-03-08 |  | As per requester. | 43750 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44619 | -44619
10521300007 | Bahrain, 66kV Substations (TD-0038/MV-1282) | 517 | Acess road associated works (Electrical utility shifting) for liyah and salman Town SS. | APPROVED | No | 2022-03-02 | Abas, Mohammed Fekry | 2022-03-13 | 2022-03-13 |  |  |  | 15000 | 4044 | 0 | STANDARD | BAHZAD ELECTRICAL AND CONSTRUCTION | BHD | 14960.1 | APPROVED |  |  | 2022-04-06 | 39.9 | 24 | Babic, Marian | -44633 | 24
10521100008 | King Fahad National Centre for Children's Cancer (ES-0023) | 519 | KFNCCC- Heaters control | APPROVED | No | 2022-03-06 | Abas, Mohammed Fekry | 2022-03-08 | 2022-03-08 |  |  |  | 255176 | 4039 | 0 | STANDARD | Smart Controls Systems Contracting Est. | SAR | 255176 | APPROVED |  |  | 2022-03-22 | 0 | 14 | Abuhammad, Samir | -44628 | 14
10522309999 | Infrastructure and Security Projects - Job Orders | 538 | UPS fir KACND | RETURNED | No | 2022-03-20 | Abuhammad, Samir | 2022-04-04 | 2022-03-24 | 2022-04-04 |  | Due to wronge shimpment deatls"destination Organization" | 27500 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44644 | -44644
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 540 | JEC- SS Lighting Small Material | APPROVED | No | 2022-03-10 | Abas, Mohammed Fekry | 2022-03-15 | 2022-03-16 |  | 2022-03-10 |  | 61283.2 | 4163 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 80744.8 | APPROVED |  |  | 2022-08-07 | -19461.6 | 144 | Babic, Marian | -44636 | 144
| ORA-01403: no data found | 543 | 16M ARTICULATING DIESEL BOOM | RETURNED | No | 2022-03-09 | Abuhammad, Samir | 2022-03-24 | 2022-03-13 | 2022-03-24 |  | The cost not matching with Offer and project requirment , returned as per creater request. | 6000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44633 | -44633
| ORA-01403: no data found | 544 | SUN CONTROL WINDOW FILMS | APPROVED | No | 2022-03-09 | Abas, Mohammed Fekry | 2022-03-13 | 2022-03-13 |  |  |  | 139587 | 4046 | 0 | STANDARD | smart daimond Trading Co | SAR | 113750 | APPROVED |  |  | 2022-03-21 | 25837 | 8 | Abuhammad, Samir | -44633 | 8
| ORA-01403: no data found | 545 | Equipment maintenance | RETURNED | No | 2022-03-09 | Abuhammad, Samir | 2022-03-24 | 2022-03-13 | 2022-03-24 |  | as per project "LOG" request. | 66900 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44633 | -44633
10521300010 | Rehabilitation of NAF SS (TD-0040) | 546 | Telecom Equipment TPI - NAF | APPROVED | No | 2022-03-13 | Abas, Mohammed Fekry | 2022-03-15 | 2022-03-16 |  |  |  | 7500 | 4050 | 0 | STANDARD | ARAB INSPECTION & Q.A.CO. | SAR | 7000 | APPROVED |  |  | 2022-03-29 | 500 | 13 | AlQuraish, Sajjad Hazem | -44636 | 13
10521300010 | Rehabilitation of NAF SS (TD-0040) | 547 | HV Cables Test-NAF | APPROVED | No | 2022-03-13 | Abas, Mohammed Fekry | 2022-03-15 | 2022-03-16 |  |  |  | 60000 | 4069 | 0 | STANDARD | GCC Electrical Testing Laboratory Co | SAR | 60000 | APPROVED |  |  | 2022-04-06 | 0 | 21 | Babic, Marian | -44636 | 21
10521300010 | Rehabilitation of NAF SS (TD-0040) | 548 | Protection Panels TPI-NAF | APPROVED | No | 2022-03-13 | Abas, Mohammed Fekry | 2022-03-15 | 2022-03-16 |  |  |  | 6000 | 4049 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | SAR | 5550 | APPROVED |  |  | 2022-03-22 | 450 | 6 | AlQuraish, Sajjad Hazem | -44636 | 6
10521300010 | Rehabilitation of NAF SS (TD-0040) | 548 | Protection Panels TPI-NAF | APPROVED | No | 2022-03-13 | Abas, Mohammed Fekry | 2022-03-15 | 2022-03-16 |  |  |  | 6000 | [5 empty] | 0 |  |  |  |  | 0 |  | AlQuraish, Sajjad Hazem | -44636 | -44636
10521300010 | Rehabilitation of NAF SS (TD-0040) | 549 | MV Termination Kit TPI-NAF | APPROVED | No | 2022-03-13 | Abas, Mohammed Fekry | 2022-03-15 | 2022-03-16 |  |  |  | 6000 | 4153 | 0 | STANDARD | SGS GULF LIMITED | USD | 3000 | APPROVED |  |  | 2022-06-30 | 3000 | 106 | Babic, Marian | -44636 | 106
10521300010 | Rehabilitation of NAF SS (TD-0040) | 550 | HV Termination Kit TPI-NAF | APPROVED | No | 2022-03-13 | Abas, Mohammed Fekry | 2022-03-15 | 2022-03-16 |  |  |  | 6000 | 4134 | 0 | STANDARD | SGS GULF LIMITED | USD | 6000 | APPROVED |  |  | 2022-06-08 | 0 | 84 | Babic, Marian | -44636 | 84
10521300010 | Rehabilitation of NAF SS (TD-0040) | 551 | MV Termination Kit-NAF | APPROVED | No | 2022-03-13 | Abas, Mohammed Fekry | 2022-03-15 | 2022-03-16 |  |  |  | 24000 | 4047 | 0 | STANDARD | Nima Arabia Company Limited | SAR | 23260 | APPROVED |  |  | 2022-03-31 | 740 | 15 | Babic, Marian | -44636 | 15
10521300010 | Rehabilitation of NAF SS (TD-0040) | 552 | LV,Control, MV,HV Cables TPI-NAF | APPROVED | No | 2022-03-13 | Abas, Mohammed Fekry | 2022-03-15 | 2022-03-16 |  |  |  | 4500 | 4055 | 0 | STANDARD | ARAB INSPECTION & Q.A.CO. | SAR | 4200 | APPROVED |  |  | 2022-03-29 | 300 | 13 | AlQuraish, Sajjad Hazem | -44636 | 13
10521300010 | Rehabilitation of NAF SS (TD-0040) | 552 | LV,Control, MV,HV Cables TPI-NAF | APPROVED | No | 2022-03-13 | Abas, Mohammed Fekry | 2022-03-15 | 2022-03-16 |  |  |  | 4500 | 4152 | 0 | STANDARD | Atlas Support and Services | SAR | 3400 | APPROVED |  |  | 2022-06-30 | 1100 | 106 | Babic, Marian | -44636 | 106
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 559 | GitLab Ultimate | APPROVED | No | 2022-03-14 | Abas, Mohammed Fekry | 2022-03-15 | 2022-03-16 |  |  |  | 169290 | 4042 | 0 | STANDARD | Amazic BV | USD | 169290 | APPROVED |  |  | 2022-03-24 | 0 | 8 | Abuhammad, Samir | -44636 | 8
10529140008 | Yanbu North S/S (TD-0012/HV-1164) | 562 | Tap Changer | APPROVED | No | 2022-03-14 | Abas, Mohammed Fekry | 2022-03-22 | 2022-03-22 |  |  |  | 42167.2 | 4071 | 0 | STANDARD | Reinhausen Middle East FZE | EUR | 42167.2 | APPROVED |  |  | 2022-04-06 | 0 | 15 | Babic, Marian | -44642 | 15
10531109999 | Trading - Job Orders | 563 | Supply of 380kV CTs for HAIL-3 – AL JOUF-1 D/C OH LINE AT AL JOUF-1 BSP - Alfanar-PO#4800020464 | APPROVED | No | 2022-03-15 | Abas, Mohammed Fekry | 2022-03-17 | 2022-03-20 |  |  |  | 276563.28 | 4068 | 0 | STANDARD | KONCAR INSTRUMENT TRANSFORMERS | EUR | 276563.28 | APPROVED |  |  | 2022-04-14 | 0 | 25 | Babic, Marian | -44640 | 25
10521300005 | Modon (TD-0034/HV-1294) | 565 | ELECTRIC GENERATORS | REJECTED | No | 2022-03-16 | Badhman, Saeed | 2022-12-05 | 2022-03-23 |  |  |  | 53850 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -44643 | -44643
10521300010 | Rehabilitation of NAF SS (TD-0040) | 566 | HV termination Kit-NAF | RETURNED | No | 2022-03-16 | Babic, Marian | 2024-04-15 | 2022-03-22 | 2024-04-15 |  | these PR lines are not required | 247107 | 4065 | 0 | STANDARD | Brugg Kable AG | USD | 238353.75 | APPROVED |  |  | 2022-05-17 | 8753.25 |  | Abuhammad, Samir | -44642 | 56
10521300010 | Rehabilitation of NAF SS (TD-0040) | 566 | HV termination Kit-NAF | RETURNED | No | 2022-03-16 | Babic, Marian | 2024-04-15 | 2022-03-22 | 2024-04-15 |  | these PR lines are not required | 135500 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44642 | -44642
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 567 | JEC SS- SAS Furniture | APPROVED | No | 2022-03-17 | Abas, Mohammed Fekry | 2022-03-24 | 2022-03-28 |  |  |  | 80000 | 4073 | 0 | STANDARD | ALFANAR CO | SAR | 50000 | APPROVED |  |  | 2022-04-26 | 30000 | 29 | Babic, Marian | -44648 | 29
10521100008 | King Fahad National Centre for Children's Cancer (ES-0023) | 574 | Additional Meters for KFNCCC | APPROVED | No | 2022-03-22 | Abas, Mohammed Fekry | 2022-03-27 | 2022-03-28 |  |  |  | 48050 | 4066 | 0 | STANDARD | Energy Tracks For Contracting | SAR | 48050 | APPROVED |  |  | 2022-04-07 | 0 | 10 | Abuhammad, Samir | -44648 | 10
| ORA-01403: no data found | 575 | New office modifications | APPROVED | No | 2022-03-22 | Abas, Mohammed Fekry | 2022-03-22 | 2022-03-23 |  |  |  | 75000 | 4056 | 0 | STANDARD | Dunya Al Mashari For Trading | SAR | 57060 | APPROVED |  |  | 2022-03-27 | 17940 | 4 | Abuhammad, Samir | -44643 | 4
10521300010 | Rehabilitation of NAF SS (TD-0040) | 576 | O-RINGS - NAF | APPROVED | No | 2022-03-22 | Abas, Mohammed Fekry | 2022-03-28 | 2022-03-29 |  |  |  | 26596.25 | 4076 | 0 | STANDARD | Koncar - Switchgear Inc. | EUR | 26594.19 | APPROVED |  |  | 2022-04-14 | 2.06 | 16 | Babic, Marian | -44649 | 16
| ORA-01403: no data found | 577 | Equipment Maintenance - second part | APPROVED | No | 2022-03-23 | Abas, Mohammed Fekry | 2022-03-24 | 2022-03-24 |  |  |  | 60000 | 4057 | 0 | STANDARD | SAWARY Trading and Contracting | SAR | 60000 | APPROVED |  |  | 2022-03-31 | 0 | 7 | Abuhammad, Samir | -44644 | 7
10529110001 | Dammam Port (DSP-0038) | 578 | Manlift for DDP | RETURNED | No | 2022-03-24 | Abuhammad, Samir | 2022-03-28 | 2022-03-27 | 2022-03-28 |  | The project changed to site petty cash. | 8000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44647 | -44647
10521300005 | Modon (TD-0034/HV-1294) | 582 | Transformer Oil Sampling-Modon Asfan | APPROVED | No | 2022-03-27 | Abas, Mohammed Fekry | 2022-03-27 | 2022-03-27 |  |  |  | 40000 | 4063 | 0 | STANDARD | MAMDOH BAKHET AL HARBI EST | SAR | 33000 | APPROVED |  |  | 2022-03-30 | 7000 | 3 | Babic, Marian | -44647 | 3
10521300005 | Modon (TD-0034/HV-1294) | 584 | Cable for Security System - Outdoor | APPROVED | No | 2022-03-28 | Abas, Mohammed Fekry | 2022-03-30 | 2022-04-03 |  |  |  | 11720 | 4072 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 11720 | APPROVED |  |  | 2022-04-06 | 0 | 3 | Babic, Marian | -44654 | 3
10521300010 | Rehabilitation of NAF SS (TD-0040) | 585 | Bonding Cables - NAF | APPROVED | No | 2022-03-30 | Abas, Mohammed Fekry | 2022-04-07 | 2022-04-10 |  |  |  | 37500 | 4096 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 34519.25 | APPROVED |  |  | 2022-04-26 | 2980.75 | 16 | Babic, Marian | -44661 | 16
10531109999 | Trading - Job Orders | 586 | Supply of 132kV CTs for Housing Project M.O.D. Jizan | APPROVED | No | 2022-03-30 | Abas, Mohammed Fekry | 2022-03-31 | 2022-04-03 |  |  |  | 404073 | 4078 | 0 | STANDARD | KONCAR INSTRUMENT TRANSFORMERS | EUR | 404073 | APPROVED |  |  | 2022-04-17 | 0 | 14 | Babic, Marian | -44654 | 14
10521300010 | Rehabilitation of NAF SS (TD-0040) | 589 | Link Box TPI - NAF | APPROVED | No | 2022-04-06 | Abas, Mohammed Fekry | 2022-04-11 | 2022-04-12 |  |  |  | 1800 | 4084 | 0 | STANDARD | Atlas Support and Services | SAR | 1700 | APPROVED |  |  | 2022-04-20 | 100 | 8 | Babic, Marian | -44663 | 8
10521300010 | Rehabilitation of NAF SS (TD-0040) | 590 | GIS CT TPI - NAF | APPROVED | No | 2022-04-06 | Abas, Mohammed Fekry | 2022-04-12 | 2022-04-12 |  |  |  | 7500 | 4085 | 0 | STANDARD | SGS GULF LIMITED | USD | 7500 | APPROVED |  |  | 2022-04-20 | 0 | 8 | Babic, Marian | -44663 | 8
10521300010 | Rehabilitation of NAF SS (TD-0040) | 594 | Cable Clamps - NAF | APPROVED | No | 2022-04-07 | Abas, Mohammed Fekry | 2022-04-11 | 2022-04-12 |  |  |  | 44380 | 4109 | 0 | STANDARD | POWER TRANSMISSION & TELECOM. EQUIPMENTS FACTORY CO | SAR | 41273.4 | APPROVED |  |  | 2022-05-16 | 3106.6 | 34 | Babic, Marian | -44663 | 34
10522309999 | Infrastructure and Security Projects - Job Orders | 595 | UPS for KACND | APPROVED | No | 2022-04-10 | Abas, Mohammed Fekry | 2022-04-13 | 2022-04-14 |  |  |  | 25840 | 4092 | 0 | STANDARD | MEJDAF TRADING COMPANY | SAR | 25840 | APPROVED |  |  | 2022-04-26 | 0 | 12 | Abuhammad, Samir | -44665 | 12
10522300003 | ITC- MOH Project-PO#13916 NTT-147 | 600 | Change order for PO#3782 | REJECTED | No | 2022-04-17 | Abseh, Qusai Khaled Mohammad | 2023-01-04 | 2022-04-17 |  |  |  | 54720 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -44668 | -44668
10521300010 | Rehabilitation of NAF SS (TD-0040) | 605 | HV termination Kit- NAF | APPROVED | No | 2022-04-20 | Abas, Mohammed Fekry | 2022-04-25 | 2022-04-28 |  |  |  | 5643 | 4065 | 0 | STANDARD | Brugg Kable AG | USD | 5568.75 | APPROVED |  |  | 2022-05-17 | 74.25 | 19 | Abuhammad, Samir | -44679 | 19
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 606 | RBG-1 FAT test for protection panels | APPROVED | No | 2022-04-20 | Abas, Mohammed Fekry | 2022-04-25 | 2022-04-28 |  |  |  | 1700 | 4106 | 0 | STANDARD | Atlas Support and Services | SAR | 3400 | APPROVED |  |  | 2022-05-16 | -1700 | 18 | Babic, Marian | -44679 | 18
| ORA-01403: no data found | 608 | Construction work for new archive room | APPROVED | No | 2022-04-24 | Abas, Mohammed Fekry | 2022-04-24 | 2022-04-24 |  |  |  | 200000 | 4099 | 0 | STANDARD | NAMA Wittwer Company for General Contracting | SAR | 135014.5 | APPROVED |  |  | 2022-10-20 | 64985.5 | 179 | Abuhammad, Samir | -44675 | 179
| ORA-01403: no data found | 609 | ARCHIVE SHELVES | APPROVED | No | 2022-04-24 | Abas, Mohammed Fekry | 2022-04-24 | 2022-04-24 |  |  |  | 162600 | 4098 | 0 | STANDARD | ARCOMA ARABIA COMMERCIAL AGENCY CO. LTD. | SAR | 157000 | APPROVED |  |  | 2022-05-10 | 5600 | 16 | Abuhammad, Samir | -44675 | 16
10521100011 | Energy Savings Performance-MOJ | 612 | FLUKE Meters | APPROVED | No | 2022-04-25 | Abas, Mohammed Fekry | 2022-05-10 | 2022-05-11 |  |  |  | 50810 | 4113 | 0 | STANDARD | Arab Engineers for Trading company limited | SAR | 50810 | APPROVED |  |  | 2022-05-31 | 0 | 20 | Abuhammad, Samir | -44692 | 20
10521300010 | Rehabilitation of NAF SS (TD-0040) | 613 | Installation - NAF | APPROVED | No | 2022-04-26 | Abas, Mohammed Fekry | 2022-05-12 | 2022-05-15 |  |  |  | 810000 | 4125 | 0 | STANDARD | MASEERAT AL NAMA CONT.EST. | SAR | 785000 | APPROVED |  |  | 2022-06-19 | 25000 | 35 | Babic, Marian | -44696 | 35
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 614 | FAT test for control panels -RBG1 | RETURNED | No | 2022-04-26 | Babic, Marian | 2024-03-26 | 2022-05-11 | 2024-03-26 |  | old PR, not required | 3400 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44692 | -44692
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 615 | FAT test for OHTC - RBG1 | APPROVED | No | 2022-04-26 | Abas, Mohammed Fekry | 2022-05-10 | 2022-05-11 |  |  |  | 3400 | 4108 | 0 | STANDARD | ARAB INSPECTION & Q.A.CO. | SAR | 1400 | APPROVED |  |  | 2022-05-16 | 2000 | 5 | Babic, Marian | -44692 | 5
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 616 | FAT test for LCC -RBG1 | APPROVED | No | 2022-04-26 | Abas, Mohammed Fekry | 2022-05-10 | 2022-05-11 |  |  |  | 2000 | 4243 | 0 | STANDARD | ARAB INSPECTION & Q.A.CO. | SAR | 800 | APPROVED |  |  | 2022-10-03 | 1200 | 145 | Babic, Marian | -44692 | 145
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 617 | FAT test for GIS - RBG1 | APPROVED | No | 2022-04-26 | Abas, Mohammed Fekry | 2022-05-10 | 2022-05-11 |  |  |  | 3400 | 4243 | 0 | STANDARD | ARAB INSPECTION & Q.A.CO. | SAR | 3400 | APPROVED |  |  | 2022-10-03 | 0 | 145 | Babic, Marian | -44692 | 145
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 618 | FAT test for PACU - RBG1 | APPROVED | No | 2022-04-26 | Abas, Mohammed Fekry | 2022-05-10 | 2022-05-11 |  |  |  | 2000 | 4217 | 0 | STANDARD | ARAB INSPECTION & Q.A.CO. | SAR | 1400 | APPROVED |  |  | 2022-09-08 | 600 | 120 | Babic, Marian | -44692 | 120
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 619 | FAT test for DDC - RBG1 | APPROVED | No | 2022-04-26 | Abas, Mohammed Fekry | 2022-05-10 | 2022-05-11 |  |  |  | 2000 | 4197 | 0 | STANDARD | ARAB INSPECTION & Q.A.CO. | SAR | 1400 | APPROVED |  |  | 2022-08-30 | 600 | 111 | Babic, Marian | -44692 | 111
10521300010 | Rehabilitation of NAF SS (TD-0040) | 620 | MV LUGS - NAF | APPROVED | No | 2022-04-26 | Abas, Mohammed Fekry | 2022-05-10 | 2022-05-11 |  |  |  | 16000 | 4114 | 1 | STANDARD | MOHAMMAD RASHID SARWAR EST. | SAR | 13215 | APPROVED |  |  | 2022-10-10 | 2785 | 152 | Babic, Marian | -44692 | 152
10521300010 | Rehabilitation of NAF SS (TD-0040) | 620 | MV LUGS - NAF | APPROVED | No | 2022-04-26 | Abas, Mohammed Fekry | 2022-05-10 | 2022-05-11 |  |  |  | 17000 | 4114 | 0 | STANDARD | MOHAMMAD RASHID SARWAR EST. | SAR | 16561 | APPROVED |  |  | 2022-05-25 | 439 | 14 | Babic, Marian | -44692 | 14
10521200006 | Overhead Gantry with Data Sensors- NEOM | 625 | Neom - Gantry - | RETURNED | No | 2022-04-27 | Abuhammad, Samir | 2023-08-24 | 2022-05-10 | 2023-08-24 | 2022-04-27 | Due to cahnge the budget based on the change requirments. | 640000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44691 | -44691
10521300010 | Rehabilitation of NAF SS (TD-0040) | 631 | Protection TPI - NAF | APPROVED | No | 2022-05-08 | Abas, Mohammed Fekry | 2022-05-11 | 2022-05-11 |  |  |  | 2520 | 4049 | 1 | STANDARD | INTERTEK SAUDI ARABIA LTD | SAR | 2520 | APPROVED |  |  | 2022-05-16 | 0 | 5 | Babic, Marian | -44692 | 5
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 637 | Cloudera Professional Services for SDAIA | APPROVED | No | 2022-05-11 | Abas, Mohammed Fekry | 2022-05-16 | 2022-05-16 |  |  |  | 246845.88 | 4111 | 0 | STANDARD | Starlink MDMC Arabian Trading Co | SAR | 246836 | APPROVED |  |  | 2022-06-22 | 9.88 | 37 | Abuhammad, Samir | -44697 | 37
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 641 | MV Cable 3X300mm2 | APPROVED | No | 2022-05-17 | Abas, Mohammed Fekry | 2022-06-13 | 2022-06-15 |  | 2022-05-17 |  | 143250 | 4150 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 142879.95 | APPROVED |  |  | 2022-07-04 | 370.05 | 19 | Babic, Marian | -44727 | 19
10522309999 | Infrastructure and Security Projects - Job Orders | 648 | SmartNet for KACND | APPROVED | No | 2022-05-22 | Abas, Mohammed Fekry | 2022-05-23 | 2022-05-23 |  |  |  | 24278.51 | 4123 | 0 | STANDARD | Westcon Saudi Company | SAR | 22953 | APPROVED |  |  | 2022-06-05 | 1325.51 | 13 | Abuhammad, Samir | -44704 | 13
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 658 | JEC-Termination Materials | REJECTED | No | 2022-05-30 | Chughtai, Sameer | 2022-06-26 | 2022-06-07 |  | 2022-06-27 |  | 55000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -44719 | -44719
10521300010 | Rehabilitation of NAF SS (TD-0040) | 666 | GIS CT TPI (Change order 4085-HV1317-0) - NAF | APPROVED | No | 2022-06-01 | Abas, Mohammed Fekry | 2022-06-05 | 2022-06-07 |  |  |  | 3750 | 4085 | 1 | STANDARD | SGS GULF LIMITED | USD | 3750 | APPROVED |  |  | 2022-06-12 | 0 | 5 | Babic, Marian | -44719 | 5
10521300010 | Rehabilitation of NAF SS (TD-0040) | 667 | Control Panels TPI - NAF | APPROVED | No | 2022-06-01 | Abas, Mohammed Fekry | 2022-06-05 | 2022-06-07 |  |  |  | 4200 | 4133 | 0 | STANDARD | ARAB INSPECTION & Q.A.CO. | SAR | 4200 | APPROVED |  |  | 2022-06-12 | 0 | 5 | Babic, Marian | -44719 | 5
10521300010 | Rehabilitation of NAF SS (TD-0040) | 668 | Fiber Cables- NAF | APPROVED | No | 2022-06-01 | Abas, Mohammed Fekry | 2022-06-05 | 2022-06-07 |  |  |  | 173500 | 4137 | 0 | STANDARD | SMART TECH | SAR | 165000 | APPROVED |  |  | 2022-06-22 | 8500 | 15 | Babic, Marian | -44719 | 15
| ORA-01403: no data found | 672 | Cameras for NESMA HO in Jeddah | RETURNED | No | 2022-06-02 | Babic, Marian | 2024-04-15 | 2022-06-02 | 2024-04-15 |  | very old PR, hence returned | 43360 | 4139 | 0 | STANDARD | Simat INT. Security EST. | SAR | 32520 | APPROVED |  |  | 2022-06-14 | 10840 |  | Babic, Marian | -44714 | 12
| ORA-01403: no data found | 672 | Cameras for NESMA HO in Jeddah | RETURNED | No | 2022-06-02 | Babic, Marian | 2024-04-15 | 2022-06-02 | 2024-04-15 |  | very old PR, hence returned | 32375 | 4254 | 0 | STANDARD | Simat INT. Security EST. | SAR | 24281.25 | APPROVED |  |  | 2022-10-19 | 8093.75 |  | Babic, Marian | -44714 | 139
| ORA-01403: no data found | 672 | Cameras for NESMA HO in Jeddah | RETURNED | No | 2022-06-02 | Babic, Marian | 2024-04-15 | 2022-06-02 | 2024-04-15 |  | very old PR, hence returned | 10985 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44714 | -44714
| ORA-01403: no data found | 673 | Nesma Data center installation | APPROVED | No | 2022-06-02 | Badhman, Saeed | 2022-06-02 | 2022-06-02 |  |  |  | 120000 | 4138 | 0 | STANDARD | Smart Technology Contracting | SAR | 98000 | APPROVED |  |  | 2022-06-13 | 22000 | 11 | Babic, Marian | -44714 | 11
10521300005 | Modon (TD-0034/HV-1294) | 682 | Timers and Lockout relays- Modon | RETURNED | No | 2022-06-06 | Babic, Marian | 2023-11-14 | 2022-06-13 | 2023-11-14 |  | no update for a long time | 6766.8 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44725 | -44725
10521300005 | Modon (TD-0034/HV-1294) | 684 | HVAC Airl Balancing test - Modon | APPROVED | No | 2022-06-07 | Abas, Mohammed Fekry | 2022-06-14 | 2022-06-15 |  |  |  | 19500 | 4165 | 0 | STANDARD | Sana Al-Ibtikar Contracting Est | SAR | 19500 | APPROVED |  |  | 2022-08-07 | 0 | 53 | Babic, Marian | -44727 | 53
10521300005 | Modon (TD-0034/HV-1294) | 684 | HVAC Airl Balancing test - Modon | APPROVED | No | 2022-06-07 | Abas, Mohammed Fekry | 2022-06-14 | 2022-06-15 |  |  |  | 19500 | 4222 | 0 | STANDARD | Al Mutajaddedah Alhaditha for Electrical and Mechanical Works Co. | SAR | 16000 | APPROVED |  |  | 2022-09-14 | 3500 | 91 | Babic, Marian | -44727 | 91
| ORA-01403: no data found | 692 | Equipment Rental | INCOMPLETE | No | [7 empty] | 80000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10531109999 | Trading - Job Orders | 696 | Supply of Communication Material Naval Base Project | APPROVED | No | 2022-06-16 | Abas, Mohammed Fekry | 2022-06-19 | 2022-06-20 |  |  |  | 12520 | 3910 | 2 | STANDARD | Hardware Solutions Builders Co Ltd | SAR | 12520 | APPROVED |  |  | 2022-06-27 | 0 | 7 | Abuhammad, Samir | -44732 | 7
10521300010 | Rehabilitation of NAF SS (TD-0040) | 697 | Substation Furniture | APPROVED | No | 2022-06-20 | Abas, Mohammed Fekry | 2022-06-26 | 2022-06-28 |  |  |  | 15000 | 4155 | 0 | STANDARD | DANAH AL RAYEDA ESTABLISHMENT | SAR | 13175 | APPROVED |  |  | 2022-06-30 | 1825 | 2 | Babic, Marian | -44740 | 2
10521300006 | Arafat 3 S/S (TD-0037) | 699 | Supply of Indopol oil for Outdoor HV Termination consist of 13kg Oil. | APPROVED | No | 2022-06-20 | Abas, Mohammed Fekry | 2022-08-25 | 2022-08-28 |  |  |  | 13000.05 | 4246 | 0 | STANDARD | CIVIL ELECT.PROJECTS CONTG.CO | SAR | 13000 | APPROVED |  |  | 2022-10-19 | 0.05 | 52 | Babic, Marian | -44801 | 52
10521300010 | Rehabilitation of NAF SS (TD-0040) | 700 | HV termination - NAF | APPROVED | No | 2022-06-21 | Abas, Mohammed Fekry | 2022-06-26 | 2022-06-28 |  |  |  | 116077.5 | 4287 | 0 | STANDARD | BRUGG CABLES COMAPNY | SAR | 112500 | APPROVED |  |  | 2022-12-13 | 3577.5 | 168 | Babic, Marian | -44740 | 168
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 701 | JEC Termination Materials | APPROVED | No | 2022-06-21 | Abas, Mohammed Fekry | 2022-06-28 | 2022-07-07 |  |  |  | 55000 | 4163 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 34806 | APPROVED |  |  | 2022-08-07 | 20194 | 31 | Babic, Marian | -44749 | 31
10521200006 | Overhead Gantry with Data Sensors- NEOM | 706 | Neom- Gantry | REJECTED | No | 2022-06-23 | Mraish, Fahed Mhd Yaser | 2022-09-11 | 2022-06-26 |  |  |  | 2240000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -44738 | -44738
| ORA-01403: no data found | 707 | Change order on civil, mechanical and electricl work for Nesm new office | RETURNED | No | 2022-06-23 | Babic, Marian | 2022-07-20 | 2022-06-23 | 2022-07-20 |  | It was replaced with PR 729 with higher value | 500000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44735 | -44735
10521300005 | Modon (TD-0034/HV-1294) | 708 | Fire Detectors - Modon Asfan | APPROVED | No | 2022-06-26 | Abas, Mohammed Fekry | 2022-06-30 | 2022-07-07 |  | 2022-06-28 |  | 17999.76 | 4164 | 0 | STANDARD | Nukhba Aletfa EST. | SAR | 13370 | APPROVED |  |  | 2022-10-03 | 4629.76 | 88 | Babic, Marian | -44749 | 88
10511000004 | Energy & Communication Operation Overhead | 709 | Montioring system FOR PMAH, IGH an KFNCCC in NESMA Office | APPROVED | No | 2022-06-26 | Abas, Mohammed Fekry | 2022-06-29 | 2022-07-03 |  |  |  | 185954 | 4181 | 0 | STANDARD | Smart Controls Systems Contracting Est. | SAR | 174383 | APPROVED |  |  | 2022-09-12 | 11571 | 71 | Abuhammad, Samir | -44745 | 71
10521300010 | Rehabilitation of NAF SS (TD-0040) | 714 | Generator Rental - NAF | APPROVED | No | 2022-06-29 | Abas, Mohammed Fekry | 2022-06-30 | 2022-06-30 |  |  |  | 28000 | 4162 | 0 | STANDARD | Deyar United Advance Contracting Company | SAR | 28000 | APPROVED |  |  | 2022-07-18 | 0 | 18 | Abuhammad, Samir | -44742 | 18
10521300006 | Arafat 3 S/S (TD-0037) | 717 | 185mmsq Tinned bare copper conductor | APPROVED | No | 2022-06-30 | Abas, Mohammed Fekry | 2022-08-30 | 2022-08-30 |  |  |  | 47500 | 4229 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 28140.14 | APPROVED |  |  | 2022-09-25 | 19359.86 | 26 | Babic, Marian | -44803 | 26
10521300010 | Rehabilitation of NAF SS (TD-0040) | 719 | Battery Charger TPI (Change order) - NAF | APPROVED | No | 2022-07-03 | Abas, Mohammed Fekry | 2022-07-07 | 2022-07-14 |  | 2022-07-03 |  | 2850 | 4115 | 1 | STANDARD | SGS GULF LIMITED | USD | 2437.5 | APPROVED |  |  | 2022-07-20 | 412.5 | 6 | Babic, Marian | -44756 | 6
10521300006 | Arafat 3 S/S (TD-0037) | 720 | Fire detectors & sensor | APPROVED | No | 2022-07-03 | Abas, Mohammed Fekry | 2022-07-07 | 2022-07-14 |  |  |  | 16630 | 4238 | 0 | STANDARD | Nukhba Aletfa EST. | SAR | 12365 | APPROVED |  |  | 2022-10-03 | 4265 | 81 | Babic, Marian | -44756 | 81
| ORA-01403: no data found | 729 | Change Order on civil, mechanical and electrical work for Nesma new office | APPROVED | No | 2022-07-07 | Badhman, Saeed | 2022-07-07 | 2022-07-07 |  |  |  | 600000 | 3797 | 1 | STANDARD | Construction Formation | SAR | 564108.24 | APPROVED |  |  | 2022-08-10 | 35891.76 | 34 | Babic, Marian | -44749 | 34
| ORA-01403: no data found | 732 | SUN CONTROL WINDOW FILMS-1 | APPROVED | No | 2022-07-17 | Badhman, Saeed | 2022-07-17 | 2022-07-17 |  |  |  | 10725 | 4046 | 1 | STANDARD | smart daimond Trading Co | SAR | 10725 | APPROVED |  |  | 2022-07-24 | 0 | 7 | Abuhammad, Samir | -44759 | 7
| ORA-01403: no data found | 753 | Project consulting, Design project, Report for Security and Consulting and check each point | APPROVED | No | 2022-08-03 | Abas, Mohammed Fekry | 2022-08-04 | 2022-08-07 |  |  |  | 25000 | 4203 | 0 | STANDARD | JUSOOR For Telecom & IT | SAR | 25000 | APPROVED |  |  | 2022-09-05 | 0 | 29 | Babic, Marian | -44780 | 29
| ORA-01403: no data found | 753 | Project consulting, Design project, Report for Security and Consulting and check each point | APPROVED | No | 2022-08-03 | Abas, Mohammed Fekry | 2022-08-04 | 2022-08-07 |  |  |  | 25000 | 4203 | 1 | STANDARD | JUSOOR For Telecom & IT | SAR | 18750 | APPROVED |  |  | 2024-01-31 | 6250 | 542 | Babic, Marian | -44780 | 542
10521300010 | Rehabilitation of NAF SS (TD-0040) | 759 | Standing AC - NAF | APPROVED | No | 2022-08-14 | Abas, Mohammed Fekry | 2022-08-21 | 2022-08-24 |  |  |  | 56000 | 4259 | 0 | STANDARD | Ahmmed Shar Hafees Almarhabi EST. | SAR | 46200 | APPROVED |  |  | 2022-11-02 | 9800 | 70 | Babic, Marian | -44797 | 70
| ORA-01403: no data found | 760 | Generator Maintenance | APPROVED | No | 2022-08-14 | Abas, Mohammed Fekry | 2022-08-17 | 2022-08-18 |  |  |  | 12000 | 4187 | 0 | STANDARD | HUDA NASER ABDULLAH FADAAQ EST. | SAR | 10070 | APPROVED |  |  | 2022-08-29 | 1930 | 11 | Babic, Marian | -44791 | 11
10529110001 | Dammam Port (DSP-0038) | 761 | Crash Barrier | APPROVED | No | 2022-08-15 | Abas, Mohammed Fekry | 2022-08-25 | 2022-08-28 |  |  |  | 3196517 | 4204 | 0 | STANDARD | Pan Gulf Telecommunications Co Ltd | SAR | 2779580 | APPROVED |  |  | 2022-09-15 | 416937 | 18 | Abuhammad, Samir | -44801 | 18
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 762 | SRF1302-65-TPI For SAS Panels | REJECTED | No | 2022-08-17 | VIKATAKAVI, KISHORE KUMAR | 2022-08-17 |  |  | 2022-08-17 |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 763 | TPI For SAS Panels | INCOMPLETE | No | [7 empty] | 3500 | [5 empty] | 0 |  |  |  |  | 0 |  | VIKATAKAVI, KISHORE KUMAR | 0 | 0
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 764 | SRF1302-77-TPI For SAS Panels | APPROVED | No | 2022-08-17 | Abas, Mohammed Fekry | 2022-08-30 | 2022-09-01 |  |  |  | 3500 | 3843 | 1 | STANDARD | Atlas Support and Services | SAR | 1700 | APPROVED |  |  | 2022-09-14 | 1800 | 13 | Babic, Marian | -44805 | 13
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 765 | SRF1302-78-TPI For ACSE,ACCS Panels | APPROVED | No | 2022-08-17 | Abas, Mohammed Fekry | 2022-08-30 | 2022-09-01 |  |  |  | 5000 | 4216 | 0 | STANDARD | ARAB INSPECTION & Q.A.CO. | SAR | 1400 | APPROVED |  |  | 2022-09-05 | 3600 | 4 | Babic, Marian | -44805 | 4
10522100007 | PSS Out Systems - Phase 2 | 776 | Upgrade outsystems | APPROVED | No | 2022-08-28 | Abas, Mohammed Fekry | 2022-08-30 | 2022-08-30 |  |  |  | 84350 | 4215 | 0 | STANDARD | JADARA Solutions for Information Technology Compayny | SAR | 84350 | APPROVED |  |  | 2022-09-07 | 0 | 8 | Abuhammad, Samir | -44803 | 8
10521300010 | Rehabilitation of NAF SS (TD-0040) | 786 | Firestop Coating - NAF | APPROVED | No | 2022-09-04 | Abas, Mohammed Fekry | 2022-09-05 | 2022-09-06 |  |  |  | 18000 | 4234 | 0 | STANDARD | HILTI SADUI ARABIA | SAR | 16095 | APPROVED |  |  | 2022-09-25 | 1905 | 19 | Babic, Marian | -44810 | 19
10529110001 | Dammam Port (DSP-0038) | 788 | Substations Name Plates | APPROVED | No | 2022-09-05 | Abas, Mohammed Fekry | 2022-09-07 | 2022-09-13 |  |  |  | 39000.18 | 4233 | 0 | STANDARD | Modern Al-Fouad Printing Press | SAR | 29500 | APPROVED |  |  | 2022-10-11 | 9500.18 | 28 | Abuhammad, Samir | -44817 | 28
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 789 | SRF1302-79-High Voltage Test for GIS | APPROVED | No | 2022-09-05 | Abas, Mohammed Fekry | 2022-09-08 | 2022-09-13 |  |  |  | 90000 | 4272 | 0 | STANDARD | CIVIL ELECT.PROJECTS CONTG.CO | SAR | 69000 | APPROVED |  |  | 2022-11-23 | 21000 | 71 | Babic, Marian | -44817 | 71
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 792 | RENTAL GENERATOR | APPROVED | No | 2022-09-06 | Abas, Mohammed Fekry | 2022-09-08 | 2022-09-13 |  |  |  | 9800 | 4231 | 0 | STANDARD | HUDA NASER ABDULLAH FADAAQ EST. | SAR | 8500 | APPROVED |  |  | 2022-09-19 | 1300 | 6 | Babic, Marian | -44817 | 6
| ORA-01403: no data found | 794 | Dilo Machine Maintenance | APPROVED | No | 2022-09-07 | Abas, Mohammed Fekry | 2022-09-15 | 2022-09-15 | 2022-09-12 |  | Needs to be revised based on new offer received from vendor | 60866 | 4244 | 0 | STANDARD | GULF EXPERTS COMPANY LIMITED | SAR | 60866 | APPROVED |  |  | 2022-10-20 | 0 | 35 | Babic, Marian | -44819 | 35
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 808 | TPI for MV terimnation kit | APPROVED | No | 2022-09-07 | Abas, Mohammed Fekry | 2022-09-18 | 2022-09-18 |  |  |  | 8500 | 4237 | 0 | STANDARD | SGS GULF LIMITED | USD | 7893.75 | APPROVED |  |  | 2022-10-02 | 606.25 | 14 | Babic, Marian | -44822 | 14
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 810 | TPI For Remaining SAS Panels | APPROVED | No | 2022-09-08 | Abas, Mohammed Fekry | 2022-09-14 | 2022-09-14 |  |  |  | 5900 | 3926 | 1 | STANDARD | Atlas Support and Services | SAR | 5900 | APPROVED |  |  | 2022-09-19 | 0 | 5 | Babic, Marian | -44818 | 5
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 810 | TPI For Remaining SAS Panels | APPROVED | No | 2022-09-08 | Abas, Mohammed Fekry | 2022-09-14 | 2022-09-14 |  |  |  | 5900 | 3926 | 2 | STANDARD | Atlas Support and Services | SAR | 5900 | REJECTED |  |  |  | 0 |  | Babic, Marian | -44818 | -44818
10521300010 | Rehabilitation of NAF SS (TD-0040) | 817 | Fire Proof Coated Conduits with accessories - NAF | APPROVED | No | 2022-09-11 | Abas, Mohammed Fekry | 2022-09-12 | 2022-09-14 |  |  |  | 9764 | 4251 | 0 | STANDARD | NEW VICTORY ELECTRICALS CO. LTD | SAR | 8080 | APPROVED |  |  | 2022-10-17 | 1684 | 33 | Babic, Marian | -44818 | 33
10522100002 | Operational Data Processor - RSAF - ODP | 831 | Screens Installations | APPROVED | No | 2022-09-13 | Abas, Mohammed Fekry | 2022-09-14 | 2022-09-15 |  |  |  | 94600 | 4230 | 0 | STANDARD | Dorat AlAsaama Contracting Co. | SAR | 94600 | APPROVED |  |  | 2022-09-25 | 0 | 10 | Abuhammad, Samir | -44819 | 10
10521300010 | Rehabilitation of NAF SS (TD-0040) | 851 | DC DC Converter TPI - NAF | APPROVED | No | 2022-09-25 | Abas, Mohammed Fekry | 2022-10-10 | 2022-10-11 | 2022-10-03 |  | Please increase the amount | 4500 | 4245 | 0 | STANDARD | SGS GULF LIMITED | USD | 4500 | APPROVED |  |  | 2022-10-17 | 0 | 6 | Babic, Marian | -44845 | 6
10521300010 | Rehabilitation of NAF SS (TD-0040) | 852 | MV Lugs - NAF | APPROVED | No | 2022-09-25 | Abas, Mohammed Fekry | 2022-09-29 | 2022-10-02 |  |  |  | 6080 | 4114 | 1 | STANDARD | MOHAMMAD RASHID SARWAR EST. | SAR | 6080 | APPROVED |  |  | 2022-10-10 | 0 | 8 | Babic, Marian | -44836 | 8
10529140008 | Yanbu North S/S (TD-0012/HV-1164) | 856 | Capacitor Bank Testing- Rented Testing engineer | APPROVED | No | 2022-09-29 | Abas, Mohammed Fekry | 2022-10-10 | 2022-10-10 |  |  |  | 20000 | 4257 | 0 | STANDARD | National Excellence For Constrution & Energy co. | SAR | 23875 | APPROVED |  |  | 2022-11-16 | -3875 | 37 | Babic, Marian | -44844 | 37
10531109999 | Trading - Job Orders | 858 | Supply of 380kV CTs for REINFORCEMENT OF JILAH 380kV BSP | APPROVED | No | 2022-10-04 | Abas, Mohammed Fekry | 2022-10-05 | 2022-10-09 |  |  |  | 287040 | 4248 | 0 | STANDARD | KONCAR INSTRUMENT TRANSFORMERS | EUR | 287040 | APPROVED |  |  | 2022-10-20 | 0 | 11 | Babic, Marian | -44843 | 11
10522309999 | Infrastructure and Security Projects - Job Orders | 859 | NGHA-Qassim Project | APPROVED | No | 2022-10-03 | Abas, Mohammed Fekry | 2022-10-04 | 2022-10-04 |  |  |  | 210000 | 4247 | 0 | STANDARD | Fiber way Est. for Communications and Information Technology | SAR | 210000 | APPROVED |  |  | 2022-10-11 | 0 | 7 | Abuhammad, Samir | -44838 | 7
10521300010 | Rehabilitation of NAF SS (TD-0040) | 860 | LV,MV Control Cables (Change order) - NAF | APPROVED | No | 2022-10-03 | Abas, Mohammed Fekry | 2022-10-12 | 2022-10-16 |  |  |  | 1927776.73 | 3949 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 1941443.37 | APPROVED |  |  | 2022-10-25 | -13666.64 | 9 | Babic, Marian | -44850 | 9
10521300010 | Rehabilitation of NAF SS (TD-0040) | 861 | Bondig Cable (Change order) - NAF | APPROVED | No | 2022-10-04 | Abas, Mohammed Fekry | 2022-10-10 | 2022-10-10 |  |  |  | 700 | 4096 | 1 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 35209.64 | APPROVED |  |  | 2022-10-17 | -34509.64 | 7 | Babic, Marian | -44844 | 7
10521300006 | Arafat 3 S/S (TD-0037) | 872 | supply of miscellaneous consuamble materials | REJECTED | No | 2022-10-10 | Ilyas, Mohammed | 2022-10-16 | 2022-10-12 |  |  | Total budget available under the required budget lines is SAR 523,698 ,so this PR will be over budget SAR 6,302 | 530000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -44846 | -44846
10521300010 | Rehabilitation of NAF SS (TD-0040) | 876 | Generator Rental (400KVA) - NAF | APPROVED | No | 2022-10-16 | Abas, Mohammed Fekry | 2022-10-25 | 2022-10-25 |  |  |  | 54000 | 4162 | 1 | STANDARD | Deyar United Advance Contracting Company | SAR | 54000 | APPROVED |  |  | 2022-11-02 | 0 | 8 | Babic, Marian | -44859 | 8
10521300006 | Arafat 3 S/S (TD-0037) | 878 | Supply of Miscellaneous consumable materials | REJECTED | No | 2022-10-16 | Malek, Warren | 2022-10-17 | 2022-10-17 |  | 2022-10-20 |  | 552986 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -44851 | -44851
10521300007 | Bahrain, 66kV Substations (TD-0038/MV-1282) | 879 | Water tank sheds for AMAS projects | APPROVED | No | 2022-10-16 | Abas, Mohammed Fekry | 2022-10-25 | 2022-10-25 |  |  |  | 36000 | 4263 | 0 | STANDARD | PAN FOCUS INTERIOR DECORATIONS CO. W.L.L | BHD | 35820 | APPROVED |  |  | 2022-11-28 | 180 | 34 | Babic, Marian | -44859 | 34
10521300006 | Arafat 3 S/S (TD-0037) | 880 | Supply of Miscellaneous consumable materials | APPROVED | No | 2022-10-17 | Alqahtani, Ms. Sarah Saleh | 2022-10-20 | 2022-10-19 |  |  | "Loop in and out of existing 110KV" line is over the budget by SR 310,000, and the "Ground system" line is over the | 480857.39 | 4340 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 480857.39 | APPROVED |  |  | 2023-02-15 | 0 | 118 | Babic, Marian | -44853 | 119
[12 empty] | budget by SR 223,657, The "Transport & offloading of materials & equipment" is budgeted and the remaining balance is SR | [14 empty] | 0 | 0
[12 empty] | 46498 | [14 empty] | 0 | 0
10531109999 | Trading - Job Orders | 881 | Supply of 380kV CTs for AL-WESSAM BSP #9098 in Riyadh Area- Babtain | APPROVED | No | 2022-10-17 | Abas, Mohammed Fekry | 2022-10-20 | 2022-10-20 |  |  |  | 286746 | 4260 | 0 | STANDARD | KONCAR INSTRUMENT TRANSFORMERS | EUR | 286745.94 | APPROVED |  |  | 2022-11-06 | 0.06 | 17 | Babic, Marian | -44854 | 17
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 894 | RENT FOR GENERATOR | APPROVED | No | 2022-10-26 | Abas, Mohammed Fekry | 2022-11-06 | 2022-11-06 |  |  |  | 58800 | 4231 | 1 | STANDARD | HUDA NASER ABDULLAH FADAAQ EST. | SAR | 35000 | APPROVED |  |  | 2022-11-14 | 23800 | 8 | Babic, Marian | -44871 | 8
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 895 | supervisortion of installing capacitor bank | APPROVED | No | 2022-10-26 | Abas, Mohammed Fekry | 2022-11-06 | 2022-11-06 |  |  |  | 55000 | 4269 | 0 | STANDARD | YASIR M ALI AL-ZAHRANI EST. | SAR | 43500 | APPROVED |  |  | 2022-11-14 | 11500 | 8 | Babic, Marian | -44871 | 8
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 896 | SRF1302-85-Receptacles | RETURNED | No | 2022-10-26 | Babic, Marian | 2022-11-02 | 2022-11-01 | 2022-11-02 |  | It should be item-wise, not as 1 lot | 125000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44866 | -44866
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 897 | Lightning (Mast) | APPROVED | No | 2022-10-26 | Abas, Mohammed Fekry | 2022-11-01 | 2022-11-01 |  |  |  | 81000 | 3809 | 1 | STANDARD | Al-Babtain Power & Telecom | SAR | 10600 | APPROVED |  |  | 2022-11-14 | 70400 | 13 | Babic, Marian | -44866 | 13
10521300010 | Rehabilitation of NAF SS (TD-0040) | 899 | Testing and Commissioning (Change Order) - NAF | RETURNED | No | 2022-10-30 | Babic, Marian | 2022-11-13 | 2022-11-03 | 2022-11-13 |  | The original PO was manual, so this change order is also processed manually | 130000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44868 | -44868
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 900 | OM4 MPO (Unpinned) to MPO | APPROVED | No | 2022-10-31 | Abas, Mohammed Fekry | 2022-11-03 | 2022-11-03 |  |  |  | 105534 | 4268 | 0 | STANDARD | Hardware Solutions Builders Co Ltd | SAR | 100500 | APPROVED |  |  | 2022-11-17 | 5034 | 14 | Abuhammad, Samir | -44868 | 14
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 901 | Supply with Installation of APC Schneider Cabinet with accessories_manual PO8027-NTT110-1 | APPROVED | No | 2022-11-03 | Abas, Mohammed Fekry | 2022-11-07 | 2022-11-07 |  | 2022-11-03 |  | 587975.28 | 4271 | 0 | STANDARD | Emaar Executive for Information Technology | SAR | 587975.28 | APPROVED |  |  | 2022-12-13 | 0 | 36 | Abuhammad, Samir | -44872 | 36
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 902 | Supply with installation of APC Schneider Cabinet with accessories manual PO#8027-NTT110-2 | APPROVED | No | 2022-11-03 | Abas, Mohammed Fekry | 2022-11-07 | 2022-11-07 |  |  |  | 104365 | 4271 | 0 | STANDARD | Emaar Executive for Information Technology | SAR | 104365 | APPROVED |  |  | 2022-12-13 | 0 | 36 | Abuhammad, Samir | -44872 | 36
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 903 | Receptacles | RETURNED | No | 2022-11-09 | Babic, Marian | 2023-07-30 | 2022-11-20 | 2023-07-30 |  | PO issued manually | 103006 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44885 | -44885
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 909 | Supply with installation of commscope cabinet with accessories manual PO8027-NTT110-3 | APPROVED | No | 2022-11-21 | Abas, Mohammed Fekry | 2022-11-28 | 2022-11-29 |  |  |  | 204044 | 4271 | 0 | STANDARD | Emaar Executive for Information Technology | SAR | 210844 | APPROVED |  |  | 2022-12-13 | -6800 | 14 | Abuhammad, Samir | -44894 | 14
| ORA-01403: no data found | 911 | Generator Maintenance | APPROVED | No | 2022-11-15 | Badhman, Saeed | 2022-11-15 | 2022-11-15 |  |  |  | 10000 | 4286 | 0 | STANDARD | Deyar United Advance Contracting Company | SAR | 9200 | APPROVED |  |  | 2022-12-18 | 800 | 33 | Babic, Marian | -44880 | 33
| ORA-01403: no data found | 912 | Generator Maintenance | APPROVED | No | 2022-11-15 | Abas, Mohammed Fekry | 2022-11-22 | 2022-11-22 |  |  |  | 23400 | 4286 | 0 | STANDARD | Deyar United Advance Contracting Company | SAR | 21900 | APPROVED |  |  | 2022-12-18 | 1500 | 26 | Babic, Marian | -44887 | 26
| ORA-01403: no data found | 920 | QEHS Executive Manager Car | RETURNED | No | 2022-11-21 | Babic, Marian | 2022-11-29 | 2022-11-22 | 2022-11-29 |  | As requested | 243760 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44887 | -44887
10521300010 | Rehabilitation of NAF SS (TD-0040) | 922 | DC DC Converter TPI (Change Order) - NAF | APPROVED | No | 2022-11-27 | Abas, Mohammed Fekry | 2022-11-29 | 2022-12-01 |  |  |  | 4650 | 4245 | 1 | STANDARD | SGS GULF LIMITED | USD | 4650 | APPROVED |  |  | 2022-12-07 | 0 | 6 | Babic, Marian | -44896 | 6
10522100007 | PSS Out Systems - Phase 2 | 923 | Outsystem upgrade and Splitting the database of development and test and additional server to production for high availability PO#4215-NTT23-0 | APPROVED | No | 2022-11-27 | Abas, Mohammed Fekry | 2023-01-31 | 2023-02-01 |  |  |  | 56000 | 4215 | 1 | STANDARD | JADARA Solutions for Information Technology Compayny | SAR | 56000 | APPROVED |  |  | 2023-02-14 | 0 | 13 | Abuhammad, Samir | -44958 | 13
10531100005 | Supply of 380kV CTs for Construction of New AFIF 9081 S/S. | 933 | Supply of 380kV CTs for Construction of New AFIF 9081 S/S | APPROVED | No | 2022-12-05 | Abas, Mohammed Fekry | 2022-12-05 | 2022-12-06 |  |  |  | 979667.82 | 4289 | 0 | STANDARD | KONCAR INSTRUMENT TRANSFORMERS | EUR | 979667.82 | APPROVED |  |  | 2022-12-13 | 0 | 7 | Babic, Marian | -44901 | 7
10521300010 | Rehabilitation of NAF SS (TD-0040) | 934 | Fiber Optics Cables | APPROVED | No | 2022-12-05 | Abas, Mohammed Fekry | 2022-12-11 | 2022-12-12 |  |  |  | 50000 | 4137 | 1 | STANDARD | SMART TECH | SAR | 66500 | APPROVED |  |  | 2023-01-01 | -16500 | 20 | Babic, Marian | -44907 | 20
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 935 | TPI for MV CABLES | APPROVED | No | 2022-12-05 | Abas, Mohammed Fekry | 2022-12-06 | 2022-12-06 |  |  |  | 10000 | 4290 | 0 | STANDARD | INTERTEK SAUDI ARABIA LTD | SAR | 5000 | APPROVED |  |  | 2022-12-11 | 5000 | 5 | Babic, Marian | -44901 | 5
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 936 | Change order in Civil PO PREMCO PCC FENCE | APPROVED | No | 2022-12-05 | Abas, Mohammed Fekry | 2022-12-06 | 2022-12-06 |  |  |  | 130000 | 4100 | 1 | STANDARD | Precast Manufacturing Company (PREMCO) | SAR | 121221 | APPROVED |  |  | 2022-12-13 | 8779 | 7 | Abuhammad, Samir | -44901 | 7
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 945 | Lighting Fixture - Rabigh | APPROVED | No | 2022-12-07 | Abas, Mohammed Fekry | 2022-12-15 | 2022-12-18 |  |  |  | 13725 | 4298 | 0 | STANDARD | Al-Raed Al-Arabi Industry Trading & Contracting Co.Ltd | SAR | 13725 | APPROVED |  |  | 2022-12-28 | 0 | 10 | Babic, Marian | -44913 | 10
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 946 | supply commscope MPO cable | REJECTED | No | 2022-12-22 | Gaber, Mr. Ahmad | 2022-12-22 |  |  | 2022-12-22 |  | 56280 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 948 | Supply of Google Workspace appications | APPROVED | No | 2022-12-08 | Abas, Mohammed Fekry | 2022-12-08 | 2022-12-08 |  |  |  | 32400 | 3823 | 1 | STANDARD | Invent Solutions | SAR | 32400 | APPROVED |  |  | 2022-12-13 | 0 | 5 | Abuhammad, Samir | -44903 | 5
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 951 | PUSH BUTTON & SWITCHES FOR NORMAL LIGHTING | RETURNED | No | 2022-12-13 | Babic, Marian | 2023-07-30 | 2022-12-18 | 2023-07-30 |  | PO issued manually | 7147 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44913 | -44913
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 952 | Jira software License Renewal | APPROVED | No | 2022-12-20 | Abas, Mohammed Fekry | 2022-12-21 | 2022-12-22 |  |  |  | 417266 | 4304 | 0 | STANDARD | Atlassian Pty Ltd | SAR | 361875 | APPROVED |  |  | 2023-02-07 | 55391 | 47 | Abuhammad, Samir | -44917 | 47
10521300007 | Bahrain, 66kV Substations (TD-0038/MV-1282) | 953 | Main access and bus bay interlock & kerb stone works ABU SUBH SS | RETURNED | No | 2022-12-21 | Babic, Marian | 2022-12-22 | 2022-12-22 | 2022-12-22 |  | 46773.08 should be in BD, instead of SAR | 46773.08 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -44917 | -44917
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 954 | Supply of commscope MPO | APPROVED | No | 2022-12-22 | Abas, Mohammed Fekry | 2022-12-29 | 2023-01-02 |  |  |  | 56280 | 4268 | 1 | STANDARD | Hardware Solutions Builders Co Ltd | SAR | 56280 | APPROVED |  |  | 2023-01-23 | 0 | 21 | Abuhammad, Samir | -44928 | 21
10521300007 | Bahrain, 66kV Substations (TD-0038/MV-1282) | 955 | Main Acess & Bus Bay Interlock & Kerb stone works- Abu Subh SS | APPROVED | No | 2022-12-24 | Abas, Mohammed Fekry | 2022-12-27 | 2022-12-28 |  |  |  | 467730.75 | 4041 | 3 | STANDARD | Interlock Maintenance construction WLL | BHD | 467730.75 | APPROVED |  |  | 2023-01-16 | 0 | 19 | Babic, Marian | -44923 | 19
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 957 | tinned copper conductor | APPROVED | No | 2022-12-25 | Abas, Mohammed Fekry | 2022-12-26 | 2022-12-28 |  |  |  | 105000 | 4306 | 0 | STANDARD | AL MOUSA SPECIALIZED CABLES | SAR | 74376 | APPROVED |  |  | 2023-01-04 | 30624 | 7 | Babic, Marian | -44923 | 7
10521300017 | CONSTRUCTION OF NEW 132/33kV NIC NORTH (NIC NR) S/S & NIC EV2 S/S. | 964 | High Voltage 132kV GIS | APPROVED | No | 2023-01-02 | Abas, Mohammed Fekry | 2023-01-10 | 2023-01-15 |  |  |  | 31781250 | 4508 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 31781250 | APPROVED |  |  | 2023-06-20 | 0 | 156 | Kumar, Mr. Ranjan | -44941 | 156
10521300017 | CONSTRUCTION OF NEW 132/33kV NIC NORTH (NIC NR) S/S & NIC EV2 S/S. | 964 | High Voltage 132kV GIS | APPROVED | No | 2023-01-02 | Abas, Mohammed Fekry | 2023-01-10 | 2023-01-15 |  |  |  | 31781250 | 4508 | 1 | STANDARD | Hitachi Energy Ltd | SAR | 0 | APPROVED |  |  | 2024-04-03 | 31781250 | 444 | Kumar, Mr. Ranjan | -44941 | 444
10521300017 | CONSTRUCTION OF NEW 132/33kV NIC NORTH (NIC NR) S/S & NIC EV2 S/S. | 964 | High Voltage 132kV GIS | APPROVED | No | 2023-01-02 | Abas, Mohammed Fekry | 2023-01-10 | 2023-01-15 |  |  |  | 30093750 | 4509 | 0 | STANDARD | Hitachi Energy Ltd | SAR | 30093750 | APPROVED |  |  | 2023-06-20 | 0 | 156 | Kumar, Mr. Ranjan | -44941 | 156
10521300017 | CONSTRUCTION OF NEW 132/33kV NIC NORTH (NIC NR) S/S & NIC EV2 S/S. | 964 | High Voltage 132kV GIS | APPROVED | No | 2023-01-02 | Abas, Mohammed Fekry | 2023-01-10 | 2023-01-15 |  |  |  | 30093750 | 4509 | 1 | STANDARD | Hitachi Energy Ltd | SAR | 0 | APPROVED |  |  | 2024-04-02 | 30093750 | 443 | Kumar, Mr. Ranjan | -44941 | 443
| ORA-01403: no data found | 976 | Biometric System | APPROVED | No | 2023-01-05 | Abas, Mohammed Fekry | 2023-01-15 | 2023-01-16 |  |  |  | 2330 | 3913 | 2 | STANDARD | Advance International Company | SAR | 2330 | APPROVED |  |  | 2023-01-30 | 0 | 14 | Abuhammad, Samir | -44942 | 14
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 982 | SAS PANELS FAT | APPROVED | No | 2023-01-03 | Abas, Mohammed Fekry | 2023-01-08 | 2023-01-09 |  |  |  | 4800 | 4341 | 0 | STANDARD | Atlas Support and Services | SAR | 2000 | APPROVED |  |  | 2023-03-07 | 2800 | 57 | Babic, Marian | -44935 | 57
10521300010 | Rehabilitation of NAF SS (TD-0040) | 984 | TPI (AC,DC&Lighting Panels), | APPROVED | No | 2023-01-04 | Abas, Mohammed Fekry | 2023-01-05 | 2023-01-09 |  |  |  | 9225 | 4311 | 0 | STANDARD | SGS GULF LIMITED | USD | 9225 | APPROVED |  |  | 2023-01-15 | 0 | 6 | Babic, Marian | -44935 | 6
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 992 | Supply of Auxi applications | APPROVED | No | 2023-01-05 | Abas, Mohammed Fekry | 2023-01-16 | 2023-01-16 |  |  |  | 326250 | 4322 | 0 | STANDARD | Auxi Inc. | USD | 326250 | APPROVED |  |  | 2023-03-01 | 0 | 44 | Abuhammad, Samir | -44942 | 44
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 1005 | Civil work | APPROVED | No | 2023-01-18 | Abas, Mohammed Fekry | 2023-01-22 | 2023-01-22 |  |  |  | 2625000 | 4327 | 0 | STANDARD | Zone Advertising for Contracting | SAR | 2625000 | APPROVED |  |  | 2023-02-05 | 0 | 14 | Babic, Marian | -44948 | 14
| ORA-01403: no data found | 1007 | Fortigate Firewall License | APPROVED | No | 2023-01-19 | Abas, Mohammed Fekry | 2023-01-22 | 2023-01-22 |  |  |  | 10350 | 4325 | 0 | STANDARD | Exclusive Networks For Information Systems Technology | SAR | 10350 | APPROVED |  |  | 2023-01-25 | 0 | 3 | Abuhammad, Samir | -44948 | 3
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 1024 | LV cables 500 Single Core | APPROVED | No | 2023-01-28 | Abas, Mohammed Fekry | 2023-02-02 | 2023-02-02 |  |  |  | 380640 | 4336 | 0 | STANDARD | AL-ITQAN AL-NAMUZAJI TRADING EST. | SAR | 380640 | APPROVED |  |  | 2023-02-26 | 0 | 24 | Babic, Marian | -44959 | 24
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 1025 | Zif Relay MV SWGR | APPROVED | No | 2023-01-28 | Abas, Mohammed Fekry | 2023-02-02 | 2023-02-02 |  |  |  | 3000 | 4339 | 0 | STANDARD | ALFANAR CO | SAR | 3000 | APPROVED |  |  | 2023-02-13 | 0 | 11 | Babic, Marian | -44959 | 11
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 1043 | fireproof material | REJECTED | No | 2023-02-05 | Ibrahim, Mr. Ahmed Abdulkadir | 2023-02-05 |  |  | 2023-02-06 |  | 129804 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 1047 | Fire fighting stop materials | APPROVED | No | 2023-02-06 | Abas, Mohammed Fekry | 2023-02-19 | 2023-02-20 |  |  |  | 129804 | 4360 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 85950 | APPROVED |  |  | 2023-03-09 | 43854 | 17 | Babic, Marian | -44977 | 17
| ORA-01403: no data found | 1056 | New Workstation for Jeddah Head office | APPROVED | No | 2023-02-12 | Abas, Mohammed Fekry | 2023-02-21 | 2023-02-21 |  | 2023-02-16 |  | 26600 | 4365 | 0 | STANDARD | MAJESTIC OFFICE FOR FURNITURE | SAR | 26600 | APPROVED |  |  | 2023-03-05 | 0 | 12 | Babic, Marian | -44978 | 12
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 1078 | HP PC's | APPROVED | No | 2023-02-16 | Abas, Mohammed Fekry | 2023-02-19 | 2023-02-20 |  |  |  | 247000 | 4356 | 0 | STANDARD | Fast Computers for Trading Est | SAR | 247000 | APPROVED |  |  | 2023-04-02 | 0 | 41 | Abuhammad, Samir | -44977 | 41
| ORA-01403: no data found | 1088 | New Laptops | APPROVED | No | 2023-02-26 | Abas, Mohammed Fekry | 2023-03-09 | 2023-03-12 |  |  |  | 248000 | 4374 | 0 | STANDARD | APTEC Saudi Arabia LCC | SAR | 235700 | APPROVED |  |  | 2023-03-16 | 12300 | 4 | Abuhammad, Samir | -44997 | 4
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 1089 | Rental Generator | INCOMPLETE | No | [7 empty] | 86000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 1090 | Tinned Copper Conductor | APPROVED | No | 2023-02-28 | Abas, Mohammed Fekry | 2023-03-06 | 2023-03-08 |  |  |  | 33840 | 4380 | 0 | STANDARD | BAHRA ADVANCED CABLE MANUFACTURE CO LTD | SAR | 32571.28 | APPROVED |  |  | 2023-03-21 | 1268.72 | 13 | Babic, Marian | -44993 | 13
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 1091 | Rental Generator | APPROVED | No | 2023-03-01 | Abas, Mohammed Fekry | 2023-03-06 | 2023-03-08 |  |  |  | 86000 | 4376 | 0 | STANDARD | HUDA NASER ABDULLAH FADAAQ EST. | SAR | 26000 | APPROVED |  |  | 2023-04-04 | 60000 | 27 | Babic, Marian | -44993 | 27
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 1098 | Supply of creative cloud apps | RETURNED | No | 2023-03-07 | Abuhammad, Samir | 2023-03-12 | 2023-03-12 | 2023-03-12 |  | As there is no spacific venor, online purchase. | 10800 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44997 | -44997
10529110001 | Dammam Port (DSP-0038) | 1099 | SRF - Cable termination & Joints - DPP | RETURNED | No | 2023-03-06 | Abuhammad, Samir | 2023-03-20 | 2023-03-08 | 2023-03-20 |  | based on PM request. | 102000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -44993 | -44993
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 1106 | Gitlab subscription | IN PROCESS | No | 2023-03-09 | Gaber, Mr. Ahmad | 2023-03-09 | 2023-03-09 |  |  |  | 253575 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -44994 | -44994
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 1112 | MV TERMNATION KIT | APPROVED | No | 2023-03-07 | Abas, Mohammed Fekry | 2023-04-04 | 2023-04-05 |  |  |  | 26500 | 3855 | 1 | STANDARD | Nima Arabia Company Limited | SAR | 23040 | APPROVED |  |  | 2023-04-11 | 3460 | 6 | Babic, Marian | -45021 | 6
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 1114 | Single Cable Cleats | APPROVED | No | 2023-03-07 | Abas, Mohammed Fekry | 2023-03-09 | 2023-03-12 |  |  |  | 55815.39 | 4381 | 0 | STANDARD | ABDULLAH M. AL-SHAHRANI FACTORY | SAR | 55565.21 | APPROVED |  |  | 2023-03-21 | 250.18 | 9 | Babic, Marian | -44997 | 9
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 1116 | Lighting panels and AC Auxiliary Loose materials | APPROVED | No | 2023-03-11 | Abas, Mohammed Fekry | 2023-03-14 | 2023-03-14 |  |  |  | 79590 | 4395 | 0 | STANDARD | ETA-PCS SWITCHGEAR MANUFACTRING LLC | SAR | 79590 | APPROVED |  |  | 2023-04-09 | 0 | 26 | Babic, Marian | -44999 | 26
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 1119 | Gitlab subscription | REJECTED | No | 2023-03-09 | Gaber, Mr. Ahmad | 2023-03-09 |  |  | 2023-03-09 |  | 55040 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 1120 | Supply of Gitlab License | APPROVED | No | 2023-03-09 | Abas, Mohammed Fekry | 2023-03-12 | 2023-03-12 |  |  |  | 206400 | 4042 | 1 | STANDARD | Amazic BV | USD | 206400 | APPROVED |  |  | 2023-03-16 | 0 | 4 | Abuhammad, Samir | -44997 | 4
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 1131 | Recepticals | APPROVED | No | 2023-03-15 | Abas, Mohammed Fekry | 2023-03-28 | 2023-03-30 |  |  |  | 10731.06 | 4409 | 0 | STANDARD | Multilines Electrical and Mechanical Trading | SAR | 10731.06 | APPROVED |  |  | 2023-04-13 | 0 | 14 | Babic, Marian | -45015 | 14
10521300010 | Rehabilitation of NAF SS (TD-0040) | 1133 | 13.8KV Cable Partial Discharge Test at NAF SS | RETURNED | No | 2023-03-15 | Babic, Marian | 2024-04-21 | 2023-03-22 | 2024-04-21 |  | not required | 60000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45007 | -45007
| ORA-01403: no data found | 1134 | Calibration of Instrument (Inside-alfanar Calibration LAB) | APPROVED | No | 2023-03-15 | Abas, Mohammed Fekry | 2023-03-15 | 2023-03-16 |  |  |  | 17950 | 4390 | 0 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 18477.5 | APPROVED |  |  | 2023-03-26 | -527.5 | 10 | Babic, Marian | -45001 | 10
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 1137 | Supply of Creator – License offline activation | APPROVED | No | 2023-03-19 | Abas, Mohammed Fekry | 2023-03-20 | 2023-03-22 |  |  |  | 151000 | 4397 | 0 | STANDARD | Sure Global Tech | SAR | 151000 | APPROVED |  |  | 2023-04-02 | 0 | 11 | Abuhammad, Samir | -45007 | 11
10529110001 | Dammam Port (DSP-0038) | 1140 | Temination & Joint of MV Cable | APPROVED | No | 2023-03-21 | Abas, Mohammed Fekry | 2023-04-19 | 2023-04-30 |  |  |  | 128000 | 4392 | 0 | STANDARD | Hashim Rodini Contracting Est. | SAR | 128000 | APPROVED |  |  | 2023-05-18 | 0 | 18 | Abuhammad, Samir | -45046 | 18
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 1146 | MV termnation kit | APPROVED | No | 2023-03-22 | Abas, Mohammed Fekry | 2023-04-04 | 2023-04-05 |  |  |  | 135400 | 3813 | 1 | STANDARD | MASEERAT AL NAMA CONT.EST. | SAR | 135400 | APPROVED |  |  | 2023-05-18 | 0 | 43 | Babic, Marian | -45021 | 43
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 1150 | Earthing and Sheilding Material | APPROVED | No | 2023-04-06 | Abas, Mohammed Fekry | 2023-04-11 | 2023-04-11 |  |  |  | 25263.47 | 4420 | 0 | STANDARD | SADAF ELECTRIC INDUSTIES CO. | SAR | 23788.39 | APPROVED |  |  | 2023-04-30 | 1475.08 | 19 | Babic, Marian | -45027 | 19
10521300006 | Arafat 3 S/S (TD-0037) | 1153 | Supply of Engineer ( permit receiver) to Open permit at remote end of Arafat-3 | APPROVED | No | 2023-04-03 | Abas, Mohammed Fekry | 2023-04-09 | 2023-04-10 |  |  |  | 10000 | 4510 | 0 | STANDARD | National Excellence For Constrution & Energy co. | SAR | 10000 | APPROVED |  |  | 2023-06-13 | 0 | 64 | Abuhammad, Samir | -45026 | 64
10521300006 | Arafat 3 S/S (TD-0037) | 1156 | final inspection and certification for capacitor bank | APPROVED | No | 2023-04-03 | Abas, Mohammed Fekry | 2023-04-05 | 2023-04-09 |  |  |  | 11500 | 4408 | 0 | STANDARD | YASIR M ALI AL-ZAHRANI EST. | SAR | 11500 | APPROVED |  |  | 2023-04-30 | 0 | 21 | Babic, Marian | -45025 | 21
| ORA-01403: no data found | 1175 | Office Cable Pulling | APPROVED | No | 2023-04-09 | Abas, Mohammed Fekry | 2023-04-09 | 2023-04-10 |  |  |  | 83400 | 4422 | 0 | STANDARD | NAMA Wittwer Company for General Contracting | SAR | 80000 | APPROVED |  |  | 2023-05-18 | 3400 | 38 | Abuhammad, Samir | -45026 | 38
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 1193 | MV Cable Lug | APPROVED | No | 2023-04-13 | Abas, Mohammed Fekry | 2023-04-19 | 2023-04-30 |  |  |  | 33365 | 4441 | 0 | STANDARD |  | SAR | 33425 | INCOMPLETE |  |  |  | -60 | 1008 | Eranhikkal, Mr. Riyaz Mohammed | -45046 | -45046
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 1193 | MV Cable Lug | APPROVED | No | 2023-04-13 | Abas, Mohammed Fekry | 2023-04-19 | 2023-04-30 |  |  |  | 33365 | [5 empty] | 0 |  |  |  |  | 0 |  | Eranhikkal, Mr. Riyaz Mohammed | -45046 | -45046
| ORA-01403: no data found | 1218 | New Laptops | RETURNED | No | 2023-04-30 | Abuhammad, Samir | 2023-05-04 | 2023-04-30 | 2023-05-04 |  | To modify the organization- DFF. | 246675 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45046 | -45046
| ORA-01403: no data found | 1234 | New Laptops | APPROVED | No | 2023-05-07 | Abas, Mohammed Fekry | 2023-05-11 | 2023-05-11 |  |  |  | 246675 | 4427 | 0 | STANDARD | REDINGTON SAUDI ARABIA DISTRIBUTION CO. | SAR | 246675 | APPROVED |  |  | 2023-05-18 | 0 | 7 | Abuhammad, Samir | -45057 | 7
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 1236 | Supply of NVIDIA with services | INCOMPLETE | No | [7 empty] | 1253355 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 1292 | Supply of NVIDIA with software license and services additional items | APPROVED | No | 2023-05-29 | Abas, Mohammed Fekry | 2023-06-05 | 2023-06-06 |  |  |  | 1213355 | 4513 | 0 | STANDARD | Watad Energy & Communications Co | SAR | 1213355 | APPROVED |  |  | 2023-06-20 | 0 | 14 | Abuhammad, Samir | -45083 | 14
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 1294 | TPI for GIS LCC Panels | APPROVED | No | 2023-05-29 | Abas, Mohammed Fekry | 2023-06-05 | 2023-06-05 |  |  |  | 4220 | 4511 | 0 | STANDARD | SGS GULF LIMITED | USD | 3337.5 | APPROVED |  |  | 2023-06-15 | 882.5 | 10 | Babic, Marian | -45082 | 10
10522100006 | MOI Diwan Project | 1297 | Data Center Cabinet shifting & Dressing | APPROVED | No | 2023-05-30 | Abas, Mohammed Fekry | 2023-06-07 | 2023-06-07 |  |  |  | 59560 | 4517 | 0 | STANDARD | ORIENTALS TECHNOLOGY EST. FOR CONTRACTING | SAR | 59560 | APPROVED |  |  | 2023-08-03 | 0 | 57 | Abuhammad, Samir | -45084 | 57
| ORA-01403: no data found | 1304 | Hanger File Addition | APPROVED | No | 2023-06-04 | Abas, Mohammed Fekry | 2023-06-05 | 2023-06-05 |  |  |  | 31668 | 4098 | 1 | STANDARD | ARCOMA ARABIA COMMERCIAL AGENCY CO. LTD. | SAR | 31600 | APPROVED |  |  | 2023-07-16 | 68 | 41 | Abuhammad, Samir | -45082 | 41
10522100006 | MOI Diwan Project | 1309 | Supply of SFP's | APPROVED | No | 2023-06-07 | Abas, Mohammed Fekry | 2023-06-15 | 2023-06-18 |  |  |  | 11800 | 4526 | 0 | STANDARD | Asari Operation and Maintenance | SAR | 9800 | APPROVED |  |  | 2023-07-04 | 2000 | 16 | Abuhammad, Samir | -45095 | 16
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 1314 | Supply of Cisco and Dell PC's&HDD and commscope cables services | APPROVED | No | 2023-06-08 | Abas, Mohammed Fekry | 2023-06-11 | 2023-06-12 |  |  |  | 609094 | 4512 | 0 | STANDARD | Abdulrahman A. Al-Moussa Trading Co.LtD | SAR | 609094 | APPROVED |  |  | 2023-06-21 | 0 | 9 | Abuhammad, Samir | -45089 | 9
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 1314 | Supply of Cisco and Dell PC's&HDD and commscope cables services | APPROVED | No | 2023-06-08 | Abas, Mohammed Fekry | 2023-06-11 | 2023-06-12 |  |  |  | 286080 | 4520 | 0 | STANDARD | Golden Technology trading Company. | SAR | 258200 | APPROVED |  |  | 2023-06-20 | 27880 | 8 | Abuhammad, Samir | -45089 | 8
10522100004 | APSSM - Operation and support of NIC data warehouse appliance | 1314 | Supply of Cisco and Dell PC's&HDD and commscope cables services | APPROVED | No | 2023-06-08 | Abas, Mohammed Fekry | 2023-06-11 | 2023-06-12 |  |  |  | 19335 | 4529 | 0 | STANDARD | Golden Technology trading Company. | SAR | 12860 | APPROVED |  |  | 2023-07-04 | 6475 | 22 | Abuhammad, Samir | -45089 | 22
10529110001 | Dammam Port (DSP-0038) | 1324 | FOC Work | APPROVED | No | 2023-06-19 | Abas, Mohammed Fekry | 2023-06-25 | 2023-06-26 |  |  |  | 27185 | 4581 | 0 | STANDARD | Majal Gulf Company Limited | SAR | 27185 | APPROVED |  |  | 2023-08-30 | 0 | 65 | Abuhammad, Samir | -45103 | 65
| ORA-01403: no data found | 1325 | New Workstation | APPROVED | No | 2023-06-19 | Abas, Mohammed Fekry | 2023-06-20 | 2023-06-20 |  |  |  | 65230 | 4534 | 0 | STANDARD | MAJESTIC OFFICE FOR FURNITURE | SAR | 61968.5 | APPROVED |  |  | 2023-07-12 | 3261.5 | 22 | Kumar, Mr. Ranjan | -45097 | 22
10529110001 | Dammam Port (DSP-0038) | 1334 | SCADA Building Civil work | APPROVED | No | 2023-06-22 | Abas, Mohammed Fekry | 2023-06-25 | 2023-06-26 |  |  |  | 840325 | 4561 | 0 | STANDARD | Sun Rise United Contracting EST | SAR | 831631.4 | APPROVED |  |  | 2023-08-27 | 8693.6 | 62 | Kumar, Mr. Ranjan | -45103 | 62
| ORA-01403: no data found | 1338 | Accommodation Maintenance - Al Rehaily | APPROVED | No | 2023-07-04 | Abas, Mohammed Fekry | 2023-07-09 | 2023-07-09 |  |  |  | 25804.07 | 4539 | 0 | STANDARD | Al Gherbal Building Materials Est | SAR | 25804.07 | APPROVED |  |  | 2023-07-12 | 0 | 3 | Babic, Marian | -45116 | 3
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 1341 | Rental Safety officer | APPROVED | No | 2023-07-05 | Abas, Mohammed Fekry | 2023-07-13 | 2023-07-13 |  |  |  | 79560 | 4557 | 0 | STANDARD | Upcoming Engineering Contracting Co. | SAR | 78650 | APPROVED |  |  | 2023-10-11 | 910 | 90 | Babic, Marian | -45120 | 90
10522100006 | MOI Diwan Project | 1345 | Power BI Resource for MOI Diwan Project | APPROVED | No | 2023-07-09 | Abas, Mohammed Fekry | 2023-07-23 | 2023-07-24 |  |  |  | 140400 | 4560 | 0 | STANDARD | Nesma Injazat Information Technology Company | SAR | 140400 | APPROVED |  |  | 2023-08-20 | 0 | 27 | Abuhammad, Samir | -45131 | 27
10522100006 | MOI Diwan Project | 1346 | Supply & Installation of InterMapper | RETURNED | No | 2023-07-09 | Abuhammad, Samir | 2023-09-05 | 2023-07-24 | 2023-09-05 |  | Due to change the budget | 69660 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45131 | -45131
| ORA-01403: no data found | 1353 | CCTV - Jeddah Accommodation | RETURNED | No | 2023-07-17 | Akhtar, Farhan | 2024-05-06 | 2023-07-19 | 2024-05-06 |  | Reassign Buyer | 10190 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45126 | -45126
| ORA-01403: no data found | 1366 | Generators Maintenance | APPROVED | No | 2023-07-23 | Abas, Mohammed Fekry | 2023-07-23 | 2023-07-24 |  |  |  | 67000 | 4554 | 0 | STANDARD | Deyar United Advance Contracting Company | SAR | 65800 | APPROVED |  |  | 2023-08-01 | 1200 | 8 | Babic, Marian | -45131 | 8
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 1381 | MV CLAMPING AND CLEADS | APPROVED | No | 2023-08-03 | Abas, Mohammed Fekry | 2023-08-20 | 2023-08-21 |  |  |  | 4440 | 4381 | 1 | STANDARD | ABDULLAH M. AL-SHAHRANI FACTORY | SAR | 4440 | APPROVED |  |  | 2023-08-30 | 0 | 9 | Babic, Marian | -45159 | 9
| ORA-01403: no data found | 1383 | CCTV - Jeddah Accommodation A3 | RETURNED | No | 2023-08-06 | Babic, Marian | 2023-11-14 | 2023-08-07 | 2023-11-14 |  | Needs to be modified due to increase of scope | 7380 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45145 | -45145
10521300031 | CONSTRUCTION OF HARAM-3 SS | 1386 | ccccc | INCOMPLETE | No | [6 empty] | Needs to be modified due to increase of scope | 100 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 1387 | Cabel Extension for PO No. 4422 | APPROVED | No | 2023-08-07 | Abas, Mohammed Fekry | 2023-08-07 | 2023-08-08 |  |  |  | 26600 | 4422 | 1 | STANDARD | NAMA Wittwer Company for General Contracting | SAR | 26600 | APPROVED |  |  | 2023-08-20 | 0 | 12 | Abuhammad, Samir | -45146 | 12
10529110001 | Dammam Port (DSP-0038) | 1406 | Cable Testing Services | APPROVED | No | 2023-08-13 | Abas, Mohammed Fekry | 2023-08-27 | 2023-08-27 |  |  |  | 152400 | 4591 | 0 | STANDARD | Expertise Contracting Co. | SAR | 152400 | APPROVED |  |  | 2023-09-11 | 0 | 15 | Abuhammad, Samir | -45165 | 15
10522100006 | MOI Diwan Project | 1432 | MOI Diwan- Passive Work | RETURNED | No | 2023-08-23 | Abuhammad, Samir | 2025-11-13 | 2023-09-10 | 2025-11-13 |  | One site ready you can raise again. | 114160 | 4616 | 0 | STANDARD | ORIENTALS TECHNOLOGY EST. FOR CONTRACTING | SAR | 114160 | APPROVED |  |  | 2023-10-04 | 0 |  | Abuhammad, Samir | -45179 | 24
10522100006 | MOI Diwan Project | 1432 | MOI Diwan- Passive Work | RETURNED | No | 2023-08-23 | Abuhammad, Samir | 2025-11-13 | 2023-09-10 | 2025-11-13 |  | One site ready you can raise again. | 78220 | 4617 | 1 | STANDARD | Frontline Investment Company | SAR | 78220 | APPROVED |  |  | 2024-11-27 | 0 |  | Abuhammad, Samir | -45179 | 444
10522100006 | MOI Diwan Project | 1432 | MOI Diwan- Passive Work | RETURNED | No | 2023-08-23 | Abuhammad, Samir | 2025-11-13 | 2023-09-10 | 2025-11-13 |  | One site ready you can raise again. | 87510 | 4617 | 0 | STANDARD | Frontline Investment Company | SAR | 87510 | APPROVED |  |  | 2023-10-02 | 0 |  | Abuhammad, Samir | -45179 | 22
10522100006 | MOI Diwan Project | 1432 | MOI Diwan- Passive Work | RETURNED | No | 2023-08-23 | Abuhammad, Samir | 2025-11-13 | 2023-09-10 | 2025-11-13 |  | One site ready you can raise again. | 89140 | 5632 | 0 | STANDARD | Nabea Al Gawdah Company | SAR | 89140 | APPROVED |  |  | 2024-06-03 | 0 |  | Abuhammad, Samir | -45179 | 267
10522100006 | MOI Diwan Project | 1432 | MOI Diwan- Passive Work | RETURNED | No | 2023-08-23 | Abuhammad, Samir | 2025-11-13 | 2023-09-10 | 2025-11-13 |  | One site ready you can raise again. | 73040 | 6885 | 0 | STANDARD | Nabea Al Gawdah Company | SAR | 73040 | APPROVED |  |  | 2025-02-26 | 0 |  | Abuhammad, Samir | -45179 | 535
10522100006 | MOI Diwan Project | 1432 | MOI Diwan- Passive Work | RETURNED | No | 2023-08-23 | Abuhammad, Samir | 2025-11-13 | 2023-09-10 | 2025-11-13 |  | One site ready you can raise again. | 110750 | 7417 | 0 | STANDARD | Nabea Al Gawdah Company | SAR | 110750 | APPROVED |  |  | 2025-07-01 | 0 |  | Abuhammad, Samir | -45179 | 660
10522100006 | MOI Diwan Project | 1432 | MOI Diwan- Passive Work | RETURNED | No | 2023-08-23 | Abuhammad, Samir | 2025-11-13 | 2023-09-10 | 2025-11-13 |  | One site ready you can raise again. | 14000 | 7622 | 0 | STANDARD | ORIENTALS TECHNOLOGY EST. FOR CONTRACTING | SAR | 14000 | APPROVED |  |  | 2025-08-28 | 0 |  | Abuhammad, Samir | -45179 | 718
10522100006 | MOI Diwan Project | 1432 | MOI Diwan- Passive Work | RETURNED | No | 2023-08-23 | Abuhammad, Samir | 2025-11-13 | 2023-09-10 | 2025-11-13 |  | One site ready you can raise again. | 19750 | 7650 | 0 | STANDARD | Nabea Al Gawdah Company | SAR | 19750 | APPROVED |  |  | 2025-09-28 | 0 |  | Abuhammad, Samir | -45179 | 749
10522100006 | MOI Diwan Project | 1432 | MOI Diwan- Passive Work | RETURNED | No | 2023-08-23 | Abuhammad, Samir | 2025-11-13 | 2023-09-10 | 2025-11-13 |  | One site ready you can raise again. | 114250 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45179 | -45179
10522100006 | MOI Diwan Project | 1439 | Training for MOI Project | APPROVED | No | 2023-08-27 | Abas, Mohammed Fekry | 2023-09-07 | 2023-09-10 |  |  |  | 843562.5 | 4612 | 0 | STANDARD | Abad Networks for Training | SAR | 843562.5 | APPROVED |  |  | 2023-10-17 | 0 | 37 | Abuhammad, Samir | -45179 | 37
| ORA-01403: no data found | 1487 | OSP CCTV | INCOMPLETE | No | [7 empty] | 5400 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 1488 | OSP CCTV | REJECTED | No | 2023-09-11 | AlShehri, Ali | 2023-09-11 |  |  | 2023-09-11 |  | 5400 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 1566 | Change order for RTV | APPROVED | No | 2023-10-09 | Abas, Mohammed Fekry | 2023-10-11 | 2023-10-11 |  |  |  | 5000 | 3932 | 1 | STANDARD | YAHYA SALMAN ALGHAZWANI CONT.EST. | SAR | 5000 | APPROVED |  |  | 2023-10-26 | 0 | 15 | Babic, Marian | -45210 | 15
10522100006 | MOI Diwan Project | 1572 | Supply Of Passive Materials | APPROVED | No | 2023-10-10 | Abas, Mohammed Fekry | 2023-10-26 | 2023-10-26 |  | 2023-10-10 |  | 252425 | 4684 | 0 | STANDARD | Hardware Solutions Builders Co Ltd | SAR | 223255 | APPROVED |  |  | 2023-11-16 | 29170 | 21 | Abuhammad, Samir | -45225 | 21
10521300006 | Arafat 3 S/S (TD-0037) | 1578 | Supply of rental engineer for testing of Cap. Banks | APPROVED | No | 2023-10-11 | Abas, Mohammed Fekry | 2023-10-12 | 2023-10-12 |  |  |  | 20000 | 4662 | 0 | STANDARD | National Excellence For Constrution & Energy co. | SAR | 20000 | APPROVED |  |  | 2023-11-07 | 0 | 26 | Babic, Marian | -45211 | 26
10522100006 | MOI Diwan Project | 1580 | Supply of PC's | APPROVED | No | 2023-10-11 | Abas, Mohammed Fekry | 2024-02-19 | 2024-02-19 |  |  |  | 15840 | 5306 | 0 | STANDARD | Fast Computers for Trading Est | SAR | 15840 | APPROVED |  |  | 2024-05-27 | 0 | 98 | Abuhammad, Samir | -45341 | 98
10522100006 | MOI Diwan Project | 1658 | SUPPLY OF FLEXIBLE STEEL CONDUIT FOR MOI DIWAN PROJECT | APPROVED | No | 2023-11-05 | Abas, Mohammed Fekry | 2023-11-08 | 2023-11-09 |  |  |  | 108000 | 4713 | 0 | STANDARD | Integrated Network Solutions Trading Est. | SAR | 108000 | APPROVED |  |  | 2023-11-26 | 0 | 17 | Abuhammad, Samir | -45239 | 17
10522100006 | MOI Diwan Project | 1682 | Supply of power BI services for MOI Diwan project | APPROVED | No | 2023-11-12 | Abas, Mohammed Fekry | 2023-11-22 | 2023-11-22 |  |  |  | 156200 | 4560 | 1 | STANDARD | Nesma Injazat Information Technology Company | SAR | 156200 | APPROVED |  |  | 2024-04-30 | 0 | 160 | Abuhammad, Samir | -45252 | 160
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 1849 | oFFICE fURNITURE | APPROVED | No | 2023-11-29 | Abas, Mohammed Fekry | 2023-11-30 | 2023-12-03 |  |  |  | 33000 | 4785 | 0 | STANDARD | EMAD S. AL HARBI TRADING | SAR | 32300 | APPROVED |  |  | 2023-12-19 | 700 | 16 | Badhman, Saeed | -45263 | 16
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 1858 | Screening | APPROVED | No | 2023-11-29 | Abas, Mohammed Fekry | 2023-11-30 | 2023-12-03 |  |  |  | 1582250 | 4783 | 0 | STANDARD | IMPACT ENGINEERING | SAR | 1582250 | APPROVED |  |  | 2023-12-11 | 0 | 8 | Babic, Marian | -45263 | 8
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 1859 | Fault Recorder | APPROVED | No | 2023-11-29 | Abas, Mohammed Fekry | 2023-11-30 | 2023-12-03 |  |  |  | 25500 | 4784 | 0 | STANDARD | SAUDI ARABIAN INDUSTRIAL & TRADING Co. | SAR | 24500 | APPROVED |  |  | 2023-12-10 | 1000 | 7 | Babic, Marian | -45263 | 7
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 1877 | Laptop request for SEC | REJECTED | No | 2023-12-12 | Rafie, Mohamed | 2024-04-17 | 2023-12-13 |  | 2024-04-28 |  | 5000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45273 | -45273
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 1889 | Cable Raceway material | APPROVED | No | 2023-12-12 | Abas, Mohammed Fekry | 2023-12-14 | 2023-12-17 |  |  |  | 13723 | 4913 | 0 | STANDARD | AL-AMAL ELECTRICAL SWITCHBOARDS | SAR | 12595.93 | APPROVED |  |  | 2023-12-31 | 1127.07 | 14 | Babic, Marian | -45277 | 14
| ORA-01403: no data found | 1906 |  | APPROVED | No | 2023-12-07 | Abas, Mohammed Fekry | 2023-12-11 | 2023-12-11 |  |  |  | 6500 | 4837 | 0 | STANDARD | QUDRA COMMUNICATION AND INFORMATION TECHNOLOGY | SAR | 6500 | APPROVED |  |  | 2023-12-18 | 0 | 7 | Abuhammad, Samir | -45271 | 7
| ORA-01403: no data found | 1917 |  | APPROVED | No | 2023-12-07 | Abas, Mohammed Fekry | 2023-12-11 | 2023-12-11 |  |  |  | 10125 | 4836 | 0 | STANDARD | Exclusive Networks For Information Systems Technology | SAR | 10125 | APPROVED |  |  | 2023-12-19 | 0 | 8 | Abuhammad, Samir | -45271 | 8
10522100006 | MOI Diwan Project | 1939 | Supply of Commvult licenses | APPROVED | No | 2023-12-12 | Abas, Mohammed Fekry | 2023-12-14 | 2023-12-17 |  |  |  | 351669.06 | 4874 | 0 | STANDARD | Starlink MDMC Arabian Trading Co | SAR | 346944 | APPROVED |  |  | 2023-12-26 | 4725.06 | 9 | Abuhammad, Samir | -45277 | 9
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 1957 | STRIP LIGHT-for | APPROVED | No | 2023-12-14 | Abas, Mohammed Fekry | 2023-12-19 | 2023-12-25 |  |  |  | 225249.6 | 4925 | 0 | STANDARD | Qalaa Aladha Al-Tajaria | SAR | 220000 | APPROVED |  |  | 2024-02-27 | 5249.6 | 64 | Babic, Marian | -45285 | 64
| ORA-01403: no data found | 2081 | Riyadh office printer supply | APPROVED | No | 2024-01-02 | Abas, Mohammed Fekry | 2024-01-04 | 2024-01-04 |  |  |  | 4672 | 4985 | 0 | STANDARD | Munira Suleiman Yahya Al-Fifi Trading EST | SAR | 4672 | APPROVED |  |  | 2024-01-24 | 0 | 20 | Abuhammad, Samir | -45295 | 20
10529220008 | MOI_PO#20403 | 2082 | Supply of Passive Materials- Corning Materials | APPROVED | No | 2024-01-02 | Abas, Mohammed Fekry | 2024-01-09 | 2024-01-11 |  |  |  | 102180 | 4986 | 0 | STANDARD | Hardware Solutions Builders Co Ltd | SAR | 95560 | APPROVED |  |  | 2024-01-17 | 6620 | 6 | Abuhammad, Samir | -45302 | 6
| ORA-01403: no data found | 2124 | NIT IT requirements | IN PROCESS | No | 2024-01-09 | Aljarmawi, Omar | 2024-01-09 |  |  |  |  | 621437 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 2139 | National CommNIT IT requirementsercial Bank | APPROVED | No | 2024-01-09 | Abas, Mohammed Fekry | 2024-01-15 | 2024-01-16 |  |  |  | 15157 | 4999 | 0 | STANDARD | Golden Technology trading Company. | SAR | 11920 | APPROVED |  |  | 2024-01-24 | 3237 | 8 | Abuhammad, Samir | -45307 | 8
| ORA-01403: no data found | 2141 | Hardware and Software Requirements | APPROVED | No | 2024-01-09 | Abas, Mohammed Fekry | 2024-01-11 | 2024-01-14 |  |  |  | 13212.35 | 4990 | 0 | STANDARD | Golden Technology trading Company. | SAR | 11374 | APPROVED |  |  | 2024-01-28 | 1838.35 | 14 | Abuhammad, Samir | -45305 | 14
| ORA-01403: no data found | 2161 |  | APPROVED | No | 2024-01-14 | Abas, Mohammed Fekry | 2024-01-15 | 2024-01-16 |  |  |  | 9637.89 | 5002 | 0 | STANDARD | Nesma Injazat Information Technology Company | SAR | 9637 | APPROVED |  |  | 2024-01-31 | 0.89 | 15 | Abuhammad, Samir | -45307 | 15
| ORA-01403: no data found | 2162 |  | APPROVED | No | 2024-01-14 | Abas, Mohammed Fekry | 2024-01-22 | 2024-01-22 |  |  | Please share detailed of item description with Mr. Samir | 2940 | 5009 | 0 | STANDARD | Nesma Injazat Information Technology Company | SAR | 2940 | APPROVED |  |  | 2024-01-31 | 0 | 9 | Abuhammad, Samir | -45313 | 9
| ORA-01403: no data found | 2176 | Furniture for New Extension Head office - Jeddah | RETURNED | No | 2024-01-16 | Babic, Marian | 2024-04-16 | 2024-01-16 | 2024-04-16 |  | not required, PO 4998 issued | 119060 | 4998 | 0 | STANDARD | MAJESTIC OFFICE FOR FURNITURE | SAR | 221901 | APPROVED |  |  | 2024-01-30 | -102841 |  | Babic, Marian | -45307 | 14
| ORA-01403: no data found | 2176 | Furniture for New Extension Head office - Jeddah | RETURNED | No | 2024-01-16 | Babic, Marian | 2024-04-16 | 2024-01-16 | 2024-04-16 |  | not required, PO 4998 issued | 88373 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45307 | -45307
| ORA-01403: no data found | 2231 | Furniture for New Extension Head office - Jeddah - 1 | APPROVED | No | 2024-01-21 | Badhman, Saeed | 2024-01-21 | 2024-01-21 |  |  |  | 47300 | 4998 | 0 | STANDARD | MAJESTIC OFFICE FOR FURNITURE | SAR | 40205 | APPROVED |  |  | 2024-01-30 | 7095 | 9 | Babic, Marian | -45312 | 9
| ORA-01403: no data found | 2265 | Design Agreement for New head office Extension | RETURNED | No | 2024-01-23 | Babic, Marian | 2024-01-30 | 2024-01-23 | 2024-01-30 |  | as discussed | 50000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45314 | -45314
| ORA-01403: no data found | 2266 | Design for Dammam office | APPROVED | No | 2024-01-23 | Abas, Mohammed Fekry | 2024-01-25 | 2024-01-28 |  |  |  | 105000 | 5038 | 0 | STANDARD | FATEHIA M. KAMAL M. JAMJOOM DESIGN ESTABLISHMENT | SAR | 105000 | APPROVED |  |  | 2024-02-08 | 0 | 11 | Babic, Marian | -45319 | 11
| ORA-01403: no data found | 2267 | Design Agreement for New head office Extension | APPROVED | No | 2024-01-23 | Abas, Mohammed Fekry | 2024-01-25 | 2024-01-28 |  |  |  | 50000 | 5037 | 0 | STANDARD | FATEHIA M. KAMAL M. JAMJOOM DESIGN ESTABLISHMENT | SAR | 50000 | APPROVED |  |  | 2024-02-06 | 0 | 9 | Babic, Marian | -45319 | 9
| ORA-01403: no data found | 2268 | Civil , electromechanical work for the new extension head office - Jeddah | APPROVED | No | 2024-01-23 | Abas, Mohammed Fekry | 2024-01-25 | 2024-01-28 |  |  |  | 856779.77 | 5131 | 0 | STANDARD | 4D Imension for contracting Company | SAR | 745025.89 | APPROVED |  |  | 2024-03-06 | 111753.88 | 38 | Badhman, Saeed | -45319 | 38
10511000001 | Overhead (JED) | 2382 | New Hires ¦ Q1&2 2024 | APPROVED | No | 2024-01-31 | Abas, Mohammed Fekry | 2024-02-01 | 2024-02-01 |  |  |  | 558000 | 5040 | 0 | STANDARD | Golden Technology trading Company. | SAR | 526000 | APPROVED |  |  | 2024-02-19 | 32000 | 18 | Abuhammad, Samir | -45323 | 18
| ORA-01403: no data found | 2505 | CCTV - NIT Accomodation | APPROVED | No | 2024-02-08 | Abas, Mohammed Fekry | 2024-02-14 | 2024-02-15 |  |  |  | 17920 | 5106 | 0 | STANDARD | Instant Solutions Limited Co | SAR | 17856 | APPROVED |  |  | 2024-03-04 | 64 | 18 | Badhman, Saeed | -45337 | 18
| ORA-01403: no data found | 2512 | Chairs for New Jeddah office | APPROVED | No | 2024-02-08 | Abas, Mohammed Fekry | 2024-02-11 | 2024-02-11 |  |  |  | 14400 | 5094 | 0 | STANDARD | Riyadh House Branch of Jeraisy Group Company | SAR | 14400 | APPROVED |  |  | 2024-02-27 | 0 | 16 | Babic, Marian | -45333 | 16
| ORA-01403: no data found | 2529 | Office Furniture - Dammam office (Petromin) | APPROVED | No | 2024-02-12 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-18 |  |  |  | 32280 | 5104 | 0 | STANDARD | Kassim M.A. Al Driweesh Sons co. Ltd | SAR | 31000 | APPROVED |  |  | 2024-02-29 | 1280 | 11 | Babic, Marian | -45340 | 11
| ORA-01403: no data found | 2561 | Printer and Monitor | APPROVED | No | 2024-02-14 | Abas, Mohammed Fekry | 2024-02-15 | 2024-02-15 |  |  |  | 8193.75 | 5101 | 0 | STANDARD | Golden Technology trading Company. | SAR | 7125 | APPROVED |  |  | 2024-03-05 | 1068.75 | 19 | Abuhammad, Samir | -45337 | 19
| ORA-01403: no data found | 2578 | CEO Requirements | APPROVED | No | 2024-02-18 | Abas, Mohammed Fekry | 2024-02-20 | 2024-02-21 |  |  |  | 12558 | 5123 | 0 | STANDARD | Golden Technology trading Company. | SAR | 10920 | APPROVED |  |  | 2024-03-03 | 1638 | 11 | Abuhammad, Samir | -45343 | 11
| ORA-01403: no data found | 2683 | Civil, electromechanical work for Dammam new head office | APPROVED | No | 2024-02-25 | Abas, Mohammed Fekry | 2024-03-03 | 2024-03-03 |  |  |  | 2210000 | 5511 | 0 | STANDARD | 4D Imension for contracting Company | SAR | 2205426.09 | APPROVED |  |  | 2024-05-19 | 4573.91 | 77 | Badhman, Saeed | -45354 | 77
| ORA-01403: no data found | 2686 | AutoCAD License | APPROVED | No | 2024-02-26 | Abas, Mohammed Fekry | 2024-02-27 | 2024-02-28 |  |  |  | 39300 | 4990 | 1 | STANDARD | Golden Technology trading Company. | SAR | 39300 | APPROVED |  |  | 2024-03-28 | 0 | 29 | Abuhammad, Samir | -45350 | 29
| ORA-01403: no data found | 2687 | Quotation of Laptop | APPROVED | No | 2024-02-26 | Abas, Mohammed Fekry | 2024-03-04 | 2024-03-04 |  |  |  | 58050 | 5165 | 0 | STANDARD | High Point Technology Co, | SAR | 57402 | APPROVED |  |  | 2024-03-13 | 648 | 9 | Abuhammad, Samir | -45355 | 9
| ORA-01403: no data found | 2737 | Quotation of Router | REJECTED | No | 2024-03-03 | Al-Ahmadi, Ms. Sarah Mohammed | 2024-03-04 |  |  | 2024-03-04 |  | 7920 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 2768 | Quotation of Router | RETURNED | No | 2024-03-04 | Abuhammad, Samir | 2024-03-27 | 2024-03-10 | 2024-03-27 |  | Due to wrong description | 3960 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45361 | -45361
| ORA-01403: no data found | 2782 | Laptop and other IT request for the employee in KSA and Egypt office | REJECTED | No | 2024-03-05 | Al-Ahmadi, Ms. Sarah Mohammed | 2024-03-05 |  |  | 2024-03-05 |  | 24754 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 2797 | Laptop and other IT request for the employee in KSA and Egypt office | APPROVED | No | 2024-03-06 | Abas, Mohammed Fekry | 2024-03-10 | 2024-03-10 |  |  |  | 24754 | 5217 | 0 | STANDARD | Golden Technology trading Company. | SAR | 24754 | APPROVED |  |  | 2024-03-20 | 0 | 10 | Abuhammad, Samir | -45361 | 10
| ORA-01403: no data found | 2803 | Laptop and other IT request for the employee in KSA and Egypt office ! | REJECTED | No | 2024-03-07 | Al-Ahmadi, Ms. Sarah Mohammed | 2024-03-07 |  |  | 2024-03-10 | Rejected as per requester request. | 24754 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 2804 | Supply of IT equipment for New Extension Head office - Jeddah | APPROVED | No | 2024-03-07 | Abas, Mohammed Fekry | 2024-03-12 | 2024-03-13 |  |  |  | 78120 | 5259 | 0 | STANDARD | Expert Tech Est. | SAR | 78120 | APPROVED |  |  | 2024-03-21 | 0 | 8 | Badhman, Saeed | -45364 | 8
| ORA-01403: no data found | 2824 | Toner for dammam office printer | APPROVED | No | 2024-03-14 | Abas, Mohammed Fekry | 2024-03-18 | 2024-03-19 |  |  |  | 6658 | 5287 | 0 | STANDARD | Munira Suleiman Yahya Al-Fifi Trading EST | SAR | 3990 | APPROVED |  |  | 2024-03-31 | 2668 | 12 | Abuhammad, Samir | -45370 | 12
| ORA-01403: no data found | 2837 | NIT ¦ Internet Upgrade ¦ 60Mbps | APPROVED | No | 2024-03-18 | Abas, Mohammed Fekry | 2024-03-20 | 2024-03-21 | 2024-03-19 |  | Dut to change the duration for 12 Months. | 504000 | 5272 | 0 | STANDARD | Zone Network Information Technology Est. | SAR | 504000 | APPROVED |  |  | 2024-04-30 | 0 | 40 | Abuhammad, Samir | -45372 | 40
| ORA-01403: no data found | 2898 | Internet Services for Jeddah New extention office | REJECTED | No | 2024-03-25 | Bahuwayni, Mr. Abdulrahman Saleh | 2024-04-15 | 2024-03-25 |  | 2024-04-16 |  | 27000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45376 | -45376
| ORA-01403: no data found | 2904 | Internet Services for Jeddah New extention office | APPROVED | No | 2024-03-26 | Abas, Mohammed Fekry | 2024-03-27 | 2024-03-28 |  |  |  | 269000 | 5410 | 0 | STANDARD | Zone Network Information Technology Est. | SAR | 269000 | APPROVED |  |  | 2024-06-24 | 0 | 88 | Abuhammad, Samir | -45379 | 88
| ORA-01403: no data found | 2911 | Refurbishing Dammam office (Petromin) | APPROVED | No | 2024-03-27 | Abas, Mohammed Fekry | 2024-04-22 | 2024-04-23 |  |  |  | 40000 | 5274 | 0 | STANDARD | Construction Expertise Est. | SAR | 40000 | APPROVED |  |  | 2024-05-08 | 0 | 15 | Badhman, Saeed | -45405 | 15
| ORA-01403: no data found | 2914 | Router | APPROVED | No | 2024-03-27 | Abas, Mohammed Fekry | 2024-03-28 | 2024-03-31 |  |  |  | 3960 | 5219 | 0 | STANDARD | High Point Technology Co, | SAR | 3676 | APPROVED |  |  | 2024-04-08 | 284 | 8 | Abuhammad, Samir | -45382 | 8
10529110001 | Dammam Port (DSP-0038) | 3070 | SCADA Building Manpower Supply - AC Test works) | REJECTED | No | 2024-04-22 | BABEKAR, MOHAMMED HUSSAIN | 2024-04-22 |  |  | 2024-04-22 |  | 265000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10529110001 | Dammam Port (DSP-0038) | 3071 | SCADA Building Manpower Supply - AC Test works) | RETURNED | No | 2024-04-21 | Kumar, Mr. Ranjan | 2025-04-06 | 2024-05-14 | 2025-04-06 | 2024-04-29 | PO was rejected with this notw: PR quantity and PR value is exchanged (It shall be considerd as 1 Lot, SAR 264,650). While receving it may create an issue. Project manager to submit correct PR. | 265000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45426 | -45426
| ORA-01403: no data found | 3096 | NIT new office IP Phone Call Manager GW PR | RETURNED | No | 2024-04-22 | Abuhammad, Samir | 2024-05-14 | 2024-04-25 | 2024-05-14 |  | as per requester. | 17000 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45407 | -45407
| ORA-01403: no data found | 3098 | Toners for Ricoh printer at Petromin Dammam office | APPROVED | No | 2024-04-22 | Abas, Mohammed Fekry | 2024-04-25 | 2024-04-25 |  |  |  | 3300 | 5450 | 0 | STANDARD | Munira Suleiman Yahya Al-Fifi Trading EST | SAR | 2320 | APPROVED |  |  | 2024-05-21 | 980 | 26 | Abuhammad, Samir | -45407 | 26
| ORA-01403: no data found | 3130 | HP Printers-Tabuk warehouse | IN PROCESS | No | 2024-04-25 | Aljarmawi, Omar | 2024-04-30 | 2024-04-29 |  |  |  | 2300 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45411 | -45411
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 3165 | TPI for lighting Panel inspection | APPROVED | No | 2024-04-27 | Abas, Mohammed Fekry | 2024-04-30 | 2024-05-01 |  |  |  | 4500 | 5494 | 0 | STANDARD | Atlas Support and Services | USD | 4500 | APPROVED |  |  | 2024-05-20 | 0 | 19 | Babic, Marian | -45413 | 19
| ORA-01403: no data found | 3215 | Laptops | APPROVED | No | 2024-04-29 | Abas, Mohammed Fekry | 2024-05-01 | 2024-05-01 |  |  |  | 15940 | 5501 | 0 | STANDARD | Golden Technology trading Company. | SAR | 15940 | APPROVED |  |  | 2024-05-14 | 0 | 13 | Abuhammad, Samir | -45413 | 13
| ORA-01403: no data found | 3235 | Toners for Jeedah warhouse | APPROVED | No | 2024-05-01 | Abas, Mohammed Fekry | 2024-05-02 | 2024-05-02 |  |  |  | 3200 | 5506 | 0 | STANDARD | Munira Suleiman Yahya Al-Fifi Trading EST | SAR | 1560 | APPROVED |  |  | 2024-05-14 | 1640 | 12 | Abuhammad, Samir | -45414 | 12
| ORA-01403: no data found | 3236 | Monitors | APPROVED | No | 2024-05-01 | Abas, Mohammed Fekry | 2024-05-01 | 2024-05-01 |  |  |  | 13755 | 5501 | 0 | STANDARD | Golden Technology trading Company. | SAR | 13755 | APPROVED |  |  | 2024-05-14 | 0 | 13 | Abuhammad, Samir | -45413 | 13
| ORA-01403: no data found | 3239 | purchase 5G routers for Project sites and warehouses across the Kingdom | APPROVED | No | 2024-05-01 | Abas, Mohammed Fekry | 2024-05-02 | 2024-05-02 |  |  |  | 12500 | 5569 | 0 | STANDARD | Mohammad Abdul Rahman Mohd Al Zahid Information Technology Co | SAR | 12500 | APPROVED |  |  | 2024-05-26 | 0 | 24 | Abuhammad, Samir | -45414 | 24
10522100006 | MOI Diwan Project | 3312 | Symantec Licenses | APPROVED | No | 2024-05-06 | Abas, Mohammed Fekry | 2024-05-14 | 2024-05-14 |  |  |  | 691381.04 | 5575 | 0 | STANDARD | APTEC Saudi Arabia LCC | SAR | 691200.7 | APPROVED |  |  | 2024-06-13 | 180.34 | 30 | Abuhammad, Samir | -45426 | 30
| ORA-01403: no data found | 3349 | Bulk laptop purchase | APPROVED | No | 2024-05-08 | Abas, Mohammed Fekry | 2024-05-08 | 2024-05-12 |  |  |  | 525700 | 5530 | 0 | STANDARD | Golden Technology trading Company. | SAR | 525100 | APPROVED |  |  | 2024-05-23 | 600 | 11 | Abuhammad, Samir | -45424 | 11
10521100008 | King Fahad National Centre for Children's Cancer (ES-0023) | 3350 | corrective maintenance | APPROVED | No | 2024-05-08 | Abas, Mohammed Fekry | 2024-05-09 | 2024-05-12 |  |  |  | 11298.5 | 5570 | 0 | STANDARD | DAIKIN AIR CONDITIONING SAUDI ARABIA | SAR | 11298.5 | APPROVED |  |  | 2024-06-02 | 0 | 21 | Abuhammad, Samir | -45424 | 21
| ORA-01403: no data found | 3353 | Supply of Furnitures (Dammam) | APPROVED | No | 2024-05-08 | Abas, Mohammed Fekry | 2024-05-16 | 2024-05-17 |  |  |  | 13650 | 5587 | 0 | STANDARD | Excellence Area Trading Est.(S) | SAR | 13650 | APPROVED |  |  | 2024-05-26 | 0 | 9 | Babic, Marian | -45429 | 9
| ORA-01403: no data found | 3356 | RFQ-Router | RETURNED | No | 2024-05-09 | Abuhammad, Samir | 2024-05-23 | 2024-05-12 | 2024-05-23 |  | due to change the Qty | 73657.36 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45424 | -45424
| ORA-01403: no data found | 3412 | IT Material Request for Industrial Solutions Executive Manager | APPROVED | No | 2024-05-16 | Abas, Mohammed Fekry | 2024-05-23 | 2024-05-26 |  |  |  | 5730 | 5673 | 0 | STANDARD | Golden Technology trading Company. | SAR | 5730 | APPROVED |  |  | 2024-06-10 | 0 | 15 | Abuhammad, Samir | -45438 | 15
| ORA-01403: no data found | 3433 | Chairs for Dammam office | APPROVED | No | 2024-05-19 | Abas, Mohammed Fekry | 2024-05-20 | 2024-05-22 |  |  |  | 18000 | 5685 | 0 | STANDARD | Riyadh House Branch of Jeraisy Group Company | SAR | 18000 | APPROVED |  |  | 2024-06-11 | 0 | 20 | Babic, Marian | -45434 | 20
| ORA-01403: no data found | 3449 | Menaitech ZKTeco devices integration | APPROVED | No | 2024-05-20 | Abas, Mohammed Fekry | 2024-05-23 | 2024-05-26 |  |  |  | 6325 | 5623 | 0 | STANDARD | Advance International Company | SAR | 5500 | APPROVED |  |  | 2024-06-03 | 825 | 8 | Abuhammad, Samir | -45438 | 8
| ORA-01403: no data found | 3488 | Cisco ISR Router | APPROVED | No | 2024-05-23 | Abas, Mohammed Fekry | 2024-05-28 | 2024-05-28 |  |  |  | 73650.98 | 5543 | 0 | STANDARD | JERAISY COMPUTER & COMM.SERVICES | SAR | 73638 | APPROVED |  |  | 2024-06-11 | 12.98 | 14 | Abuhammad, Samir | -45440 | 14
10521100015 | Emarat Al Madinah | 3590 | Lighting for EM | APPROVED | No | 2024-06-04 | Abas, Mohammed Fekry | 2024-06-10 | 2024-06-10 |  |  | payable item | 111000 | 5728 | 0 | STANDARD | Optical Circuit Trading Co | SAR | 92000 | APPROVED |  |  | 2024-07-04 | 19000 | 24 | Abuhammad, Samir | -45453 | 24
| ORA-01403: no data found | 3636 | Request for bulk licnese (Acrobat pro and Autocad) | APPROVED | No | 2024-06-10 | Abas, Mohammed Fekry | 2024-06-13 | 2024-06-13 |  |  |  | 27850 | 5837 | 0 | STANDARD | Golden Technology trading Company. | SAR | 27750 | APPROVED |  |  | 2024-08-05 | 100 | 53 | Abuhammad, Samir | -45456 | 53
| ORA-01403: no data found | 3654 | Request for Office Equipment & Computer Accessories (RTR PROJECT) | REJECTED | No | 2024-06-13 | Dadoukh, Hassan | 2024-06-26 | 2024-06-23 |  | 2024-06-26 |  | 25830 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45466 | -45466
| ORA-01403: no data found | 3708 | Toner & Screen | RETURNED | No | 2024-06-30 | Abuhammad, Samir | 2024-08-06 | 2024-07-03 | 2024-08-06 |  | Due to change the Task No under sharfia project not OH. | 31830 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45476 | -45476
| ORA-01403: no data found | 3709 | Screen & PC | APPROVED | No | 2024-06-30 | Abas, Mohammed Fekry | 2024-07-03 | 2024-07-03 |  |  |  | 10900 | 5800 | 0 | STANDARD | Golden Technology trading Company. | SAR | 9740 | APPROVED |  |  | 2024-07-21 | 1160 | 18 | Abuhammad, Samir | -45476 | 18
10521100008 | King Fahad National Centre for Children's Cancer (ES-0023) | 3714 | Oil replacement Chiller KFNCCC | APPROVED | No | 2024-07-01 | Abas, Mohammed Fekry | 2024-07-02 | 2024-07-02 |  |  |  | 8646.32 | 5770 | 0 | STANDARD | DAIKIN AIR CONDITIONING SAUDI ARABIA | SAR | 8644 | APPROVED |  |  | 2024-07-21 | 2.32 | 19 | Abuhammad, Samir | -45475 | 19
| ORA-01403: no data found | 3763 | Board Meeting Room Table - Dammam office | APPROVED | No | 2024-07-04 | Abas, Mohammed Fekry | 2024-07-04 | 2024-07-04 |  |  |  | 48000 | 5772 | 0 | STANDARD | Innovate General Contracting EST. | SAR | 48000 | APPROVED |  |  | 2024-07-09 | 0 | 5 | Babic, Marian | -45477 | 5
| ORA-01403: no data found | 3764 | Meeting Table Chairs - Dammam office | APPROVED | No | 2024-07-04 | Abas, Mohammed Fekry | 2024-07-04 | 2024-07-04 |  |  |  | 17836 | 5774 | 0 | STANDARD | Riyadh House Branch of Jeraisy Group Company | SAR | 17836 | APPROVED |  |  | 2024-07-09 | 0 | 5 | Babic, Marian | -45477 | 5
| ORA-01403: no data found | 3817 | Laptop & Mouse & Bag | APPROVED | No | 2024-07-10 | Abas, Mohammed Fekry | 2024-07-11 | 2024-07-11 |  |  |  | 525100 | 5811 | 0 | STANDARD | Golden Technology trading Company. | SAR | 525100 | APPROVED |  |  | 2024-07-31 | 0 | 20 | Abuhammad, Samir | -45484 | 20
| ORA-01403: no data found | 3894 | AutoCad Licenses. | APPROVED | No | 2024-07-15 | Abas, Mohammed Fekry | 2024-07-17 | 2024-07-18 |  |  |  | 51200 | 5875 | 0 | STANDARD | Golden Technology trading Company. | SAR | 51160 | APPROVED |  |  | 2024-08-22 | 40 | 35 | Abuhammad, Samir | -45491 | 35
| ORA-01403: no data found | 3943 | Printer | APPROVED | No | 2024-07-17 | Abas, Mohammed Fekry | 2024-07-21 | 2024-07-21 |  |  |  | 2700 | 5880 | 0 | STANDARD | Mohammad Abdul Rahman Mohd Al Zahid Information Technology Co | SAR | 2700 | APPROVED |  |  | 2024-08-11 | 0 | 21 | Abuhammad, Samir | -45494 | 21
| ORA-01403: no data found | 3958 | Design for Riyadh office | APPROVED | No | 2024-07-18 | Abas, Mohammed Fekry | 2024-07-21 | 2024-07-21 |  |  |  | 140000 | 5862 | 0 | STANDARD | FATEHIA M. KAMAL M. JAMJOOM DESIGN ESTABLISHMENT | SAR | 135000 | APPROVED |  |  | 2024-07-31 | 5000 | 10 | Babic, Marian | -45494 | 10
| ORA-01403: no data found | 3977 | Printer Maintenance | APPROVED | No | 2024-07-22 | Abas, Mohammed Fekry | 2024-07-22 | 2024-07-23 |  |  |  | 2320 | 5924 | 0 | STANDARD | Munira Suleiman Yahya Al-Fifi Trading EST | SAR | 2320 | APPROVED |  |  | 2024-08-20 | 0 | 28 | Abuhammad, Samir | -45496 | 28
| ORA-01403: no data found | 3987 | ZKT | APPROVED | No | 2024-07-22 | Abas, Mohammed Fekry | 2024-07-23 | 2024-07-25 |  |  |  | 4400 | 5925 | 0 | STANDARD | Advance International Company | SAR | 4100 | APPROVED |  |  | 2024-08-20 | 300 | 26 | Abuhammad, Samir | -45498 | 26
| ORA-01403: no data found | 4033 | Purchasing New Forklifts | APPROVED | No | 2024-07-28 | Abas, Mohammed Fekry | 2024-07-28 | 2024-07-28 |  |  |  | 795000 | 5893 | 0 | STANDARD | Machinery Rental Alternatives Co. Ltd | SAR | 795000 | APPROVED |  |  | 2024-08-25 | 0 | 28 | Badhman, Saeed | -45501 | 28
| ORA-01403: no data found | 4033 | Purchasing New Forklifts | APPROVED | No | 2024-07-28 | Abas, Mohammed Fekry | 2024-07-28 | 2024-07-28 |  |  |  | 795000 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45501 | -45501
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 4051 | Supply & instal Stand ACs | APPROVED | No | 2024-07-31 | Alharbi, Atef Saud | 2024-08-05 | 2024-08-05 |  |  |  | 24600 | 5927 | 0 | STANDARD | Current Makers For Contracting EST | SAR | 24600 | APPROVED |  |  | 2024-08-08 | 0 | 3 | Babic, Marian | -45509 | 3
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 4113 | Supply of lighting materials | APPROVED | No | 2024-08-07 | Alharbi, Atef Saud | 2024-08-08 | 2024-08-12 |  |  |  | 43685 | 5975 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 40857 | APPROVED |  |  | 2024-08-21 | 2828 | 9 | Abuhammad, Samir | -45516 | 9
| ORA-01403: no data found | 4143 | Riyadh Printer | APPROVED | No | 2024-08-12 | Abas, Mohammed Fekry | 2024-08-12 | 2024-08-13 |  |  |  | 3990 | 5972 | 0 | STANDARD | Munira Suleiman Yahya Al-Fifi Trading EST | SAR | 3990 | APPROVED |  |  | 2024-08-25 | 0 | 12 | Abuhammad, Samir | -45517 | 12
| ORA-01403: no data found | 4148 | Fire Pump | RETURNED | No | 2024-08-13 | Badhman, Saeed | 2024-09-30 | 2024-08-19 | 2024-09-30 |  | further details and requiremtnts clarification from logistics are needed | 118700 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45523 | -45523
| ORA-01403: no data found | 4176 | Laptops for Nesma employees at Cairo office | APPROVED | No | 2024-08-18 | Abas, Mohammed Fekry | 2024-08-19 | 2024-08-19 |  |  |  | 31890 | 6016 | 0 | STANDARD | High Point Technology Co, | SAR | 31890 | APPROVED |  |  | 2024-08-21 | 0 | 2 | Abuhammad, Samir | -45523 | 2
| ORA-01403: no data found | 4262 | Toner | IN PROCESS | No | 2024-08-25 | Aljarmawi, Omar | 2024-08-26 |  |  |  |  | 3990 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 4263 | Toner | APPROVED | No | 2024-08-25 | Abas, Mohammed Fekry | 2024-08-26 | 2024-08-26 |  |  |  | 2320 | 6158 | 0 | STANDARD | Munira Suleiman Yahya Al-Fifi Trading EST | SAR | 2320 | APPROVED |  |  | 2024-09-26 | 0 | 31 | Abuhammad, Samir | -45530 | 31
| ORA-01403: no data found | 4264 | Riyadh Pirnter | APPROVED | No | 2024-08-25 | Abas, Mohammed Fekry | 2024-08-26 | 2024-08-26 |  |  |  | 4305 | 6102 | 0 | STANDARD | Munira Suleiman Yahya Al-Fifi Trading EST | SAR | 4305 | APPROVED |  |  | 2024-09-26 | 0 | 31 | Abuhammad, Samir | -45530 | 31
| ORA-01403: no data found | 4391 | IMS Certification for NIT | APPROVED | No | 2024-09-09 | Abas, Mohammed Fekry | 2024-09-10 | 2024-09-10 |  |  |  | 66000 | 6194 | 0 | STANDARD | Knowledge Seekers Training Center | SAR | 66000 | APPROVED |  |  | 2024-09-26 | 0 | 16 | Abuhammad, Samir | -45545 | 16
10521300008 | Construction of JEC 110/13.8kV Substation in Jeddah (TD-0039) | 4469 | Testing & Commissioning Servise (Change Order) | APPROVED | No | 2024-09-17 | Alharbi, Atef Saud | 2024-09-22 | 2024-09-22 |  |  |  | 129000 | 3824 | 1 | STANDARD | National Excellence For Constrution & Energy co. | SAR | 129000 | APPROVED |  |  | 2024-10-22 | 0 | 30 | Babic, Marian | -45557 | 30
| ORA-01403: no data found | 4517 | 100 Laptops Quotation | APPROVED | No | 2024-09-25 | Abas, Mohammed Fekry | 2024-09-25 | 2024-09-26 |  |  |  | 525100 | 6254 | 0 | STANDARD | Excellence Arabia Trading Company | SAR | 517600 | APPROVED |  |  | 2024-10-01 | 7500 | 5 | Abuhammad, Samir | -45561 | 5
| ORA-01403: no data found | 4518 | CCTV for Dammam Store | RETURNED | No | 2024-09-25 | Akhtar, Farhan | 2024-12-22 | 2024-09-26 | 2024-12-22 |  | this one item is extra | 53476.99 | 6320 | 0 | STANDARD | Megamind IT Solutions | SAR | 53476.99 | APPROVED |  |  | 2024-11-28 | 0 |  | Akhtar, Farhan | -45561 | 63
| ORA-01403: no data found | 4518 | CCTV for Dammam Store | RETURNED | No | 2024-09-25 | Akhtar, Farhan | 2024-12-22 | 2024-09-26 | 2024-12-22 |  | this one item is extra | 53476.99 | 6320 | 1 | STANDARD | Megamind IT Solutions | SAR | 53476.99 | IN PROCESS |  |  |  | 0 |  | Akhtar, Farhan | -45561 | -45561
| ORA-01403: no data found | 4518 | CCTV for Dammam Store | RETURNED | No | 2024-09-25 | Akhtar, Farhan | 2024-12-22 | 2024-09-26 | 2024-12-22 |  | this one item is extra | 6000 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45561 | -45561
| ORA-01403: no data found | 4584 | Jeddah Head office - Additional Offices | APPROVED | No | 2024-10-06 | Abas, Mohammed Fekry | 2024-10-07 | 2024-10-07 |  |  |  | 46250 | 6314 | 0 | STANDARD | MAJESTIC OFFICE FOR FURNITURE | SAR | 32077.5 | APPROVED |  |  | 2024-10-10 | 14172.5 | 3 | Babic, Marian | -45572 | 3
10511000001 | Overhead (JED) | 4618 | Supply of Furniture and Appliances for Nesma Accomodation | APPROVED | No | 2024-10-07 | Abas, Mohammed Fekry | 2024-10-09 | 2024-10-09 |  |  |  | 86515 | 6321 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 86515 | APPROVED |  |  | 2024-10-24 | 0 | 15 | Babic, Marian | -45574 | 15
| ORA-01403: no data found | 4684 | Waly Alahad-3 SS in Makkah-Lghting Pole | REJECTED | No | 2024-10-15 | Yamama, Loai Mohamed | 2024-10-20 | 2024-10-15 |  | 2024-10-20 |  | 600 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45580 | -45580
| ORA-01403: no data found | 4689 | Screen | RETURNED | No | 2024-10-15 | Abuhammad, Samir | 2024-10-28 | 2024-10-17 | 2024-10-28 |  | As per requester. | 2465 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45582 | -45582
| ORA-01403: no data found | 4696 | License | APPROVED | No | 2024-10-16 | Abas, Mohammed Fekry | 2024-10-17 | 2024-10-17 |  |  |  | 12880 | 6375 | 0 | STANDARD | Golden Technology trading Company. | SAR | 12800 | APPROVED |  |  | 2024-10-28 | 80 | 11 | Abuhammad, Samir | -45582 | 11
| ORA-01403: no data found | 4778 | IT Material | APPROVED | No | 2024-10-23 | Abas, Mohammed Fekry | 2024-10-24 | 2024-10-27 |  |  |  | 18455 | 6387 | 0 | STANDARD | Golden Technology trading Company. | SAR | 18455 | APPROVED |  |  | 2024-11-03 | 0 | 7 | Abuhammad, Samir | -45592 | 7
| ORA-01403: no data found | 4788 | FortiGate | APPROVED | No | 2024-10-24 | Abas, Mohammed Fekry | 2024-10-27 | 2024-10-27 |  |  |  | 7537.5 | 6396 | 0 | STANDARD | Exclusive Networks For Information Systems Technology | SAR | 7537.5 | APPROVED |  |  | 2024-11-03 | 0 | 7 | Abuhammad, Samir | -45592 | 7
| ORA-01403: no data found | 4795 | NIT Dammam network switches | APPROVED | No | 2024-10-27 | Abas, Mohammed Fekry | 2024-10-27 | 2024-10-27 |  |  |  | 8062.8 | 6437 | 0 | STANDARD | EBTTIKAR TECHNOLOGY COMPANY LTD. | SAR | 7589.64 | APPROVED |  |  | 2024-11-10 | 473.16 | 14 | Abuhammad, Samir | -45592 | 14
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 4815 | Testing and Commissioning | APPROVED | No | 2024-10-31 | Alharbi, Atef Saud | 2024-10-31 | 2024-11-03 |  |  |  | 416000 | 6428 | 0 | STANDARD | Middle East Technical Solutions Company | SAR | 415833.72 | APPROVED |  |  | 2024-11-12 | 166.28 | 9 | Babic, Marian | -45599 | 9
| ORA-01403: no data found | 4852 | Calibration of Instruments | APPROVED | No | 2024-11-10 | Abas, Mohammed Fekry | 2024-11-11 | 2024-11-11 |  |  |  | 20300 | 6384 | 0 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 18885 | APPROVED |  |  | 2024-11-17 | 1415 | 6 | Akhtar, Farhan | -45607 | 6
| ORA-01403: no data found | 4922 | Fire Pump for Neom warehose | APPROVED | No | 2024-11-13 | Abas, Mohammed Fekry | 2024-11-17 | 2024-11-18 |  |  |  | 54900 | 6614 | 0 | STANDARD | AlHareer AlSakhri Est. | SAR | 54900 | APPROVED |  |  | 2024-12-24 | 0 | 36 | Babic, Marian | -45614 | 36
| ORA-01403: no data found | 4969 | Printer | APPROVED | No | 2024-11-17 | Abas, Mohammed Fekry | 2024-11-18 | 2024-11-19 |  |  |  | 1355 | 6582 | 0 | STANDARD | Munira Suleiman Yahya Al-Fifi Trading EST | SAR | 1355 | APPROVED |  |  | 2024-12-18 | 0 | 29 | Abuhammad, Samir | -45615 | 29
| ORA-01403: no data found | 4970 | Printer | APPROVED | No | 2024-11-17 | Abas, Mohammed Fekry | 2024-11-18 | 2024-11-19 |  |  |  | 2150 | 6582 | 0 | STANDARD | Munira Suleiman Yahya Al-Fifi Trading EST | SAR | 2150 | APPROVED |  |  | 2024-12-18 | 0 | 29 | Abuhammad, Samir | -45615 | 29
| ORA-01403: no data found | 4989 | Board Meeting Table for Riyadh New office | APPROVED | No | 2024-11-19 | Abas, Mohammed Fekry | 2024-11-24 | 2024-11-24 |  |  |  | 50400 | 6544 | 0 | STANDARD | Innovate General Contracting EST. | SAR | 50400 | APPROVED |  |  | 2024-11-28 | 0 | 4 | Babic, Marian | -45620 | 4
| ORA-01403: no data found | 4991 | Furniture for Riyadh New office | APPROVED | No | 2024-11-19 | Abas, Mohammed Fekry | 2024-11-24 | 2024-11-24 |  |  |  | 278870 | 6545 | 0 | STANDARD | MAJESTIC OFFICE FOR FURNITURE | SAR | 278870 | APPROVED |  |  | 2024-12-02 | 0 | 8 | Babic, Marian | -45620 | 8
10521100008 | King Fahad National Centre for Children's Cancer (ES-0023) | 5043 | O&M Streetlights Stock for KFNCCC | APPROVED | No | 2024-11-24 | Abas, Mohammed Fekry | 2024-12-04 | 2024-12-04 |  |  |  | 17286.6 | 6600 | 0 | STANDARD | SAUDI LIGHTING CO LTD | SAR | 17286.6 | APPROVED |  |  | 2024-12-30 | 0 | 26 | Abuhammad, Samir | -45630 | 26
| ORA-01403: no data found | 5076 | NTT-Furniture for New Riyadh Office | APPROVED | No | 2024-11-28 | Abas, Mohammed Fekry | 2024-11-28 | 2024-11-28 |  |  |  | 23373 | 6573 | 0 | STANDARD | Riyadh House Branch of Jeraisy Group Company | SAR | 70119 | APPROVED |  |  | 2024-12-04 | -46746 | 6 | Babic, Marian | -45624 | 6
| ORA-01403: no data found | 5077 | NTT- RYD Office for logistics | APPROVED | No | 2024-11-28 | Abas, Mohammed Fekry | 2024-12-24 | 2024-12-25 | 2024-12-11 |  | Please revise the unit price for consumeble itmes (as per the quotations) | 96336 | 6702 | 0 | STANDARD | Arabian Business Machines | SAR | 96336 | APPROVED |  |  | 2025-01-12 | 0 | 18 | Akhtar, Farhan | -45651 | 18
| ORA-01403: no data found | 5106 | Dammam Office | RETURNED | No | 2024-12-01 | Akhtar, Farhan | 2025-07-23 | 2024-12-12 |  | 2024-12-02 |  | 18147 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45638 | -45638
| ORA-01403: no data found | 5110 | Riyadh office - Overhead | APPROVED | No | 2024-12-02 | Abas, Mohammed Fekry | 2024-12-03 | 2024-12-03 |  |  |  | 19279 | 6591 | 0 | STANDARD | Riyadh House Branch of Jeraisy Group Company | SAR | 19279 | APPROVED |  |  | 2024-12-12 | 0 | 9 | Babic, Marian | -45629 | 9
| ORA-01403: no data found | 5127 | Riyadh Office | APPROVED | No | 2024-12-04 | Abas, Mohammed Fekry | 2024-12-05 | 2024-12-08 |  |  |  | 405460 | 6647 | 0 | STANDARD | Expert Tech Est. | SAR | 405460 | APPROVED |  |  | 2025-01-22 | 0 | 45 | Babic, Marian | -45634 | 45
| ORA-01403: no data found | 5129 | Overhead- JED&RYD | APPROVED | No | 2024-12-04 | Abas, Mohammed Fekry | 2024-12-09 | 2024-12-10 |  |  |  | 140000 | 6661 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 144800 | APPROVED |  |  | 2024-12-25 | -4800 | 15 | Babic, Marian | -45636 | 15
| ORA-01403: no data found | 5130 | Printer | RETURNED | No | 2024-12-04 | Abuhammad, Samir | 2025-04-14 | 2024-12-09 | 2025-04-14 |  | Request rejected by CEO During PO Cycle. | 2820 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45635 | -45635
| ORA-01403: no data found | 5200 |  | RETURNED | No | 2024-12-09 | Abuhammad, Samir | 2025-04-14 | 2024-12-12 | 2025-04-14 |  | Request rejected by CEO During PO Cycle. | 108100 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45638 | -45638
| ORA-01403: no data found | 5203 | JEDDAH &Riyadh accommodation, ACs | APPROVED | No | 2024-12-10 | Abas, Mohammed Fekry | 2024-12-16 | 2024-12-16 |  |  |  | 2520 | 6661 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 2520 | APPROVED |  |  | 2024-12-25 | 0 | 9 | Babic, Marian | -45642 | 9
| ORA-01403: no data found | 5205 | Intenet for NIT New Office Dammam | REJECTED | No | 2024-12-10 | AlShehri, Ali | 2024-12-10 |  |  | 2024-12-11 |  | 37299 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 5216 | JEDDAH &Riyadh accommodation, ACs | APPROVED | No | 2024-12-11 | Abas, Mohammed Fekry | 2024-12-16 | 2024-12-16 |  |  |  | 4800 | 6661 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 55200 | APPROVED |  |  | 2024-12-25 | -50400 | 9 | Babic, Marian | -45642 | 9
10531109999 | Trading - Job Orders | 5224 | Supply of 13.8kV Koncar NCT at Qiran Housing Project S/S # 8367 in Riyadh | APPROVED | No | 2024-12-12 | Abas, Mohammed Fekry | 2024-12-16 | 2024-12-19 |  |  |  | 36735 | 6901 | 0 | STANDARD | KONCAR INSTRUMENT TRANSFORMERS | EUR | 36735 | APPROVED |  |  | 2025-02-20 | 0 | 63 | Babic, Marian | -45645 | 63
| ORA-01403: no data found | 5227 | Laptops | APPROVED | No | 2024-12-15 | Abas, Mohammed Fekry | 2024-12-16 | 2024-12-19 |  |  |  | 542200 | 6668 | 0 | STANDARD | Golden Technology trading Company. | SAR | 534100 | APPROVED |  |  | 2024-12-25 | 8100 | 6 | Abuhammad, Samir | -45645 | 6
| ORA-01403: no data found | 5228 | Jeddah Head office | APPROVED | No | 2024-12-15 | Abas, Mohammed Fekry | 2024-12-16 | 2024-12-19 |  |  |  | 98420 | 6829 | 0 | STANDARD | 4D Imension for contracting Company | SAR | 73620 | INCOMPLETE |  |  |  | 24800 | 409 | Akhtar, Farhan | -45645 | -45645
| ORA-01403: no data found | 5228 | Jeddah Head office | APPROVED | No | 2024-12-15 | Abas, Mohammed Fekry | 2024-12-16 | 2024-12-19 |  |  |  | 98420 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45645 | -45645
| ORA-01403: no data found | 5250 | 3X Unit PALFINGER PK30002B OFFER | APPROVED | No | 2024-12-22 | Abas, Mohammed Fekry | 2024-12-23 | 2024-12-25 |  | 2024-12-22 |  | 840000 | 6770 | 0 | STANDARD | Truck Technologies and Trading Co.L.L.C | SAR | 840000 | APPROVED |  |  | 2025-04-22 | 0 | 118 | Babic, Marian | -45651 | 118
| ORA-01403: no data found | 5251 | Dammam Warehouse | RETURNED | No | 2024-12-22 | Kumar, Mr. Ranjan | 2025-04-22 | 2024-12-25 | 2025-04-22 |  | Please raise the PR and contact with concerned Procurement official to complete PR to PO transistion. | 14000 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45651 | -45651
| ORA-01403: no data found | 5256 | Assets Overhead - Jeddah | RETURNED | No | 2024-12-22 | Babic, Marian | 2025-01-16 | 2024-12-25 | 2025-01-16 |  | not required | 7600000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45651 | -45651
| ORA-01403: no data found | 5257 | Assets - OverHead | APPROVED | No | 2024-12-22 | Abas, Mohammed Fekry | 2024-12-23 | 2024-12-25 |  |  |  | 984000 | 6771 | 0 | STANDARD | Zahid Tractor & Heavy Mch. Co. Ltd -Riyadh | SAR | 984000 | APPROVED |  |  | 2025-04-22 | 0 | 118 | Babic, Marian | -45651 | 118
| ORA-01403: no data found | 5270 | Riyadh Accoumendation | RETURNED | No | 2024-12-24 | Akhtar, Farhan | 2025-07-03 | 2025-01-01 | 2025-07-03 |  | - | 36375.5 | 6734 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 36375.5 | APPROVED |  |  | 2025-01-28 | 0 |  | Akhtar, Farhan | -45658 | 27
| ORA-01403: no data found | 5270 | Riyadh Accoumendation | RETURNED | No | 2024-12-24 | Akhtar, Farhan | 2025-07-03 | 2025-01-01 | 2025-07-03 |  | - | 11400 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45658 | -45658
| ORA-01403: no data found | 5273 | EGYPT | APPROVED | No | 2024-12-25 | Abas, Mohammed Fekry | 2024-12-26 | 2024-12-30 |  |  |  | 56000 | 6719 | 1 | STANDARD | High Point Technology Co, | SAR | 52250 | APPROVED |  |  | 2025-01-22 | 3750 | 23 | Abuhammad, Samir | -45656 | 23
| ORA-01403: no data found | 5273 | EGYPT | APPROVED | No | 2024-12-25 | Abas, Mohammed Fekry | 2024-12-26 | 2024-12-30 |  |  |  | 64000 | 6719 | 0 | STANDARD | High Point Technology Co, | SAR | 64000 | APPROVED |  |  | 2025-01-12 | 0 | 13 | Abuhammad, Samir | -45656 | 13
| ORA-01403: no data found | 5275 | Jeddah Ovderhead | APPROVED | No | 2024-12-26 | Abas, Mohammed Fekry | 2024-12-29 | 2024-12-30 |  |  |  | 897000 | 6772 | 0 | STANDARD | Machinery Rental Alternatives Co. Ltd | SAR | 888000 | APPROVED |  |  | 2025-04-17 | 9000 | 108 | Babic, Marian | -45656 | 108
| ORA-01403: no data found | 5365 | Printer | INCOMPLETE | No | [7 empty] | 800 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 5386 | Printer | RETURNED | No | 2025-01-12 | Kumar, Mr. Ranjan | 2025-04-22 | 2025-01-14 | 2025-04-22 |  | Please raise the PR and contact with concerned Procurement official to complete PR to PO transistion. | 800 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45671 | -45671
| ORA-01403: no data found | 5426 | CCTV For New Dammam Warehouse | APPROVED | No | 2025-01-15 | Abas, Mohammed Fekry | 2025-01-15 | 2025-01-16 |  |  |  | 28397.51 | 6320 | 1 | STANDARD | Megamind IT Solutions | SAR | 28397.51 | IN PROCESS |  |  |  | 0 | 381 | Akhtar, Farhan | -45673 | -45673
| ORA-01403: no data found | 5426 | CCTV For New Dammam Warehouse | APPROVED | No | 2025-01-15 | Abas, Mohammed Fekry | 2025-01-15 | 2025-01-16 |  |  |  | 28397.51 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45673 | -45673
| ORA-01403: no data found | 5439 | CCTV & Outdoor LED For Riyadh Warehouse | APPROVED | No | 2025-01-15 | Abas, Mohammed Fekry | 2025-08-28 | 2025-08-28 | 2025-04-22 |  | Please raise the PR and contact with concerned Procurement official to complete PR to PO transistion. | 27225 | 7652 | 0 | STANDARD | Zone Network Information Technology Est. | SAR | 27225 | APPROVED |  |  | 2025-09-17 | 0 | 20 | Abuhammad, Samir | -45897 | 20
| ORA-01403: no data found | 5440 | Smart Screen For Riyadh Office | APPROVED | No | 2025-01-16 | Abas, Mohammed Fekry | 2025-01-16 | 2025-01-19 |  |  |  | 40600 | 6647 | 0 | STANDARD | Expert Tech Est. | SAR | 40600 | APPROVED |  |  | 2025-01-22 | 0 | 3 | Babic, Marian | -45676 | 3
10521100008 | King Fahad National Centre for Children's Cancer (ES-0023) | 5447 | O&M Controllers for Chiller | APPROVED | No | 2025-01-16 | Abas, Mohammed Fekry | 2025-01-21 | 2025-01-23 |  |  |  | 14874.78 | 6836 | 0 | STANDARD | DAIKIN AIR CONDITIONING SAUDI ARABIA | SAR | 14874.78 | APPROVED |  |  | 2025-02-06 | 0 | 14 | Abuhammad, Samir | -45680 | 14
10522100006 | MOI Diwan Project | 5474 | Fortra's Intermapper Network Monitoring | APPROVED | No | 2025-01-20 | Abas, Mohammed Fekry | 2025-01-26 | 2025-01-27 |  |  |  | 77600 | 4559 | 0 | STANDARD | Bulwark Saudi for Information Technology | SAR | 77600 | APPROVED |  |  | 2025-02-27 | 0 | 31 | Abuhammad, Samir | -45684 | 31
| ORA-01403: no data found | 5527 | Annual Camera Maintenance Contract - Jeddah Main Warehouse | RETURNED | No | 2025-01-22 | Kumar, Mr. Ranjan | 2025-04-22 | 2025-01-26 | 2025-04-22 |  | Please raise the PR and contact with concerned Procurement official to complete PR to PO transistion. | 8120.55 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45683 | -45683
| ORA-01403: no data found | 5720 | Server License | APPROVED | No | 2025-01-29 | Abas, Mohammed Fekry | 2025-01-30 | 2025-01-30 |  |  |  | 11200 | 6865 | 0 | STANDARD | Golden Technology trading Company. | SAR | 11200 | APPROVED |  |  | 2025-02-10 | 0 | 11 | Abuhammad, Samir | -45687 | 11
| ORA-01403: no data found | 5733 | supply of Ezviz Camera | RETURNED | No | 2025-01-30 | Kumar, Mr. Ranjan | 2025-04-22 | 2025-02-05 | 2025-04-22 |  | Please raise the PR and contact with concerned Procurement official to complete PR to PO transistion. | 26040 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45693 | -45693
| ORA-01403: no data found | 5735 | support renewal of Fusion Module 800 | APPROVED | No | 2025-01-30 | Abas, Mohammed Fekry | 2025-02-04 | 2025-02-05 |  |  |  | 12997.35 | 6957 | 0 | STANDARD | REDINGTON SAUDI ARABIA DISTRIBUTION CO. | SAR | 11302 | APPROVED |  |  | 2025-03-09 | 1695.35 | 32 | Abuhammad, Samir | -45693 | 32
| ORA-01403: no data found | 5777 | Accomendation Westren Region - Jeddah Nuzha | APPROVED | No | 2025-02-04 | Abas, Mohammed Fekry | 2025-02-06 | 2025-02-09 |  |  |  | 28525 | 6906 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 28525 | APPROVED |  |  | 2025-03-09 | 0 | 28 | Akhtar, Farhan | -45697 | 28
| ORA-01403: no data found | 5778 | Accomendation Westren Region -Rabigh | APPROVED | No | 2025-02-04 | Abas, Mohammed Fekry | 2025-02-06 | 2025-02-09 |  |  |  | 14000 | 6907 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 14000 | APPROVED |  |  | 2025-03-09 | 0 | 28 | Akhtar, Farhan | -45697 | 28
| ORA-01403: no data found | 5806 | Westren Region - Jeddah Rehily | APPROVED | No | 2025-02-06 | Abas, Mohammed Fekry | 2025-02-10 | 2025-02-11 |  |  |  | 42850 | 6908 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 42850 | APPROVED |  |  | 2025-03-09 | 0 | 26 | Akhtar, Farhan | -45699 | 26
| ORA-01403: no data found | 5808 | Western Region Madinah NIT | APPROVED | No | 2025-02-06 | Abas, Mohammed Fekry | 2025-02-10 | 2025-02-11 |  |  |  | 106225 | 6909 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 106225 | APPROVED |  |  | 2025-03-11 | 0 | 28 | Akhtar, Farhan | -45699 | 28
| ORA-01403: no data found | 5810 | Estern Region - AL Hasa Accomendation | APPROVED | No | 2025-02-06 | Abas, Mohammed Fekry | 2025-02-10 | 2025-02-11 |  |  |  | 34212.5 | 6910 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 34212.5 | APPROVED |  |  | 2025-03-09 | 0 | 26 | Akhtar, Farhan | -45699 | 26
| ORA-01403: no data found | 5823 | Accomendation - South Region Farasan | APPROVED | No | 2025-02-09 | Abas, Mohammed Fekry | 2025-02-10 | 2025-02-11 |  |  |  | 19575 | 6911 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 19575 | APPROVED |  |  | 2025-03-09 | 0 | 26 | Akhtar, Farhan | -45699 | 26
| ORA-01403: no data found | 5824 | Accomendation - South Region - Khamis musheet | APPROVED | No | 2025-02-09 | Abas, Mohammed Fekry | 2025-02-10 | 2025-02-11 |  |  |  | 33650 | 6912 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 33650 | APPROVED |  |  | 2025-03-11 | 0 | 28 | Akhtar, Farhan | -45699 | 28
| ORA-01403: no data found | 5825 | Accomendation - North Region - Haqel | APPROVED | No | 2025-02-09 | Abas, Mohammed Fekry | 2025-02-10 | 2025-02-11 |  |  |  | 19962.5 | 6913 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 19962.5 | APPROVED |  |  | 2025-05-11 | 0 | 89 | Akhtar, Farhan | -45699 | 89
| ORA-01403: no data found | 5826 | Accomendation - North Region - Baada1 | APPROVED | No | 2025-02-09 | Abas, Mohammed Fekry | 2025-02-10 | 2025-02-11 |  |  |  | 1718.75 | 6914 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 1718.75 | APPROVED |  |  | 2025-05-11 | 0 | 89 | Akhtar, Farhan | -45699 | 89
| ORA-01403: no data found | 5827 | Accomendation - South Region - Baada 2 | APPROVED | No | 2025-02-09 | Abas, Mohammed Fekry | 2025-02-10 | 2025-02-11 |  |  |  | 2062.5 | 6915 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 2062.5 | APPROVED |  |  | 2025-05-11 | 0 | 89 | Akhtar, Farhan | -45699 | 89
| ORA-01403: no data found | 5828 | Accomendation - South Region - Tabouk | APPROVED | No | 2025-02-09 | Abas, Mohammed Fekry | 2025-02-10 | 2025-02-11 |  |  |  | 3062.5 | 6916 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 3062.5 | APPROVED |  |  | 2025-03-09 | 0 | 26 | Akhtar, Farhan | -45699 | 26
| ORA-01403: no data found | 5830 | Renewal fo Forigate firewall(Nesma Projects) | APPROVED | No | 2025-02-09 | Abas, Mohammed Fekry | 2025-02-13 | 2025-02-13 |  |  |  | 3847.5 | 6905 | 0 | STANDARD | Exclusive Networks For Information Systems Technology | SAR | 3847.5 | APPROVED |  |  | 2025-02-19 | 0 | 6 | Abuhammad, Samir | -45701 | 6
| ORA-01403: no data found | 5831 | Accomendation - South Region - Duba | APPROVED | No | 2025-02-09 | Abas, Mohammed Fekry | 2025-02-16 | 2025-02-16 |  |  |  | 12906.25 | 6917 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 12906.25 | APPROVED |  |  | 2025-05-12 | 0 | 85 | Akhtar, Farhan | -45704 | 85
| ORA-01403: no data found | 5832 | Accomendation- Central Region Riyadh - Monisya | APPROVED | No | 2025-02-09 | Abas, Mohammed Fekry | 2025-02-16 | 2025-02-16 |  |  |  | 20450 | 6918 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 20450 | APPROVED |  |  | 2025-03-09 | 0 | 21 | Akhtar, Farhan | -45704 | 21
| ORA-01403: no data found | 5833 | (Request for quote for the renewal of Fortigate Firewall (FGT80FTK22047782)-Jeddah Branch office | APPROVED | No | 2025-02-09 | Abas, Mohammed Fekry | 2025-02-13 | 2025-02-13 |  |  |  | 8343.75 | 7125 | 0 | STANDARD | Exclusive Networks For Information Systems Technology | SAR | 8343.75 | APPROVED |  |  | 2025-04-13 | 0 | 59 | Abuhammad, Samir | -45701 | 59
| ORA-01403: no data found | 5838 | Accomendation - Western Region - Madinah NP | APPROVED | No | 2025-02-10 | Abas, Mohammed Fekry | 2025-02-16 | 2025-02-16 |  |  |  | 1875 | 6919 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 1875 | APPROVED |  |  | 2025-03-09 | 0 | 21 | Akhtar, Farhan | -45704 | 21
| ORA-01403: no data found | 5839 | Accomendation - Eastern Region - Ain Dar | APPROVED | No | 2025-02-10 | Abas, Mohammed Fekry | 2025-02-16 | 2025-02-16 |  |  |  | 18212.5 | 6923 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 18212.5 | APPROVED |  |  | 2025-03-09 | 0 | 21 | Akhtar, Farhan | -45704 | 21
| ORA-01403: no data found | 5840 | Transportation to sites | APPROVED | No | 2025-02-10 | Abas, Mohammed Fekry | 2025-02-16 | 2025-02-16 |  |  |  | 36000 | 6909 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 36000 | APPROVED |  |  | 2025-03-11 | 0 | 23 | Akhtar, Farhan | -45704 | 23
| ORA-01403: no data found | 5862 | Accomendation - Eastern Region - Qatif | APPROVED | No | 2025-02-13 | Abas, Mohammed Fekry | 2025-02-16 | 2025-02-16 |  |  |  | 35112.5 | 6920 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 35112.5 | APPROVED |  |  | 2025-03-09 | 0 | 21 | Akhtar, Farhan | -45704 | 21
| ORA-01403: no data found | 6048 | Hi-Care Standard 9x5xNBD (Access Switch | APPROVED | No | 2025-02-25 | Abas, Mohammed Fekry | 2025-02-26 | 2025-02-26 |  |  |  | 19985.68 | 7014 | 0 | STANDARD | REDINGTON SAUDI ARABIA DISTRIBUTION CO. | SAR | 19985.68 | APPROVED |  |  | 2025-03-18 | 0 | 20 | Abuhammad, Samir | -45714 | 20
| ORA-01403: no data found | 6049 | Nesma Infrastructure & Technology) | APPROVED | No | 2025-02-25 | Abas, Mohammed Fekry | 2025-02-26 | 2025-02-26 |  |  |  | 56867.22 | 6964 | 0 | STANDARD | Excellence Arabia Trading Company | SAR | 53513 | APPROVED |  |  | 2025-03-17 | 3354.22 | 19 | Abuhammad, Samir | -45714 | 19
| ORA-01403: no data found | 6077 | Request for Quote of the Cairo Egypt office | APPROVED | No | 2025-02-27 | Abas, Mohammed Fekry | 2025-03-02 | 2025-03-03 |  |  |  | 120500 | 6995 | 0 | STANDARD | High Point Technology Co, | SAR | 120500 | APPROVED |  |  | 2025-03-13 | 0 | 10 | Abuhammad, Samir | -45719 | 10
| ORA-01403: no data found | 6078 | Nesma NIT Jeddah Office 2 - Interior Design & Fee Proposal | APPROVED | No | 2025-02-27 | Abas, Mohammed Fekry | 2025-03-02 | 2025-03-03 |  |  |  | 50000 | 6978 | 0 | STANDARD | FATEHIA M. KAMAL M. JAMJOOM DESIGN ESTABLISHMENT | SAR | 50000 | APPROVED |  |  | 2025-04-07 | 0 | 35 | Babic, Marian | -45719 | 35
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 6148 | Cable Trey materials | APPROVED | No | 2025-03-11 | Alharbi, Atef Saud | 2025-03-13 | 2025-03-13 |  |  |  | 13488.8 | 4913 | 1 | STANDARD | AL-AMAL ELECTRICAL SWITCHBOARDS | SAR | 11500 | APPROVED |  |  | 2025-03-27 | 1988.8 | 14 | Babic, Marian | -45729 | 14
| ORA-01403: no data found | 6151 | Follow-up on Site Readiness and Project Timelin | RETURNED | No | 2025-03-11 | Kumar, Mr. Ranjan | 2025-04-22 | 2025-03-12 | 2025-04-22 |  | Please raise the PR and contact with concerned Procurement official to complete PR to PO transistion. | 17120 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | -45728 | -45728
10511000001 | Overhead (JED) | 6169 | CCTV Monitoring system | APPROVED | No | 2025-03-18 | Abas, Mohammed Fekry | 2025-03-19 | 2025-03-19 |  |  |  | 127550 | 7047 | 0 | STANDARD | Al Arab Modern Contracting Est | SAR | 127550 | APPROVED |  |  | 2025-03-27 | 0 | 8 | Babic, Marian | -45735 | 8
| ORA-01403: no data found | 6180 | Request for 100 Lenovo laptops | APPROVED | No | 2025-03-13 | Abas, Mohammed Fekry | 2025-03-18 | 2025-03-20 |  |  |  | 529700 | 7070 | 0 | STANDARD | Golden Technology trading Company. | SAR | 529100 | APPROVED |  |  | 2025-04-10 | 600 | 21 | Abuhammad, Samir | -45736 | 21
| ORA-01403: no data found | 6267 | Windows Server Licenses | APPROVED | No | 2025-03-25 | Abas, Mohammed Fekry | 2025-03-27 | 2025-03-27 |  |  |  | 1960 | 7126 | 0 | STANDARD | LOGICOM SAUDI ARABIA . | SAR | 1960 | APPROVED |  |  | 2025-04-14 | 0 | 18 | Abuhammad, Samir | -45743 | 18
| ORA-01403: no data found | 6330 | Quotation Request for Dilo Machine Vacuum Pump machine | APPROVED | No | 2025-04-14 | Abas, Mohammed Fekry | 2025-05-21 | 2025-05-21 | 2025-05-18 |  | Please change the quantity and prices and resubmit again | 4978725 | 7179 | 0 | STANDARD | CIVIL ELECT.PROJECTS CONTG.CO | SAR | 4626264.5 | APPROVED |  |  | 2025-05-29 | 352460.5 | 8 | Akhtar, Farhan | -45798 | 8
| ORA-01403: no data found | 6367 | O365 batch MAR 2025 ¦ NIT | APPROVED | No | 2025-04-17 | Abas, Mohammed Fekry | 2025-04-20 | 2025-04-21 |  |  |  | 3925.93 | 7181 | 0 | STANDARD | APTEC Saudi Arabia LCC | SAR | 3422.24 | APPROVED |  |  | 2025-04-28 | 503.69 | 7 | Abuhammad, Samir | -45768 | 7
| ORA-01403: no data found | 6395 | Request 40' Container (YCC) | INCOMPLETE | No | [7 empty] | 30000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 6432 | Purchasing Trucks. | RETURNED | No | 2025-04-23 | Babic, Marian | 2025-11-02 | 2025-04-28 | 2025-11-02 |  | this is duplicated PR, already PO issued from another PR | 984000 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45775 | -45775
| ORA-01403: no data found | 6462 | ABQ-340 Al-Khobar Regional Office | APPROVED | No | 2025-04-27 | Abas, Mohammed Fekry | 2025-08-05 | 2025-08-06 |  | 2025-06-22 |  | 80000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45875 | -45875
| ORA-01403: no data found | 6467 | Bisha Accommodation furniture | APPROVED | No | 2025-05-13 | Abas, Mohammed Fekry | 2025-05-15 | 2025-05-15 |  |  | To be delivered to Bisha accommodation. | 32075 | 7355 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 32075 | APPROVED |  |  | 2025-05-29 | 0 | 14 | Akhtar, Farhan | -45792 | 14
| ORA-01403: no data found | 6469 | Request for Tow 40 feet Containers (YCC) | APPROVED | No | 2025-04-28 | Abas, Mohammed Fekry | 2025-08-17 | 2025-08-18 |  | 2025-06-16 |  | 15000 | 7208 | 0 | STANDARD | NAMMA CARGO SERVICES CO LTD - Khobar | SAR | 11500 | APPROVED |  |  | 2025-11-02 | 3500 | 76 | Badhman, Saeed | -45887 | 76
| ORA-01403: no data found | 6470 | Request for Tow 40 feet Containers(Namma) | RETURNED | No | 2025-04-28 | Badhman, Saeed | 2025-10-23 | 2025-08-18 | 2025-10-23 | 2025-05-04 | not needed | 11500 | 7208 | 0 | STANDARD | NAMMA CARGO SERVICES CO LTD - Khobar | SAR | 11500 | APPROVED |  |  | 2025-11-02 | 0 |  | Badhman, Saeed | -45887 | 76
| ORA-01403: no data found | 6470 | Request for Tow 40 feet Containers(Namma) | RETURNED | No | 2025-04-28 | Badhman, Saeed | 2025-10-23 | 2025-08-18 | 2025-10-23 | 2025-05-04 | not needed | 2400 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45887 | -45887
| ORA-01403: no data found | 6502 | PO for Abha Office | APPROVED | No | 2025-05-05 | Abas, Mohammed Fekry | 2025-05-06 | 2025-05-06 |  |  | There is a discount for your information | 89440 | 7235 | 0 | STANDARD | Abdurahman Yahya Hamoud Sadeq Contracting Est. (S) | SAR | 75000 | APPROVED |  |  | 2025-05-15 | 14440 | 9 | Babic, Marian | -45783 | 9
| ORA-01403: no data found | 6537 | NIT O365 patch April 2025 | APPROVED | No | 2025-05-06 | Abas, Mohammed Fekry | 2025-05-11 | 2025-05-11 | 2025-05-08 |  | Due to change the license code. | 1244.63 | 7244 | 0 | STANDARD | APTEC Saudi Arabia LCC | SAR | 1244.63 | APPROVED |  |  | 2025-05-15 | 0 | 4 | Abuhammad, Samir | -45788 | 4
| ORA-01403: no data found | 6581 | ZKT attendance project across all sites NIT | RETURNED | No | 2025-05-11 | Abuhammad, Samir | 2025-06-22 | 2025-05-20 | 2025-06-22 |  | Cancel the PO as they need only supply of devices. | 482500 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45797 | -45797
| ORA-01403: no data found | 6582 | Furniture request for Abqaq accommodaion | RETURNED | No | 2025-05-20 | Akhtar, Farhan | 2025-06-12 | 2025-05-21 | 2025-06-12 |  | Change the unite price and the location | 98993.04 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45798 | -45798
| ORA-01403: no data found | 6611 | Waly Alahad-3 SS in Makkah-Supply, Installation, Splicing, and Testing of Fiber Optic Cables, Patch Cords, SAS & Serial Cables, and CAT6 Cables. | REJECTED | No | 2025-05-13 | UR Rehman, Habib | 2025-05-18 | 2025-05-14 | 2025-05-15 | 2025-05-15 | Please correct the Item Description and the UOM in the PR and resend it for approval. | 260000 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45791 | -45791
| ORA-01403: no data found | 6612 | Renewal of licenses AutoCad and Acrobat | APPROVED | No | 2025-05-13 | Abas, Mohammed Fekry | 2025-05-15 | 2025-05-15 |  |  |  | 67950 | 7293 | 0 | STANDARD | Golden Technology trading Company. | SAR | 67950 | APPROVED |  |  | 2025-06-17 | 0 | 33 | Abuhammad, Samir | -45792 | 33
| ORA-01403: no data found | 6627 | Installation of Warehouse Cameras in Jazan | APPROVED | No | 2025-05-15 | Abas, Mohammed Fekry | 2025-05-18 | 2025-05-18 |  |  |  | 43047.83 | 7398 | 0 | STANDARD | BURK AL-SAMMAN For Security Surveillance Est. | SAR | 40000 | APPROVED |  |  | 2025-06-22 | 3047.83 | 35 | Akhtar, Farhan | -45795 | 35
10511000001 | Overhead (JED) | 6635 | Furniture purchase for Jeddah new accommodation | INCOMPLETE | No | [7 empty] | 2925 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 6673 | Nesma NIT Jeddah Office 2 - Interior Design & Fee Proposal | APPROVED | No | 2025-05-20 | Abas, Mohammed Fekry | 2025-05-21 | 2025-05-21 |  |  | Old P.O: 6978-0 | 80000 | 6978 | 1 | STANDARD | FATEHIA M. KAMAL M. JAMJOOM DESIGN ESTABLISHMENT | SAR | 80000 | APPROVED |  |  | 2025-06-17 | 0 | 27 | Babic, Marian | -45798 | 27
| ORA-01403: no data found | 6678 | Replacement of chairs in Dammam Office | APPROVED | No | 2025-05-21 | Abas, Mohammed Fekry | 2025-05-21 | 2025-05-21 |  |  |  | 102831 | 7354 | 0 | STANDARD | Dunya Al Mashari For Trading | SAR | 102831 | APPROVED |  |  | 2025-05-29 | 0 | 8 | Babic, Marian | -45798 | 8
| ORA-01403: no data found | 6680 | Jeddah new accomodation furniture | APPROVED | No | 2025-05-21 | Abas, Mohammed Fekry | 2025-05-22 | 2025-05-27 |  |  | to be sent to Jeddah new accommodation | 255950 | 7391 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 194862.5 | INCOMPLETE |  |  |  | 61087.5 | 250 | Badhman, Saeed | -45804 | -45804
| ORA-01403: no data found | 6680 | Jeddah new accomodation furniture | APPROVED | No | 2025-05-21 | Abas, Mohammed Fekry | 2025-05-22 | 2025-05-27 |  |  | to be sent to Jeddah new accommodation | 255950 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45804 | -45804
| ORA-01403: no data found | 6682 | Hafer Al Batin accommodation | RETURNED | No | 2025-05-21 | Akhtar, Farhan | 2025-06-12 | 2025-05-27 | 2025-06-12 |  | change the unit prices | 88412.5 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45804 | -45804
| ORA-01403: no data found | 6683 | Tindha accommodation Khamis Mushet | RETURNED | No | 2025-05-21 | Akhtar, Farhan | 2025-06-02 | 2025-05-27 | 2025-06-02 |  | change the unit price for item# 9,11 and 14 as per the offer | 58187.5 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45804 | -45804
| ORA-01403: no data found | 6685 | Related to P.R 6678 | APPROVED | No | 2025-05-22 | Abas, Mohammed Fekry | 2025-05-22 | 2025-05-25 |  |  |  | 6500 | 7354 | 0 | STANDARD | Dunya Al Mashari For Trading | SAR | 6500 | APPROVED |  |  | 2025-05-29 | 0 | 4 | Babic, Marian | -45802 | 4
| ORA-01403: no data found | 6693 | FW: NIT-Approval Request ##(100 Laptops along with mouse and bag) | APPROVED | No | 2025-05-22 | Abas, Mohammed Fekry | 2025-05-25 | 2025-05-26 |  |  |  | 529100 | 7365 | 0 | STANDARD | Golden Technology trading Company. | SAR | 526600 | APPROVED |  |  | 2025-06-04 | 2500 | 9 | Abuhammad, Samir | -45803 | 9
| ORA-01403: no data found | 6697 | Tindha accommodation Split A/cs | APPROVED | No | 2025-05-25 | Abas, Mohammed Fekry | 2025-05-25 | 2025-05-26 |  |  | These A/cs to be delivered to Tindha accommodation in Abha. | 12000 | 7371 | 0 | STANDARD | MULTI ACTIVITY SERVICES FOR TRADING | SAR | 10000 | INCOMPLETE |  |  |  | 2000 | 251 | Akhtar, Farhan | -45803 | -45803
[12 empty] | Please contact Mr. Feras Bashehab for delivere 0556094788 | [14 empty] | 0 | 0
| ORA-01403: no data found | 6697 | Tindha accommodation Split A/cs | APPROVED | No | 2025-05-25 | Abas, Mohammed Fekry | 2025-05-25 | 2025-05-26 |  |  | These A/cs to be delivered to Tindha accommodation in Abha. | 12000 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45803 | -45803
[12 empty] | Please contact Mr. Feras Bashehab for delivere 0556094788 | [14 empty] | 0 | 0
| ORA-01403: no data found | 6709 | Renewal of Fortigate Firewall license -Nesma Projects | RETURNED | No | 2025-05-26 | Abuhammad, Samir | 2025-05-27 | 2025-05-26 | 2025-05-27 |  | No need as we already issue PO No.6905-0 | 4915 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45803 | -45803
| ORA-01403: no data found | 6737 | NIT Quotation for Broadcom Endpoint | APPROVED | No | 2025-05-28 | Abas, Mohammed Fekry | 2025-05-28 | 2025-05-28 |  |  |  | 4125 | 7384 | 0 | STANDARD | APTEC Saudi Arabia LCC | SAR | 3700 | APPROVED |  |  | 2025-05-29 | 425 | 1 | Abuhammad, Samir | -45805 | 1
| ORA-01403: no data found | 6755 | PR for Jazera container | APPROVED | No | 2025-05-29 | Abas, Mohammed Fekry | 2025-06-02 | 2025-06-02 |  |  |  | 22000 | 7218 | 0 | STANDARD | Construction Expertise Est. | SAR | 22000 | APPROVED |  |  | 2025-07-03 | 0 | 31 | Badhman, Saeed | -45810 | 31
| ORA-01403: no data found | 6768 | Request for Quote | APPROVED | No | 2025-06-03 | Abas, Mohammed Fekry | 2025-06-03 | 2025-06-12 |  |  |  | 45090 | 7410 | 0 | STANDARD | Golden Technology trading Company. | SAR | 42990 | APPROVED |  |  | 2025-06-22 | 2100 | 10 | Abuhammad, Samir | -45820 | 10
| ORA-01403: no data found | 6800 | O365 License annual renewal 2025-2026 ¦ NIT | APPROVED | No | 2025-06-15 | Abas, Mohammed Fekry | 2025-06-17 | 2025-06-17 |  |  |  | 165259.97 | 7412 | 0 | STANDARD | APTEC Saudi Arabia LCC | SAR | 49896.9 | APPROVED |  |  | 2025-06-22 | 115363.07 | 5 | Abuhammad, Samir | -45825 | 5
| ORA-01403: no data found | 6803 | Qatif new accommodation | RETURNED | No | 2025-06-16 | Akhtar, Farhan | 2025-07-28 | 2025-07-27 |  |  |  | 104105 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45865 | -45865
| ORA-01403: no data found | 6806 | Thuqbah accommodation furniture completion | RETURNED | No | 2025-06-16 | Akhtar, Farhan | 2025-08-17 | 2025-07-27 |  |  |  | 27712.5 | 7561 | 0 | STANDARD | DANAH AL RAYEDA ESTABLISHMENT | SAR | 25300 | APPROVED |  |  | 2025-08-04 | 2412.5 |  | Akhtar, Farhan | -45865 | 8
| ORA-01403: no data found | 6806 | Thuqbah accommodation furniture completion | RETURNED | No | 2025-06-16 | Akhtar, Farhan | 2025-08-17 | 2025-07-27 |  |  |  | 1125 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45865 | -45865
| ORA-01403: no data found | 6837 | NI-202505007 - Technical and Commercial Proposal for Google Workspace Migration to Microsoft 365 - Revised Proposal for M365 E5 – 1700 Users v7.0 | APPROVED | No | 2025-06-19 | Abas, Mohammed Fekry | 2025-06-22 | 2025-06-26 |  |  |  | 3931538 | 7440 | 0 | STANDARD | Nesma Injazat Information Technology Company | SAR | 3931538 | APPROVED |  |  | 2025-08-21 | 0 | 56 | Abuhammad, Samir | -45834 | 56
| ORA-01403: no data found | 6838 | Request for Quote | APPROVED | No | 2025-06-19 | Abas, Mohammed Fekry | 2025-06-22 | 2025-06-26 |  |  |  | 25950 | 7482 | 0 | STANDARD | Golden Technology trading Company. | SAR | 25950 | APPROVED |  |  | 2025-07-20 | 0 | 24 | Abuhammad, Samir | -45834 | 24
| ORA-01403: no data found | 6839 | ZKT attendance project across | APPROVED | No | 2025-06-19 | Abas, Mohammed Fekry | 2025-06-22 | 2025-06-26 |  |  |  | 116000 | 7441 | 0 | STANDARD | Advance International Company | SAR | 116000 | APPROVED |  |  | 2025-07-10 | 0 | 14 | Abuhammad, Samir | -45834 | 14
| ORA-01403: no data found | 6846 | Quotation for Office Furniture Supply and Installation – New Jeddah Branch | APPROVED | No | 2025-06-22 | Abas, Mohammed Fekry | 2025-06-22 | 2025-06-22 |  |  |  | 241780 | 7420 | 0 | STANDARD | MAJESTIC OFFICE FOR FURNITURE | SAR | 450430 | APPROVED |  |  | 2025-07-14 | -208650 | 22 | Babic, Marian | -45830 | 22
| ORA-01403: no data found | 6876 | New PR for the new increased price item for Jeddah new accommodation | APPROVED | No | 2025-06-24 | Abas, Mohammed Fekry | 2025-06-30 | 2025-07-01 |  |  | As requested from procurement department. | 7500 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45839 | -45839
| ORA-01403: no data found | 6877 | New PR for Tindha accommodation | APPROVED | No | 2025-06-24 | Abas, Mohammed Fekry | 2025-06-26 | 2025-06-29 |  |  | These items to be delivered to Tindah accommodation, please contact Mr. Feras Bashehab for other inquries fr delivery | 69300 | 7448 | 0 | STANDARD | DANAH AL RAYEDA ESTABLISHMENT | SAR | 62500 | APPROVED |  |  | 2025-07-18 | 6800 | 19 | Akhtar, Farhan | -45837 | 19
| ORA-01403: no data found | 6878 | New PR for Hafer Al Batin accommodation | APPROVED | No | 2025-06-24 | Abas, Mohammed Fekry | 2025-06-26 | 2025-06-29 |  |  | These items to be sent to Hafer Al Batin new accommodation, please contact MR. Feras Bashehab for delivery infomations. | 114190 | 7447 | 0 | STANDARD | DANAH AL RAYEDA ESTABLISHMENT | SAR | 105000 | APPROVED |  |  | 2025-07-18 | 9190 | 19 | Akhtar, Farhan | -45837 | 19
| ORA-01403: no data found | 6890 | Additional Office Furniture – Jeddah Branch | APPROVED | No | 2025-06-25 | Abas, Mohammed Fekry | 2025-06-25 | 2025-06-26 |  |  |  | 15590 | 7582 | 0 | STANDARD | MAJESTIC OFFICE FOR FURNITURE | SAR | 12590 | APPROVED |  |  | 2025-09-02 | 3000 | 68 | Babic, Marian | -45834 | 68
| ORA-01403: no data found | 6951 | Hafer Al Batin accommodation | REJECTED | No | 2025-07-01 | Sahin, Feyzullah | 2025-07-02 |  |  | 2025-07-07 | These items to be sent to Hafer Al Batin new accommodation, please contact Mr. Feras for delivery instructions (0556094788) | 98339 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 6952 | Purchase of items for Nuzha accommodation Jeddah | IN PROCESS | No | 2025-07-01 | Badhman, Saeed | 2025-07-10 | 2025-07-07 |  |  |  | 29337.5 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45845 | -45845
| ORA-01403: no data found | 6954 | Items purchase for Regily accommodation | IN PROCESS | No | 2025-07-01 | Badhman, Saeed | 2025-07-10 | 2025-07-07 |  |  |  | 38787.5 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45845 | -45845
| ORA-01403: no data found | 6956 | Item purchase for Al Beda'a accommodation | IN PROCESS | No | 2025-07-01 | Badhman, Saeed | 2025-07-10 | 2025-07-07 |  |  |  | 1912.5 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45845 | -45845
| ORA-01403: no data found | 6958 | Items purchase for Haqel accommodation | IN PROCESS | No | 2025-07-01 | Badhman, Saeed | 2025-07-10 | 2025-07-07 |  |  |  | 22137.5 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45845 | -45845
| ORA-01403: no data found | 6959 | Items purchase for Deba accommodation | IN PROCESS | No | 2025-07-01 | Badhman, Saeed | 2025-07-10 | 2025-07-07 |  |  |  | 25487.5 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45845 | -45845
| ORA-01403: no data found | 6960 | Items purchase for Monsia accommodation in Riyadh | IN PROCESS | No | 2025-07-01 | Badhman, Saeed | 2025-07-10 | 2025-07-07 |  |  |  | 19825 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45845 | -45845
| ORA-01403: no data found | 6961 | Items purchase for Murjan accommodation in Riyadh | IN PROCESS | No | 2025-07-01 | Badhman, Saeed | 2025-07-10 | 2025-07-07 |  |  |  | 6375 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45845 | -45845
| ORA-01403: no data found | 6983 | CCTV at Diryiah warehouse | APPROVED | No | 2025-07-06 | Abas, Mohammed Fekry | 2025-07-21 | 2025-07-22 |  |  |  | 12617.4 | 7557 | 0 | STANDARD | BURK AL-SAMMAN For Security Surveillance Est. | SAR | 12617.4 | APPROVED |  |  | 2025-08-15 | 0 | 24 | Akhtar, Farhan | -45860 | 24
10522100006 | MOI Diwan Project | 6985 | Passive PS work | APPROVED | No | 2025-07-06 | Abas, Mohammed Fekry | 2025-07-21 | 2025-07-22 |  |  | MOI-PASSIVE PS WORK -BUDGET-CTC:4.1.1.1 | 42440 | 7596 | 0 | STANDARD | Nabea Al Gawdah Company | SAR | 42440 | APPROVED |  |  | 2025-08-21 | 0 | 30 | Abuhammad, Samir | -45860 | 30
| ORA-01403: no data found | 6986 | Al Qaisomah new accommodation | REJECTED | No | 2025-07-06 | Sahin, Feyzullah | 2025-07-08 |  |  | 2025-07-14 | These items to be delivered to Al Qaisomah new accommodation | 65775 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 7027 | Supply of TFR VT/CT board | APPROVED | No | 2025-07-09 | Alharbi, Atef Saud | 2025-07-10 | 2025-07-13 |  |  | Urgent | 19000 | 4086 | 1 | STANDARD | ADWAN MARKETING CO. | SAR | 18000 | APPROVED |  |  | 2025-09-29 | 1000 | 78 | Babic, Marian | -45851 | 78
| ORA-01403: no data found | 7059 | Q00473 Nesma, JDS CEO OFFICE | APPROVED | No | 2025-07-10 | Abas, Mohammed Fekry | 2025-07-13 | 2025-07-14 |  |  |  | 158063 | 7487 | 0 | STANDARD | Dunya Al Mashari For Trading | SAR | 141863 | APPROVED |  |  | 2025-07-22 | 16200 | 8 | Babic, Marian | -45852 | 8
| ORA-01403: no data found | 7084 | RFQ - equipment calibration | REJECTED | No | 2025-07-14 | AlShehri, Ali | 2025-07-14 |  |  | 2025-07-16 |  | 6625 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 7097 | NIT Approval Request # #Autocad 6 licenses# | APPROVED | No | 2025-07-15 | Abas, Mohammed Fekry | 2025-07-17 | 2025-07-20 |  |  |  | 38400 | 7528 | 0 | STANDARD | Golden Technology trading Company. | SAR | 38400 | APPROVED |  |  | 2025-07-23 | 0 | 3 | Abuhammad, Samir | -45858 | 3
| ORA-01403: no data found | 7146 | O365 first batch July 2025 ¦ Nesma.com ¦ NIT | APPROVED | No | 2025-07-20 | Abas, Mohammed Fekry | 2025-08-13 | 2025-08-13 |  |  |  | 3607.76 | 7571 | 0 | STANDARD | APTEC Saudi Arabia LCC | SAR | 3607.76 | APPROVED |  |  | 2025-08-19 | 0 | 6 | Abuhammad, Samir | -45882 | 6
| ORA-01403: no data found | 7159 | RFQ NIT Jeddah New Office (Randa Tower) | APPROVED | No | 2025-07-21 | Abas, Mohammed Fekry | 2025-07-21 | 2025-07-22 |  |  |  | 1394535 | 7525 | 0 | STANDARD | 4D Imension for contracting Company | SAR | 1394535 | APPROVED |  |  | 2025-07-29 | 0 | 7 | Babic, Marian | -45860 | 7
10521300010 | Rehabilitation of NAF SS (TD-0040) | 7188 | DC to AC Inverter for SAS System | APPROVED | No | 2025-07-22 | Alharbi, Atef Saud | 2025-07-24 | 2025-07-27 |  |  | Urgnet | 10545 | 7463 | 0 | STANDARD | Global Alliance Est | SAR | 10545 | APPROVED |  |  | 2025-09-25 | 0 | 60 | Babic, Marian | -45865 | 60
| ORA-01403: no data found | 7201 | [SR-54639] 1 Adobe acrobat license | APPROVED | No | 2025-07-24 | Abas, Mohammed Fekry | 2025-07-28 | 2025-07-29 |  |  |  | 1150 | 7598 | 0 | STANDARD | Golden Technology trading Company. | SAR | 1150 | APPROVED |  |  | 2025-08-13 | 0 | 15 | Abuhammad, Samir | -45867 | 15
| ORA-01403: no data found | 7214 | Request for PR-T&C Equipment's (Asset) | APPROVED | No | 2025-07-27 | Abas, Mohammed Fekry | 2025-07-28 | 2025-07-29 |  |  | There is a discuont for your refarence | 1508932 | 7573 | 0 | STANDARD | CIVIL ELECT.PROJECTS CONTG.CO | SAR | 1367843.25 | APPROVED |  |  | 2025-10-05 | 141088.75 | 68 | Akhtar, Farhan | -45867 | 68
| ORA-01403: no data found | 7216 | Request for PR-T&C Equipment's (Asset) | APPROVED | No | 2025-07-27 | Abas, Mohammed Fekry | 2025-07-28 | 2025-07-28 |  |  |  | 638081.7 | 7611 | 0 | STANDARD | MEJDAF TRADING COMPANY | SAR | 606000 | APPROVED |  |  | 2025-10-05 | 32081.7 | 69 | Akhtar, Farhan | -45866 | 69
| ORA-01403: no data found | 7243 | Additional Office Furniture – Jeddah Branch | APPROVED | No | 2025-07-30 | Abas, Mohammed Fekry | 2025-08-03 | 2025-08-03 |  |  | There is a discount for your referance | 12135 | 7582 | 0 | STANDARD | MAJESTIC OFFICE FOR FURNITURE | SAR | 10800 | APPROVED |  |  | 2025-09-02 | 1335 | 30 | Babic, Marian | -45872 | 30
| ORA-01403: no data found | 7313 | Old Riyadh office devices relocation | APPROVED | No | 2025-08-07 | Abas, Mohammed Fekry | 2025-08-10 | 2025-08-10 |  |  |  | 2250 | 7731 | 0 | STANDARD | Expert Tech Est. | SAR | 2250 | APPROVED |  |  | 2025-10-09 | 0 | 60 | Abuhammad, Samir | -45879 | 60
| ORA-01403: no data found | 7319 | NIT O365 2nd batch July 2025 | APPROVED | No | 2025-08-10 | Abas, Mohammed Fekry | 2025-08-17 | 2025-08-18 |  |  |  | 712.75 | 5945 | 0 | STANDARD | APTEC Saudi Arabia LCC | SAR | 712.75 | APPROVED |  |  | 2025-08-25 | 0 | 7 | Abuhammad, Samir | -45887 | 7
10522100006 | MOI Diwan Project | 7322 | MOI Electrical Work | APPROVED | No | 2025-08-10 | Abas, Mohammed Fekry | 2025-08-17 | 2025-08-18 |  |  | MOI-Electrical Work- Cable PR | 72000 | 7625 | 0 | STANDARD | High Point Technology Co, | SAR | 64000 | APPROVED |  |  | 2025-08-21 | 8000 | 3 | Abuhammad, Samir | -45887 | 3
| ORA-01403: no data found | 7328 | Request for 100 Laptops + Bag + Mouse | APPROVED | No | 2025-08-11 | Abas, Mohammed Fekry | 2025-08-18 | 2025-08-18 |  |  |  | 526600 | 7624 | 0 | STANDARD | Golden Technology trading Company. | SAR | 526600 | APPROVED |  |  | 2025-09-14 | 0 | 27 | Abuhammad, Samir | -45887 | 27
| ORA-01403: no data found | 7344 | Quotation for Your Jeddah – Al Taawuniya Office | APPROVED | No | 2025-08-13 | Abas, Mohammed Fekry | 2025-08-14 | 2025-08-18 |  |  |  | 23400 | 7640 | 0 | STANDARD | MAJESTIC OFFICE FOR FURNITURE | SAR | 23400 | APPROVED |  |  | 2025-09-04 | 0 | 17 | Akhtar, Farhan | -45887 | 17
| ORA-01403: no data found | 7345 | (Developer for Toshiba Copier machine -Estudio 2500 AC Riyadh) | APPROVED | No | 2025-08-13 | Abas, Mohammed Fekry | 2025-08-13 | 2025-08-13 |  |  |  | 800 | 7614 | 0 | STANDARD | Munira Suleiman Yahya Al-Fifi Trading EST | SAR | 800 | APPROVED |  |  | 2025-08-19 | 0 | 6 | Abuhammad, Samir | -45882 | 6
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 7362 | Supply SOE D20 DI module and modification of existing GE | APPROVED | No | 2025-08-14 | AlShehri, Salem Amer | 2025-08-18 | 2025-08-19 |  |  | Task no. 10.1 | 57230 | 7726 | 0 | STANDARD | TRINERGY TECHNOLOGIES SA | SAR | 51507 | APPROVED |  |  | 2025-09-29 | 5723 | 41 | Muaz, Alaa | -45888 | 41
10521300053 | Construction of Farasan Island 132/33/13.8 kV Substation in Jazan | 7371 | Lighting fixture | INCOMPLETE | No | [6 empty] | Task no. 10.1 | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | 0 | 0
| ORA-01403: no data found | 7372 | Purchase of furniture for Farasan accommodation | RETURNED | No | 2025-08-18 | Akhtar, Farhan | 2025-08-24 | 2025-08-21 | 2025-08-24 |  | purchase from Petty cash | 16890 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -45890 | -45890
10522100006 | MOI Diwan Project | 7373 | Active Passive Services MOI Visitior Buildings and Between Buildings | REJECTED | No | 2025-08-18 | Abseh, Qusai Khaled Mohammad | 2025-08-18 |  |  | 2025-08-19 | PR For Active Passive Services-MOI | 64310 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 7394 | Supply of Licenses Microsoft O365 - O365 first batch August 2025 | APPROVED | No | 2025-08-19 | Abas, Mohammed Fekry | 2025-08-20 | 2025-08-21 |  |  |  | 1379.68 | 7634 | 0 | STANDARD | APTEC Saudi Arabia LCC | SAR | 1151 | APPROVED |  |  | 2025-08-28 | 228.68 | 7 | Abuhammad, Samir | -45890 | 7
10521300043 | Construction of Hada-2 (Andalus) 115/13.8kv Substation | 7407 | Asphalt works and Steel boundary fence | REJECTED | No | 2025-08-21 | Sherif, Marwa | 2025-08-25 | 2025-08-21 |  | 2025-08-27 |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45890 | -45890
| ORA-01403: no data found | 7417 | Toshiba e Studio Document Imaging Solution | APPROVED | No | 2025-08-21 | Abas, Mohammed Fekry | 2025-08-24 | 2025-08-26 |  |  |  | 18600 | 7628 | 0 | STANDARD | Arabian Business Machines | SAR | 18600 | APPROVED |  |  | 2025-09-03 | 0 | 8 | Akhtar, Farhan | -45895 | 8
10522100006 | MOI Diwan Project | 7438 | Power Bi Service-MOI | APPROVED | No | 2025-08-24 | Abas, Mohammed Fekry | 2025-08-26 | 2025-08-26 |  |  | PowerBI-Dashboard-MOI | 198000 | 7647 | 0 | STANDARD | Business Space Company Limited | SAR | 198000 | APPROVED |  |  | 2025-09-08 | 0 | 13 | Abuhammad, Samir | -45895 | 13
10521300060 | INTERCONNECTION OF NAWARYAH SUBSTATION | 7441 | Supply of Cybersecurity System | INCOMPLETE | No | [6 empty] | PowerBI-Dashboard-MOI | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | 0 | 0
10521300048 | Construction of Uruba 115/13.8kv Substation | 7472 | Cable Glands and Lugs | INCOMPLETE | No | [6 empty] | PowerBI-Dashboard-MOI | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | 0 | 0
10521300036 | CONSTRUCTION OF WALY ALAHAD-3 110/13.8 KV SUBSTATION IN MAKKAH | 7477 | Design, Supply, Installation, Termination, Testing, and Commissioning of the Premises Distribution System (PDS) Cabling. | REJECTED | No | 2025-08-25 | Yamama, Loai Mohamed | 2025-08-26 | 2025-08-25 |  | 2025-08-26 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45894 | -45894
10521300017 | CONSTRUCTION OF NEW 132/33kV NIC NORTH (NIC NR) S/S & NIC EV2 S/S. | 7496 | Supply of Lighting Fixtures (Amendment PO #8722) | REJECTED | No | 2025-08-26 | Yamama, Loai Mohamed | 2025-08-27 | 2025-08-27 |  | 2025-08-28 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45896 | -45896
10521300025 | POWER SUPPLY TO HAFAR AL-BATIN INDUSTRIAL CITY 115/33kV SUBSTATION (SUBSTATION PORTION) | 7499 | GIB Steel Support Structure (Approved Manual PO# 7483) | REJECTED | No | 2025-08-26 | Sherif, Marwa | 2025-08-26 | 2025-08-26 |  | 2025-08-28 |  | 20165.6 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45895 | -45895
| ORA-01403: no data found | 7500 | PO No.8736-0 Intenet for NIT New Office Dammam | APPROVED | No | 2025-08-26 | Abas, Mohammed Fekry | 2025-08-28 | 2025-08-28 |  |  |  | 36200 | 7722 | 0 | STANDARD | Zone Network Information Technology Est. | SAR | 36200 | APPROVED |  |  | 2025-11-10 | 0 | 74 | Abuhammad, Samir | -45897 | 74
10521300036 | CONSTRUCTION OF WALY ALAHAD-3 110/13.8 KV SUBSTATION IN MAKKAH | 7502 | Design, Supply, Installation, Termination, Testing, and Commissioning of the Premises Distribution System (PDS) Cabling. | REJECTED | No | 2025-08-26 | Yamama, Loai Mohamed | 2025-08-27 | 2025-08-26 |  | 2025-08-27 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45895 | -45895
10522100006 | MOI Diwan Project | 7505 | Active Passive Work-MOI | APPROVED | No | 2025-08-26 | Abas, Mohammed Fekry | 2025-08-28 | 2025-08-28 |  |  | Activie Passive Services-MOI-Budget Task-4.1.1.1 | 64310 | 7650 | 0 | STANDARD | Nabea Al Gawdah Company | SAR | 64310 | APPROVED |  |  | 2025-09-28 | 0 | 31 | Abuhammad, Samir | -45897 | 31
10521300045 | Construction of Abu Maan 115/13.8kV Substation | 7518 | Rubber Duct Seal for Spare Cable Openings | REJECTED | No | 2025-08-27 | Abdel Naiem, Tarek Ali | 2025-08-27 |  |  | 2025-08-27 | Line Item 2.13, Rubber Duct Seal for Spare Cable Openings | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | 0 | 0
| ORA-01403: no data found | 7523 | NIT new Randa Tower office IT Requirements | RETURNED | No | 2025-08-27 | Abuhammad, Samir | 2025-10-12 | 2025-08-28 | 2025-10-12 |  | No need these items as per update and confirmation email. | 325550 | 7011 | 0 | STANDARD | Fan Al Turath Trading Company. | SAR | 228050 | APPROVED |  |  | 2025-10-02 | 97500 |  | Abuhammad, Samir | -45897 | 35
| ORA-01403: no data found | 7523 | NIT new Randa Tower office IT Requirements | RETURNED | No | 2025-08-27 | Abuhammad, Samir | 2025-10-12 | 2025-08-28 | 2025-10-12 |  | No need these items as per update and confirmation email. | 230600 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45897 | -45897
10522100006 | MOI Diwan Project | 7539 | FOC Cable MOI | APPROVED | No | 2025-08-27 | Abas, Mohammed Fekry | 2025-08-28 | 2025-08-28 |  |  | FOC Cable MOI - budget Task#4.1.1.1 | 17492 | 7651 | 0 | STANDARD | APTEC Saudi Arabia LCC | SAR | 17492 | APPROVED |  |  | 2025-09-09 | 0 | 12 | Abuhammad, Samir | -45897 | 12
| ORA-01403: no data found | 7569 | Head phones | APPROVED | No | 2025-08-28 | Abas, Mohammed Fekry | 2025-08-31 | 2025-09-01 |  |  |  | 11400 | 7669 | 0 | STANDARD | Golden Technology trading Company. | SAR | 10200 | APPROVED |  |  | 2025-09-15 | 1200 | 14 | Abuhammad, Samir | -45901 | 14
| ORA-01403: no data found | 7570 | Request for AutoCAD and Acrobat DC License | APPROVED | No | 2025-08-28 | Abas, Mohammed Fekry | 2025-08-31 | 2025-09-01 |  |  |  | 7600 | 7669 | 0 | STANDARD | Golden Technology trading Company. | SAR | 7588 | APPROVED |  |  | 2025-09-15 | 12 | 14 | Abuhammad, Samir | -45901 | 14
10521300058 | Construction of Rumah 380kV BSP 9077 and Installation of Line Reactors at Airport North & PS3 BSP | 7577 | MV cables | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
10521300043 | Construction of Hada-2 (Andalus) 115/13.8kv Substation | 7578 | Asphalt Works and Steel Fence | INCOMPLETE | No | [7 empty] | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10521300058 | Construction of Rumah 380kV BSP 9077 and Installation of Line Reactors at Airport North & PS3 BSP | 7582 | MV cable | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
| ORA-01403: no data found | 7589 | Supply Accessories at Dammam Office | APPROVED | No | 2025-08-31 | Abas, Mohammed Fekry | 2025-08-31 | 2025-09-01 |  |  |  | 38473.74 | 7703 | 0 | STANDARD | Ayar Balcony Contracting Company | SAR | 38474 | APPROVED |  |  | 2025-09-24 | -0.26 | 23 | Babic, Marian | -45901 | 23
| ORA-01403: no data found | 7625 | Toshiba Color Multifunction Machine ¦ Randa Tower ¦ NIT 1st Floor | APPROVED | No | 2025-09-02 | Abas, Mohammed Fekry | 2025-09-03 | 2025-09-03 |  |  |  | 52964 | 7733 | 0 | STANDARD | Arabian Business Machines | SAR | 52964 | APPROVED |  |  | 2025-10-02 | 0 | 29 | Abuhammad, Samir | -45903 | 29
10521300046 | Construction of Wadi Al-Dhahran 115/13.8kv Substation | 7637 | 40*6 Copper Tape | REJECTED | No | 2025-09-04 | Issa, Amr Ali | 2025-09-04 | 2025-09-04 |  | 2025-09-04 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | -45904 | -45904
10521300046 | Construction of Wadi Al-Dhahran 115/13.8kv Substation | 7646 | 40*6 Copper Tape | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | 0 | 0
10521300043 | Construction of Hada-2 (Andalus) 115/13.8kv Substation | 7648 | Steel Fence and Asphalt Works | INCOMPLETE | No | [7 empty] | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10521300036 | CONSTRUCTION OF WALY ALAHAD-3 110/13.8 KV SUBSTATION IN MAKKAH | 7664 | Supply of cable Tray | REJECTED | No | 2025-09-07 | Yamama, Loai Mohamed | 2025-09-08 | 2025-09-07 |  | 2025-09-08 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | -45907 | -45907
| ORA-01403: no data found | 7698 | Request for Lenovo Yoga X1 Laptop | APPROVED | No | 2025-09-09 | Abas, Mohammed Fekry | 2025-09-10 | 2025-09-10 |  |  |  | 9800 | 7686 | 0 | STANDARD | Kayan Advanced System Trading Est | SAR | 9595 | APPROVED |  |  | 2025-09-29 | 205 | 19 | Abuhammad, Samir | -45910 | 19
10521300046 | Construction of Wadi Al-Dhahran 115/13.8kv Substation | 7748 | CAT 6 Cable | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | 0 | 0
| ORA-01403: no data found | 7755 | Riyadh Office Attendance Machines installation ¦ Parking floor | APPROVED | No | 2025-09-15 | Abas, Mohammed Fekry | 2025-09-16 | 2025-09-21 |  |  |  | 1270 | 7743 | 0 | STANDARD | Expert Tech Est. | SAR | 1270 | APPROVED |  |  | 2025-10-09 | 0 | 18 | Abuhammad, Samir | -45921 | 18
| ORA-01403: no data found | 7767 | PO No.8736-0 Intenet for NIT New Office Dammam | RETURNED | No | 2025-09-16 | Abuhammad, Samir | 2025-10-01 | 2025-09-21 | 2025-10-01 |  | wrong PR as the correct issued under PR#7770 | 1099 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45921 | -45921
| ORA-01403: no data found | 7770 | PO No.8736-0 Intenet for NIT New Office Dammam | APPROVED | No | 2025-09-17 | Abas, Mohammed Fekry | 2025-09-18 | 2025-09-21 |  |  |  | 13188 | 7722 | 0 | STANDARD | Zone Network Information Technology Est. | SAR | 13188 | APPROVED |  |  | 2025-11-10 | 0 | 50 | Abuhammad, Samir | -45921 | 50
10521300062 | Increasing the Electrical Power of King Fahd Causeway | 7781 | Auxalary Transformer | REJECTED | No | 2025-09-18 | Sendi, Fahad Fawaz | 2025-09-22 | 2025-09-18 |  | 2025-09-22 | please approve the PR for the Auxiliary Transformers | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45918 | -45918
10521300062 | Increasing the Electrical Power of King Fahd Causeway | 7789 | Total station & level device | INCOMPLETE | No | [6 empty] | please approve the PR for the Auxiliary Transformers | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
| ORA-01403: no data found | 7797 | ABM Toshiba Printer | APPROVED | No | 2025-09-22 | Abas, Mohammed Fekry | 2025-09-29 | 2025-09-30 |  |  |  | 18295 | 7780 | 0 | STANDARD | Arabian Business Machines | SAR | 18295 | APPROVED |  |  | 2025-10-07 | 0 | 7 | Abuhammad, Samir | -45930 | 7
| ORA-01403: no data found | 7807 | NIT O365 License 01 Month Extend till 24 Oct | APPROVED | No | 2025-09-21 | Abas, Mohammed Fekry | 2025-09-22 | 2025-09-23 |  |  |  | 17958.7 | 7742 | 0 | STANDARD | APTEC Saudi Arabia LCC | SAR | 17958.7 | APPROVED |  |  | 2025-09-29 | 0 | 6 | Abuhammad, Samir | -45923 | 6
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 7817 | Supply of Synchronizing Relay | APPROVED | No | 2025-09-24 | Alharbi, Atef Saud | 2025-10-01 | 2025-10-05 |  |  | Task number 10.1 for Control panels | 0 | 7857 | 0 | STANDARD | power and control system contracting Establishment | SAR | 59500 | APPROVED |  |  | 2025-11-06 | -59500 | 32 | Babic, Marian | -45935 | 32
10521300023 | CONSTRUCTION OF AL-MURJAN 132/13.8kV SUBSTATION # 8274 IN RIYADH CITY | 7868 | Construction of Al Murjan | INCOMPLETE | No | [6 empty] | Task number 10.1 for Control panels | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | 0 | 0
10521300023 | CONSTRUCTION OF AL-MURJAN 132/13.8kV SUBSTATION # 8274 IN RIYADH CITY | 7874 | % | REJECTED | No | 2025-10-01 | Bahuwayni, Mr. Abdulrahman Saleh | 2025-10-02 | 2025-10-01 |  | 2025-10-02 |  | 1 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45931 | -45931
10521300023 | CONSTRUCTION OF AL-MURJAN 132/13.8kV SUBSTATION # 8274 IN RIYADH CITY | 7905 | % | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Mohammed, Faisal Ansari | 0 | 0
| ORA-01403: no data found | 7930 | Additional costs for the boards at RYD | APPROVED | No | 2025-10-08 | Abas, Mohammed Fekry | 2025-10-08 | 2025-10-08 |  |  |  | 17260 | 7824 | 0 | STANDARD | Shadda Public Relations and Communications Est | SAR | 17260 | APPROVED |  |  | 2025-10-26 | 0 | 18 | Babic, Marian | -45938 | 18
| ORA-01403: no data found | 7932 | Adobe acrobat license | APPROVED | No | 2025-10-08 | Abas, Mohammed Fekry | 2025-10-13 | 2025-10-13 |  |  |  | 1150 | 7809 | 0 | STANDARD | Golden Technology trading Company. | SAR | 1150 | APPROVED |  |  | 2025-10-19 | 0 | 6 | Abuhammad, Samir | -45943 | 6
10521300032 | CONSTRUCTION OF MEDNO-3 SS | 7943 | Fiber Optic inside Ss | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
10521300032 | CONSTRUCTION OF MEDNO-3 SS | 7944 | Telecom Cable inside SS | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10521300053 | Construction of Farasan Island 132/33/13.8 kV Substation in Jazan | 7946 | 33 KV 1000mm2 plugin Termination | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | 0 | 0
10522100006 | MOI Diwan Project | 7968 | LAN configuration & LLD design for MOI. | APPROVED | No | 2025-10-15 | Abas, Mohammed Fekry | 2025-10-19 | 2025-10-19 |  |  | Lan Configuration For MOI | 0 | 7879 | 0 | STANDARD | High Point Technology Co, | SAR | 60000 | APPROVED |  |  | 2025-11-11 | -60000 | 23 | Abuhammad, Samir | -45949 | 23
| ORA-01403: no data found | 7973 | signboard at RYD office | APPROVED | No | 2025-10-16 | Abas, Mohammed Fekry | 2025-10-19 | 2025-10-19 |  |  | To be note, There is a discount from supplier | 77501 | 7824 | 0 | STANDARD | Shadda Public Relations and Communications Est | SAR | 69750 | APPROVED |  |  | 2025-10-26 | 7751 | 7 | Babic, Marian | -45949 | 7
10521300060 | INTERCONNECTION OF NAWARYAH SUBSTATION | 7981 | Link Boxes | INCOMPLETE | No | [6 empty] | To be note, There is a discount from supplier | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | 0 | 0
| ORA-01403: no data found | 7982 | Nesma_Access points | RETURNED | No | 2025-10-16 | Abuhammad, Samir | 2025-10-21 | 2025-10-21 | 2025-10-21 |  | for modification brand | 5680 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -45951 | -45951
10521300032 | CONSTRUCTION OF MEDNO-3 SS | 7990 | testt | INCOMPLETE | No | [6 empty] | for modification brand | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
| ORA-01403: no data found | 7994 | Additional NIT new Randa Tower office IT Requirements | APPROVED | No | 2025-10-19 | Abas, Mohammed Fekry | 2025-10-23 | 2025-10-25 |  |  |  | 4080 | 7839 | 0 | STANDARD | Fan Al Turath Trading Company. | SAR | 4080 | APPROVED |  |  | 2025-10-30 | 0 | 5 | Abuhammad, Samir | -45955 | 5
10521300053 | Construction of Farasan Island 132/33/13.8 kV Substation in Jazan | 8012 | tet | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdulqader, Ahmed Abdulhalim | 0 | 0
| ORA-01403: no data found | 8014 | Request for Monitors and headphones | APPROVED | No | 2025-10-20 | Abas, Mohammed Fekry | 2025-10-22 | 2025-10-23 |  |  |  | 15450 | 7843 | 0 | STANDARD | Excellence Arabia Trading Company | SAR | 15290 | APPROVED |  |  | 2025-11-04 | 160 | 12 | Abuhammad, Samir | -45953 | 12
10521300060 | INTERCONNECTION OF NAWARYAH SUBSTATION | 8018 | Link Boxes | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | 0 | 0
10521100008 | King Fahad National Centre for Children's Cancer (ES-0023) | 8025 | KFNCCC - Streetlights for O&M | APPROVED | No | 2025-10-22 | Abas, Mohammed Fekry | 2025-10-23 | 2025-10-25 |  |  |  | 0 | 7840 | 0 | STANDARD | SAUDI LIGHTING CO LTD | SAR | 9592.8 | APPROVED |  |  | 2025-11-06 | -9592.8 | 12 | Abuhammad, Samir | -45955 | 12
| ORA-01403: no data found | 8027 | Additional O365 Licenses required for NIT post migration functional continuity | APPROVED | No | 2025-10-22 | Abas, Mohammed Fekry | 2025-10-26 | 2025-10-27 |  |  |  | 14111.16 | 7911 | 0 | STANDARD | Nesma Injazat Information Technology Company | SAR | 14111.16 | APPROVED |  |  | 2025-11-23 | 0 | 27 | Abuhammad, Samir | -45957 | 27
| ORA-01403: no data found | 8028 | Wifi devices at NIT new Randa Tower office IT Requirements | APPROVED | No | 2025-10-22 | Abas, Mohammed Fekry | 2025-10-23 | 2025-10-25 |  |  |  | 7840 | 7839 | 0 | STANDARD | Fan Al Turath Trading Company. | SAR | 7840 | APPROVED |  |  | 2025-10-30 | 0 | 5 | Abuhammad, Samir | -45955 | 5
| ORA-01403: no data found | 8029 | Cabinet installation at NIT new Randa Tower office IT Requirements | APPROVED | No | 2025-10-22 | Abas, Mohammed Fekry | 2025-10-23 | 2025-10-25 |  |  |  | 9600 | 7839 | 0 | STANDARD | Fan Al Turath Trading Company. | SAR | 9600 | APPROVED |  |  | 2025-10-30 | 0 | 5 | Abuhammad, Samir | -45955 | 5
10521300031 | CONSTRUCTION OF HARAM-3 SS | 8037 | Diesel for GENSET | REJECTED | No | 2025-10-23 | Ghith, Saad Gamal | 2025-10-29 | 2025-10-23 |  | 2025-10-29 |  | 100000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -45953 | -45953
| ORA-01403: no data found | 8048 | Supplies at Randa Tower 1st floor | APPROVED | No | 2025-10-26 | Abas, Mohammed Fekry | 2025-10-28 | 2025-10-29 |  |  |  | 2470 | 7420 | 1 | STANDARD | MAJESTIC OFFICE FOR FURNITURE | SAR | 2470 | APPROVED |  |  | 2025-11-04 | 0 | 6 | Babic, Marian | -45959 | 6
10521300062 | Increasing the Electrical Power of King Fahd Causeway | 8052 | MV Cables for reclaimer island | REJECTED | No | 2025-10-26 | Bahuwayni, Mr. Abdulrahman Saleh | 2025-10-30 | 2025-10-28 |  | 2025-11-02 | This request is a replacement related to return PR No. 7838, so it remains within the tender quantities | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | -45958 | -45958
10521300032 | CONSTRUCTION OF MEDNO-3 SS | 8061 | Civil Scope | INCOMPLETE | No | [6 empty] | This request is a replacement related to return PR No. 7838, so it remains within the tender quantities | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
| ORA-01403: no data found | 8062 | PR for cars Dashcams and GPS | INCOMPLETE | No | [6 empty] | This request is a replacement related to return PR No. 7838, so it remains within the tender quantities | 264725 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 8064 | PR Request Dashcam - AVL | APPROVED | No | 2025-10-27 | Abas, Mohammed Fekry | 2025-11-13 | 2025-11-16 |  | 2025-10-30 |  | 535035 | [5 empty] | 0 |  |  |  |  | 0 |  | Badhman, Saeed | -45977 | -45977
| ORA-01403: no data found | 8072 | Price Comparison-Quotation Rahaili Accommodation | APPROVED | No | 2025-10-28 | Abas, Mohammed Fekry | 2025-10-29 | 2025-10-30 |  |  |  | 114000 | 7842 | 0 | STANDARD | Amjad Al Youm Contracting. | SAR | 114000 | APPROVED |  |  | 2025-11-05 | 0 | 6 | Abuhammad, Samir | -45960 | 6
| ORA-01403: no data found | 8098 | 1st Floor switch Raised on behalf of logistics team | APPROVED | No | 2025-10-29 | Abas, Mohammed Fekry | 2025-11-02 | 2025-11-04 |  |  |  | 20700 | 7864 | 0 | STANDARD | Fan Al Turath Trading Company. | SAR | 20700 | APPROVED |  |  | 2025-11-12 | 0 | 8 | Abuhammad, Samir | -45965 | 8
10521300058 | Construction of Rumah 380kV BSP 9077 and Installation of Line Reactors at Airport North & PS3 BSP | 8116 | SUBSTATION SECURITY SYSTEM | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
| ORA-01403: no data found | 8133 | Copilot License for nit.com.sa - NI-202509047-BH - M365 Co-Pilot NIT | APPROVED | No | 2025-11-05 | Abas, Mohammed Fekry | 2025-11-06 | 2025-11-09 |  |  |  | 7110 | 7919 | 0 | STANDARD | Nesma Injazat Information Technology Company | SAR | 7110 | APPROVED |  |  | 2025-11-23 | 0 | 14 | Abuhammad, Samir | -45970 | 14
10521300060 | INTERCONNECTION OF NAWARYAH SUBSTATION | 8134 | Telecommunication System | REJECTED | No | 2025-11-09 | Ghaleb, Nour Mahmoud Omaya | 2025-11-11 | 2025-11-10 |  | 2025-11-11 |  | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45971 | -45971
| ORA-01403: no data found | 8142 | maintenance of Dilo Machine | APPROVED | No | 2025-11-05 | Abas, Mohammed Fekry | 2025-11-06 | 2025-11-09 |  |  |  | 26906 | 7856 | 0 | STANDARD | GULF EXPERTS COMPANY LIMITED | SAR | 26906 | APPROVED |  |  | 2025-11-13 | 0 | 4 | Babic, Marian | -45970 | 4
| ORA-01403: no data found | 8143 | Upgrading network grid at company offices in Randa tower | APPROVED | No | 2025-11-05 | Abas, Mohammed Fekry | 2025-11-10 | 2025-11-11 |  |  |  | 37000 | 7892 | 0 | STANDARD | Zone Network Information Technology Est. | SAR | 37000 | APPROVED |  |  | 2025-11-23 | 0 | 12 | Abuhammad, Samir | -45972 | 12
10521300009 | Expansion of 380/110/13.8kV Rabigh Substation (110kV GIS extension) (TD-0040) | 8147 | MODIFICATION OF EXISTING GE SOER SYSTEM WITH ONE 020 DI MODULE AT RABIGH-I SS | APPROVED | No | 2025-11-06 | Alharbi, Atef Saud | 2025-11-09 | 2025-11-11 |  |  | task No. 10.1 (Control and Protection) | 0 | 7726 | 1 | STANDARD | TRINERGY TECHNOLOGIES SA | SAR | 51507 | APPROVED |  |  | 2025-12-03 | -51507 | 22 | Babic, Marian | -45972 | 22
10521300062 | Increasing the Electrical Power of King Fahd Causeway | 8182 | grounding material for KFSA project | INCOMPLETE | No | [6 empty] | task No. 10.1 (Control and Protection) | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
| ORA-01403: no data found | 8184 | Consultancy for LEED certification (Gold) | APPROVED | No | 2025-11-11 | Abas, Mohammed Fekry | 2025-11-12 | 2025-11-13 |  |  |  | 62727 | 7858 | 0 | STANDARD | TUV SUD for Safety Engineering | SAR | 62727 | APPROVED |  |  | 2025-11-16 | 0 | 3 | Alhadi, Khalid | -45974 | 3
10521300062 | Increasing the Electrical Power of King Fahd Causeway | 8224 | Lighting for KFCA | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
| ORA-01403: no data found | 8240 | O365 License 02 Months Extension till January 24, 2026 | APPROVED | No | 2025-11-17 | Abas, Mohammed Fekry | 2025-11-18 | 2025-11-19 |  |  |  | 34517.72 | 7891 | 0 | STANDARD | APTEC Saudi Arabia LCC | SAR | 34517.72 | APPROVED |  |  | 2025-11-23 | 0 | 4 | Abuhammad, Samir | -45980 | 4
10521300041 | Construction of Bayoniyah (South Khobar) 115/13.8kv Substation | 8256 | Motor for Bayouniah Main Gate | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Abdelghaffar Abuelseoud, Mr. Mohamed Ahmed | 0 | 0
| ORA-01403: no data found | 8323 | Hafer Albatin - Warehouse | APPROVED | No | 2025-11-23 | Abas, Mohammed Fekry | 2025-11-24 | 2025-11-24 |  |  |  | 66000 | 7939 | 0 | STANDARD | Najd Developers General Contracting Establishment | SAR | 66000 | APPROVED |  |  | 2025-12-07 | 0 | 13 | Abuhammad, Samir | -45985 | 13
10521300058 | Construction of Rumah 380kV BSP 9077 and Installation of Line Reactors at Airport North & PS3 BSP | 8331 | ACDB,DCDB and lighting panels | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
10521300058 | Construction of Rumah 380kV BSP 9077 and Installation of Line Reactors at Airport North & PS3 BSP | 8332 | ACDB , DCDB , LIGHTING Panels | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 8335 | Kitchen Upgrade 5th Floor | APPROVED | No | 2025-11-25 | Abas, Mohammed Fekry | 2025-11-30 | 2025-12-02 |  |  |  | 35007.5 | 8024 | 0 | STANDARD | 4D Imension for contracting Company | SAR | 35007.5 | APPROVED |  |  | 2025-12-25 | 0 | 23 | Babic, Marian | -45993 | 23
10521300067 | 380kV OHTL SAMHA BSP #9105 | 8336 | EDS | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10521300062 | Increasing the Electrical Power of King Fahd Causeway | 8339 | protection & Control system for KFCA project | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
10521300020 | CONSTRUCTION OF JAFURAH 380/230kV BSP . | 8343 | GIS | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
| ORA-01403: no data found | 8349 | PO for transformer transportation - Farasan Island | RETURNED | No | 2025-11-25 | Babic, Marian | 2025-12-09 | 2025-12-02 | 2025-12-09 |  | this PR should be raised from the project budget | 457050 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -45993 | -45993
10521300063 | 230 KV AND 115KV INTERTIES PROJECT IN JUBAIL | 8352 | Cybersecurity | INCOMPLETE | No | [6 empty] | this PR should be raised from the project budget | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10521300058 | Construction of Rumah 380kV BSP 9077 and Installation of Line Reactors at Airport North & PS3 BSP | 8358 | NGR | INCOMPLETE | No | [6 empty] | this PR should be raised from the project budget | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
10521300035 | OHTL CONSTRUCTION OF 132kV BETWEEN PSSA and PSSB IN NEOM | 8369 | xyz | INCOMPLETE | No | [6 empty] | this PR should be raised from the project budget | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | 0 | 0
10521300060 | INTERCONNECTION OF NAWARYAH SUBSTATION | 8423 | Telecommunication System | INCOMPLETE | No | [6 empty] | this PR should be raised from the project budget | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | 0 | 0
10521300034 | SUBSTATIONS CONSTRUCTION OF 132/33 KV NM PSS-A & PSS-B IN NEOM | 8450 | DGA for Power Transformers - NM PSS-B | INCOMPLETE | No | [6 empty] | this PR should be raised from the project budget | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Kumar, Mr. Ranjan | 0 | 0
| ORA-01403: no data found | 8468 | Makkah Nawariya | INCOMPLETE | No | [6 empty] | this PR should be raised from the project budget | 27900 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 8469 | Makkah Nawariya | RETURNED | No | 2025-12-07 | Akhtar, Farhan | 2025-12-29 | 2025-12-14 | 2025-12-29 |  | PO issued with new PR-8531 (PR-8469 should be cancelled) | 28850 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -46005 | -46005
| ORA-01403: no data found | 8485 | remove the existing sign at RYD | APPROVED | No | 2025-12-18 | Abas, Mohammed Fekry | 2025-12-22 | 2025-12-23 |  |  |  | 25000 | 8046 | 0 | STANDARD | Horizon Marketing Communications | SAR | 25000 | APPROVED | 2025-12-25 | 2025-12-26 | 2026-01-19 | 0 | 27 | Abuhammad, Samir | 3 | 27
10511000001 | Overhead (JED) | 8493 | test | INCOMPLETE | No | [7 empty] | 2 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
10521300063 | 230 KV AND 115KV INTERTIES PROJECT IN JUBAIL | 8497 | Supply of OPGW and OPGW Joint Box | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Alhadi, Khalid | 0 | 0
| ORA-01403: no data found | 8502 | Furnitures for Accomdation (Riyadh murjan ) | APPROVED | No | 2025-12-11 |  |  | 2026-01-13 | 2026-01-01 |  | please change the unit prices and resubmit again | 18815 | 7590 | 0 | STANDARD | DANAH AL RAYEDA ESTABLISHMENT | SAR | 26000 | APPROVED | 2026-01-19 | 2026-01-26 | 2026-01-28 | -7185 | 15 | Akhtar, Farhan | 13 | 15
| ORA-01403: no data found | 8505 | Furnitures for Accomdation (Jeddah Nuzha ) | APPROVED | No | 2025-12-11 |  |  | 2026-01-13 | 2026-01-05 |  | Please recheck. PO already issued for this location- PO-6906 | 34565 | 7591 | 0 | STANDARD | DANAH AL RAYEDA ESTABLISHMENT | SAR | 29000 | IN PROCESS |  |  |  | 5565 | 19 | Akhtar, Farhan | -46035 | -46035
| ORA-01403: no data found | 8505 | Furnitures for Accomdation (Jeddah Nuzha ) | APPROVED | No | 2025-12-11 |  |  | 2026-01-13 | 2026-01-05 |  | Please recheck. PO already issued for this location- PO-6906 | 34565 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -46035 | -46035
| ORA-01403: no data found | 8516 | Technician fees | REJECTED | No | 2025-12-14 | Sahin, Feyzullah | 2026-01-15 |  |  | 2026-01-18 |  | 4000 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 8525 | 100 Lenovo laptop - Test run | INCOMPLETE | No | [7 empty] | 523100 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 8530 | Jeddah Rehily accommodation furniture renwel | REJECTED | No | 2025-12-16 | Ghazzawi, Modar Qusay Hussain | 2025-12-17 |  |  | 2026-01-07 |  | 83250 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 8531 | Makkah Nawariya new furniture | APPROVED | No | 2025-12-16 | Abas, Mohammed Fekry | 2025-12-18 | 2025-12-18 |  |  |  | 47830 | 7821 | 0 | STANDARD | DANAH AL RAYEDA ESTABLISHMENT | SAR | 42000 | APPROVED | 2025-12-29 | 2026-01-01 | 2026-01-05 | 5830 | 18 | Akhtar, Farhan | 14 | 18
| ORA-01403: no data found | 8565 | quotation to Close of SEC points at Tabuk warehouse | APPROVED | No | 2025-12-22 | Abas, Mohammed Fekry | 2025-12-24 | 2025-12-24 |  |  |  | 12622 | 15033 | 0 | STANDARD | AlHareer AlSakhri Est. | SAR | 12622 | APPROVED | 2026-01-08 | 2026-01-13 | 2026-01-14 | 0 | 21 | Abuhammad, Samir | 20 | 21
| ORA-01403: no data found | 8578 | Additional Fee signed bord | APPROVED | No | 2025-12-23 | Abas, Mohammed Fekry | 2025-12-28 | 2025-12-31 |  |  |  | 7000 | 8046 | 1 | STANDARD | Horizon Marketing Communications | SAR | 7000 | APPROVED | 2026-01-21 | 2026-01-25 | 2026-01-26 | 0 | 26 | Abuhammad, Samir | 25 | 26
| ORA-01403: no data found | 8613 | Request for 100 Laptops + Bag + Mouse | APPROVED | No | 2025-12-30 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-13 |  |  |  | 531600 | 15039 | 0 | STANDARD | Golden Technology trading Company. | SAR | 531600 | APPROVED | 2026-01-19 | 2026-01-21 | 2026-01-28 | 0 | 15 | Abuhammad, Samir | 8 | 15
| ORA-01403: no data found | 8624 | Hafer Al Batin new blankets | APPROVED | No | 2026-01-04 | Abas, Mohammed Fekry | 2026-01-06 | 2026-01-07 |  |  |  | 16650 | 15024 | 0 | STANDARD | DANAH AL RAYEDA ESTABLISHMENT | SAR | 14850 | APPROVED | 2026-01-07 | 2026-01-13 | 2026-01-14 | 1800 | 7 | Akhtar, Farhan | 6 | 7
| ORA-01403: no data found | 8654 | Customer requested replace of Internal storage tank pipe (broken) | APPROVED | No | 2026-01-07 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-08 |  |  |  | 13885 | 7856 | 1 | STANDARD | GULF EXPERTS COMPANY LIMITED | SAR | 13885 | IN PROCESS | 2026-01-26 | 2026-01-29 |  | 0 | 24 | Babic, Marian | 21 | -46030
| ORA-01403: no data found | 8654 | Customer requested replace of Internal storage tank pipe (broken) | APPROVED | No | 2026-01-07 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-08 |  |  |  | 13885 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | -46030 | -46030
| ORA-01403: no data found | 8662 | Rahily new items | APPROVED | No | 2026-01-07 | Abas, Mohammed Fekry | 2026-01-19 | 2026-01-20 | 2026-01-18 |  | change the item description for Washing machine 12 KG instead of 9KG | 105955 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -46042 | -46042
| ORA-01403: no data found | 8663 | Al Beda'a new items | APPROVED | No | 2026-01-07 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-08 |  |  |  | 18540 | 15063 | 0 | STANDARD | DANAH AL RAYEDA ESTABLISHMENT | SAR | 22600 | IN PROCESS |  |  |  | -4060 | 24 | Akhtar, Farhan | -46030 | -46030
| ORA-01403: no data found | 8663 | Al Beda'a new items | APPROVED | No | 2026-01-07 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-08 |  |  |  | 18540 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -46030 | -46030
| ORA-01403: no data found | 8664 | Haqel new items | APPROVED | No | 2026-01-07 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-08 |  |  |  | 4585 | 15063 | 0 | STANDARD | DANAH AL RAYEDA ESTABLISHMENT | SAR | 9770 | IN PROCESS |  |  |  | -5185 | 24 | Akhtar, Farhan | -46030 | -46030
| ORA-01403: no data found | 8664 | Haqel new items | APPROVED | No | 2026-01-07 | Abas, Mohammed Fekry | 2026-01-08 | 2026-01-08 |  |  |  | 4585 | [5 empty] | 0 |  |  |  |  | 0 |  | Akhtar, Farhan | -46030 | -46030
| ORA-01403: no data found | 8666 | Calibration Certificate | APPROVED | No | 2026-01-12 | Abas, Mohammed Fekry | 2026-01-15 | 2026-01-15 |  |  |  | 20300 | 6384 | 1 | STANDARD | Alfanar Co-Testing & Commissioning. | SAR | 91550 | APPROVED | 2026-01-15 | 2026-01-21 | 2026-01-22 | -71250 | 7 | Babic, Marian | 6 | 7
| ORA-01403: no data found | 8673 | O365 licenses 01 month | APPROVED | No | 2026-01-12 | Abas, Mohammed Fekry | 2026-01-19 | 2026-01-20 |  |  |  | 2627.75 | 15048 | 0 | STANDARD | APTEC Saudi Arabia LCC | SAR | 2627.75 | IN PROCESS |  |  |  | 0 | 12 | Abuhammad, Samir | -46042 | -46042
| ORA-01403: no data found | 8673 | O365 licenses 01 month | APPROVED | No | 2026-01-12 | Abas, Mohammed Fekry | 2026-01-19 | 2026-01-20 |  |  |  | 2627.75 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46042 | -46042
10521300066 | JUBAIL NORTH 230/34.5 KV BSP | 8716 | supply 230/34.5/13.8 KV 133 MVA Power Transformers and 230 KV , 80 MVAR Shunt Reactors | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 8734 | Core Switch-Hi-Care Standard S6730-H48X6C_Renewals | IN PROCESS | No | 2026-01-19 | Mengash, Khalid | 2026-01-22 |  |  |  |  | 14467.26 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 8735 | Switch-Hi-Care Standard S5736-S24UM4XC-Renewals | IN PROCESS | No | 2026-01-19 | Mengash, Khalid | 2026-01-22 |  |  |  |  | 50352.61 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 8737 | MicroStation 12-month subscription license | APPROVED | No | 2026-01-19 | Abas, Mohammed Fekry | 2026-01-25 | 2026-01-26 |  |  |  | 9250 | 15064 | 0 | STANDARD | Golden Technology trading Company. | SAR | 9250 | INCOMPLETE |  |  |  | 0 | 6 | Abuhammad, Samir | -46048 | -46048
| ORA-01403: no data found | 8737 | MicroStation 12-month subscription license | APPROVED | No | 2026-01-19 | Abas, Mohammed Fekry | 2026-01-25 | 2026-01-26 |  |  |  | 9250 | [5 empty] | 0 |  |  |  |  | 0 |  | Abuhammad, Samir | -46048 | -46048
10521300067 | 380kV OHTL SAMHA BSP #9105 | 8766 | Steel Rebars | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | 0 | 0
10521300065 | JUBAIL SOUTH EAST 230/115/34.5kV BSP | 8767 | 115KV GIS including Special Tools as per PTS-24ER208 | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | 0 | 0
10521300065 | JUBAIL SOUTH EAST 230/115/34.5kV BSP | 8770 | Telecome System for Main Substation including all Remote Ends as per PTS-24ER208 | INCOMPLETE | No | [7 empty] | 0 | [5 empty] | 0 |  |  |  |  | 0 |  | Babic, Marian | 0 | 0
| ORA-01403: no data found | 8795 | Welcome Kits for new joiners (Office and Site) | APPROVED | No | 2026-01-26 | Abas, Mohammed Fekry | 2026-01-26 | 2026-01-26 |  |  | Kindly for your approval. | 132500 | [5 empty] | 0 |  |  |  |  | 0 |  |  | -46048 | -46048
| ORA-01403: no data found | 8830 | NIT Huawei HI-Care | IN PROCESS | No | 2026-01-29 | Mengash, Khalid | 2026-01-29 |  |  |  | Kindly for your approval. | 19213.38 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 8831 | be - Hi-Care Standard 9x5xNBD support for Fusion Module 800 | IN PROCESS | No | 2026-01-29 | Mengash, Khalid | 2026-01-29 |  |  |  | Kindly for your approval. | 17580.63 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0
| ORA-01403: no data found | 8832 | - Hi-Care Standard 9x5xNBD support for OceanStor Dorado 3000 V6 storage | IN PROCESS | No | 2026-01-29 | Mengash, Khalid | 2026-01-29 |  |  |  | Kindly for your approval. | 25325.75 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0 | 0

## Statistics
| previous period |  | this month |  |  | total |  | this month
Forwarded to Vendor | Nos |  | Nos |  | Nos | Nos | Total | Total
Within 15 days | 0 |  | 33 |  | #VALUE! | 33
16 to 30 Days | 0 |  | 18 |  | #VALUE! | 18
31 to 45 Days | 0 |  | 18 |  | #VALUE! | 18
46 and above Days | 0 |  | 18 |  | #VALUE! | 18
|  |  | 0 | 0 | #VALUE! |  | #VALUE!
|  |  | 0 | 0 | #VALUE! |  | #VALUE!
| 0 | 0 | 87 | 0 | #VALUE! | 87 | #VALUE! | 0
previous period
Within 15 days |  | 0 |  | 40866772 | #VALUE! | 0 | #VALUE! | 40866772
16 to 30 Days |  | 0 |  | 4979491 | #VALUE! | 0 |  | 4979491
31 to 45 Days |  | 0 |  | 85663612 | #VALUE! | 0 |  | 85663612
46 and above Days |  | 0 |  | 7452849 | #VALUE! | 0 |  | 7452849
| 0 | 0 | 0 | 138962724 | #VALUE! | 0 | #VALUE! | 138962724

## Sheet1
PR | PO | under approval
7483 | 4142 | 5243
7661 | 4828 | 5243
7736 | 5317 | 5243
7803 | 5536 | 5514
7812 | 5635 | 5514
7840 | 5638 | 5584
7941 | 5638 | 5584
8024 | 5638 | 5647
8080 | 5638 | 5647
8089 | 5678 | 5665
8130 | 6031 | 5665
8179 | 6031 | 5665
8185 | 6039 | 5680
8219 | 6043 | 5680
8222 | 6047 | 5680
8223 | 6258 | 6320
8237 | 6259 | 6320
8370 | 6384 | 6586
8404 | 6446 | 6586
8425 | 6502 | 6586
8427 | 6561 | 6794
8428 | 6586 | 6826
8430 | 6586 | 6826
8456 | 6803 | 6826
8489 | 7336 | 6842
8502 | 7338 | 6842
8504 | 7339 | 7082
8505 | 7340 | 7082
8515 | 7342 | 7259
8518 | 7345 | 7259
8534 | 7347 | 7344
8535 | 7351 | 7348
8536 | 7363 | 7467
8537 | 7364 | 7467
8538 | 7367 | 7467
8544 | 7368 | 7467
8556 | 7395 | 7497
8557 | 7470 | 7497
8558 | 7543 | 7508
8559 | 7543 | 7508
8561 | 7553 | 7566
8571 | 7587 | 7566
8574 | 7590 | 7591
8575 | 7590 | 7641
8576 | 7605 | 7707
8577 | 7646 | 7708
8579 | 7677 | 7728
8582 | 7748 | 7805
8584 | 7795 | 7810
8585 | 7821 | 7853
8586 | 7827 | 7856
8588 | 7830 | 7856
8589 | 7835 | 7887
8590 | 7845 | 7890
8591 | 7851 | 7890
8592 | 7861 | 7906
8593 | 7862 | 7908
8594 | 7890 | 7916
8595 | 7900 | 7918
8596 | 7924 | 7953
8597 | 7933 | 7954
8598 | 7935 | 7955
8599 | 7938 | 7955
8602 | 7942 | 7967
8603 | 7942 | 7993
8604 | 7961 | 8001
8605 | 7962 | 8027
8608 | 7963 | 8029
8610 | 7965 | 8029
8612 | 7966 | 8040
8613 | 7973 | 8047
8614 | 7992 | 15023
8615 | 7996 | 15025
8616 | 8002 | 15026
8617 | 8003 | 15032
8619 | 8008 | 15044
8620 | 8011 | 15048
8621 | 8013 | 15051
8624 | 8020 | 15061
8626 | 8021 | 15063
8627 | 8028 | 15063
8628 | 8031
8629 | 8036
8630 | 8038
8631 | 8046
8632 | 8046
8633 | 15000
8634 | 15004
8635 | 15015
8636 | 15020
8637 | 15024
8638 | 15029
8640 | 15030
8641 | 15033
8642 | 15035
8643 | 15036
8644 | 15039
8645 | 15040
8647 | 15041
8648 | 15042
8649
8650
8651
8652
8653
8654
8655
8656
8657
8658
8659
8660
8661
8662
8663
8664
8665
8666
8668
8669
8670
8672
8673
8677
8678
8680
8681
8682
8683
8684
8685
8686
8687
8688
8689
8691
8692
8693
8694
8695
8696
8697
8698
8699
8701
8702
8704
8705
8706
8708
8709
8710
8713
8715
8717
8718
8720
8721
8722
8723
8724
8725
8726
8727
8728
8729
8730
8731
8732
8733
8736
8737
8739
8740
8741
8742
8743
8745
8746
8747
8748
8749
8750
8751
8752
8753
8754
8755
8757
8758
8759
8760
8762
8763
8764
8765
8768
8769
8771
8772
8773
8774
8775
8776
8777
8778
8779
8780
8781
8782
8783
8784
8785
8786
8787
8788
8789
8791
8792
8793
8794
8795
8797
8798
8799
8800
8801
8802
8803
8804
8805
8806
8809
8810
8811
8812
8813
8814
8815
8816
8817
8818
8819
8821
8823
8825
8826
8827
8828
8829
8834