## Sheet 2 (hidden)
No. | Job Order# | Arraival Port | Supplier | Shipment Name | Freight Type | Project Code | Project | Value (USD) | Arrival Date | Clearance Date | Clearance period (Days) | Custom Duty | Demurage cost (SAR) | Detention Charges (SAR) | Total Custom Clearance (SAR) | Remarks
1 |  | Jeddah | LS ELECTRIC | 145 kv GIS Spare part | Seafreight | HV-1222 | Al-Jawad | 163417 | 2022-05-28 |  |  | 5%
2 |  | Jeddah | Schreder | SF#14-R3-17-AS | Seafreight | ES-211 | Riyadh phase 3 | 316057.62 | 2022-06-02 |  |  | 5%
3 |  | Jeddah | Schreder | SF#14-R3-18-AS | Seafreight | ES-211 | Riyadh phase 3 | 485451.12 | 2022-06-02 |  |  | 5%
4 |  | Jeddah | Schreder | SF#14-R3-19-AS | Seafreight | ES-211 | Riyadh phase 3 | 329279.03 | 2022-06-02 |  |  | 5%
5 |  | Jeddah | Schreder | SF#14-R3-20-AS | Seafreight | ES-211 | Riyadh phase 3 | 7192.43 | 2022-06-02 |  |  | 5%
6 |  | Jeddah | Securna | Supply of wireless network equipment - Antenna - 1st batch | Airfreight | CS-187 | RED SEA | 55269 | 2022-06-04 | [6 empty] | DDP - Arready arrived
7 |  | Jeddah | Securna | Battery | Seafreight | CS-187 | RED SEA | 78846 | 2022-06-06
8 |  | Jeddah | Schreder | SF#14-J5-11-AS | Seafreight | ES-213 | Jeddah Phase 5 | 300422.36 | 2022-06-07
9 |  | Jeddah | Securna | Supply of Wireless Network Equipment (2nd) | Airfreight | CS-187 | RED SEA | TBD | 2022-06-07 | [6 empty] | DDP
10 |  | TBD | Easy world for communication Est. | Supply of CCTV/POE - Videotec (Camera and accessories) | Airfreight | CS-187 | RED SEA | TBD | 2022-06-07 | [6 empty] | DDP
11 |  | TBD | CANFORD AUDIO LIMITED | Supply of Cabinet IP66 | Airfreight | CS-187 | RED SEA | 9416.18 | 2022-06-12 | [6 empty] | DDP
12 |  | Jeddah | Schreder | SF#14-J5-12-AS | Seafreight | ES-213 | Jeddah Phase 5 | TBD | 2022-06-20
13 |  | Jeddah | Schreder | SF#14-J5-13-AS | Seafreight | ES-213 | Jeddah Phase 5 | TBD | 2022-06-27
14 |  | Jeddah | SKY NETWORKS | Supply of 6M Pole | Seafreight | CS-187 | RED SEA | 8330 |  |  |  | 15%
15 |  | TBD | Easy world for communication Est. | Supply of CCTV/POE Moxa industrial ethernt switch and power supply | TBD | CS-187 | RED SEA | TBD |  |  |  | TBD
17 |  | Dammam | Trident Structures Pvt Ltd | Cow Tower - 2 units | Seafreight | CS-187 | RED SEA | TBD |  |  |  | 15%
18 |  | Dammam | Trident Structures Pvt Ltd | Cow Tower - 4 units | Seafreight | CS-187 | RED SEA | TBD |  |  |  | 15%
19 |  | Jeddah | Realfiction ApS / Paraddax | HD32 Stand | TBD | NTT - SARAB | NTT Overheaad | TBD |  |  |  | TBD |  |  |  | Put on hold as per PM request
20 |  | Jeddah | PREIS GROUP | Supply of Transformer bushing | TBD | HV-1144 | Jeddah Gate | 3600 |  |  |  | TBD
21 |  | TBD | Koncar | 380kV outdoor current Transformer | SeaFreight | Sales & Trading | TBD - Bidding purpose | 75000 |  |  |  | TBD
22 |  | Jeddah | Securna | Supply of Wireless Network Equipment - 2nd ship - 2nd batch - 30 W Controllers | Airfreight | CS-187 | RED SEA | TBD |  |  |  | TBD |  |  |  | DDP
23 |  | Jeddah | Securna | Supply of wireless network equipment - 3rd shipment - 2nd batch - Parabolic Antennas | Airfreight | CS-187 | RED SEA | TBD |  |  |  | TBD |  |  |  | DDP
24 |  |  |  | Light | TBD | NTT - SARAB | NTT Overheaad | TBD |  |  |  | TBD
25 |  |  | Koncar | GIS Parts | Seafreight | HV-1317 | NAF | 390000 |  |  |  | 5% |  |  |  | still waiting for the final draft document and the supplier to fill the excel form of the product to start the registration on SABER. We have obtained a booking on 12th of July but it depens on the readiness

## Schreder email (hidden)
No. | Job Order # | Shipment Name | Demurage cost (SAR) | Detention Charges (SAR) | Total Demurage + Detention | Total Custom Clearance (SAR) | DHL Tracking | Document arrival date to bank as per DHL tracking | Original docuemt recived date from Bank | Original Document receival date as per DHL tracking | Shipment Arrival Date | Sadad notification date | Custom payment | Delivery Order Linking date
1 | SIC220772 | SF#14-R3-08-AS | 2700 | 3720 | 6420 | 51488.1 | 8406406606 | 17/4/2022 | 2022-04-25
2 | SIC220703 | SF#14-J5-08-AS | 2700 | 3240 | 5940 | 61586.61 | 1625971152 |  |  | 20/4/2022 | 26/04/2022 | 28/4/2022 | 2022-01-05 | 2022-07-05
3 | SIC220766 | SF#14-R3-12-AS | 11250 | 0 | 11250 | 143430.48 | 9000766213 |  |  | 21/4/2022 | 2022-03-05 | 2022-01-05 | 2022-09-05
4 | SIC220791 | SF#14-R3-09-AS | 12450 | 3780 | 16230 | 105388.65 | 4729461833 | 26/4/2022 | 2022-05-09 |  | 2022-03-05 | 2022-12-05 | 16/5/2022
5 | SIC220792 | SF#14-R3-10-AS | 4150 | 1920 | 6070 | 37088.66 | 4729461833 | 26/4/2022 | 2022-05-09 |  | 2022-03-05 | 2022-12-05 | 15/5/2022
6 | SIC220793 | SF#14-R3-11-AS | 4150 | 1920 | 6070 | 42418.86 | 4729461833 | 26/4/2022 | 2022-05-09 |  | 2022-03-05 | 2022-11-05 | 16/5/2022
7 | SIC220787 | SF#14-R3-13-AS | 11250 | 5820 | 17070 | 161578.08 | 4729461833 | 26/4/2022 | 2022-05-09 |  | 2022-07-05 | 2022-11-05 | 16/5/2022
8 | SIC220789 | SF#14-R3-14-AS | 4500 | 2400 | 6900 | 85167.95 | 4729461833 | 26/4/2022 | 2022-05-09 |  | 2022-07-05 | 2022-11-05 | 16/5/2022
9 | SIC220811 | SF#14-R3-15-AS | 0 | 2475.4 | 2475.4 | 155809.53 | 1357988936 | 28/4/2022 | 2022-05-09 |  | 16/5/2022 | 16/5/2022 | 18/5/2022
10 | SIC220812 | SF#14-R3-16-AS | 0 | 1080 | 1080 | 63315.96 | 1357988936 | 28/4/2022 | 2022-05-09 |  | 16/5/2022 | 16/5/2022 | 18/5/2022
|  |  |  | Total | 79505.4

## Sheet4 (hidden)
No. | Job Order # | Shipment Name | Demurage cost (SAR) | Detention Charges (SAR) | Total Demurage + Detention | DHL Tracking | Document arrival date to bank as per DHL tracking | Original docuemt recived date from Bank | Original document received directly (Not LC) | Shipment Arrival Date | Sadad notification date | Custom payment | Delivery Order Linking date | Shipment notification to YCC | Shipment delivery Date | Reasons | Vendor Charges | YCC Charges
1 | SIC220772 | SF#14-R3-08-AS | 2700 | 3720 | 6420 | 8406406606 | 17/4/2022 | 25/4/2022 |  | 26/4/2022 | 29/4/2022 | 30/4/2022 | 2022-07-05 | 2022-08-05 | 22/5/2022 | Vendor is responsible for the demmurage and part of the detention charges until 12th of May. YCC (Clearance Agent) is responsible for the detention charges from 13th of May until 22nd of May
2 | SIC220703 | SF#14-J5-08-AS | 2700 | 3240 | 5940 | 1625971152 |  |  | 20/4/2022 | 26/04/2022 | 28/4/2022 | 2022-01-05 | 2022-07-05 | 15/5/2022 | 21/5/2022 | Vendor is responsible for the demmurage and part of the detention charges until 13th of May. YCC (Clearance Agent) is responsible for the detention charges from 19th of May until 21st of May Rest of the days, 3 days was due to the fact that warehous is full.
3 | SIC220766 | SF#14-R3-12-AS | 11250 | 0 | 11250 | 9000766213 |  |  | 21/4/2022 | 2022-03-05 | 2022-01-05 | 2022-08-05 |  | 2022-08-05 | 14/5/2022
4 | SIC220791 | SF#14-R3-09-AS | 12450 | 3780 | 16230 | 4729461833 | 26/4/2022 | 2022-09-05 |  | 2022-03-05 | 2022-12-05 | 16/5/2022 |  | 18/5/2022 | 23/5/2022 | Vendor is responsible for the demmurage and detention
5 | SIC220792 | SF#14-R3-10-AS | 4150 | 1920 | 6070 | 4729461833 | 26/4/2022 | 2022-09-05 |  | 2022-03-05 | 2022-12-05 | 15/5/2022 |  | 20/5/2022 | 25/5/2022 | Vendor is responsible for the demmurage and detention
6 | SIC220793 | SF#14-R3-11-AS | 4150 | 1920 | 6070 | 4729461833 | 26/4/2022 | 2022-09-05 |  | 2022-03-05 | 2022-11-05 | 16/5/2022 |  | 20/5/2022 | 25/5/2022 | Vendor is responsible for the demmurage and detention
7 | SIC220787 | SF#14-R3-13-AS | 11250 | 5820 | 17070 | 4729461833 | 26/4/2022 | 2022-09-05 |  | 2022-07-05 | 2022-11-05 | 16/5/2022 |  | 21/5/2022 | 26/5/2022 | Vendor is responsible for the demmurage and detention
8 | SIC220789 | SF#14-R3-14-AS | 4500 | 2400 | 6900 | 4729461833 | 26/4/2022 | 2022-09-05 |  | 2022-07-05 | 2022-11-05 | 16/5/2022 |  | 21/5/2022 | 26/5/2022 | Vendor is responsible for the demmurage and detention
9 | SIC220811 | SF#14-R3-15-AS | 0 | 2475.4 | 2475.4 | 1357988936 | 28/4/2022 | 2022-09-05 |  | 16/5/2022 | 16/5/2022 | 18/5/2022 |  | 21/5/2022 | 30/5/2022 , 31/5/2022 , 2/6/2022 | Vendor is responsible for the demmurage and part of the detention charges until 26th of May. YCC (Clearance Agent) is responsible for the detention charges from 26th of May until 2nd of June
10 | SIC220812 | SF#14-R3-16-AS | 0 | 1080 | 1080 | 1357988936 | 28/4/2022 | 2022-09-05 |  | 16/5/2022 | 16/5/2022 | 18/5/2022 |  | 21/5/2022 | 2022-01-06 | Vendor is responsible for the demmurage and part of the detention charges until 26th of May. YCC (Clearance Agent) is responsible for the detention charges from 26th of May until 1st of June
|  |  |  | Total | 79505.4

## LC documents (hidden)
LC NO | BANK NAME | Beneficiary Name | Project | DUE DATE | Currency | Amount in SAR | Payment Amount USD
W074315-001 | SFB | Schreder Gulf Lighting LLC | TARSHID PROJECT - Riyadh Phase 3 | 2022-07-26 | USD | 892,822.05 | 238,085.88 | SF#14-R3-04-AS | 2022-04-25
W074315-002 | SFB | Schreder Gulf Lighting LLC | TARSHID PROJECT - Riyadh Phase 3 | 2022-07-27 | USD | 884,952.23 | 235,987.26 | SF#14-R3-08-AS | 2022-04-25
W074315-003 | SFB | Schreder Gulf Lighting LLC | TARSHID PROJECT - Riyadh Phase 3 | 2022-07-26 | USD | 1,166,372.36 | 311,032.63 | SF#14-R3-07-AS | 2022-04-25
W074315-004 | SFB | Schreder Gulf Lighting LLC | TARSHID PROJECT - Riyadh Phase 3 | 2022-08-03 | USD | 608,805.00 | 162,348.00 | SF#14-R3-10-AS | 2022-05-09
W074315-005 | SFB | Schreder Gulf Lighting LLC | TARSHID PROJECT - Riyadh Phase 3 | 2022-08-03 | USD | 714,353.63 | 190,494.30 | SF#14-R3-11-AS | 2022-05-09
W074315-006 | SFB | Schreder Gulf Lighting LLC | TARSHID PROJECT - Riyadh Phase 3 | 2022-08-03 | USD | 1,755,973.09 | 468,259.49 | SF#14-R3-09-AS | 2022-05-09
W074315-007 | SFB | Schreder Gulf Lighting LLC | TARSHID PROJECT - Riyadh Phase 3 | 2022-08-08 | USD | 1,542,375.00 | 411,300.00 | SF#14-R3-14-AS | 2022-05-09
W074315-008 | SFB | Schreder Gulf Lighting LLC | TARSHID PROJECT - Riyadh Phase 3 | 2022-08-08 | USD | 2,847,882.08 | 759,435.22 | SF#14-R3-13-AS | 2022-05-09
W074315-009 | SFB | Schreder Gulf Lighting LLC | TARSHID PROJECT - Riyadh Phase 3 | 2022-08-16 | USD | 1,224,909.90 | 326,642.64 | SF#14-R3-16-AS | 2022-05-09
W074315-010 | SFB | Schreder Gulf Lighting LLC | TARSHID PROJECT - Riyadh Phase 3 | 2022-08-16 | USD | 3,022,656.08 | 806,041.62 | SF#14-R3-15-AS | 2022-05-09
W074315-011 | SFB | Schreder Gulf Lighting LLC | TARSHID PROJECT - Riyadh Phase 3 | 2022-08-22 | USD | 1,185,216.08 | 316,057.62 | SF#14-R3-17-AS | 2022-05-18
W074315-012 | SFB | Schreder Gulf Lighting LLC | TARSHID PROJECT - Riyadh Phase 3 | 2022-09-06 | USD | 1,820,441.70 | 485,451.12 | SF#14-R3-18-AS | 2022-06-02
W074315-013 | SFB | Schreder Gulf Lighting LLC | TARSHID PROJECT - Riyadh Phase 3 | 2022-09-06 | USD | 1,234,796.36 | 329,279.03 | SF#14-R3-19-AS | 2022-06-02

## Under Clearance June (hidden)
No. | Arraival Port | Supplier | Shipment Name | Freight Type | Project Code | Project | Value (USD) | Arrival Date | Projected Custom Duty | Estimated Custom duty Cost (SAR) | Remarks
1
2
3
4
5

## Under preparation
No. | Job Order # | Shipped from | Arrival port | Supplier | Shipment Name | Freight Type | Project Code | Project | Value (USD) | Projected Custom Duty | Estimated Custom duty Cost (SAR) | Contractual Arrival Date | Remark
1 |  |  | Jeddah | brugcables | cable sealing ends | sea frieght | HV 8171 , HV8242 | Diriyah 8171, 8242 | TBD | TBD | TBD | 2025-03-01
2 |  |  | Jeddah | TBD | Supply of DMR | TBD | 105-113 | NEOM | TBD | TBD | TBD | 2026-02-01
3 |  |  | Dammam | HYUNDAI | GIS | sea frieght | TBD | alhada | TBD | TBD | TBD | 2023-08-01
4 |  |  | Jeddah | tridelta | surge arrester | TBD | HV-1638 | bisha | TBD | TBD | TBD | 2026-02-01
5 |  |  | Damam | HYUNDAI | GIS | sea frieght | TBD | HADRIYAH | TBD | TBD | TBD | 2026-02-01
6 |  |  | Dammam | Lorünser | (Tubular Bus bars / Tubes +Connectors+conecters | sea frieght | TBD | HADRIYAH | TBD | TBD | TBD | 2026-04-01
7 |  |  | TBD | koncar | Grounding transformer | TBD | HV-1638 | bisha | TBD | TBD | TBD | 2026-02-01
8 |  |  | TBD | hyundai | shunt reactor | air frieght | HV 105-131 | FARASAN | TBD | 5% | TBD | 2026-04-01

## Waiting for Arrival - Jan-26
No. | Job Order # | Shipped From | Arraival Port | Supplier | Shipment Name | Freight Type | Project Code | Project | Value (USD) | Estimated Arrival Date | Contractual Date of arrival | Custom Duty Project | Estimated Custom Duty Cost (SAR) | Remarks
1 | TBD | China | Jeddah | HYOSUNG | transformer | Seafrieht | HV1638 | bisha | 8629200 | 2026-02-15 | 2026-02-01 | 15% | 4853925
2 | TBD | china | jeddah | lingrfan | Voltage Stabilizer | Seafrieht | HV 105-131 | FARASAN | 45500 | 2026-02-10 | Npv-25 | 0 | 0
3 | Serivice CO | china | Dammam | ztt | OPGW | sea frieght | HV1405 | ain dar | 8205 | 2026-02-10 | 2025-10-01 | 0 | 0
4 | AIC260295 | Spain | jeddah | arruti | Connectors and Clamps | air freight | HV 105-131 | FARASAN | 25999.74 | 2026-02-02 | 2026-02-01 | 5% , 15% | 6562.89
[9 empty] | 8708904.74 |  |  |  | 4860487.89
[8 empty] | SAR | 32658392.775

## Under Clearance - Jan-26
No. | Job Order # | Shipped From | Arraival Port | Supplier OR subject mail | Shipment Name | Freight Type | Project Code | Project | Value (USD) | Arrival Date | Contractual Arrival Date | Projected Custom Duty | Estimated Custom duty Cost (SAR) | Remarks
[9 empty] | #REF! |  |  |  | #REF!
#REF!

## Cleared - Jan-26
No. | Job Order # | Shipped From | Arraival Port | Supplier | Shipment Name | Freight Type | Project Code | Project | Value (USD) | Arrival Date | Clearance Date | Contractual Arrival Date | Clearance period (Days) | Custom Duty | Demurage cost (SAR) | Detention Charges (SAR) | Total Custom Clearance (SAR) | Remarks | Remarks
1 |  |  | damam | arruti | Connectors and Clamps | air freight | 8386 | sharfiyah | 1365.47 | 2026-01-23 | 2026-01-23 | 2025-11-01 | 0 | 15% | 0 | 0 | 441.5
2 |  |  | jeddah | ste | Indoor current transformer | sea freight | HV 105-112 | Medno | 3552.66 | 2026-01-14 | 2026-01-14 | 2025-11-01 | 0 | 15% | 0 | 0 | 1998.3712
3 |  |  | Dammam | iscns | gis sealing end | air freight | HV1393-0 | jafurah | 13350 | 2026-01-13 | 2026-01-13 | 2026-01-01 | 0 | 5% | 0 | 0 | 2578.45
4 |  |  | Dammam | arteche | 380/230kV BSP | Sea frieght | HV1393-0 | JAFURAH | 16834.5 | 2026-01-19 | 2026-01-19 | 2024-01-01 | 0 | 15% | 0 | 0 | 9469.4062
5 |  |  | jeddah | pfisterer | type termination | air freight | HV 105-131 | FARASAN | 55230.12 | 2026-01-26 | 2026-01-26 | 2025-06-01 | 0 | 5% | 0 | 0 | 10556.34
[9 empty] | 90332.75 | [6 empty] | SAR | 25044.0675
[8 empty] | SAR | 338747.8125

## Under Taking not closed (hidden)
No. | Job Order # | Shipped From | Arraival Port | Supplier | Shipment Name | Freight Type | Project Code | Project | Value (USD) | Arrival Date | Clearance Date | Clearance period (Days) | Custom Duty | Demurage cost (SAR) | Detention Charges (SAR) | Total Custom Clearance (SAR) | Remarks
1 | SIC221728 | China | Jeddah | Schreder | SF#14-J5-14-AS & SF#14-J5-14-AS (FOC-2%) | Seafreight | ES-213 | Jeddah Phase 5 | 239704.59 | 2022-09-27 | 2022-10-02 | 5 | 15% | 0 | 0 | 140619 | Hs code is revised. Undertaking still not closed. Sample faild the lab test . Customs Duty includes the lab test fees ( SAR 3,940)

## Calculation (hidden)
PBI Shipment
No. | Date | Day | Status without Telex | Remark | Demmurage
1 | 2023-05-21 | Sunday | Shipment Arrival | Shipment arrival | Free
2 | 2023-05-22 | Monday |  |  | Free
3 | 2023-05-23 | Tuesday |  |  | Free
4 | 2023-05-24 | Wednesday |  |  | 3150
5 | 2023-05-25 | Thursday |  | Document arrival at bank | 3150
6 | 2023-05-26 | Friday |  |  | 3150
7 | 2023-05-27 | Saturday |  | LC document processing | 3150
8 | 2023-05-28 | Sunday |  | LC document processing | 3150
9 | 2023-05-29 | Monday |  | LC document processing | 3150
10 | 2023-05-30 | Tuesday |  | LC document processing | 3150
11 | 2023-05-31 | Wednesday |  | Document Collection | 3500
12 | 2023-06-01 | Thursday |  | Prebayan , DO collection & Customs duty payment | 3500
Total |  |  |  |  | 29050
G60 Shipment
No. | Date | Day | Remark | Expected Shipment Status | Estimated Demmurage
1 | 2023-06-27 | Tuesday | EID | Shipment arrival | Free
2 | 2023-06-28 | Wednesday | EID |  | Free
3 | 2023-06-29 | Thursday | EID |  | Free
4 | 2023-06-30 | Friday | EID |  | 1350
5 | 2023-07-01 | Saturday | EID |  | 1350
6 | 2023-07-02 | Sunday | EID |  | 1350
7 | 2023-07-03 | Monday |  | LC document processing | 1350
8 | 2023-07-04 | Tuesday |  | LC document processing | 1350
9 | 2023-07-05 | Wednesday |  | LC document processing | 1350
10 | 2023-07-06 | Thursday |  | LC document processing | 1350
11 | 2023-07-07 | Friday | Weekend | Weekend | 1500
12 | 2023-07-08 | Saturday | Weekend | Weekend | 1500
13 | 2023-07-09 | Sunday |  | LC document processing | 1500
14 | 2023-07-10 | Monday |  | LC document processing | 1500
15 | 2023-07-11 | Tuesday |  | Document Collection | 1500
16 | 2023-07-12 | Wednesday |  | DO Collection & Bayan Printing | 1800
17 | 2023-07-13 | Thursday |  | Bayan activation | 1800
Total |  |  |  |  | 20550